## Table 1
'1P PFS Engineering Ltd 175 Riverlea Rd Hamilton, New Zealand Ph: +64 7 856 6225 Fx: +64 7 856 6226 | [14 empty] | C INSPECTION AND TEST PLAN Downer
Inspection & Test Plan Description: Downer ITP for site installation - Homai pedestrian bridge
Downer- Hamai pedestrian bridge Customer: Downer Prepared by: Bashir Heidarian Dale: 12112/2024 | [16 empty] | Location: Hamilton Customer Job Reference: 746-24-847-AC PFS Job Reference 39028 Review by: Tennille Nisbet Date: 1/01/2024 | [36 empty] | ITP Doc No: ITP--003-39028 Revision: C
Construction Category CCJ Service Category SC2 Fabrication Category FC1 Weld Category SP Tolerance Class]
Seq |  | Task/ QA Activity | [6 empty] | Specification Standard | [5 empty] | _;;, Acceptance Cfiteria | [10 empty] | Certify Doc / Ref | [12 empty] | PFS Engineering |  |  |  |  | Sign | [6 empty] | C |  |  | $\lbcontracted scope | [5 empty] | Sign | [6 empty] | C |  |  | Downer | [5 empty] | sign | [5 empty] | C |  |  | Rimaik
Engineering
1 |  | Inspection and Test Plan Reviewed ancl Approved by Customer | [6 empty] | Project Strnclure Specificalion C0702 Rev. 01 IFC structure OWG | [5 empty] | lnspeclion and Test plan shall be submitted to the Engineer lor review and approval before fabrication is commenced. | [10 empty] | IFC DWGs | [12 empty] | PM/PE |  |  |  |  | lnitial:T -. Sig I I | [6 empty] | s -- |  |  | - | [15 empty] | Downer | [5 empty] | Initial _/_ | [6 empty] | H
"';- ...
[44 empty] | - |  |  |  |  | I | ( | s | [18 empty] | Downer (. | [5 empty] | '
2 |  | Submit the required documenls lo Client for review | [6 empty] | Project Structure Specilication C0702 Rev. 01 | [5 empty] | Site installation methodology shall be submitted to the Engineer for review | [10 empty] | Erection Sequence Methodology | [12 empty] | PM/PE |  |  |  |  | lnitial:71-,...,_ | [31 empty] | lniti |  |  |  |  | ') |  | R
[44 empty] | Si:,,.. l.nJ/r:,//? | [6 empty] | -t:r" | [24 empty] | Sign: ,/o,/e.,
3 |  | lnslallalion Procwemenl - Cast in items | [6 empty] | Project Structme Specification C0702 Rev. 01 IF? | [5 empty] | Confirm Procurement and delivery of all Casi in Items: i.shear keys. ii. uplift restrainls and associated nuts 111. pa e rs. TA 06/0;;; ouple,s with denso v. Reidbar and couplers+ touch up protechve coalmg. vi. Nylon washers and rubber sleeves. vii. Temporary bearing components. | [10 empty] | IFCDWG PFS: 39028-3202-000-FABRC PFS: 39028-3201-000-FABRC Mill Certs Compliance Documentation | [12 empty] | PM/PE |  |  |  |  | Initial :7_Z... N-.,_ Sig 01/o\/( | [6 empty] | V |  |  | -
[9 empty] | fe®\Jl'i:.O Ob'ol le. >- | [16 empty] | Good Receipt on site
4 |  | Inspection upon receipt at site | [6 empty] | Project Structure Specification C0702 Rev. 01 IFC structure DWG | [5 empty] | The material receipt at site need lo be visually inspected for quantity and make sure no damage occurred during transport | [10 empty] | IFC DWG , £)- | [12 empty] | PM/PE |  |  |  |  | lnitial n,-.., 5; | [6 empty] | v r- |  |  | -- | [15 empty] | Downer | [5 empty] | lnitial:<:JX .S.ig /:. | [5 empty] | n
V
[9 empty] | ·,C,u PA'NT | [34 empty] | :::-2..1o1 / | [31 empty] | ,,,.....
5 |  | Inspection upon receipt at sile - Casi in Items. | [6 empty] | Project Structwe Specification C0702 Rev. 01 IFC structure OWG | [5 empty] | The male1ial receipt at sile need to be visually inspected for quantity, make sure no damage occurred cluling transport. All related documents have been received. | [10 empty] | IFCDWG | [12 empty] | PM/PE |  |  |  |  | lnitia-l:1-1---,.,-_-, Sig e-9:-/nl/f | [6 empty] | I | V |  | - | [15 empty] | Downer
[76 empty] | Initial: IAI Signr-c,_;:;;;- | [5 empty] | ......-
,- .,.
1"l2JC'///
[26 empty] | Steel structure Erection | [54 empty] | '
-- -
S: Submit Documents H: Hold Point 0: Dimensional Inspection RA: Review and Approve Documents W: Witness V: Visual Inspection
iSeq |  |  |  |  | Task/ QA Activity | [5 empty] | ' Specificatlo,n Stan ard | [8 empty] | ; rt - C Acceptance C |  |  |  |  | ;1" - | [7 empty] | Certify Doc f,1R8:f | [8 empty] | PFS 1Englneering | [5 empty] | Sign "! | [6 empty] | .,. - ubcontractea \.. /! scope ,..,,..,.,.. | [8 empty] | Sign | [5 empty] | : ' C .-,- |  |  |  | ·Downer |  |  |  |  | I: sign - C | [8 empty] | Remark
Preparation work- prior lo Span Lifting 6 for All Spans | [10 empty] | Sile installation methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | [5 empty] | Make sure survey has been done and center marks on the framevmrk as a reference have been provided by Downer Installation of 100x100 EA as a lifting aid on temporary structure Span unloaded from truck and placed on Dunnage on ground p1ior to rigging adjustment Attaching the lag lines lo Spans to prevent rotation during | [15 empty] | lift plan | [6 empty] | Site project Manager | [6 empty] | Initial:'1l..,..J " - H Si - | [21 empty] | Downer | [9 empty] | Initial: -- / Sign-(J,Y" b¥d1/c
Confirm alt Manufaclure documentation | [10 empty] | Project Slructure | [6 empty] | installalion Confirming that the fabrication, coaling, | [17 empty] | DZ/ol/'7 lnitialt | [26 empty] | -- --
7 has been completed for Span #2 | [10 empty] | Specification C0702 Rev. 01 Site installation methodology | [5 empty] | and factory erection {including balustrade and deck panel bolting) wo1ks have been signed off. Verify that Ille structural component is securely rigged according lo the rigging plan To lift Span #2 and Position the component precisely over | [14 empty] | QA Documentation | [8 empty] | PM/PE | [5 empty] | S,!:I,. • lnz,10/n | [6 empty] | v_ -Jt- |  |  | :E.-rCV1110 I IVS -r-,JtI\,,_ ,: | [14 empty] | Da,vi,A'L-
8 lnslallalion of Span#2 | [10 empty] | Project Structure Specification C0702 Rev. 01 IFC structure OWG | [5 empty] | the pile and lower ii slowly into its final placement on temporary girder support structure Chain block will be connected to the West end to adjust level. | [15 empty] | Lift plan | [6 empty] | Site project Manager | [6 empty] | lniti-:r,r;=., Sig | [5 empty] | H 06/ol ,I | [15 empty] | Downer | [9 empty] | Initial V R Sign:
•.vhen location is confirmed by surveyor and PFS staff, span to be secured in place to the slim soldiers. | [37 empty] | 0/ct,c,// t,s:r" | [28 empty] | 1t, c1,f'5
Ir I 9 lloy Sacs installation for Span #2 Confirm all Manufacture documentation 10 has been completed for Span #3 | [10 empty] | Site installation methodology Project Structure Specification C0702 Rev. 01 IFC structure ow | [5 empty] | To keep Macalloy bar aligned, a coupler to Ile lightened to extend the Macalloy bar and Ternpory nut v.;11be added to the rod on the Span 2 high end. The nuts will be lightened to hold the Macalloy bars in correct position. | [15 empty] | Site project at Manager | [13 empty] | Initial H ,"1/1/)-! | [21 empty] | 'i1 v
Project Structure Specification C0702 | [16 empty] | Confirming that the fabrication, coaling, and faclo1y erection (including balustrade and deck panel | [12 empty] | QA Documentation | [11 empty] | PM/PE |  |  |  |  | Initial: | [6 empty] | V | [18 empty] | Downer | [5 empty] | lniti'
Rev. 01 | [16 empty] | bolling) works have been signed off. | [29 empty] | Sign -- | [31 empty] | Sigt
Verify that the structural component is securely rigged | [36 empty] | 0-/(ol/1' ,.- | [19 empty] | s-vro /01/V.. | [12 empty] | ..... | [5 empty] | - ,-,._./.. /, -r
11 lnstalla1ion of Span#3 | [10 empty] | Site installation methodology Project Structure Specification C0702 Rev. 01 | [5 empty] | according to the lilt plan To lift Span #3 and Position the component precisely over the pile and lower it slovvty into its final placement on temporary girder support structure vvt1e11 localion is confirmed by surveyor and PFS staff, span | [15 empty] | Lift plan | [6 empty] | Site project Manager | [6 empty] | lnitia Sign: | [5 empty] | (2.£,u:,..J - --- | [9 empty] | ,,,. ---.,,,t:> 1/t..,s- | [9 empty] | Downer | [5 empty] | lniti Sign. |  | p-1 .,
Shear Keys, Hold Down Bolt and 12 | [10 empty] | IFC structure DWG Sile installation methodology Project Struclure | [5 empty] | to be secured in place to the slim soldiers. The longitudinal ancl laliludi11al Shear keys are lo be installed to secure the position of span from movement during Head stock Pouring | [12 empty] | Shear keys, Hold Down bolls and | [11 empty] | Site project |  |  |  |  | cR-tc:>11 -zc: Initial:7l..r,.J H | [17 empty] | Downer | [13 empty] | c'7/t:11/ lmt1al: -
Reidbars Installation for Span #3 | [10 empty] | Specification C0702 Rev. 01 IFC structure DWG | [5 empty] | Hold Down Bolt to be Installed Nuts on Reidbar to be snug tightened to help minimal lateral movement. | [14 empty] | Reidbars Drawing | [8 empty] | Manager | [5 empty] | Sig, - | [17 empty] | Sign(}_/.& cr1/or I�1
Confirrn all Man11faclure documentation 13 has been completed for Span #4 | [10 empty] | Project Stmctme Specification C0702 | [5 empty] | Confirming that the fabrication, coaling, and factory ereclion {including llalustrade and deck panel | [14 empty] | QA Doc11rnentation | [8 empty] | PM/PE | [5 empty] | O':/re,J t l?'c --- lnitial:'fL.t-...J V | [17 empty] | -- -- Dow
Rev. 01 Site installation | [16 empty] | bolling) works have been signed off. Verify that the structural component is securely rigged | [19 empty] | Si 01/0J/7 | [17 empty] | - £,r0'-1IJo//1-5 I/
14 Installation of Span#4 | [10 empty] | methodology Project Structure Specification C0702 Rev. 01 | [5 empty] | according lo the lift plan To lift Span #4 and Position the component precisely over the pile and lower it slov.-1y into its final placement on temporary gi1cler support structure | [15 empty] | Lift plan | [6 empty] | Site project Manager | [6 empty] | lnitiatTL,r--J Sign:-- | [7 empty] | t-UOwJ -•A",,_... 0(-10-:,.1,01/7. | [14 empty] | Downer | [8 empty] | lnitia |  | ,?/, R
IFC structure DWG | [16 empty] | ,,vhen location is co11fi11ned by surveyor and PFS staff, span to be seemed in place to the slim soldiers. | [20 empty] | o-=lfe,fl-. c:.:-i- | [31 empty] | Si';; 7/("/,/i 0
SHEQ-04-05-0034 ITP003- 39028 Rev C- Hamai Level Crossing
Seq |  | Task/ QA Activity |  |  |  | Specification Standard | [7 empty] | Acceptance c.J{ J | [8 empty] | ertify Doc I Ref | [11 empty] | PFS | [7 empty] | Sign | [5 empty] | r,. ,, ( bcontracted | [10 empty] | - Sign |  |  |  |  | C Downer | [9 empty] | sign |  |  |  |  | C Remark
|  | Shear Keys, Hold Down Boll and 15 Reidbars lnstaUalion for Span #4 | [5 empty] | Site installalion methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG | [5 empty] | The longitudinal and latitudinal Shear keys are to be installed lo secure the position of span rrorn movemenl during Head stock Pouring Hold Down Solt to be lnslalled Nuls on Reidhar to be snug tightened to help minimal lateral movement. | [11 empty] | C Shear keys, Hold Down bolls and Reidbars Drawing | [11 empty] | 1Eng'ineering Site project Manager | [5 empty] | Initial: Si" |  |  | \.a scope | [10 empty] | " ,, | [6 empty] | Downer | [9 empty] | ,v-r- Initial:_ Sign:¥ o'l/41/- | [6 empty] | l.,?R
16 Confirm all Manufaclure documentation has been completed for Span #5 | [8 empty] | Project Structure Specificalion C0702 |  |  |  |  | Confiuning that the fab1ication, coaling, and factory erection (including balustrade and deck panel | [10 empty] | QA Documentation | [9 empty] | PMIPE | [7 empty] | lnitia ,-..J V | [10 empty] | [Dc,...,'IJ'(l
[10 empty] | Rev. 01 Sile installation |  |  | boltino) works have been sioned off. Verify that the structural component is securely riaged | [11 empty] | Sign: ICU/o// :,,r- sere::5"""/ol/ls-- I,
17 lnstaUalion of Span#S Shear Keys, Hold Down Boll and 18 Reidbars lnslallation for Span #5
[8 empty] | methodology Project Structure Specification C0702 Rev. 01 IFC structure DWG Sile inslaltalion methoclology Project Stn1cture Specification C0702 | [5 empty] | according lo lhe lift plan To lift Span #5 and Position the component precisely over the pile and lower it slowly into its final placement on temporary girder support structure \•,·hen location is confirmed by surveyor and PFS staff, spaIt to be secured in place lo the slim soldiers. The longitudinal and lalitudinal Shear keys are lo be installecl lo secure the position of span from movement during Head stock Pourin!) Hold Down Bolt lo be Installed | [11 empty] | Lift plan Shear keys, Hold Down bolts and Reidbars Drawing | [11 empty] | Site project Manager Site project Manager | [5 empty] | lnitial:n,r--J . .-. :::i 16=/-/ol/ lnitia | [9 empty] | o=t-rcf II | [6 empty] | ---- D | [7 empty] | Downer Downer | [5 empty] | lnili. <7'1/ ,jt ) ,, Initial: 4 R
| 19 Confi,rn all Manufacture documentation | [7 empty] | Rev. 01 IFC structure DWG Project Structure Specification C0702 |  |  |  |  | Nuls on Reidbar lo be snug lightened to help minimal lateral movement. Confirming that the fabrication, coaling, ancl factory erection (including baluslrade and deck panel | [11 empty] | QA Documentation | [8 empty] | PM/PE | [8 empty] | Sig 03/011 '"'" Initial:--,r:i..J V | [11 empty] | 0 Volti., FlL | [12 empty] | Sign:f /R'C'"' o /4,f \ /b,.14 t
| has been completed for Span #6 20 lnslallalion of Span#6 | [7 empty] | Rev. 01 Site installation methodology Project Slruclure Specificalion C0702 Rev. 01 IFC structure DWG |  |  |  |  | bolling) works have been signed off. Verify that the structural component is securely rigged according to the lift plan To lift Span #6 and Position the component precisely over the pile and lower ii slovAy into its final placement on lemporary girder support structure wt1en location is confirmed by surveyor and PFS staff, span | [11 empty] | Lift plan | [8 empty] | Site project Manager | [8 empty] | Si ln'iti al ,..-.J Sig . - | [5 empty] | cR-/o 'I:::> H | [9 empty] | ) IL3- I.i | [8 empty] | Downer | [5 empty] | lniU :I Sign: |  |  |  | tfY7. I,
| Shear Keys, Hold Do. ,, Boll and 21 Reidbars Installation for Span #6 | [6 empty] | Sile installation methodology Project Structure Specification C0702 Rev. 01 | [5 empty] | lo be secured in place to the slim soldiers. The longitudinal and latitudinal Shear keys are lo be installed to secure lhe position of span from movement during Head stock Pouring Hold Down Bolt to be Installed Tempora,y Bearing installation under lower encl | [11 empty] | Shear keys, Hole!Down bolts and Reidbars Drawing | [11 empty] | Site project Manager | [5 empty] | o:::1-tbl I z r lniti H Sign: | [9 empty] | Downer | [20 empty] | 07/o,/, f '- i, lni: Sig .
[10 empty] | IFC structure DWG |  |  |  | Nuls on Reidbar lo be snug lightened to help minimal lateral movement. | [11 empty] | Of,/Olh< --- | [27 empty] | C) 43/o(/r4
i-- -22 |  | Dimensional survey By Downer
[8 empty] | Site inslatlalion methodology IFC Drawings | [5 empty] | Conduct a thorough dimensinal survay inspection to confirm Iha! the component is correctly positioned and secured basecl on IFC Drawing. Measured dimensions shall be within stated tolerances unless noted othe1Wse. Project specification clause C0702.1.3 Functional Tolerances shall be class 2 as per ASINZS 5131 Table F2.1 to F2.10 Record the lifting operation in the project log, including any devialions or required adjustments lo he made. | [11 empty] | Marked up ancl Signed lFC OWGs | [11 empty] | Site project Manager | [5 empty] | lnitialfj2/J-, H Sign:( .;z.e'/0- | [9 empty] | I Downer | [20 empty] | Initial: H Sign:
[19 empty] | ..... _( J 1: | [11 empty] | ' , Y . .
Seq . |  |  |  | TaslU QA Activity |  |  |  | Specification Standard Site installation | [53 empty] | Sign C - - | [8 empty] | ,Downer | [5 empty] | sign |  |  |  |  | C Remar":-: ' ' .
[16 empty] | Acceptaric.e Cr1t1: | [5 empty] | ' ,Certify Doc l Ref, | [15 empty] | PFS Engineering , | [7 empty] | Initial: |  |  |  | l uticontracted .=4 scope ...
|  |  | 23 Remove Reid bar tension. 24 Reid bar touch up painllng (if required) | [6 empty] | methodology IFC DraVIJings |  |  |  |  | Lassen Reidbars to match IFC drawing detail at all peirs before any headstock pours. Any coatings damage to Reidbars touched llp as per paint spedficatiofl, Coatings to comply VIJith nole 1.2 on drav-ling | [12 empty] | IFC DWGs Project Paint Specification | [10 empty] | Site project Manager Site project | [6 empty] | s·a:7d"- H Initial: V | [8 empty] | II> |  |  |  |  | Downer Downer | [16 empty] | lniti Sign;.., ?: r Initial: | [6 empty] | ,c- V |  |  | ,. .
|  |  | G I• ro c. iJ-u ,. Coc-c.-h',,\.<> ' v | [17 empty] | Pouring Headstock and Grouting by Downer I I Post Head stock Pouring activities .
25 Hold Down Bolts li Ihtening | [8 empty] | Site installation methodology IFC Drawings Standard operation procedure for steel structure bolt tightening SHEO-01-02-0038 Site installation methodology | [6 empty] | Remove additional nuts, tape (masking and double sided) used for alignment. Apply rubber sleeves to the exposed threads. Reinstall oversized washers, apply instulating washers and lighten nuts down to achive a 1rnmgap between washer and nut, lock nut lo be inslalled as per detail C & Section 5 on ST-3202, Detail O on ST-3200. lo Undo the coupler, remove lemporary alignment nut, install | [13 empty] | Bolt Tightening report | [7 empty] | Site project Manager | [7 empty] | lnitial:7'-. ,V H - 'IQ'() //05> | [8 empty] | ';111 _, - -
26 Macalloy Bolts lightening | [8 empty] | IFC Drawings Standard operation proceclure for steel structure boll tightening | [6 empty] | the rubber sleeves to the exposed rod, install the washers, Boll Tightening report nuts and snug lighten the nuts (as there are compressible components in contanc area) | [21 empty] | Site project Manager | [7 empty] | lnitialr;;:;; ,1_.,. , |  |  |  | - H --<- | [6 empty] | - ',: -·,.""'*. | [22 empty] | Ill\ yt , | [8 empty] | '',A,1/2
A -"'
|  |  | 27 Temporary restraints removal | [5 empty] | SHEO-01-02-0038 Site installalion methodology IFC DravJings | [6 empty] | All temporary restraints to the temporary shoring to be removed All positioning Jigs and scre'NS applied to PTFE on Shear Keys to be removed | [11 empty] | l'ilnllz lni:al/11!/ Team Leader V Sign: - | [28 empty] | "',v::).., | [10 empty] | l 4bufm \
|  |  |  | Sile installation | [10 empty] | The Temporary Bearing to be removed and Granor Bearing | [12 empty] | ...- | [34 empty] | ,.<..!_i':IV ,,r,-J t:)10 l "" | [22 empty] | ;;,r,
(_.28.,,)lnstallalion of Graner Bearing
... I 29
[9 empty] | IFC DravJings Standard procedure for steel structure bolt tightening SHEO-01-02-0038 Site installation methodology IFC Drawings | [18 empty] | IFC OWGs | [20 empty] | e - If' D | [14 empty] | .;; ' | [6 empty] | Aue: |  |  |  |  | _.,., , |  |  |  |  | ·--- ,. | w,,. _,,_ | [5 empty] | "IJIJI =-,...!
[16 empty] | the Bolts need to be snug tightened to the girdeIs (top) and screws neecl lo be snug lightened into the base plate. The keeper plates· bolls (M20) for uplift restraint to be lightened (full Tensioned). Carefully position the Decking and wall panels in the conjunction area according to the approved dra \llngs. | [20 empty] | Site project Manager Team Leader
|  |  |  | Installation of remaining Decking panels and wall panels | [66 empty] | _.-..--
30 Snug tightening of Decking panels and wait panels | [10 empty] | Standard operation procedure for steel structure bolt tightening SHE0-01-02-0038 |  |  |  |  | Fasteners of Decking and wall panels to be inspected for snug tight condition and marked v-lilh coloured painl pen lo Boll Tightening report confirm fixing condtion has been checked and verified. | [22 empty] | Site project Manager | [6 empty] | 'S"ign':"/J"1'";/ | [8 empty] | . Q1· | [9 empty] | ,. :, "
f
|  |  | 31 Installation of remaining handrails between the spans | [6 empty] | Site instaijalion methodology IFC DrayJings |  |  |  |  | andrails in the conjunction area he approved dra\'Jings. | [12 empty] | IFC DWGs | [8 empty] | Initial Team Leader D Sign:
...,iCS\E..•. P ,PA1,-.l'\'TO 8E. IT ,£0 =cr-J s o.....s oFsrEe.c.... '{3 s-e .pe..,,1c:Yc:... \\ S: Submit Docu ts H: Hold Point D: Dirnensional lnspection RA: Review and Approve Documents W: Witness V: Visual Inspection \ | [68 empty] | oie.,,....,ct:Pu. •
I, ,seq |  |  | Task/ QA Activity |  |  |  | 1 'Sp cificatlon Standard"' | [8 empty] | 'A.Cceptance Cwr .J..... | [5 empty] | Certify Doc f Ref | [13 empty] | PFS Engln8erlng | [8 empty] | Sign |  |  |  |  | ''! )b.contra.cted , "li. scope | [10 empty] | Slgfi |  |  |  |  | C Downer ! | [11 empty] | Sign |  |  | C ' Remark
[7 empty] | - - Fasteners of handrails to be inspected for snug light | [18 empty] | fl.I-I | [23 empty] | -/.4Jc .f1A+·d | [16 empty] | I 'ff |  |  |  | l,¢d :to· n·11iil1-:, '
32 Snug lightening of Conduti Brackets | [8 empty] | Standard operalion procedure for steel structure bolt lightening SHEO-01-02-0038 | [5 empty] | conrlition viith addition of Loctile or Locknut to prevent loosening and marked with coloured paint pen to confirm fixing condtion has been checked and verified. Note: The connections for the EA's spanning the pier movement joints shall be hand tightened, Ref CAN 063. | [11 empty] | Bolt Tightening report | [9 empty] | Site project Manager | [7 empty] | Initial: H Sig,.. :,..Lf,/cf/ ' | [8 empty] | - t-J«n | [6 empty] | I-\- | [9 empty] | y,e.J ·tQl'\${0 | [11 empty] | Je• •
33 Installation of Expansion plates | [7 empty] | Site installation methodology IFC Drav..ings | [5 empty] | The expansion plates to be installed between Span 1 and 2 and between span 6 and 7 | [12 empty] | IFC DWGs | [7 empty] | Team Leader '"""',"! D : Sign: f"
34 Inspection to identify any damage lo painted surfaceses requiring touchup | [8 empty] | Inspect paint for any required repair and touch up of paint woiks (bolled connections and any damage paint to steelwork). Repair method proposed shalt be approved by the independent coaling inspector. Areas repaired shall be reinspected by the coaling applicator and independent inspector. | [17 empty] | Note 1.2, Drawing ST-3202 | [10 empty] | Site project Manager | [6 empty] | Initial:./<)}- H Sign - | [14 empty] | Downer | [15 empty] | Initial: H Sign:
35 Sile Installation and Sign-off. | [7 empty] | Erection seque11ce methodology (EMS) IFC Draviings | [6 empty] | Visual and Dimensional inspections completed by PFS Project Manager lo confirm manufactured items have been completely installed. Inspection of erected steelwork in accordance viilh AS/NZS 5131 Section 13.11 as per specification C0702.1.10. Inspections shall cover all relevant items listed in clause 13.11.1. Inspections shall be documented in inspection reports as per clause 13.11.3 of AS/NZS5131, and included in the QA documentation. Inspections shall be conducted by competent personnel. Evidence of expe1ience or qualifications for nominated individual(s) shall be provided for review. An example of qualification of competent personnel is a relevant trade qualification and over 10 years experience in structural steel erection. FoUoving inspection on site, should any modification or repairs be required a w1itten procedure shall be submitted to the Engineer prior to any work proceeding as per C0702.3. | [11 empty] | IFC DWGs | [7 empty] | Site project Manager | [9 empty] | ·' ' l lnitial:RH '• H Sign: .. ' - | [13 empty] | " !' .• ' | [7 empty] | Downer | [8 empty] | Initial: H Sign:
Quality Review
36 Compile, review and submit documentation | [7 empty] | Project Structure Specification C07 Rev. 01 IFC structuIe DWG | [6 empty] | Documentation and reports to suppoI1installation of steel structure items compiled into PFS Manufactures Data Report | [11 empty] | PFS Manufactures Data Report | [11 empty] | Site project Manager | [5 empty] | Initial: /(.jJ- s s | [8 empty] | .I< | [11 empty] | Downer | [9 empty] | Initial: RA Sign:
PFS Revision Record: 39028-ITP-003-39028 RevC
Approved lly {Engineer/Clien!I | [11 empty] | Name: | [5 empty] | Date: | [12 empty] | Sign:
Issued for Construction | [10 empty] | Name: q_r"'\ t,lvSe. | [12 empty] | Dale 0/ /Of /2.s Sign: /, ).,#,L,#0
Comments/Notes:
f
--
-
'"-:;.,. ,- - -, co u
ot
-"'"
.. @7
J
-
H
-
Sign:_
Sign:
-
-..
--
D
'
,
'
. I;
I - JO
◄ ':'J ,, ----, • 'J"""' I ; •;J I -·,- I , @·r c.oc,.•n ,
..,
,...,..Aiic.a,h>v
'
ST-3202.
,
,
Manager
Sign:
Sign:
i:-Aff. ,',Qi-io"'/air- l'l'\ c, S"
Sl\qll QC, ei_rr'o·---- 'T ,._,.._ ..,, r -· 14 Sf't:,,c;.,f1 C>"l Yr
,- I
''""'
I
H
w
" .
I
.
I