## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DN1212-ITP-016 Fences and gates | itp |  |  |  |  | DN1212-ITP-016 Fences and gates Rev2
section | 1 - PRELIMINARY AND GENERAL
checkpoint | 1.1 - IFC Drawings and Specification
label | Standard, Drawing or Specification Reference - ACC
label | Construction Activity Description, Test Type and Acceptance Criteria - A minimum of two weeks prior to construction: document review. DWG’s are for construction or as per instruction
label | ○ Works done in accordance with Project specification
label | Test Frequency - Once
label | QA Record - N/A
label | DNZ Engineer - R
label | Designer Rep - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Method Statement & JSEA Development
label | Standard, Drawing or Specification Reference - The Downer Standards (TDS)
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction: document review.
label | Test Frequency - Once
label | QA Record - Method Statement & JSEA Completed & signed by relevant authority
label | DNZ Engineer - H
label | Engineer's Rep - R
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Permit to Dig
label | Standard, Drawing or Specification Reference - DN-ZH-ST043 Ground Disturbance
label | Construction Activity Description, Test Type and Acceptance Criteria - Prior to construction. Permit in work package
label | Test Frequency - Permit issued each week
textbox | QA Record - Permit number
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Survey Model
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Model Review.
label | Test Frequency - Once
label | QA Record - Visual Inspection & measurement Survey Check set out as per design
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Corridor Access Requests (CAR)
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Corridor Access Requests (CARs) is required before any work is carried out on public roads.
label | Test Frequency - Once
label | QA Record - Approved CAR
label | DNZ Engineer - H
holdpoint | AUTHORITY HOLDPOINT
section | 2 - MATERIAL APPROVALS
checkpoint | 2.1 - Fence panels
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1017 Note: 1
label | Construction Activity Description, Test Type and Acceptance Criteria - Fences to be hot dip galvanized.
label | Test Frequency - Preconstruction - once
label | QA Record - Delivery Dockets, Ineight Approvals
label | DNZ Engineer - I
label | Designer Rep - R
checkpoint | 2.2 - Fence posts
label | Standard, Drawing or Specification Reference - 3235599-SP03-CA-1017 Note: 3
label | Construction Activity Description, Test Type and Acceptance Criteria - Fence post must be 65mm SHS hot dip R3 Galvanised square hollow section or similar approved.
label | Test Frequency - Preconstruction - once
label | QA Record - Delivery Dockets, Ineight Approvals
label | DNZ Engineer - R
label | Designer Rep - R
section | 3 - CONSTRUCTION ACTIVITIES
checkpoint | 3.1 - Pre-installation
label | Standard, Drawing or Specification Reference - DN1212: CKT - 000060
label | Construction Activity Description, Test Type and Acceptance Criteria - complete permanent fencing checksheets
label | Test Frequency - During construction - once
label | QA Record - Checksheets & photos
label | DNZ Engineer - I
section | 4 - FINAL RECORDS
checkpoint | 4.1 - Construction Record Compilation
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Compile construction records for final submission ensuring defects (NCRs) / Snags / missing records are captured or closed out, all tests have been received and passed, and changes / omissions have been noted.
label | Test Frequency - Once
label | QA Record - QA Records
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.2 - Survey Records
label | Standard, Drawing or Specification Reference - N/A
label | Construction Activity Description, Test Type and Acceptance Criteria - Ensure all items have been surveyed.
label | Test Frequency - Once
label | QA Record - As-Built
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.3 - Redline Drawings
label | Standard, Drawing or Specification Reference - IFC Drawings
label | Construction Activity Description, Test Type and Acceptance Criteria - Create a set of Redline Drawings for Asbuilt creation noting all changes and departures in red pen.
label | Test Frequency - Once
label | QA Record - IFC Mark-Up
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Non-conformances
label | Standard, Drawing or Specification Reference - DN1212-DOW-PLA-PM-0005 QMP
label | Construction Activity Description, Test Type and Acceptance Criteria - Non-conformances reports to be raised when specification not met. All non-conformances within the area under review need to be listed on the NCR report.
textbox | NCR Reference
label | Test Frequency - When Required
label | QA Record - NCR Forms on InEight
label | DNZ Engineer - H
label | Designer Rep - R
holdpoint | AUTHORITY HOLDPOINT
section | ITP APPROVAL PROCESS
checkpoint-no-status | ITP APPROVAL PROCESS
label | Prepared By: Site Engineer - Moses Kaufanga
label | Reviewed By: Quality Mgr./Eng. - Nas Matar
label | Reviewed By: Project Manager - Dan Trotman
label | Reviewed By: Design Engineer - Daniel Cvitanich
label | Reviewed By: AT Project Manager - Werner Nel
label | Reviewed By: AT Engineer to Contract - Mike Robertson
date | Date:
section | FINAL ITP CLOSE-OUT
checkpoint | FINAL ITP CLOSE-OUT
textbox | Downer Project/Site Engineer:
textbox | QA Mgr./Engineer:
textbox | Designers Rep(Assistant):
date | Date:
checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
textbox | Contractor's Rep Name:
textbox | Engineer's Rep. Name:
date | Date:
signoff | Add Signature