## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 6e3c86e6-7574-42d0-83ea-d48aa28576c2 |  | checklist | PAC AC |  |  |  |  | Yes | Commissioning - PAC AC | 21a355c7-c722-4921-8175-652e8bb5738d
checkpoint-status | 5f270861-1321-4d97-9a5c-0953979bba86 |  | checkpoint | System is energised
checkpoint-status | 2985766e-15a2-4b04-b608-c2fdb83bcf71 |  | checkpoint | System is labled at MSSB/SB
checkpoint-status | 33b70e9f-d875-4d66-b153-d66ef9942576 |  | checkpoint | Power isolation at equipment installed (isolator lead/PB)
checkpoint-status | 1c111267-6780-4a89-a26b-856c2f198187 |  | checkpoint | All Control Accessories are fit off and operational IF APPLICABLE
checkpoint-status | 34cf8569-ea1a-47a6-a5e6-18c48350ebb3 |  | checkpoint | Temperature Coils can be operated.
checkpoint-status | 463ad5f7-fb2d-4a61-9004-90cda7fcfb15 |  | checkpoint | System Temps are verified against specifications
checkpoint-status | 95875a38-b9af-4bc9-b377-d4ce69ae1fb5 |  | checkpoint | Access is installed by builder IF APPLICABLE
checkpoint-status | 8277ec1e-d8b6-4d92-9331-256f3d433535 |  | checkpoint | Access is suffient to service electrical
checkpoint-status | 810de158-6610-4a0c-9016-1fa74527756d |  | checkpoint | model and seriel number are clearly visable (TAKE PHOTO)
checkpoint-status | 1e1b357b-5e05-43e5-aeab-c565ba4aaa21 |  | checkpoint | All Ductwork on System is complete
checkpoint-status | 4bcc62f3-2cd5-4b22-a60d-106c98637a21 |  | checkpoint | Supply Air Ducts completed and installaed correctly
checkpoint-status | 8f5786c4-e74e-4ee7-a865-6e879259e5bc |  | checkpoint | Return Air Ducts completed and installed correctly
checkpoint-status | d73d878d-d145-4385-9717-4d16e9185cf9 |  | checkpoint | Fresh Air Duct completed and installed correctly
checkpoint-status | 6abe546f-a869-47bc-b4f6-47eab9b32268 |  | checkpoint | Fresh Air Grilles installed correctly
checkpoint-status | cc36f181-149f-4528-91dc-957b7fad672d |  | checkpoint | All Dampers are installed as per drawings
checkpoint-status | 4d455b2e-b20e-4e57-89e1-7137ee1d745c |  | checkpoint | All Dampers are verified as operational and in correct position
checkpoint-status | 237db053-cbec-4b2e-9049-7862dfaff8fd |  | checkpoint | All Grilles are installed as per drawings
checkpoint-status | 9e5f076b-010a-4eed-a486-a4f0dafdf0bc |  | checkpoint | All Door Relief Grille are installed as per drawings IF APPLICABLE
checkpoint-status | 8c50847b-76af-4ed9-a2ba-4c7c0b90b97c |  | checkpoint | Other Comments or Notes
checklist-flat | 2a79a2fb-a335-449d-9443-8372308a832c |  | checklist | MSSB |  |  |  |  | Yes | Commissioning - MSSB | 2b14bf9e-daea-46e0-9849-9985f14ee75e
checkpoint-status | 9f39953e-e74c-40d3-bad3-0d4ef68f8fff |  | checkpoint | Board is energised
checkpoint-status | 802231c0-2fd0-4b36-afc9-295589203961 |  | checkpoint | Systems that are energised (note systems)
checklist-flat | 8e1e1081-46d7-4dbb-8eed-3daf37fbf731 |  | checklist | SPLIT AC |  |  |  |  | Yes | Commissioning - SPLIT AC | 42d2cceb-d616-4b3f-b08c-5ed0faf4e665
checkpoint-status | d4bc9b57-2a91-4c11-aec3-e055d191cdae |  | checkpoint | System is energised
checkpoint-status | 38f8eac6-a687-4532-8472-a69ab16bce4a |  | checkpoint | System is labled at SB
checkpoint-status | ba953922-c9d4-477d-91ac-4fac59245947 |  | checkpoint | System has been tested with remote and IR confirmed operational
checkpoint-status | 069d07aa-8e50-48db-9e83-60c1e481617c |  | checkpoint | Drain termination point accessable and complete
checkpoint-status | 27a38bc0-1a13-4ced-9a63-a23bd6f51ebd |  | checkpoint | Drain has been terminated correctly termination point (TAKE PHOTO)
checkpoint-status | 1e0f1800-9686-4b0e-af8b-1a0f78c73fdc |  | checkpoint | Drain is installed correctly at indoor unit
checkpoint-status | 7b266962-5ef3-4feb-8957-a48b6912ac29 |  | checkpoint | Drain passed flow test
checkpoint-status | 77193838-30ea-4624-91a9-23d4269078cc |  | checkpoint | Model and Serial number are clearly visable (TAKE PHOTO)
checkpoint-status | 95ac69e0-9e84-430e-8bd3-3a32396f91b3 |  | checkpoint | Head Unit is mounted correctly and level on wall. (TAKE PHOTO)
checkpoint-status | ee8522a3-1011-4a44-b0a4-9fa6c08abc71 |  | checkpoint | No visible damage or marks on unit.
checkpoint-status | bb6c1306-7ada-4fc3-9d23-8df79c81a31d |  | checkpoint | Vane is operating and opening correctly
checkpoint-status | 1f61118f-79ff-4596-9b11-51133faff5f4 |  | checkpoint | Fan is operating and free of vibration
checkpoint-status | d6bf5d84-85a7-4d53-bec2-396e3c2e185a |  | checkpoint | Fan has been checked for correct operation L/M/H
checkpoint-status | 0b765cee-6ed9-45c6-9984-51703ccb70d2 |  | checkpoint | Temperatures have been checked in heating and cooling
checkpoint-status | 44e1cfe8-77c2-4acb-bf7c-cb5f54a73ec1 |  | checkpoint | Other Comments or Notes
checklist-flat | ec649c99-e00f-4e76-8c14-488274f88d6e |  | checklist | FAN |  |  |  |  | Yes | Commissioning - FAN | 7ebf1c24-26c6-441a-8ee1-2ca1626619c4
checkpoint-status | 3150fddf-ce13-449b-9cf9-fcadf9ec6dd2 |  | checkpoint | Builders works are completed
checkpoint-status | 3a2074f2-d044-4f65-b954-1baae0669b2b |  | checkpoint | System is energised
checkpoint-status | d4724caa-9067-40aa-b1d2-ec26feaa905c |  | checkpoint | System is labled at MSSB/SB
checkpoint-status | 8ede2acb-91f3-4cb8-86b6-095759694b63 |  | checkpoint | Power isolation at equipment installed (isolator lead/PB)
checkpoint-status | f3f22351-e7ca-46e1-82c8-6756a8e7750b |  | checkpoint | All Control Accessories are fit off and operational IF APPLICABLE
checkpoint-status | 6942e1fe-df73-4dc6-b8ed-adc6b678b539 |  | checkpoint | Access is installed by builder IF APPLICABLE
checkpoint-status | c5dba549-8e1e-4185-b184-fa03a38d48d8 |  | checkpoint | Access is suffient to service electrical
checkpoint-status | 0d224325-e179-49ea-8bd5-c40559c16dec |  | checkpoint | model and seriel number are clearly visable (TAKE PHOTO)
checkpoint-status | 167fc2cf-3c0f-4b50-a59e-e403075f8bf6 |  | checkpoint | All Ductwork on System is complete
checkpoint-status | 0b20b433-f722-46a8-bbea-1b4b6b440f48 |  | checkpoint | All Dampers are installed as per drawings
checkpoint-status | dbf0e00d-c207-4478-8791-a5c862a2d8d5 |  | checkpoint | All Grilles are installed as per drawings
checkpoint-status | 68128d28-5a07-4192-b286-329876cfdcc1 |  | checkpoint | All Door Relief Grille are installed as per drawings IF APPLICABLE
checkpoint-status | 304674c3-4fd6-4a01-b119-8bb1bd70fe2d |  | checkpoint | All Filters are installed IF APPLICABLE
checkpoint-status | ea004369-3ff2-4f6b-9107-303f3e80d026 |  | checkpoint | Other Comments or Notes
checklist-flat | 96cb5747-7068-4b97-90a5-a78a1916da45 |  | checklist | BULKHEAD AC |  |  |  |  | Yes | Commissioning - BULKHEAD AC | 8721d726-d94e-4c87-ac93-8591425021d3
checkpoint-status | 7b671b37-169c-4745-b06f-78fe5f744c69 |  | checkpoint | System is energised
checkpoint-status | 52dff93a-9f4a-44c0-a417-58027c0384c8 |  | checkpoint | System is labled at SB
checkpoint-status | 84ba2028-bed3-4651-9742-24d1bdb711f8 |  | checkpoint | Power isolation at equipment installed (isolator lead/PB)
checkpoint-status | 1381b039-e9a0-4a0a-944a-716dd03da52a |  | checkpoint | Wall Controller is installed
checkpoint-status | 34727d8d-bb7b-43a7-8d06-6c43038efb8a |  | checkpoint | Wall Controller is mounted level
checkpoint-status | 5fafb337-9df6-4ffe-ac44-f461553df776 |  | checkpoint | Wall Controller initial setup is complete (ie time and date)
checkpoint-status | a2c7a382-f4aa-4e89-b5c1-403ae5108e61 |  | checkpoint | Drain termination point accessable and complete
checkpoint-status | 72012769-e6ac-4147-8e39-eb4ad70ec535 |  | checkpoint | Drain has been terminated correctly at termination point (TAKE PHOTO)
checkpoint-status | dcdcd6c0-49d2-4f12-9e4c-8082965851a9 |  | checkpoint | Access/Access Panel is installed at Indoor Unit
checkpoint-status | ebd280b8-dedf-4d9d-a50a-8c50c5372e91 |  | checkpoint | Access is suffient to service electrical, test drains and access filters
checkpoint-status | f6b233e5-3f81-4154-b82a-6f333e7a6989 |  | checkpoint | Return Air Filters are installed
checkpoint-status | e83032f7-7a8f-4104-acb3-89dab5f3b547 |  | checkpoint | Drain is installed correctly at indoor unit
checkpoint-status | e3abc9d3-2a39-4dd0-ad0a-e50bf55711e1 |  | checkpoint | Drain passed flow test
checkpoint-status | 2a4e8f69-3c73-4d05-bef3-73331bb23169 |  | checkpoint | Model and Serial numbers are clearly visable (TAKE PHOTO)
checkpoint-status | 9d8a4948-e1e6-4f11-84d0-375dde7f4ba3 |  | checkpoint | Unit installed and mounted correctly
checkpoint-status | 6139d4a2-e803-4225-8999-0554cfc6a98a |  | checkpoint | Pipes and Flare Connections are fully insulated
checkpoint-status | fc68992c-d1c3-4c32-8e9f-efcac8c72419 |  | checkpoint | Fan operating and free of vibration
checkpoint-status | 61cb5733-208e-426d-861b-ea0deb405953 |  | checkpoint | Fan is free of obstruction
checkpoint-status | b0138e9e-a9db-4dc4-8f7f-075b621f720b |  | checkpoint | Grilles installed correctly (level and without obstruction)
checkpoint-status | 67a7d496-1cd1-4af5-a088-a8ef0a0d3583 |  | checkpoint | Strings removed from damper IF APPLICABLE
checkpoint-status | d1f19400-344b-4f65-aa4a-3df54c3a1f15 |  | checkpoint | Airflow is measured to meet design (record airflow)
checkpoint-status | dc539736-079d-4d3d-8f7b-16ba1f0f5113 |  | checkpoint | Record Fan Speed and Static Pressure Setting at time of Airflow measurement
checkpoint-status | 6bdf1a32-9f01-40b2-9c80-ae56acf64f4a |  | checkpoint | Record Temperature Difference in heating (K)
checkpoint-status | e9d5033f-ecef-4cfb-9506-eb14bbb7468b |  | checkpoint | Other Comments or Notes
checklist-flat | d09867f1-9adc-4edf-bcb2-db449411960e |  | checklist | Apartments - Rough In Checklist |  |  |  |  | Yes | Apartments - Rough In Checklist | 893e2e6a-90cc-4b77-81ce-9e8c67b8fc48
checkpoint-status | 61ad7858-fda0-4f8c-a6a0-05afe63dcd14 |  | checkpoint | Toilet / Laundry PVC, flex duct, Plenum, NRD & In-line Fan installed and correctly fixed
checkpoint-status | b3ef2869-3612-4cb6-9ed1-f75c966da6a9 |  | checkpoint | Make Air installed c/w with Plenum, NRD and acoustic flex
checkpoint-status | 0a8b6c1e-8dbd-479e-a77e-3874ae66b273 |  | checkpoint | Ducted AC unit in Living, levelled with isolation mounts (S/A ducted plenum installed & cushion boxes, if required)
checkpoint-status | b0d9b32e-2290-4bb5-bca1-9ba9e78e3d7b |  | checkpoint | IF APPLICABLE -Ducted AC unit in Bed 1, levelled with isolation mounts
checkpoint-status | 1798c748-a005-4e44-b6c9-210c1737cff9 |  | checkpoint | IF APPLICABLE -Ducted AC unit in Bed 2, levelled with isolation mounts
checkpoint-status | a1c4eb09-8a44-405a-9060-36ecc8f01a43 |  | checkpoint | IF APPLICABLE -Ducted AC unit in Bed 3, levelled with isolation mounts
checkpoint-status | 93e306c2-26c6-425e-88a3-45c2eb35e8a4 |  | checkpoint | IF APPLICABLE -Ducted AC unit in Bed 4 or Study, levelled with isolation mounts
checkpoint-status | 0204b66a-5d5d-4521-a32b-ba30b8bfa450 |  | checkpoint | Sireal and model numbers of indoor A/C units
checkpoint-status | fe60f293-c415-48d5-addc-64a2083c4e45 |  | checkpoint | All Ducted AC unit that filters installed
checkpoint-status | ff5402e5-72c4-4115-ae1d-66dc46465c8c |  | checkpoint | Access panels marked on floor
checkpoint-status | 494f94bb-83f9-4692-b390-43dcff955fd3 |  | checkpoint | Refrigeration pipes roughed in and connected ref nets, pipe run to balcony or pipe riser
checkpoint-status | 3d8260bf-72fc-4ae7-8f0a-1cbb74d929e1 |  | checkpoint | Drain pipes roughed in TD at nominated sink
checkpoint-status | 5fa5db20-9989-4c95-8dae-692fd19d8419 |  | checkpoint | Electrical cables roughed in and correctly clipped including thermostat roughed in and located in wall
checkpoint-status | e5953835-1d46-4c59-ac00-ecc237e6507e |  | checkpoint | Wall penetration Fire caulking completed and fire penetration labelled / documented.
checkpoint-status | c5ab15fa-aa2e-47d6-8b81-169e6edc65c8 |  | checkpoint | Builders works complete
checkpoint-status | b1cd4901-ed97-4068-a764-5f65b0b5b7d3 |  | checkpoint | Pressure testing of Refrigeration pipework complete
checklist-flat | 58529d50-94fa-41a7-850d-42700c301487 |  | checklist | Apartments Fit Off Checklist |  |  |  |  | Yes | Apartments Fit Off Checklist | a673ee6b-0683-4c3d-9f00-4e9bb391a075
checkpoint-status | 5aab9508-cb98-4895-804d-9a57cffd3b35 |  | checkpoint | S/A & R/A Grilles fit off
checkpoint-status | 177a903b-fc47-4ffd-84af-b326f0885af5 |  | checkpoint | E/A Grilles fit off
checkpoint-status | 66373063-cd1b-440b-af2e-354cefcee577 |  | checkpoint | Fans fit off, powered and set medium speed
checkpoint-status | b6b55911-2067-44aa-9f31-5aae90bce300 |  | checkpoint | Access panels installed and equipment accessible
checkpoint-status | 1a09d437-5a0f-4335-a7ac-e824a3fe465a |  | checkpoint | Rangehood installed and flex connected
checkpoint-status | 349c33b6-b26d-4a43-ab82-cf0fe441f3de |  | checkpoint | Indoor A/C units power fit off and addressed
checkpoint-status | 083bba95-81ac-4487-bb27-921f8473aed8 |  | checkpoint | All drains fit off and tested
checkpoint-status | 1970ccb7-3710-47aa-b8fc-82d72bd46a48 |  | checkpoint | Condenser unit fit off, pipes and wires sealed and capped where required
checkpoint-status | 7e108463-cae3-47ef-8a2d-c12eeebd5755 |  | checkpoint | Therstate installed and tested
checklist-flat | 2cc4f4c9-26f5-4fed-ac05-0c7138532b91 |  | checklist | OUTDOOR |  |  |  |  | Yes | Commissioning - OUTDOOR | b2e38e06-0264-4efe-b4ed-b9bc204d443e
checkpoint-status | 94d3583d-40b3-4822-9824-cce2851e0aa4 |  | checkpoint | System Vacced and Gassed
checkpoint-status | eb311294-2edf-4646-a459-101b29a0e021 |  | checkpoint | Electrical fit off and correctly labeled at MSSB/SB
checkpoint-status | 2678e03a-1456-4944-b5b6-96a5b07ba511 |  | checkpoint | Lockable Isolation device is installed at outdoor unit
checkpoint-status | 733b6845-10eb-4e07-bbab-dbd3b83a97a8 |  | checkpoint | Outdoor Unit is correctly and clearly labled for identification
checkpoint-status | 68cc1b95-3f6a-4487-9f4b-2553d6025586 |  | checkpoint | System is energised
checkpoint-status | 0704be98-13a5-43c0-8a54-55ac1c356d2d |  | checkpoint | Unit is mounted securely (TAKE PHOTO)
checkpoint-status | 57d523a2-3c66-46a1-bda6-291944eca5c5 |  | checkpoint | Unit is installed on anti-vibration pads
checkpoint-status | 27691ce0-3c4e-451c-9485-b30e785d3f1d |  | checkpoint | Model and Serial number are clearly visable (TAKE PHOTO)
checkpoint-status | 67d28ba1-e474-49c8-8bea-f3b483d97cab |  | checkpoint | Pipes are fully insulated
checkpoint-status | b41068a2-0d0e-4227-8dae-16ce7e522379 |  | checkpoint | Electical conduit is secure and no cable is visible
checkpoint-status | baafac7d-bd50-42d9-ae9a-3fb9f88b0826 |  | checkpoint | Fan operating and free of vibration
checkpoint-status | 0349277f-b718-473f-82f9-9bf4117d3069 |  | checkpoint | Drain correctly terminated
checkpoint-status | 0cbc7d08-5c6c-4092-af5f-5f5ef9314a96 |  | checkpoint | Drain flow tested and good
checkpoint-status | 5939a242-3e82-455a-8426-b1ce1becddcf |  | checkpoint | Other Comments or Notes
checklist-flat | ad664ed6-e287-4d69-bd00-a671486801c2 |  | checklist | DUCTED AC |  |  |  |  | Yes | Commissioning - DUCTED AC | d41fd0d2-912c-42fc-8b55-0ab5abac59a3
checkpoint-status | 6a67a0b1-2d60-4a03-a1ae-d6223ffcde76 |  | checkpoint | System is energised
checkpoint-status | 183f89eb-e785-42e3-9d27-3ae5c3393738 |  | checkpoint | System is labled at SB
checkpoint-status | 9c30b1b6-f013-4e5d-a9c0-499be326d72c |  | checkpoint | Power isolation at equipment installed (isolator lead/PB)
checkpoint-status | 9dd9474c-1e9c-4c74-bfd0-3f4c2fefc709 |  | checkpoint | Wall Controller is installed
checkpoint-status | 92631daa-ef4d-45dc-96ca-083e70f67dfe |  | checkpoint | Wall Controller is mounted level
checkpoint-status | 99ab1056-dd14-41b3-ae9f-d06036f4a097 |  | checkpoint | Wall Controller initial setup is complete (ie time and date)
checkpoint-status | 3d561316-f4a5-4792-9cdb-1895326dff76 |  | checkpoint | Drain termination point accessable and complete
checkpoint-status | da36afc8-bd7d-4139-9e4c-60cf20cca6c7 |  | checkpoint | Drain has been terminated correctly at termination point (TAKE PHOTO)
checkpoint-status | c3b9e798-5af7-413d-91c8-4e4526d1bd32 |  | checkpoint | Access/Access Panel is installed at Indoor Unit
checkpoint-status | 0068e000-8dd4-4a33-ac65-f288180b4986 |  | checkpoint | Access is suffient to service electrical, test drains and access filters
checkpoint-status | 76900b08-4362-425c-b88c-1da75bbca972 |  | checkpoint | Return Air Filters are installed
checkpoint-status | 0f5043f9-3eaf-4823-a528-c6e677d56925 |  | checkpoint | Drain is installed correctly at indoor unit
checkpoint-status | e27886f5-4282-4368-8cc1-845366a81ff5 |  | checkpoint | Drain passed flow test
checkpoint-status | 238eb4bd-7c6a-4d8c-a4b0-4b679da3137c |  | checkpoint | Model and Serial numbers are clearly visable (TAKE PHOTO)
checkpoint-status | eb31f6a2-31d1-497b-9e90-e13239166ff5 |  | checkpoint | Unit installed and mounted correctly
checkpoint-status | c0193872-fe46-4c01-992b-2412e2b6b9a8 |  | checkpoint | Pipes and Flare Connections are fully insulated
checkpoint-status | 2745901b-4b91-4d58-a706-2ee19296e6e1 |  | checkpoint | Fan operating and free of vibration
checkpoint-status | 0d21741f-3234-4113-aa78-2ee8110165d4 |  | checkpoint | All Ductwork on System is complete
checkpoint-status | ca60bb83-f29e-42a2-a724-9c55c39e532d |  | checkpoint | All Dampers are installed as per drawings
checkpoint-status | 1198dff7-0368-4baa-8216-e668c3727dd0 |  | checkpoint | Grilles installed correctly (level and without obstruction)
checkpoint-status | cb8818ef-a2ab-48ee-9d9d-a00cf1d9e2ce |  | checkpoint | Strings removed from damper IF APPLICABLE
checkpoint-status | 02d2ff93-67b7-4d58-8c28-0a484da34283 |  | checkpoint | Airflow is measured to meet design (record airflow)
checkpoint-status | af3da0b8-4c6e-428f-ad9b-16c609a735be |  | checkpoint | Record Fan Speed and Static Pressure Setting at time of Airflow measurement
checkpoint-status | 19d134db-8fa8-41c0-8f29-1e6dcf96ba9d |  | checkpoint | Record Temperature Difference in heating (K)
checkpoint-status | 652444a4-a6e1-42ba-bb77-856210382dac |  | checkpoint | Other Comments or Notes
checklist-flat | fe4ed2d7-59a5-4445-8dfe-9b105545f429 |  | checklist | Riser - Checklist |  |  |  |  | Yes | Riser - Checklist | e9d84faa-9515-431d-8a8c-3d6d83c3082a
checkpoint-status | 9d7d6b75-6513-4e57-9f1a-35ccd2e807b3 |  | checkpoint | Lobby Relief riser 2x OFF - pre cast panels installed correctly, grilles fitted off
checkpoint-status | d2b585ac-c6f0-4de7-adee-66937e67b87a |  | checkpoint | Pressure sensors for relief Level 6 and 9
checkpoint-status | 2b5a5ac9-4329-4027-b761-f1dd40f351f9 |  | checkpoint | Stair 1 - Copper pressure tubing run, Grille fitted off
checkpoint-status | 648f271f-12a5-4f31-b004-f349d7b7110c |  | checkpoint | Stair 2 - Copper pressure tubing run, Grille fitted off
checkpoint-status | 8ff49c3a-0f15-4fec-bd6e-020422f5f9e0 |  | checkpoint | Pressure sensors for stair press fans 1 and 2 on levels B1,6,9
checkpoint-status | 238684a4-ba06-46ba-b7cc-7452c57c948b |  | checkpoint | Kitchen Exhaust Ducted installed and mounted correctly
checkpoint-status | 4fcbbc15-92c0-43a9-9c38-95f3369166e2 |  | checkpoint | Binroom Exhaust Ducted installed and mounted correctly
checkpoint-status | 44d147e2-a986-4b47-811c-9f07f9587b7b |  | checkpoint | Binroom Exhaust Room - Fire damper, OBD and grille installed
checkpoint-status | f53b0029-e4ec-4072-be05-bd9f0a4607d6 |  | checkpoint | Lobby Supply - Fire damper, duct, flex duct, cushion box installed
checkpoint-status | 1f04db94-ac0c-48a1-9ef9-acb1bebc6e91 |  | checkpoint | Lobby Supply - Grille fitted off