## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat | 9e074061-2437-4cab-8742-9b44cc6a5217 |  | checklist | Punch windows (site glazed) |  |  |  |  | Yes | Punch windows (site glazed) | 9073bda4-0fac-4f01-991c-298992a7dd77
checkpoint-status | 7ecede72-5d68-4dff-bff9-95b309949b3d |  | checkpoint | Opening inspected and sizes correct
checkpoint-status | 1f452f95-ee40-4409-97d1-c5f3ac3e7177 |  | checkpoint | Opening wraped & prepared correctly by others
checkpoint-status | 5097dd9e-b212-4014-8b49-b5a9447b37b5 |  | checkpoint | Picture of packers and fixings
checkpoint-status | 0c0367b8-340f-452a-8c62-643c3eba7c4a |  | checkpoint | Frames packed and fixed correctly
checkpoint-status | e579f511-6faa-49b3-8812-9b3d0619af53 |  | checkpoint | External flashings / weather seals as per shop drawings
checkpoint-status | 6148c693-fb8f-4b9f-bb90-86fa22590c5a |  | checkpoint | Frame airseals with PF rod completed
checkpoint-status | c9a50670-2aca-4236-a96c-8af5c6c806bb |  | checkpoint | Glazing completed with all rubbers
checkpoint-status | eb58cd9b-1d39-496f-a58d-a3e8108a2839 |  | checkpoint | Trade clean done
checkpoint-status | 283a028b-3ad5-4fd8-9dec-9a0ea7dc652c |  | checkpoint | Final inspections complete by Wights
checkpoint-status | 6b2e3974-420a-4d3f-b49f-689a6d5631aa |  | checkpoint | Main contractor sign off and approved
checklist-flat | b7beec91-a647-43c3-9bb6-b041008b0159 |  | checklist | Sliders (Partial site glaze) |  |  |  |  | Yes | Sliders (Partial site glaze) | e7970e16-be7b-4e05-8e93-6ac435861216
checkpoint-status | d6b1730a-e23f-45a0-86f7-6839b9f4bbf3 |  | checkpoint | Opening inspected and sizes correct
checkpoint-status | c2f35055-edd1-4a7d-9203-912e6c4fd038 |  | checkpoint | Opening wraped & prepared correctly by others
checkpoint-status | bbc82844-b19d-4d05-b04a-ebd87872291b |  | checkpoint | Picture of packers and fixings
checkpoint-status | 5106330a-e90a-47f3-bdbc-ca3e23fd08be |  | checkpoint | Frames packed and fixed correctly
checkpoint-status | 723ee133-099d-4f39-a35c-dfc2e260ca7a |  | checkpoint | External flashings / weather seals as per shop drawings
checkpoint-status | 93cac723-9b19-4b5d-8021-f44c8eea52b9 |  | checkpoint | Frame airseals with PF rod completed
checkpoint-status | bcdbb7ae-12a1-44f4-bbf8-a071d9e15ff2 |  | checkpoint | Sliders installed and slide smoothly
checkpoint-status | 302d15c5-0ebb-47da-844d-906f8b2af33d |  | checkpoint | Glazing; completed with all rubbers
checkpoint-status | 59ed831a-c47a-4b4a-8933-c2c6be002775 |  | checkpoint | Trade clean done
checkpoint-status | 65f3c93c-29fa-495e-8e20-5bc86248395a |  | checkpoint | Final inspections complete by Wights
checkpoint-status | f3aacde1-002f-4028-a737-7d070217d36f |  | checkpoint | Main contractor sign off and approved