## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Passive Fire Module Assembly Inspection |  |  |  |  | Yes | Passive Fire Module Assembly Inspection | 218a9e61-4e92-4466-bacb-b0160d33fd20
checkpoint-group |  |  | section | First Fix Passive Fire
checkpoint-status |  |  | checkpoint | Check and review as per approved passive fire report, and provide picture of the respective report which clearly shows page number
checkpoint-status |  |  | checkpoint | Install fire dampers, collars and sealants as per manufacturer specifications
text | 9749e696-a0c5-54fe-b78a-2bd1eeb9c537 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check fire rated linings; materials and passive fire protection measures as per related GIB Fire rate system: External Wall: GWTLE 60a; Marriage Wall / Intertenancy Wall: GBUW 60; Ceiling: GBUC 60.
checkpoint-status |  |  | checkpoint | Check installation installed as per manufacturer specifications and approved design
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by fire contractor before going to next step
checklist-sectioned |  |  | checklist | Exterior - Insulation, Wrap and Flashings & Tapes Inspection |  |  |  |  | Yes | Exterior - Insulation, Wrap and Flashings & Tapes Inspection | 2210bc97-176c-4c47-9f32-fc7da55361c0
checkpoint-group |  |  | section | Insulation
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install insulation as per fabrication plan
text | 0553b798-2289-521a-8fc3-556a3323b818 |  | textbox | Operator name
checkpoint-status |  |  | checkpoint | Attach Insulation Certificate
text | ebfbda4a-f877-5c4f-a9d5-cc7faccf36ab |  | textbox | Operator name
checkpoint-status |  |  | checkpoint | Check and verify installed insulation as per fabrication plan
text | a015f917-4ca1-5648-a2a7-8fa4dcd193c7 |  | textbox | Operator name
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Wrap (Rigid Air Barrier)
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Seal penetrations and install correct RAB and fixing as per fabrication plan
text | 2a7adc43-c7e0-5415-b557-661713c0d1ad |  | textbox | Operator name
checkpoint-status |  |  | checkpoint | Check and verify installed RAB and fixing as per fabrication plan
checkpoint-status |  |  | checkpoint | Check and verify joints and junctions taped/flashed as per fabrication plan
checkpoint-status |  |  | checkpoint | Check and verify penetration sealed
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Flashings and Tapes
checkpoint-status |  |  | checkpoint | Check and review approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install all flashing tapes/Sealants to RAB joints, windows, doors, penetrations/junctions, etc., as required
text | cc68e2fc-ea22-50a2-a93f-33067bc7bafb |  | textbox | Operator name
checkpoint-status |  |  | checkpoint | Install all flashings: Int/Ext corner, cavity closer, etc., as required
text | 5af709ff-7d2c-508a-8d8d-d29ebc9569a5 |  | textbox | Operator name
checkpoint-status |  |  | checkpoint | Check and verify all flashing complete and weathertight as per plan
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checklist-flat |  |  | checklist | Project Documentation Upload |  |  |  |  | Yes | Project Documentation Upload | 37e27158-94d9-45a0-9b28-79acd110022b
checkpoint-no-status |  |  | checkpoint | Documentation Links for Blocks outlined below
checklist-sectioned |  |  | checklist | Structure - Floor Cassette Inspection |  |  |  |  | Yes | Structure - Floor Cassette Inspection | 435ab25d-a753-4cbf-8520-b2ee987ca57a
checkpoint-group |  |  | section | Structural framing and Preline Inspection
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install all floor framing elements and fixings as per fabrication plan
text | 4e33a2e4-6386-5475-b616-ed9b8127be18 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and Verify sizes, spacings, treatment, grade as per fabrication plan
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | 864bcda2-6371-5afb-b98f-98a134ab6fc3 |  | textbox | Diagonal #1:
text | c720fcfb-1803-552b-9e7d-b872f07b4bbf |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify installed elements as per fabrication plan
checkpoint-status |  |  | checkpoint | Check and verify installed structural fixings as per fabrication plan
checkpoint-status |  |  | checkpoint | Check and verify installed nogs/blockings as per fabrication plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Floor sheeting
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install floor sheeting and fixing as per fabrication plan
text | f74a687f-12eb-5ccf-9785-caee7b12d3cd |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | 326d442a-1011-5bdd-aa24-0ffa89f19e8a |  | textbox | Diagonal #1:
text | 93e4231e-85e1-5cf6-8957-2dfbf7fb35a7 |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify sheet edges in correct locations as per fabrication plan
checkpoint-status |  |  | checkpoint | Check and verify installed fixings as per fabrication plan
checkpoint-status |  |  | checkpoint | Hold point: Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | HOLDPOINT
checklist-flat |  |  | checklist | P/S - External Packing |  |  |  |  | Yes | P/S - External Packing | 491b547e-c2d1-4980-94c0-04737ccde4e0
checkpoint-status |  |  | checkpoint | Use protective film to cover a module completely
checkpoint-status |  |  | checkpoint | Use heat Gun to seal the protective film.
text | e494dde3-fa2e-564a-a903-66904b1f948e |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Make sure there are no gaps in the film
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before moving a Module to a Storage area.
checklist-flat |  |  | checklist | DB Board Fit Off Checklist |  |  |  |  | Yes | DB Board Fit Off Checklist | 4a43504c-35a4-42cf-a92e-cf3404617f7e
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install Distribution Board as per approved electrical services plan
text | 2d10a95f-bc74-50f5-bd8d-a1131cfb6281 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Install all electrical cablings as per approved electrical services plan
text | d98407c6-74b2-5b7d-84e4-7adb228ab8d2 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify installed switchgear values as per plan
checkpoint-status |  |  | checkpoint | All cables are labeled correctly.
checkpoint-status |  |  | checkpoint | Ensure all screws are torqued to correct specification
checkpoint-status |  |  | checkpoint | Visual inspection: Cable protection/Support/fixing are in good condition without obvious damage.
checkpoint-status |  |  | checkpoint | Hold point: photo required an signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | Structure - External Wall / Marriage Wall / Intertenancy Wall Inspection |  |  |  |  | Yes | Structure - External Wall / Marriage Wall / Intertenancy Wall Inspection | 596cdfe7-7a5b-49be-9183-4a95af8f0629
checkpoint-group |  |  | section | Structural Framing and Preline Inspections
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install all wall framing elements and fixing as per fabrication plan
text | 9a92f73b-107f-53ae-93a0-c8f89f7169d5 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Install Portal frame and brace chord as per fabrication plan as required
text | 4ced78c2-bcb5-5fd9-8cfe-cb425a6c3c27 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and Verify sizes, spacings, treatment, grade as per fabrication plan
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | c1b86dd1-3016-51c5-8064-d56ece6b3a4a |  | textbox | Diagonal #1:
text | 71f1d7d9-7962-57ca-8bd1-46ba6139d82c |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify installed elements as per fabrication plan
checkpoint-status |  |  | checkpoint | Check and verify installed structural fixings as per fabrication plan
checkpoint-status |  |  | checkpoint | Check and verify installed nogs/blockings as per fabrication plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Structural Sheet Bracing
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install bracing and fixing as per fabrication plan
text | a75a60f1-1aeb-5fc1-917d-c7f14628e9b1 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | 7a6ac290-200e-5441-aff8-5a911324cdf5 |  | textbox | Diagonal #1:
text | 9ce15da8-2351-5d6d-8c5f-c5974d9e3a6e |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify installed bracing as per fabrication plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per fabrication plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Fire Lining 1st Layer
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install 1st Layer and fixing as per fabrication plan
text | 31ac0771-2f5a-5231-9d32-4012ec7ad0b5 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify installed layer edges in correct locations as per fabrication plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per fabrication plan
holdpoint |  |  | signoff | Photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Fire Lining 2nd Layer
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install 2nd Layer and fixing as per fabrication plan
text | bd90c939-ecf9-5a7e-b0a3-b66b95df7b14 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify installed layer edges in correct locations as per fabrication plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per fabrication plan
holdpoint |  |  | signoff | Photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | E/M - First Fix Module Assembly |  |  |  |  | Yes | E/M - First Fix Module Assembly | 80ba9d0d-10c2-49e9-b64c-d6d5159960aa
checkpoint-group |  |  | section | Penetrations
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Locate and cut out all penetrations as per fabrication plan
text | db1b971c-649d-5c06-ae5c-f7486669cb52 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify all penetrations as per fabrication plan
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | First Fix Electrical and Mechanical
checkpoint-status |  |  | checkpoint | Check and review as per electrical and mechanical services Plan and provide picture of the respective services plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install all flush boxes as per electrical services plan
text | a2dc79a7-d3bd-53ab-8ee7-43206e1a7b83 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Confirm the fire rated pads of flush boxes have been installed properly
checkpoint-status |  |  | checkpoint | Install all electrical conduit and draw wires as per electrical services plan
text | 8249849e-445b-54dc-90f2-50e7a04aea76 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Install all electrical cablings as per electrical services plan
text | b5c3895d-28b2-5482-af26-c6fa47a964af |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Apply fire sealant around cut-outs if needed
text | 85dfddf5-dbb0-5b71-973e-ed2a499aeaa4 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify installed elements as per electrical services plan
checkpoint-status |  |  | checkpoint | Visual inspection: Cable protection/Support/fixing and damages
checkpoint-status |  |  | checkpoint | Check and verify fire sealants have been applied
holdpoint |  |  | signoff | Hold point: photo required and signed off by Electrical team leader before going to next step
checklist-sectioned |  |  | checklist | Structure - Internal Wall Inspection |  |  |  |  | Yes | Structure - Internal Wall Inspection | 86f2b076-c162-4de7-8540-b2a3928ddb6d
checkpoint-group |  |  | section | Structural Framing and Fixing and Preline Inspections
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install all wall framing elements and fixing as per fabrication plan
text | 0ed3b459-135c-5bef-9138-22feb0d18389 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Install Portal frame and brace chord as per fabrication plan as required
text | 1156084d-fe4c-58f2-a2eb-0a489b87fa5b |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and Verify sizes, spacings, treatment, grade as per fabrication plan
checkpoint-status |  |  | checkpoint | Check and verify installed elements as per fabrication plan
checkpoint-status |  |  | checkpoint | Check and verify installed structural fixings as per fabrication plan
checkpoint-status |  |  | checkpoint | Check and verify installed nogs/blockings as per fabrication plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Standard/Single Layer Gib board
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan
checkpoint-status |  |  | checkpoint | Apply Layer 1 as per fabrication plan
text | 147abb3f-6096-539d-8570-79b0288ced63 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Fixings as per fabrication plan
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Second Standard/Single Layer Gib board
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan
checkpoint-status |  |  | checkpoint | Apply Layer 1 as per fabrication plan
text | b3aade6e-78f9-57c5-9c4f-8288f5558245 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Fixings as per fabrication plan
checkpoint-status |  |  | checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | Interior Fit Out - Painting Inspection |  |  |  |  | Yes | Interior Fit Out - Painting Inspection | a2d523f7-d985-4198-860e-1d2b3f933b62
checkpoint-group |  |  | section | Gib stopping
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install internal Gib stopping as per approved plans
text | 4f514883-f30a-5d30-8e68-5de1082c310c |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify the installed GIB stopping as per approved plans
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | 1st and 2nd Painting
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Complete the 1st and 2nd internal painting as per approved plans and manufacture specifications
text | 54d6414a-d830-5d83-a053-7fa4dc3441c8 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check the painting
checklist-sectioned |  |  | checklist | Exterior - Windows and Doors |  |  |  |  | Yes | Exterior - Windows and Doors | c0901e80-8589-40f8-8c5e-39cdc60c06a6
checkpoint-group |  |  | section | Windows Installation
checkpoint-status |  |  | checkpoint | Check and review approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Seal all windows joinery as per plan and manufacture specifications
text | 98a4c0fc-f494-577f-8d9f-ad5b52a8796d |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify all windows sealed and weathertight as per plan.
checkpoint-status |  |  | checkpoint | Install windows as per approved plans and manufacture specifications
text | 9ec9a9bc-4fad-5b4d-be88-63c2762a0cd7 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify all windows installed as per plan. Take photos of window/door glazing permanent parking if possible.
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Doors Installation
checkpoint-status |  |  | checkpoint | Check and review approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Seal all doors joinery as per plan and manufacture specifications
text | a6d1bb14-6fb0-5a82-bb83-d25dd631eca2 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify all doors joinery sealed and weathertight as per plan.
checkpoint-status |  |  | checkpoint | Install doors as per approved plans and manufacture specifications
text | b6e7a3ab-707f-5e76-9e48-8517d8f79994 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify all doors installed as per plan. Take photos of window/door glazing permanent parking if possible.
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | Interior Fit Out - Floor Inspection |  |  |  |  | Yes | Interior Fit Out - Floor Inspection | c2af55f4-19d9-4986-82a8-c7feb6cfa89f
checkpoint-group |  |  | section | Acoustic floor
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install acoustic floor as per approved plans and manufacture specifications
checkpoint-status |  |  | checkpoint | Check and verify the installed acoustic floor as per approved plans and specifications: Battens, Spacing, Insulation, etc.
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Floor sheeting and trims
checkpoint-status |  |  | checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install all internal floors sheeting and trims as per approved plans
text | 25454853-9cd0-5457-80cf-69faaac7416d |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify the installed floor sheeting and trim as per approved plans
holdpoint |  |  | signoff | Hold point: photo required and signed off by Team leader before going to next step
checklist-flat |  |  | checklist | Final Sign Off |  |  |  |  | Yes | Final Sign Off | d7719ccb-4ce6-44b6-a4e0-64c4f42baf03
checkpoint-status |  |  | checkpoint | Module Sign off by Licensed Building Practitioner
holdpoint |  |  | signoff | HOLDPOINT: SIGNED OFF BY LICENSED BUILDING PRACTITIONER
checklist-flat |  |  | checklist | Structure - Roof Assembly |  |  |  |  | Yes | Structure - Roof Assembly | d8b751da-c178-42d1-9201-cba70b6ec768
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install roof framing/trusses/purlins as per fabrication plan
text | bee6f911-634f-5f76-b642-2acd88fa475c |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Install all structural fixings as per fabrication plan
text | ddc3621d-c9c7-5f0e-a313-db7458685c6d |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify roof framing treatment and grade as per plan
checkpoint-status |  |  | checkpoint | Check and verify bracing as per plan: roof plane braces, fixings and tensioners, roof space braces and fixings
checkpoint-status |  |  | checkpoint | Check and verify roof pitch, overhang and truss/rafter sizes & spacings as per plan
checkpoint-status |  |  | checkpoint | Check and verify purlin / batten sizes, centres and fixings as per plan
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | Structure - Deck Inspection |  |  |  |  | Yes | Structure - Deck Inspection | dceb1dd2-17a6-4e5a-8b97-65de3a66fdf3
checkpoint-group |  |  | section | Structural Framing and Fixing
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Check and confirm Joist: Sizes, spacings, treatment, grade as per fabrication plan
checkpoint-status |  |  | checkpoint | Install all deck framing elements as per fabrication plan
text | fcf03749-a962-5ad6-94fb-6080e9a1ef6b |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Install all deck structural fixings as per fabrication plan
text | 2e481a58-98c3-5cf1-9234-535a637bff32 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify installed elements and fixings as per fabrication plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checkpoint-group |  |  | section | Deck Sheeting
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Check and Verify sizes, spacings, treatment, grade as per fabrication plan
checkpoint-status |  |  | checkpoint | Apply deck sheeting as per fabrication plan
text | 1c7b534e-0421-50eb-a7a2-da9b44c6fdbf |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Deck fixed off as per fabrication plan
text | 8d2f9255-4483-5a15-b1bb-e644068456b5 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check Sheet edges in correct locations as per fabrication plan
checkpoint-status |  |  | checkpoint | Check deck sheeting sloped as per fabrication plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | Hold point: Photo required and signed off by Team leader before going to next step
checklist-flat |  |  | checklist | P/D - Floor Cassette |  |  |  |  | Yes | P/D - Floor Cassette | e6498a71-7088-472f-a515-7b8e225dd5c2
checkpoint-status |  |  | checkpoint | Check and review as per approved plumbing and drainage services Plan, and provide picture of the respective plan which clarify shows page number
checkpoint-status |  |  | checkpoint | Install pipes as per approved plans and manufacture instructions
text | 3bac5d4d-271f-54dc-a917-1c7015fb707d |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify the pipework installed as per approved plan
checkpoint-status |  |  | checkpoint | Check and verify foul water pipe gradients compliant
checkpoint-status |  |  | checkpoint | Complete air test to AS/NZS3500
text | e07731da-4507-5918-9560-a729e88150f4 |  | textbox | Operator Name:
holdpoint |  |  | signoff | Hold point: photo required and signed off by before going to next step
checklist-flat |  |  | checklist | P/D - Module Assembly |  |  |  |  | Yes | P/D - Module Assembly | f0a6967c-e954-4f4f-90b9-6f26e47d7586
checkpoint-status |  |  | checkpoint | Check and review as per approved plumbing and drainage services Plan, and provide picture of the respective plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install pipes and connections as per plan
text | ab6be0e4-f736-525b-bb69-be837099559f |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify the pipework installed as per approved plan
holdpoint |  |  | signoff | Hold point: Photo required of pressure gauge and signed off by Plumbing team leader before going to next step
checklist-sectioned |  |  | checklist | Structure - Module Assembly |  |  |  |  | Yes | Structure - Module Assembly | f0c2372b-7502-4337-ab29-44a456b5ede8
checkpoint-group |  |  | section | Exterior Walls and Deck Inspection
checkpoint-status |  |  | checkpoint | Confirm all exterior walls and deck have been inspected and signed off by team leader before starting the module assembly inspection
holdpoint |  |  | signoff | Hold point
checkpoint-group |  |  | section | Module Assembly
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Locate floor cassette on the podium
text | dc1a0b8f-8ece-5386-94fb-83a64e246816 |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Install all external walls, internal walls, and ceiling cassette as per fabrication plan. Support/Prop necessary.
text | 23e09857-b95b-585c-bc8d-5c3019968a7a |  | textbox | Operator Name:
checkpoint-status |  |  | checkpoint | Check and verify installed floor, ceiling, and walls as per fabrication plan.
checkpoint-status |  |  | checkpoint | Check and verify all structural fixings as per fabrication plan.
checkpoint-status |  |  | checkpoint | Hold point: photo required an signed off by Team leader before going to next step
holdpoint |  |  | signoff | Hold point: photo required an signed off by Team leader before going to next step
checkpoint-group |  |  | section | Internal Walls Inspection
checkpoint-status |  |  | checkpoint | Go to Structure / Wall Panels section to carry out the inspection and sign off as required
checkpoint-status |  |  | checkpoint | Signed off by Team leader before going to next step
holdpoint |  |  | signoff | Hold point: Signed off by Team leader before going to next step
checklist-sectioned |  |  | checklist | Structure - Ceiling Cassette Inspection |  |  |  |  | Yes | Structure - Ceiling Cassette Inspection | f9af825c-a48e-4e7f-ae35-a1073bb57b9a
checkpoint-group |  |  | section | Structural Framing and Preline Inspection
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install all ceiling framing elements and fixings as per fabrication plan
text | 144a8f64-a40d-5b88-aa0d-289b2628b218 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and Verify sizes, spacings, treatment, grade as per fabrication plan
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | a04181c5-0be0-54d2-979b-b689d497abd3 |  | textbox | Diagonal #1:
text | 1df872eb-213e-5812-b982-c7a147e8a064 |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify installed structural fixings as per fabrication plan
checkpoint-status |  |  | checkpoint | Check and verify installed nogs/blockings as per fabrication plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Sheet Bracing as required
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install sheeting bracing and fixing as per fabrication plan
text | 630b01c5-3b9a-5054-9dc1-660d8be9254b |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check the diagonals (photo required) and confirm 90 degrees on four external corners. Please write down the actual readings of two diagonals.
text | 4db6df4b-9ca9-522f-919c-02250026b4fc |  | textbox | Diagonal #1:
text | 3cdeed67-4302-540f-8b51-94c0ad5d257a |  | textbox | Diagonal #2:
checkpoint-status |  |  | checkpoint | Check and verify sheet edges in correct locations as per fabrication plan
checkpoint-status |  |  | checkpoint | Check and verify installed fixings as per fabrication plan
checkpoint-status |  |  | checkpoint | Hold point: Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Fire Lining 1st Layer
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install 1st Layer and fixing as per fabrication plan
text | 717ff329-5547-5ca6-86ed-f615c3bbbe5e |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify installed layer edges in correct locations as per fabrication plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per fabrication plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | HOLDPOINT
checkpoint-group |  |  | section | Fire Lining 2nd Layer
checkpoint-status |  |  | checkpoint | Check and review correct fabrication plan and provide picture of the respective fabrication plan which clearly shows page number
checkpoint-status |  |  | checkpoint | Install 2nd Layer and fixing as per fabrication plan
text | e7d5f915-0cb9-5a38-bfd7-29055b5f7fd4 |  | textbox | Operator name:
checkpoint-status |  |  | checkpoint | Check and verify installed layer edges in correct locations as per fabrication plan
checkpoint-status |  |  | checkpoint | Check and verify fixings as per fabrication plan
checkpoint-status |  |  | checkpoint | Photo required and signed off by Team leader before going to next step
holdpoint |  |  | signoff | HOLDPOINT