## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Internal Membrane Checklist | [5 empty] | Internal Membrane Checklist
section | Plumber to confirm first fix plumbing complete
checkpoint | Hold point: photo required and signed off by Plumbing team leader before going to next step
signoff | Hold point: signed off by Team leader before going to next step
section | Electrician to confirm first fix electrical complete
checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
signoff | Hold point: signed off by Team leader before going to next step
section | Complete internal wall lines
checkpoint | Complete all internal wall lines as per approved plans and manufacture specifications.
textbox | Operator Name:
signoff | Hold point: Postline inspection photos required and signed off by Team leader before going to next step
section | Complete all passive fire requirements
checkpoint | Hold point: photo required and signed off by passive fire contractor
signoff | Hold point: signed off by Team leader before going to next step
section | Mechanical ducts and ventilation
checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
signoff | Hold point: signed off by Team leader before going to next step
section | False ceiling and bulkheads
checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Install all false ceiling and bulkheads as per approved plans and specifications.
textbox | Operator Name:
signoff | Hold point: signed off by Team leader before going to next step
section | Gib stopping
checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Complete all internal Gib stopping as per approved plans and manufacture specifications.
textbox | Operator Name:
signoff | Hold point: photo required and signed off by Team leader before going to next step
section | Acoustic floor
checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Install acoustic floor as per approved plans and manufacture specifications.
textbox | Operator Name:
signoff | Hold point: photo required and signed off by Team leader before going to next step
section | Door and trims
checkpoint | Check and review as per approved plans and specifications
signoff | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Install all internal floors and trims
textbox | Operator Name:
signoff | Install all internal floors and trims as per approved plans and manufacture specifications.
checkpoint | Hold point
signoff | Hold point: photo required and signed off by Team leader before going to next step
section | Painting
checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Complete all internal painting as per approved plans and manufacture specifications.
textbox | Operator Name:
signoff | Hold point: photo required and signed off by Team leader before going to next step
section | Kitchen and bathroom joinery install
checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Install kitchen and bathroom joinery as per approved plans and manufacture specifications.
textbox | Operator Name:
signoff | Hold point: photo required and signed off by Team leader before going to next step
section | Tiling and waterproofing: bathroom laundry Kitchen
checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Complete all waterproofing membrane to tile areas as per approved plans and manufacture specifications.
textbox | Operator Name:
checkpoint | Hold point: photo required and signed off by Team leader before going to next step
checkpoint | Install tiles to bathroom, laundry and kitchen as per approved plans and specifications.
textbox | Operator Name:
signoff | Hold point: photo required and signed off by Team leader before going to next step
section | Hardware
checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Complete all hardware as per approved plans and manufacture specifications.
textbox | Operator Name:
signoff | Hold point: photo required and signed off by Team leader before going to next step
section | Plumbing
checkpoint | Plumber to confirm second fix plumbing complete
checkpoint | Hold point: photo required and signed off by Plumbing team leader before going to next step
signoff | Hold point: signed off by Team leader before going to next step
section | Electrical
checkpoint | Electrician to confirm second fix electrical complete
checkpoint | Hold point: photo required and signed off by Electrical team leader before going to next step
signoff | Hold point: signed off by Team leader before going to next step
section | Floor Coverings
checkpoint | Check and review as per approved plans and specifications, and provide picture of the respective plan which clarify shows page number
checkpoint | Install all floor coverings as per approved plans and manufacture specifications.
textbox | Operator Name:
signoff | Hold point: photo required and signed off by Team leader before going to next step