## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP039 - AGL Boring Installation | itp |  |  |  |  | FH-ZU2-QU-ITP039 - AGL Boring Installation - Rev 0
section | 1.0 - Preliminary Activities – Permits, Documentation, Approvals, Survey Documentation
checkpoint | 1.1 - Check for correct documentation
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Ensure that all employees and subcontractors are:
label | – using the correct and complete set of drawings.
label | – all drawings are the latest revision.
label | Reference Documents - Drawings / Aconex Register
label | Inspection/Test Method - Verify
label | Record of conformity - Drawings and drawing registers
label | HP*
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - All necessary measures and controls being implemented, that is PSP, EMP, TMP, SWMS & WP.
label | Reference Documents - PSP, EMP, TMP, JSEA, SWMS, WP
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 1.3 - Definition of the work area (survey)
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Work area has been cleared and surveyed (marked on site). Limits of excavation clearly defined.
label | Reference Documents - Drawings
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | HP*
label | Responsibility - Project Engineer / Surveyor
date | Date Completed:
checkpoint | 1.4 - Material Submissions
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - – Ensure material submissions for the conduits and grout are submitted
label | Reference Documents - ZULU-BECA-001-SPC-00003 cl. 3.4, AS 1477 AS 2053
label | Inspection/Test Method - Verify
label | Record of conformity - Aconex reference This ITP signed
label | HP
label | Responsibility - Project Engineer / Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Methodology
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Prepare and implement a Methodology that includes the following at a minimum:
label | – Full details of the steps to be taken for the underbore works; and
label | – Details of equipment to be used.
label | ○ This must be submitted at least 7 days prior to the commencement of site work
label | Reference Documents - ZULU-BECA-001-SPC-00004
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP Signed
label | HP
label | Responsibility - Project Engineer / Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.6 - Locate and prove existing services
label | Frequency - Prior to commencing activity
label | Acceptance Criteria - Location of services to be found and marked on the ground within the works;
label | – Contractor to obtain excavation permit from APAM prior to any demolition works.
label | – Services located within the works area to be exposed/proven, recorded as survey data and also on a service plan which is to be attached to the Excavation Permit.
label | Reference Documents - ZULU-BECA-001-SPC-00004 cl. 3.15
label | Inspection/Test Method - Verify
label | Record of conformity - Melbourne Airport Excavation Permit
label | HP*
label | Responsibility - Project Engineer / Surveyor
date | Date Completed:
section | 2.0 - Construction
checkpoint | 2.1 - Excavate trenches for Entry and Exit Pits
label | Frequency - Each lot
label | Acceptance Criteria - Trenches for entry and exit pits shall be excavated to the width and depth required enabling construction of the conduits to the requirements specified on the drawings.
label | – The level at the bottom of the trench shall not be above the required level at any point.
label | – Any over excavation under pavements shall be restored using 5MPa lean mix concrete in conjunction with the embedment.
label | Reference Documents - Drawings ZULU-BECA-001-SPC-00004 cl. 3.6
label | Inspection/Test Method - Visual inspection
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project Engineer / Foreman
date | Date Completed:
checkpoint | 2.2 - Existing services crossing new conduits
label | Frequency - Each lot
label | Acceptance Criteria - Only approved methods of excavation that has been approved by the Principal’s Representative shall be used.
label | – Location, level and configuration of existing service crossing to be recorded in as built documentation prior to backfill (including CAD model file)
label | Reference Documents - WMS002 – Working Near Existing Services
label | Inspection/Test Method - Visual inspection
label | Record of conformity - As-built survey report
label | SCP
label | Responsibility - Project Engineer / Surveyor
date | Date Completed:
checkpoint | 2.3 - Survey as-built
label | Frequency - Prior to backfilling each lot
label | Acceptance Criteria - Surveyor to pick up completed conduit runs
label | Reference Documents - FH QMP
label | Inspection/Test Method - Verify / Inspection
label | Record of conformity - Survey report
label | SCP / IP
label | Responsibility - Project Engineer / Surveyor
date | Date Completed:
checkpoint | 2.4 - Cover
label | Frequency - Each lot
label | Acceptance Criteria - Services installed under road and taxiway pavements and shoulders by under boring must have a minimum cover below the surface as shown in the drawings.
label | Notify the Contract Administrator at the following stages of construction:
label | – At setting up for the commencement of drilling; and
label | – At completion of drilling prior to connection of ducting to pits and backfilling
label | Reference Documents - Drawings, ZULU-BECA-001-SPC-00004
label | Inspection/Test Method - Verify
label | Record of conformity - Test report Aconex reference, This ITP signed
label | HP
label | Responsibility - Project Engineer / Principal’s Representative
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Conduit draw cord
label | Frequency - Each lot
label | Acceptance Criteria - Each duct way in each duct bank shall be fitted with a single unjointed length of draw cord of a length equal to the length of the duct plus 4m. The draw cord shall be nylon rope and be 6mm in diameter, blue in colour. The ends of the rope shall be coiled at the bottom of each pit or wound around a stake.
label | Reference Documents - ZULU-BECA-001-SPC-00004 cl. 3.10
label | Inspection/Test Method - Visual
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project Engineer / Foreman
date | Date Completed:
checkpoint | 2.6 - Grout
label | Frequency - Each Lot
label | Acceptance Criteria - 1. Verify that pulling back of 63mm diameter grout lines are limited to 10m.
label | 2. Measure volume of grout used per pull back to identify where full encasement may not have occurred.
label | Reference Documents - DCWC Mgt-CONTIN-000853
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed
label | IP
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | 2.7 - Bore Logs
label | Frequency - Each Lot
label | Acceptance Criteria - Submit bore logs for the underbore
label | Reference Documents - ZULU-BECA-001-SPC-00004
label | Inspection/Test Method - Verify
label | Record of conformity - This ITP signed JLM Borelog
label | HP*
label | Responsibility - Project Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the Fulton Hogan’s Quality\System Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Work Completed On:
date | Date: