## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | CULVERT DIMENSIONAL & COVER CHECKS |  | CULVERT DIMENSIONAL & COVER CHECKS | 3686bedf-f898-46e8-adae-50e2bb940c7f
| section | Details
| checkpoint-no-value | Details
008e76d4-75c9-5134-9cbe-1f60a7756a2b | textbox | Project Name
a24a7c10-e9fb-5e4f-8a9b-7d13892928bc | dropdown | Type of Culvert | Uni Culvert, Box Culvert
debecbb3-5439-5603-b046-bb031eff8aca | dropdown | Concrete Mix design Code | 980,880,680,VT Pipe (Dry Mix), HCP VR450/50 SCC
dee4ef01-2d96-5a10-9d89-7319a505b062 | radio | Method of Manufacture | Machine-Made Process,Standard Wet Cast Process, Automated SCC Cast Process
d2b667f3-2b6b-5600-804f-eb85b5158e7a | date | Date of Product Cast
89e25ee5-a4d7-5f89-b220-fa84ef26f9ae | date | Date of Test
| checkpoint | Internal Span & Leg Height
e7c85d09-7387-54ee-8ca0-cd77b51efd9f | number | Specified Internal Span (mm)
cbfb07ca-c8c4-573d-83f6-967afea57aa3 | number | Measured Internal Front Span (mm)
77815073-ea48-5573-ac9d-95c610f3aa90 | number | Measured Internal Back Span (mm)
8c077a07-a528-5cbb-b452-bd887496b842 | number | Specified Leg Height (mm)
09400e57-2307-5e63-bdb6-ccd727e1e798 | number | Measured Front 1st Leg Height (mm)
af62f28e-8331-5807-b5cc-adce2df79071 | number | Measured Front 2st Leg Height (mm)
29117a36-c916-5b6f-943c-d3390fb8d10a | number | Measured Rear 1st Leg Height (mm)
b26e592d-443d-5c74-b79f-5d557966cc1c | number | Measured Rear 2st Leg Height (mm)
68ab46f1-28d6-5e5b-bc46-1f6638d2d2c1 | dropdown | Tolerances (accordance with AS1597.1 & 2 cl.2.10.2) | Small RCBC (upto 1200x1200) = ± 5, Large RCBC (upto 2400x2400) = ± 10
f9bdb65c-29bb-5ee6-8861-76fd2e9c2fe0 | radio | Criteria: Does above measured leg heights & spans fall within the given tolerance above? | Yes,No
| checkpoint | Overall Length
63914b5e-4be1-5797-9241-a961eb8f08cc | number | Specified Overall Length (mm)
355de425-7994-55c5-8e49-41524811428e | number | Measured Left Leg Length (mm)
a0614953-086d-58f7-81d1-769f1b217dc8 | number | Measured Right Leg Length (mm)
8e2e3e6a-a073-545e-b93a-cff6065ac052 | number | Measured Crown Length (mm)
d0915c07-4e62-5fee-95f2-e7e92dfbc651 | note | The following measurement is only applicable to Uni-Culvert.
5b64efdc-e68c-555c-9b6c-5f8eab7c3a12 | number | Measured Base Length (mm)
a77ed222-1dd5-54c7-b22e-55ea2e2bf429 | dropdown | Tolerances (accordance with AS1597.1 & 2 cl.2.10.2) | Small RCBC (upto 1200x1200) = ± 15, Large RCBC (upto 2400x2400) = ± 15
cab0f226-6597-52f5-9ef9-06d7da319a0c | radio | Criteria: Does above measured legs and crown length fall within the given tolerance above? | Yes,No
3bd98d03-24ec-503c-807f-364488d56a79 | note | If No, please provide comment including (which is/are outside of tolerance)
| checkpoint | Thickness
3cc3e400-ee91-5931-8949-8ab7cff3ddf8 | number | Specified Legs Top Thickness (mm)
83d08093-4c9d-54c1-b9ac-0e9c31c64dc8 | number | Specified Legs Bottom Thickness (mm)
92cb7589-c983-5c55-88cf-94a85f5c063a | number | Measured Legs Top Thickness (mm)
7b79da51-d330-5278-a956-4045a3635bc4 | number | Measured Legs Bottom Thickness (mm)
24aad5af-b11b-514d-a868-6eb0304db618 | number | Specified Crown Thickness (mm)
8c3ecafa-636a-500a-a382-e129df6de98c | number | Measured Left Crown Thickness (mm)
b292b1b3-a042-5d68-a9aa-4b29e4796ac1 | number | Measured Mid Crown Thickness (mm)
86620f45-ba3c-51f1-82f1-df91592ab667 | number | Measured Right Crown Thickness (mm)
43c7fcfd-d9fe-597d-91e7-0de15b509828 | note | The following measurements are only applicable to Uni-Culvert.
5f9694c6-f73d-59fe-8fbf-bc7bcb2070f6 | number | Measured Left BaseThickness (mm)
8b99131d-cde4-5868-a133-52edc70595a9 | number | Measured Mid BaseThickness (mm)
519495c2-2f37-54aa-9cac-cc3b5195d7eb | number | Measured Right Base Thickness (mm)
270fd28a-620e-5786-a828-76d3d8f8efaa | dropdown | Tolerances (accordance with AS1597.1 & 2 cl.2.10.2) | Small RCBC (upto 1200x1200) = +8/-5, Large RCBC (upto 2400x2400) = +8/-5
5f6abefd-1c3d-56b7-8f14-130ea1c61e44 | radio | Criteria: Does above measured thicknesses fall within the given tolerance above? | Yes,No
2f0b051a-4391-5861-9a94-09ff45d58e50 | note | If No, please provide in comment (which is/are outside of tolerance)
| checkpoint | Cover
594e99da-685f-57a3-b233-78cd4633cae2 | radio | Method Of Test | Direct, Indirect
74a03bb3-415e-517d-b2e2-c238c3b1064f | number | Specified Cover Internal (mm)
11db3d22-365a-5079-97cf-3e5a249c2b8c | number | Specified Cover External (mm)
83d6dd0e-5971-5ec9-98b6-8db587d09fab | number | Measured Internal Left Leg Top (mm)
2b983047-a51c-5972-85fe-8fb342932396 | number | Measured Internal Left Leg Bottom (mm)
f3aac641-82fe-54de-adcd-c5cf73d95438 | number | Measured External Left Leg Top (mm)
28654838-6542-5ace-840e-86596316de8c | number | Measured External Left Leg Bottom (mm)
b2e86153-a1c5-5e9f-bd36-938a9e0bc264 | number | Measured Internal Right Leg Top (mm)
2d02d164-817c-51a8-bfca-2913febea336 | number | Measured Internal Right Leg Bottom (mm)
cfd7fcb9-9d6e-56a6-b959-b9496b2cf197 | number | Measured External Right Leg Top (mm)
72b2c6d1-6b77-5bca-b300-3c75941a623c | number | Measured External Right Leg Bottom (mm)
752b516d-844c-581d-be3e-bc6a7a0f7363 | number | Measured Left Side Internal Crown (mm)
7b74f5c1-3e2a-5fc2-8011-68941e043941 | number | Measured Middle in Internal Crown (mm)
d2f69ba4-e33b-55fe-afb7-dd920a754365 | number | Measured Right Side Internal Crown (mm)
4651a581-afab-5cdd-9843-af5e4058884d | number | Measured Left Side External Crown (mm)
3deecf01-dd96-562e-8fef-1ab3503fdee1 | number | Measured Middle in External Crown (mm)
0108a2ef-5ec6-5f41-a496-b592d983b3b3 | number | Measured Right Side External Crown (mm)
f1e6f19d-7704-5f40-8498-37f1def65b5d | note | The following measurements are only applicable to Uni-Culvert.
c66b5dcc-ee4f-57e2-b195-30c19a3b1c23 | number | Measured Left Side Internal Base(mm)
52bf108c-966b-5911-b334-9d86f661d9a9 | number | Measured Middle in Internal Base(mm)
fcd40041-248e-547a-b6f9-04b036281897 | number | Measured Right Side Internal Base (mm)
928b7911-c4da-541d-84bc-81fe7e0027d5 | number | Measured Left Side External Base (mm)
f4017831-eb54-5dca-9bbe-608738d51200 | number | Measured Middle in External Base(mm)
5d85359f-c22c-573f-9dda-21108e137d08 | number | Measured Right Side External Base (mm)
432b0867-dcf0-5321-9177-b860b7ec1ee4 | dropdown | Tolerances (accordance with AS1597.1 & 2 cl.2.10.2) | Small RCBC (upto 1200x1200) = +10/-5, Large RCBC (upto 2400x2400) = +10/-5
fc1f3fe3-e9a3-598e-a5f5-3486eb7b1714 | radio | Criteria: Does above measured covers fall within the given tolerance above? | Yes,No
959fb3d3-3c59-5f94-bcd5-a3dce3b13854 | note | If No, please provide in comment (which is/are outside of tolerance)
| checkpoint | Shape
b2d3bf35-fef9-5d17-9850-7d33c7581b9a | number | Measured Front End Face (mm)
1e1be74b-bf5d-5d63-aec9-84b6ef566acc | number | Measured Back End Face (mm)
5d356b54-6e63-536c-ac49-6365fbd2f8a6 | dropdown | Tolerances (accordance with AS1597.1 & 2 cl.2.10.2) | Small RCBC (upto 1200x1200) = N/A, Large RCBC (upto 2400x2400) = ± 4
cd75523b-8430-5dd8-9993-29de273c0b1d | radio | Criteria: Does above measured shape within the given tolerance above? | Yes,No
05b4baa5-f511-5e01-ae49-e36faeabca9d | note | If No, please provide in comment (difference in both measurements)
1fe80c34-2fe3-5bb0-a273-d64433c1012e | number | Measured Vertical at Front (mm)
d526e916-7609-5dd9-a245-ec91887c1a3b | number | Measured Vertical at Back (mm)
bd529ecf-7195-58c7-b7db-b93607f2e117 | number | Measured Variations (Vertical Front-Vertical Back) (mm)
148df401-8e65-579c-8ef8-7d69aeecf3fe | dropdown | Tolerances (accordance with AS1597.1 & 2 cl.2.10.2) | Small RCBC (upto 1200x1200) = N/A, Large RCBC (upto 2400x2400) = ± 20
8a3c2b4a-0095-5d4f-9cc3-d1ea77093542 | radio | Criteria: Does above measured shape within the given tolerance above? | Yes,No
733af5f7-f715-58f1-bd79-bd843df68347 | note | If No, please provide in comment (difference in both measurements)
| checkpoint | Squareness
ae2ae09c-054d-5656-bef1-cd8bfc42683e | number | Measured Left Leg Front Diagonals (mm)-1
c0122ba3-43e8-5252-b5a7-e91c1549db47 | number | Measured Left Leg Back Diagonals (mm)-2
e0b6e060-4ae9-5675-8e7d-ce8a7f6b4743 | number | Difference In Diagonals (mm) (1-2)
5a8242cb-f9be-5ce3-ac0b-ef58a72e2251 | number | Measured Right Leg Front Diagonals (mm)-1
0c7a9dbf-683c-5e28-8ff4-73cd1f0da830 | number | Measured Right Leg Back Diagonals (mm)-2
842e11eb-db6b-53c6-84b7-355ee5847a82 | number | Difference In Diagonals (mm) (1-2)
f11c4001-b310-57e6-a575-721e84bb7619 | number | Measured Crown Front Diagonals (mm)-1
c9de7d05-36d9-54f5-a2a1-c94bc7d2cba9 | number | Measured Crown Back Diagonals (mm)-2
2a6bf1d7-66e2-5db2-bc76-bcc79e933023 | number | Difference In Diagonals (mm) (1-2)
ca8accaf-01e8-5b11-b3c9-240245c614c6 | note | The following measurements are only applicable to Uni-Culvert.
c99e58b3-4367-5934-961b-04ca28c5ca12 | number | Measured Base Front Diagonals (mm)-1
730a7f92-08b7-5e6c-915d-20a8acd84b59 | number | Measured Base Back Diagonals (mm)-2
adc7fcf6-d3df-561b-a3aa-ab4ee7bd9a05 | number | Difference In Diagonals (mm) (1-2)
d2170a4d-0c81-52d4-8450-86fa391a7dbf | dropdown | Tolerances (accordance with AS1597.1 & 2 cl.2.10.2) | Small RCBC (upto 1200x1200) = N/A, Large RCBC (upto 2400x2400) = ± 20
7459e021-c35f-597e-882c-5f60a60cf232 | radio | Criteria: Does difference in diagonals above within the given tolerance? | Yes,No
4e44e835-e7ab-59df-9daa-8a13db32ce60 | note | If No, please provide in comment (which is/are outside of tolerance,ex: Legs,Crown)
| checkpoint | Test Result
e33c3737-a6b6-5572-b264-7119024d2adc | textbox | Tested By:
2c76187a-d927-4366-8d69-813922de5ba1 | checklist | Detailed ITP |  | Detailed ITP | d425d2f5-1dc5-4e73-9584-ca94eeba9c0b
6a8062f8-b8f0-4ef7-a58b-3b4f83d7b727 | section | Pre Pour
76e0627b-bc84-47f3-a0cc-6e29b0399663 | checkpoint | Sign off by client
474c8462-ae9d-4303-bf95-945f8676e39d | checkpoint | Surface clean, secured & release agent applied
86e47734-ed99-4fe2-b8fa-2d4f64c241c7 | checkpoint | Dimensions as per shop drawing
e3d92650-4ce8-4ca3-879f-3a0b2d4ac7f2 | checkpoint | Reinforcement installed as per drawing
5ecfdcc3-8f1c-45b9-a842-4372273d3fb4 | checkpoint | Cover confirmed as specified
f4a05f36-b707-4559-a7c3-2ecd6d894f1c | checkpoint | Reinforcement secured
1161f59e-49a3-4a3d-865d-dea593f0070d | checkpoint | Pins in correct position
3923c4e9-afb9-4b5f-9e8a-deaa69a68a11 | checkpoint | Former & pin secured
471cd51e-06ff-4205-9532-a98057ad814c | checkpoint | Correct pin rating & length
7eb1e142-8e10-4243-832d-315c8539bfeb | checkpoint | Blockout correct diameter & position
1e33abdc-2394-44f1-98f6-40f5ee0fdceb | checkpoint | Approved mix & supplier as required
94205ee3-119c-4e0d-bfd2-48b02d5c3c0c | section | Post Pour
3d8d5615-52cb-482f-91bc-12b98b715b29 | checkpoint | Date of pour
5d2f9051-7373-53f9-b9e7-c4e843bf0753 | textbox | Test Conducted
461c7cf5-06f0-56df-80a3-cfb1a652c0c2 | textbox | Time of pour
4df074e4-0466-48bf-bd3b-e7e05cca3033 | checkpoint | Curing commenced
b8042587-b7a3-5469-8d4b-4f5968417626 | textbox | Date
3f1e17aa-2cd9-597e-b376-4265b22f7c3c | textbox | Time
4a4d686f-733c-4a23-b0b5-c6ffa5435e26 | checkpoint | Pins in correct position
66a3f4d5-5038-4cae-ad78-8431d2df2803 | checkpoint | Curing complete
1b8b2e04-6eaa-589b-a152-5756db197301 | textbox | Date
a0c57388-b6b8-5b79-b69b-abc89b5f40a9 | textbox | Time
72bc2e45-32d0-416f-b0c6-eb73f85c1e4d | checkpoint | Surfaces free from imperfections, crack & misalignments
5c9db4a3-1472-4895-8ab7-a98c8e8f6f86 | checkpoint | Dimensional accuracy checks as per drawing
1ec38270-f2f6-5678-ab05-7ff68a491c1a | note | Note: Should the product require defects rectification than a non conformance shall be completed & attached
e71c7fca-942b-465a-b163-5e83db62be18 | checkpoint | Unit cleared for delivery
4fe75ff7-f0c2-45bb-a8bc-144b6e5445a3 | checkpoint | Sign off by client
855767fb-e109-418b-8838-844993934dbc | checklist | Standard ITP |  | Standard ITP | 347135f7-bdf2-46d1-96f0-2b8bc6863c98
fe7b19c1-d2b3-40e8-938e-377085c88b7f | section | Details
60719beb-f236-462c-a387-d9204908d3d7 | checkpoint | Mould set up correctly and mould oil applied
35f4ff72-d5a4-4eeb-8965-a6976cabf2d2 | checkpoint | Lifting pins correct & in place
c28de908-12f5-44f5-86ce-dbac9f84f633 | checkpoint | Reinforcement correct & secure
58e895f7-6971-41a0-814a-2033cdd72ce8 | checkpoint | Inserts or blockouts checked
77d2ae6f-3978-4048-8740-222a0654553d | checkpoint | Cover to reo checked
f2d9203b-9eb3-4eb4-a340-2ef2157e7a8c | checkpoint | Confirm approved to Pour
991c7731-cc45-4e4c-bc67-eed2c6ec9a46 | checkpoint | Stripped ok, no cracking or chipping
8cee83c9-4960-4ee0-9b53-c6ef53b6e472 | checkpoint | Lifting pins sound, unit labelled
da4a2fa8-4388-4840-a3b5-6f08bf947e14 | checkpoint | Cleared for delivery
| checklist | ULTIMATE & PROOF LOAD TESTING (BASE) |  | ULTIMATE & PROOF LOAD TESTING (BASE) | ab5d59ea-c02a-4ae4-af08-c6f386316472
| section | Vertical Load Test
| checkpoint | Vertical Load Test:
1abbb91b-211a-5aae-b7d6-280a2b23e224 | dropdown | Sample Type | DN1050 x 600 BASE UNIT,DN1050 x 900 BASE UNIT, DN1200 x 600 BASE UNIT,DN1200 x 900 BASE UNIT,DN1200 x 1200 BASE UNIT,DN1200 x 1500 BASE UNIT,DN1500 x 600 BASE UNIT,DN1500 x 900 BASE UNIT,DN1500 x 1200 BASE UNIT,DN1500 x 1500 BASE UNIT
f5c5a735-787e-5b6b-a3aa-16fd5187bdf4 | dropdown | HCP Concrete Mix Design Code | 980,880,680,VT Pipe (Dry Mix)
13fe059a-656e-53cb-97a0-493f74976899 | date | Date of Pour
6b391890-0b67-588f-b0db-54e1c74e0e41 | date | Date of Test
4ea8f66a-1766-5883-8056-10349e98e066 | textbox | Time of Test
| checkpoint | All testing Apparatus Arranged As Per AS 4198 Appendix-C
023cb081-9cfc-5ffe-8ec6-b33aaf543031 | radio | Any Crack Presence Before Proof Load or Any Major Defects | Yes, No
6f189b92-7d68-500d-bb05-8c81864d0b58 | note | If Yes, Provide numbers and widths of crack or any other details
| checkpoint-no-value | Evidence Before Test
| checkpoint | Proof Load Test
c1534c46-0565-5999-8bda-cd35e2df0261 | dropdown | Required Apply Load (KN) as per AS4198 Table 3.2.2 | DN≤1200 P=112, DN>1200 P= 112& 2x81
82379266-034c-5097-81f9-0f54af7233d7 | number | Applied Load (KN)
2eda38fd-d6c9-5270-a857-ba16ab81b2ac | radio | Any Crack Observed when component loaded | Yes, No
8ef01f4b-8db5-59d0-86f4-bf64ac64b834 | number | Crack width (mm), if yes
7ede33cb-f9c5-55bb-9c62-c5556c4a067d | radio | Any Crack Observed after load removed | Yes, No
40e56f0c-972d-566b-bbd0-818eec16e089 | number | Crack width (mm), if yes
| checkpoint | Ultimate Load Test
b9b1f0f5-8ba4-5dcf-a019-46970bd2b2ca | dropdown | Required Apply Load (KN) as per AS4198 Table 3.2.2 | DN≤1200 U=210, DN>1200 P= 210& 2x146
84f47c58-ff5a-5d03-b649-da4562bc6a49 | number | Applied Load (KN)
1b7aba45-7fd9-5272-afef-f5c49b933e1f | radio | Applied load sustained 60 Sec. without loss of load | Yes, No
1010147f-f7e7-5046-a606-b5ed5f746c1e | number | If No, Load (KN) at which failure occurred
| checkpoint-no-value | Evidence After Test
1003395d-4db3-54ac-8727-ecc525c56a57 | radio | Any Crack Observed after load removed | Yes, No
534c7066-e66b-5169-9335-315529bfd3f7 | number | Crack width (mm), if yes
e80f56e5-c91f-5df4-8eb5-8b9a854e3ead | radio | Does this test method comply with AS4198, Appendix C | Yes, No
e6ccf531-8b4e-5f05-817f-ea63a71cdcac | note | If No, Reason and Short Description
06df14d4-b243-546f-ba8f-8b20b10abaeb | textbox | Tested By:
| checklist | ULTIMATE & PROOF LOAD TESTING (SHAFT) |  | ULTIMATE & PROOF LOAD TESTING (SHAFT) | bf842c5f-eeff-4762-a241-2dddd32a4ea5
| section | Vertical Load Test
| checkpoint | Vertical Load Test:
54f1ee88-be36-571f-a3ec-95ffceddc764 | dropdown | Sample Type | DN1050 x 300 SHAFT UNIT,DN1050 x 600 SHAFT UNIT, DN1050 x 900 SHAFT UNIT,DN1050 x 1200 SHAFT UNIT,DN1050 x 1500 SHAFT UNIT,DN1200 x 300 SHAFT UNIT,DN1200 x 600 SHAFT UNIT,DN1200 x 900 SHAFT UNIT,DN1200 x 1200 SHAFT UNIT,DN1200 x 1500 SHAFT UNIT, DN1500 x 300 SHAFT UNIT,DN1500 x 600 SHAFT UNIT,DN1500 x 900 SHAFT UNIT,DN1500 x 1200 SHAFT UNIT,DN1500 x 1500 SHAFT UNIT
a7a5efee-2a85-5849-85b4-171ff179bf24 | dropdown | HCP Concrete Mix Design Code | 980,880,680,VT Pipe (Dry Mix)
0c9a4377-57d0-5688-b514-897d224c6a08 | date | Date of Pour
7a16d653-4c18-5a97-934f-341f72626a8f | date | Date of Test
b57f9ec6-ddc9-59e2-8598-5bf7271ab773 | textbox | Time of Test
| checkpoint | All testing Apparatus Arranged As Per AS 4198 Appendix-C
936a3fe1-cc5a-5136-9ae2-47106bf13846 | radio | Any Crack Presence Before Proof Load or Any Major Defects | Yes, No
4ac734a5-d986-5478-997f-da4cb8fc751a | note | If Yes, Provide numbers and widths of crack or any other details
| checkpoint-no-value | Evidence Before Test
| checkpoint | Proof Load Test
c94f90ff-0e85-5471-9f6e-a90dffd9641a | dropdown | Required Apply Load (KN) as per AS4198 Table 3.2.2 | DN≤1200 P=112, DN>1200 P= 112& 2x81
f2e30bde-3359-5f71-acf5-ce71dff9d00c | number | Applied Load (KN)
2fadbc11-04a1-5644-a5b4-760a0942bc46 | radio | Any Crack Observed when component loaded | Yes, No
9266164a-99ce-5fef-880d-26c79a20a59a | number | Crack width (mm), if yes
d3c7560a-52be-5e71-a6db-c767b34d61e8 | radio | Any Crack Observed after load removed | Yes, No
9288d797-8562-59e1-8cbd-60e4ab00b53a | number | Crack width (mm), if yes
| checkpoint | Ultimate Load Test
39a453c1-dcf8-5568-b792-675960b6074e | dropdown | Required Apply Load (KN) as per AS4198 Table 3.2.2 | DN≤1200 U=210, DN>1200 P= 210& 2x146
563c2d0a-89aa-59fb-a50a-52ca40bac9c5 | number | Applied Load (KN)
22a00102-fd9b-5f13-b3ea-f6311c93116e | radio | Applied load sustained 60 Sec. without loss of load | Yes, No
6ecd0700-97cc-5c78-9a71-6b8e76754265 | number | If No, Load (KN) at which failure occurred
| checkpoint-no-value | Evidence After Test
75468793-2a14-55f1-88e6-c705f2e3bd58 | radio | Any Crack Observed after load removed | Yes, No
fb5fba53-477b-5d37-9316-9bb93e562255 | number | Crack width (mm), if yes
9af5f9e0-0121-5bc6-b1f0-a37f0e772ee6 | radio | Does this test method comply with AS4198, Appendix C | Yes, No
678b3dbb-e12c-5202-a6c0-9d22c2daea70 | note | If No, Reason and Short Description
c447141b-95bc-5ac8-8ab9-07b5a159e3f4 | textbox | Tested By:
| section | Horizontal Load Test
| checkpoint-no-value | Horizontal Load Test:
7aa19dc2-610f-54dc-a4ff-930c47b2b0aa | dropdown | Sample Type | DN600 SHAFT UNIT, DN900 SHAFT UNIT, DN1050 SHAFT UNIT, DN1200 SHAFT UNIT, DN1500 SHAFT UNIT
05be5036-7844-5596-a364-b85128e0a2f7 | dropdown | HCP Concrete Mix Design Code | 980,880,680,VT Pipe (Dry Mix)
5f5a2bd8-dd06-59d5-8db7-4c27affb734b | date | Date of Pour
5cfae2e7-42fd-5db1-810d-06ecb25d32ea | date | Date of Test
9b567e6c-eb0d-5d47-8428-c246c079f773 | textbox | Time of Test
| checkpoint | All testing Apparatus Arranged As Per AS 4198 Appendix-C
4f7dc504-1ee5-5fb5-adcf-4492a37f2af2 | radio | Any Crack Presence Before Proof Load or Any Major Defects | Yes, No
3ba46dcd-85f4-52cf-a91e-810285384564 | note | If Yes, Provide numbers and widths of crack or any other details
| checkpoint-no-value | Evidence Before Test
| checkpoint | Proof Load Test
91db3256-0a71-569c-b749-367de8566bca | dropdown | Size/ Required Loads to Applied (KN/m) (AS per AS 4198 Table 3.2.3) | DN600 P=23,DN900 P=20,DN1050 P=19,DN1200 P=19,DN1500 P=20,DN1800 P=22
84a1d1ec-465e-5c89-9ea1-346260c45b11 | number | Applied Load (KN)
0d8b7be1-dcd2-5984-a9ec-daac3741d044 | radio | Any Crack Observed when component loaded | Yes, No
5ade380c-729c-5c40-a950-ca3103202e54 | number | Crack width (mm), if yes
f38086c9-0d3d-5b81-b9c8-2cb43ee9e093 | radio | Any Crack Observed after load removed | Yes, No
b80e71f0-5dde-54fa-b7b5-69bf719b900e | number | Crack width (mm), if yes
| checkpoint | Ultimate Load Test
124eed73-9004-53db-88a3-579396c0db53 | dropdown | Size/ Required Loads to Applied (KN/m) (AS per AS 4198 Table 3.2.3) | DN600 U=35,DN900 U=30,DN1050 U=29,DN1200 U=29,DN1500 U=30,DN1800 U=33
94239591-44f6-57f1-a857-315fe971c550 | number | Applied Load (KN)
05cc99ea-8f49-55ef-bee1-348a2d2282ce | radio | Applied load sustained 60 Sec. without loss of load | Yes, No
0ea21b15-82f5-56d2-bdc7-76f2b36a98fc | number | If No, Load (KN) at which failure occurred
| checkpoint-no-value | Evidence After Test
5bf14195-e67e-5ef9-9ee0-d4c0d419e19f | radio | Any Crack Observed after load removed | Yes, No
0aec64c2-e9a0-5b37-810d-1c92034c4973 | number | Crack width (mm), if yes
351673a1-079c-5be9-818f-5fdd8993b685 | radio | Does this test method comply with relevent sections of AS4198 & AS4058 | Yes, No
99c524f8-2359-5325-9ce2-b527855b5ce4 | note | If No, Reason and Short Description
14264caa-22ff-5b6f-bae8-078462048ec9 | textbox | Tested By:
| checklist | ULTIMATE & PROOF LOAD TESTING (SURROUNDS) |  | ULTIMATE & PROOF LOAD TESTING (SURROUNDS) | c84a9501-1555-47e7-ab71-3e55e1f6acdf
| section | Vertical Load Test
| checkpoint | Vertical Load Test:
1f994698-799c-5583-a0e2-cadbcb2151f8 | dropdown | Sample Type | 750 mm Surround L/D,750 mm Surround H/D,1395 mm Surround C/O L/D,1390 mm Surround Offset L/D,1390 mm Surround Offset H/D,DN1500 Class B M/H Offset Surround,DN1500 Class D Offset Surround,DN1500 Class B Circular C/O,DN1500 Class D Circular C/O,DN1500 Class B Square C/O,DN1500 Class D Square C/O
3624bce8-8549-5d76-a0af-860d2dbb9f32 | dropdown | HCP Concrete Mix Design Code | 980,880,680,VT Pipe (Dry Mix)
e1a9b5a5-23a8-5f86-9370-0dcfd5a54c52 | date | Date of Pour
77806250-df56-5bc4-8152-0d8044ecc27d | date | Date of Test
676beebd-9739-5d71-baa4-9e0e3d1d7fcf | textbox | Time of Test
| checkpoint | All testing Apparatus Arranged As Per AS 4198 Appendix-C
6ee0f8e7-b3a7-56c4-86ca-ada8d4c782c1 | radio | Any Crack Presence Before Proof Load or Any Major Defects | Yes, No
ce6e4ab5-8dd5-5b04-afa1-3f00f92d37c5 | note | If Yes, Provide numbers and widths of crack or any other details
| checkpoint-no-value | Evidence Before Test
| checkpoint | Proof Load Test
dcb1086e-5143-507f-ae09-a3208df33cd4 | dropdown | Required Apply Load (KN) as per AS4198 Table 3.2.2 | DN≤1200 P=112, DN>1200 P= 112& 2x81
366386f9-c140-5f22-b3a1-4f1fe8bef966 | number | Applied Load (KN)
8b162c5e-1f41-5dd0-b17d-41f8a4be48fd | radio | Any Crack Observed when component loaded | Yes, No
3af9da6e-ad41-5eee-915b-8853c892db4a | number | Crack width (mm), if yes
ffba999a-9bd9-5b54-b19c-e50ad11f8ab1 | radio | Any Crack Observed after load removed | Yes, No
cee1a303-b823-5655-ba7a-c793156d6295 | number | Crack width (mm), if yes
| checkpoint | Ultimate Load Test
9b1859d5-55b7-5896-b38c-440e4ea1bf97 | dropdown | Required Apply Load (KN) as per AS4198 Table 3.2.2 | DN≤1200 U=210, DN>1200 P= 210& 2x146
1b668072-c17f-564f-b56e-8e0150695d04 | number | Applied Load (KN)
2e29af02-8a95-50bd-950a-514096c854c0 | radio | Applied load sustained 60 Sec. without loss of load | Yes, No
b1ed9443-72a1-54f1-974a-4d0015a2f238 | number | If No, Load (KN) at which failure occurred
| checkpoint-no-value | Evidence After Test
1dc99b7a-ecca-5e47-b06b-114771df45db | radio | Any Crack Observed after load removed | Yes, No
967ff964-e946-50fe-85d7-bec66968ecea | number | Crack width (mm), if yes
71f3b1d2-0d2f-5383-95a8-5c830da5a587 | radio | Does this test method comply with AS4198, Appendix C | Yes, No
65a3c08d-fc6e-5310-b369-24bf2f5b8bc3 | note | If No, Reason and Short Description
04302e26-c620-53fd-80c5-58b7602560ba | textbox | Tested By:
| checklist | VACUUM TEST (ASSEMBLY) |  | VACUUM TEST (ASSEMBLY) | 031702f1-4468-4046-b5a2-f254b473f6e3
| section | Vacuum Test
| checkpoint | Vacuum Test:
cb1df39e-735c-51dc-8480-905423b174af | dropdown | Type of Base Unit- At Bottom | DN1050 x 600 BASE UNIT,DN1050 x 900 BASE UNIT, DN1200 x 600 BASE UNIT,DN1200 x 900 BASE UNIT,DN1200 x 1200 BASE UNIT,DN1200 x 1500 BASE UNIT,DN1500 x 600 BASE UNIT,DN1500 x 900 BASE UNIT,DN1500 x 1200 BASE UNIT,DN1500 x 1500 BASE UNIT
5f1daed3-e1de-5b11-a346-17b245adc572 | dropdown | Type of Shaft Unit- At Bottom or At Top (Optional) | DN1050 x 300 SHAFT UNIT,DN1050 x 600 SHAFT UNIT, DN1050 x 900 SHAFT UNIT,DN1050 x 1200 SHAFT UNIT,DN1050 x 1500 SHAFT UNIT,DN1200 x 300 SHAFT UNIT,DN1200 x 600 SHAFT UNIT,DN1200 x 900 SHAFT UNIT,DN1200 x 1200 SHAFT UNIT,DN1200 x 1500 SHAFT UNIT, DN1500 x 300 SHAFT UNIT,DN1500 x 600 SHAFT UNIT,DN1500 x 900 SHAFT UNIT,DN1500 x 1200 SHAFT UNIT,DN1500 x 1500 SHAFT UNIT
3625d270-e797-5af8-9965-c247c1144601 | dropdown | Type of Shaft Unit- At Top | DN1050 x 300 SHAFT UNIT,DN1050 x 600 SHAFT UNIT, DN1050 x 900 SHAFT UNIT,DN1050 x 1200 SHAFT UNIT,DN1050 x 1500 SHAFT UNIT,DN1200 x 300 SHAFT UNIT,DN1200 x 600 SHAFT UNIT,DN1200 x 900 SHAFT UNIT,DN1200 x 1200 SHAFT UNIT,DN1200 x 1500 SHAFT UNIT, DN1500 x 300 SHAFT UNIT,DN1500 x 600 SHAFT UNIT,DN1500 x 900 SHAFT UNIT,DN1500 x 1200 SHAFT UNIT,DN1500 x 1500 SHAFT UNIT
ccbe1ef9-519e-5d74-acdd-534d1b7ce8d6 | dropdown | HCP Concrete Mix Design Code (Base Unit) | 980,880,680,VT Pipe (Dry Mix)
a06f47bd-5d37-54d9-999f-4aa3ab091064 | dropdown | HCP Concrete Mix Design Code (Shaft Unit) | 980,880,680,VT Pipe (Dry Mix)
37c72430-2a81-5848-a980-ca8fc503b370 | date | Date of Pour-Shaft unit
aedfc3bc-2908-5063-9c32-3a066c1e188a | date | Date of Pour-Base unit
103a3166-0e44-5c90-ab26-318e83f75bdb | date | Date of Test
40f298f5-f7bf-5da2-bb6a-4465ec30a365 | textbox | Time of Test
| checkpoint | All testing Apparatus Arranged As Per AS 4198 Appendix-K
5ed462db-cc81-5a80-9018-410612182cac | radio | Any Crack Presence Before Proof Load or Any Major Defects | Yes, No
382303ba-f75e-55dc-8f62-c252f75ae8f2 | note | If Yes, Provide numbers and widths of crack or any other details
| checkpoint-no-value | Test Arrangement Photos Before Test
a270b4c5-385b-51a1-a8e3-c6f32df534ac | button | Required to Build Vacuum Pressure as per AS4198 K4.1 | 35 kPa,Other
f52fdfce-e3c5-5579-9138-bab4b693ba77 | button | Any Change in Pressure After 3.0 Minutes | Yes, No
58b0a1c7-cae4-5182-acbc-4034e088a72a | note | If yes, How much Pressure Drop (kPa) Observed?
6bc6e47f-d63b-57b5-b976-82e1f1226c31 | dropdown | Has Pressure Drop more than 5kPa after 3.0 minutes? | Yes, No, N/A
ed9804e1-18e7-514b-866c-1eab4b5497c7 | dropdown | Has Assembly Been Retested? | Yes, No, N/A
| checkpoint | Results of Test In case of Retest.
05d33f0b-4b1d-58c1-99fc-147b3b0bb0ae | radio | Does this test method comply with AS4198, Appendix-K | Yes, No
063ae9b6-5c87-553b-9956-a56e5c783283 | note | If No, Reason and Short Description
| checkpoint | Test Result
4e41b6f3-9187-550f-a013-f0608d7008b5 | textbox | Tested By:
| checklist | WATER ABSORPTION & COMPRESSIVE STENGTH TESTS |  | WATER ABSORPTION & COMPRESSIVE STRENGTH TESTS | 97cd8066-1481-457c-a62a-6d60962ec8f1
| section | Water Absorption Test
| checkpoint | Water Absorption Test:
2834ddcb-3b79-5217-8dd8-7c8888b38546 | dropdown | Description of Component Test | DN1050 x 600 BASE UNIT,DN1050 x 900 BASE UNIT, DN1200 x 600 BASE UNIT,DN1200 x 900 BASE UNIT,DN1200 x 1200 BASE UNIT,DN1200 x 1500 BASE UNIT,DN1500 x 600 BASE UNIT,DN1500 x 900 BASE UNIT,DN1500 x 1200 BASE UNIT,DN1500 x 1500 BASE UNIT,DN1050 x 300 SHAFT UNIT,DN1050 x 600 SHAFT UNIT, DN1050 x 900 SHAFT UNIT,DN1050 x 1200 SHAFT UNIT,DN1050 x 1500 SHAFT UNIT,DN1200 x 300 SHAFT UNIT,DN1200 x 600 SHAFT UNIT,DN1200 x 900 SHAFT UNIT,DN1200 x 1200
ee49f6f5-e9b4-5dc7-992c-ccfff1b160e8 | dropdown | Concrete Mix design Code | 980,880,680,VT Pipe (Dry Mix)
f31bac63-1d91-5426-a753-175cd6ad0078 | radio | Method of Manufacture | Machine-Made Process,Standard Wet Cast Process, Automated SCC Cast Process
6deeba0f-c61f-5667-8972-29e45b791aa3 | radio | Curing Method | Moist Curing, Membrane Curing, Accelerated Curing
4005e80c-9c5b-5b26-9201-67dd8d141c5e | date | Date of Product Cast
c954eae1-9293-5367-97c9-68a415d5fc80 | date | Date of Core Sample | 980,880,680,VT Pipe (Dry Mix)
c671e2b8-3836-5c89-85d4-972d60a20bbd | date | Date of Test Started
b2deb60f-b8ac-5295-975b-35e8045213ac | date | Date of Test Finished
c6975b5e-857b-5ffa-869a-554656a6d834 | radio | Types Of Test | Type test, Routine Test
| checkpoint-no-value | Mass M1
| checkpoint-no-value | Mass M2
| checkpoint-no-value | Mass M3
| checkpoint-no-value | Mass M4
2b2cfe94-629b-5d63-8e52-0d125481717e | dropdown | Maximum Allowable Percentage Absorption As Per AS 4198 Table 2.4.5 | 6.0,5.5,5.0
39b2833c-ec88-520d-8f19-42166c5288cc | note | Percentage Absorption
791a8a48-8316-5b41-a99d-84ee502dbfe6 | dropdown | Maximum Allowable Percentage Absorption As Per AS 4198 Table 2.4.5 | 5.5,5.0,4.5
0d8ec3dd-264f-56f3-99cc-b1a3ce68decd | note | Net Absorption
917271ff-dc8f-588c-8989-3a5717fcbf4e | radio | Water Absorption Test Of Cored Specimen | Pass,Fail
aa3088e2-9785-5be0-b747-37164b7767ab | note | If Fail, Please provide details
a90781ba-a4ac-5b08-ac62-4f98a077781f | textbox | Tested By:
| section | Compressive Strength Test
| checkpoint | Compressive Strength Test:
27f853ef-78cb-58b8-87a1-7b736842687e | dropdown | Concrete Mix design Code | 980,880,680,VT Pipe (Dry Mix),VR450/50 SCC
| checkpoint | Compressive Strength test (Upload Test Report)
16e25460-d202-5fe5-a1f1-defcada45862 | textbox | Tested By: