## Checklist Templates
Id | Type | Name | Values | Prompting Name
8a5d09f1-38a2-450b-8a57-454e1adde0ee | checklist | Final Installation Checklist |  | Final Installation Checklist
c34f120e-fb0c-43c8-8cdc-bb8a10ed9922 | checkpoint | Fit Off documentation reviewed and circuits ready for testing
a3775bc0-040f-450b-82c8-ae6a720803b4 | signoff | Add Signature / Request Sign Off
c790b33b-d7c1-4ccf-9681-2860a97c7b3b | checklist | QA_TEM_003_Earth Electrode |  | QA_TEM_003_Earth Electrode
755077da-36d6-40eb-818f-71282f118cb6 | checkpoint | Record electrode type and size (AS/NZS 3000 Table 5.2)
a1cb0ccc-d83b-5161-80e2-71c501212ec2 | textbox | Material
f6839b47-984e-5b03-9971-938c7c45e2d5 | textbox | Diameter
eff7fe58-bc8a-457f-a49c-35ad08b822b8 | checkpoint | Earth electrode is driven to the minimum depth (AS/NZS 3000 5.3.6.3)
a42106cf-44e7-5be0-be4e-21681f3b458f | tickbox | Vertical type - 1.2 metres
19441990-911e-5942-a4bc-f07190ae27a7 | tickbox | Strip type - 3 metres
36025092-8c98-4c9c-97a3-d7acee61dad0 | checkpoint | Earth electrode is installed in a correct location (AS/NZS 3000 5.3.6.4)
cd183679-30f3-5c78-9389-fd893b5ef494 | note | External to the building in ground that is exposed to the weather
81d5f693-5edc-52d3-b826-a9a3eaaf77be | note | Separated from conductive enclosures of other buried services
3c5ce98e-6fad-5c6b-8114-ecd5b497022d | note | Is in an accessible location
f8f5991c-5411-4e9b-9a40-488dc41f2835 | checkpoint | Earth electrode is mechanically protected and labelled in accordance with AS/NZS 3000 5.5.1.3
15985882-5cb5-5173-9c9d-e3924f778c6b | note | WARNING MAIN ELECTRICAL EARTHING CONDUCTOR—DO NOT DISCONNECT
0452aa58-b834-4e52-83cd-2588a6bd0de4 | checkpoint | Earth connection point to stake is protected from corrosion (i.e. painted earth clamp) (AS/NZS 3000 5.5.5.3)
ec763e54-4c11-4768-963b-78af8400d303 | checkpoint | Location of the earth electrode has been identified at the main switchboard.
d0baabf1-82ed-4383-8a15-e36bfd76ef68 | checkpoint | If measurement of the resistance of the earth electrode is requested, refer to the test procedure detailed in AS/NZS 3017 clause 3.8.
df8f761a-832f-44fa-a2c0-1385342d5e38 | checklist | QA_TEM_004_Trench and Backfill |  | QA_TEM_004_Trench and Backfill
e77583d3-f61c-43af-935b-0db64de19f39 | checkpoint | Prior to excavation:
6ba3cba5-7e62-5e10-bcb6-5c514574f874 | textbox | Stage / Section location
93fd684f-dc57-553f-8966-5b9f19fab77e | tickbox | Mark out route as per electrical services drawings
fd6ab775-964e-5428-af40-20ad7c1defd4 | tickbox | Potholing/Service Locations - mark-up all documentation identifying any service clashes. Co-ordinate with other trades i.e. civil, hydraulic, comms Route and dimensions agreed with Principal Contractor
61288be8-5735-4352-b24c-c7e3cfd0fc43 | checkpoint | Obtain excavation permit from Principal Contractor
e04e0555-9dc2-40a9-b64b-e5a41c66fdfb | signoff | Hold Point - All above must be completed before further works proceed
87bcd322-5784-4af2-8e3f-3d2b141e6791 | checkpoint | During excavation:
8b3a33fd-2673-53f3-845e-5112b789f03e | tickbox | Confirm signs / safety barriers in place
bbc80c25-6b04-5186-adbf-49c318a97376 | tickbox | Confirm trenching is correct - Size / Alignment / Depth (Use Datum Points)
585b7281-293e-440c-9f8d-aa2a4333c6f8 | checkpoint | Prior to backfilling:
e89bb9b2-5289-5c10-9b05-32adf76777c8 | note | Confirm the completion of QA_TEM_005_Underground Conduit Installation has not raised any non-conformances
9f4f6384-dd2f-59a6-a61d-162bf9dd9e0e | note | Confirm suitability of proposed backfill
0e3118b1-f9af-5c94-a169-e8a8b2f111d4 | note | Check compaction and frequency requirements
723cbeb8-ae89-597b-b62d-6cefb1ce5d66 | note | Confirm layers being replaced i.e., geotextile fabric, road base, general fill
1d58f23a-f721-4fca-bc92-97b1cf796012 | signoff | Hold Point - All above must be completed before further works proceed
b97be3a3-71c0-4ac3-b223-312f767be917 | checkpoint | During and after backfilling, check that:
6c354798-25a4-598e-a2f8-88d95cd6e5e0 | tickbox | Cable marker tape is correct (Type & Depth)
fd4c6b89-73c3-59fe-9ca0-d9dc474456f2 | tickbox | Survey points for as built documentation has been completed
60a422a2-ca2f-5acc-81cf-f4d9f0194108 | tickbox | Route markers installed
e9b349c1-08d2-55e2-bc6e-efb7d733f8c4 | tickbox | Compaction is correct - refer to specification
8892480e-a048-55e2-a404-6a51a4379596 | tickbox | Route markers are correct
81e9208f-2044-56e1-a2ca-3c1c853fdd48 | tickbox | Soil is properly removed
b2b7dc1a-146a-5658-86cb-5404fabcd66b | tickbox | Cable protection installed
37dfec50-9e72-437d-a6ac-f90da4cb8815 | checkpoint | On completion:
10724456-24f9-51ca-a0e0-915c67d553ee | tickbox | Layer clean fill
9b5d6ad0-acfe-5fc1-82aa-eeb8d8d3d753 | tickbox | Co-ordinate compaction tests as required with Principal Contractor
615d4b81-73b1-5959-88a1-3d8e5304a87e | tickbox | Surface reinstatement to agreed standard
6852e12d-87d2-4979-9975-196aa2e8513e | checklist | QA_TEM_005_Underground Conduit Installation |  | QA_TEM_005_Underground Conduit Installation
044191b6-999c-476c-a1e4-4f2f18959b66 | checkpoint | Conduits are the correct type, configuration, size, quantity split and fill out
8d9aaaaa-72a4-43ba-93e5-3e6a4a664e50 | checkpoint | Conduits are the correct depth & following the correct route
a511103b-9869-4bf6-a46b-9712a36564ec | checkpoint | Conduits are correctly joined
d898ffe5-888f-4ccc-bb27-9556fc34758a | checkpoint | Layer of clean fill
a8914f9b-a8e3-4a66-8cdb-9427a7f0c6a6 | checkpoint | Seal pit around conduits
e18e27c4-7b37-4459-9465-ff1a99d2c2a4 | checkpoint | As Built drawings completed
1898f9f3-2048-4d24-8ae8-4120f20ab208 | checkpoint | Cleaned rodded and roped
b72ee3fe-87db-484a-9938-4eb168577061 | checklist | QA_TEM_006_Surface Conduit Installation |  | QA_TEM_006_Surface Conduit Installation
e839778b-02a3-409a-8fb8-2cbcfd0354d6 | checkpoint | Conduits are the correct type
5b980931-1c05-48b2-83c9-754fc6b031a1 | checkpoint | Conduits are following the approved route as specified
b77b214c-ac74-4164-95bc-affefdbd7551 | checkpoint | Conduits are straight plumb/parallel
8558eab0-ea15-41d4-a363-c84fee7b936e | checkpoint | Conduits have sharp edges and burrs removed (steel)
4dc8f893-3d43-43d9-9e21-2d823052facb | checkpoint | Conduits have expansion joints installed where required
fbe44864-3709-488e-8c95-a2e4ddff0d18 | checkpoint | Conduits have specified support installed
a9527b93-8639-46be-a2e9-d6ff1aac5087 | checkpoint | Conduits have product branding cables removed or not visible
6d1be8e0-3876-4ec6-9ee1-40e6030cd48b | checkpoint | Conduits are sealed against water ingress where required
0c369358-f2ac-4a4c-858c-6445963b7bb2 | checkpoint | Conduits have equipment entries correctly sealed
2d201547-cf60-4efe-a40b-e4ea3c275cf9 | checklist | QA_TEM_007_Cast in Conduit Installation |  | QA_TEM_007_Cast in Conduit Installation
4b4ffd37-c84d-4120-8257-7061e1da0047 | checkpoint | Conduits are the correct type, size and quantity
63e40199-cd92-4460-9d1f-4a45af7be9e6 | checkpoint | Conduits are following the correct route
5774181d-7ec0-45d4-bed9-1e2516ed914f | checkpoint | Conduits are correctly joined
ab266b66-07bc-4f6c-b522-4115b297fb34 | checkpoint | Condutis are tied in
7906aa7d-6746-411b-a799-bee787bd61cd | checkpoint | Correct concrete cover installed
b8cdb154-9612-4a43-8639-839d6672633b | checklist | QA_TEM_008_Cable Support Prior to Cabling |  | QA_TEM_008_Cable Support Prior to Cabling
6eda5ebf-6f77-45ac-b7b5-390f3e9c6e84 | checkpoint | Cable support has correct origin and destination
b1496d36-4d9a-4308-9805-c60e00afd61b | checkpoint | Cable support follows correct route
b6c4755b-66cd-41b3-8e9d-9809c9d3ebed | checkpoint | Cable support is correct type material and not damaged
f2ac37fc-4e4b-4c09-a432-11c3f9a2bac2 | checkpoint | Cable support is correctly aligned
251aac9a-b110-4404-b457-5fa9a6e10777 | checkpoint | Cable support has correct type/quantity supports
79dc9a06-cdcf-41ab-a2ae-37d8991b61a2 | checkpoint | Cable support is attached securely to supports
055b8399-0452-4400-b769-ef7910f94416 | checkpoint | Cable support has correct type and size of fittings
c9478d0e-6edb-47cb-8d55-b4e040bf6a34 | checkpoint | Cable support is complete for the entirety of its length
4eedbf54-d9fd-4155-afdd-086a18c7b347 | checkpoint | Cable support has correct segregation
9c51c521-d72c-4e0e-b402-40ad6d0b38ea | checkpoint | Cable support is earthed correctly
08efeb1c-69e3-4cfd-bc98-a67fd8b32886 | checklist | QA_TEM_009_Cable Support Post Cabling |  | QA_TEM_009_Cable Support Post Cabling
e115bf2d-eecf-4c58-8f40-63396fd7b830 | checkpoint | Cable support is properly sealed at all penetrations
b367f96c-0afb-4f77-8258-f46a49305d7d | checkpoint | Cable support has divider strip if required
5e05fef8-d0e7-44f9-bea0-e603ab160597 | checkpoint | Cable support has cover fitted if required
89fd5baf-4468-4157-9594-9fe211c6477f | checkpoint | Cable support has correct segregation
7e6d620a-9502-4b29-af5a-8a9a54c5decd | checklist | QA_TEM_010_Final Sub Circuit Installation |  | QA_TEM_010_Final Sub Circuit Installation
67d21af6-d046-4be2-a6ff-220a88bfe52d | checkpoint | Cable has correct origin and destination
7f883a5f-d2d1-4dc8-b39a-3df3057c55a0 | checkpoint | Cable has correct number of cores
8adae2a1-6429-4316-8c3b-17e5e8f8e491 | checkpoint | Cable cores are of the correct cross sectional area
2bab1812-3191-4a1d-8ba4-d6597e48aab5 | checkpoint | Cable type and configuration is as specified
24baf0bd-e81d-4faf-a6fc-e8f7ac41bea4 | checkpoint | Cable follows the correct route
d6f4deb8-caa5-4f67-bd5e-6bbc665b8e4a | checkpoint | Cable meets minimum bending radius requirements
59a6a745-6bf5-4e56-bf8a-6c9e8c27f11f | checkpoint | Cable is clear of heat sources
ed8f196e-99ca-47b3-a91d-b6a59dc1ef23 | checkpoint | Cable is clear of electronic / signal cables
44923017-bfaf-4f2a-a734-9b3bb6de32d8 | checkpoint | Cable is secured as specified
2b78e8aa-1261-4ec7-b9d6-5f7a717bb97c | checkpoint | Cable is installed in a neat and orderly manner
ebbf9818-8c23-4147-a6c8-181b184041e6 | checkpoint | Cable is routed to minimise crossovers
b105636a-3dfd-4b6d-bd60-384c1dd865cf | checkpoint | Mechanical protection of cable is correct
7ec5de4f-71c9-446b-9c83-06e466dce595 | checkpoint | Cable is supported correctly
768a3394-172e-411a-b6b2-9b31e78fb03a | checkpoint | Cable is marked with cable or circuit number
4ca2d30a-a3c7-4666-bbca-bba01d8e257f | checkpoint | Cable has correct segregation
7ecfe0c8-684c-4e1e-8fc7-3e39dae6cd5d | checklist | QA_TEM_011_Mains & Submains Installation |  | QA_TEM_011_Mains & Submains Installation
576d0726-0660-4b60-8234-3ca74d663cde | checkpoint | Cable is in good condition and free from damage and defects
56df4bf8-32b0-4af5-840f-2a34cf50b890 | checkpoint | Cable has correct origin and destination
118f2c2c-c94a-5616-89c7-a0ca5bf1d8db | textbox | Origin
ccb4aeb5-a5ce-503b-a4ca-905a16672341 | textbox | Destination
edb4307d-e3d0-4400-93f5-ab82858a4266 | checkpoint | Cable Type, Number of Cores, Size and Configuration is as specified
169850f7-cc1d-5441-997a-2c76f536818f | textbox | Size (mm2)
c92d2734-382a-5285-9d29-4f9921cf0833 | textbox | Cores
beb98381-ec29-507d-8a51-7a0dcc116d66 | textbox | Cable Type
a06b031d-f30f-5e58-9f8e-1f1d849477e7 | textbox | Earth Size (mm2)
7e3e40a8-5d3d-5fca-b983-d6616bbf1fb2 | textbox | Cores
6ddf0c52-1bbd-5a4e-b1e1-bcaaf6f4a736 | textbox | Cable Type
c1939834-9b6a-4d56-aff3-3fc374d8df2d | checkpoint | Bending radius recommended by the cable manufacturer has been observed
1653f9b8-c81a-5b43-9007-fd71362cdddf | textbox | Bending Radius (mm)
bf5f3950-79bf-5e1e-a876-6361f8a8a1e0 | note | Where manufacturer’s information is not available, the following minimum internal radii may be considered suitable
e9e98c1c-dc25-58da-bc78-f2dcf4e28eef | note | Unarmoured sheathed cables = 6 times the cable diameter
3a9d60f8-cef7-5eb3-a9a6-8a41c33431fa | note | Armoured sheathed cables = 12 times the cable diameter
feeca9d5-2e6c-476a-9cf4-6bf8248e9493 | checkpoint | Cable follows the correct route
70f07a55-69eb-4188-be20-13f11de55394 | checkpoint | Cable is clear of heat sources
d304dc5b-19e2-4b69-8658-59d739983de5 | checkpoint | Cable is segregated from telecommunications cables by either a continuous barrier or separated by at least 50mm - AS/NZS 3000 Clause 3.9.8.4 (c).
45127ab8-89dd-47b3-86be-5e4a874a4622 | checkpoint | Cable is secured and mechanically protected (where required).
3675befc-c1c0-4358-bf7c-430ba080488c | checkpoint | Cable is marked with cable or circuit number
bbad091a-b162-4a71-8cd1-921f7865e89d | checklist | QA_TEM_012_Switchboard & Distribution Board Installation |  | QA_TEM_012_Switchboard & Distribution Board Installation
2d263221-2dd2-4f65-bb55-dddbce906d48 | section | Check that the switchboard
ae290464-fcc6-49f4-8b73-0ba6a6062a66 | checkpoint | Is the correct unit
0f93b0f7-19f6-425e-b5d9-837cd89ca3f0 | checkpoint | Is located in the correct position
8dc64a99-8ca2-4e77-a6be-b1ff53a38dfa | checkpoint | Has correct clearances on all sides
25905a3f-7d59-41d3-b0fb-d02f5cde7f21 | checkpoint | Is properly secured
6ab583af-0983-4c4a-b15f-32dc537c478c | checkpoint | Is labelled correctly
9ee23463-01bd-4722-9b24-0c2ab1d52826 | checkpoint | Is fitted with correct types, ratings and quantities of functional units
399031d5-6d91-40ef-855f-cd1f04592f57 | checkpoint | All escutcheons and cover plates are fitted
75582ed2-f955-4bdc-a419-0da96249edc7 | checkpoint | Finishes are as specified
955544ca-c6a9-4a11-af71-f2092dcea454 | section | Check each functional unit for
441c973b-7613-4a8d-bfca-e5d4e68ed5f7 | checkpoint | Correct labelling
81949c09-ff7f-4e2d-bb27-45f5aedb6281 | checkpoint | Check all cable terminations are secured correctly & tensioned as per switchboard manufacturers advice
4086b0d4-0638-416a-93b5-21b9ffa9907d | checkpoint | Check all busbar connections are secured correctly & tensioned as per switchboard manufacturers advice
f7746f12-2d3e-4196-8029-9ac801736700 | checkpoint | Check cubicle has been cleaned of all rubbish, dust, filings, tools, etc.
9bcb5a35-5b78-4140-93e8-d02596071d60 | checkpoint | Check for presence of properly completed circuit
491f6482-1d34-4dda-8289-f5ad5d7191dd | checkpoint | Schedule/single line diagram
99e2abca-6495-4b3e-a70c-ef05283d9502 | checklist | QA_TEM_013_Switchboard & Distribution Board Assembly |  | QA_TEM_013_Switchboard & Distribution Board Assembly
588084e1-cbba-49c1-b380-01d93c802bde | section | Built as per plans
e0efdddb-5f60-43ca-84e0-19fb64906da1 | checkpoint | Main Switch
2681f27e-b9fa-527d-bb8b-5963a5087d62 | textbox | Correct Size, Rating & Type
95232d62-b7b2-41b0-92d2-cd7ec27056b3 | checkpoint | Isolators
9a52721d-5de6-5b2f-a19b-f71520b70547 | textbox | Correct Size, Rating & Type
7fe11e7f-0673-4601-a507-87c254d72d43 | checkpoint | Circuit Breakers
a285ff98-4898-5b4d-ad17-80d83ba052b6 | textbox | Correct Size, Rating & Type
93d2d47e-4487-4df0-ad89-89f87323a3e8 | checkpoint | Cable Size
8889d72c-36f2-5ca2-b242-033093c4ec29 | textbox | Correct Size, Rating & Type
e7ab52ed-b767-4ec1-a390-f00996767e68 | checkpoint | CT's
270b963b-fa6d-5ca1-b701-f4c20ad9c712 | textbox | Correct Size, Rating & Type
2dfb31f7-cd90-4316-acce-cda47c164e85 | section | Visual Check
ecd17209-c5c3-40c3-82f0-44fe2620524d | checkpoint | Escutcheons Fitted Correctly
7a71e090-f7b0-4a4a-8b42-22ca1e2ec7e1 | checkpoint | Gland Plates Fitted Correctly
78ab816e-f427-4064-8b7d-a24da8524f88 | checkpoint | All Locks Fitted correctly, operation and keys incl.
7c07224a-6cd2-4200-a5ae-9a833af6789d | checkpoint | Earth straps fitted correctly
4c9e9cb5-9eff-44e8-a108-fb2e24217bbc | checkpoint | Labels
d7b2540e-e26d-5977-b078-cfb57ad80c8b | tickbox | Main Switch
9cf044be-4173-5a84-b433-dfc2526d99ee | tickbox | Isolators
f5483772-833e-5063-af26-d38a34191441 | tickbox | Strip Labels
ac72e4d5-9253-505e-8141-07ae9a6a1554 | tickbox | Earthing & Neutral Bars
d59c3d4a-e60d-5fa2-9a53-5fa393237003 | tickbox | Meters
c2cbe92e-b5cf-482d-95bb-b9d132f0d5d3 | section | Cables
40aac298-00f4-484a-ab06-b23538770b29 | checkpoint | Terminated & Tensioned
7f536a76-a5b4-48a0-935a-b27f25ae880d | checkpoint | Neutrals - Correct terminal and number
b201ce45-2623-4a9a-a0e8-55131f2fd188 | checkpoint | Bend Radius as per AS 3000
e961a9cf-237b-4adc-a577-9d1e0cf227b1 | checkpoint | Correctly Labelled
ed0e989c-3dc4-4837-a471-0827f063e77c | section | Testing (as per QA_FRM_005_Final Installation Test Sheet)
345181ee-c9b2-4fef-955b-43e15f255b7b | checkpoint | 3 ø Board @ 1000V
715b25a0-3469-4207-8356-49d58b2044de | checkpoint | 1 ø Board @ 500V
12f7422e-1d5b-412b-bb4c-87441fcf9a7e | checkpoint | Point to Point - Control Circuits
c74f3649-ddf4-4aec-86c9-67554acf2a3e | checkpoint | Correct Operation of Control Circuits
2b6bad7f-717b-46ba-9596-a43dde7913d4 | section | Cabinet
916a9649-a757-4674-b96b-ce4fa6b9bb46 | checkpoint | Correct Finish
0b3d201f-eda2-4d97-8fec-c42ec229daca | checkpoint | Correct Size
10c2083d-9b6c-4c09-a98b-d5b6c1a83428 | checkpoint | Clean & damage free
1ae120e6-ea62-4d96-a2ff-4407f5a18573 | checklist | QA_TEM_014_Cable Terminations |  | QA_TEM_014_Cable Terminations
f93cd25e-92d5-420a-8d90-1d8feaf5f074 | checkpoint | Correct type and size gland
9e4c95b3-903f-4e9c-8ba7-fada21e9991f | checkpoint | Gland properly and securely fitted
c1780cc3-2e09-435d-834f-842ab6cdc3d9 | checkpoint | Correct cable identification
40e2e70a-8757-4686-b347-f7d201317719 | checkpoint | Correct core identification
ebe798e1-79a7-410b-b997-4e31d5fb8575 | checkpoint | Cores loomed properly
081da640-523c-47c9-b579-12ed2fa01b85 | checkpoint | Cores on correct terminals
2f58e458-519e-4ab9-a92f-beb645cd0877 | checkpoint | Terminals properly tensioned
ead92039-9668-4dbb-8039-236dd5aa8bdf | checkpoint | Cores correctly lugged
a3318e1e-61e6-4926-a736-3f76179cbcb7 | checkpoint | Lugs correctly insulated
a4975087-b6f1-4127-a9be-15cede611d8c | checkpoint | Adequate clearances
385849d9-ed0d-480f-aec9-448296524611 | checklist | QA_TEM_015_Accessories Installation |  | QA_TEM_015_Accessories Installation
42be8319-8d20-4c91-b01a-d068a7456d74 | checkpoint | Accessories are the correct type
ce730564-7bd8-42ed-9c7d-e37c0b165beb | checkpoint | Accessories are located in the correct position
8c3af6d7-c83d-45cd-a3c2-e40545dd3f09 | checkpoint | Accessories are securely fitted
d2c1f851-669e-4b92-81c6-d8b3f027e62e | checkpoint | Accessories are fitted in accordance with manufacturers recommendation
ee4f656a-0124-45b5-96d8-18f5c3791d09 | checkpoint | Accessories are plumb & level parallel
c24094ce-d0bb-464f-82d9-3a051945bc38 | checkpoint | Accessories are sealed correctly
cce44596-4793-4f0e-a00a-c0f185a2619e | checklist | QA_TEM_016_Light Fitting Installation |  | QA_TEM_016_Light Fitting Installation
6040a867-12d0-4968-a0e9-cc5b39eef88e | checkpoint | Fitting/s are the correct type
377afd08-c1f6-440c-bf63-d02ee752355b | checkpoint | Fitting/s are located in the correct position
31b87b6d-5e6b-4c8d-940e-934f1f36b2f7 | checkpoint | Fitting/s are securely fitted
21437d88-5acc-4b8d-9895-463b3b261137 | checkpoint | Fitting/s are fitted with correct lamps
1e9896ca-5abc-4543-b407-65d0a4eb122e | checkpoint | Fitting/s accessories fitted in accordance with manufacturers recommendation
71a6e0d6-dc9e-4436-a4ad-49d5b72b8711 | checkpoint | Fitting/s are damage free
a1c784f5-561a-4a09-a450-78ee138f4fb9 | checkpoint | Fittings/s have correct termination
1cfa0b51-f528-443e-94fa-22ee0fa21c94 | checklist | QA_TEM_017_Fire Sealing |  | QA_TEM_017_Fire Sealing
235fcf30-684e-4812-a413-9d0c0eda0ce6 | checkpoint | Covers are 1.6mm minimum galvanised sheet metal
2a92f4a5-62e5-4875-9ebc-0ad56ce2cd11 | checkpoint | Fire proof material is in place to comply with AS 3000 & the Building Act
38679970-2158-48db-bec8-b87d83325fdb | checkpoint | Plastic grommet is around metal edges bearing against cable
74d10d8a-551e-49fa-9cb9-822732eee67c | checkpoint | Sheet metal covers are painted to match surrounds
6d906af8-1570-444d-b8a5-61c82f8b1363 | checkpoint | Proprietary fire barriers to comply with the Building Act in lieu of above
b33f96fe-f779-4228-81be-81a5b3742144 | checklist | QA_TEM_018_LCP's & Field Devices |  | QA_TEM_018_LCP's & Field Devices
3169b26f-e038-4333-90b0-7ccb64fcaf08 | checkpoint | Installation/s are the correct type
3341dc11-7be9-4434-9fac-76dbd5b87c37 | checkpoint | Installation/s are located in the correct position
261d9521-1e03-40d6-9969-cd44702011bf | checkpoint | Installation/s are properly secured
65e32634-2a7e-45e1-b89b-25a16e50e904 | checkpoint | Installation/s are correctly labelled or identified
800b797a-d5c1-49db-8544-d1c6084ebb1e | checkpoint | Installation/s are assembled correctly
4211daa3-ab78-4365-ac28-4f5a8131553f | checkpoint | Check all functions for correct operation
487de8e2-0a5f-478b-ad39-fbf2d034ae1d | checkpoint | Check that the support stand or bracket is
f22f6836-6bcd-5318-bba6-7043aec777a6 | tickbox | The correct type
8b3a6c56-e080-5311-bbe2-9c52329b13e8 | tickbox | Properly secured
59966ac7-1e00-4e6a-98d5-b1f98a908be7 | checkpoint | Check that all unused entries have been properly sealed against ingress of dust, solids, or liquids
9f770666-fa69-4f09-80bb-421fc7ef8a72 | checkpoint | Confirm that the whole unit/s has been installed in a workmanlike manner
a80affe1-dd1e-4b28-b70c-4c1585d13d52 | checklist | QA_TEM_020_Lighting Poles |  | QA_TEM_020_Lighting Poles
6d45ec29-7ec8-466b-a8ed-4e3a555491c0 | section | IN-GROUND BASES (Before concrete pour)
beb17f47-0fd6-42d6-a40f-52b6a11d00ea | checkpoint | Check that the excavation:
da4923cb-cfb7-59ca-a1c9-2839763d78fe | tickbox | Is in the correct location
17958a48-84cb-5ee9-b744-0d141ccb37cb | tickbox | Has the correct length, breadth, depth
787b1730-bced-5725-a672-dfd3eb93663e | tickbox | Check that the re-inforcing materials are the correct type, size & quantity
07fe5ea7-dc21-5fb6-8ee6-0fdb8d4916fa | tickbox | Check that the rag-bolt assembly is correct type and properly positioned/orientation
edb5a1b6-3f97-49bd-8588-fb2dcbca15d9 | section | LIGHTING POLES
955645a0-0bce-4360-9fae-fffcd011b2fd | checkpoint | Check that the lighting pole is:
91895e8b-35ca-5286-a3c9-cfd1adabb2b2 | tickbox | In the correct location/orientation height
8eb4b3dc-0a08-5014-a4fe-3ea7adcc9953 | tickbox | The correct type, size and colour
899b71c1-15e4-5000-a175-853226d12ac6 | tickbox | Secured/sealed correctly
06019869-5f7d-4eae-b59c-b04ccfa438bc | checkpoint | Check that the luminaire is:
7b1f9eb4-70e3-53a9-884f-ba8c64f0e797 | tickbox | The correct type and size
543a53e5-736a-58d8-9d77-7139d88b9d38 | tickbox | Secured properly
5bdce8e7-8b28-59b5-9908-6b2e6307a384 | tickbox | Focussed as required
bacc2fd8-f786-55b4-aaf7-3de6fcedc6cf | tickbox | Confirm that the assembly has been installed in a workmanlike manner
6ea59bc1-d06c-5e3a-89a4-7ee18b2ad34c | tickbox | Additional accessories installed correctly
692c226e-8c73-48a4-8134-7e1ad901b11c | checklist | QA_TEM_020(QR)_Lighting & CCTV Poles |  | QA_TEM_020(QR)_Lighting & CCTV Poles
cf3b9608-18fa-4ce9-bae6-a769bb2285a4 | section | IN-GROUND BASES (Before concrete pour)
612a8913-7f8a-4050-ac4a-c175a490f628 | checkpoint | Check that the excavation:
9e16cc48-3dc6-5150-90c1-6e11d1c6ce45 | tickbox | Is in the correct location
25fc3d08-a285-5eb8-96f5-c5cb20e331a3 | tickbox | Has the correct length, breadth, depth
0d21a06b-dc98-5e26-9915-f4f60fb4fb70 | tickbox | Check that the re-inforcing materials are the correct type, size & quantity
215bce44-18b4-5cf0-914c-ed3328708e30 | tickbox | Check that the rag-bolt assembly is correct type and properly positioned/orientation
33d7fe79-17f9-4300-a9b8-18620ac01524 | section | LIGHTING POLES
7502cb01-b139-4984-b906-09bdc1ea9444 | checkpoint | Check that the lighting pole is:
1dc31753-a8ee-52f9-9a4a-b0b68bd02f1a | tickbox | In the correct location/orientation height
3b96df7c-e96d-51a9-9e65-754436eb7920 | tickbox | The correct type, size and colour
a1a5f34a-bd6f-5041-a86f-3b63215c386a | tickbox | Secured/sealed correctly
e119e460-a429-484c-8241-9066165d4834 | checkpoint | Check that the luminaire is:
fb4a58d5-12cf-539e-8a46-6e0e4b3e0b72 | tickbox | The correct type and size
643a0ee1-b41b-51b0-9b2f-4b7be730a3a9 | tickbox | Secured properly
61ca9746-f181-53fa-8fe1-ef861dd6ab70 | tickbox | Focussed as required
1d0e6f4d-a023-5525-9d18-0262e3bb3650 | tickbox | Confirm that the assembly has been installed in a workmanlike manner
2255c635-4a76-5dfb-a1c4-4afb95744abd | tickbox | Additional accessories installed correctly
67115bc0-65e9-4f17-85f3-19c0d314a785 | section | CCTV POLES
905ac6a7-2d8d-46a1-b367-72d3f6ce9e9d | checkpoint | Confirm the pole has sufficient cabling pathway for Comms wiring
e30cbca9-608b-4b6e-b20e-90e0ff9069cf | checkpoint | Confirm draw wires have been installed
02fc2537-fb30-4523-8951-079434b8731e | checklist | QA_TEM_022_Control Cables |  | QA_TEM_022_Control Cables
a5ab59f5-36ab-4ceb-b4da-6680daccc0c6 | checkpoint | Type and configuration is as specified
5dbdd79b-4292-4e34-9416-c17c4d06abf6 | checkpoint | has correct origin and destination
dd63c5ff-a7bd-4ddf-9d42-3ffb4cc97f90 | checkpoint | has correct number of cores
557e3b58-8e16-423b-8f5e-7c55cdf46507 | checkpoint | cores are of correct Cross Sectional Area
b04b1181-8a3c-44f9-b6e0-711a4cdba9fe | checkpoint | follows the correct route
ee569e32-6d6f-45fa-ae95-a99b6854b344 | checkpoint | meets minimum bending radius requirements
8711de4e-8f08-4279-82dd-ad9097d3a5c3 | checkpoint | is clear of heat sources
011684f1-cb92-4d4e-b9f2-bf93bf60e2d7 | checkpoint | is clear of power cables
757fee24-0527-4872-b06a-f901f3f99a08 | checkpoint | is secured as specified
370c3cd2-553d-4d25-b83c-4c08ced85675 | checkpoint | is installed in a neat and orderly manner
630cecd6-74e7-46c0-9034-fdd6823d4007 | checkpoint | is routed to minimise crossovers
59a19492-7bc5-4b61-913a-6d5a642b80ff | checkpoint | mechanical protection is correct
b062e443-709c-45f6-8c65-d51770844997 | checkpoint | inter cable spacing/segregation is correct
8e1f18d5-b80a-412d-b4a1-56b0570922c0 | checkpoint | cable is correctly supported
82a9bf62-cf81-4a8d-8669-254b7c27e695 | checkpoint | cable marked with cable number
eeec0702-0759-4d61-b533-7aa11c9d283e | checklist | QA_TEM_023_Emergency & Exit Lighting |  | QA_TEM_023_Emergency & Exit Lighting
8b7fe016-9141-477d-a8be-892fb49379b2 | checkpoint | Fitting/s are the correct type
6b04ea49-456e-4582-8e03-2e417c03d7ef | checkpoint | Fitting/s are located in the correct position
14fa7fd5-6c76-4291-ad69-7811417de0ac | checkpoint | Fitting/s are securely fitted
c6cc84cf-9bed-4e93-bb3a-1833441c6853 | checkpoint | Fitting/s are fitted with correct lamps
b81fc095-76c9-451c-ae84-1b8e147545d6 | checkpoint | Fitting/s accessories fitted in accordance with manufacturers recommendation
ef6a008c-829c-4130-8c7d-6a5c880e64e9 | checkpoint | Fitting/s are compliant with specification
2794dc7e-e25a-45fb-a131-b7f4b2e3773e | checkpoint | Fitting/s are correctly identified
2a6692a7-d04b-48c0-b166-2fe96f8632c4 | checkpoint | Fittings/s are tested to AS 2293 Emergency escape lighting and exit signs for buildings
917da6d8-7ac6-4102-8f7d-64e103c5d245 | checkpoint | Log book is completed and copy on-site
2b866d78-0c13-4acd-af66-a6a0de54dd5d | checkpoint | Log book ID number and as-installed drawing/s match
082dcded-fa87-405e-8eac-47397f57b467 | checkpoint | Exit sign/s visible
bec8608c-32b8-46ae-bc50-9fca16baac74 | checkpoint | correct operation
fd50910c-3828-48a0-996f-0a9680516363 | checklist | QA_TEM_025_Data & Communications Cabling |  | QA_TEM_025_Data & Communications Cabling
b308bb26-f6cd-49ce-b6c4-909f775511aa | checkpoint | Check that cable to be installed matches Job Spec Requirement ie. Brand and Class
2f85495a-494c-4dbe-b99e-47f7adec4350 | checkpoint | Check that all cable pathways comply with ACA and Vendor requirements
d1e70ec6-1b5d-46f2-8688-983d415c7ef0 | checkpoint | Install cables, making sure of all strain and bend radius requirements, label cables correctly
36555c46-7734-497a-ace7-b6199ba960da | checkpoint | Bundle sizes to be checked to Specification and number of cables not exceeded
3501f25e-4243-4303-b74f-cd0ca27d1f22 | checkpoint | Cables to be tied in with Velcro as per specified distance between ties
faf0d71f-7ec3-4501-a05d-ee6e91ca4fca | checkpoint | All Clearances between power and other services to be maintained as per requirements
ff7b02e9-28d6-4f66-bdfe-1891c587b20a | checkpoint | When cable is installed into wall cavity, Corro should be used to maintain support and bend radius
b648914f-88ec-4a3f-9acd-9ae80e03c090 | checkpoint | Corrugated conduit to be extended to outlet position if segregation is required from power in same cavity
39c9e44c-e0ae-4bd4-a012-93695c2cb40e | checkpoint | Sort cables into correct Patch Panel Groups for looming into Data Cabinet/Frame
f62e411e-4ef3-4307-b5a2-ea9ad46a473f | checkpoint | Loom cables into Data Cabinet being sure that they are supported properly and bend radius is correct
329b59b3-b895-474b-8264-8555a33de1ee | checkpoint | Terminate cables on Patch Panels/frames adhering to all regulations for the particular cable and Vendor
66cce16b-e054-4b74-aa2e-292dabc8e905 | checkpoint | Label all Patch panels and Racks as required
fc3dc226-0198-49ed-a50b-5835f2a68510 | checkpoint | Check position of outlets on Architectural plans if available
734ad577-4524-43dc-8e09-eb453374c5cb | checkpoint | Terminate cables in the field as per regulations and Vendor requirements
f968ef98-6cd7-4cf4-9f72-8d72a9b56ccb | checkpoint | Label all field outlets correctly
0cdf606b-6c05-458c-9dcd-23529f5f91ae | checkpoint | Test Cables to the relevant standards and Vendor requirements
b0cc049d-4245-4a3d-8119-cd602795c459 | checkpoint | Fill in record books if required, Check asbuilt plans and modify if necessary
242bb951-7de6-4411-a72e-de4124f21262 | checkpoint | Supply test results and as-installed drawing/s
1a27ecf5-e542-42e1-90cf-416bd748ced8 | checklist | QA_TEM_029_Lightning Protection |  | QA_TEM_029_Lightning Protection
dcf00553-02b5-4121-9b1e-f228337bbe80 | checkpoint | Check test electrodes have been installed
234af576-734f-417f-8cad-33dde028dcaa | checkpoint | Check down conductors during construction
c1121377-85e8-4d70-aeb5-d38381b4946d | checkpoint | Check bonding to exposed metal on roof
a9005a6d-cb62-4c49-92af-6e6d72f2993a | checkpoint | Check system terminations
3c83bcd4-e63f-4e6f-b28f-2ca59c1f8fed | checkpoint | Is system fixed securely
1bfe0a2e-384f-4b30-8b1b-3a6ea4edebe0 | checkpoint | Continuity test for system completed
5f48ea7d-916c-4558-9d18-ba163bd66329 | checkpoint | Check air terminations
7c0b9c9b-7076-4648-aebf-5b2b463ad917 | checkpoint | Nominate size of bonding strap and record
119af8b1-755e-489e-9bdb-6220dcb74ff9 | checklist | QA_TEM_030_Security Inspection |  | QA_TEM_030_Security Inspection
0aca42c0-1919-4ccb-890b-5296be7a17f7 | checkpoint | Check TDCs for correct type (T), position (P), clearances (C), & attachment (A):
385ce265-2c33-5b92-bd14-b54f779d4e73 | tickbox | T
e7ab13ca-917d-53f5-bac8-f8c9048dcee8 | tickbox | P
2a878bb5-778b-5de1-a748-e0f086d8ed7c | tickbox | C
09ef1646-b9f0-5d5e-b5dc-a87bac6bb305 | tickbox | A
c3586814-e7f1-4360-8e84-a563707629c6 | checkpoint | Check Expanders for correct type (T), position (P), clearances (C), & attachment (A):
06b772ad-3892-5b1e-aac5-4f93c6e04f9b | tickbox | T
66b9e135-b8a9-5251-b0a8-52badc910b9b | tickbox | P
3120f598-e1f1-5e68-b40a-42d4e7189a0e | tickbox | C
87f1058a-0649-50c9-bac7-574edb419180 | tickbox | A
5eaabfb8-e1b9-4efa-9f4c-4dde6abc4610 | checkpoint | Check Main Panels for correct type (T), position (P), clearances (C), & attachment (A):
59c40766-2416-50a8-8afd-13b5bbfec092 | tickbox | T
893b3d16-1aca-51a8-aeff-101988e65151 | tickbox | P
78610a10-d7bd-510e-9619-ed0b25b13645 | tickbox | C
8a9f6d7c-47d1-569b-9d29-460bd4968f9f | tickbox | A
4e4d5ce7-d723-4378-abd6-5cd175858627 | checkpoint | Check Electric Locks for correct type (T), position (P), clearances (C), & attachment (A):
4c6bd10e-f0ed-5a05-8664-d8eaff7e3219 | tickbox | T
55b417ac-2aa7-583c-b866-840f85a7e819 | tickbox | P
5cb52650-2406-505a-b488-80362e9d04b3 | tickbox | C
5faa1e62-bfdf-5939-b8d7-30723ffc2983 | tickbox | A
df9fe9d7-6bf0-435e-9458-2549df8a5af7 | checkpoint | Check Proximity Points for correct type (T), position (P), clearances (C), & attachment (A):
1daa89d6-215c-5963-ba59-40f375409a5a | tickbox | T
06dc4b33-bed8-5c3a-8678-bc699619ba82 | tickbox | P
eede8d72-3273-5748-9b7d-4063ff6b63a4 | tickbox | C
e7eddb47-65ab-5149-8242-eda2ece6d3f8 | tickbox | A
8e32e305-f7c5-404e-9784-3906d9564759 | checkpoint | Check Single Door Controllers for DOTL (D), Forced Doors (F), Prox operation (P), & Lock activation (L):
68949049-2e5f-5e47-a1d9-fa4241dd9273 | tickbox | D
8576204e-9f19-5c50-b30b-e2081d56c043 | tickbox | F
cac05976-1b2d-5d3a-8f92-0c361104ba8e | tickbox | P
23e6be8d-540d-5b14-992b-b534030f4251 | tickbox | L
dc35807a-c1c5-4745-b1a3-d95ee5087f3a | checkpoint | Check Two Door Controllers for DOTL (D), Forced Doors (F), Prox operation (P), & Lock activation (L):
886daaad-25b8-5295-96c6-0324525dfd99 | tickbox | D
0de550a1-dac1-51c0-9fc6-8e6bdd720254 | tickbox | F
db57f98d-46dd-5ccf-99e5-e77dd151d51b | tickbox | P
9ce18971-ca38-5998-ac85-436100137b62 | tickbox | L
63654f4b-197c-463c-8c18-ada526c95d0c | checkpoint | Check Four Door Controllers for DOTL (D), Forced Doors (F), Prox operation (P), & Lock activation (L):
9a5ca388-ce1a-5fd5-ae80-ef68fd3e0a01 | tickbox | D
ec871048-d693-5a7e-8b40-1249d735346f | tickbox | F
bd1e8d04-c89c-5e3a-b6fc-95e4ae5e05b5 | tickbox | P
f760264f-f261-507f-990a-7b5113de983f | tickbox | L
ca48e6a0-0e98-4665-8306-df00aecab6ab | checkpoint | Check Active Panels Timezones (T), Holidays (H), Auxilleries (AU), Automation (A):
48714c67-bee9-520b-aca6-45c6664487b2 | tickbox | T
7be4c647-7d14-58ab-966f-21d8be1e882d | tickbox | H
fe990f19-3331-5ffa-9269-1208f07f8aee | tickbox | AU
3d19ccd5-cc23-55b3-875d-55607e3a5ced | tickbox | A
1413a67d-54c4-4ba6-84ed-bc3811ac9269 | checkpoint | Check Single Door Controllers Timezones (T), Holidays (H), Auxilleries (AU), Automation (A):
d7ad0af4-bc90-5bda-80f1-d7c042d63f34 | tickbox | T
8a7d1506-0663-5580-937f-8caf9e2d7d4a | tickbox | H
c0936b23-8833-54b5-bb64-b820f4b0ef07 | tickbox | AU
76547764-7a12-52c3-8f24-c38a01ea2a0e | tickbox | A
83c90f9a-ac3a-4305-966f-942500c3d7c1 | checkpoint | Check Two Door Controllers Timezones (T), Holidays (H), Auxilleries (AU), Automation (A):
301d9536-58ef-5155-88af-b7c60e79d45e | tickbox | T
25158897-8f47-5dba-834e-ccbd279c41a9 | tickbox | H
1a8d303a-8b01-5de9-9bcc-40e4a9b0cc36 | tickbox | AU
2cbc027c-45d0-5041-9f49-2ec9b61fe43b | tickbox | A
a4bf82e3-9656-4038-b155-600d4a484136 | checkpoint | Check Four Door Controllers Timezones (T), Holidays (H), Auxilleries (AU), Automation (A):
c7f576ff-2264-5196-9db4-cb08b9b1e4c7 | tickbox | T
7aa00e5a-cb6d-5afd-95c3-6e9bdf15045c | tickbox | H
f468070c-f04b-5f58-b073-81a1a92f0ef8 | tickbox | AU
08e6046d-76b1-5b39-acf8-5e6287f47120 | tickbox | A
97f398a7-ea6f-45bd-a7c7-21f71e2121de | checkpoint | Check activation of Door Reed Switches
16f47065-8246-4088-963d-b67e154a6a6f | checkpoint | Check activation of Intruder Detectors
8634fca3-84be-4e77-a90a-380ee75f3cf0 | checkpoint | Check that all cables are the correct type, size, configuration, length & quantity
fa2ceeb8-c034-4686-a1e4-f69422375bda | checkpoint | Visually check all terminations for correct colour codes and acceptable looming
40e06c4d-92a3-4651-8b25-8220805b0fc2 | checklist | QA_TEM_033_Control Cable Point to Point Testing |  | QA_TEM_033_Control Cable Point to Point Testing
28dcdebf-c050-443d-8372-6a70d1a8665f | checkpoint | Continuity test of each & every individual core
370f4c60-e07c-5970-8093-f67392618978 | textbox | Earth
eb54b3f5-e86e-58cb-a3a6-5800de407f6a | textbox | 1
38fef54f-26ad-5413-a8ed-d0dd50be3571 | textbox | 2
20847031-7cc7-5b1d-85f1-009dd064a127 | textbox | 3
65469ece-581d-5892-a162-817dbd302621 | textbox | 4
65a62b83-2792-527b-b873-351d3c95a6a7 | textbox | 5
742eb233-ac4b-5382-b8b4-783a6ae79f66 | textbox | 6
a73a57cd-a1a0-5090-a697-6fcaafd5bd5a | textbox | 7
5692ed46-1125-5dc2-bcff-58920c53fd08 | textbox | 8
b702c243-0634-5e95-9cac-130ab1ccdd51 | textbox | 9
9edf64cb-e6c0-56cf-82ba-a751c493ca43 | textbox | 10
56002fcf-4ad3-579a-8269-dd4982c3b7c6 | textbox | 11
0930700d-c01e-58cd-8824-83bdc6eb9d82 | textbox | 12
deb85a30-a53a-5b20-af71-3381f7d0e643 | textbox | 13
a74f25b3-55e6-546a-8a23-f9cabd19f27c | textbox | 14
9d010e5e-92d8-57b9-a34c-420f60b511c0 | textbox | 15
4e3e8673-beb1-5d28-aad6-9ef153ec36b5 | textbox | 16
de28b90f-8fdb-5b4a-9f4d-fde4067b64d7 | textbox | 17
870e2cf7-756b-538d-87a2-8ea2e09995f5 | textbox | 18
ed47e756-524d-5da0-aac3-974860965411 | textbox | 19
6cfd069e-0736-5504-a5c8-cee46a7fa8b3 | textbox | 20
63537e3d-667d-4d3a-a662-e0a68a86d07b | checklist | QA_TEM_035_Multi-Core Point to Point Testing |  | QA_TEM_035_Multi-Core Point to Point Testing
d11c6cc7-40d8-4aaf-8d6d-8da0ec2a62a1 | checkpoint | Continuity test of every core
800009fc-f738-59a4-a275-3a0a8e3ea025 | textbox | Earth
ced06d48-4ee3-5a61-b993-03ce6f2b38cc | textbox | Core 1
850baf95-0b74-5cc5-8b18-b495bf5edb8b | textbox | Core 2
31cd576d-a6d7-58be-9289-a94d9e5db484 | textbox | Core 3
78baffab-1935-5aa5-9d00-2b7408d5d406 | textbox | Core 4
c235fa0b-5b21-5918-901e-ed5619d86983 | textbox | Core 5
d1b2630f-69dc-580b-8f85-80cb6cfa7a87 | textbox | Core 6
af01f029-1427-5e72-a64e-a93ee31c70a0 | textbox | Core 7
9f99fc78-07db-589c-a61d-4a2fbe1c0819 | textbox | Core 8
09e398a3-12b2-53c7-8a55-f8b42b9dcd9e | textbox | Core 9
e6577f20-3901-5dad-a09e-d1a3422c3749 | textbox | Core 10
c817d897-f28f-59bc-9608-44cf5f7706a1 | textbox | Core 11
94610dab-b2e9-5bdb-837b-6746fb0fffed | textbox | Core 12
e5c59f5c-9333-5176-938d-dcf9366f517c | textbox | Core 13
adda062f-c017-5679-88a5-938d7f0fd80a | textbox | Core 14
42837d5e-10f7-5e58-b1c9-7dd708ad0e4f | textbox | Core 15
7cf7e002-dfa2-569e-bb5a-57431dd507fa | textbox | Core 16
2daccff7-e111-5911-aa52-ea885ba0438a | textbox | Core 17
c604face-058e-5a88-9fc8-7d4eca37f234 | textbox | Core 18
03cda502-f00d-5005-8f27-8df299b37f3f | textbox | Core 19
a27dc8dd-447a-55c5-a439-ada8dc859cad | textbox | Core 20
c7abb90e-3ef6-5dfe-bbef-9ff257a45e7f | textbox | Core 21
1bdba8ec-93eb-52f3-849d-213274694479 | textbox | Core 22
8da073c2-b196-5f31-8b10-2d0780e46660 | textbox | Core 23
8685f429-b48a-5229-b2b6-d008a38cc77f | textbox | Core 24
42ee0469-e7f5-512d-84e7-4d493f97c943 | textbox | Core 25
58b5f7fc-b2f0-49b6-8e03-d767b35986cc | checklist | QA_TEM_036_Power Cable Point to Point Testing |  | QA_TEM_036_Power Cable Point to Point Testing
67f9baa1-d4d3-49c8-b66b-87dcf69ccd1b | checkpoint | Continuity test of each & every individual core
b91d9f52-29ae-512e-9160-212e130aca7a | textbox | Earth 1
265300ab-c925-5b70-b49a-74dc2f054f0c | textbox | Earth 2
546477c0-947d-580d-8a66-e5dbc99d3a03 | textbox | Earth 3
e878a8c7-6b2a-5958-9882-e6a16598b4e2 | textbox | Screen
3846562f-b83b-5ae5-9d45-cc4eca2b4c05 | textbox | Neutral
e718e787-c216-53db-ba87-03474571b65a | textbox | Phase A
7e6129e4-7c50-58ab-8377-827bbdfed770 | textbox | Phase B
475dc602-12e2-52b2-9fb5-ae524d5eb09a | textbox | Phase C
9a662a8a-ba2b-46e8-b57e-cfb94ac911c4 | checklist | QA_TEM_037_Install Field Instruments |  | QA_TEM_037_Install Field Instruments
240590b4-6e87-463d-9bbb-686ee203f076 | section | Check that all Instruments are:
358def69-cfe5-4c93-93c2-bdc3f980595f | checkpoint | the correct type
b6232781-308e-4ce6-bc3e-29551fb897a2 | checkpoint | located in the correct position
cd2b675b-16c3-4137-b74c-0b919accca73 | checkpoint | properly secured
713927f1-b68a-4acd-80e6-0a7f4c3c2044 | checkpoint | correctly labelled or identified
8f621c04-47c0-482c-b74c-64a254d289b1 | checkpoint | Check that the support stand or bracket is:
683d118d-c23b-5f35-a8e1-206a937afc1e | tickbox | the correct type
1166f284-e273-5f29-9e5d-f5c64509553c | tickbox | properly secured
52df27c9-4a24-49c3-bb2b-86990ca9821c | section | Check that the instrument air is:
4a34492e-5be2-4ee9-afda-62096865f726 | checkpoint | connected correctly to the instrument
7e827e0a-1148-44d1-83fb-b480509e9cce | checkpoint | connected correctly to its supply point
1a03da55-6f00-4cdf-a762-7b14cb329484 | checkpoint | adequately secured along its length
320b4f2b-b9dc-4386-ac5f-02c1495dbca5 | checkpoint | Check that all unused entries have been properly sealed against the ingress of dust, solids, or liquids
11573db4-7cd7-4fb8-ba43-02cc7f120a95 | checkpoint | Confirm that the whole unit has been installed in a workmanlike manner
b4376895-c62f-40c0-a526-ad181f54498f | checklist | QA_TEM_040_Multi-Core Cable Commissioning |  | QA_TEM_040_Multi-Core Cable Commissioning
0aca39e8-b80d-4d86-a459-b54a099cc72f | section | Cable Install
64358203-9b34-42aa-b1a1-406647226148 | checkpoint | Type, configuration, number of cores & cross sectional area is as specified
87eacc4d-07fa-4e41-a3c5-91d2c148df07 | checkpoint | Cable has correct origin and destination & follows the correct route
861fa9b5-c686-4726-a2ec-0b958b16ae8c | checkpoint | Meets minimum bending radius requirements with minimal crossovers
fc32fcb8-3588-4b39-af02-588a5daf6685 | checkpoint | Is clear of heat sources with mechanical protection fitted if required
bef3f9b1-9ef5-4950-8ec3-43ef9716379a | checkpoint | Is secured properly & correctly supported as specified
98a30f90-a1d8-4188-905b-f0ef879ba58c | checkpoint | Is installed in a neat & orderly manner with inter cable spacing/segregation
bda4b808-8b87-4791-aaa0-29f340f01d65 | section | Origin Termination, Location
8c5baa18-52bb-4992-85f7-2ab1608e4970 | checkpoint | Gland is correct type & size, & also fitted & secured properly
6d8c03f3-e057-4331-85c3-26fb12940132 | checkpoint | Cable numbers fitted correctly & securely
44628054-931f-4c83-b673-d5d3b4c6d845 | checkpoint | Cores loomed neatly with correct identification
1943d301-e468-47e6-8a1d-005d212313fd | checkpoint | Cores in the correct terminals & correctly tensioned
b14ecb07-1316-4011-b249-0aa23e8cb5c5 | checkpoint | Cores correctly lugged & insulated
4434e71d-c6ca-40fd-a203-560ae43c2ffc | section | Destination Termination, Location
7124c769-105a-4ce1-a5a2-832f6f4390b4 | checkpoint | Gland is correct type & size, & also fitted & secured properly
eebb2449-e66f-4768-8455-d5f619c5541b | checkpoint | Cable numbers fitted correctly & securely
312a8001-a513-44fa-809d-7dba40c5ecad | checkpoint | Cores loomed neatly with correct identification
92e906d3-fa03-4d8a-af42-c048aad02b5a | checkpoint | Cores in the correct terminals & correctly tensioned
53663df0-b48d-4083-bd95-737a47082416 | checkpoint | Cores correctly lugged & insulated
c4f582b3-5294-49d2-9f60-7c83f4b8532b | section | Testing
c742f742-b922-4c65-a32f-af696ee871b6 | checkpoint | Point to Point, Continuity test of each core
57c25b67-3df6-58aa-a7a7-a247705f3ccb | tickbox | Earth
655cb0ee-ae49-505e-a67f-9ffcfe07422a | tickbox | Core 1
278c70d0-b01b-5064-b993-c60dc3e11de1 | tickbox | Core 2
e2cf8382-70d6-5537-810f-aa0bfdffe796 | tickbox | Core 3
5ca6232f-1f46-5097-ab7b-66eb7e95fe4b | tickbox | Core 4
222a0f44-c5f7-5798-9a15-d723a5ceca10 | tickbox | Core 5
b5965bd0-bae7-52b3-b49a-41f6f0734006 | tickbox | Core 6
5c4f183a-b02d-5487-947f-6e72d37947b5 | tickbox | Core 7
fb95bddf-b41d-5e3a-8f13-c6ae028e5ccb | tickbox | Core 8
520b8eb5-de37-5e3f-8489-32850af9b0b0 | tickbox | Core 9
6aae7e57-85c9-56fd-9c21-7cb09920111c | tickbox | Core 11
6e8ba169-094e-5cf5-add1-6a662f999966 | tickbox | Core 12
6ec4ad13-e73f-5773-ad12-18ba98b05ed1 | tickbox | Core 13
ce745128-dd47-541c-92e5-81dc68ae67bf | tickbox | Core 14
1017acc4-1ea4-58c3-8b41-c3aa2c55b8ff | tickbox | Core 15
72362c9b-81d7-5f91-b699-2081929e7698 | tickbox | Core 16
d3ebfc27-95d5-541e-a95b-c6add65cce09 | tickbox | Core 17
bbb8acc9-5d7e-509d-89bf-bfab4207e4c0 | tickbox | Core 18
b3306bbe-d61f-5563-b439-5671b35da548 | tickbox | Core 19
d27f4c55-6fec-517b-957e-18bd9633c885 | tickbox | Core 20
a6f92f92-576e-49dd-b37e-f0586ad6ed57 | checklist | QA_TEM_041_Power Cable Commissioning |  | QA_TEM_041_Power Cable Commissioning
acf48c0a-da1b-412b-ab43-3b5d05bb351e | section | Cable Install
fb33a12e-e2e2-4e47-b7cc-3ed81b4bda1c | checkpoint | Confirm cable type, configuration, number of cores & cross sectional area is as specified
c37fb228-e9fd-417f-b963-d3f487321ffb | checkpoint | Confirm cable has correct origin and destination & follows the correct route
228aa1f1-30a4-473a-bc23-abb832fc4b44 | checkpoint | Confirm cable meets minimum bending radius requirements with minimal crossovers
f3bc5443-022b-4f00-9c09-ab8dbf69ce74 | checkpoint | Confirm cable is clear of heat sources with mechanical protection fitted if required
1f0c4e16-4671-4d17-ad92-f9a63f8eb3c6 | checkpoint | Confirm cable is secured properly & correctly supported as specified
01a1739c-5d48-4271-aaa0-d1514527d847 | checkpoint | Confirm cable is installed in a neat & orderly manner with inter cable spacing/segregation
b6e32375-0726-4aa4-802d-b898fe475d56 | section | Origin Termination / Location
e18c95be-bfed-49da-bc9f-ab824b03c56f | checkpoint | Confirm gland is correct type & size, & also fitted & secured properly
ff1abb46-c436-4700-9540-5d95e78c8f71 | checkpoint | Confirm cable numbers fitted correctly & securely
7b3e4383-2f52-4faf-a326-cd6dbd98c8ea | checkpoint | Confirm cores loomed neatly with correct identification
585bdc7a-9afe-43c6-93b7-33ed74f6c5ee | checkpoint | Confirm cores in the correct terminals & correctly tensioned
7acfa09a-1e56-4964-bf0a-5b82bd8da9ce | checkpoint | Confirm cores correctly lugged & insulated
dee08a0a-93a1-4b1b-b91e-7addf775a9dc | section | Origin Termination / Location
d303c985-c669-4831-8822-74a4c8cdef84 | checkpoint | Confirm gland is correct type & size, & also fitted & secured properly
f1f1d135-7837-4380-bebb-078478fbe251 | checkpoint | Confirm cable numbers fitted correctly & securely
b48f9640-2d07-46c7-b27b-ed34bba10d4b | checkpoint | Confirm cores loomed neatly with correct identification
0c072561-9d90-47ee-8038-36421026d484 | checkpoint | Confirm cores in the correct terminals & correctly tensioned
018babfe-02f4-4524-9cea-52f84106ef08 | checkpoint | Confirm cores correctly lugged & insulated
82372de4-434d-42c5-9c79-f9b9febb09c5 | section | Testing
280a2519-9b09-477a-9c66-8e9c48636ce3 | checkpoint | Point to point / Continuity of each core
46eb8842-4c02-5f79-b763-3da0e7024c11 | tickbox | Earth
15cd286d-c8b4-5218-bc3d-2213d7a67f2a | tickbox | Red
7b079030-15ca-59e9-bc66-76bcfccad57d | tickbox | White
5e822000-d94d-564c-ad9b-196cd68d0504 | tickbox | Blue
97b6bd67-fbb6-5ec7-a54b-0f07e435e103 | tickbox | Black
974371a5-36f6-472b-90d3-abed9ee615a2 | checkpoint | Insulation Resistance Test (results recorded on QA_FRM_005_Final Installation Test Sheet)
34cef972-2888-41c9-a2d5-d229089516d4 | checklist | QA_TEM_042_Rough In Checklist |  | QA_TEM_042_Rough In Checklist
7f3f16ff-c4b4-48da-a712-c303dd94b772 | section | Inspection 1
7a95a8fb-3489-496d-9a27-d7f5d59bcda2 | checkpoint | Has all information been recorded and checks completed?
667fb88a-6789-53f7-a7e7-09732a6cb46d | textbox | Circuit ID
8eb5b76e-940e-59ee-95b0-04c32665f6f5 | textbox | Cable Size/Type
7f2dcee6-0c4d-551a-89ef-504d94014ca9 | textbox | Number of Points
eb3ebf30-3c96-54e2-83a7-793139e0d09d | tickbox | Feeds - Visual Check - All feeds have been roughed in
06244b43-0136-5cff-baf8-e464fe024a21 | tickbox | Feeds - Identification - All feed cables have been identified/marked
17d1c104-5901-5944-852e-8e3d26f28322 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
200cdbcf-ee13-5bae-9476-ca6d01fe3ff0 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
fc59d1b8-949a-5a36-9761-c7a10d65fefa | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
bd8d3817-c75b-563b-a9f6-334a57fe9131 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
8bba7d17-21dd-47d5-953c-48dc5b929808 | section | Inspection 2
db14e9d1-6a33-450f-bebb-7446c3c91ee3 | checkpoint | Has all information been recorded and checks completed?
31a18c00-7575-52b6-8247-6d70e170de25 | textbox | Circuit ID
f9214b1c-14c7-59ad-8f70-6ce27441284a | textbox | Cable Size/Type
37834d2e-5cb3-5c65-a1a2-1d89dab089a6 | textbox | Number of Points
86712f6b-e4de-5039-be46-99add8a5e7d7 | tickbox | Feeds - Visual Check - All feeds have been roughed in
cbc23dac-b9f9-51de-97a5-f3a21eeac52e | tickbox | Feeds - Identification - All feed cables have been identified/marked
c8587324-f645-5086-96ab-1a0212e07302 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
5baac39c-a401-5fff-9b5c-57a6511cda57 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
97e5d451-f64f-5971-a448-bd09c6de2e01 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
bbd5e913-76ab-5985-912c-be2705bd35c7 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
0449bfe6-f36f-4a11-a8f8-8ed6ae36f7eb | section | Inspection 3
6acdb34e-b121-42a4-b292-23a891c44f4c | checkpoint | Has all information been recorded and checks completed?
2f9ddb88-467f-5db5-8f6a-cd8f0f9a1120 | textbox | Circuit ID
30e41e56-00f9-598a-bbb3-5ae61d88b1f4 | textbox | Cable Size/Type
1a71a8f3-b5fc-5880-a50d-65efda26cf50 | textbox | Number of Points
bcd332d5-c792-5d2f-8d10-cd5a98e471fe | tickbox | Feeds - Visual Check - All feeds have been roughed in
64fc30ac-10a7-55a3-84b6-56802963b7ed | tickbox | Feeds - Identification - All feed cables have been identified/marked
93a336f4-9d68-569c-80e3-93cdb66b2d85 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
921c95ae-5efb-5db1-abe0-97328ccf17ea | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
0a6652f1-ca71-5680-b669-a99dafd5b96b | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
aab9ec2f-3d8b-5867-a86e-6dbcf75c4665 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
25563ed0-d728-4501-afef-aaf689c0e83f | section | Inspection 4
7a5f8727-8cc3-4a5a-82ed-34471f133c8e | checkpoint | Has all information been recorded and checks completed?
cdb51585-61ce-5338-9318-6cac77da1f0d | textbox | Circuit ID
377fea5d-4bf2-5c37-9d80-19c1083eab66 | textbox | Cable Size/Type
61011d62-05d8-5325-accd-4096d65cd065 | textbox | Number of Points
16286de3-a6a2-5967-8030-de5bb3ee68a0 | tickbox | Feeds - Visual Check - All feeds have been roughed in
c661f4ec-2779-509a-8106-65c7bc3b5b70 | tickbox | Feeds - Identification - All feed cables have been identified/marked
26adbb4a-eca0-5392-8f2d-3444a1eddac1 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
bcf339a1-0b54-5db1-8982-7d10f3a952c4 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
5d592e73-da08-58bf-a33e-43ceb1e6030d | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
342d6cc6-751b-59a7-9a6e-3270783e858f | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
6d28858b-538d-4b68-b4a8-dc317ac8dc66 | section | Inspection 5
a06fb5c2-4ec6-46e0-92f5-e15a83369e3b | checkpoint | Has all information been recorded and checks completed?
446255f9-929d-50f6-a449-df6246b4fd18 | textbox | Circuit ID
26197ed5-0a0c-54c5-8b61-33ac3dbc283f | textbox | Cable Size/Type
1dfc2dd0-e1ff-5654-af8a-80922fe882f1 | textbox | Number of Points
a1c512ac-bdef-50f2-acbd-75d6527d9706 | tickbox | Feeds - Visual Check - All feeds have been roughed in
0b6e01de-e6e2-5985-8f45-7bd94cf94ee2 | tickbox | Feeds - Identification - All feed cables have been identified/marked
2c49794e-3440-5fd8-8416-4c7b619e8f46 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
05b0a281-abf5-5074-8dcd-f9cc6ee4acd5 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
23ba1fa1-0c23-50e5-8825-c34124cefa27 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
5caeb392-2322-5f36-97fd-c5bdabbbf918 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
d1883d40-7fe4-4a9f-a74f-e3cb39b99228 | section | Inspection 6
1f9b2497-0946-406c-a370-dd72cdc45434 | checkpoint | Has all information been recorded and checks completed?
6f3e6699-a9f9-5ca2-8a06-49e5a65cfd7c | textbox | Circuit ID
eab682a1-4c8c-5a35-9a6b-bf94a7458be7 | textbox | Cable Size/Type
1937492d-5694-5ad6-90db-589b619de188 | textbox | Number of Points
3587b004-98dc-54e6-9017-e44ae6d82f7b | tickbox | Feeds - Visual Check - All feeds have been roughed in
878ce500-a6da-540f-b3be-7ac092b866c1 | tickbox | Feeds - Identification - All feed cables have been identified/marked
c41db617-d31b-5e94-8638-65720b7b48f3 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
5c7f30ae-e1d2-5e48-9cb2-a4f57175370d | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
7adba90e-ce4a-5804-b4fa-85be1f06f290 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
4a5ea663-4b01-5bca-b08a-e9bf05dde578 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
45e74101-2801-40e3-888f-41a4d02ff915 | section | Inspection 7
0592a80f-74d1-4477-8ccf-030cb194b6fe | checkpoint | Has all information been recorded and checks completed?
01c1401e-83ad-568e-baa6-aa318a982fb0 | textbox | Circuit ID
b99ab75f-45ab-5981-abcd-f50804c3ed01 | textbox | Cable Size/Type
256b7420-33cd-57ed-a665-b7d2e38021af | textbox | Number of Points
77725f33-29ca-50ad-a679-0f4a1ce8f4aa | tickbox | Feeds - Visual Check - All feeds have been roughed in
cbe5e353-d9b4-59f1-9194-4dab125e72f1 | tickbox | Feeds - Identification - All feed cables have been identified/marked
518ae56d-4eb4-54e0-a267-e4c8f420a7a7 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
4ace2103-7ddf-5c39-a171-428dcd9e25ea | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
0499a918-cc84-5c48-af4e-d2365020bfcb | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
ab3d802d-9187-57c4-93d7-33e0c663f5d2 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
4b978457-36d4-4698-bce8-c0bd6e8d48c0 | section | Inspection 8
32e0a383-74ac-4c44-bcf8-dd9ab31720bf | checkpoint | Has all information been recorded and checks completed?
cbe6158c-6c91-5a18-bdbb-5fc16324590c | textbox | Circuit ID
2cc28e32-7e1f-5714-a2b1-054f86f58d06 | textbox | Cable Size/Type
59ef0919-f48b-501e-a68b-1901ce879a6c | textbox | Number of Points
6fc1a3e5-7210-5ead-b5a0-306bc383ccaf | tickbox | Feeds - Visual Check - All feeds have been roughed in
abf3d217-5386-5977-bd8a-e6f02930a1c2 | tickbox | Feeds - Identification - All feed cables have been identified/marked
864b5e4b-ee2d-59c3-8e93-5448bea6d739 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
8f73413d-d4a4-526b-90fd-f6cfd2d0b803 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
6c4ebf0e-81c6-5e4b-b8b7-0b6a446048dc | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
3c127a79-4e7d-550a-bdda-168f9456c6c1 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
b8f75848-23ac-450e-a68f-46c3dac29612 | section | Inspection 9
db63732c-e760-4c2c-a3b5-b25bca6f535a | checkpoint | Has all information been recorded and checks completed?
4535e98e-78ce-5ad1-8283-933d3aa6f8f9 | textbox | Circuit ID
104b630f-97e4-59df-94ed-f61ea5d5db5e | textbox | Cable Size/Type
635bf160-1f69-5914-b6a1-f3099d862ffd | textbox | Number of Points
4a440640-021c-5dd4-8304-286c841f5e00 | tickbox | Feeds - Visual Check - All feeds have been roughed in
a29f056f-a2a4-57ad-81b0-05d555e416a8 | tickbox | Feeds - Identification - All feed cables have been identified/marked
a3b29835-0f49-561f-831f-9c4cd7bd4d76 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
67d7e017-333b-55b7-9476-25f8adb45450 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
d0c2480e-48cf-53d2-a06b-ed598b9715e7 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
904d62c8-dd01-52a8-b764-eecffc96cd75 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
a18e1bed-1a1c-41b6-9d35-3a409d0e6640 | section | Inspection 10
f4b6449b-d929-4915-8412-423acf3135d3 | checkpoint | Has all information been recorded and checks completed?
33829cc6-c293-5468-a6d7-d8271b1d76f1 | textbox | Circuit ID
8656504e-7d64-5e2b-b72f-193087f22a3f | textbox | Cable Size/Type
c1c8de67-97e3-56df-a30c-4dc1549e87f1 | textbox | Number of Points
702a7743-e8b0-534b-bd31-2eee337c2eaf | tickbox | Feeds - Visual Check - All feeds have been roughed in
37fd279b-ac62-57e3-a3ce-f5993d099231 | tickbox | Feeds - Identification - All feed cables have been identified/marked
8598164e-e768-5abf-8564-28102b19208e | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
622a089b-f368-56be-931f-c7c98efe26f0 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
c9cc6a3f-fa90-5c68-a31f-d2e56363075c | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
bbfb8f81-56e6-57a6-932c-1e4dd06c1dd1 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
0e449a70-a619-46ca-9b70-f3c8b923fc33 | section | Inspection 11
50c5f705-43b4-4422-a82e-d4f07ad9055f | checkpoint | Has all information been recorded and checks completed?
161635cb-22b4-5aed-91f6-6bf7968e564c | textbox | Circuit ID
54374613-ae82-56f1-8725-8918b131b65b | textbox | Cable Size/Type
ca1fb5b6-6231-58d2-aec0-bb408d269a3b | textbox | Number of Points
772ac444-28be-5a83-a8f7-cf643e8e3ed8 | tickbox | Feeds - Visual Check - All feeds have been roughed in
9be9618c-32cb-5954-8021-16be763354cf | tickbox | Feeds - Identification - All feed cables have been identified/marked
f2090bbe-33fd-5694-b239-8041a5a0bf89 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
d3a0cefd-1ecf-5b92-9bbb-eea4ea711536 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
9c497700-9fbc-5580-9ce3-9fb6aee5d804 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
70ea131a-9219-5fdd-b80f-75dfb50b03a9 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
72ffe65e-238d-4fd0-8ae2-6fce7bdb0bb4 | section | Inspection 12
ae4837a3-fffc-45e7-adfb-1964170e34fe | checkpoint | Has all information been recorded and checks completed?
5399758c-d36b-5596-865e-06e027d83903 | textbox | Circuit ID
d5a37cc2-9adc-592b-b73d-c4281b456cd0 | textbox | Cable Size/Type
81a93c3e-648c-5134-b0dc-6f282e286c3e | textbox | Number of Points
30a6e3dc-1dff-576c-b9a5-78a8b4693580 | tickbox | Feeds - Visual Check - All feeds have been roughed in
9f2c5ee2-c1d3-57fd-a1c4-c571fe402131 | tickbox | Feeds - Identification - All feed cables have been identified/marked
9bd8299a-9811-5ccf-87d9-132b356ac662 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
71fbd2af-d7e9-560c-9375-3aca089175ae | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
fc08dcdd-99dc-51c4-b7c9-092250916eea | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
c3f604ff-e678-5325-83c8-c74f03b23c5b | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
5fe8a75a-32c5-4a8c-8566-53cfce87a5f9 | section | Inspection 13
8c0508d7-08ef-4053-a3a4-585dc40bcd57 | checkpoint | Has all information been recorded and checks completed?
3d7e4ab7-8907-527e-92bc-872f8f6b1166 | textbox | Circuit ID
edf47fc4-3322-508c-8883-86c7b7468e7a | textbox | Cable Size/Type
00d2579b-520a-5cdc-8484-aea16d2629be | textbox | Number of Points
c98c1ae8-039a-5812-b79c-a69358842eda | tickbox | Feeds - Visual Check - All feeds have been roughed in
1897cda3-a2b0-5496-b484-4edab4fccafb | tickbox | Feeds - Identification - All feed cables have been identified/marked
64f5e50f-9788-56f7-bc7a-a9322413de87 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
f3ce7efb-85a5-53b2-b277-1f46ec82ba3a | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
6cc08534-d499-5cdd-bfe0-e64d1bf55904 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
3934a03b-ffc1-5f02-a7ca-53b69a524fc0 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
3fe34a5e-0ff3-410c-afeb-563d26b9b78c | section | Inspection 14
6f3993f0-c514-4877-8139-b3d1848836e9 | checkpoint | Has all information been recorded and checks completed?
a4187083-9932-5c93-9616-7fffaa8542ce | textbox | Circuit ID
2123be42-44f2-5f3a-895b-c7634caf57f2 | textbox | Cable Size/Type
8ae1227e-cd78-5f17-91d2-e694c9aabe80 | textbox | Number of Points
87ff5521-7669-53d2-8c47-18aa3c20b039 | tickbox | Feeds - Visual Check - All feeds have been roughed in
328dfbbf-acac-50ac-ac0e-d64194bc2c2f | tickbox | Feeds - Identification - All feed cables have been identified/marked
51ceeb44-7060-5ddb-ab50-bf48afafa54d | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
dd4fc5f4-3903-53ac-9902-948ae238a070 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
265c6039-6be7-577e-8afa-c04339f8f560 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
a8258ecb-c591-52ee-ac2f-3ed403ceb88f | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
c8a9578f-a337-42a9-9e4e-69b5b7742834 | section | Inspection 15
eaf4d13d-c2d3-42af-b5a5-f69c497f74d5 | checkpoint | Has all information been recorded and checks completed?
222f03fb-1532-5d0f-aa79-b9a99fda4b90 | textbox | Circuit ID
5c24097a-42d0-5687-8373-de7de250c4d1 | textbox | Cable Size/Type
8b3bf9cc-1f0e-5791-9e4c-39b2ed969e2e | textbox | Number of Points
3d50b2a2-5d5e-5414-a3e0-13c351d54995 | tickbox | Feeds - Visual Check - All feeds have been roughed in
43990314-5af0-5c59-abc4-9ea51f5fc61f | tickbox | Feeds - Identification - All feed cables have been identified/marked
4157af52-a760-534f-ac4f-f1b1b0f3ceb2 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
7a3b125a-6ef6-5312-a30a-4f10e0ab9a91 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
44ca40fb-eff3-52ea-82de-dc1385e78164 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
8fc97129-d1eb-5a41-91b5-83a4b9558926 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
0213bf79-814d-431f-b456-743d9cfb8211 | section | Inspection 16
db5f2d38-89c4-408e-b786-56b289084767 | checkpoint | Has all information been recorded and checks completed?
7b61447f-c8f7-5d6b-8a67-8aad6ad3247e | textbox | Circuit ID
8a05536e-0ffc-5428-9730-f43c226d446c | textbox | Cable Size/Type
bca11e32-a122-5d96-acc5-3395bb3e9ef4 | textbox | Number of Points
6aa24fe6-1243-520b-8971-8041e76e0157 | tickbox | Feeds - Visual Check - All feeds have been roughed in
ce85145a-63b6-5e40-b4fd-330e8f16fe0f | tickbox | Feeds - Identification - All feed cables have been identified/marked
2512956c-42f7-525a-bf2a-21a7665e79e3 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
f8456370-5243-53c6-9c87-e84f7a81e217 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
73f6b693-74de-52cf-8927-fe2c22ff3a80 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
fb275f8f-bb3b-5f7b-90e4-0df54a5cbb31 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
e3e4cae9-9152-4272-b0e2-5417ac710fd0 | section | Inspection 17
7fdfd264-85d4-4a83-9985-8c2e4ed834ed | checkpoint | Has all information been recorded and checks completed?
455e44d9-06b6-5d5d-9e45-2b2b3310d4b8 | textbox | Circuit ID
da829049-96f9-51d0-866f-9ed083d83f51 | textbox | Cable Size/Type
49cff808-9d89-57b3-b447-9c0bc4caa2c0 | textbox | Number of Points
11ccac3f-8b44-5a8f-8dfa-1b9d8ce244f3 | tickbox | Feeds - Visual Check - All feeds have been roughed in
0d4ab29d-1610-5ba0-8471-e959a6bf7f99 | tickbox | Feeds - Identification - All feed cables have been identified/marked
449148f7-fd82-515c-a87d-4b4adf531541 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
923bc9e9-4838-5833-ac53-a65ee8b62496 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
a78873ae-6f73-52df-9c78-070d529e5985 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
b67ee8de-c238-5460-92c7-5ef37f3fc495 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
4a85eb42-47e2-4fd5-a2bf-496259932d18 | section | Inspection 18
cfa7650a-1aad-42c7-b6da-8158afdce131 | checkpoint | Has all information been recorded and checks completed?
694d92ed-8bce-5b23-9366-c78ceefd8c2e | textbox | Circuit ID
091923db-6a81-5295-82bd-513453076ce9 | textbox | Cable Size/Type
99a30b5a-80b0-5028-b16b-41c877f97899 | textbox | Number of Points
edef44b7-61d9-5f2c-bfcb-8cc6f5df3800 | tickbox | Feeds - Visual Check - All feeds have been roughed in
2b7eee98-bae3-51ad-b484-f083aa931210 | tickbox | Feeds - Identification - All feed cables have been identified/marked
7cc27322-9bf9-53fa-9da6-bd98ca916d5f | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
bf5f8c4b-b576-5443-9720-2327660297c5 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
6d118316-ce6b-5349-9457-fce28402e6cc | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
b5e18189-97c1-535a-a1a9-e873b0e9ece0 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
65ecb26c-bfca-4e6a-8767-8ccb84e89535 | section | Inspection 19
6e8b46b7-a85c-42ee-9f7f-3753f68f1c6c | checkpoint | Has all information been recorded and checks completed?
1d59fabd-19f0-5c89-9d86-42149e3b5be4 | textbox | Circuit ID
7f608e80-3de4-5230-b912-9e9374557a4a | textbox | Cable Size/Type
019be100-8752-55e6-9352-6ef12f91682f | textbox | Number of Points
c661fd50-df2e-5d1b-b187-35e4fb7d00cb | tickbox | Feeds - Visual Check - All feeds have been roughed in
b70bc9b9-fe10-5077-b553-7ce7062f1f71 | tickbox | Feeds - Identification - All feed cables have been identified/marked
38e39d91-f66e-5ef9-b143-a5f6b91edfdf | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
5e8f1aab-463e-5bd6-b7c9-c9a5a9297b98 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
f0b960a5-c30e-5fbc-9840-0b5f4add7951 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
7c18bbad-f323-51bd-a0d1-d9a184755bce | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
ac5c9156-4e37-4d79-86cd-1d92940378f8 | section | Inspection 20
74ee21de-d42b-465e-b331-fd827a8804bd | checkpoint | Has all information been recorded and checks completed?
ad6be1e0-3738-554b-9c27-67d706170248 | textbox | Circuit ID
a6c0749e-28f9-591c-9f9e-9cd1273e2aa6 | textbox | Cable Size/Type
67c2b338-67cc-5b0f-b60b-055a854c7674 | textbox | Number of Points
f2e63ec2-22b0-5759-bcee-3783266617ff | tickbox | Feeds - Visual Check - All feeds have been roughed in
b44ed70e-3966-5970-acd3-85297d49d626 | tickbox | Feeds - Identification - All feed cables have been identified/marked
eaab4b24-9186-5c04-ab67-3686963444fa | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
5c7e8093-f79e-5fa0-8c18-5fee3508f0a4 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
971f8986-a103-5880-b52a-f48e2cd91ded | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
70c5b2df-b361-581f-b4d8-50c1f0d4c4ae | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
d8f4b45b-82a6-47e1-9c6b-1407527c7e83 | section | Inspection 21
48b0521d-de18-4aaa-b5fc-5fbe6b70ba95 | checkpoint | Has all information been recorded and checks completed?
23d85fbd-1d35-5786-9b8c-3ec3908b47f0 | textbox | Circuit ID
686becac-7b68-5656-8d83-ca43fc7dd677 | textbox | Cable Size/Type
75c804be-7ac0-5c4b-8a7a-6437b5ba09d7 | textbox | Number of Points
386b6ecc-3e15-5c17-960d-36685467925a | tickbox | Feeds - Visual Check - All feeds have been roughed in
5d6bdeab-b27a-57c6-8399-e6fcd58efa74 | tickbox | Feeds - Identification - All feed cables have been identified/marked
bf3f5df7-cfb1-59ff-a932-070ab027a457 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
f22589fa-5e2c-586f-b41b-bbdfeb623c0f | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
813a8321-db04-5c23-8e26-723b9f14bd93 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
9f6572fd-43ab-50f9-80f3-2c483367d6dc | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
e4992800-f0a6-4e6a-8e75-b010ebfbbc12 | section | Inspection 22
4c29c047-eb98-4700-8a8b-6f5652708380 | checkpoint | Has all information been recorded and checks completed?
ca6f736f-1336-5754-a3b5-68063ddadbe4 | textbox | Circuit ID
c459a81b-8401-521c-b730-7edd254865ea | textbox | Cable Size/Type
fc38e819-0332-54f3-8c94-d529da967e6e | textbox | Number of Points
23653160-0398-54c9-a9fb-72416b5cdba8 | tickbox | Feeds - Visual Check - All feeds have been roughed in
a90a1652-279c-5953-93df-402d9e8dc3f7 | tickbox | Feeds - Identification - All feed cables have been identified/marked
ef11f846-3874-5693-8a72-0882d5b1348a | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
1fde43b5-e540-5a21-9a8a-509df6379ee5 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
ffb3bb39-0022-5c73-83d9-30768485c2e9 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
56d3e7c1-dd25-5248-93d7-64ce8984dbb7 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
67529d61-0d9c-4363-8161-f3e48e43a361 | section | Inspection 23
39e2c561-5667-4a22-aad0-6e89d1cadd1d | checkpoint | Has all information been recorded and checks completed?
15c1c75d-355f-5ca2-bfc0-d977604cad42 | textbox | Circuit ID
3b7187b2-0b3a-5cfc-9639-ae792eaccc85 | textbox | Cable Size/Type
958ce42c-1f38-5e05-bbed-0914413ed052 | textbox | Number of Points
a7c015b8-d78c-5a8a-94dc-b5d032f4924d | tickbox | Feeds - Visual Check - All feeds have been roughed in
a0333166-f325-523e-9b8a-37ded4c52fc5 | tickbox | Feeds - Identification - All feed cables have been identified/marked
64e0909f-07e7-5fe5-b0fd-a4caed31ff97 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
b8f6dc7a-3edf-5626-afe2-64a304a374dd | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
06a790c0-1429-54af-95a1-d6a388408610 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
50d3a712-1866-581e-b2c0-f23154910e62 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
040ed1f0-58e0-408f-bae8-d25599392a5a | section | Inspection 24
342b8077-8ad7-42a9-8ea3-173735f9db9a | checkpoint | Has all information been recorded and checks completed?
1e5c7351-0601-51f9-861b-a6e34a06fbfc | textbox | Circuit ID
2cd3418d-cdf8-5b2a-8174-0ed70ec3ac79 | textbox | Cable Size/Type
5a664fa4-0ffd-54e3-a6f6-4cc9fb6205aa | textbox | Number of Points
9a6de60a-c3f1-5ebf-969e-1477d843b26b | tickbox | Feeds - Visual Check - All feeds have been roughed in
5018f459-3028-50fd-93d8-a25717f7869b | tickbox | Feeds - Identification - All feed cables have been identified/marked
36736ec9-c436-5f36-8ebb-83f50503df6d | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
55c54e56-fa39-5cf5-b52c-8917e7d208fe | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
3e3405cf-502e-5850-b0d3-746f55ec6397 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
ebc8f5b5-969d-5247-af33-33d53ac3a40c | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
cadea287-fbbe-4ba9-a84b-118012866033 | section | Inspection 25
d521842d-3277-4bb1-8175-c34036adace0 | checkpoint | Has all information been recorded and checks completed?
eefc5af0-4789-5c47-855d-e35a8818aafc | textbox | Circuit ID
04d6becb-5d2b-5b7c-bc00-85290b727c8d | textbox | Cable Size/Type
7fdfea8e-278e-59be-89e4-232abec9b038 | textbox | Number of Points
9b082f84-2d99-5cb0-adec-36c9dad09400 | tickbox | Feeds - Visual Check - All feeds have been roughed in
8b1b5937-bfa1-5638-9f7d-c52c8a962c93 | tickbox | Feeds - Identification - All feed cables have been identified/marked
711b595b-4662-56b7-b309-87006532d012 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
577c9c6b-2c06-5341-ad4b-31c42455429c | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
5ef46e29-70aa-5e30-86b7-74f5797c1d12 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
11eaf27b-8e7b-5a7e-9d06-eceb0bdecf06 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
a3808144-52c1-44c1-97ea-9b582489d832 | section | Inspection 26
8b2d4e61-0b83-4166-a92b-ec57029c4163 | checkpoint | Has all information been recorded and checks completed?
c92d2ba6-ac29-5dfd-a645-b051c90a0ead | textbox | Circuit ID
85d3d0fa-4434-5a21-933c-451010cb31e1 | textbox | Cable Size/Type
d6104182-d848-5f74-b4d0-de7106bf5b1e | textbox | Number of Points
4a7128b6-96a3-5b61-9b5f-a421e97e2f3d | tickbox | Feeds - Visual Check - All feeds have been roughed in
21f5629a-5878-58f2-9623-72a00cc3f7e3 | tickbox | Feeds - Identification - All feed cables have been identified/marked
f5784c7e-f3e8-56ff-a9ee-caf33a98dd75 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
e8323f02-8ae9-55fe-b843-20a90eea9ebb | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
bbf20734-0bc8-5bf0-ae56-4c89b0da3b80 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
32a491b2-bdff-5e4c-ab8b-3a62c75309b3 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
07d9272e-8f9a-476b-bc8a-b7f0ae27f58f | section | Inspection 27
49228ab1-8534-404d-9a02-a152a60cf76c | checkpoint | Has all information been recorded and checks completed?
48bd9cdc-b36b-5667-8dff-374aa88aec0c | textbox | Circuit ID
f67670a9-3e88-5ad9-8144-b6169a3e3041 | textbox | Cable Size/Type
9df474b7-79e5-5c67-a80b-c40c1e6da222 | textbox | Number of Points
34fc8552-fab9-5d52-93c1-9e9c1a302c7e | tickbox | Feeds - Visual Check - All feeds have been roughed in
7a0af88e-f3e7-507f-a76f-0442a97e78dc | tickbox | Feeds - Identification - All feed cables have been identified/marked
e82317dc-3704-5963-83c5-832d17f997fa | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
436b171e-7575-5cfa-8ee0-cc8c3516e4c9 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
f8243620-9f6f-5a01-91b1-e5ea723b2d96 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
34686e8e-75b1-594c-984b-c7a4b670cc0a | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
879a96a2-262e-4a63-a9d5-50ac18bf4931 | section | Inspection 28
6e83cc23-55a7-4e28-8f1c-d3a5f60ee82f | checkpoint | Has all information been recorded and checks completed?
1aef0ed6-2eb1-5c26-8ca8-164d5fca4929 | textbox | Circuit ID
e6777793-d814-5b06-8116-9a7cbaae9233 | textbox | Cable Size/Type
a45316b2-7336-52d2-b07f-57742f8df521 | textbox | Number of Points
2f7bf7c0-8022-56f1-861a-452735cf8291 | tickbox | Feeds - Visual Check - All feeds have been roughed in
30f996fc-9207-59c6-9930-7c9d0eb24122 | tickbox | Feeds - Identification - All feed cables have been identified/marked
a018e4c9-04b5-5e8c-8d22-9ea736642bae | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
22bc4b78-7c07-5f0c-841a-0ecf6cba6667 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
7cf106b7-93cd-591e-8ea6-c616b29760cb | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
065054fa-1844-54a9-8417-b773d5c435cc | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
f13eac72-233b-4292-b290-ed2a5d443458 | section | Inspection 29
34788687-cdc1-460f-ba59-b06302ae6c84 | checkpoint | Has all information been recorded and checks completed?
25ec72fa-b829-58fa-862b-b1d6f892afc6 | textbox | Circuit ID
c1214d9c-7ea4-511d-b521-f5408f16c7df | textbox | Cable Size/Type
d8ffe648-fdf2-5160-96e7-159dcbc4e358 | textbox | Number of Points
5d2515c7-0007-5dbf-b411-32036edecb21 | tickbox | Feeds - Visual Check - All feeds have been roughed in
b3a4f32a-9325-5e74-abbb-d8a90227904e | tickbox | Feeds - Identification - All feed cables have been identified/marked
327c5619-2efe-58a9-88fa-0f9b1c32c1c7 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
bef1d6ea-a11c-5e3e-8a2b-0dcb1e9de41f | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
3f293314-27ac-5a4b-a240-a28b0338c53a | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
2741bfb1-f53c-5cc7-a24b-0626b460634c | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
b2c03abe-6bd2-4022-8b39-b799668fd8e8 | section | Inspection 30
a8bc2bde-bed3-4322-b457-db3f4e993bbe | checkpoint | Has all information been recorded and checks completed?
e92304af-d6e2-51a8-be3e-5223830ddabe | textbox | Circuit ID
7762a281-d471-5114-ae56-b113993efac3 | textbox | Cable Size/Type
19b8afdd-30ef-56f0-aafd-53e3d40a5cdd | textbox | Number of Points
9157f621-9e18-5089-8a8c-47607e859a13 | tickbox | Feeds - Visual Check - All feeds have been roughed in
df7fc50f-530d-5f73-bc2a-3497c4e508e9 | tickbox | Feeds - Identification - All feed cables have been identified/marked
c68600a6-84cd-5754-8d91-ca4628fb3b67 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
b6c4c8bb-b3b7-5517-b9b2-b15292778bc7 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
d574e98f-e057-537e-ba9e-f4a8a497adc3 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
a87a4e1b-d50d-58b1-b918-65fcdb888cb8 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
290af5a9-ce5e-482d-b602-1433985886a9 | section | Inspection 31
168274cb-8273-46bd-a49f-2dd1632e4e74 | checkpoint | Has all information been recorded and checks completed?
795d256d-d6ea-5410-90b2-fa63815f587a | textbox | Circuit ID
79726bb2-9010-5a32-ac1f-b9e4a02df0ae | textbox | Cable Size/Type
9147bae6-f832-566e-9abc-6910f50b92c4 | textbox | Number of Points
7e26aad5-1e40-5b6c-8030-4dc65fa8a563 | tickbox | Feeds - Visual Check - All feeds have been roughed in
f383770d-ddf5-5a1c-a660-8448aef44aea | tickbox | Feeds - Identification - All feed cables have been identified/marked
b31f1022-4c17-577e-a211-1c95ff21e116 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
598597eb-bc06-59fb-8ceb-9f8c7718ce05 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
67e6abe3-5c7c-5a9a-9af7-6eec188cceab | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
84039dbe-300e-563a-8d86-2e0670127706 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
8ee4e1c3-d62a-402c-a733-a6309a6da714 | section | Inspection 32
a55e5ce3-72c2-4d6a-bd4e-282b512303bf | checkpoint | Has all information been recorded and checks completed?
23ac5bd8-f466-52fe-add2-fa1eb58e277b | textbox | Circuit ID
9ea7fa87-3041-5dc8-96c9-5b1f74d3cc47 | textbox | Cable Size/Type
0c7d6a07-ba36-5d24-b567-237d9f295f13 | textbox | Number of Points
aa7d0dad-8721-54c6-8fcd-584564bb6dd6 | tickbox | Feeds - Visual Check - All feeds have been roughed in
cec8e4ac-0553-562b-9bfe-18095f0e92e8 | tickbox | Feeds - Identification - All feed cables have been identified/marked
8bc97ad7-16be-53f2-a39b-9c0e7f754939 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
371c750d-c803-595a-95a7-3ffb0ea7ada0 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
52574afd-1e8a-5d72-8206-d3437d246025 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
f40680bf-f8c5-5958-90a3-957708ca585a | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
69d2513c-d767-4e8e-8d96-968d302c2ff0 | section | Inspection 33
d0ed5b17-e3b5-4480-886d-e5408e8ef4ee | checkpoint | Has all information been recorded and checks completed?
740d429c-ca35-5af5-8537-96535772016e | textbox | Circuit ID
d00cae1e-5a4f-5396-ad4f-220ae2cf5ef1 | textbox | Cable Size/Type
b241cbdf-3359-56f5-b1c3-9325caed5c28 | textbox | Number of Points
5129d760-62be-5d6e-84e5-2b30a3e64b50 | tickbox | Feeds - Visual Check - All feeds have been roughed in
e370ffda-53d8-5498-8d82-41798b96ed0a | tickbox | Feeds - Identification - All feed cables have been identified/marked
fc0e707d-6409-5a13-b03c-587d3ce26774 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
38c6ad09-2bd6-5f22-b7e0-11ba42c9200c | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
97f5aa0f-9c2f-580d-be01-42e4467a83db | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
bc1d4ed9-9fcf-5b92-873c-2217650d9cc3 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
b322a777-bb0e-4e64-9c13-0fd0ee5cc8ed | section | Inspection 34
44ce3832-6e7d-4f08-8305-39d5ea1efa6d | checkpoint | Has all information been recorded and checks completed?
399638ac-ce0d-54f1-8b42-6837b2e9aca7 | textbox | Circuit ID
88601710-6a2a-5efb-8d9b-d19a0c47975f | textbox | Cable Size/Type
2f7d0c13-6a21-5fb2-8f0d-6e7931c71825 | textbox | Number of Points
37617d6a-9e45-55bd-9250-1a5a60a7a478 | tickbox | Feeds - Visual Check - All feeds have been roughed in
11c57e04-facd-5bfa-bb22-d77e257e8592 | tickbox | Feeds - Identification - All feed cables have been identified/marked
a8050139-6fe2-54fd-a05d-ad2dc1eb066d | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
336289a1-e065-52e5-bd10-db0fe39ba999 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
3177e751-7bf0-5a86-82ec-d116431e904b | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
33a2a0ec-67f2-51fb-94a7-93d254bd06c6 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
3b95566f-36a3-4a31-a87d-c813fcc95466 | section | Inspection 35
dcac1329-4bfa-486a-844d-640186acdf6a | checkpoint | Has all information been recorded and checks completed?
696885a2-dd3e-59f3-8cb8-8a6efd9861e7 | textbox | Circuit ID
2f53a785-f7f5-514a-a590-23fe3259d1ca | textbox | Cable Size/Type
4552694e-cd69-56d1-a1f4-6fee330a3213 | textbox | Number of Points
c1ae66f6-9140-5f65-87d0-6dc7740fe9fb | tickbox | Feeds - Visual Check - All feeds have been roughed in
537d362f-fc59-5ca0-9d3e-352145dd2322 | tickbox | Feeds - Identification - All feed cables have been identified/marked
180a322b-15db-5d12-b37c-96c99e73d9b4 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
9aed1bbb-5ab1-50c7-8e99-66c725b3bd32 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
05052853-4c38-5b71-9f45-c87e4f88e71e | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
e201370c-94e5-5daf-899d-8129956f8638 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
44287dcc-596b-4d44-a6be-f029df26f2aa | section | Inspection 36
d1d8f03e-48e1-47b8-af7f-52a676a0d159 | checkpoint | Has all information been recorded and checks completed?
c797c7e0-57e0-5a9c-9313-e8ef16725885 | textbox | Circuit ID
2fa1fb45-2e82-549b-ad1d-90ce98d55788 | textbox | Cable Size/Type
578a7c2d-8e2a-51ed-a3c5-9b3f6eb46929 | textbox | Number of Points
3d28ecad-c31b-58f4-be70-afac42a79193 | tickbox | Feeds - Visual Check - All feeds have been roughed in
8ecdb3f6-245b-5e75-9211-4906cb94e462 | tickbox | Feeds - Identification - All feed cables have been identified/marked
38bd84f2-c2d5-5e7a-a8e7-6408642a3f72 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
0a848001-aec2-585c-865b-0b6e5e86536c | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
6255cfc4-19db-53e4-b270-556ffa06b8b4 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
2bcec6a4-5e19-5247-ad57-680445278056 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
8203ea38-0da8-4288-aac3-b0a07a481e6e | section | Inspection 37
e4e8d68a-cb05-4a30-b9b3-7592fa4e64d3 | checkpoint | Has all information been recorded and checks completed?
f2c73043-3a0c-5738-a01b-0e789398d3f1 | textbox | Circuit ID
fe55c750-8a69-5979-add6-0056d66db72e | textbox | Cable Size/Type
1f32043d-4c83-5ca8-ae72-a93eeb2b605c | textbox | Number of Points
2d764a9e-2b1c-5213-a0a3-1fe56a631085 | tickbox | Feeds - Visual Check - All feeds have been roughed in
59430051-6d7c-509d-8e5c-160314c05361 | tickbox | Feeds - Identification - All feed cables have been identified/marked
0f7e5357-abe2-5506-a7ec-acd8275182e6 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
859c11ea-333d-5b0e-8638-7f4e6ec0fe10 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
1ce2d14e-42a4-5029-ab0d-1ae1614888e8 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
d89486e5-5464-56c7-9503-f87162b9f116 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
accf3cf9-a81a-4a69-acb1-3b7d35f55d17 | section | Inspection 38
fc485da0-8785-4dde-8c89-e0734ae898d0 | checkpoint | Has all information been recorded and checks completed?
2eab56d2-44f4-56fb-b513-16970f09fc91 | textbox | Circuit ID
eb98639a-6d97-5c3a-8c88-4cf6f016be6b | textbox | Cable Size/Type
22c3af11-8136-568c-b11f-189870232f81 | textbox | Number of Points
300c0bac-b065-555d-b874-dc91de1df793 | tickbox | Feeds - Visual Check - All feeds have been roughed in
bbaa99ad-6703-5e0a-9c17-06ee6ef44faf | tickbox | Feeds - Identification - All feed cables have been identified/marked
790eeb3d-5955-5ee9-a389-6edbefb9da9d | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
035d5b65-6349-5f05-b51d-3c4ae933d9f9 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
623e6761-c806-584a-a4b1-fd90962be33f | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
09dae863-90aa-567b-81b3-67385b1b3c6c | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
dc94da9c-1c5b-4709-adfa-43b5585f8d7d | section | Inspection 39
f0ae4263-05fa-43e2-8f11-c4c6e9285735 | checkpoint | Has all information been recorded and checks completed?
22d97daf-4886-50cc-8680-81df77668612 | textbox | Circuit ID
c65988c9-6637-5961-89cf-75d29dcb0018 | textbox | Cable Size/Type
151876ba-bf6e-5994-af84-52e1fa804132 | textbox | Number of Points
3d53a561-e825-5d12-83dd-683461ffd60c | tickbox | Feeds - Visual Check - All feeds have been roughed in
68b14fdb-9183-5954-92a5-b5f78a6e2656 | tickbox | Feeds - Identification - All feed cables have been identified/marked
854e7d32-5d01-546f-81e6-25fc96723cba | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
44992971-430f-5112-a0a8-68f81857e732 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
be45843e-f090-57bb-8aba-5c69845f6a83 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
84ce1cd7-01d8-5cf8-ad22-c58c6440c030 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
7b3ecfb0-af14-432b-b602-638bc4b044ee | section | Inspection 40
0ade6f2f-5f63-42cd-b23b-348208b31572 | checkpoint | Has all information been recorded and checks completed?
f25b67b3-fd8f-51ce-9c16-ee6bbbc7504f | textbox | Circuit ID
1a4d83f0-c4e1-56c7-9b2f-defc104233c4 | textbox | Cable Size/Type
363125cd-4326-57b6-bc73-891782382539 | textbox | Number of Points
e5b7164f-ea37-5b6d-a390-0c71537b0cf2 | tickbox | Feeds - Visual Check - All feeds have been roughed in
bebc6902-18ff-5376-9b43-c08b5cbb54f6 | tickbox | Feeds - Identification - All feed cables have been identified/marked
a2a73ade-0e2b-5af0-93b1-8f4d23689f4e | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
342d2a2b-4448-5ff9-b486-37003cc57b11 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
4ace3404-7c73-584d-b79d-ea6620a4d719 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
a90e8833-952a-546a-aa92-308e4fa7e737 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
cb42d893-3aa8-47e4-a2f2-fd302ca0f415 | section | Inspection 41
afc8bb98-8154-4d0e-9bf9-572e16b4acc0 | checkpoint | Has all information been recorded and checks completed?
8b07f292-2f89-5950-9e95-7da66bf6dc87 | textbox | Circuit ID
5445fe4f-941d-55c7-afdf-c881900cd62d | textbox | Cable Size/Type
d409e3a7-f4a5-5bd7-b4dc-90255c81788b | textbox | Number of Points
f22e3bb2-e339-5dda-bffc-ce1dfd5f1471 | tickbox | Feeds - Visual Check - All feeds have been roughed in
50e7ad9b-820f-503b-a019-d8e6216fd0e6 | tickbox | Feeds - Identification - All feed cables have been identified/marked
25d8c472-dbe8-55b1-b712-b83f23aea746 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
c3386e9b-83b3-5b4c-ab0b-5929eefbef63 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
29026e11-610a-50b7-ab7e-18e0a0972b9e | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
c9c7052e-fc6b-5de1-8098-0c3c513eb070 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
1b237104-881a-4a1a-b9ee-8bb5625e3704 | section | Inspection 42
78b2d4b1-2954-4ced-9467-3a6cdebd4474 | checkpoint | Has all information been recorded and checks completed?
83935b8d-9080-5c5a-aa61-bece90241a2c | textbox | Circuit ID
e31e3216-d2e4-57df-98c1-c1635b8b9e78 | textbox | Cable Size/Type
d218394e-89f8-540e-9e34-79c7829e4a15 | textbox | Number of Points
b5260816-d999-50ed-adfc-c8a9465c6de6 | tickbox | Feeds - Visual Check - All feeds have been roughed in
c048bfb8-f10f-53fa-9ff1-b391a7c1b719 | tickbox | Feeds - Identification - All feed cables have been identified/marked
4e17bfd9-671b-59eb-a88a-598a432502ff | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
c02dc45e-464c-5aaf-a2c5-a796f387315a | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
9d804b6f-ad4e-5c2c-9ced-3f9e691b9a0e | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
370b7ab2-6075-564c-b17d-4c95aad4f1f6 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
9db67178-e9ff-4b5a-9442-c8de17c9ee3b | section | Inspection 43
b8c13f69-b725-4607-a36b-26431b1ed2a0 | checkpoint | Has all information been recorded and checks completed?
de08101d-743b-5a39-b4da-b1c8afeedd15 | textbox | Circuit ID
158e90f6-1302-52b1-a98a-76c852666cb9 | textbox | Cable Size/Type
5d75ac43-7827-5c96-94d4-2e02425c0617 | textbox | Number of Points
f995db61-7ca8-59d9-a0b4-9bdef7a893d8 | tickbox | Feeds - Visual Check - All feeds have been roughed in
f5213ac3-33c9-5bb5-9907-39eb312e542b | tickbox | Feeds - Identification - All feed cables have been identified/marked
250149c0-32af-5964-9694-a841560e8a48 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
49a3f8e2-556c-50a7-b388-fec2303de3ad | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
00741321-b5a8-55ce-a5bd-e621dc44fe2d | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
371fcef8-8825-5eab-84e0-2f5589075ae0 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
428a0eb6-0648-49bf-a81a-0856603c97fc | section | Inspection 44
f6d1afdf-2cab-4df6-b3b7-8946fadc346d | checkpoint | Has all information been recorded and checks completed?
34870e73-8bca-5f93-b39a-6fbb656e2557 | textbox | Circuit ID
d128136c-8396-517b-862d-7066740d7492 | textbox | Cable Size/Type
93ab4176-464d-5756-8d93-31039d9891af | textbox | Number of Points
2ba433d4-d838-58d5-be3f-d6c30383b456 | tickbox | Feeds - Visual Check - All feeds have been roughed in
c6de6692-0407-59bb-8d15-5fd0086e8202 | tickbox | Feeds - Identification - All feed cables have been identified/marked
19744aae-a7be-52af-ae99-1246eec17752 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
596b41b1-8086-5a58-ba35-377266b83d4b | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
04138d3e-a2e4-55d3-9814-09ee45e89df4 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
71e49ec9-e990-5024-b154-9bd703fa582a | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
508acb71-8c77-45a7-adb8-5123d57210a7 | section | Inspection 45
c5459d00-4932-4098-98bf-d9f9eb1b3e9a | checkpoint | Has all information been recorded and checks completed?
d0767f23-913d-5aee-ade3-3d3782e54ff9 | textbox | Circuit ID
f7726573-36da-50ed-b074-57ef30f6883c | textbox | Cable Size/Type
c24ed56a-e3c7-5dd8-9070-24eb04264330 | textbox | Number of Points
87271b7b-0ff5-548d-9044-15c313e550f2 | tickbox | Feeds - Visual Check - All feeds have been roughed in
1cd2a62b-69a8-52d7-a7ef-dfd61722ed78 | tickbox | Feeds - Identification - All feed cables have been identified/marked
a2a394fa-10f7-592a-afd9-1de370c9669c | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
f0eb6297-13a6-58da-a3df-e9da54be2333 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
e4e8ce74-b3b4-52d7-a4c3-eef0d16d453d | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
2c2f46db-6039-5acc-ac35-9a2b4d010f50 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
b2531a22-2e7c-4a4c-a79e-4227128635ec | section | Inspection 46
ba609983-642b-4f63-9a41-ceb420aa3ff3 | checkpoint | Has all information been recorded and checks completed?
f68122ee-6f26-53bb-8975-f6d80dae177a | textbox | Circuit ID
a7c4014c-c1ae-5d5f-b87d-b7339200d5b4 | textbox | Cable Size/Type
7048ba70-52ba-5686-8070-980df6d08eee | textbox | Number of Points
cfc9fb91-bf10-5e37-8aca-68c4ec80ef90 | tickbox | Feeds - Visual Check - All feeds have been roughed in
24bf4b29-e9f7-59fc-a49c-33d90ff96424 | tickbox | Feeds - Identification - All feed cables have been identified/marked
c3726dbc-710c-5c6f-934d-6501afd03fed | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
37e7169b-bbf4-5319-8ca3-cffeedd9eeed | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
768793fe-da49-5da5-8b2e-4ad23c5be80e | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
9780b667-3544-5bc3-9876-8a6b3e124faa | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
2219b6d8-cf7f-4c0b-af21-3d6bccc6f635 | section | Inspection 47
cfb70ea5-0406-4aee-b7f1-675011dfae90 | checkpoint | Has all information been recorded and checks completed?
ae110e8a-b368-566b-a0ec-8910999ec993 | textbox | Circuit ID
b0c1ff07-ea6d-57bb-bc64-8bf037d44b98 | textbox | Cable Size/Type
8f047308-7b5f-5310-a16a-feb622ffb570 | textbox | Number of Points
b1153ee5-625b-554f-bd81-b79ef2289d0d | tickbox | Feeds - Visual Check - All feeds have been roughed in
064154e8-0de5-5d99-b695-281cc4d0f630 | tickbox | Feeds - Identification - All feed cables have been identified/marked
abac6cad-58cd-5748-b57f-b9af6a6b5821 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
bbd460eb-af54-5443-a3a6-b8dac8f24131 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
5b3f9b13-45dc-52fe-81ed-9a71a587607c | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
40329c57-f22f-51b3-bf26-ab638391f496 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
d5036d33-25d4-4c0b-818d-d9fbfa96a804 | section | Inspection 48
6a0fd0ab-a379-477e-939e-6419750a8968 | checkpoint | Has all information been recorded and checks completed?
5d1c0ea9-6cdd-5b6e-8a99-6373908cfc5c | textbox | Circuit ID
df3c19cb-d995-5564-bd31-c6b1f3762996 | textbox | Cable Size/Type
286f57d5-d182-543c-91b5-4d8b7ab449bd | textbox | Number of Points
1b55ee06-9524-5a6c-b4aa-a7c74bbdaebb | tickbox | Feeds - Visual Check - All feeds have been roughed in
1f0942de-dc24-59e7-a0c4-18af215617b4 | tickbox | Feeds - Identification - All feed cables have been identified/marked
3caaa395-756e-5f89-9ca5-c436b022cc95 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
8ad4c26a-efb1-5fdb-94bb-3ea32c273ac1 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
9a9f8eaf-83c8-5808-b185-25dc5801d9b8 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
583e1964-e5e1-5d88-8a49-752b7c8d3642 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
c33a6b2f-f053-4592-94b3-051525031686 | section | Inspection 49
9fad3e3f-b7b4-4420-955e-1b9319edde05 | checkpoint | Has all information been recorded and checks completed?
7147fc94-5b14-5d1b-8615-aa97f0e41391 | textbox | Circuit ID
9bbe1fab-ca4a-5a34-b12c-29c24bfa6f8d | textbox | Cable Size/Type
5370a56e-4215-5e81-9580-dc91650d5239 | textbox | Number of Points
f693e2fe-1997-5208-8f7f-c151a50e1997 | tickbox | Feeds - Visual Check - All feeds have been roughed in
905814e9-8cb7-541b-80fc-e28ae8e34a29 | tickbox | Feeds - Identification - All feed cables have been identified/marked
f457296a-b5ee-58f0-88eb-7b58bdf0e070 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
f2b55618-bc72-5689-992c-d5a7bcc4d3b3 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
b122b886-5ea4-5f23-82dc-564049bd6bf7 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
803b8fa7-bc3f-56b9-bbaa-c6485a862b7d | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
d7d8b983-1484-44a6-801e-159d6bfb1454 | section | Inspection 50
4a7a9d63-1de7-4169-b0bb-248403144ba9 | checkpoint | Has all information been recorded and checks completed?
aab28a9e-dde4-545d-a91e-c57d2b49cc86 | textbox | Circuit ID
8f549e68-149c-5d43-856a-5beb30ef2697 | textbox | Cable Size/Type
25c74707-551c-5d73-b407-d80fea41bbcc | textbox | Number of Points
f3ccc5a9-8a7d-5f33-8783-791ec169737b | tickbox | Feeds - Visual Check - All feeds have been roughed in
bf482b5c-56f3-5401-b424-0d07f65519d6 | tickbox | Feeds - Identification - All feed cables have been identified/marked
7b7ee4ba-5cb8-5c63-8590-5d90957aca48 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
294e0b7e-fd69-5f7c-97b8-00575433d37c | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
c62df032-e6ad-55cc-84ac-7e8da40d30be | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
438a4320-6e8b-5d87-97af-66e6697be641 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
71a35e0c-4296-41e3-a33e-9d68dc4adfef | section | Inspection 51
c50c43c8-20ac-4ccd-84ff-052636c96f87 | checkpoint | Has all information been recorded and checks completed?
470275a4-ea8e-54b2-af6b-6a8e301abc74 | textbox | Circuit ID
a4999c9b-d484-54f2-9bad-b828ebf6be24 | textbox | Cable Size/Type
9baee5b0-b6cb-5e60-8fdc-6a12606a9b3f | textbox | Number of Points
dae68232-3681-525c-9fd4-885d8edb36c1 | tickbox | Feeds - Visual Check - All feeds have been roughed in
e8671ffa-c8ad-5eea-bdbb-7020b5a4edaf | tickbox | Feeds - Identification - All feed cables have been identified/marked
81013077-b40a-5772-9722-4b363632963d | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
71df0e72-ef62-533b-90ef-740a86cc6fcc | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
e167f40f-593c-5840-b2f0-4eb5f39cbacb | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
fc8b21e3-69ee-54b9-8ed9-b36d896f39fc | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
37c278ca-5c59-4395-947f-a4ce4a32ffe9 | section | Inspection 52
8a3a57a3-456d-4b54-b01b-8f5a42c583ee | checkpoint | Has all information been recorded and checks completed?
40fd828c-2551-5bdc-8139-473a7264557c | textbox | Circuit ID
8a313659-fca4-56ef-acf5-b3cc4d5db6a5 | textbox | Cable Size/Type
e0511932-a5eb-52e4-bae0-58efe456b037 | textbox | Number of Points
8ea8d5e1-672c-56da-b3aa-268dcbe46e10 | tickbox | Feeds - Visual Check - All feeds have been roughed in
29da8dde-4726-5f8d-b846-ba4c7df94664 | tickbox | Feeds - Identification - All feed cables have been identified/marked
9ec98a1e-ebdb-5fa6-89e4-5830b814a0e2 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
29190daf-7a3c-53fa-8bdb-fe17c7aed309 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
d567ec63-1708-5208-b79c-0fd66109ece7 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
5644c0aa-6941-55aa-aeb2-4452a5e3578f | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
7656001f-8e5b-47d8-8c5f-92a6494f1c60 | section | Inspection 53
780edc89-5624-47ce-834a-b91044803c95 | checkpoint | Has all information been recorded and checks completed?
e7b70053-8ae1-5473-a4aa-42457dbd88d5 | textbox | Circuit ID
1a08f680-45c6-5df7-a8fe-0304d79416e0 | textbox | Cable Size/Type
1aeec279-01ff-51e0-b886-5e0de0af989c | textbox | Number of Points
2303501c-604f-5600-b80f-2ba2b0be05b3 | tickbox | Feeds - Visual Check - All feeds have been roughed in
bf6b2b3f-020d-5a7f-9627-23274976df44 | tickbox | Feeds - Identification - All feed cables have been identified/marked
15c3d08c-57db-5e72-8c9f-32e85f87b48f | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
0ceca659-3b5f-5eea-aff8-bf3e4a0063c1 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
0b0043e4-a422-5165-8cc0-0d5c5f87311f | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
33ca6604-ed5d-5957-91d5-add1b8f6ce88 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
34c2aecd-5941-475c-b272-e90fa1409109 | section | Inspection 54
68bd5982-2ef4-4032-a7e1-6bfe20fa6d65 | checkpoint | Has all information been recorded and checks completed?
e7657783-98c1-52fd-96f9-b221466162e3 | textbox | Circuit ID
f51e7133-2fa8-52e1-b4a7-0ea5c0a91b58 | textbox | Cable Size/Type
9eada300-b98d-55fc-a469-9790a21839e1 | textbox | Number of Points
bb1b3ebe-3eab-5ec2-937d-a266ce0ddb43 | tickbox | Feeds - Visual Check - All feeds have been roughed in
0373b785-2afd-5c24-bb38-1eff9b8f1026 | tickbox | Feeds - Identification - All feed cables have been identified/marked
b145e637-f277-552c-bf1f-ee2176bdae81 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
73b5af73-26c9-5201-8bb6-556b54111774 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
53374a0c-ddcb-51fc-87e6-c44e5db23fb6 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
00a6d868-98e2-522c-a691-045c0f018515 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
f6b555d1-12ea-4395-94ea-da143e9afc32 | section | Inspection 55
0026bd2b-0e70-41f3-87e1-d11058040d7d | checkpoint | Has all information been recorded and checks completed?
2984aba4-03d5-5384-a5f3-88f144719f17 | textbox | Circuit ID
b3755e03-3537-5a92-94c0-a2c531a54e5b | textbox | Cable Size/Type
9c63fc16-8a9f-5b5b-a0e2-a385574220f5 | textbox | Number of Points
66a910b6-dc3a-5c98-a2d6-a6645fbd5688 | tickbox | Feeds - Visual Check - All feeds have been roughed in
b58df1ac-49dc-5693-aa43-44580ff97cc8 | tickbox | Feeds - Identification - All feed cables have been identified/marked
8405376c-4729-5895-a084-e21061996bf6 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
1b1181d0-0be6-5c82-b2a9-f23f685b91e8 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
119f3b69-dd15-504a-9f7e-f1f2c98d6375 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
5882fae1-cd27-5410-8a0c-169f2ddee447 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
fd0f9403-7924-4198-8022-e5e3c326b103 | section | Inspection 56
5939106f-c160-43ba-9457-e5ec727fd9a5 | checkpoint | Has all information been recorded and checks completed?
f89b603c-98b3-55be-a767-3d2aea0b6975 | textbox | Circuit ID
e7267b07-e0d8-5433-bf2e-5074846739e0 | textbox | Cable Size/Type
01fa8a52-bb36-59f0-bf70-94a8f6da4d63 | textbox | Number of Points
b4a4bc29-4a6f-5dcd-9740-2f5539a6a037 | tickbox | Feeds - Visual Check - All feeds have been roughed in
e95ba703-3acb-5375-96cc-cebe242ce21f | tickbox | Feeds - Identification - All feed cables have been identified/marked
86be66c8-17f5-5869-839f-be9a985ee208 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
3310d8cc-f6d8-53bd-a294-21c8a7a3289c | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
37c6e2a3-67e5-56bf-accf-b08d8e0a7ebc | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
29e84a67-65a1-5f42-adb4-bb017a27d27a | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
db35d957-1cfa-45ab-add6-52c129d6d035 | section | Inspection 57
0fe8620b-5bc2-4beb-ae7b-ec127a477c78 | checkpoint | Has all information been recorded and checks completed?
c6d1db73-05e4-502c-ab04-a35c58518399 | textbox | Circuit ID
15eed241-2ac6-5a11-9856-d60477144170 | textbox | Cable Size/Type
25a8f9b7-7bcf-5744-97bf-3ab579f876d2 | textbox | Number of Points
666d4693-32ae-5567-93e9-87162987c36d | tickbox | Feeds - Visual Check - All feeds have been roughed in
937cd9bd-9c23-5a3f-aa90-d6bca65d9de6 | tickbox | Feeds - Identification - All feed cables have been identified/marked
d1db00db-98c5-51c4-9a55-977650143a27 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
38d404cd-892e-50ec-9766-bf06ae297cc5 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
ec560003-3ad8-504a-9fc8-5c2f06be7266 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
94abd152-82d0-53ae-906b-0c7fbcb4e645 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
83c0cccf-4a0c-4491-82be-d90abb66a603 | section | Inspection 58
93a1c079-fc6f-45dc-a93b-7c87d8c46dc3 | checkpoint | Has all information been recorded and checks completed?
d75de9b4-345c-5681-a462-3cbc6b192779 | textbox | Circuit ID
50b3d23a-5d89-5475-b5dc-60a8e44f10e0 | textbox | Cable Size/Type
fbf1001a-03c3-5044-82da-d1040653ebec | textbox | Number of Points
91ed50d8-51e4-5996-8f1c-1220f75500b8 | tickbox | Feeds - Visual Check - All feeds have been roughed in
0cd88300-5c89-5498-b764-c4b6361a58af | tickbox | Feeds - Identification - All feed cables have been identified/marked
e422331c-c7da-5786-8f49-dc201b49f9b3 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
32f2ca8e-b6ec-5b3f-8690-c61482885247 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
8436fb7b-2e0b-584a-8527-8f93478cead2 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
8fefa701-3dff-5b97-9f78-d7d1e58feee8 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
c2d93a47-35cb-4529-9ad1-09adacfbcfc0 | section | Inspection 59
fd94ef90-edca-4383-bd82-143adda954be | checkpoint | Has all information been recorded and checks completed?
1dd0306a-e4f6-5d9f-8765-95d395a90332 | textbox | Circuit ID
e3a91aba-acc1-5178-b5c7-7013181e2748 | textbox | Cable Size/Type
820130e7-0860-5078-aba5-2792ee70b719 | textbox | Number of Points
5581a430-be6c-525f-981a-7d36001176c7 | tickbox | Feeds - Visual Check - All feeds have been roughed in
78f31e4a-31e9-5c5c-bda0-f2a6698a0e4e | tickbox | Feeds - Identification - All feed cables have been identified/marked
1089f4a0-e690-50b8-84e3-9e45135fed52 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
b1cb43ee-c9f5-57ae-bcd8-c12c269c7e38 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
87dcafa8-3e06-5d90-8de2-f1d08c213e8d | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
532c5a31-cc91-5873-b13c-ef1e174ebf47 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
a497a420-57fe-4d3a-9801-6a0ceae423b7 | section | Inspection 60
f03180f2-e951-44af-83df-bb563044b3aa | checkpoint | Has all information been recorded and checks completed?
205918c5-1df6-52d0-a26f-99caba1e8264 | textbox | Circuit ID
b4ea3889-0cc1-5d9d-9fb0-111fbbe73f14 | textbox | Cable Size/Type
8772f752-f22a-5bfe-85ee-e7db1ff12c4e | textbox | Number of Points
09610da0-73c5-5bc7-a402-725f8b87f30f | tickbox | Feeds - Visual Check - All feeds have been roughed in
fc2b5431-3dfa-5204-8610-2e46d43e7396 | tickbox | Feeds - Identification - All feed cables have been identified/marked
8a4a3428-98e5-54db-8721-f73bfa4354c4 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
9dd6cd40-cde3-5a66-853f-2ebecada3752 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
8d00d4d5-311f-5531-9133-e87c77f1ca9f | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
509368f5-f631-5c0c-99d3-f885119c5576 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
8fe1d2e9-bc83-4633-807c-f9c29e7b7ea1 | section | Inspection 61
ffe8fa5a-e1f5-468d-b5f6-08960b148590 | checkpoint | Has all information been recorded and checks completed?
d9de20c0-336b-5123-aba2-cc9585890aab | textbox | Circuit ID
15c53cb1-ba90-57e9-bdf4-aff8c0aef853 | textbox | Cable Size/Type
c8e5e7e3-fd99-5773-bf7e-06cfcdf4d805 | textbox | Number of Points
4ee0a60e-4934-5c1d-bae7-1a18c6ff9db7 | tickbox | Feeds - Visual Check - All feeds have been roughed in
0eecfde6-6486-572b-97a3-4373a83adbb5 | tickbox | Feeds - Identification - All feed cables have been identified/marked
2c604bde-276f-59f4-995d-b10dc8e08851 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
cec8b4b0-34fa-5fdb-a92e-6f6efc46b2e5 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
9009f90a-20dd-52b8-84a0-cc127c05f84d | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
ba815f03-4624-5752-b23a-df5ebf877910 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
258ac9ce-4482-403b-86f4-121bc5de3056 | section | Inspection 62
0fafdfd5-76eb-4943-9d7b-9d97ddba40a1 | checkpoint | Has all information been recorded and checks completed?
b7c98c56-a745-5ee5-a10e-94dc004083a4 | textbox | Circuit ID
a9b419cf-9365-5dcf-92f0-fb6ceff5fb9c | textbox | Cable Size/Type
fcd30873-78a1-5566-ba5f-445f9fa21e19 | textbox | Number of Points
d3290bc8-80ce-520d-9b2c-094454eace1d | tickbox | Feeds - Visual Check - All feeds have been roughed in
9512bebc-6081-5aa9-b74a-6e6344298a95 | tickbox | Feeds - Identification - All feed cables have been identified/marked
b7277728-486b-59b3-814a-db6a8624e72b | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
84849e79-9a6b-52ae-b6b6-96a018dae534 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
ee4b5843-c65c-5641-9b12-ce458ae0d13d | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
6c534ffa-98bc-596f-895b-9374f332c51d | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
3aa60ede-891b-47e4-a87a-b0ccb6009935 | section | Inspection 63
0baa5747-c515-46b7-a07f-5090e80adcec | checkpoint | Has all information been recorded and checks completed?
6332cd57-fb39-5c82-91cf-cb68f5606517 | textbox | Circuit ID
b5936512-e3ec-5f30-90e9-59edacd2efb2 | textbox | Cable Size/Type
bfe74343-a59f-56f9-814f-4b66faa92576 | textbox | Number of Points
921c6ee2-6022-581c-9c56-6ef26a79b2ea | tickbox | Feeds - Visual Check - All feeds have been roughed in
76f0c146-44dd-57a7-ad30-0ee41a4588b5 | tickbox | Feeds - Identification - All feed cables have been identified/marked
81f44e58-1c81-5b95-a233-d19488f66c65 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
a5023755-3f85-569b-8454-e6c7b32b0d28 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
e4152de2-260d-5e91-bac2-4225ad34932a | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
40a0c56b-8b04-5835-a93b-cf2ef095f190 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
42918745-0459-4bbb-9b97-f4b1da49d162 | section | Inspection 64
e52b60fb-6eaa-4ac8-b900-9a736725b8ea | checkpoint | Has all information been recorded and checks completed?
bbde8386-4b91-5e51-851a-2cb53e0e9358 | textbox | Circuit ID
334dce34-bb08-52c9-a138-41c0873375ea | textbox | Cable Size/Type
991bff44-a94e-5ff7-840a-44f44236bc31 | textbox | Number of Points
4bd5cb14-8b66-5cb6-a1c0-acf2efc0b291 | tickbox | Feeds - Visual Check - All feeds have been roughed in
4dc69406-1d37-55e5-a0bf-c73ed0847547 | tickbox | Feeds - Identification - All feed cables have been identified/marked
3fee12ac-566a-5161-8fa0-8dcdb4526a97 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
09ffe632-11df-5049-9830-69a8fa850176 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
3359a470-b9cb-5934-89a8-b4c71a7603ce | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
46a52f82-08a2-5f79-9ad3-51835287ce1b | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
f1d688ff-fa5a-4ca3-b037-b0779b362034 | section | Inspection 65
7b27a6f0-dd54-4b41-ae7b-887e804b8e6e | checkpoint | Has all information been recorded and checks completed?
0024f917-5952-59bd-8060-3c225782bcae | textbox | Circuit ID
f7a78243-a76a-5319-bf41-43308c255a87 | textbox | Cable Size/Type
0a74a538-d0bc-5c8a-b089-5ee80f97f037 | textbox | Number of Points
8f2457d0-2565-5314-b615-0d0a14bfb7b1 | tickbox | Feeds - Visual Check - All feeds have been roughed in
46e1f4e9-e9e2-5afe-b728-c8296fe374ca | tickbox | Feeds - Identification - All feed cables have been identified/marked
4b9b421c-7880-5193-8a00-86a73918730a | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
ec6d0a16-2ee4-518f-8b79-8e75949a01ce | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
9a5a2d62-3684-5bb6-95c6-adba8c172117 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
fdd29a9b-1d7c-5300-9480-69201e25e85e | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
f3fce7c0-0fd4-4d08-b281-c13ff92add4a | section | Inspection 66
b09afa04-2469-4ee1-8f16-e2bed8719d71 | checkpoint | Has all information been recorded and checks completed?
7b3dba89-8719-5a66-942a-30d80430e419 | textbox | Circuit ID
d58f8849-67f3-5005-b7a0-fca72242531f | textbox | Cable Size/Type
fa7e2294-4dfd-5c69-94b6-0630b25f0f5f | textbox | Number of Points
e591c919-7e2e-5bd5-bd7a-fbd24d21fca6 | tickbox | Feeds - Visual Check - All feeds have been roughed in
57df5fff-a4eb-5faf-9da6-3252aead728c | tickbox | Feeds - Identification - All feed cables have been identified/marked
b9f9214b-55db-5764-8831-45e22853c208 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
b1b0dd47-a1f3-5476-af63-20311b25e1ec | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
d3953788-26be-5eb2-9871-7b8b33f67f1c | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
0c099ee4-36f9-5d0f-a43a-4642219e7375 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
62006853-0d35-4dcf-9886-793ad4f0db47 | section | Inspection 67
cfabc097-87b8-4052-88dc-07c86a149491 | checkpoint | Has all information been recorded and checks completed?
62c5ac10-04b8-5e8f-87f8-dea79499a244 | textbox | Circuit ID
b322cea3-17f0-54e5-9b5e-d0661a800f7b | textbox | Cable Size/Type
c489cac1-3bd6-51b7-8d8c-54187f9e3a62 | textbox | Number of Points
bf86f606-ebf6-5433-89fa-3d75b9402ef3 | tickbox | Feeds - Visual Check - All feeds have been roughed in
6fd82182-30f5-5c80-b815-db000ccbcbe2 | tickbox | Feeds - Identification - All feed cables have been identified/marked
15c01c7b-afed-53ef-a3c1-f32d0bf4d92a | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
b9f11aba-9397-58c4-a557-974bd3a7bffc | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
ad0b4257-0fe8-55b4-82c4-eff19bffd677 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
ca525d11-f656-5348-8eb8-93fd29850096 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
64991b38-8199-42da-a612-a909651dc253 | section | Inspection 68
2d3f2e1e-aecf-4e2a-aaeb-8a87255db276 | checkpoint | Has all information been recorded and checks completed?
ee8f4f58-5968-5c86-a144-44a8f62cc113 | textbox | Circuit ID
3023fc74-d458-51c0-8a0d-79d36fce072d | textbox | Cable Size/Type
ab274edc-6f82-588d-a83c-bea62e44bcad | textbox | Number of Points
727bb62d-59a0-51eb-a5f4-4d8bfabfeb5c | tickbox | Feeds - Visual Check - All feeds have been roughed in
b73c48aa-dc8f-5f43-a66b-edde664ce628 | tickbox | Feeds - Identification - All feed cables have been identified/marked
2879f607-7f75-57fc-87f0-e7bdd9c8c5dc | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
48501add-a842-5047-854e-27c82deddfed | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
ebbe6557-de1d-5fdd-aca1-dd9d9fe9b076 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
badb3719-4a35-5777-b21c-bd3cc8d46231 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
6a36dac0-ef02-4f3a-8bd0-4b22aa19f026 | section | Inspection 69
f4ecac42-08d5-4ace-83ba-ae91856881ba | checkpoint | Has all information been recorded and checks completed?
95f3386f-a6d3-5783-b058-8b57e27d1003 | textbox | Circuit ID
6188c2ea-60a5-57fa-b9fb-2706fde6aa3b | textbox | Cable Size/Type
25062709-eacb-5ccb-a939-298e18286509 | textbox | Number of Points
95d2f006-ba73-5fe9-b245-79d8937b5128 | tickbox | Feeds - Visual Check - All feeds have been roughed in
b2d1b2e6-a760-5e9a-9d59-0e9d8386cab9 | tickbox | Feeds - Identification - All feed cables have been identified/marked
3d569613-18d4-5a98-839d-4913fad90920 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
d4cc07e4-9546-5c75-896b-9306b0737839 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
b20be146-dcd1-503a-a1e3-7687c71b8c4d | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
aa38b0af-b834-563b-8fa5-da1d65132e78 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
f09fd8b5-0d3a-4830-abcc-dd9932a31941 | section | Inspection 70
5f228956-5758-42e9-a394-4d27e3592181 | checkpoint | Has all information been recorded and checks completed?
409aa4a8-c7c5-5afa-84ef-4542f7055d14 | textbox | Circuit ID
d21b5d35-6b16-5169-a70b-59ceb0a26115 | textbox | Cable Size/Type
0566884a-b8a9-55e7-bc84-f131c02ce5d7 | textbox | Number of Points
43d34c05-f6f7-5b89-9d22-ddb077c3e18b | tickbox | Feeds - Visual Check - All feeds have been roughed in
feac25c5-3573-512a-9729-8e4b099dc828 | tickbox | Feeds - Identification - All feed cables have been identified/marked
234c96ec-c21d-546d-b274-fb8c5a4b7a52 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
5cf3dc93-e830-58ff-bef5-5955a56eb06f | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
8cef61d4-dc7a-5dd9-94b8-904ad491425b | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
619eb0af-2e13-576c-afa1-a010298743f4 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
ccf2a358-baf7-4a1e-a67b-3e09cd173dc8 | section | Inspection 71
17f46a8c-2686-4c59-808f-54c09decf350 | checkpoint | Has all information been recorded and checks completed?
af1c330b-72ef-5727-8e3e-4d0ef3385dd9 | textbox | Circuit ID
9c779e9f-caef-557b-882c-396ec297c234 | textbox | Cable Size/Type
5cd591f4-1e24-58d8-b3e7-0f5b92fde973 | textbox | Number of Points
cbcd25df-9134-5c15-9796-5c607671f90f | tickbox | Feeds - Visual Check - All feeds have been roughed in
7328e1b4-dd3f-55cf-a8e8-814ba9ed8581 | tickbox | Feeds - Identification - All feed cables have been identified/marked
512eb501-f631-5dbe-85cf-ff7a30eb353a | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
39f73de2-a374-529f-8153-93d3c6ed9c16 | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
dd6ee324-b03b-5dbd-b629-737108907c97 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
2d9fcc61-5859-5164-931d-9003c2828d43 | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
e2afce90-036c-422f-ab81-e22efe6debf8 | section | Inspection 72
13c000ce-f342-4dd4-8b06-0207a9ba281d | checkpoint | Has all information been recorded and checks completed?
9627a4e6-3ab7-518b-ac4b-69cfa8e5a727 | textbox | Circuit ID
d1cff54a-ddf1-561b-a8f6-ec165116d09e | textbox | Cable Size/Type
ded790a3-91f0-5e9c-9e45-05df00e6395a | textbox | Number of Points
4a3f66cc-cece-5dc7-93d2-69b20b91a303 | tickbox | Feeds - Visual Check - All feeds have been roughed in
ef017566-0798-5c65-bbae-1600175dd334 | tickbox | Feeds - Identification - All feed cables have been identified/marked
23bcd997-e7ff-53e4-a8aa-816decec1e30 | tickbox | 1st Rough In - Visual Check - All cable loops have been roughed in
fb2ef4e4-e7d7-52db-8e27-5ca4efce988d | tickbox | 1st Rough In - Identification - All cable loops have been identified/marked
de6925ee-2c0a-5bf6-8285-1cc4e5d891e7 | tickbox | 2nd Rough In - Visual Check - All cable loops have been positioned and ready for fit off
c6352b13-d904-56e8-8e82-a1dbac4754ff | tickbox | 2nd Rough In - Final Check - Ensure cable is appropriately identified and made safe, if required
09edb9d1-e5c1-433e-a05e-319373dc00b8 | checklist | QA_TEM_043_Fit Off Checklist |  | QA_TEM_043_Fit Off Checklist
ef50974b-2e9f-4253-b697-f9517869b2a1 | section | Inspection 1
4c840b99-53a8-4aac-9d30-de84bcee0f6e | checkpoint | Has all information been recorded and checks completed?
ce772ec6-8fc9-5873-8278-d2f0c6be06c4 | textbox | Circuit ID
e9ab4b9a-ff02-5be8-b5af-bb9606ce5787 | textbox | Number of Points
e941150e-2d11-55d5-b527-0b998984681f | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
020196d9-6a5b-58eb-920e-2f1c71c45325 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
94722888-f256-5c31-984a-3e95e80c94b0 | tickbox | Final Check - All fit off complete, ready for switchboard termination
f678d880-ffd4-4445-8676-212c0984bb03 | section | Inspection 2
1eebefc0-1c39-4d89-95e9-c0cbb8e9c263 | checkpoint | Has all information been recorded and checks completed?
24573a1b-f2f2-56a7-b08a-e19dbd6c319b | textbox | Circuit ID
5f392dd9-05bf-5631-9fa1-838e6044d5fa | textbox | Number of Points
71189691-7446-58fc-8e18-844f6862076f | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
7f636c59-43cd-587f-bec5-ff492c2932f0 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
8008d6d4-e84d-51b7-a71c-9a392b30b164 | tickbox | Final Check - All fit off complete, ready for switchboard termination
289599a6-8f7e-432f-8758-8744934ebd8b | section | Inspection 3
ef048b59-5a30-49cc-9c8e-92a615395770 | checkpoint | Has all information been recorded and checks completed?
29506e83-bdb0-5915-a1dc-8f4926cdcf57 | textbox | Circuit ID
3d342514-b144-5de7-9d02-c85f9c632d4f | textbox | Number of Points
5936fd17-3e72-586f-ae4c-ccf8ac40fdd4 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
c6564564-225b-5a5d-a0e3-e5f183319e86 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
30ff84c2-bd6a-50e2-9880-6d428d21ccf3 | tickbox | Final Check - All fit off complete, ready for switchboard termination
a8fa4f0e-be10-4dce-a8ad-fa4a35fcd87f | section | Inspection 4
80ce9f26-81f6-4908-a61e-02df650586f9 | checkpoint | Has all information been recorded and checks completed?
10217e52-d8d1-5639-9839-7f3ec4a28d31 | textbox | Circuit ID
2a7dd868-8646-52d1-9752-23d339be64e0 | textbox | Number of Points
870bd15e-c587-5035-a5fe-910d29ca2770 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
ba724de3-e990-558c-9221-8a27d91d78fe | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
f3030239-8097-5a4b-8463-daccfcdde92a | tickbox | Final Check - All fit off complete, ready for switchboard termination
ba53fb17-a92c-41f8-8dfe-a2ae9d995941 | section | Inspection 5
fe92e1a7-4feb-4d36-a71e-3a0a346a7ed4 | checkpoint | Has all information been recorded and checks completed?
ca40c243-b72f-51a7-bc1a-f93244daea08 | textbox | Circuit ID
c3fa6723-2ee2-5f85-bed9-24a8ccbc45e0 | textbox | Number of Points
0ad3f9df-d4bc-53ad-9051-9b7a4278364b | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
10295413-3aa6-5e7d-9171-fd2921049d47 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
414b7e36-456f-5962-bce5-00645c11adfd | tickbox | Final Check - All fit off complete, ready for switchboard termination
292bca13-4091-4780-9b59-ef296556c97f | section | Inspection 6
a6d9e39a-9a0c-4d59-8d18-c087512c519e | checkpoint | Has all information been recorded and checks completed?
a78bd9ec-d8ed-5bd7-9da7-ded2114fc249 | textbox | Circuit ID
cfdd1110-1ec0-5be0-a943-95bdc9813a51 | textbox | Number of Points
dfc4cd59-22b2-5c96-b0ec-3623a4fe59f3 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
5d944abe-3490-5a1d-bff5-b12d0d11f65d | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
69b23686-404c-55e9-9cc1-7cb7f589ad7a | tickbox | Final Check - All fit off complete, ready for switchboard termination
cbc102dc-a4b4-48e9-b7fa-f81062a7942c | section | Inspection 7
abbd62bd-1a39-4b00-8429-72708427a440 | checkpoint | Has all information been recorded and checks completed?
9f736df6-fcfc-526f-af19-63023b6ec935 | textbox | Circuit ID
9825313e-b747-5755-8a0c-ef78280e7843 | textbox | Number of Points
2b4de4a8-1539-5447-9714-f7ca3ce5b9a6 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
e047b37f-befb-5dee-9810-a9b1b8366ebc | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
0bf389e4-7f60-5db8-a83c-8cf082970e99 | tickbox | Final Check - All fit off complete, ready for switchboard termination
29d2312c-8974-420b-8f37-c320149aca3c | section | Inspection 8
185cdd22-0ffb-4db7-b517-6f6e9ea7317b | checkpoint | Has all information been recorded and checks completed?
172519f4-7242-55ab-806d-273ee083f86b | textbox | Circuit ID
49336568-8f0e-5b2c-aca5-10c58464c6b8 | textbox | Number of Points
1715cc5d-7ecd-51c9-8b5d-c3ae0cf0298e | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
582cc0a7-5cf1-50f8-8c9e-292c6bd61ddd | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
872bdb4b-2068-5ec2-a273-8a7c361f2656 | tickbox | Final Check - All fit off complete, ready for switchboard termination
cf97968d-2a73-4018-b3c4-d3781993e5cb | section | Inspection 9
44ec8263-414f-4e44-94d8-8d69e5e8093c | checkpoint | Has all information been recorded and checks completed?
d1f9f95d-5de4-5150-b1f7-b8feb18dcbdd | textbox | Circuit ID
5e8aeba3-82e3-5be9-9361-fca12b8747d1 | textbox | Number of Points
0a1facb2-84a0-516a-bc1d-690c06990600 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
b2e0e114-38ac-53e8-bb57-b78921feefc4 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
2e1cf873-53ad-5b51-83ff-fabaf6a3123f | tickbox | Final Check - All fit off complete, ready for switchboard termination
9cef4d8a-4483-4117-92ea-a24da0911f96 | section | Inspection 10
d1c2bbbf-38fc-4030-a3c7-c909b6928f9e | checkpoint | Has all information been recorded and checks completed?
87f0bf04-365a-5ffb-a257-c6c85c2cf2f7 | textbox | Circuit ID
e1fc2285-ae83-593f-881c-552be96ac147 | textbox | Number of Points
d7a71324-f38c-5690-a4cb-93977d3628bc | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
31275139-dfe0-5fdf-870d-61b305bddb22 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
521b68d1-129d-527e-9fd0-9b2e7b9c4fc3 | tickbox | Final Check - All fit off complete, ready for switchboard termination
5ec8f7ec-1a1c-4673-a724-79662990d0bf | section | Inspection 11
674c43e3-6e8a-4ded-be5f-0960694a1413 | checkpoint | Has all information been recorded and checks completed?
b71147c2-7057-5dba-8255-4e29d0cee197 | textbox | Circuit ID
6afe47a8-8ce0-5669-851b-c64fd36e2473 | textbox | Number of Points
31193ea3-b7c2-53be-b4d3-f274c8bda886 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
01de5ab0-b6cd-5abd-b596-db7a3bed6a4f | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
ca2b18d2-e776-5f61-8e71-cdb033c7d451 | tickbox | Final Check - All fit off complete, ready for switchboard termination
aace6e63-1c08-4885-9909-d1063b8ffd04 | section | Inspection 12
0a9d92cc-7173-4a4d-8d76-e6065c6bc6bf | checkpoint | Has all information been recorded and checks completed?
a5bcc7a4-55dc-517f-992f-541e32a0b6f2 | textbox | Circuit ID
9eee4ede-335d-58aa-8040-375a8c479cf9 | textbox | Number of Points
9ca87287-7c16-5c48-abd3-80c638641e52 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
4244411b-33df-5bd9-87b4-6aa1dc159180 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
bc7b65be-db77-5c19-af12-97b4b980960d | tickbox | Final Check - All fit off complete, ready for switchboard termination
b52b8200-dfc4-47c1-87a5-f69e3f5144b7 | section | Inspection 13
1e2965e8-63d1-4b8b-922b-0d26202328fb | checkpoint | Has all information been recorded and checks completed?
8040f234-eefd-5f08-ad84-2e0eed73a3e2 | textbox | Circuit ID
a0f99e3d-3228-599e-a2e2-f4beb96f4fe3 | textbox | Number of Points
e3ea0df8-75b3-5bcd-b03b-75eda0c40c15 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
d5377915-aef9-510e-8a0c-f9ed3b3599aa | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
2f7b536d-e849-5aa2-ba0c-0097efdf1145 | tickbox | Final Check - All fit off complete, ready for switchboard termination
f7dc6776-ff89-4a9f-afff-dff7ed11558d | section | Inspection 14
6042312a-a472-497d-9bcc-801de7cd032c | checkpoint | Has all information been recorded and checks completed?
ece74818-bb8e-55ca-be17-b947c6fadec2 | textbox | Circuit ID
4984c13c-8a0c-578a-ad1c-c46da365f865 | textbox | Number of Points
57bf1e71-4596-51b1-8467-ac7fcacc56b9 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
9695b3c7-3692-5041-8a79-0ab3f38257c9 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
6fffb58d-f385-5d2a-bb68-df27c955d986 | tickbox | Final Check - All fit off complete, ready for switchboard termination
d9c8ce58-d298-4ddd-a474-5e036da4fe49 | section | Inspection 15
64b27ba9-a224-4e48-be7b-ef313ebe41b1 | checkpoint | Has all information been recorded and checks completed?
3b30d40d-335c-5d30-8e38-a69e32b0688b | textbox | Circuit ID
604ea64a-afbe-5b03-ad84-47c5015064d8 | textbox | Number of Points
855d4ccd-b200-504a-949a-c451807bb3a6 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
b9abbcdc-1792-5b5b-8b46-d52e9d10d639 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
9fc86291-0efb-5bb6-95f5-72506e366c06 | tickbox | Final Check - All fit off complete, ready for switchboard termination
fcef3cd5-8aa6-4a45-a103-5048127df58c | section | Inspection 16
51a33fbf-ce8c-4c2f-9471-ad3ccee403c6 | checkpoint | Has all information been recorded and checks completed?
314abf97-d0b6-5703-b659-0c617efe4e71 | textbox | Circuit ID
218badd3-dd4f-5435-873f-c8cf5ae1effe | textbox | Number of Points
6680467f-bfe7-5558-9b54-16aaf11bb2b9 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
6cbccacc-83bb-5f89-8185-c2dc55bed9ee | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
194050e8-6e3a-55df-9093-14660b0837a7 | tickbox | Final Check - All fit off complete, ready for switchboard termination
357b66d8-9918-4990-863e-0a8de24ae577 | section | Inspection 17
29471b67-c250-4843-b4be-a5ec9bf0152a | checkpoint | Has all information been recorded and checks completed?
167cc5c8-e872-557a-a74d-ff0eb8c1b053 | textbox | Circuit ID
fcdc988b-3758-567e-9670-76629d6da59e | textbox | Number of Points
78e33f9e-7d59-5bda-b63c-8e7de5cc3f62 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
5feafe9d-9dfd-5f02-b613-13a5a80bedfc | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
d966c12b-0982-5662-94c4-7b7981035386 | tickbox | Final Check - All fit off complete, ready for switchboard termination
99ba1833-350e-489c-8447-b6cfbfd77aef | section | Inspection 18
4f5617b1-cb44-44af-a8aa-738cb375f86c | checkpoint | Has all information been recorded and checks completed?
6f447d74-4f81-508f-af0e-58d7dbb83485 | textbox | Circuit ID
04bc704d-b9f8-5d09-8d24-e084f342971b | textbox | Number of Points
9a7c75d6-bac3-5703-a571-24ca67713aae | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
6b239e26-9663-5e1b-9960-11583343ec85 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
1dab8f9d-6ae2-5a7b-9b8f-770ff3829a2d | tickbox | Final Check - All fit off complete, ready for switchboard termination
feac1ede-c92b-4017-8fe4-aad6b2634434 | section | Inspection 19
534a2e3d-f754-4eee-90be-32b10de187df | checkpoint | Has all information been recorded and checks completed?
6e8bf733-9ed4-5ef4-b85a-453758189f14 | textbox | Circuit ID
9cb39182-4118-5da6-95f9-20ec973512bb | textbox | Number of Points
1ff77d81-1323-54db-bbd7-6d5b24b3719a | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
e65f0eaa-b99b-56c1-8730-f52219988822 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
4abd1fb6-edd2-58f2-bedf-ddaa24b77074 | tickbox | Final Check - All fit off complete, ready for switchboard termination
35b64d58-1f01-4abf-814f-c066bf9e6989 | section | Inspection 20
7f28d0e3-352f-409f-80ce-6f2bdba1b239 | checkpoint | Has all information been recorded and checks completed?
82ebcdf6-0e75-5393-b0b4-71dcc3506a71 | textbox | Circuit ID
d7a194ef-f13f-5a13-b3b9-ac54e4632b2c | textbox | Number of Points
31cb5d27-c4ba-55b5-90be-d50991ca93db | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
340ffb55-b04b-54ca-a9fc-bbe4084edb34 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
be180eb4-dd6b-53f5-9c31-0a03e26f7633 | tickbox | Final Check - All fit off complete, ready for switchboard termination
a548e874-e022-45bf-983d-cbc59d45dea5 | section | Inspection 21
a7214e5e-f098-4e0b-b0ee-23d85d08f6e5 | checkpoint | Has all information been recorded and checks completed?
b948e99d-141c-5635-aea3-7d8e2008183e | textbox | Circuit ID
033f83ae-2e46-5850-b4f2-ce5332a3907b | textbox | Number of Points
23d1ebd1-aab0-5326-9536-bd4e60d9d2f2 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
da4fd58d-a0c7-55f1-bf37-5d9b0d098c53 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
f00d9858-9a3d-5a4f-a9f0-ae7fb6bb4433 | tickbox | Final Check - All fit off complete, ready for switchboard termination
3b82a6e7-43af-4e97-9784-624abd1cf13c | section | Inspection 22
b96f9fe2-9951-4869-811b-dea3e6243f30 | checkpoint | Has all information been recorded and checks completed?
af554eb1-29ce-58fa-a60c-9f9fcde92120 | textbox | Circuit ID
dda70522-4e57-56a6-b561-1a924eed458d | textbox | Number of Points
f5289ad8-aa0f-5145-8a6a-5bf09dface9c | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
c3852e13-a5fe-53fc-ad4c-2981d7d1643f | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
4a2c7875-50f6-5db9-90cb-3c57da881279 | tickbox | Final Check - All fit off complete, ready for switchboard termination
292d19e8-8f01-4485-9066-c6da1b99b5bb | section | Inspection 23
a2d89a55-a8a2-4c9f-8920-a4e506768faf | checkpoint | Has all information been recorded and checks completed?
6e8263c3-fe39-592c-b55f-0eedc8340854 | textbox | Circuit ID
ad16b4be-02d2-52eb-87e8-60a3b3d14dd1 | textbox | Number of Points
a88cfa21-d54b-5b99-a950-da0e995ece82 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
d8fbf685-59fc-56cb-8dce-7fb9d5b0944d | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
1e904f7e-501b-5b3e-9dfd-0b6843404c4e | tickbox | Final Check - All fit off complete, ready for switchboard termination
0d0fa3d4-d388-4f66-bc2f-7cbdc5e0fa51 | section | Inspection 24
afff9795-abbb-4077-8944-1e892f5ad6dd | checkpoint | Has all information been recorded and checks completed?
38a99804-8b55-54c1-8989-1e81981a909b | textbox | Circuit ID
b22b6424-3608-5acc-8ec9-e5eaebc47337 | textbox | Number of Points
9a31baa5-20ca-581a-9c51-8c1dd8c9e432 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
13ffe777-631c-5a4b-a6a7-2855f3a6167a | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
156b2693-c6bd-555d-b565-26dc97e21b0d | tickbox | Final Check - All fit off complete, ready for switchboard termination
f6e7beb5-d83f-4099-a767-5624a34f9a9d | section | Inspection 25
e08ef9de-ee02-470e-a9d0-e7fda25a194d | checkpoint | Has all information been recorded and checks completed?
198fdfa1-f774-5508-9e4f-82ead93b6525 | textbox | Circuit ID
41fa5b68-a27d-5d9e-a22c-9d0c09687b4a | textbox | Number of Points
821b291e-5dbb-57b2-8725-9cfcaf8ae9a5 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
acdbedf7-f392-5de9-aad8-c1cc55c3e1e6 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
c2c29aad-1652-5b1f-8eb1-97d6f19a62cb | tickbox | Final Check - All fit off complete, ready for switchboard termination
ec501334-e590-4733-b073-81a5d6a5eb4c | section | Inspection 26
54a62d48-05ab-4b43-afbc-52ffec61aa7a | checkpoint | Has all information been recorded and checks completed?
c5ff98ed-eb8d-5c81-b5e8-fa6c4396a257 | textbox | Circuit ID
955c51fd-eb75-5297-ae5a-0374240a5a86 | textbox | Number of Points
b371ee56-38ea-5c7d-8818-0850389a7980 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
3df2678d-0893-5da6-b3ab-c9259115cd9f | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
e91bd0d9-3f95-5c4b-8c2e-a842c91ace4d | tickbox | Final Check - All fit off complete, ready for switchboard termination
3a4b9b3d-a737-457b-a95a-58945a7987fd | section | Inspection 27
1b4da8ea-d96c-4a81-a544-5a1716946441 | checkpoint | Has all information been recorded and checks completed?
954b21ae-b780-5c35-b240-473b2b4ec95c | textbox | Circuit ID
86f92ab9-9c3e-54dd-b07c-d3ba93de2568 | textbox | Number of Points
63749cac-feff-5d91-aad4-fa85d54e99e8 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
80739c1a-9b41-5cdc-95b2-7125f853b363 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
c549ff60-4f99-5406-a684-9cc8655d9902 | tickbox | Final Check - All fit off complete, ready for switchboard termination
e5262706-baa4-4b8d-8251-622b5387418d | section | Inspection 28
ebb5b28d-b3a2-428f-bb2c-e2eefc9de5b6 | checkpoint | Has all information been recorded and checks completed?
6a8fa48f-e87e-55fe-a19d-5f6879f9bb2f | textbox | Circuit ID
bc3b16b8-f7ac-5621-b21a-968504537dc2 | textbox | Number of Points
bc6063fe-4d3e-5491-916b-67b55f951a87 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
1f1b5b71-4082-5899-97d7-871e9a42be2e | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
2b26d4a7-7364-5b3d-8de7-8ef45d5b74fc | tickbox | Final Check - All fit off complete, ready for switchboard termination
9f8f93ae-1867-4c9a-9f65-d378de2dd829 | section | Inspection 29
1db91500-d873-4ad9-8c61-55eeb5f09c88 | checkpoint | Has all information been recorded and checks completed?
cff06494-a71a-5541-9d91-b012b9e6415f | textbox | Circuit ID
1422814d-5ae6-5184-a249-42cc46e78ade | textbox | Number of Points
122b355e-2b7e-580d-9d9b-b6b2dc56cb40 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
cbcedee2-a969-54d0-847c-5f04431fdc32 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
a9802dfe-ff7d-52d7-baec-1e7446770b3e | tickbox | Final Check - All fit off complete, ready for switchboard termination
aa526434-439c-4cf0-93d4-be546d2095b0 | section | Inspection 30
c6033491-6686-46b3-ba44-07152ececd78 | checkpoint | Has all information been recorded and checks completed?
f6342502-74bf-50b0-87da-80a26a859590 | textbox | Circuit ID
38561f90-a693-5df4-8e57-7f7a61543829 | textbox | Number of Points
ced99d08-5f7c-5348-8d89-87b9f52f4997 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
b381a552-34d4-5b2a-bf20-5cec67e322f0 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
fba38021-fbd0-5513-8d1e-7b835e16b468 | tickbox | Final Check - All fit off complete, ready for switchboard termination
57dfe6d8-bbc3-42d0-97c4-81b5bc1eb185 | section | Inspection 31
72ac49f1-0baf-4c6c-8485-1ac1f2c1faef | checkpoint | Has all information been recorded and checks completed?
271c6acc-6b9f-5a6f-a9c5-ef610bfa1f0e | textbox | Circuit ID
ef99d606-4a71-5e50-bc94-c136a7fc5d2e | textbox | Number of Points
057210ed-28aa-51a3-9f1a-33153cf15d43 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
df187500-652a-5f08-87a4-183532576054 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
664602ca-c089-5180-aa98-f1ab56e63a00 | tickbox | Final Check - All fit off complete, ready for switchboard termination
6403d748-8e3f-4ba7-ac62-083249982856 | section | Inspection 32
46a1a349-a1c0-423b-a932-4b5e3974babc | checkpoint | Has all information been recorded and checks completed?
15ff9f69-9466-59c3-86cf-9e186ef31fe4 | textbox | Circuit ID
ca0baf39-0476-5a60-a5df-b405e217ffab | textbox | Number of Points
274586fa-a59a-5588-9693-cd35b2c9c158 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
7b0d511c-a5cc-5ca1-889d-b7937f8078fa | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
a873ddf3-30ed-5a8c-a012-06dc54ce596f | tickbox | Final Check - All fit off complete, ready for switchboard termination
59636985-0c52-49f0-8376-dd59c28c2b60 | section | Inspection 33
274b14fa-6601-40eb-9b33-35d59ac07a13 | checkpoint | Has all information been recorded and checks completed?
50f4a535-e425-5953-8974-eed4ccb83088 | textbox | Circuit ID
4c0b1b65-a669-511d-ba8a-9e44e47effa5 | textbox | Number of Points
75ae12c1-2dfa-5614-8e2e-1b97dbb55c28 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
ee4b4c3b-3620-583c-8e5d-7d329e2dbf22 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
e6693141-e720-5955-a408-f3fc39223029 | tickbox | Final Check - All fit off complete, ready for switchboard termination
f074aa2b-9009-4287-bb05-25872d1c821d | section | Inspection 34
5ec9d5a8-6f56-47ff-937e-c300750a5ecf | checkpoint | Has all information been recorded and checks completed?
9666ffad-f9c7-5f4d-8821-59b17b0e0a7c | textbox | Circuit ID
b251e720-7b16-58f3-a83f-74a7fc00c627 | textbox | Number of Points
c61328c3-61f6-5462-b74f-1e0af441792c | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
97eb7c4e-5987-52ee-a672-f94c88a5492e | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
db140276-a38c-51fb-8ae2-13663ffd63fa | tickbox | Final Check - All fit off complete, ready for switchboard termination
adae137c-8870-4345-9440-0e7964ba2bfe | section | Inspection 35
964e5716-4a97-437d-81c9-6827f622a677 | checkpoint | Has all information been recorded and checks completed?
45ab7405-68d1-50ca-a484-8b371b8fe48d | textbox | Circuit ID
a0ea66f5-d674-54c0-b9d3-b08285d93abf | textbox | Number of Points
d8fb6270-732e-5820-b351-4db344174ca4 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
d64050c4-fb62-5d97-9f58-e872a80e625b | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
cec3c8ea-73b8-5b1e-8940-79225a44d940 | tickbox | Final Check - All fit off complete, ready for switchboard termination
ae3ba3e8-8813-4e38-a1c0-8baf81ca9ccb | section | Inspection 36
2fd1a567-1d44-4116-981a-212ad205b593 | checkpoint | Has all information been recorded and checks completed?
be719b07-408e-58a2-9690-6e0d59b712f1 | textbox | Circuit ID
df181da2-efbd-5458-8b1c-3960e899d6f5 | textbox | Number of Points
fd4054c0-d874-5349-aa7b-2d67068a1fd3 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
6c9e0da4-e264-5968-a2d7-22b389619508 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
48b38037-4195-57b6-9903-2e939146093f | tickbox | Final Check - All fit off complete, ready for switchboard termination
5ffbd122-4ea9-4c22-ade5-c786954837b8 | section | Inspection 37
9b528200-6ccd-4d33-92ea-9856e788e54c | checkpoint | Has all information been recorded and checks completed?
dfad80ce-61a9-57e4-8431-e4b323c07f29 | textbox | Circuit ID
aa8e326b-9d5c-5d64-ac7f-d7b7cc1b555e | textbox | Number of Points
6edbae9c-8632-535e-a37a-84baa477d71f | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
a7208154-8212-5b8c-ab5a-9c73fb1d79b2 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
758303ce-7cf5-5e79-a1cb-36f6353b71f1 | tickbox | Final Check - All fit off complete, ready for switchboard termination
d6f855da-6113-4d8d-89fd-10b336bda76f | section | Inspection 38
f961c714-2907-499b-be5b-f87cfa4c8a99 | checkpoint | Has all information been recorded and checks completed?
ed603325-bad8-5f6c-ba96-9ee0605295a5 | textbox | Circuit ID
15b42cab-2e83-5ddb-a2f1-bddb0a09982a | textbox | Number of Points
9b255df6-9d27-5cfc-a6b3-bda6a7a5b41a | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
add62e7c-f892-51f5-b771-4c0b22b35050 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
66c5305c-d9bd-5935-bde4-e069ce3baf5e | tickbox | Final Check - All fit off complete, ready for switchboard termination
6de64347-f393-40eb-af90-6377a65d313a | section | Inspection 39
edebde33-ab54-431b-af04-20e8639dae71 | checkpoint | Has all information been recorded and checks completed?
b23b7b66-a647-56b7-834c-f23e78e22775 | textbox | Circuit ID
6da999a3-52de-5a95-9c6f-14f1bb4beba1 | textbox | Number of Points
1952526c-2aa9-5898-a9ac-f2ee76a0e97d | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
7c4314a0-e3d1-5ae2-b77d-85cc51375d0d | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
feb9c60f-df15-55ab-8f7e-6bef67b8e697 | tickbox | Final Check - All fit off complete, ready for switchboard termination
a8013f95-970e-4ef1-8ac9-e3ed337bcc4b | section | Inspection 40
0a1f6169-19ef-4c8d-b25b-730a762d2659 | checkpoint | Has all information been recorded and checks completed?
1d53bc98-0045-5118-8fa1-88f4432220c1 | textbox | Circuit ID
428e017f-f03f-5667-81b9-101a8ae00a7d | textbox | Number of Points
f882f115-cb41-57bb-ab38-e3d69f2b7cdb | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
d93483bb-17a1-58b6-8ed9-579243e3af9a | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
b318b1c8-4622-5cc0-ac3a-1061435acdce | tickbox | Final Check - All fit off complete, ready for switchboard termination
fd0e4650-b9d3-46af-9e9a-1aa163607840 | section | Inspection 41
e1668efb-b106-47f7-96f9-0441e235fc97 | checkpoint | Has all information been recorded and checks completed?
3f824ad3-44b9-5de3-b029-86872e20600f | textbox | Circuit ID
e28fd82c-56be-5460-964a-a5b924e1ef09 | textbox | Number of Points
cb131ca7-f96a-5570-9c7e-7e9cac7914fa | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
72a4cfcb-9e5f-5462-a67b-6b3a37fc9c2b | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
0c94a3f9-5476-56d0-ac39-3c7c0894fe57 | tickbox | Final Check - All fit off complete, ready for switchboard termination
c2082e1f-c4c2-4546-82ec-fdeb45f14bec | section | Inspection 42
15fe433d-6deb-416a-ae8c-192c1750894c | checkpoint | Has all information been recorded and checks completed?
0f9aff9e-4e4a-5aa7-8953-894b08e6c938 | textbox | Circuit ID
36b60111-27ab-5e17-8867-89e812de373d | textbox | Number of Points
fb315600-0b14-5504-8e0a-0e99aca17dd4 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
03401f06-6dba-53df-b526-97e3ce4340a9 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
393a6e23-5a7c-5145-9b94-bcf14f497904 | tickbox | Final Check - All fit off complete, ready for switchboard termination
3479d09a-d8d4-4466-b4a5-40daacba8618 | section | Inspection 43
e2089927-0ff7-428b-86ea-3f54c4d1fa01 | checkpoint | Has all information been recorded and checks completed?
eb2ee158-faee-59fc-a314-0a288b3d3797 | textbox | Circuit ID
9dbce4e9-21a5-561a-95e3-3245fc5cb41d | textbox | Number of Points
2a92b0c0-a4aa-5dbc-a319-1ea23776b240 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
a00b31ad-56ee-5f83-b8ba-d8cde0a3ca29 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
0887bcca-c195-57db-905d-7a35bc4efe73 | tickbox | Final Check - All fit off complete, ready for switchboard termination
80062939-bc8e-44d1-a83b-453a8152d068 | section | Inspection 44
8abdb88f-6ca3-48e0-9909-7c5261992f23 | checkpoint | Has all information been recorded and checks completed?
c5cc1e87-8a06-5db0-919c-f3cd5deaad5f | textbox | Circuit ID
38f8ef60-4f2e-5373-8b4f-ebf8a467e8dd | textbox | Number of Points
5c12a977-3062-52fd-8df1-6f047f5512a1 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
7af74bde-ea99-5364-8087-e4572c659a8a | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
bddba93d-c5a3-5553-a2c6-2ac8914d95b1 | tickbox | Final Check - All fit off complete, ready for switchboard termination
336468ee-3f4e-499a-b0f0-b458764783b4 | section | Inspection 45
f5d288bc-8a41-46f4-89dc-bbad52cfb571 | checkpoint | Has all information been recorded and checks completed?
f6e1c4be-1b3a-5518-a823-138b9a8dd3b5 | textbox | Circuit ID
4d46cd88-1a58-516c-ba01-5ac1f33725c4 | textbox | Number of Points
119059f7-ade1-5bc5-b7dd-a01055004c38 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
95403daa-44eb-5c1f-ac72-14bef1e056e1 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
95407e4b-0570-573d-b6c9-9f12d8abdee8 | tickbox | Final Check - All fit off complete, ready for switchboard termination
f5c46fe7-2078-46b9-a553-d221c3491a25 | section | Inspection 46
38660e44-f099-4bb8-9cd4-f938d2ccea03 | checkpoint | Has all information been recorded and checks completed?
459db101-d4b7-57d5-b115-fc1d0d2547c6 | textbox | Circuit ID
3ed6b72a-1266-5050-b0cd-46b3ee3f7c6b | textbox | Number of Points
4aeea3ed-378a-5450-8126-f0c565ff0eff | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
91cd7b40-5fa8-5fbe-8c19-8005517d3102 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
4e9886f3-7cb1-5609-8a76-467b55934b08 | tickbox | Final Check - All fit off complete, ready for switchboard termination
82bd232c-cbe5-4ca6-8615-cbbc2d32f8f7 | section | Inspection 47
7e3cdb68-39be-4174-bd52-8d5ae4acaada | checkpoint | Has all information been recorded and checks completed?
6a6485ce-18d9-5b1d-9268-e046ae448fe0 | textbox | Circuit ID
ee21b233-3d42-5a85-8055-3e40a3abd841 | textbox | Number of Points
2f004126-2d77-5538-b8d3-20c40df8449c | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
a5d166b5-12c0-50a8-92ae-c7eb795d4147 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
4f01970c-0de2-5a9b-b382-c9888d7ff0bc | tickbox | Final Check - All fit off complete, ready for switchboard termination
2b9e473d-94e2-4b10-b0bc-230ee61c9217 | section | Inspection 48
6aa4a15e-36ad-444c-a923-71f92482a646 | checkpoint | Has all information been recorded and checks completed?
bd79244d-50b1-5c0c-a3ec-b1197e498fed | textbox | Circuit ID
97e05cf0-59ee-5d1d-9ba6-80dea1f65de4 | textbox | Number of Points
7e7b55a2-3464-5186-9b73-083e1c8c062f | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
3d25170f-79ab-5523-8378-485909f166f6 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
609c9da3-9ded-5737-9d18-d0afe8891aaa | tickbox | Final Check - All fit off complete, ready for switchboard termination
3720d735-19e2-4c36-98b3-5c7a5fa1ea97 | section | Inspection 49
4f6956d4-ee2d-4df0-b106-62ec5852f8d7 | checkpoint | Has all information been recorded and checks completed?
771350a7-1be2-53a5-9422-d5d39fcc9a2f | textbox | Circuit ID
e516a74e-d10a-5a03-b381-a46c6c0518c1 | textbox | Number of Points
dfaabd23-ddde-53ab-85bc-e891cfc7314b | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
bd0c1337-0517-53a1-8ab2-ed6b605de89a | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
8025d566-0611-50f7-93d9-e781d947b9c3 | tickbox | Final Check - All fit off complete, ready for switchboard termination
cb2dde2d-3b28-4a7c-afdb-104da7f42ffd | section | Inspection 50
e24454a2-7350-45a4-94d7-7c5fd07032cd | checkpoint | Has all information been recorded and checks completed?
3cc542fc-a690-526c-9164-7c6870aeb51a | textbox | Circuit ID
ac2b983d-2b7b-5ae7-b2bc-6a74ac10c7e3 | textbox | Number of Points
5592ce61-879d-57fa-8e9c-5a3bd2496e25 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
f4fa68e1-538e-5d3d-9c3f-9504e225d9ca | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
b9ae3936-6e7c-5b62-a9ae-ae71f3860290 | tickbox | Final Check - All fit off complete, ready for switchboard termination
3f4969d0-d467-405b-a7bb-988f6f4995e4 | section | Inspection 51
0e0d8e43-21fc-44c7-ba05-aab14543f8ef | checkpoint | Has all information been recorded and checks completed?
d90fa785-6654-5e2c-bf7d-8d2b01f2dea1 | textbox | Circuit ID
f5a3a02d-14e4-5eab-9236-ee8f6424f1d3 | textbox | Number of Points
99727171-0765-59c8-8dc4-6686950bcfa1 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
f139abf9-16e3-53a7-8905-ff2268161aef | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
39a282bb-3640-58e2-8cab-f2fb6c052adb | tickbox | Final Check - All fit off complete, ready for switchboard termination
58eb0540-4d52-42db-863f-aee2e722333b | section | Inspection 52
0a54690d-d50c-4897-9c87-93451e3863f4 | checkpoint | Has all information been recorded and checks completed?
231bc1f3-c7cf-5045-92fa-9d5369c947e7 | textbox | Circuit ID
c2df9532-10a0-5ed4-9e33-7fbd9c41bd63 | textbox | Number of Points
bf025b7a-afef-5e53-a2c7-031385d8a53d | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
691bd918-de9b-5c73-84bf-4a36df2cba36 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
0f8e2e24-40eb-5b5d-9349-68107af7f569 | tickbox | Final Check - All fit off complete, ready for switchboard termination
74af1c73-93a4-4577-9e04-108940a72365 | section | Inspection 53
d20f84bf-cbb0-4ac8-83a9-a1b9f7e4d065 | checkpoint | Has all information been recorded and checks completed?
3f9fe8d8-2a00-525e-afd5-0edeab5585ad | textbox | Circuit ID
ada72018-3891-5b43-a598-0864b5936079 | textbox | Number of Points
fa05cfbe-b17e-5178-af48-43f19d09dc20 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
3198c57f-9598-5dc8-a0dc-6a6f6d7836da | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
879617fa-6804-58a2-9e0e-9dca36b99455 | tickbox | Final Check - All fit off complete, ready for switchboard termination
9ff62a78-0582-440a-90c6-22b5fcb9e051 | section | Inspection 54
64f896c0-dede-4d18-8f80-4d321ec9c67f | checkpoint | Has all information been recorded and checks completed?
688e6604-e689-5417-b6b8-e7b97b4d0328 | textbox | Circuit ID
767bb89c-451f-5bea-b889-053e68cf80b9 | textbox | Number of Points
0adfa49e-77d5-559f-821d-d5becdac94fd | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
a95c58a1-e964-5df3-81fe-b83fe79286a5 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
b9bb677c-dbed-5786-8483-8518619eee04 | tickbox | Final Check - All fit off complete, ready for switchboard termination
96d6adc6-8571-4496-8953-0d54a0c6a807 | section | Inspection 55
833a12b4-f134-46e3-a575-95c2755b49d6 | checkpoint | Has all information been recorded and checks completed?
23fad4a2-bee6-5f87-8012-ea18520d650a | textbox | Circuit ID
674ef60b-7fb7-58d4-8ec6-1ed2fd7a706d | textbox | Number of Points
502cc644-6b01-5273-a048-45e50f959363 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
36802be3-b5b1-50c8-859d-878efeeb23af | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
a6510328-568f-58ae-9fe2-2ddc0b472b23 | tickbox | Final Check - All fit off complete, ready for switchboard termination
9c63bc4d-706e-4eec-8821-bc26e0f3ec58 | section | Inspection 56
772c1907-df3c-427a-96af-576caaa23a21 | checkpoint | Has all information been recorded and checks completed?
190af83d-baac-5cf2-9878-3a6df8380cd6 | textbox | Circuit ID
2a15a178-2c80-56b8-8e96-a22d8df3c4c6 | textbox | Number of Points
c88061c0-5c28-58cb-baca-7e3ff393d2f2 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
74162e5a-838b-54c7-afe7-5b5915a8f8a2 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
97fa1919-e830-5591-9360-9c210dfb9770 | tickbox | Final Check - All fit off complete, ready for switchboard termination
5a001153-890f-4835-a5cd-20054ad4c223 | section | Inspection 57
589ced87-22a4-4ede-a653-cb66a03364f0 | checkpoint | Has all information been recorded and checks completed?
555e2bc5-1a42-5e36-a643-9ff7040674f0 | textbox | Circuit ID
ec9bfba0-c9e5-5cd7-9620-baf1a2ff45ae | textbox | Number of Points
f2503805-1996-5b60-ba18-fb98262351de | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
d2d4b0d9-bfb7-584b-8d30-d70ff4bd68bc | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
7bf46fee-8dd3-5b45-bd22-ab899a45c18e | tickbox | Final Check - All fit off complete, ready for switchboard termination
69417cdb-0b55-4b45-b39c-bdd584274e8c | section | Inspection 58
0314f351-8282-4d7d-8af4-79e7047a090f | checkpoint | Has all information been recorded and checks completed?
83564f8f-3da6-5f97-970e-4f4c5dab82e9 | textbox | Circuit ID
cdf74257-a403-57cb-b82c-bb98230435bb | textbox | Number of Points
a0be524c-b200-55f0-925a-0e62a0e9f955 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
03884251-cfa4-505c-b422-9a5bb3e9e834 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
87cca761-6971-597b-b91b-936709ce88a9 | tickbox | Final Check - All fit off complete, ready for switchboard termination
a43c9830-4623-4695-a19e-fa5d7f15e600 | section | Inspection 59
fe546c25-7954-47d2-b109-200eb48d0ccd | checkpoint | Has all information been recorded and checks completed?
1294b971-1d1d-5e53-9911-0efee08caddb | textbox | Circuit ID
dff6cd35-7a97-543c-b408-ddd2d2e35c0c | textbox | Number of Points
99ff6e74-6dd3-55e4-ae7b-6432e9dd51d2 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
c07c6a7e-5d6f-5724-9d95-595d6cc40145 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
0eda3d60-ce76-5d23-928c-d052712470c3 | tickbox | Final Check - All fit off complete, ready for switchboard termination
a958306d-b8fe-45fe-9522-285f43cf7e20 | section | Inspection 60
1e4050a6-6fb0-4cd1-8b12-37b30337ef2a | checkpoint | Has all information been recorded and checks completed?
3130439d-1e1f-5983-8168-3e773b8a50ae | textbox | Circuit ID
774321c2-7faa-5ea2-a0e9-85729d2a59b7 | textbox | Number of Points
fd2e9abe-6e6a-5d55-b62b-9d78fda417e5 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
5031f841-84de-5d9a-884f-d1cfa939d044 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
a9b9afd0-a749-5c71-b51e-7cace25de3be | tickbox | Final Check - All fit off complete, ready for switchboard termination
88ffd37e-3a53-4bc3-a3c2-0a403d2294c4 | section | Inspection 61
9989e585-ddf4-406f-8792-383db7d73848 | checkpoint | Has all information been recorded and checks completed?
474ea86f-7214-550f-aa9f-9d12836cc523 | textbox | Circuit ID
a0b26f4f-6f9c-5bcd-a311-4bc6ac1cb0d9 | textbox | Number of Points
14a8b809-74c0-5413-8a7f-a66b686abeb6 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
465536f9-b175-56ba-a1df-0105892ad8fd | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
760c34b0-6257-5728-bbd6-db8f59051778 | tickbox | Final Check - All fit off complete, ready for switchboard termination
77e2f42f-fdad-4981-9e41-296fe44157a7 | section | Inspection 62
bd7a084e-2148-4a8c-a9c3-a8f67276b7cf | checkpoint | Has all information been recorded and checks completed?
e878ff18-3489-5509-b89b-684db329d1e4 | textbox | Circuit ID
8a83a1bd-6a03-5fcb-a1cb-e77018f7a6a1 | textbox | Number of Points
0c15b050-4be3-5bae-913d-e6b49a4c7a0b | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
18f21ce7-bc5f-5c4b-ba6e-7da4654c0359 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
c9b618f8-5526-5f0e-bf0c-6d88626c9bf5 | tickbox | Final Check - All fit off complete, ready for switchboard termination
60ebdb01-a209-4e5d-84c2-9904ae6b1973 | section | Inspection 63
0b950115-c971-460d-9f97-d2bd86e0f587 | checkpoint | Has all information been recorded and checks completed?
99c4538c-7e5a-5b2d-aad3-e69cb618edd2 | textbox | Circuit ID
7be51fd4-9e0a-56e2-ad87-522c3201d9ab | textbox | Number of Points
e6f84cda-6737-5133-b0f8-af0f2ea7c6db | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
74eda6f5-8a62-59ab-8661-107e22e6be7c | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
4bbba65f-e453-59c2-a02c-16dd84875b6f | tickbox | Final Check - All fit off complete, ready for switchboard termination
6b6b4c9f-1c97-4692-8796-ff412c0889db | section | Inspection 64
4126fbb5-8f3a-4642-8945-0034a9d91e82 | checkpoint | Has all information been recorded and checks completed?
6d027632-7eac-5fb9-ba21-caf69b1718a9 | textbox | Circuit ID
26805a77-fd1c-5285-9a28-48e98b486f6b | textbox | Number of Points
6c5ff034-0337-552e-8a6b-67d570df6d22 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
20216618-5c5d-529a-a776-db25e4d984b9 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
659e451d-6fc9-5354-b42c-b205b2b3f1e8 | tickbox | Final Check - All fit off complete, ready for switchboard termination
1f150717-3464-46f6-ab17-60a301dc3f73 | section | Inspection 65
67649d03-6aaf-4cb6-ac54-2d151098d255 | checkpoint | Has all information been recorded and checks completed?
cd90632e-6709-5250-a54c-5bfc8adaf922 | textbox | Circuit ID
0a5a5a12-db37-54ea-a62c-e7f6382995a6 | textbox | Number of Points
2587891e-3630-5dd6-8d8e-a9ee3d739df3 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
0fd221ae-d041-5efc-a5fc-431d1d2f6f30 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
b70c4d6c-3a14-50d7-b294-358935821644 | tickbox | Final Check - All fit off complete, ready for switchboard termination
15a7088e-adb3-4047-b028-76660100187b | section | Inspection 66
4d0162a7-1fb6-4fd8-a682-ae599371cb2e | checkpoint | Has all information been recorded and checks completed?
110bb124-1e97-5890-a49d-7dea484554f4 | textbox | Circuit ID
b37e2cce-5439-5a42-981d-a009ff074a27 | textbox | Number of Points
d3e471e0-522f-506a-9096-4029413e6ee1 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
9f32b7ae-6b42-5bb7-b846-fdeee9d87d2f | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
fc75f1d9-f886-549c-81e8-d929c1893e06 | tickbox | Final Check - All fit off complete, ready for switchboard termination
feb417ad-bf1a-49b5-9034-eef18967a8d7 | section | Inspection 67
3d4e332d-8b23-43c3-b12e-48dae1f1d182 | checkpoint | Has all information been recorded and checks completed?
5a2f8378-4ee7-5b09-86c0-60c0c2f7130e | textbox | Circuit ID
906eaba5-c61a-5611-8abc-7b8cb41a366a | textbox | Number of Points
94ffe099-f06d-5622-927e-45a754967058 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
b22d94a0-d3ec-5e2b-a764-d94059b391a0 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
838cc270-f3f7-587d-86db-65b2fb113e63 | tickbox | Final Check - All fit off complete, ready for switchboard termination
f9e0f5eb-ee9f-4928-949b-00c7b9d391de | section | Inspection 68
df100ffb-3ad2-4212-820c-51b52b605041 | checkpoint | Has all information been recorded and checks completed?
5b9da202-b4c8-56f5-a774-b1c2f1f7d1d0 | textbox | Circuit ID
b609e730-3e5b-52d0-bb0c-7ef1fb119037 | textbox | Number of Points
5d5af2d0-f067-564b-96ce-aaff1b785d22 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
9bb9301a-3051-5e03-a6b5-2853535cb5f5 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
1535681a-46d0-5292-9922-b177468a1b0c | tickbox | Final Check - All fit off complete, ready for switchboard termination
ad79afa5-f434-4fb1-b5c5-9a7c7cb296ad | section | Inspection 69
7718e37d-84d6-4edd-887a-16f5ffbaa651 | checkpoint | Has all information been recorded and checks completed?
7b7d2a4a-6d2f-5d2e-9364-ace2caccf9e3 | textbox | Circuit ID
44a02f99-6ec1-5a6d-baa5-62b5bc082c0b | textbox | Number of Points
66dd072d-f8ef-5ed5-9e1d-16d868e0c39c | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
d073d3b0-d4f5-5d79-b94e-b69a62faf2c3 | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
92b646e5-5b9d-5180-a2f3-8506446a8959 | tickbox | Final Check - All fit off complete, ready for switchboard termination
ea9a2648-068d-48c6-aa54-0aaac696d887 | section | Inspection 70
94fb8c39-1eb5-4a9b-894c-94933c722078 | checkpoint | Has all information been recorded and checks completed?
371d2eaa-9ba6-5688-914b-21d4c0a8906b | textbox | Circuit ID
f421022f-d82e-5bbd-bd71-1eb30410aa46 | textbox | Number of Points
0de45f16-8b90-5abd-8736-a8ebdccc2e5c | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
5cbf9ea6-010d-52cc-a315-09f5887f17ce | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
3af7a84e-4168-5852-8ee7-445a56d75520 | tickbox | Final Check - All fit off complete, ready for switchboard termination
cc989d5a-790b-4d95-8197-81520cbabf6f | section | Inspection 71
64d53843-8881-4097-9bb6-114d2fe50a25 | checkpoint | Has all information been recorded and checks completed?
4f635e3c-7c65-5a49-b13b-407b92cbaf2f | textbox | Circuit ID
d477776d-9789-55e0-a37c-5d4ca7406ef3 | textbox | Number of Points
83a263e5-9fcb-511f-8b90-e475dbe1eb57 | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
c302d6da-f094-5400-ab30-baef18b0025b | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
aa9eda05-1eb5-551d-ba73-8cafe1f40cc6 | tickbox | Final Check - All fit off complete, ready for switchboard termination
d76e4b12-a703-48a3-a0c7-92172f6af2f7 | section | Inspection 72
441102b1-2b78-42c8-90fe-812aa3c7f9c6 | checkpoint | Has all information been recorded and checks completed?
6eb3d062-a323-5e24-bff3-362ca9d5d48f | textbox | Circuit ID
dac1eca3-9abd-5d97-8d92-7298dd540f0c | textbox | Number of Points
632cd846-5b5a-5a0d-9d9d-ee60789e545a | tickbox | Fit Off - Visual Check - All points have been fit off/terminated
0161f244-79b9-5dd8-b18d-282e63fb76de | tickbox | Fit Off - Identification - Ensure cable is appropriately identified, post termination
c6493a7b-5cb6-5084-a0e6-2188a4ba6ae1 | tickbox | Final Check - All fit off complete, ready for switchboard termination
5da322b7-c99b-48a6-b521-3c7f6d21db28 | checklist | QA_TEM_058_Construction Wiring Checklist |  | QA_TEM_058_Construction Wiring Checklist
5e56ff64-5147-423f-abfe-1e86f4b8e94d | checkpoint | AS/NZS 3012:2019 - Construction Wiring Checklist
0bfd1b8d-caf7-5cee-9bca-d1d763e05601 | textbox | Building # / Area / Distribution Board:
f1fb7687-65e4-5eb3-b527-160a42903289 | date | Date:
8256b499-73cc-470b-b24c-ff6af3121428 | signoff | Signature:
d5340a11-7aa6-4b3f-8f64-efc3a3ac4a46 | checkpoint | 2.3.1.1 - Switchboard is legibly and indelibly marked to identify the source of supply from which it originates
80134713-ad8d-4e76-8350-b0222052db28 | checkpoint | 2.3.1.1 - The switchboard shall be readily accessible and protected from damage
48c119b8-344f-40d0-900c-d9d10a2b4523 | checkpoint | 2.3.1.2 - The switchboard shall be positioned in a manner that eliminates the need for leads to be run between levels
9d317576-160c-4865-8c29-27859193823c | checkpoint | 2.3.2.1 (a & b) - The switchboard shall be of robust construction with a minimum IP 23 rating
b879c7e7-7c52-4164-a4a1-2a0bfdd670bd | checkpoint | 2.3.2.1 (c) - Live parts shall be eﬀectively protected at all times against contact by personnel operating equipment located on the switchboard, including the connection or disconnection of plugs to socket-outlets. (All penetrations MUST be closed oﬀ, with propriety fittings, i.e. bungs & lock rings for unused holes in the bottom of the board, pole fillers and all covers to outlets).
56edb7a4-499c-404b-a7c7-0553b9f7b95b | checkpoint | 2.3.2.1 (d) - An insulated tie bar shall be fitted for extension leads to prevent strain on socket/outlets.
6ee8d02a-8a7f-4e67-9770-9413d105bc33 | checkpoint | 2.3.2.1 (e) (i) - The door or lid shall require the use of tool for removal.
1c7b04c2-d9cc-4c82-9b82-0c17696af40a | checkpoint | 2.3.2.1 (e) (ii) - The door or lid shall be fitted with a facility for locking.
338dfc97-7466-4c96-80f4-27a1a6800684 | checkpoint | 2.3.2.1 (e) (iii) - The door or lid shall be fitted with means of retention in the open position.
cec9e49c-2cea-4b45-93ee-f86fb0c7bba4 | checkpoint | 2.3.2.1 (e) (iv) - The door or lid shall not damage leads and allow the safe entry of leads.
ebd47a8f-a77e-43e9-9ee8-e591f4ddd0dd | checkpoint | 2.3.2.1 (e) (v) - A clearly visible and legible sign shall be fixed on the external surface. KEEP CLOSED - RUN ALL LEADS THROUGH BOTTOM.
986ebb2d-3e8b-42c0-903c-a35d91894490 | checkpoint | 2.3.2.1 (f) - Where there is more than one switchboard on the site, markings shall distinguish one board from another. (by means of numbers, letters or both)
73c9a5d1-f4e6-4335-9840-7622c6916cdf | checkpoint | 2.3.2.1 (g) - Switchboards shall be marked in accordance with appendix C to indicate presence of live parts.
dd4c3d29-fffc-43a3-b388-5b57beeb0337 | checkpoint-no-value | NOTE: Locking covers required for CB's and RCD's, but not isolation switches - this is generally a state or client based requirement aimed at controlling the resetting of breakers and RCD's
a3d38d93-0f4e-44d2-afd7-dca1000e56ba | checkpoint | 2.3.3 - Switchboards SHALL be securely fixed in position, attached to a pole, post, wall, floor. (if it is not fixed down for any reason the board should not be in service)
cddf6180-4835-4ddb-8f64-2f709bd9d33a | checkpoint | 2.3.5 - At each switchboard, a fixed secure and stable means shall be provided to support cables entering switchboards e.g. cross arm covered in non-conductive material.
790b827d-276d-43cf-b2a5-84236cf20bb1 | checkpoint | 2.4.1 - Each switchboard SHALL be provided with one isolation switch marked in accordance with clause 2.4.3. This switch shall interrupt supply to all downstream circuits including outlets mounted on the switchboard.
aa52c47d-e9e7-4812-8d67-f56e97caf040 | checkpoint | 2.4.2 - Isolating switches SHALL be lockable or located within a lockable enclosure
606987a4-9658-4c71-aaf9-207615dd0525 | checkpoint | 2.4.3 (a) - All isolating switched shall be marked - MAIN SWITCH - on main switchboards (min 6mm letters)
2496b48f-4c55-4738-8b93-1270b37bed27 | checkpoint | 2.4.3 (b) - All isolating switched SHALL be marked - DISTRIBUTION BOARD ISOLATING SWITCH - on distribution boards (min 6mm letters)
03c60e92-20ed-4410-b618-fa23b005b07b | checkpoint | 2.5.2 (a & b) - Construction wiring shall not be tied, bundled or grouped with permanent wiring, and shall not be attached to free standing fencing.
277da751-a0d3-42f2-a2a1-840e82a5ccc0 | checkpoint | 2.5.4 - Construction wiring shall be readily distinguishable from permanent wiring by using cable sheath of a diﬀerent colour or by attaching iridescent yellow tape spaced at intervals not exceeding 5m and marked with the words "CONSTRUCTION WIRING"
c2ae5cca-9ffa-4be1-8ea0-2ff5d311ea9c | checkpoint | 2.5.4 - If live permanent wiring is located where construction wiring is occurring, or its location, then it SHALL be marked with the words "LIVE WIRING" at interval not exceeding 5m. Live permanent wiring SHALL be readily distinguishable from construction wiring. NOTE: Unidentified wiring is to be deemed LIVE.
a052dada-fb08-48ed-9001-8e0bf56c7278 | checkpoint | 2.7.3.1 - Emergency lighting SHALL be provided in designated access and egress paths and directly above and in front of switchboards, (where the general lighting cannot be met using natural lighting)
06b7e52f-3f4a-47ed-adc4-f3a251715c4c | checkpoint | 2.7.3.1 - NOTE: Requirement to prevent unauthorised disconnection of emergency lighting that has detachable connections (i.e. hard wired for Low Voltage). ELV control boxes to be hard hardwired at construction distribution boards.
7dfe8321-3f67-45a6-b0f4-ef44f6ccaf68 | checkpoint | Current single line drawing is readily available
a4bd478b-3003-4683-bef1-758d6831c5be | checkpoint | Switchboards have signage attached with correct Q Electrical site contact details
0c78e510-4e19-4850-a73e-c17717458b45 | checkpoint | All Conduits MUST have adaptors fitted and glued
f96d29d5-b436-41d0-a855-9379d300841e | checkpoint | All cables MUST have glands fitted
bbc5a76c-9a1a-4c85-b4a6-f9b4abcfd173 | checkpoint | All penetrations MUST be eﬀectively sealed by use of a propriety fitting e.g. screwed bung and lock ring.
3ea64c25-dfce-4a06-947c-bb45f1864307 | checkpoint | Table 6 - RCD's - Push button test by user - Non portable fixed - frequency monthly. (Note the RCD count in comments)
064e687c-3b6b-49ba-bd5b-ca75c883048d | checkpoint | 2.5.3 Risk assessment should be conducted prior to the installation of cables or whenever a change occurs, as to the likelihood of any cables being exposed to mechanical damage.
de45595c-0fdf-49d7-a7c2-e6915e91b940 | checklist | QA_TEM_061_Construction Lighting |  | QA_TEM_061_Construction Lighting
d83820e3-757a-4085-ba64-5c8b2bb95ee2 | checkpoint | Check Light fittings are securely fitted
8cbe9256-0a13-4af5-85ee-ab2d33a3c9dc | checkpoint | Check Emergency Exit signs visible and clear from obstructions
f48bf7d3-9644-4fb9-90ab-6bc8429b3385 | checkpoint | AS3012:2019 - 2.7.1 - Ensure minimum lighting levels are at least 40 lx for walkways and 160 lx for general areas, lunch rooms and site offices. Record results on layout drawing and attach to this ITC
b431470d-a376-55bb-8da1-8b0295b40042 | textbox | Record Drawing Reference:
c297b9a6-14c9-4c00-a3bb-9ba1d211ab56 | checkpoint | AS3012:2019 - 2.7.2 - Light fittings are the correct type for the application and are protected against Mechanical damage
f7c1aa4b-66ff-4113-b63d-eb5cbfa38227 | checkpoint | AS3012:2019 - 2.7.3.1 - Emergency lighting is provided in designated access and egress paths
6a150bd1-b57b-4e51-bfc6-8a1ada774926 | checkpoint | AS3012:2019 - 2.7.3.1 - Emergency lighting is provided directly above and in front of switchboards (if natural lighting unavailable)
7e048f72-8680-4573-bb04-da06e7b75443 | checkpoint | AS3012:2019 - 2.7.3.1 Complete fields for one of the following : Item (a) or Item (b) below
554a872c-f36d-59ed-8a33-57738021a39f | tickbox | a) An average of 20 lx at 900 mm above floor level along the centre line of the corridor containing the emergency luminaires has been achieved. Record results on layout drawing and attach to this ITC
f65f0131-95c1-5374-b731-5bcc640a87ed | tickbox | b) Emergency lighting has been installed using luminaires complying with AS2293.3:2018 luminaire classification and the mounting height and spacing, as specified in AS3012:2018 Tables 2,3,4 and 5.
59e2818c-47a5-515b-8193-d9ec50d71bf7 | textbox | EM Light Type or Model No.
d83f3d31-c50d-5a7a-89c8-a47577bcd555 | textbox | Fitting Classification
00a47006-b4b2-5145-976d-bc74ed6f09d8 | textbox | Table No.
c61bd2aa-0205-5dfd-a727-bb346fce1743 | textbox | Mounting Height
62e744fb-b96a-5a07-aa36-0b23ba7bd69b | textbox | Max Spacing between fittings (C 90, C 0)
721c5524-3e7c-4be7-ba75-ae814720c479 | checkpoint | AS3012:2019 - 2.7.3.1 - Emergency lighting levels are maintained for at least 60 mins following loss of normal lighting in the area.
26f2bf6f-fa50-4264-b1ab-9aa7af7e798a | checkpoint | Log book is completed and copy on-site
cbd5eebc-fdb8-4f88-b4ce-151c03b58ce6 | checkpoint | Emergency light fittings are correctly identified in line with log book
4666170c-6463-4323-9270-697ebafbbf18 | checklist | QA_TEM_062_Construction Main Switchboards |  | QA_TEM_062_Construction Main Switchboards
1ec82087-cdbc-491e-9156-fe4b0536c49e | checkpoint | AS 3012:2019 - 2.3.1.1 - Switchboard is legibly and indelibly marked to identify the source of supply from which it originates. (min 6mm letters)
f2d8dcc3-97e6-43bf-be1d-2a9c829c608c | checkpoint | AS 3012:2019 - 2.3.1.1 - The switchboard shall be readily accessible and protected from damage
51943e72-0c7c-460c-86e3-4117dcb59da5 | checkpoint | AS 3012:2019 - 2.3.2.1 (a & b) - The switchboard shall be of robust construction with a minimum IP 23 rating
954694f7-bb61-4ea7-bfde-212e23b14cda | checkpoint | AS 3012:2019 - 2.3.2.1 (c) - Live parts are eﬀectively protected at all times against contact by personnel operating equipment located on the switchboard, including the connection or disconnection of plugs to socket-outlets.
1d36e0fa-ee98-46f0-9ddc-3cbc87334801 | checkpoint | AS 3012:2019 - 2.3.2.1 (c) - All penetrations are closed oﬀ, with propriety fittings, i.e. bungs & lock rings for unused penetrations and pole fillers for unused circuit breaker poles
9b9a58cf-d7b4-40cf-9455-c96e42f7140e | checkpoint | AS 3012:2019 - 2.3.2.1 (e) (i) - The door or lid requires the use of tool for removal
d23c1b93-61d8-4a0b-9565-bf81e2981e62 | checkpoint | AS 3012:2019 - 2.3.2.1 (e) (ii) - The door or lid is fitted with a facility for locking
c352cd09-9b8d-4e9f-8aed-c8f93aca04b8 | checkpoint | AS 3012:2019 - 2.3.2.1 (f) - Switchboard is clearly labelled to distinguish one board from another. (by means of numbers, letters or both)
a2ea56c8-fce0-4759-bf7e-913926ea1d17 | checkpoint | AS 3012:2019 - 2.3.2.1 (g) - Switchboards is marked in accordance with appendix C to indicate presence of live parts
519352bd-409c-4219-aeef-ab2312ac9bdc | checkpoint | An electric shock risk sign is displayed in locations where additional attention is required in the removal of covers, e.g. covers for switchboards or cable junctions
f2b398ac-926f-4f5e-9841-65745602a819 | checkpoint | A danger sign with an additional message indicating the presence of live parts within, is conspicuously displayed on the enclosure
2da588d1-3c30-46b8-af19-eba344b4cc27 | checkpoint | AS 3012:2019 - 2.3.3 - Switchboard is securely fixed in position, attached to a pole, post, wall, floor. (if it is not fixed down for any reason the board should not be in service)
f12647c3-61fa-43e9-93f3-919a90668801 | checkpoint | AS 3012:2019 - 2.4.1 - Switchboard has one isolation switch marked in accordance with clause 2.4.3. (6mm Text) ‘MAIN SWITCH’ and confirm switch interrupts supply to all downstream circuits
71c5cb9a-fcd6-4a41-9d41-444875070a80 | checkpoint | AS 3012:2019 - 2.4.2 - Isolating switches are lockable or located within a lockable enclosure
686c9d1a-2d65-4709-a7eb-5f3f036dd31a | checkpoint | Current single line drawing is readily available within the switchboard
bc7f9383-e048-4883-8119-304d0a7509f5 | checkpoint | Switchboards have signage attached with correct Q Electrical site contact details
de7aa89b-8e35-4708-99fe-bc5e4390e90e | checkpoint | Switchboards have up to date schedules and are correctly labelled
83c33eaf-2bdf-425e-aff6-9491f186cabb | checkpoint | All conduit entries into Switchboard have adaptors fitted and glued
ed79ef2b-7458-4934-ad3e-2f70477f1b31 | checkpoint | All cables are correctly glanded into the switchboard
badf2fa1-5e67-4814-98d2-283a3df88f5d | checkpoint | All spare penetrations are eﬀectively sealed by use of a propriety fitting e.g. screwed bung and lock ring
5fcfce03-f860-4d95-b660-74cb7bbb0c47 | checkpoint | Check cubicle has been cleaned of all rubbish, dust, filings, tools, etc
b7e182d5-c88b-4236-aaf9-6fefa2251172 | checkpoint | Check all cable terminations and Bus bar connections are secured correctly & tensioned: (Attach reference documents)
d8f2c019-1687-5080-ab99-4d2fa62f09a4 | textbox | Item or Part
800c7cec-f3d0-5130-a776-9d2c5207b066 | textbox | Torque Setting
9eb95a7b-1321-4170-9306-5c6080698086 | checklist | QA_TEM_063_Construction Distribution Boards |  | QA_TEM_063_Construction Distribution Boards
b2cdbd13-dd0b-4d46-bafd-0ff0b1fa55ff | checkpoint | AS/NZS 3012:2019 - 2.3.1.1 - The distribution board is legibly and indelibly marked to identify the source of supply from which it originates. (min 6mm letters)
1e305d09-96ca-4891-b199-984ddec27502 | checkpoint | AS/NZS 3012:2019 - 2.3.1.1 - The distribution board shall be readily accessible and protected from damage.
b0fa8fab-c3ac-42fc-bb62-6b6c04330e97 | checkpoint | AS/NZS 3012:2019 - 2.3.1.2 - The distribution board shall be positioned in a manner that eliminates the need for leads to be run between levels.
151d3df1-e50b-4623-b201-2f4d6ab79ff2 | checkpoint | AS/NZS 3012:2019 - 2.3.2.1 (a & b) - The distribution board is of robust construction with a minimum IP 23 rating.
90d9368d-eede-400b-b857-be8c5b4e7a33 | checkpoint | AS/NZS 3012:2019 - 2.3.2.1 (c) - Live parts are eﬀectively protected at all times against contact by personnel operating equipment located on the distribution board, including the connection or disconnection of plugs to socket-outlets.
75337f1b-a8e1-4771-91a4-ec76516820e5 | checkpoint | AS/NZS 3012:2019 - 2.3.2.1 (c) - All penetrations are closed oﬀ, with propriety fittings, i.e. bungs & lock rings for unused penetrations and pole fillers for unused circuit breaker poles.
5e2e6a1d-3642-4b20-a8b7-8384106fb57c | checkpoint | AS/NZS 3012:2019 - 2.3.2.1 (d) - An insulated tie bar is fitted for extension leads to prevent strain on socket/outlets.
84dd4b76-1ec6-46e4-a185-ebd9596be6fa | checkpoint | AS/NZS 3012:2019 - 2.3.2.1 (e) (i) - The door or lid requires the use of tool for removal.
7b4606c1-7d79-4c4e-851f-44c6c6545903 | checkpoint | AS/NZS 3012:2019 - 2.3.2.1 (e) (ii) - The door or lid is fitted with a facility for locking.
8bef4e3b-d743-49ee-baa7-3e61a44bd871 | checkpoint | AS/NZS 3012:2019 - 2.3.2.1 (e) (iii) - The door or lid shall be fitted with means of retention in the open position.
a983f442-22fd-48b8-9304-bee8e0b86c45 | checkpoint | AS/NZS 3012:2019 - 2.3.2.1 (e) (iv) - The door or lid shall not damage leads and allow the safe entry of leads.
2d43c994-8221-4c6a-ae3d-ff6eb832bbdb | checkpoint | AS/NZS 3012:2019 - 2.3.2.1 (e) (v) - A clearly visible and legible sign shall be fixed on the external surface. "KEEP CLOSED - RUN ALL LEADS THROUGH BOTTOM"
bb7b3ce7-0e3d-4e3d-b7d2-c80bb0799251 | checkpoint | AS/NZS 3012:2019 - 2.3.2.1 (f) - Distribution board is clearly labelled to distinguish one board from another. (by means of numbers, letters or both)
a395f7c7-17e7-49be-92e8-c6f6957948f0 | checkpoint | AS/NZS 3012:2019 - 2.3.2.1 (g) - Switchboards is marked in accordance with appendix C to indicate presence of live parts.
d5060abf-0cda-40c5-a09b-cad378c4d83c | checkpoint | An electric shock risk sign is displayed in locations where additional attention is required in the removal of covers, e.g. covers for switchboards or cable junctions.
ac5afdc3-b71a-4881-9204-5293ade4b00d | checkpoint | A danger sign with an additional message indicating the presence of live parts within, is conspicuously displayed on the enclosure.
7af9b4be-84c5-464e-910b-931301bb1e56 | checkpoint | AS/NZS 3012:2019 - 2.3.3 - Distribution board is securely fixed in position, attached to a pole, post, wall, floor. (if it is not fixed down for any reason the board should not be in service)
7f4942c7-0408-4237-920c-5a828dddf5fd | checklist | QA_TEM_064_Construction Wiring & Accessories |  | QA_TEM_064_Construction Wiring & Accessories
c80034fb-c2eb-445b-b4a9-b45b816df456 | checkpoint | Check that the accessories are the correct type
52fd34ca-70ae-5a81-a868-ab4b9b54edb7 | textbox | Reference Document:
034f93ce-56d6-4eed-9c45-260937f1a351 | checkpoint | Check that the accessories are located in the correct position
2f2638da-ccc0-58c6-9462-de19b69783c3 | textbox | Reference Document:
8a9bb76f-fc49-453b-a175-7e316589fc1f | checkpoint | Are securely fitted and field equipment and cabling is clearly labelled
50be5659-085e-4c8b-9a57-08881a02347e | checkpoint | Are fitted in accordance with manufacturers recommendation :
22931490-c297-4fd4-8179-6799683086ca | checkpoint | AS 3012:2019 - 2.5.2 - Check wiring is not tied, bundled or grouped with permanent wiring; nor attached to free-standing fencing.
c191d0dd-8283-41cc-b90a-6a5eab6596b3 | checkpoint | AS 3012:2019 - 2.5.3 - Check wiring is mechanically protected in accordance with previously conducted risk assessment.
d10a3f28-5ae4-5e55-a245-18df03d5d532 | note | (QA_TEM_057_Construction Wiring Risk Assessment)
72fabcff-d708-5c2e-adef-366d1aeebf35 | note | Or not less than;
4f22a303-a646-5e09-8829-625be4929a14 | note | (a) medium duty rigid or corrugated conduit of insulating material;
f8ac13ed-12e0-569b-9ff7-a3718a22ad6e | note | (b) heavy-duty rigid or corrugated conduit of insulating material;
5ee945a9-924e-57f4-b426-e3019c7c9779 | note | (c) flexible electrical hose;
0909767d-5a32-5347-bbe5-a718680be671 | note | (d) armoured cable; or
7164abc6-ff18-57fc-b272-4a30306d8451 | note | (e) other means that provide equivalent protection against mechanical damage.
19955736-17ef-439b-b667-8e67445596e9 | checkpoint | AS 3012:2019 - 2.5.4 - Construction wiring is readily distinguishable from permanent wiring by using cable sheath of a diﬀerent colour or by attaching iridescent yellow tape spaced at intervals not exceeding 5m and marked with the words "CONSTRUCTION WIRING"
d9551376-246e-4e59-aa3d-43d3a7f4e1a6 | checkpoint | AS 3012:2019 - 2.5.4 - If live permanent wiring is located where construction wiring is occurring, or its location, check that it be marked with the words "LIVE WIRING" at interval not exceeding 5m.
a534f09a-dc20-4fe8-9715-c64ca6c1bb6a | checkpoint | Confirm all Field wiring to Isolators, Socket outlets and point off supply has been terminated correctly
ad1da838-51f9-4c97-ac7a-1794ca0879bd | checklist | QA_TEM_078_Cable Installation Checksheet |  | QA_TEM_078_Cable Installation Checksheet
06f25219-74f1-4bf0-8181-d4e62fd70fc7 | section | Inspection 1
decd0e62-badf-4c36-bb5a-6fc0103c5dc5 | checkpoint | Has all information been recorded and checks completed?
fbe68ad4-570f-584d-b176-dafcad24182d | textbox | Circuit ID
8fcb73ff-906c-55fd-9bdb-8e5f11ca28a8 | textbox | Cable Size/Type
25fd36ef-1f33-52d1-a637-6b500484855a | textbox | Number of Points
118e652b-9ab7-566d-b560-ab698724a6dc | tickbox | Rough In - Feeds complete
d9010324-df4c-5517-b0f8-22fd976d79c4 | tickbox | Rough In - Loops complete
bc8e087b-5e4a-5c64-af5b-876a6a35d8c2 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
13225a0e-de54-5cf4-9d9d-1cf85df9b67a | tickbox | Fit Off - Field checked
8bf1b52a-7ae3-5fe7-abcd-1b561cadee1f | tickbox | Fit Off - Switchboard checked
e83cd695-48f7-59d6-ba83-dc1aa1a85766 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
05f249b1-b5c5-5b19-a274-c7b65fb55677 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
d4ebd813-5e5b-55fa-ab18-3a9380a449f1 | tickbox | Layout Drawing - Checked / Marked-Up
f8d04509-aa0a-5d78-a958-529da3c28687 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
b89129ef-3b89-5404-9066-400f9dc87faf | tickbox | Labelling QA Complete
0936197c-095d-4bde-a701-5f90090b395a | section | Inspection 2
c9829d75-8483-44cf-9b7f-636ae7e36066 | checkpoint | Has all information been recorded and checks completed?
e8c4a128-87da-5f87-a440-58b10de4993b | textbox | Circuit ID
4ed9c389-9f03-5673-a82a-079cb6b11a5f | textbox | Cable Size/Type
696a6c5d-b678-5b1c-a2a0-925db5b373ed | textbox | Number of Points
03d5ea75-8f31-5182-99ae-512cc86dfcdf | tickbox | Rough In - Feeds complete
321460a5-2a66-5370-9305-d8ea437fcb1e | tickbox | Rough In - Loops complete
57f93a3c-18b5-5e81-84a6-8515ea87bd5b | tickbox | Rough In - All cable loops have been roughed in/identified/marked
cd8a74d8-f1db-5d5b-9bf7-4735b4b901ca | tickbox | Fit Off - Field checked
8042f374-699f-54bc-8d3f-8f6d959056ba | tickbox | Fit Off - Switchboard checked
b2d32af9-40ea-50a1-9700-3c8e37c87b19 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
8a181385-c58e-5735-b71e-9e7fa9db39fb | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
e02d8ef1-5c6e-5732-af52-fe03ff8cd314 | tickbox | Layout Drawing - Checked / Marked-Up
0163c221-83db-50cc-bffa-1bc3423a3d87 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
afbb9dac-f88c-526a-b43b-66346f80a455 | tickbox | Labelling QA Complete
17cdc837-f23a-4824-abbb-326c04212686 | section | Inspection 3
46d8c4f4-a9ed-438e-b8f6-e3d901dcf106 | checkpoint | Has all information been recorded and checks completed?
d471c93b-37e3-5c97-970b-17d5001977c3 | textbox | Circuit ID
da8db475-9de5-54ff-b13c-1e2917593d82 | textbox | Cable Size/Type
98f07c85-80a9-5609-b82b-b0322bf70018 | textbox | Number of Points
0f26c33d-6a87-5a4e-b329-28e89820362a | tickbox | Rough In - Feeds complete
293cfcf3-b1db-5f56-9a12-ec78875b614f | tickbox | Rough In - Loops complete
6114c8e4-9783-5ad2-9088-190f9d12ec76 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
4f27342f-171b-50b2-84fe-0c127119e199 | tickbox | Fit Off - Field checked
be0f2674-a421-5639-bdd5-f756a4889717 | tickbox | Fit Off - Switchboard checked
c10c4e27-9777-5c22-ae75-e65d2643dcf4 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
ab595fcd-45b5-5c4a-9bc3-82e5b91fc13b | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
de320aa4-df75-5fcf-9255-9ea76db9b29e | tickbox | Layout Drawing - Checked / Marked-Up
d472f01b-1802-575d-b1c1-55cb7d3e924b | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
2a64cddc-1100-5b1f-8ab1-be3d7dd3cbb2 | tickbox | Labelling QA Complete
844556df-9d4a-40b0-b19c-5202192c371c | section | Inspection 4
79bb4967-57fa-43e1-87f3-60533ae9f3f0 | checkpoint | Has all information been recorded and checks completed?
eb1c9946-a8b8-5ed9-a00e-949dbdb02965 | textbox | Circuit ID
57f57288-4c2b-5a5c-99d3-8125ddd049e7 | textbox | Cable Size/Type
1aca2029-11c3-588b-a46c-7017857cf2a1 | textbox | Number of Points
48782db6-368d-555f-9ef0-83d46d47d65c | tickbox | Rough In - Feeds complete
c4e9270c-479c-5027-b71e-e401a3863d97 | tickbox | Rough In - Loops complete
435eaa3e-c180-5c8e-b867-c8db8bc2f54a | tickbox | Rough In - All cable loops have been roughed in/identified/marked
4cd0f5c2-ba3e-5719-a71c-3629f22a40cf | tickbox | Fit Off - Field checked
401738b4-d669-5b4e-8782-14332672d41d | tickbox | Fit Off - Switchboard checked
41dd980b-07d4-5d6a-aea8-ac236b485973 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
612c8d78-10cb-5f25-b603-bd46ebb9dcc6 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
14b2abf5-77de-5090-9f5a-6da5e82e325d | tickbox | Layout Drawing - Checked / Marked-Up
948c9cd0-42be-53eb-aa77-0b7ff6a1e4c2 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
7a95656a-8ec2-5eda-84cf-457688533669 | tickbox | Labelling QA Complete
307b1ace-cfc8-4f0d-8a94-47913d8ab895 | section | Inspection 5
93d311ce-e4c5-433b-a7cc-f46c53598817 | checkpoint | Has all information been recorded and checks completed?
264bd32f-24d6-5f8d-a534-9bd4dbbe2995 | textbox | Circuit ID
a073444e-148c-5384-939d-000434878d59 | textbox | Cable Size/Type
a9d5c09b-318d-5c88-b46d-8114eb688f9a | textbox | Number of Points
eace6b9c-f867-5de2-bd7e-62794c57cde3 | tickbox | Rough In - Feeds complete
ffc9661b-4086-5f6f-91c4-73a21bec82f7 | tickbox | Rough In - Loops complete
51dc9ff5-4197-582c-914b-814c40e49096 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
34fad1fa-27b1-5483-8660-4263df89f63a | tickbox | Fit Off - Field checked
92768188-b11d-5b02-b250-8ec5b2f21a09 | tickbox | Fit Off - Switchboard checked
63a4c506-c6a7-588e-9576-5e86fe8bd9b2 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
38b5092f-6cbd-5214-ace8-6e2632604254 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
5191c39f-1f23-5742-924d-c1745e5c108a | tickbox | Layout Drawing - Checked / Marked-Up
fe689600-2a65-579c-94a1-d758b47504a4 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
c68d7555-0169-5004-9fa2-22a6c87dd0dd | tickbox | Labelling QA Complete
c409bc9c-b584-4491-8147-0fd619cac2b5 | section | Inspection 6
a39f386b-728f-49c4-ba5a-46be70fcebd1 | checkpoint | Has all information been recorded and checks completed?
064bedb9-4e9d-5e7c-850b-021f79e0a03f | textbox | Circuit ID
bfb3b856-805a-5476-8541-24794b4a8c5d | textbox | Cable Size/Type
269bb0ad-59bb-548f-9f54-19aa7785333a | textbox | Number of Points
0baf1487-dfa5-5bdf-a260-f4482636cf2b | tickbox | Rough In - Feeds complete
e1bf5d45-e15e-5870-bbc2-30d84120dfa7 | tickbox | Rough In - Loops complete
e594fd69-3ac5-5889-8c21-20d71f8e10cb | tickbox | Rough In - All cable loops have been roughed in/identified/marked
be3b6b52-debe-5526-8914-79105f8d0db2 | tickbox | Fit Off - Field checked
8a94dd98-3b18-5d56-9d78-c6dfea240166 | tickbox | Fit Off - Switchboard checked
6dee0ee7-e814-58be-a9a4-b5f9769cd104 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
ecd6aa21-75d6-531a-986d-593203d5e41d | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
68ff72c4-0454-527f-ae64-327451a6f5c9 | tickbox | Layout Drawing - Checked / Marked-Up
70b8fa47-acf8-5ce7-9564-566739abe923 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
44b4409b-656f-5515-bef9-8740fd1aad92 | tickbox | Labelling QA Complete
80c02f40-11ef-43e8-b3a2-bd8278220b10 | section | Inspection 7
8cd25a45-9f34-4c09-8ed5-6de0ae2f52bf | checkpoint | Has all information been recorded and checks completed?
82533d6a-1842-5d75-b428-6d18b646bd7b | textbox | Circuit ID
964bff3a-26ca-5c98-8325-e25a6b2a0610 | textbox | Cable Size/Type
2b64441e-534c-5f36-b150-37c2f7ddafcf | textbox | Number of Points
6857b32a-8988-5575-b498-80b0aecfabfa | tickbox | Rough In - Feeds complete
a5691414-3277-5168-a94d-9752392ba909 | tickbox | Rough In - Loops complete
58227818-fb87-53a3-a82c-1fad4f341bc6 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
b653a7b1-0201-5767-8a57-bf16e30c497f | tickbox | Fit Off - Field checked
9f0e8872-e4cf-5644-a8e7-a8aae0cd52d0 | tickbox | Fit Off - Switchboard checked
4fb6f73b-6d28-5d70-829b-07893e067742 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
77cf98d6-6ba8-5557-8567-592bc09b2201 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
cb81be35-e2b8-5ca0-b568-6c4197ddbcf5 | tickbox | Layout Drawing - Checked / Marked-Up
48c756ec-2ed9-5cd2-8538-7d5d77c93561 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
d9ff0d81-dcdc-5069-959d-8ce0d104c2ee | tickbox | Labelling QA Complete
6f6f61b6-476f-4620-a28f-88262528d905 | section | Inspection 8
e51d7a0a-4f04-4879-922e-090d95ce5c13 | checkpoint | Has all information been recorded and checks completed?
2a906439-1967-5a50-836a-2be6e75090ad | textbox | Circuit ID
452010d3-883a-5691-a250-9481c40d128d | textbox | Cable Size/Type
d8cdb7fd-5095-55fc-b297-874e4fcd2045 | textbox | Number of Points
aaa26a4b-8d63-5e99-8a6f-fb7fb4508557 | tickbox | Rough In - Feeds complete
2bdbf9a1-c980-5e5c-9118-bcb81f49dbed | tickbox | Rough In - Loops complete
760d3c4b-850f-522e-a37a-b70aea778f2d | tickbox | Rough In - All cable loops have been roughed in/identified/marked
932bc68c-34ca-5b10-b778-878a6486bcdd | tickbox | Fit Off - Field checked
9066ef7a-3617-5e43-a22f-987c4dcb6542 | tickbox | Fit Off - Switchboard checked
3b1154c0-cb6c-5edf-95a5-38d8bbfd037a | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
ad746ece-a483-517d-a6fb-87655a993a2a | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
4ca83cc0-0bd4-5a9e-b24f-eafe654add2d | tickbox | Layout Drawing - Checked / Marked-Up
324ae11e-402d-5a67-9ad7-29dc72826ffa | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
de6fdb88-8205-5bcd-9bdc-39f0ecdbbb2e | tickbox | Labelling QA Complete
c5b1b00a-fc5c-40cc-9ef4-58e68b15cd8d | section | Inspection 9
12bf08a1-5123-41d3-9b37-a6b40515661d | checkpoint | Has all information been recorded and checks completed?
96aa6842-71cb-531a-80cc-4d65ff0e3b5c | textbox | Circuit ID
2a022a4a-96c8-5e34-ba23-c24a37be3692 | textbox | Cable Size/Type
a51b5315-5494-5633-b43e-fe5fdca7d3dc | textbox | Number of Points
56a60d3f-eaf4-5611-a8b6-3bd238d53f92 | tickbox | Rough In - Feeds complete
953d9569-0cab-5cfd-8347-fe97b5c21299 | tickbox | Rough In - Loops complete
5d79fb0e-6598-50ed-9639-9a6a123056ec | tickbox | Rough In - All cable loops have been roughed in/identified/marked
c89b38c7-bdac-5db6-899d-ab0c2b918e45 | tickbox | Fit Off - Field checked
373ca150-b0cc-570c-b6ce-f0fae0b4036f | tickbox | Fit Off - Switchboard checked
0ec57571-6720-5352-be16-99ef8172b135 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
7c36c084-8205-5000-9e90-f1493bbe96ec | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
a5ef819d-662f-5082-b51f-807353713ebf | tickbox | Layout Drawing - Checked / Marked-Up
ecf511a7-368e-5af2-ab52-e1a83932982e | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
c8b9afa7-0d70-53d1-be4a-d67763b4edd8 | tickbox | Labelling QA Complete
aa96daf4-a6a6-4f2a-ad5b-c1e13d23172c | section | Inspection 10
2b138019-7aab-4e58-9ec2-41713c715a71 | checkpoint | Has all information been recorded and checks completed?
3e6786e5-858f-50a0-9e9d-aa51a5635a2b | textbox | Circuit ID
cac0c142-b0fa-54b4-bc80-f54d4b8eb8da | textbox | Cable Size/Type
27ab3d8f-2a45-5de0-8c47-3e417281ad39 | textbox | Number of Points
dd3d6088-a4e8-556a-af6f-a4acafc168a0 | tickbox | Rough In - Feeds complete
0a9d66f4-12db-5134-b076-8c7176a756ba | tickbox | Rough In - Loops complete
adfb367d-cec5-5538-ac7b-43722551b5ee | tickbox | Rough In - All cable loops have been roughed in/identified/marked
cd31ad1f-742e-5387-9270-60a64ce88b6d | tickbox | Fit Off - Field checked
1f55f9e5-0755-5c6f-ab5e-722894d32fc9 | tickbox | Fit Off - Switchboard checked
06f2edb1-dfae-5fc9-9172-7cf19581b3e3 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
dc7bd0fb-bf87-57ba-8bb6-f1aa36998c08 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
35afe2a0-3857-559e-b9e6-3aefd16ebac6 | tickbox | Layout Drawing - Checked / Marked-Up
af359462-5ffd-5210-9a57-3b0d6a776c67 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
2ef61461-78a3-5a56-973b-be19a53701ea | tickbox | Labelling QA Complete
d63ef41b-3413-4b67-ba3d-b9c5f8110fc5 | section | Inspection 11
3a2567af-6b12-45b8-aa0e-4ee4105e4a35 | checkpoint | Has all information been recorded and checks completed?
6dbf6008-b48b-5b9f-912d-620a8bec6f1b | textbox | Circuit ID
7c284d73-1aca-5a3b-9cf6-6a9fd9cf8c14 | textbox | Cable Size/Type
d780c899-5594-5239-aa04-7ec1efee32d1 | textbox | Number of Points
5890cc6d-a4a6-5a31-a2ed-c257a4006f60 | tickbox | Rough In - Feeds complete
45ae81e7-8c13-5cb7-aa01-21e4083f5629 | tickbox | Rough In - Loops complete
d564e819-58b9-53e1-8c84-3b23f777101e | tickbox | Rough In - All cable loops have been roughed in/identified/marked
ded2150c-8514-55af-85e4-3487e7614ff1 | tickbox | Fit Off - Field checked
1371893c-19a4-58fc-b5c5-f999dd7ff719 | tickbox | Fit Off - Switchboard checked
35a40ee1-3b9e-5d97-9e13-64f7959d98a4 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
65ca12bc-4617-5934-8786-82d1684c8d7d | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
a66431fa-7b6b-5ff6-9469-1b95a3dbdbbd | tickbox | Layout Drawing - Checked / Marked-Up
af26daf5-4208-517e-bfa8-b82a2db17c0f | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
9adb3d50-0898-5f67-a410-3120b9d766d6 | tickbox | Labelling QA Complete
c0ad6f9e-edab-4c8c-995a-c940abbd93f0 | section | Inspection 12
b6bd32ae-579a-4f2d-9117-3d2a78b0c1f7 | checkpoint | Has all information been recorded and checks completed?
daba3244-0e50-50c0-aea5-e72b7431794f | textbox | Circuit ID
1a76637a-4cd0-5e86-b378-d00800857b80 | textbox | Cable Size/Type
eded4e22-319d-5b20-9895-c50c189d7f12 | textbox | Number of Points
a83c1355-fd73-58c1-b726-3521d54dc1f1 | tickbox | Rough In - Feeds complete
e202fb6e-2a6f-5125-afb8-ee1fde3b48ff | tickbox | Rough In - Loops complete
2ddca8ab-0b29-5244-aff5-0424f2d6293a | tickbox | Rough In - All cable loops have been roughed in/identified/marked
ad50d6db-4138-5d5a-820d-335a561c5ab3 | tickbox | Fit Off - Field checked
51890f65-ad19-564d-bd47-fe3b18d311ea | tickbox | Fit Off - Switchboard checked
8c170170-fcf0-57da-8890-a487ad4fef46 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
c3d7425d-4b41-56f0-a77f-329183d6b594 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
5569df4f-dc6d-52de-9e07-08db7e4d7964 | tickbox | Layout Drawing - Checked / Marked-Up
0724ec3c-8ed0-5a50-a69b-6fa5d1ddf8c7 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
321082bd-cdd1-56b2-87ac-cec412f4e0b0 | tickbox | Labelling QA Complete
91cec837-bb25-43f3-8670-8023536fa570 | section | Inspection 13
71e5a61e-5754-4ba3-b867-b98e6c863ec8 | checkpoint | Has all information been recorded and checks completed?
01c630c9-f10e-5a90-bfc6-b4ffc3dd4e90 | textbox | Circuit ID
cbd4ab18-0bf2-5be6-bac9-de96f5c81af7 | textbox | Cable Size/Type
262d0390-4b62-5cb7-a57a-76164c133713 | textbox | Number of Points
c79c3082-856a-5c91-9608-a5090ff4f157 | tickbox | Rough In - Feeds complete
2fdf9505-605d-5c3a-a914-e2f70e28055b | tickbox | Rough In - Loops complete
bc190205-ea51-5610-92ff-e27411cb47fc | tickbox | Rough In - All cable loops have been roughed in/identified/marked
414a53c0-9748-5ec5-a2a0-3dd13e966c61 | tickbox | Fit Off - Field checked
0257ae31-db2e-52f5-9e25-a535ef327596 | tickbox | Fit Off - Switchboard checked
1dcdf4f5-d064-5243-801c-c1507b9dd4dd | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
48b05c80-c36f-5849-ac99-946f71caba4c | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
81f17e36-4b36-5889-a083-476531581b11 | tickbox | Layout Drawing - Checked / Marked-Up
7d446c6d-131e-5e06-90ec-b3968d7e52b7 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
cd732182-7f5e-5420-8a31-0f935a95a4de | tickbox | Labelling QA Complete
2b5d1bae-e585-4b27-a0c3-b4606810ac40 | section | Inspection 14
5f592e48-7854-4b15-aa10-c241bf362a27 | checkpoint | Has all information been recorded and checks completed?
ed5b3fa3-977c-59f1-8354-517a6eca5696 | textbox | Circuit ID
00d50830-7c84-551a-82ef-cd38c3472571 | textbox | Cable Size/Type
6b5524cc-7823-51ea-8bf3-3042f8ecff2d | textbox | Number of Points
bda91524-2fc9-513f-881c-6d46552cd1cb | tickbox | Rough In - Feeds complete
7ee62783-4e78-59b8-9cbd-c57928cf8f9d | tickbox | Rough In - Loops complete
c05d7f7b-125e-5bc6-8bd9-6e44f7d4d8d0 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
92f3d4d4-c07c-5cfa-92cb-13c84539f48a | tickbox | Fit Off - Field checked
6377bd98-c33b-5dcc-920f-2a62ce93fa9a | tickbox | Fit Off - Switchboard checked
9d3647a3-0009-5828-a0a8-4bd56d8671ea | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
99335a23-1664-5fe9-b578-7989edb03b95 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
20ee8b8a-f156-5b39-b1ce-e679d2cfade9 | tickbox | Layout Drawing - Checked / Marked-Up
7c199cbc-d6d0-5490-b98b-77ae5d733339 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
343b3b1d-e92d-533d-bf09-9ff12bd1cf77 | tickbox | Labelling QA Complete
63511d3c-937a-42b0-bdd6-1222b3b3360e | section | Inspection 15
d07b12a8-6f66-41b8-a48d-985563592d88 | checkpoint | Has all information been recorded and checks completed?
ed9a114d-4799-5eaa-b351-72740aece428 | textbox | Circuit ID
4f5c27b2-c52a-51b5-acfd-d28f393a4281 | textbox | Cable Size/Type
ad8e755f-8495-5bf6-8e35-93d1fca45fbb | textbox | Number of Points
a8565071-635e-5ac4-9b28-39f4a7f1fc83 | tickbox | Rough In - Feeds complete
2cd0fe2d-c477-5048-8dd9-3c7fab17a200 | tickbox | Rough In - Loops complete
c119aaae-22bb-554a-bb2a-68e2262a4442 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
0f8f7336-7d9d-5a36-81c9-1fde33ea5449 | tickbox | Fit Off - Field checked
175db4d5-da95-5280-99f5-789f3c30f4b8 | tickbox | Fit Off - Switchboard checked
347b4db2-bf70-54b6-93e9-320f565e5757 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
31aa9da3-0e7e-53a6-807d-8ed3eec69e9a | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
3ff10505-d2b4-5d13-a719-57bb579452c5 | tickbox | Layout Drawing - Checked / Marked-Up
f30ad453-a125-5330-88cd-f7cf5afa17f8 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
60e211c0-a430-5060-8293-49b267ae1235 | tickbox | Labelling QA Complete
213bba14-bccd-4b12-8a18-c71004a69408 | section | Inspection 16
02e05e07-039c-4b61-99a4-2fbafc44d876 | checkpoint | Has all information been recorded and checks completed?
96e1da3e-c54d-5f1b-a532-1f8f09d0478d | textbox | Circuit ID
7b65b6b3-4859-56e9-895d-85ed0201c52c | textbox | Cable Size/Type
94faa0a9-95e2-5e3e-8dfe-302a8a3c4483 | textbox | Number of Points
9eabfa0f-17a9-57bd-8d0c-b4971b25820d | tickbox | Rough In - Feeds complete
e5312d76-1bf9-5b76-a80b-7cdc3d64f807 | tickbox | Rough In - Loops complete
a01672b3-bf0f-52d0-b893-ec028caac676 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
d1ba2fca-355f-5114-a386-ca8335ba9945 | tickbox | Fit Off - Field checked
95342e80-732b-5d09-9092-308a266b8f9c | tickbox | Fit Off - Switchboard checked
67af4caf-99c3-5eac-8a6f-9baae6f3d81f | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
4f3cbf3b-f6ec-531d-a67a-839e37139b22 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
9b8e622a-869e-5315-96a9-1c355af0c6b2 | tickbox | Layout Drawing - Checked / Marked-Up
1a841c3e-e484-5fd8-a580-e81da8dcd20f | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
e8216b12-8609-5295-90ef-e3c30dd6c3b8 | tickbox | Labelling QA Complete
3d594a2d-1bd1-438a-bf35-be98316cb2e9 | section | Inspection 17
f02367f2-6812-4348-911a-38765ccc545b | checkpoint | Has all information been recorded and checks completed?
51a7e349-a0d2-5dca-9a4d-65f32afdb5b8 | textbox | Circuit ID
f5e2aaeb-b074-5c2d-9aba-b32a906e090c | textbox | Cable Size/Type
6220af79-40a3-54d6-8085-de243e58fd89 | textbox | Number of Points
f463fd2f-3f3c-558d-8167-8b4694b46f89 | tickbox | Rough In - Feeds complete
811a4607-1264-50ba-9c1c-a0a403cfd752 | tickbox | Rough In - Loops complete
9a270ecc-0b5a-576a-9159-88e8ef1b3949 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
bb135bdd-a50a-5827-a878-df2eac95204a | tickbox | Fit Off - Field checked
5a41bf1c-9d64-5d9d-b4be-f369189c904a | tickbox | Fit Off - Switchboard checked
da7cb047-488e-5129-8bb8-1e4a096cf634 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
a2391e4b-5468-5b48-8376-1fa0f31c8992 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
a47b1e0d-7b0e-5b4b-8aab-eb2a7a28982d | tickbox | Layout Drawing - Checked / Marked-Up
f7b39ca1-0d03-5fc8-ad4f-6ec7f25df430 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
374ddacd-cbfc-563e-8221-d58d95ddc375 | tickbox | Labelling QA Complete
be59ee25-abd6-4a8f-86e9-3f36a607eb47 | section | Inspection 18
62b55ce8-750a-46c7-96e9-025e37b2ce14 | checkpoint | Has all information been recorded and checks completed?
b41fdec5-d123-5802-b9af-481f56513945 | textbox | Circuit ID
63e54749-9845-5e7b-8bbd-70695eaff0d8 | textbox | Cable Size/Type
612f2770-54e3-5558-9ee6-d2aa7e1bb2a9 | textbox | Number of Points
29be4eb6-0bef-58fd-a91a-89b7e8b8495c | tickbox | Rough In - Feeds complete
83273df4-0693-5c03-a209-7399f038d515 | tickbox | Rough In - Loops complete
af791cc1-a31d-5dc0-9ba0-54a8a2f5420a | tickbox | Rough In - All cable loops have been roughed in/identified/marked
ad262236-9ed0-5c41-8e1d-9c84be68c863 | tickbox | Fit Off - Field checked
b9810d6e-c84c-578b-bd18-3cce838ede12 | tickbox | Fit Off - Switchboard checked
a1c4c8a2-fc10-5b28-ab30-0765dc30eb93 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
10b25a4c-d93f-5222-ac93-976c48e0b986 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
db89b20c-1151-5baf-afba-685ed3fc2639 | tickbox | Layout Drawing - Checked / Marked-Up
b580d18b-fd50-59f1-9513-249cdd1187bb | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
f86eba86-7dbb-5912-bdd5-9215330002c3 | tickbox | Labelling QA Complete
63b2234a-4d7b-455a-8676-5c6b9008b95a | section | Inspection 19
ece9d1d4-054d-447b-a655-fc4da9d0f246 | checkpoint | Has all information been recorded and checks completed?
f6137952-8db4-512e-b466-33a924c70b0e | textbox | Circuit ID
bec403d0-b91b-5738-ad2f-fc9da7cd3699 | textbox | Cable Size/Type
d781170f-fd15-5cb1-8e63-7665241403f2 | textbox | Number of Points
6dd9d9c8-c021-5ad8-99b7-f6dd1d0faf5b | tickbox | Rough In - Feeds complete
1153ac15-3bcb-579e-bd0a-398e24c1b6ed | tickbox | Rough In - Loops complete
94c080ba-b08e-5939-8893-e2f2e76aa51b | tickbox | Rough In - All cable loops have been roughed in/identified/marked
e3a742c6-8bb2-5e9b-a8fe-40dcac5a101c | tickbox | Fit Off - Field checked
d75e7854-f4c3-5650-aa3f-2ff7b9b19c34 | tickbox | Fit Off - Switchboard checked
3545ef61-60a6-587f-8c29-d756525010b5 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
bad93e9b-dcb1-56e8-8406-d7e503760c28 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
488eda1a-18c1-5ea1-9058-0dd4438c7e91 | tickbox | Layout Drawing - Checked / Marked-Up
c00af261-45a6-59b3-aa85-dfc32154928a | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
fe698010-972c-5afd-a217-73003a0532a2 | tickbox | Labelling QA Complete
01cff30a-cf84-4e70-9e57-0a41bb2cb8cb | section | Inspection 20
8b0995f9-0df9-46ce-a016-d7b539a1be26 | checkpoint | Has all information been recorded and checks completed?
6a7bd0c0-1916-54f0-bee8-dc64508f4854 | textbox | Circuit ID
0101da49-45dd-5503-be26-38537373202b | textbox | Cable Size/Type
5d9e4644-a289-50b8-a9f9-cb674e717684 | textbox | Number of Points
0b51fbe8-4fcc-503b-842c-217dab32d2d0 | tickbox | Rough In - Feeds complete
50883ce4-5052-5005-9193-5d38c366e3ca | tickbox | Rough In - Loops complete
80891c92-923c-5e67-8a7d-ff69992a181d | tickbox | Rough In - All cable loops have been roughed in/identified/marked
687300c6-4ac1-5377-9dc8-659da5a14c4c | tickbox | Fit Off - Field checked
35d0ecdf-9ffd-5b3e-9879-46821dcf0eee | tickbox | Fit Off - Switchboard checked
2d3725ac-1891-5726-b9e2-617f6f70a444 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
d297da5f-fa3f-532d-af84-3bcc0824114e | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
8d373bff-5b93-5a39-bf1b-7ae5b4324979 | tickbox | Layout Drawing - Checked / Marked-Up
ae11bbab-26d6-5e1f-8c26-a208bfb4ae44 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
0b90a824-2f81-5e92-b35a-2cc11bfcdbfa | tickbox | Labelling QA Complete
543d25b6-7bff-4375-96a1-9c78f1e53a96 | section | Inspection 21
0f8349a0-3c4b-452f-8836-11ba6a1afdbf | checkpoint | Has all information been recorded and checks completed?
6ff8c252-fc45-51cb-b10b-149976d2a6a5 | textbox | Circuit ID
7da3d0ea-481a-5175-9b9c-c9cca0a8ed0d | textbox | Cable Size/Type
f04c8ab8-2692-5357-bc5d-0d14aff06680 | textbox | Number of Points
a9df5a1e-5b2a-5577-8066-2547384ac73d | tickbox | Rough In - Feeds complete
289f4838-8082-56cf-8d2e-23d9e666049c | tickbox | Rough In - Loops complete
cd147ac5-2d50-5f8d-90d5-352cc5464275 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
4fe13f64-0065-5fff-b2d4-51c69742f4da | tickbox | Fit Off - Field checked
21d60c09-6f01-5d84-959d-5c3bfe8faada | tickbox | Fit Off - Switchboard checked
347d97a7-b142-5abb-9a1c-d99b5dc6e189 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
f05393c7-0844-5dd3-a858-2ddc59cdabec | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
1bae68c3-4c85-557c-9119-91140318b6f2 | tickbox | Layout Drawing - Checked / Marked-Up
c09a4a41-e04a-53c4-bffa-c6d137441e47 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
5d42e9ea-1728-5d89-866d-43590dff1990 | tickbox | Labelling QA Complete
3103e6b6-e7c5-4f47-a377-eebbde932cc7 | section | Inspection 22
1ad66194-b782-4ed5-91c5-1dcf3a065dee | checkpoint | Has all information been recorded and checks completed?
59bb2f77-4860-5c41-8d59-8fa3ad89f811 | textbox | Circuit ID
4d534299-f745-57e7-942a-71377b28c279 | textbox | Cable Size/Type
e9c461c9-7fc4-5e1a-b4f0-ca90fc4be60f | textbox | Number of Points
ab6f0196-9c0b-55d3-8671-74a5f9fe7fe1 | tickbox | Rough In - Feeds complete
7b4b764a-44e1-5250-a4ee-502ac723b869 | tickbox | Rough In - Loops complete
d1c986a2-1a67-5822-81c1-8548f7fc6b2c | tickbox | Rough In - All cable loops have been roughed in/identified/marked
0babddea-4081-5aa4-9b0f-58addc2da2cb | tickbox | Fit Off - Field checked
2ead2623-635a-5652-8f69-47bb5f4b0cf4 | tickbox | Fit Off - Switchboard checked
09abb884-2ca5-597f-86c6-8a3ec813cda3 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
31ac0b14-a6e8-563f-aa6a-2f1054daea17 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
2f38a931-380c-564c-a7a6-a7c63da691ca | tickbox | Layout Drawing - Checked / Marked-Up
4ede49b1-c998-5b86-ac1c-817471df7355 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
4a90b831-adc2-544a-9b33-f5ac7d63ddc3 | tickbox | Labelling QA Complete
f882b8fc-af9b-4876-b37d-f9efbdbef176 | section | Inspection 23
49b66fcc-be69-47e7-8cd4-4a45994bad46 | checkpoint | Has all information been recorded and checks completed?
b3680eed-ba4b-51b4-b3c3-af6333b1f907 | textbox | Circuit ID
cc89cb74-06ff-5e18-ac0b-ecf8242ae355 | textbox | Cable Size/Type
17a3f063-330d-5702-b365-989212be7a3c | textbox | Number of Points
31b65eb5-7a42-5044-bda5-88a38810c1bd | tickbox | Rough In - Feeds complete
3061f990-931b-5e2e-95a9-9468b7a54507 | tickbox | Rough In - Loops complete
0a5da1fd-432e-5d22-87b7-28fe2bc8979b | tickbox | Rough In - All cable loops have been roughed in/identified/marked
10a8ada8-223a-57e1-b84a-82f6b6afb88f | tickbox | Fit Off - Field checked
fa8394e9-673b-5cbc-8b89-dec03b2d6cca | tickbox | Fit Off - Switchboard checked
524df961-82bc-5ddd-a034-9a4f26dd14b5 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
9150f068-b803-50e4-9b2e-87f7f1d5aa1f | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
583c32dc-c68b-5b31-9158-8a93917ad360 | tickbox | Layout Drawing - Checked / Marked-Up
5b9eed98-da46-5b2e-88e3-3f7edb09f768 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
f1e11580-53be-5ea8-90b1-1f5275c03ba9 | tickbox | Labelling QA Complete
7f83b58b-7d3c-45b9-8a4d-fd131ced9417 | section | Inspection 24
c2551312-4db7-44f4-95d8-468f33356bbd | checkpoint | Has all information been recorded and checks completed?
05918f3d-7485-5d5e-8063-1e5b066abb68 | textbox | Circuit ID
25508785-048c-5db8-8a62-ea1143eaf57c | textbox | Cable Size/Type
2eeae7e2-539b-5011-bccd-3a02a2593c9d | textbox | Number of Points
59f5d1dc-7b29-5d65-8011-0aefe53b5708 | tickbox | Rough In - Feeds complete
ce35f2ee-8240-5abf-aeab-ff7dab4906fb | tickbox | Rough In - Loops complete
0268e4ba-609f-5394-b1ef-a41aa114fc09 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
648b785c-1fff-5d62-a5d2-aa2102df336c | tickbox | Fit Off - Field checked
2d4c6370-459f-5273-a852-ae91484a2b6c | tickbox | Fit Off - Switchboard checked
e118bbca-aab0-53e6-b184-c2d276a14d1e | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
bf08a7d8-44c9-5bb3-9d1a-e0350ede1df0 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
c51d1b20-d772-51fc-b04e-acfac5224054 | tickbox | Layout Drawing - Checked / Marked-Up
fb847b46-a1ba-58c8-b4b6-1ac0b38acedb | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
4db85af8-89f6-5262-a2b8-324ec6a21797 | tickbox | Labelling QA Complete
af08efd1-16c6-4641-9a80-4813edbfa7c4 | section | Inspection 25
8bb59861-13b9-4283-991d-d0e10b8a2ffd | checkpoint | Has all information been recorded and checks completed?
2000af07-8b61-5b0b-8eda-f97da45f6e7a | textbox | Circuit ID
0a2551c2-e5ee-5011-a78a-345c8d93fd35 | textbox | Cable Size/Type
8d8477bf-41a0-52d3-bcdf-d5dc352b3423 | textbox | Number of Points
d296e55b-0402-54c4-a12a-08454fe447e0 | tickbox | Rough In - Feeds complete
af1fd49c-c5e9-5d09-b669-c1a42d48faf1 | tickbox | Rough In - Loops complete
9275fb28-ed33-5392-b3ca-cf79bec8b906 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
0ace6354-06eb-5e76-b5ea-be725877448c | tickbox | Fit Off - Field checked
fa293c74-0b4a-510e-980e-a28bebdf8e45 | tickbox | Fit Off - Switchboard checked
9126edac-fe74-5bc1-a868-57438d431a3c | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
f75b02ec-953e-5248-a8c5-54842bdd0865 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
21776a2e-e522-54ab-b93d-f905e8ad8e8f | tickbox | Layout Drawing - Checked / Marked-Up
65dc7788-68ca-5911-aa94-ddcb103b434f | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
885c488b-c8df-560b-8aeb-c7711db26ee3 | tickbox | Labelling QA Complete
91518d9f-24a2-448a-8693-e421da3242bc | section | Inspection 26
b091243e-ed36-4f6c-9cbd-94ac0d5b2e46 | checkpoint | Has all information been recorded and checks completed?
b204c373-c2a8-5337-932c-640c135227a0 | textbox | Circuit ID
00768bba-e1ef-5761-b202-6526b9ed0cf1 | textbox | Cable Size/Type
748bd8d0-a8ac-53a2-b77a-bf9e4fec224a | textbox | Number of Points
ae8bece5-6767-5caa-a0ad-b6f3b92264ee | tickbox | Rough In - Feeds complete
d74c6e4f-9e6a-545c-adfe-23d332a31a8e | tickbox | Rough In - Loops complete
2d5eb582-3544-53ab-a501-87f95c039885 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
e3d55918-b45d-54a9-93ff-7e620ae4d02a | tickbox | Fit Off - Field checked
2f55e5f5-7e31-5c33-a59d-b7bcd295fe3f | tickbox | Fit Off - Switchboard checked
be2c4204-c2ce-5800-9af6-7b04a011c8c6 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
f1bda623-5976-5c57-b0d5-32ee813e5b63 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
25a92590-56b9-5104-b09c-0397f66ac6b0 | tickbox | Layout Drawing - Checked / Marked-Up
71d8914e-f7e1-5acd-88a5-fba5812238f9 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
d2224e9a-69dc-57bc-bfbc-8776492019de | tickbox | Labelling QA Complete
c675e2b8-8b07-40c2-b892-c6f3af1c0dcf | section | Inspection 27
e2f4dc89-84ce-4303-beab-2c81ff5075d7 | checkpoint | Has all information been recorded and checks completed?
65ba130f-55c2-5e9c-87a1-1b90f4d51a44 | textbox | Circuit ID
f94dbbc0-9cd8-5ff1-a8bb-d8e96d1a34c6 | textbox | Cable Size/Type
cefaee5d-7184-51c8-af54-5bcb7007dccd | textbox | Number of Points
3f4161db-865d-522a-8bdb-0e0dbe351f85 | tickbox | Rough In - Feeds complete
aff2c037-bc27-5910-98d6-5c8fdb7531f3 | tickbox | Rough In - Loops complete
b21ca900-5c54-5ac8-a1d5-24e270ab8b97 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
3378f405-09d1-5018-a20c-b9cf1c76c397 | tickbox | Fit Off - Field checked
ed8e85a5-de7d-56af-978e-83f24e33649a | tickbox | Fit Off - Switchboard checked
3bebbbc5-4527-58af-9ddf-3ebf456c3dc3 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
9ab34758-9804-5150-a03f-fe0b85d885b4 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
553e686a-5d25-5bcd-855b-2acb84441598 | tickbox | Layout Drawing - Checked / Marked-Up
85bfb321-bb43-5aa9-9d97-c44402d59336 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
2df5ceae-4664-5c8a-ab4a-82a81a867ea7 | tickbox | Labelling QA Complete
05a82de5-0703-450d-ad03-9f9458ecafe3 | section | Inspection 28
08df9aff-4a28-4045-9fa3-ef30503a05ca | checkpoint | Has all information been recorded and checks completed?
05bb2101-d9b9-5bbb-abe7-493fcec0ee39 | textbox | Circuit ID
135a06f6-7435-5ab5-89cb-1ffaf0efb571 | textbox | Cable Size/Type
f3f01914-c1b5-5324-8b34-1fdb5944de60 | textbox | Number of Points
ddf57d0c-f13d-58ce-a0f8-15488264c143 | tickbox | Rough In - Feeds complete
679c8bfe-755c-546c-81d7-9830757a45e5 | tickbox | Rough In - Loops complete
c39a2750-2e20-58a0-87a0-f25ca587eb09 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
f5c1cb2c-bdc5-5939-b176-55eccac45444 | tickbox | Fit Off - Field checked
5187513e-168e-5a15-9026-f319a2edbdb4 | tickbox | Fit Off - Switchboard checked
a3816826-9ff5-555b-bfd8-b120e3378a9c | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
a58f3340-168b-564c-8fb2-1d7f8cb771d4 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
c9df9159-4d66-5e71-a8e6-b9153c0f7f17 | tickbox | Layout Drawing - Checked / Marked-Up
501be84e-4381-5d69-b169-67531c71e661 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
59450d46-c111-568a-9b7e-064fe9dd04ca | tickbox | Labelling QA Complete
0739f46d-fd8c-4225-ad4d-4ba28e62f8fc | section | Inspection 29
231d3493-e726-4447-87a7-24c0d77fca71 | checkpoint | Has all information been recorded and checks completed?
4204ab9c-0c9f-551c-ac5a-a708d0734e0d | textbox | Circuit ID
72168105-38a9-5806-8754-04e4fa252395 | textbox | Cable Size/Type
5089c469-a810-57e4-a58c-6740e95f8d82 | textbox | Number of Points
c52bd1a1-e905-565c-b9f2-7271f4598f46 | tickbox | Rough In - Feeds complete
54c857c5-985d-509e-96e3-e05c0894a34d | tickbox | Rough In - Loops complete
10ffc5d8-0238-55f8-ad1f-8b9322353fbb | tickbox | Rough In - All cable loops have been roughed in/identified/marked
180602c8-c7f7-501f-8a9d-735dd3000776 | tickbox | Fit Off - Field checked
be25af65-62a3-5c0c-8e8f-0b959c8dee48 | tickbox | Fit Off - Switchboard checked
0e32eda7-1c42-53cb-b2b0-71cd9cc7bf68 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
3ec36ca0-0b22-5a42-bfd7-8ffacaeb04db | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
d5aaaff0-d684-537a-9b60-4e6f20db9066 | tickbox | Layout Drawing - Checked / Marked-Up
98c24d4c-05c3-59fc-9eb6-f1bd35fcf4df | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
6296bb45-21a3-5066-8c43-b7364e0205aa | tickbox | Labelling QA Complete
6ec0f10e-8705-4636-ac25-497279d4ef68 | section | Inspection 30
1ed79303-f6ec-4414-b4fb-ebe57c3bf1c3 | checkpoint | Has all information been recorded and checks completed?
f3f10780-2849-5ccd-9758-c4277ba4b222 | textbox | Circuit ID
e7d3786f-d06a-59dd-a6ca-e37a97419102 | textbox | Cable Size/Type
530a304a-5bdc-54ed-b47b-4b2a912fbee7 | textbox | Number of Points
3906fcb6-7add-55f3-8529-e1fa88cdf384 | tickbox | Rough In - Feeds complete
fcefba22-a9fc-571c-9fdc-9175c63cd2b8 | tickbox | Rough In - Loops complete
f62191f1-1267-5e88-a0c6-0f1da42c7871 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
791472a2-3062-5079-b1a1-369448e712f3 | tickbox | Fit Off - Field checked
da350cd8-ff2e-5e46-80df-6f644c820da3 | tickbox | Fit Off - Switchboard checked
2220da0c-d718-5364-bc9e-8437758edfbd | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
ea2fa897-423c-5e6b-8390-06b2402ff2a3 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
191956f5-a99a-5e70-8798-f19eee1bc7fb | tickbox | Layout Drawing - Checked / Marked-Up
94d5fa4c-299c-5222-a173-ea6b15c7bc9a | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
79bae131-79ba-5865-8326-71775892278b | tickbox | Labelling QA Complete
70825885-4b0a-4dd4-a0a0-853f4a9c5abf | section | Inspection 31
09d35df2-04a2-424f-8d5b-af518142d319 | checkpoint | Has all information been recorded and checks completed?
07fe8c7f-1da1-5dee-8bcf-f37803ac3ef7 | textbox | Circuit ID
9e928587-0ecd-5e49-8c13-a5c1543360dc | textbox | Cable Size/Type
98c501e4-32d2-5bb9-906b-f18622937954 | textbox | Number of Points
a6614fe2-7d6a-59ab-b3c4-0f71ab0db8b9 | tickbox | Rough In - Feeds complete
47756115-a803-502d-a8fe-1ed196b15a7e | tickbox | Rough In - Loops complete
fbd925eb-59b8-5e84-be51-46672e21a30c | tickbox | Rough In - All cable loops have been roughed in/identified/marked
6bbc9ba3-5faa-57de-9731-8214e23667bc | tickbox | Fit Off - Field checked
a92395f5-604a-54b6-9068-90ba75f8e0b6 | tickbox | Fit Off - Switchboard checked
6e2ff933-0f6a-5401-92a8-8d54090d3b26 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
194cf1a7-242f-5399-bfee-a74f2396059f | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
3601bc84-6567-50ba-b88e-53f3f0bf0c76 | tickbox | Layout Drawing - Checked / Marked-Up
535da2ce-8951-5621-8917-342cfbd76e8e | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
7ae08404-8430-5e44-8846-c8aab2108e44 | tickbox | Labelling QA Complete
115aa77a-756e-4209-8905-58c30f1696d3 | section | Inspection 32
5d13ca7a-3615-42d8-a615-a5e8e6f9231e | checkpoint | Has all information been recorded and checks completed?
30b33834-6952-5654-81ef-9f5f1a33d769 | textbox | Circuit ID
616baef5-bf77-51dd-b2bb-e7ea7504e27c | textbox | Cable Size/Type
0451984a-610f-5c06-98f9-20435db8962f | textbox | Number of Points
fe7d6abc-8738-50d4-a273-05a250c27773 | tickbox | Rough In - Feeds complete
94b81da8-0b32-50eb-8d64-8df73586bdc8 | tickbox | Rough In - Loops complete
094e86bd-d16d-548c-9243-608ae535bca4 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
8ccf8189-b5a7-5ea3-a4f3-c424ff0c69dc | tickbox | Fit Off - Field checked
c3b7b805-0940-5d0b-999d-808fac5de1f1 | tickbox | Fit Off - Switchboard checked
c056f8c2-fdaa-566f-a70f-13be3849d8ea | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
f91aab0b-f62a-5473-8720-850acdda9727 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
c46e6d36-f34f-5a8e-9c4d-f056affcb3db | tickbox | Layout Drawing - Checked / Marked-Up
2b7d3025-ac07-5967-9e8b-4be2cd8456d7 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
2daf9d3b-6118-5a29-94ca-7b4d4ff03fc3 | tickbox | Labelling QA Complete
08958cf9-b3d3-49ab-b583-8982b583df0a | section | Inspection 33
c2665316-9416-483c-b5aa-bf6545cc2db1 | checkpoint | Has all information been recorded and checks completed?
03f3edfe-6a97-5d17-87a3-108393870ac9 | textbox | Circuit ID
9db772cc-9cd2-586c-9ade-959da9fa451a | textbox | Cable Size/Type
8b6a32f7-7035-54b9-ac3f-99b1b8ee515f | textbox | Number of Points
c1052632-dc58-5618-a31d-a7d1e1350ca1 | tickbox | Rough In - Feeds complete
a5b2fbd9-fa59-5900-a26f-d5a37eba01ce | tickbox | Rough In - Loops complete
e5658874-fe86-5cee-bd5f-215a63f1ff96 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
6a7b6f9f-2202-5967-8f8f-4f9c3e799c5a | tickbox | Fit Off - Field checked
7e5131ef-b0e7-5939-9310-b9e29213339f | tickbox | Fit Off - Switchboard checked
f1a8aca0-677f-5aa6-9ece-0c7615f33d85 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
04dade7b-28fb-5149-9d4b-ba399c344a7e | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
7f9d375c-7e7e-5d39-b409-a409b5854101 | tickbox | Layout Drawing - Checked / Marked-Up
2a8b3228-4e53-5fb5-b1c6-cd91a332967c | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
040820cb-3bd8-52ea-b5f5-498863bcd48d | tickbox | Labelling QA Complete
ae378afe-003a-4e28-84c8-12c408814cc2 | section | Inspection 34
91fa0be5-44a0-423f-9521-d0d02114f04c | checkpoint | Has all information been recorded and checks completed?
3a37ad8b-2772-557c-a968-3b695c27a2f2 | textbox | Circuit ID
4fbd7fb9-c639-5763-a47e-31e7538b5b6b | textbox | Cable Size/Type
a31d35e4-8fba-5103-b1c8-75e71cbfea1c | textbox | Number of Points
dd7902a3-2896-58e0-9146-f7b0971520ce | tickbox | Rough In - Feeds complete
d2ac3d0a-1413-56e8-975e-6eb38ce67293 | tickbox | Rough In - Loops complete
83dae192-46d1-53d6-affe-42aa28c6d742 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
42764b7a-2692-59e8-b412-2ec52a961bf6 | tickbox | Fit Off - Field checked
261a217a-6bfd-5e9f-a04e-5366ee5aae06 | tickbox | Fit Off - Switchboard checked
e9bf93fc-38e4-519b-bb83-640575055dca | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
49bb9577-d606-50e4-9508-47a338ac2cdb | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
587a2711-1e0d-5c33-adbe-bbcf69492107 | tickbox | Layout Drawing - Checked / Marked-Up
169aa151-84a7-5838-8995-f0abf65efb73 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
26d2c7c3-4401-5f85-8020-6c235156dea0 | tickbox | Labelling QA Complete
27e8741d-7bf6-4a21-b148-3303dab796af | section | Inspection 35
2c67e166-8b2f-45ff-93ca-020bef0233a6 | checkpoint | Has all information been recorded and checks completed?
724bdc1a-258c-5b96-8c46-8d865cc485b8 | textbox | Circuit ID
d8e5c305-276d-55eb-8582-8ae2622c18bb | textbox | Cable Size/Type
7d99fda9-f5ca-52c4-975a-17e3216fd86c | textbox | Number of Points
ddb60fdb-f1cd-521c-bcaf-fd17d3fa2c74 | tickbox | Rough In - Feeds complete
63399c93-d379-5ce8-9e2d-862e96b3b627 | tickbox | Rough In - Loops complete
7f7914ff-b3c3-59a4-88c7-ccd295247242 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
2ec7c249-370f-5bcd-a6e1-6779f3f9fb89 | tickbox | Fit Off - Field checked
0115cb8c-d6e0-5c66-b9fb-260bea75b66d | tickbox | Fit Off - Switchboard checked
ead7629e-d2b5-5e08-94c1-9b9e558eb415 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
ed37b032-0f82-55e2-97bc-f2c36ae0d9a7 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
c95c8034-1149-5a79-b5e8-00581852a41a | tickbox | Layout Drawing - Checked / Marked-Up
bd765bce-76c5-55d9-a11c-3eed507418d8 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
faaea90d-5cd4-5e2d-bdb3-451378335a46 | tickbox | Labelling QA Complete
64be101b-079c-4e8a-aefd-971b61de04ec | section | Inspection 36
b3e234a2-17a8-414e-9081-ed9c4dcaf913 | checkpoint | Has all information been recorded and checks completed?
2b4e0371-127a-5a09-8d5a-ca76027f5bea | textbox | Circuit ID
1aff1199-89eb-5dd1-b501-ccf07828667b | textbox | Cable Size/Type
d23b6608-4ab5-515a-b90b-b5895948f85f | textbox | Number of Points
c90e4e2a-f3bf-5cf8-b530-98b1bf0227d7 | tickbox | Rough In - Feeds complete
6c93edf1-c652-54ec-828c-c242e8fa5c34 | tickbox | Rough In - Loops complete
795b604b-574a-564a-b768-ae9a021d9a99 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
f92cc94d-13a4-5afe-a094-0e1962bcdc72 | tickbox | Fit Off - Field checked
ccdad9d4-4660-54f0-afff-6e605cf07ffb | tickbox | Fit Off - Switchboard checked
cc72d79a-aead-5e6b-a27a-bda3d9c7dd1c | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
48bc186c-709b-5e3b-8a08-68477a185890 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
e09dfdda-0655-5144-98c2-f9f79002b918 | tickbox | Layout Drawing - Checked / Marked-Up
7e2d60f4-8530-5b4e-b1c5-10909816a9c5 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
2af57a61-78b8-5f88-b15c-6fa4da6c59d4 | tickbox | Labelling QA Complete
681e3598-df9a-4cdc-9307-b28f116576d4 | section | Inspection 37
b6f1acd3-7be7-455a-b18c-4d78c84de4b9 | checkpoint | Has all information been recorded and checks completed?
be42c799-c701-5a75-b327-1a011ce0b0f7 | textbox | Circuit ID
0ad845cc-764c-57b6-bb33-b3194e337211 | textbox | Cable Size/Type
a262a583-f159-5c18-8ee1-9049cbe44ae1 | textbox | Number of Points
5a3c0322-81ad-516e-8e80-d0f6a06f4762 | tickbox | Rough In - Feeds complete
5a0b2b61-bcc7-5daf-a53d-126ed569ad81 | tickbox | Rough In - Loops complete
7bd62441-22a0-585b-9aa4-b960417e1dd7 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
b0f0952c-b43b-5c68-8365-4d594b0bac3d | tickbox | Fit Off - Field checked
58936798-f5ce-5ac4-a19e-ece34169e9f0 | tickbox | Fit Off - Switchboard checked
e0d9a1ac-e179-56d8-800a-99bee1e49ddb | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
65f5fbdf-b151-531c-9696-1a2c1a1f82bc | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
ff34d62f-9e3b-5e17-be66-2687ec7f7c65 | tickbox | Layout Drawing - Checked / Marked-Up
b4b4d695-75e2-52ff-a2ca-ea3ff7001f64 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
8fc95e48-b416-546e-9c0a-c2cd956174c7 | tickbox | Labelling QA Complete
672e3ab0-58a5-467b-a400-7d631ef20a14 | section | Inspection 38
c729caca-49e4-4c72-8536-36283faf8878 | checkpoint | Has all information been recorded and checks completed?
9bbb9810-3df1-5159-96f3-89c6af3ab7fd | textbox | Circuit ID
1e56e7d6-7bf4-5348-8730-0cc2d45d9e03 | textbox | Cable Size/Type
4ec48fc2-ba05-531c-a706-31f1c9d2f0ea | textbox | Number of Points
5c0b16a2-16c5-58ce-9c23-a99ae066d5ed | tickbox | Rough In - Feeds complete
0b1f97a7-edb4-584c-be80-9fad2b4392cc | tickbox | Rough In - Loops complete
bbd3f58c-a43a-5705-a3db-d85b3cf19006 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
df530827-e73f-5327-9fb4-fe5cd1946938 | tickbox | Fit Off - Field checked
570083b4-4dd0-5138-95d3-cdedf462ff11 | tickbox | Fit Off - Switchboard checked
00963f7b-42e9-584b-8d77-3658127423e6 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
7e404bae-5127-5f85-8840-3bf154eef54f | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
b4dba377-8260-5e2c-8d0a-58600689de0f | tickbox | Layout Drawing - Checked / Marked-Up
0a822335-5f75-5c96-bbcc-0d4f95fbbab1 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
0218c125-9220-5e8b-a6bd-753eae98ded8 | tickbox | Labelling QA Complete
407145bd-ef93-4f2b-9eec-cf5062e363e4 | section | Inspection 39
b03f6183-b726-45ec-acc7-8f18b8e950d1 | checkpoint | Has all information been recorded and checks completed?
428984b7-650b-521a-90a1-2e3f3a336eca | textbox | Circuit ID
030022f7-a0dc-5b0e-9638-912fa0d989ce | textbox | Cable Size/Type
88c1aaba-e921-577d-b124-a8bea99694ac | textbox | Number of Points
7d41fbd6-2156-5774-a3be-da7741126470 | tickbox | Rough In - Feeds complete
bf3d71fe-720d-5ff4-9ff0-c584457296d6 | tickbox | Rough In - Loops complete
b7cfb021-3bdc-5c60-9545-544bc11db02f | tickbox | Rough In - All cable loops have been roughed in/identified/marked
636a03d6-4f2b-5f33-843e-c2082684599f | tickbox | Fit Off - Field checked
85501f96-f0af-559f-8b35-de805e6e1d83 | tickbox | Fit Off - Switchboard checked
5ff067b6-41b7-515d-9bec-9b91d0f90287 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
199c29cf-d62d-5917-b6ca-f005c53314f2 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
e6f7a7b2-a575-53a7-9b2b-8583145a2586 | tickbox | Layout Drawing - Checked / Marked-Up
349a5a07-6a2e-5f6d-9957-a35db16b1aba | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
85efd9b8-7d6e-53bc-8c8d-8502a8d07966 | tickbox | Labelling QA Complete
51bea881-132e-4d45-95eb-c5153f1efb5a | section | Inspection 40
357ec948-97db-4efe-bd7b-2306a6a1e1c9 | checkpoint | Has all information been recorded and checks completed?
b4ed5620-cdd6-5315-a0b7-2fd0f0989b9a | textbox | Circuit ID
59f1a23d-6a53-5f1d-a46a-f95b6ba70507 | textbox | Cable Size/Type
be11e878-5894-5941-b9c7-77c2fc2ec393 | textbox | Number of Points
7f7daa9a-4315-57ab-b72b-fb75244d0106 | tickbox | Rough In - Feeds complete
6fc330dc-7e96-5424-84fe-23e6680660b0 | tickbox | Rough In - Loops complete
f4100754-f00b-5344-a465-5723afd1f0c5 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
3dfa49c0-2138-50a2-8bea-6a1b6ac0baa8 | tickbox | Fit Off - Field checked
5a20a464-7ee6-5337-b7ee-94ede0ca48f7 | tickbox | Fit Off - Switchboard checked
f9cf7e06-d0e8-59af-aab5-a9db9407484f | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
d9da91f3-5cdd-546d-9aa5-61587e3d2def | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
916db228-1547-56ca-a78e-b96fd7748b84 | tickbox | Layout Drawing - Checked / Marked-Up
2c44e367-9efc-508e-9aaf-42bbab755787 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
630aa4c6-83bb-5fe8-ab9a-52dc3c2bc286 | tickbox | Labelling QA Complete
388bd857-e421-410d-8aa6-cf37f6c2cc2b | section | Inspection 41
98b08226-c7eb-4505-a6ee-0f6a99ac9b32 | checkpoint | Has all information been recorded and checks completed?
9c5f9640-0691-5719-a4b2-c490c568c627 | textbox | Circuit ID
31b66064-655d-5eb2-aafd-73b70febf6aa | textbox | Cable Size/Type
b1fea1b3-0157-5f40-9b64-3edf110e9bdf | textbox | Number of Points
c4042847-8809-5a72-9824-2800dba79cef | tickbox | Rough In - Feeds complete
4cee94d7-e082-5273-9cf5-c1767b224064 | tickbox | Rough In - Loops complete
0c77d103-2c83-5484-895b-56d5a522777b | tickbox | Rough In - All cable loops have been roughed in/identified/marked
b4ed0a30-bfeb-551f-80b7-c26a432bddfd | tickbox | Fit Off - Field checked
df7db2a7-cf47-5e06-9ef7-567ffbcdac91 | tickbox | Fit Off - Switchboard checked
f8ba3183-e974-50cf-a561-8df8f39f1646 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
02f0ab2e-81e0-52af-a9dd-908816bb6d1c | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
9564dae8-096a-555d-b69d-2b853dd94f35 | tickbox | Layout Drawing - Checked / Marked-Up
159f1a20-5664-5652-ae5a-9c5860b723ef | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
46ceb263-7a64-56e4-9495-ca5e0963c7fc | tickbox | Labelling QA Complete
489ce856-793f-4493-828d-319ab93429de | section | Inspection 42
dc838c9b-7bea-4a15-b674-d3c7f4704e60 | checkpoint | Has all information been recorded and checks completed?
2878c08c-c208-5e02-8bc8-ae0967c7da9d | textbox | Circuit ID
f81bb989-f015-5d6a-9811-6bf8e24bd7b2 | textbox | Cable Size/Type
275dc3f9-ac39-532b-9cee-ec60f51046f9 | textbox | Number of Points
3f8b4c18-6a45-5d77-bd2f-1f36951afef2 | tickbox | Rough In - Feeds complete
18b71bf5-e31a-563d-9b8b-cb3605cf06ff | tickbox | Rough In - Loops complete
572de0e3-29e8-5fb9-a721-5300e80cb949 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
dc4321a0-caf1-5988-803d-48e23440f917 | tickbox | Fit Off - Field checked
b8b3c0ac-10e5-5953-adcc-6581eff99bae | tickbox | Fit Off - Switchboard checked
3461e153-4d3a-5dad-97aa-36edcb43cb15 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
372ad66c-6afd-5545-8846-d99678da9358 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
8bb94891-3dec-56bc-861e-940a98ee17d3 | tickbox | Layout Drawing - Checked / Marked-Up
4cf8f208-f45d-5f82-8ee7-50134aaa3262 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
ab0f695f-1c45-52d0-ab55-a27e05c86a1a | tickbox | Labelling QA Complete
501040be-592e-4950-bfcf-199a195b4df5 | section | Inspection 43
b79aa3aa-f987-443f-a266-a235f9534383 | checkpoint | Has all information been recorded and checks completed?
d7b1397a-522d-5a48-b61c-e1b0d03e7974 | textbox | Circuit ID
3a9185be-35ed-5d2e-a351-2387b85835b2 | textbox | Cable Size/Type
f536a7d7-9a7d-55a5-b0b6-9409c9c7acf0 | textbox | Number of Points
13e43e60-d7e1-53bb-9415-11f537008dbb | tickbox | Rough In - Feeds complete
99defb0c-3f22-562a-8272-640e9ec2006f | tickbox | Rough In - Loops complete
5c0dc354-f843-5cc5-aa63-ffb1f43d7b93 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
5b40bfef-1966-56ed-bb62-644fb9a01096 | tickbox | Fit Off - Field checked
6dc44f44-d554-54f3-b529-5c5275be55a9 | tickbox | Fit Off - Switchboard checked
dba0698f-fdba-56db-911c-fe2fe1d0c37e | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
c036f45b-11ef-5b3e-8a6d-412df82fe709 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
96edcb38-2784-53bb-b9c4-75ab8acb36e5 | tickbox | Layout Drawing - Checked / Marked-Up
130ddcf2-faec-5193-8aca-d439cd0dfe6c | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
547f5356-14b3-5709-80d3-b9d2018c472c | tickbox | Labelling QA Complete
1be90a41-68d4-420b-869e-f671148f21e8 | section | Inspection 44
6f98b730-72c1-4dcb-9a6b-b5467f0b8121 | checkpoint | Has all information been recorded and checks completed?
d94f8809-c21c-5a46-9d57-45dc04b92559 | textbox | Circuit ID
3ea64c24-1b3c-5463-8c00-f9511d90c8cc | textbox | Cable Size/Type
eb8bf873-4c61-522f-9dde-4d03736a0b92 | textbox | Number of Points
1d7c7fce-33b7-5d83-80f3-2d317e6bbc83 | tickbox | Rough In - Feeds complete
ba3bdd12-820e-5f67-ad87-01f4706f157a | tickbox | Rough In - Loops complete
4a11348b-f280-5318-8f27-2b46a7e6162a | tickbox | Rough In - All cable loops have been roughed in/identified/marked
61376b66-9187-5812-97de-37aba66cab84 | tickbox | Fit Off - Field checked
b51534d1-afc1-5400-9d83-a39cbe52f86c | tickbox | Fit Off - Switchboard checked
36b42834-d4f8-54ea-b2d4-f1cf99e75418 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
8a7b2653-208d-59ca-874a-ffa76bce5962 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
ddf6b903-c391-5eda-b19b-d6a659631c80 | tickbox | Layout Drawing - Checked / Marked-Up
7a087831-cfd8-5c6f-a10e-1943642f6205 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
7b3896c4-4b08-5cbf-b63a-fc734a10606b | tickbox | Labelling QA Complete
1916084d-643a-49a3-a968-1be2f42c309b | section | Inspection 45
aeee427f-6807-403d-b450-01af971cd6a3 | checkpoint | Has all information been recorded and checks completed?
d590b351-1d51-5a86-a312-651f99c3a825 | textbox | Circuit ID
6ca350c3-5263-5956-906d-409778690e75 | textbox | Cable Size/Type
3af235a5-1ca3-5c22-a863-46e2e2d798c6 | textbox | Number of Points
34a69c48-293a-5acd-ae5b-c12eb052d5b2 | tickbox | Rough In - Feeds complete
64015f00-12b2-514b-bef6-1515329202c7 | tickbox | Rough In - Loops complete
1bc87ddb-2670-5a85-9d29-929b062f5278 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
e41a8f65-0797-5b4a-99bc-64019047ef23 | tickbox | Fit Off - Field checked
1dccc085-cb1a-554d-aead-37b4b18791a0 | tickbox | Fit Off - Switchboard checked
7153df46-77d6-52c9-888b-12ed04782e1d | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
a273bd9b-77d2-55e6-bc8d-a56e4090d3e7 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
d53ab714-2e45-5152-9579-30ed06825be6 | tickbox | Layout Drawing - Checked / Marked-Up
44a73fd7-dff2-58b8-8ece-285e898e87a8 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
28cc84ca-837a-540b-a579-f86430c924aa | tickbox | Labelling QA Complete
c2a3f73c-2a64-4f86-8dae-7ba525b013d0 | section | Inspection 46
3d204774-d3f7-4dfa-ab63-01495610e632 | checkpoint | Has all information been recorded and checks completed?
d2fe50ea-19db-5f5a-b6c0-2aaab358331b | textbox | Circuit ID
271e9997-ace9-5120-830c-d8319cac5bc2 | textbox | Cable Size/Type
e9f26e99-43e7-5a52-89c4-d1ec56850b84 | textbox | Number of Points
42f1b37d-2fed-5a63-8de2-5692886672d1 | tickbox | Rough In - Feeds complete
8a6b300f-627a-5ba1-af33-97a937fd3179 | tickbox | Rough In - Loops complete
a3782692-1286-554c-b260-8e28f722770e | tickbox | Rough In - All cable loops have been roughed in/identified/marked
7ca4fd8e-3e60-5408-9d8c-0a9153de02c9 | tickbox | Fit Off - Field checked
3945e57d-6b14-5bd5-8a49-291788db0465 | tickbox | Fit Off - Switchboard checked
920d7672-166c-56b2-b01d-474a306bb12d | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
9d925c73-b0ca-5478-b4fc-49b17568a3a5 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
9316fd64-7d19-52c4-921f-bd12eea03324 | tickbox | Layout Drawing - Checked / Marked-Up
796065e5-ac3d-57de-a463-5f507a73dcb8 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
c839cb39-8aa8-597a-9396-618434c4b6bd | tickbox | Labelling QA Complete
2648cbee-1261-4b70-a6cd-8e4de56f6515 | section | Inspection 47
2bf7e34e-bc81-41c0-b030-023cd44bfcf0 | checkpoint | Has all information been recorded and checks completed?
31026f9d-e63f-5e1a-b3f3-98d6cf0f3c54 | textbox | Circuit ID
162c6bd2-67e9-5983-b94b-2cb006004eec | textbox | Cable Size/Type
2edf5d29-fb05-58e3-8532-9bad5cae2254 | textbox | Number of Points
0e271246-3a2a-55a7-b68d-abb4754db295 | tickbox | Rough In - Feeds complete
97d1d295-f925-5e83-9d27-2cda5ad088db | tickbox | Rough In - Loops complete
66a02d14-d805-549f-a6c6-1661d2de73ad | tickbox | Rough In - All cable loops have been roughed in/identified/marked
da302788-412e-5635-9bbb-b8b768d5bcff | tickbox | Fit Off - Field checked
c2530e39-edf7-5b15-942a-cbb7b751b58b | tickbox | Fit Off - Switchboard checked
5791b47b-09ea-54a2-b52b-bd4c7703cfd0 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
12d674fb-8a75-5e34-991a-6d27b4e92588 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
beac9bcb-a21b-52cf-9911-c22ed14e6742 | tickbox | Layout Drawing - Checked / Marked-Up
9ae22883-6d40-560b-a283-d2243719dff6 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
b5121ae7-48d2-52ac-b5a4-447d1fad32d8 | tickbox | Labelling QA Complete
3ddb3c8e-84da-4027-86dc-7a7eb99ad429 | section | Inspection 48
cdd203e5-4b1a-4da1-8c5a-e1ae63890b48 | checkpoint | Has all information been recorded and checks completed?
21a8f380-64e4-52a2-be0d-ff60e44a725e | textbox | Circuit ID
64abd6fd-0a63-540c-a924-a5be192dc7f7 | textbox | Cable Size/Type
4b05105c-2e76-538b-9310-1402c68d1f21 | textbox | Number of Points
cc58140d-277f-5c7a-84a8-54c3822bddfd | tickbox | Rough In - Feeds complete
58ea799f-93f2-5abf-8ec7-d9318d25ecf3 | tickbox | Rough In - Loops complete
1fdb6ad8-95d6-5942-bb9c-14dc9dcec3ce | tickbox | Rough In - All cable loops have been roughed in/identified/marked
14987779-af51-5bba-9e1c-120ac18ff9e4 | tickbox | Fit Off - Field checked
2e21900b-3f28-584c-8b2e-0ddb2ab758cb | tickbox | Fit Off - Switchboard checked
44b3053b-4bcb-5125-bf9f-300f1a440026 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
b5164905-2194-5f82-8d9e-8188157b87f7 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
719938e0-1147-51d0-a140-8289f2d1a5c6 | tickbox | Layout Drawing - Checked / Marked-Up
e6635a34-4c2d-51d6-a212-29d202d5df93 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
b5a27494-49bc-5bf9-9367-9b2f6aee7fce | tickbox | Labelling QA Complete
6abf3447-c053-42b2-9e54-1e71e154380b | section | Inspection 49
0f0100ea-b6ec-407a-8f17-2699f303b4ca | checkpoint | Has all information been recorded and checks completed?
4b182a30-61e8-5319-bf2b-018f0ca1a63d | textbox | Circuit ID
3a03da42-b1f1-549a-a814-6fb0d29218a1 | textbox | Cable Size/Type
30915b7e-6588-5c8a-8ef8-e8cfec95c293 | textbox | Number of Points
1bf679b4-8da6-5a0a-b125-a556c1beedd4 | tickbox | Rough In - Feeds complete
8c79b7f0-9a9b-564f-b457-0597fc0ff9f4 | tickbox | Rough In - Loops complete
b6aeb2b8-9dc6-583d-9e5d-8a98c7e70370 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
7105ed93-9d63-5b16-8a03-af87242bc114 | tickbox | Fit Off - Field checked
a69ff2cc-68d6-598b-9ce9-b76e19dfb8e8 | tickbox | Fit Off - Switchboard checked
17fb76dc-0caf-5bae-bb9f-26df036e167f | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
c4167869-d695-5045-bca2-c387c1aac72a | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
57c81755-53eb-5b1f-b82d-0e7d3616dce4 | tickbox | Layout Drawing - Checked / Marked-Up
ec1f059f-c52e-59f7-8278-0155b63582c5 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
6e41eacc-99ed-5b3e-bfbd-98ecbb942695 | tickbox | Labelling QA Complete
61b84d70-2927-4fbd-800f-be17d013294d | section | Inspection 50
3308657c-663a-48bc-b321-e1e4f39c8213 | checkpoint | Has all information been recorded and checks completed?
c0277c1a-97a2-5006-8be9-e65266128346 | textbox | Circuit ID
151f7a31-9160-5230-9cb3-77694e99b61f | textbox | Cable Size/Type
09fbab26-bfa4-5868-96df-5257959da70a | textbox | Number of Points
a6030dab-ecc0-5551-ba07-d18ca46b8366 | tickbox | Rough In - Feeds complete
3e411e13-a7d3-532e-91c5-955b50d045c0 | tickbox | Rough In - Loops complete
3fef0b2f-c576-5728-9bab-990dedc30ed5 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
5f1f2c0d-5a9d-5f8c-a77a-5e8807e0c94f | tickbox | Fit Off - Field checked
98a23478-8c94-5216-beaf-a521dc66073a | tickbox | Fit Off - Switchboard checked
07f85eca-4a2f-5d4b-a6fc-c87281960edd | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
7dba84aa-54a2-505a-a1bc-b216ec2629e2 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
3481a905-dec8-518e-9856-30885c0cc107 | tickbox | Layout Drawing - Checked / Marked-Up
b5f097f6-0a6b-5e86-999d-4c122602e0b0 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
0e5ca8d4-3907-5380-839c-c433d5aaf9b0 | tickbox | Labelling QA Complete
9bb453a0-566a-4a0d-92d5-86b89e94664b | section | Inspection 51
18b73753-fff7-47fb-a19b-5f2b7d092a62 | checkpoint | Has all information been recorded and checks completed?
043091a4-26e1-561f-9cad-ef43d99585aa | textbox | Circuit ID
835bd14d-c511-5a23-96e5-c1263af30cf0 | textbox | Cable Size/Type
4dc2badf-4290-5afc-b06e-e381524dba00 | textbox | Number of Points
7cc08893-375f-5c85-b14f-d6cc3c3ad989 | tickbox | Rough In - Feeds complete
029f3683-e1b5-586c-9f79-d304f752871f | tickbox | Rough In - Loops complete
7b018762-43d0-502a-b0fc-58d6edac6ba3 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
7d181470-95d1-5c8a-8bf3-94be3909edde | tickbox | Fit Off - Field checked
b73db1b7-436e-50e6-8f41-262d9e394ee0 | tickbox | Fit Off - Switchboard checked
7977ff98-a452-54e8-8f2f-a8e95f550342 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
8adde1c9-c35e-5d70-bdc2-9c967d64d692 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
49c2aa81-6c40-5340-b4a4-4154ca9ab7ab | tickbox | Layout Drawing - Checked / Marked-Up
20c47f77-6a2c-510f-be21-6d6d3a300bbc | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
0da7a67e-baa5-5192-a5bc-d49a8084ee20 | tickbox | Labelling QA Complete
58fdc085-348e-44ba-906a-d9a230a5a779 | section | Inspection 52
d2895d8f-7fb6-4e72-a219-66c11e26a0bf | checkpoint | Has all information been recorded and checks completed?
918636d0-5e55-5df4-8591-5186fc248d9b | textbox | Circuit ID
a2435d63-e437-595a-82c2-34a2a10b834f | textbox | Cable Size/Type
502673b9-51ce-531f-ac4f-dec59cacc21d | textbox | Number of Points
a52e18cb-6f5f-5169-b0cf-352681d43bd1 | tickbox | Rough In - Feeds complete
925f3cd2-5c0c-5676-8916-a0dee669f4db | tickbox | Rough In - Loops complete
a0d5ac45-c316-53fb-b4c9-5c76ee6a3ab0 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
7c55f905-e735-553d-aa96-2a3ca6b70cf8 | tickbox | Fit Off - Field checked
4eba34ab-5c3e-5c54-8463-25f1f615aa38 | tickbox | Fit Off - Switchboard checked
91526816-8231-5bdb-b3c2-1f3888fcb9d3 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
78021190-caf1-5911-9174-e7e5bd79a19f | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
84d33d7f-1e17-51b1-a275-0fa40acd06f2 | tickbox | Layout Drawing - Checked / Marked-Up
0255d79b-1881-581d-a375-bef4a686c171 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
1c98f6c1-fd34-52ff-b843-e15629088441 | tickbox | Labelling QA Complete
e613e363-a0f0-4d78-ae87-ba8482546c32 | section | Inspection 53
10e638ee-c03d-4070-b16f-da0a70f71632 | checkpoint | Has all information been recorded and checks completed?
b4a03146-59eb-5732-90ec-3b8176ea824a | textbox | Circuit ID
6fa860bd-07c3-5dd4-9c0e-7244ffd3b7b7 | textbox | Cable Size/Type
1f96591f-88ce-558e-8914-a8eb2bc2d9c6 | textbox | Number of Points
7305ce56-3dc3-5e40-8494-93c848e3eaa1 | tickbox | Rough In - Feeds complete
5b277bf3-9149-5a2b-b4e6-d1761ffb35c2 | tickbox | Rough In - Loops complete
de83ac79-a948-5473-b3b6-444827595be6 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
16f9ae79-5b4b-51ab-816f-117e0e2d555b | tickbox | Fit Off - Field checked
97088eb0-97e4-5080-b48c-0b963b6871da | tickbox | Fit Off - Switchboard checked
46f81b9d-6da0-56d2-98a4-76602ceb2b61 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
ab4e1112-a15c-542a-b043-247c0a8fee77 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
b1d88632-51d2-5649-962c-6fe8742412a8 | tickbox | Layout Drawing - Checked / Marked-Up
0c612259-84df-5311-a171-8c7a7fe331dd | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
6dda6069-4221-56c3-a168-b92b565e70e6 | tickbox | Labelling QA Complete
ce45e1bc-76ed-4510-8c70-11380d0fc402 | section | Inspection 54
427b6920-12cb-4350-85ef-ff9563bf7478 | checkpoint | Has all information been recorded and checks completed?
3e024b3f-b7d4-56c2-973e-d464b678c51f | textbox | Circuit ID
a7afb10b-9af3-5f5c-850d-4423b37439da | textbox | Cable Size/Type
8df16a1d-468c-5b74-bee1-7318bb3ff323 | textbox | Number of Points
7c0a060f-2904-529c-97a3-88a95521f7b4 | tickbox | Rough In - Feeds complete
22c3a7ee-ba1b-5507-8bdc-0bf9e964680a | tickbox | Rough In - Loops complete
0b9c0a8e-8e0e-5472-8eb4-cd2bc72fc3b7 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
71d0de51-e0bd-56d9-b59a-7fc626d06b26 | tickbox | Fit Off - Field checked
36533119-ba31-548a-bc91-8f700104fa37 | tickbox | Fit Off - Switchboard checked
4abb2562-1938-53fa-9762-7943e68126a6 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
750d370e-f2dd-5ffa-87ed-5db961ebeda8 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
d4a1c4f6-6070-574c-9563-695dc638040b | tickbox | Layout Drawing - Checked / Marked-Up
c92ead3c-d83a-584b-82b9-bdfb2a13135f | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
64a88195-86e4-57d9-96ea-fe0fe6029641 | tickbox | Labelling QA Complete
02048a55-54bd-47a9-942c-a7bac54e48cc | section | Inspection 55
dbe046f4-34a6-4eac-8f02-0f5f7fb6ed70 | checkpoint | Has all information been recorded and checks completed?
91f92af0-0838-55cf-927d-9c054dc300b8 | textbox | Circuit ID
82c33796-dc48-5223-8f81-ed7d6f19292a | textbox | Cable Size/Type
5b37db16-35a7-58fe-9938-af2edd8be6d1 | textbox | Number of Points
f7c9fbb3-fafd-5ae1-bb55-53830a4a5e47 | tickbox | Rough In - Feeds complete
62d3726d-c338-5903-b3b0-c1812e2a3b3c | tickbox | Rough In - Loops complete
ea46e09f-5c7f-51b7-9c31-f6f2e4d5d41b | tickbox | Rough In - All cable loops have been roughed in/identified/marked
4d20902c-202d-5efd-b87c-788ae6204a15 | tickbox | Fit Off - Field checked
c29906b9-536d-5a5a-8669-c13b184e017b | tickbox | Fit Off - Switchboard checked
11397f89-a4c5-5291-ad87-6ea69fa3fa5c | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
786be763-bf15-5b45-89d3-090be694408c | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
57499971-166a-5510-b55a-e88fe32224d2 | tickbox | Layout Drawing - Checked / Marked-Up
5e2874d2-214e-5617-bd75-e29c41a96010 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
f666fb87-a0f9-5d06-a3f8-904aea23ed8f | tickbox | Labelling QA Complete
8971c789-a20c-41f2-a8bc-a54778349229 | section | Inspection 56
87eb446b-514e-4dc5-9ae9-4da739737612 | checkpoint | Has all information been recorded and checks completed?
a1b6cb9a-90f4-5ec2-b8da-46ed07b2d0c7 | textbox | Circuit ID
de0b58b4-ec21-5ea7-b523-3cfa7c34d51b | textbox | Cable Size/Type
bf120211-e5da-5139-832a-5176d06e8e21 | textbox | Number of Points
13d0da14-3bf9-537d-8cb0-8740759cd471 | tickbox | Rough In - Feeds complete
0c54785e-3156-5929-98aa-093f1241524d | tickbox | Rough In - Loops complete
0055cbef-5c1c-5f90-859a-3690c9071544 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
c63a7bf9-39cc-55c5-93ad-6307d70da38b | tickbox | Fit Off - Field checked
c0e2c5ae-b7e5-5bcd-ad93-a2d42f584292 | tickbox | Fit Off - Switchboard checked
35b8a652-4c2a-549a-819a-6ff01e6e899a | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
df211dd2-a48d-5ca9-b948-ad63584de15c | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
6043f4b9-4b78-5bc5-bce8-fe30a7fdc47e | tickbox | Layout Drawing - Checked / Marked-Up
992db747-a760-5a26-892b-f479e0e4ce63 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
279e7fb2-1883-5f61-b2f5-e5e582df385b | tickbox | Labelling QA Complete
3db8064d-6423-48bc-a0c6-00f7b38d137f | section | Inspection 57
692900d7-f852-4def-9404-d4351d5b8a2e | checkpoint | Has all information been recorded and checks completed?
42452afa-5e5d-524b-873c-88e47f4f918c | textbox | Circuit ID
b6069fe1-29ce-5288-82cc-669c9cd05fa7 | textbox | Cable Size/Type
95fba2b2-0aa5-5bcf-ae9a-c9d9fbe00c2e | textbox | Number of Points
c0f2a666-9202-595e-afbf-14cd4cba4a30 | tickbox | Rough In - Feeds complete
a1c837c4-314b-5f16-823a-fa1611e11385 | tickbox | Rough In - Loops complete
d0759d05-e827-56a3-8001-cb6e8e6bcd6b | tickbox | Rough In - All cable loops have been roughed in/identified/marked
5e47e50e-6d1d-5318-a7e3-26c419f9a2ad | tickbox | Fit Off - Field checked
54efe663-cf4e-5e44-9305-f25460d63228 | tickbox | Fit Off - Switchboard checked
b458056d-aa1a-523d-822f-2edcd2b69e64 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
4af3585b-fecc-5aa9-892c-842cb16c899a | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
68f4c23d-e648-5103-a848-f702f7954ea2 | tickbox | Layout Drawing - Checked / Marked-Up
0ad5e510-6b7a-56af-b22a-0bcb7e59ac0d | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
53894a70-5664-564e-ace4-09949c4d04b9 | tickbox | Labelling QA Complete
aa8350b6-34cc-465d-9503-8a73f22742db | section | Inspection 58
c888f5ad-c701-4234-9935-dffb43c4ec2f | checkpoint | Has all information been recorded and checks completed?
3854e21f-3b17-5a11-96a0-19898c5fbcad | textbox | Circuit ID
98be7ed8-32eb-561e-9d35-51cf65030ba7 | textbox | Cable Size/Type
cf675c9e-ef8a-530d-8ec2-a57aea231ea1 | textbox | Number of Points
3015cb35-c6e3-5330-b7bc-8d701698285b | tickbox | Rough In - Feeds complete
b7dbb9d4-2b5d-594f-8820-f11e2ee47e89 | tickbox | Rough In - Loops complete
09670288-0c4c-5ef7-b587-53a409d1650d | tickbox | Rough In - All cable loops have been roughed in/identified/marked
77a8e9df-bc8c-5de9-9ce5-3887366d3591 | tickbox | Fit Off - Field checked
3a3241b7-a50d-5d1d-8ac5-914c3010bf44 | tickbox | Fit Off - Switchboard checked
e9f1a8bc-0acc-5468-b6a2-8363902f1591 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
2533d1f6-d8c4-58d3-9492-ceb90c2080cb | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
bd11bd21-ec7d-5a1d-9afb-a7b0daea804e | tickbox | Layout Drawing - Checked / Marked-Up
ce47cd68-ae98-5ace-be1e-ace34e48716a | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
60e6e981-3376-5fd9-aecc-6de7e3bd7dea | tickbox | Labelling QA Complete
af018696-44fe-4c08-b574-ff0317fdd259 | section | Inspection 59
f63941d2-b1e1-4e5a-9fa5-f9bd0c351cd2 | checkpoint | Has all information been recorded and checks completed?
ea839139-d5fd-5501-bbc6-a459f29bf91b | textbox | Circuit ID
c4691fc0-87f7-55a2-a6f0-bf62611827c7 | textbox | Cable Size/Type
8bc7bd86-05fe-5961-b280-666f1678a289 | textbox | Number of Points
2054bfe1-2dfb-5ea0-a078-ca2fdc81e5fc | tickbox | Rough In - Feeds complete
b6f316ea-d90f-5e3d-bb86-54128db15081 | tickbox | Rough In - Loops complete
e63aa0d6-1e51-565e-89c4-1572191356b8 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
38a0b076-7846-5e7d-809f-713340e11a5c | tickbox | Fit Off - Field checked
e7d6824b-82c6-5653-afdd-8b5c4f1eae53 | tickbox | Fit Off - Switchboard checked
efbd56fd-b462-5b37-aeeb-33a5f3075811 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
e3151f65-257c-5447-abcf-c9046c086fc4 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
a918fdb9-8a35-5e48-a99d-7eb5495da063 | tickbox | Layout Drawing - Checked / Marked-Up
ca865a94-f465-59c8-b4ff-cc1da4e204cb | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
b3fcaaa5-e404-547c-9286-4467f5be1e24 | tickbox | Labelling QA Complete
643c40bf-bc30-4dbc-b0e5-692a7fbca69d | section | Inspection 60
e74f904b-0b60-4abb-9cd7-3b1505b02d91 | checkpoint | Has all information been recorded and checks completed?
e9b9fd7b-6c6a-5d27-ae4a-1a14254d5c41 | textbox | Circuit ID
8735a323-c928-5e65-8d15-488e1700f36f | textbox | Cable Size/Type
f73eef85-9611-59d7-9fac-c9487642f4ef | textbox | Number of Points
e6f8deaf-3406-5ca5-bc7b-0be6de73db8c | tickbox | Rough In - Feeds complete
a211fe91-63ea-5008-8508-38ec2c862369 | tickbox | Rough In - Loops complete
d2988011-8586-58a8-95f5-61b79e07effb | tickbox | Rough In - All cable loops have been roughed in/identified/marked
54b5a35b-60c8-5c8e-b1c3-858625bb25bd | tickbox | Fit Off - Field checked
ab925616-d015-50fa-94ad-1172b71af554 | tickbox | Fit Off - Switchboard checked
f03943cb-c71d-57cd-ba88-b70049f0f1b9 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
9506d646-5980-5ced-847c-37aea5ce41da | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
4fdec304-052a-59e7-9a40-4d356967801f | tickbox | Layout Drawing - Checked / Marked-Up
2a49f72d-bcca-536e-9e94-f242424756ec | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
e5d09a17-39fb-528c-aade-7ee25656d39c | tickbox | Labelling QA Complete
89db58a8-824d-4be7-ba45-5646bf4d90da | section | Inspection 61
a3ce1097-a47f-47da-a4b8-238377998466 | checkpoint | Has all information been recorded and checks completed?
5472e82f-60a2-5973-b21c-d9ee5df994aa | textbox | Circuit ID
c84d707e-48bb-5a9e-a3e2-7fd92ad90996 | textbox | Cable Size/Type
82c94b81-cdfd-58c5-ba8d-41132a996f0d | textbox | Number of Points
7299f757-b272-5146-9e8d-309ef6dee968 | tickbox | Rough In - Feeds complete
06e75942-ec1b-55bf-8930-18f9e3a4b169 | tickbox | Rough In - Loops complete
4e192e11-7391-55ff-b535-4075cfde95b8 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
11bfc50b-9f81-546e-955b-c95801ce5c64 | tickbox | Fit Off - Field checked
dbbeba54-6c5d-599e-9532-37d261d10e07 | tickbox | Fit Off - Switchboard checked
e3fb175b-dae2-50f0-8eaf-c7635d6d4d12 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
96adc0d8-9f7c-5872-824b-24a9eaaca774 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
36d6d674-d837-5efe-95d7-40e4138a7394 | tickbox | Layout Drawing - Checked / Marked-Up
347bed5b-511b-5ec5-849f-7020005ac6ba | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
411c8e01-a775-55f3-ba9a-6412707f56a7 | tickbox | Labelling QA Complete
42e99d1a-9d86-4306-95f4-8dafd65d3332 | section | Inspection 62
6609baf0-3d4c-4788-83da-e76bcaacc389 | checkpoint | Has all information been recorded and checks completed?
e63a6eeb-4c1c-5057-8e7a-f4da4ef773e6 | textbox | Circuit ID
2cabca22-aff6-52d9-bfea-89a6592293b1 | textbox | Cable Size/Type
5f546e5a-0515-5698-a0c9-61a66a9a9484 | textbox | Number of Points
118f814d-9f67-5c0d-bd9b-766db12c15d8 | tickbox | Rough In - Feeds complete
d6b8abcc-3626-5901-8db3-5bc09c35d126 | tickbox | Rough In - Loops complete
dcbef9c7-6c6a-5ce5-9655-6a09573f9322 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
e4d37042-ac1c-55be-8d11-80092af1b3dd | tickbox | Fit Off - Field checked
16922b13-2a9a-52c0-868d-573ac8f1c4b5 | tickbox | Fit Off - Switchboard checked
dac7aab2-d283-51b6-9eb4-6a7859c9977d | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
3f627933-9115-57f8-b7e0-753fa3268410 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
d5c11ac3-7e09-5e5c-aed2-67d35c5b8f01 | tickbox | Layout Drawing - Checked / Marked-Up
9cf93ad4-9862-5c92-8183-35dda3d80769 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
de2ef57f-1511-5797-b1e7-7348966a9378 | tickbox | Labelling QA Complete
79c67fa2-543f-46b2-8ce9-5ab69a546371 | section | Inspection 63
00202ea3-24c0-4282-a9f9-01cdc64791b6 | checkpoint | Has all information been recorded and checks completed?
49dee756-54b4-5c1e-8db4-756f396b6c0c | textbox | Circuit ID
544417db-f5d2-5fee-9f66-4d288dd3d25a | textbox | Cable Size/Type
d29b87df-a5a6-5d17-9130-4f5aab870c25 | textbox | Number of Points
7a68e997-b3d4-5b08-9629-35ddccb252e0 | tickbox | Rough In - Feeds complete
1d3193f3-a6bd-50c4-9a51-495e76e8019b | tickbox | Rough In - Loops complete
5ba09f22-b9ba-5f18-9969-9548faa9ebd5 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
f1591f17-b903-5bec-8ed5-55a2017ffb78 | tickbox | Fit Off - Field checked
9403bef9-d661-5e6c-8b09-ac0e65871ece | tickbox | Fit Off - Switchboard checked
8b13e543-4599-55b4-bdba-2626e087afd8 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
bbb8c96c-5b03-5ebe-88be-21aa45c9ac87 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
cd3dd5bb-f436-59dd-887e-ee632c783ff8 | tickbox | Layout Drawing - Checked / Marked-Up
b05a6d46-1c7f-547f-9db1-5bc2f3e78a5b | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
eabcc75c-9a8b-5f58-803b-9f4bfbd513c4 | tickbox | Labelling QA Complete
3b0c027a-887c-4493-bed3-e71dbbd12749 | section | Inspection 64
9e5bd6db-a790-4bb9-9c49-1329d50775d6 | checkpoint | Has all information been recorded and checks completed?
15b843a9-45eb-5c7a-a7ef-cf4baf9ff0f6 | textbox | Circuit ID
28f5835c-921c-532d-b865-c2b1fccc1784 | textbox | Cable Size/Type
5fd07098-8350-5b3f-a5ff-5825a5f1d5a7 | textbox | Number of Points
12a5e347-ad0f-51aa-b1e7-7b6902ee6189 | tickbox | Rough In - Feeds complete
922339ca-169a-505a-964c-e759287ea448 | tickbox | Rough In - Loops complete
3d2125b7-a005-5eee-81fc-73fd6b4e515d | tickbox | Rough In - All cable loops have been roughed in/identified/marked
0e04ef0f-f65b-5062-bad5-049b83efb7d1 | tickbox | Fit Off - Field checked
25eb7ce8-5333-5a8f-b411-61e63028a9f9 | tickbox | Fit Off - Switchboard checked
4f5e03a2-da26-54f8-b919-1c3e32992648 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
748fb22f-3c4b-546d-adc2-a9e95bedd2f7 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
445556a8-74ef-5cfc-99cc-5535b1e9959c | tickbox | Layout Drawing - Checked / Marked-Up
e15561ea-298f-51ac-8bc6-6c62ab6c1c5c | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
1d4ff3a7-70b6-5e7d-aa6f-93c79dd0257c | tickbox | Labelling QA Complete
c882b33f-4c44-456d-885a-7ac5fdc35f98 | section | Inspection 65
3298bde0-1604-4ee4-b3ca-65e1c8a29559 | checkpoint | Has all information been recorded and checks completed?
64a02c22-2c4f-5d34-a5cc-9d5f8086acb4 | textbox | Circuit ID
0a792668-d015-5ad1-90c9-f15358d98959 | textbox | Cable Size/Type
2d2865ba-d754-5d9a-bb85-a176fd78f36c | textbox | Number of Points
d39d5c6e-d8e2-553b-8e52-67327bc5e4b2 | tickbox | Rough In - Feeds complete
4c8c76df-7043-5a86-8f8b-3b1d16691a53 | tickbox | Rough In - Loops complete
5011ecec-1c4c-587d-8bee-990a5db11d78 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
53007dc5-40be-52a5-bcef-c557cddb4e23 | tickbox | Fit Off - Field checked
785bdd03-e5c8-5c32-8f87-168a4f13af09 | tickbox | Fit Off - Switchboard checked
5f249400-4449-50a8-ab46-e2cf19493601 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
fcbdef22-8d4d-5d22-a425-736793e50ec8 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
8cf67c2d-31ec-5282-b6ea-418bbf3996d1 | tickbox | Layout Drawing - Checked / Marked-Up
dc14ecb9-3b3d-5c66-92ad-bbc90954b1cd | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
4a7c30ea-97d3-52b3-8a69-a9a5a2e90e65 | tickbox | Labelling QA Complete
07510fae-4cfe-49db-aa16-7d7019d8a82d | section | Inspection 66
b0127d83-0b0d-4d19-9722-d11f14da9f75 | checkpoint | Has all information been recorded and checks completed?
227669bc-5f03-542c-b7a3-8a6d9660464b | textbox | Circuit ID
f2d979dc-9fad-5ea3-81a5-a262caa5eb5d | textbox | Cable Size/Type
cabe18ba-1d71-50ca-a340-869dacc0a1a6 | textbox | Number of Points
efdab1d2-0eeb-5479-9d8f-4eeca83e9853 | tickbox | Rough In - Feeds complete
4ac6ffff-3368-5b16-800b-ea780b4771bd | tickbox | Rough In - Loops complete
042f0b2b-76e9-5b01-99e6-19ff2d4c7d6a | tickbox | Rough In - All cable loops have been roughed in/identified/marked
03029e8f-b193-58ae-b9b6-dbd21ec356f0 | tickbox | Fit Off - Field checked
1fa52672-a6d5-5f53-9155-01a14e60a256 | tickbox | Fit Off - Switchboard checked
3dd240ea-296c-51a2-86a5-befa061cf841 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
c00e6c2e-3c4f-5c65-ab4c-bcd201d8aa83 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
be60e9eb-1e1d-57dc-9f07-ad74649392a9 | tickbox | Layout Drawing - Checked / Marked-Up
c532eaf9-3899-58c8-9a0d-4d9685c6e787 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
8d1aa99d-a45a-5a7c-bbf9-74a17364fb78 | tickbox | Labelling QA Complete
f30cd00a-f8a5-4407-847f-35ce220a930d | section | Inspection 67
8ac4d41a-f45d-4362-b972-ad9724b36bb9 | checkpoint | Has all information been recorded and checks completed?
3bc79fa8-5df4-574e-bc50-260d38775f77 | textbox | Circuit ID
218c3e1d-92a6-5f5b-8e7a-19430d1369d4 | textbox | Cable Size/Type
381cfc9a-d045-5a06-a011-08791f177283 | textbox | Number of Points
8fd7c0b0-bbdf-5dca-b0d1-60fa2230b217 | tickbox | Rough In - Feeds complete
be7b9496-10af-52cf-b9f2-f72338876a0d | tickbox | Rough In - Loops complete
bdb6ea70-a7fd-5504-813d-922b77e3d9c5 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
daf99cef-a1d9-5131-a021-a8ad218f3f6e | tickbox | Fit Off - Field checked
fcaeeb13-0e6e-5ff4-aa33-741516f05d4d | tickbox | Fit Off - Switchboard checked
85160a79-9e16-57f6-917e-c4d9c9ec48d0 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
2eb36d76-ce48-582d-bdae-a54c4913d2ca | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
c46fb7e6-3f84-55b3-b8a5-6fa57b151c4d | tickbox | Layout Drawing - Checked / Marked-Up
439243c6-8d5d-51b9-ab17-a94028f20346 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
53c334f1-9074-5e7c-8812-3c76f7a257b5 | tickbox | Labelling QA Complete
ddfb8d54-87d9-4815-910e-1930b45bbc4e | section | Inspection 68
73e34b3f-8e37-4e14-ae30-4339d575947b | checkpoint | Has all information been recorded and checks completed?
c07cd8a5-a240-5523-8b9a-c3672da96f5c | textbox | Circuit ID
3025c435-8865-5cb2-b2f2-04af57168999 | textbox | Cable Size/Type
27375c82-7194-5021-aef7-6f3e626824f5 | textbox | Number of Points
c8a477f7-d753-5b5f-bf49-89b45953991d | tickbox | Rough In - Feeds complete
7b72ef4e-923c-5053-a5d4-7bee6f78090f | tickbox | Rough In - Loops complete
1ad86113-7215-5307-ae87-36c845a6af93 | tickbox | Rough In - All cable loops have been roughed in/identified/marked
4fd12132-897d-5b5a-aa19-9b05e0e84cca | tickbox | Fit Off - Field checked
f5f62d76-7f7b-52c3-945a-2b74decfece4 | tickbox | Fit Off - Switchboard checked
201a5ac4-75c6-5696-baa1-3aa5663dfa03 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
30c55c09-1b74-54d8-8bcb-dcb2f9f00311 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
fbe8a7cb-e8ba-5c60-a72f-0126e5e46583 | tickbox | Layout Drawing - Checked / Marked-Up
715a0c2e-24f6-5401-ad1f-fbdedf54d08d | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
de58381a-8710-5742-831e-f578e9d2a4e5 | tickbox | Labelling QA Complete
dae5f47a-21b4-40e4-98d8-615f599e3ed9 | section | Inspection 69
d8cd5d4c-ca32-43b3-adff-d6ca019ce2bb | checkpoint | Has all information been recorded and checks completed?
bfdee163-262a-5360-9df2-33d6c2f8a577 | textbox | Circuit ID
722fd2ff-3116-57eb-8fd9-8bd4443f3616 | textbox | Cable Size/Type
1716eb98-d5dd-565b-864f-17c13f9859c4 | textbox | Number of Points
1ad26f56-5d60-5941-a1b4-14e67016ae09 | tickbox | Rough In - Feeds complete
4d6342eb-dceb-57f6-a538-79d7ce9ff3af | tickbox | Rough In - Loops complete
e91ac44b-8441-5a20-8f7e-7953b0aaf77d | tickbox | Rough In - All cable loops have been roughed in/identified/marked
fdf167bb-a255-599d-84ec-6ad4dfd35881 | tickbox | Fit Off - Field checked
cfb4bc94-7c41-5aed-a853-179f4a71e9cc | tickbox | Fit Off - Switchboard checked
b53f7bc1-a5e6-533d-96d3-a1aee3814120 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
099e0f50-66ae-52d6-98e5-e0dfc4e0fde2 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
ba94b6f9-41e2-552e-ba2d-a7f69dbfa4ed | tickbox | Layout Drawing - Checked / Marked-Up
b0a907c7-cc50-5182-9b42-5b23b4bcb50c | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
bcb0b8db-a5d8-576b-ba93-ffa9e2b9d022 | tickbox | Labelling QA Complete
817071d6-32e0-4ad8-967c-03756c4fa274 | section | Inspection 70
644d2945-8450-46a0-aae4-4c1a6406afbb | checkpoint | Has all information been recorded and checks completed?
42b3e782-8646-56c2-9a63-ed1424ca448a | textbox | Circuit ID
74ebe25f-3801-58fe-8d66-0168efb8f357 | textbox | Cable Size/Type
64f789d2-108c-570b-be4f-d22ed7ab972e | textbox | Number of Points
27c80676-0841-57ab-a34f-ee4965afe68c | tickbox | Rough In - Feeds complete
26f47336-3091-5817-a4ec-1ce47bfc9b62 | tickbox | Rough In - Loops complete
89873087-7261-5142-836e-7f9eeec679fd | tickbox | Rough In - All cable loops have been roughed in/identified/marked
e1eedcbd-0ed1-566a-9f10-107b4269077c | tickbox | Fit Off - Field checked
8620b0c3-969d-5c6f-86b8-aa0dc595b029 | tickbox | Fit Off - Switchboard checked
b4a69741-ca0f-5dab-b3c5-96b3b23299d5 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
6f323175-d902-50b1-b5b0-600f9284d4b1 | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
9712a4fe-4209-55e5-8e0f-aba61e511f68 | tickbox | Layout Drawing - Checked / Marked-Up
7186ba91-f489-5294-a451-be03b7e2fbe1 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
5a75a553-52f4-5ac6-973a-bbe223d3d72f | tickbox | Labelling QA Complete
2ab9b91a-d79c-4ab5-9e89-48cce6a0454c | section | Inspection 71
c27ed560-99dc-46b1-b391-d91b350be105 | checkpoint | Has all information been recorded and checks completed?
5867764f-a5c7-5f6a-89a9-fb8323683978 | textbox | Circuit ID
93b0e36c-f7b6-5794-8021-e3a0e30b8452 | textbox | Cable Size/Type
c54a482b-2db9-583a-bc47-fa9750964ed8 | textbox | Number of Points
243951b4-6748-5012-8de0-a5f8e44d64fd | tickbox | Rough In - Feeds complete
71a08e12-c056-5831-849b-829c019e1aaf | tickbox | Rough In - Loops complete
758b8c1b-af6f-531d-aba4-480924541f3e | tickbox | Rough In - All cable loops have been roughed in/identified/marked
08457743-e9fa-5d78-8d3e-741ab9a89238 | tickbox | Fit Off - Field checked
cc271ab5-03d4-59f4-be73-b9b8a470cd7e | tickbox | Fit Off - Switchboard checked
da25de78-2ac3-5bdc-82e9-446382bf5521 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
ccbc130f-af75-501f-94c0-dba3098b5c5a | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
80c07e2d-0683-554b-9664-6939729b4aef | tickbox | Layout Drawing - Checked / Marked-Up
c80ffd31-c520-54e7-894a-382dc8a21b3c | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
40610fe1-cc7b-574b-bb8e-641eff25374d | tickbox | Labelling QA Complete
48081d04-9d5c-432f-bf4d-e55567d818ff | section | Inspection 72
2ef55759-c492-4aa4-a649-f6cf2b469d11 | checkpoint | Has all information been recorded and checks completed?
0295618b-8958-5972-8036-4bddd1f46393 | textbox | Circuit ID
2058a52e-dc1f-530f-94c7-3b06039caa81 | textbox | Cable Size/Type
2b1bd5e1-7c4f-5834-adc5-cb9789f17955 | textbox | Number of Points
4e7caa71-4b59-5ab7-9c7a-25e80ab2400f | tickbox | Rough In - Feeds complete
bb11a360-abd0-5dba-86c1-e1bd657a5ebf | tickbox | Rough In - Loops complete
b5e56c3b-65a8-5074-af91-38c3d51c312b | tickbox | Rough In - All cable loops have been roughed in/identified/marked
4fa2d740-cbea-5878-ad16-dbd25509874a | tickbox | Fit Off - Field checked
884a2a07-3fa6-50a5-80e9-929229913b16 | tickbox | Fit Off - Switchboard checked
ae1214f6-e76e-57cc-9ba1-e1ecf892c007 | tickbox | Dead Testing - Complete and recorded on Final Installation Test Sheet
bce96bdd-90d4-5bc5-af10-905590b6f61c | tickbox | Live Testing - Complete and recorded on Final Installation Test Sheet
d5b467b3-14e0-59b3-98c1-a614c42313d1 | tickbox | Layout Drawing - Checked / Marked-Up
cc9b40c5-7ac2-5b63-a927-955cbe971a68 | tickbox | SLD & Switchboard Drawing - Checked / Marked-Up
fadbd317-9af3-51e7-a9c5-9ca0a69e3ebe | tickbox | Labelling QA Complete
caa2cf0b-0024-4561-8257-e069d9b37682 | checklist | QA_TEM_079_Equipotential Bonding |  | QA_TEM_079_Equipotential Bonding
3857331d-d8d7-42cb-ab08-6ad12157f215 | checkpoint | Earthing installation as per Electrical Earthing Layout (attach drawing highlighting inspected installation)
7d284107-a458-4ccd-b632-7ae4bf4bbfbc | checkpoint | Earthing networks segregated i.e., Clean Earth segregated from protective earth, intrinsically safe earth segregated from protective earth etc. (where applicable)
97cb2698-6d67-49f3-8aea-d671279fb1a9 | checkpoint | All conductors are suitably protected against mechanical damage.
6f27a9ad-ec0b-4069-8938-7bfffd6e26ee | checkpoint | Conductive water piping has been bonded to the earthing system (AS/NZS 3000 5.6.2.2) - (attach photographic evidence to checkpoint)
8f1662b2-46de-40f5-b304-486a7f2f672f | checkpoint | Conductive reinforcing within a concrete floor or wall of a room containing a shower or bath has been bonded to the earthing system (AS/NZS 3000 5.6.2.5) - (attach photographic evidence to checkpoint)
04b4bb99-dd40-4953-a1d9-477351b72a11 | checkpoint | Swimming Pools and Spas Equipotential bonding conductor connected to the conductive pool structure, electrical equipment, conductive fixtures and fittings, and earthing conductors associated with each circuit supplying the pool or spa (AS/NZS 3000 5.6.2.6) - (attach photographic evidence to checkpoint)
3ad885b4-234f-4f9b-8e36-3d47c5570035 | checkpoint | If the telephone and telecommunication earthing system is directly connected to the electrical installation earthing system, the requirements of AS/NZS 3000 5.6.2.7 have been met and the Communications Earth Terminal (CET) is labeled "COMMUNICATIONS EARTH TERMINAL".
43c806e0-1ece-4f00-9c0d-06e3288bd2b5 | checkpoint | Continuity of the earthing system meets the requirements of AS/NZS 3000 8.3.5. Resistance of the main earthing conductor or any equipotential bonding conductor is not more than 0.5 Ω. (attach drawing identifying Test Points & record results below)
7f615e92-ac37-4f88-a0c6-b8574ff9a1c4 | checkpoint | Equipotential bonding requirements as listed in AS/NZS 3000 5.6.2.1 have been completed
e3c5f8cc-b65f-4715-9390-7385b9e08c39 | checkpoint | No.1
2295d054-48fe-5156-8e20-4fbd50e5e06c | textbox | Test Point (No.) From
c1f7026f-e38f-5936-84f2-2e87dd2d7150 | textbox | Test Point (No.) To
b7e86c1c-d39e-5afe-aacf-e3d59cee16f6 | textbox | Ohms
7db43da8-834e-46c6-a1bd-26d5f71a147b | checkpoint | No.2
ba0bd277-bfda-574e-9615-f7beaeeee330 | textbox | Test Point (No.) From
3a2fa76e-9256-5a61-90b7-eed79cdb7c25 | textbox | Test Point (No.) To
7b7030e5-e0eb-5197-8faa-efeb34f8f262 | textbox | Ohms
a10c83a0-a203-4882-a82e-cc2a119f8efb | checkpoint | No.3
b7603e16-2ede-5a08-ad57-55f176a8282b | textbox | Test Point (No.) From
d2906bb3-eedb-5faf-a2cd-5bd5bb4a4b91 | textbox | Test Point (No.) To
bfa15276-6f5a-5029-9757-ff11ebd9d5d5 | textbox | Ohms
7ea99693-3076-455a-b229-cd519b22648b | checkpoint | No.4
6e73608d-6311-58e9-8d49-7ddc8021178c | textbox | Test Point (No.) From
c604aa6b-9a4f-58af-89df-d04719d27eb2 | textbox | Test Point (No.) To
57314582-129f-5d38-b2ab-4ace76537b99 | textbox | Ohms
d6bab997-f58d-4ed6-9ea4-6aa7996b6ef4 | checkpoint | No.5
1f4a7142-84b2-5c9c-8dc8-13b8c9b456ca | textbox | Test Point (No.) From
bd42d2d7-6c7e-54d9-b79e-c02bda717bce | textbox | Test Point (No.) To
fa2818d8-3414-5d12-934c-9bc23ee8628d | textbox | Ohms
58b6c090-bb33-4722-9aa7-f859df1124d6 | checkpoint | No.6
85d05659-dfa6-5559-97cd-d7117ef58f35 | textbox | Test Point (No.) From
69a23059-df61-5346-881c-02541ac8fbfe | textbox | Test Point (No.) To
03d68a98-5a3d-5582-bf95-bb8b43656c31 | textbox | Ohms
b5d135ef-3830-4d35-930b-aa0debdd1f43 | checkpoint | No.7
26dc060d-6b6d-5341-bab1-053c3a49c76d | textbox | Test Point (No.) From
89ed6a0c-56a4-5834-ac88-9014e25ce7df | textbox | Test Point (No.) To
c1af3073-5bbf-5d10-ae80-b8e3dfaf91f8 | textbox | Ohms
c292cbef-56a6-4813-8b04-d74b3078c15c | checkpoint | No.8
aed0e4a0-71a4-580c-9c6f-6b0e45c7e87d | textbox | Test Point (No.) From
ff7e7601-d4f3-5887-b535-e8f8c357ef6b | textbox | Test Point (No.) To
ff2b6276-e043-5a87-b968-89a94b5b88b3 | textbox | Ohms
61bdf793-a850-43de-96a8-f81051b26967 | checkpoint | No.9
1a496d78-d95d-5807-bbf0-ba62638ef8fe | textbox | Test Point (No.) From
4a6ed87d-341a-5dbf-8ccd-3bd58062bf04 | textbox | Test Point (No.) To
b7535905-21df-5d13-9a13-e150fe4fe8ba | textbox | Ohms
eedca716-d1bc-4472-b198-666bcd2c6a00 | checkpoint | No.10
c8681678-b1e7-5c34-84c3-00fe027289e1 | textbox | Test Point (No.) From
58d8c6d9-9e32-5c3b-a5f6-81c9cdb705d6 | textbox | Test Point (No.) To
963d3019-25dd-5d48-8c8c-245b468aa569 | textbox | Ohms
e73986ee-3a1b-4ebe-b0dd-98982fb5c735 | checklist | QA_TEM_080_Room Body Protection Checklist |  | QA_TEM_080_Room Body Protection Checklist
05402b01-fe22-4783-9ea1-8b4807b2ced3 | section | Room Body Protection Checklist details
9d82b187-38fc-42e3-b581-93f8a3f6a155 | checkpoint | Room Body Protection
63298821-66a1-5081-98e0-e7489c172594 | textbox | Room #
1d8a1d1b-eeba-5187-9e46-82234009ac04 | textbox | Drawing Reference
bcfbc29c-85d8-5974-b3b3-7c4f42a16494 | textbox | Drawing Revision
8e96a207-a86d-55f3-aec3-ac2b0d8d6d46 | button | Activity | Rough In, Fit Off
2816103a-f293-41ce-be2d-8b2baa8d66c4 | section | Item #1
5fef6f9b-6fc0-4cdd-8d30-0b458d11138a | checkpoint | Light Switch installed
f89009ca-eb24-4d0a-a57f-0740ad5b3202 | checkpoint | Installed at correct RL
62bce979-e364-447f-a1bc-bb4de9cebd51 | checkpoint | Installed in compliance with architectural drawing/s
7e9e73be-5c7e-4fe6-bf78-6110461e5dbc | checkpoint | Installed in compliance with AS/NZS 3003
a70d4e5f-6004-422a-98a7-052ef9eab9cc | section | Item #2
6c79cda0-df48-42f5-97c4-bcfca4e7e741 | checkpoint | Light Fitting/s Installed
2f8a0f53-b580-4b50-b166-945dc5df9a3f | checkpoint | Light Fitting/s are the correct type
02042eee-6339-4817-8d16-9a331a02fd31 | checkpoint | Installed in the correct location/s
b7fb3faf-840f-4f9e-9c3c-024acb618364 | checkpoint | Are securely fitted
cd57460f-1984-444d-a3d9-45298948d2ba | section | Item #3
73867ae9-d970-4c6c-810c-6c13553e41df | checkpoint | RCD installed
95c67697-fc09-4ac7-9b33-0eb0affae0a6 | checkpoint | Installed at correct RL
bbecc590-da61-481f-ad90-b2f0c352892a | checkpoint | Installed in compliance with architectural drawing/s
fdbd1814-ac24-40c7-ae11-9d5f63b115c9 | checkpoint | Installed in compliance with AS/NZS 3003
2eb8f2a1-5bfe-4141-b593-1d70d26ab00b | section | Item #4
60cbba8b-8208-4ab9-9851-1443270ba01f | checkpoint | Socket-outlet installed in ceiling
9638ff27-99f3-4a39-8505-8fc83db78dc9 | checkpoint | Installed at correct RL
673f0bb2-ffe7-435c-a359-7bb7ec79e312 | checkpoint | Installed in compliance with architectural drawing/s
27aceb1a-f4a1-4724-8fb5-b8bddbb704f3 | checkpoint | Installed in compliance with AS/NZS 3003
ed1139e4-aafa-4ef6-8d74-463251d1000d | section | Item #5
c76743df-63d6-469c-b86d-30d167dc281e | checkpoint | Normal Supply Socket-outlet (White) installed
20c68245-f50e-44c2-819c-176e4359c084 | checkpoint | Installed at correct RL
a3292f94-59ca-498b-86d3-e3054cc36003 | checkpoint | Installed in compliance with architectural drawing/s
825ddc20-0387-465b-be1e-75d1117b26f7 | checkpoint | Installed in compliance with AS/NZS 3003
182fede5-e530-41e8-bc02-fdf1a1a90a87 | section | Item #6
bc5f45d6-c2cf-4217-850f-3c4e53788cd7 | checkpoint | Essential Supply Socket-outlet (Red) installed
196c1613-aed1-4b2a-b00a-632ac8565148 | checkpoint | Installed at correct RL
8a256f9b-5c57-4a52-b72c-7c4eb78dd8ef | checkpoint | Installed in compliance with architectural drawing/s
e54a5584-4a83-454d-9286-a6ff27066044 | checkpoint | Installed in compliance with AS/NZS 3003
753f59b0-5f8a-45a3-bad2-e03f8fa46ef7 | section | Item #7
8e270c01-890e-4f43-b4ab-0cb8b0f778f0 | checkpoint | UPS Socket-outlet (Dark Blue) installed
5e0de79b-edc3-4c37-aafd-8e5f041605b4 | checkpoint | Installed at correct RL
f7a8ba5e-4c97-4ed5-a4cc-bc9b4239304b | checkpoint | Installed in compliance with architectural drawing/s
f161183d-9619-46f7-afb3-0c0c59ddfa47 | checkpoint | Installed in compliance with AS/NZS 3003
96dc96ad-081f-40e3-bfc8-f8295488e492 | section | Item #8
a799a91e-0dcc-4d15-89b5-a5ff3b6ea8a7 | checkpoint | “Cleaning Purposes Only” Socket-outlet (Beige) installed
8bb8d1df-2ec9-4d54-b768-409141e408ad | checkpoint | Installed at correct RL
6920f754-6c60-42c8-8587-d911a63163fe | checkpoint | Installed in compliance with architectural drawing/s
dacc4e12-4d59-4b4b-9917-9ca8346f53b1 | checkpoint | Installed in compliance with AS/NZS 3003
9e171962-f45e-485e-adc8-560e65099ef2 | section | Item #9
57ccaeda-b9df-4269-b696-686ac29233b0 | checkpoint | Normal Supply Double Socket-outlet (White) installed
154b50dd-3f65-4f02-8a16-b214756dfe14 | checkpoint | Installed at correct RL
01064794-21ad-481d-a143-845d02982934 | checkpoint | Installed in compliance with architectural drawing/s
c2d1e5c4-a0fe-43ca-8984-c9f67e2e8728 | checkpoint | Installed in compliance with AS/NZS 3003
1fe8bc8d-551b-4482-9b4f-69686af45979 | section | Item #10
7ca9970b-27ab-4218-aa7e-d32867a6be63 | checkpoint | Essential Supply Double Socket-outlet (Red) installed
73053649-a837-4f6a-9c2a-4d55d7cf633b | checkpoint | Installed at correct RL
595dbff5-a4a1-427f-95a9-730dde8ae6b6 | checkpoint | Installed in compliance with architectural drawing/s
37c47f9e-cc45-4ae5-9116-3cfa7f934eb7 | checkpoint | Installed in compliance with AS/NZS 3003
3dd50851-885b-41cc-bd27-a1d5fd2727f3 | section | Item #11
80392f29-65de-4537-8b0c-30d97f73e841 | checkpoint | UPS Double Socket-outlet (Dark Blue) installed
72dc0507-2e57-4a6f-99dd-97009d205c7c | checkpoint | Installed at correct RL
64b6e1ed-a9a0-4463-84f8-7710c444c418 | checkpoint | Installed in compliance with architectural drawing/s
b50880da-a807-4927-9cdd-113694379f83 | checkpoint | Installed in compliance with AS/NZS 3003
d4f725f2-caf5-4107-8eea-4864cc214b24 | section | Item #12
161aa0df-bf46-4917-b0c7-cbf54872264e | checkpoint | Medical Services Panel installed
25670507-9cb1-4252-a2e4-979f39c6122a | checkpoint | Installed at correct RL
a44dbea3-b446-4e30-8e1e-fa709088dfed | checkpoint | Installed in compliance with architectural drawing/s
2427616c-7b48-448c-88b4-f43582a8b2b0 | checkpoint | Installed in compliance with AS/NZS 3003
0788cdcc-0c61-4c44-98c4-c541d97dd79f | checklist | QA_TEM_081_Cable Pit Installation |  | QA_TEM_081_Cable Pit Installation
5b5eb048-302f-4288-9689-7bef9681b2cc | checkpoint | Confirm the completion of QA-TEM_004_Trench and Backfill (all tasks prior to backfilling) has not raised any non-conformances. Photograph trench showing correct depth.
3fa31c32-45e5-440c-8c6e-0e1bf46fd79a | checkpoint | Confirm drainage requirements of pits
64e72946-367a-4dea-9f72-f20674561c99 | checkpoint | Check that the pit is:
a5b2d528-8ae9-5fad-a880-b2816698e522 | tickbox | The correct type, configuration, size, quantity of access holes
2f44f462-7aa9-5469-b326-1fd28bda9286 | tickbox | Correct depth & following the correct route
84150cef-2bf7-5f7d-b097-36956fa2ef72 | tickbox | Correctly joined with conduits
6efe0097-46ba-4ff4-97f9-e018babfad78 | signoff | Hold Point - All above must be completed before further works proceed
8a4ba908-8844-460f-904a-8c69e52a4bf3 | checkpoint | Photograph trench detail showing correct installation method. Photograph trench showing 150mm Sand covering all conduits and installation of detectable marking tape.
cb08fdb0-9fba-4688-bcc7-30fed1a43d56 | checkpoint | Seal pit around conduits
df8ab20b-406c-44c4-9136-87052793e86a | checkpoint | As Built drawings completed
82ebccae-5e68-4395-9356-2f32363850d2 | checkpoint | Conduits are cleaned, rodded and roped
a667072e-8e1d-40f3-92a8-152764f9204e | signoff | Hold Point - All above must be recorded and signed off
656abab6-9e74-44c1-b0df-03694dae8009 | checklist | QA_TEM_082_Room Checklist |  | QA_TEM_082_Room Checklist
761062b6-b16a-4f66-be8d-cfcf46574e06 | section | Room Checklist details
0b0f42bb-52c1-47ec-b764-d198b07a23f1 | checkpoint | Room Checklist
3cbc8cc7-6b42-5a1c-9358-92ecf90bb7e8 | textbox | Room #
48d5a9d7-e736-573b-9a26-7d2f3c78c1d6 | textbox | Drawing Reference
cdfd67af-5a68-5a3b-9e32-bfb23f72e0d0 | textbox | Drawing Revision
026323ab-1e04-5586-880d-64e01e26a5da | button | Activity | Rough In, Fit Off
7a5f08c6-838d-44f8-92a8-5c016b582e6e | section | Item #1
0cd15b88-e063-4b12-9d9c-d8d5aebc23f9 | checkpoint | Light Switch installed
6bd459d1-a28e-48c4-9947-8f08a37dd37c | checkpoint | Installed at correct RL
7a28a42b-2aa4-4f29-b7cf-3fe00b5ee85e | checkpoint | Installed in compliance with architectural drawing/s
b618654a-c8fd-4414-8a7c-eabff5437bf4 | section | Item #2
43e2a139-f614-4486-885b-cea47125b986 | checkpoint | Light Fitting/s Installed
45098d4d-bae8-49f9-a778-9c6a1fb1b5f5 | checkpoint | Light Fitting/s are the correct type
73d3a0ac-84c9-4ea7-9dae-496bf09f037a | checkpoint | Installed in the correct location/s
5fabeffe-4b5c-47aa-81bf-664eb3adb74e | checkpoint | Are securely fitted
3c5fb63a-0f86-4f05-b062-fe9137273252 | section | Item #3
2f0abd35-f6b1-4be0-b426-b38d0fd8d772 | checkpoint | RCD installed
5d67dcd4-afa5-4c6c-b34e-f8a38716c3ab | checkpoint | Installed at correct RL
79901819-37b2-4a1d-aa34-11732603f456 | checkpoint | Installed in compliance with architectural drawing/s
cbcd71ac-422c-4e18-b903-7bbd14272ddc | section | Item #4
7863e930-f595-4359-b363-457ec6affa78 | checkpoint | Socket-outlet installed in ceiling
083d1192-c7d0-442b-8dee-46912c1b5809 | checkpoint | Installed at correct RL
5c90e578-18e5-4dea-8059-2a87d3a50827 | checkpoint | Installed in compliance with architectural drawing/s
8348a9d5-b725-4281-a10c-2e75f1774b48 | section | Item #5
5eaf7b07-119e-4cdd-be77-8442126ee6f0 | checkpoint | Non-essential Supply Socket-outlet (White) installed
cea6a756-8696-4426-9495-6287f71b1cc8 | checkpoint | Installed at correct RL
79b56bcb-4e6f-4fa7-aa27-6f1d70354d99 | checkpoint | Installed in compliance with architectural drawing/s
13f8f722-c706-421a-8a9e-b2eff613a232 | section | Item #6
c29447e8-a6bf-46a7-8b40-831213da08a2 | checkpoint | Essential Supply Socket-outlet (Red) installed
fb967601-b698-4f26-aa62-d344a99a8b7d | checkpoint | Installed at correct RL
7a9a420a-bc63-4f4a-b652-a90678ffd454 | checkpoint | Installed in compliance with architectural drawing/s
fac42a8e-8a7e-49d0-bc15-623601bf1593 | section | Item #7
7b8ef3ca-8e71-4e6b-86ec-22f96cd7f737 | checkpoint | UPS Socket-outlet (Dark Blue) installed
5aa00b2a-d556-4b08-a412-a7f7bc763769 | checkpoint | Installed at correct RL
79a2ef74-3d46-4cd9-9624-cfab7a1b0969 | checkpoint | Installed in compliance with architectural drawing/s
d17732a5-365c-4609-b4f4-098b9556dd04 | section | Item #8
1666bff2-95e4-4d15-9c58-bc3241918d0f | checkpoint | “Cleaning Purposes Only” Socket-outlet (Beige) installed
4396a088-9a32-4bc9-b026-5e6f91996bba | checkpoint | Installed at correct RL
11250d02-3bb8-460c-ba2f-cc2500c4dc99 | checkpoint | Installed in compliance with architectural drawing/s
dbf302e5-4e8b-434b-9572-d4e535c0c450 | section | Item #9
0d3c1fe5-f0a0-4874-97ab-51e65aac4ae8 | checkpoint | Non-essential Supply Double Socket-outlet (White) installed
200dae36-a46d-4cff-8c54-e253416473f3 | checkpoint | Installed at correct RL
06ba9437-1163-47fb-919d-7fa5bfa1f130 | checkpoint | Installed in compliance with architectural drawing/s
059eb95d-8d0c-450c-bdb4-b24e045c3172 | section | Item #10
882574fd-848a-4f3b-bca5-8f3f532bfc7a | checkpoint | Essential Supply Double Socket-outlet (Red) installed
4dedf751-4bc6-450d-970a-09ec77173cbd | checkpoint | Installed at correct RL
f94a7c15-e1e3-40fe-87ee-c8ea17661dac | checkpoint | Installed in compliance with architectural drawing/s
a987f7ac-b15a-4874-b18a-8870a848fa9b | section | Item #11
781b51a9-cbc2-46a2-a17b-e531e4ed26b2 | checkpoint | UPS Double Socket-outlet (Dark Blue) installed
5a377403-b9c8-4507-89f7-3a1dd0b7aa5b | checkpoint | Installed at correct RL
cd65e45d-d013-489e-8f48-e5309d659b61 | checkpoint | Installed in compliance with architectural drawing/s
70bc5428-302d-409e-937a-7aa9ec3c101a | checklist | SYS - QES-ITC-E03-009 |  | QES-ITC-E03-009
bbfacccb-8e24-4bbf-abcf-314b82a13ce5 | section | Room Body Protection Checklist details
11da6888-89f1-4c1c-a8f2-8d60660b3057 | checkpoint | Room Body Protection
63298821-66a1-5081-98e0-e7489c172594 | textbox | Room #
1d8a1d1b-eeba-5187-9e46-82234009ac04 | textbox | Drawing Reference
bcfbc29c-85d8-5974-b3b3-7c4f42a16494 | textbox | Drawing Revision
8e96a207-a86d-55f3-aec3-ac2b0d8d6d46 | button | Activity | Rough In, Fit Off
98eda5bb-d243-49c4-872a-1324f4098700 | section | Item #1
cec0d947-de22-4318-95c7-a6f2e007dbec | checkpoint | Light Switch installed
d1e13655-e126-4e05-8aaf-2c8a8c69f8e3 | checkpoint | Installed at correct RL
83cb55b9-7af1-4e13-a64f-06a34f03f14c | checkpoint | Installed in compliance with architectural drawing/s
ee0d77fa-2ebb-4bec-a7a4-11c975acf618 | checkpoint | Installed in compliance with AS/NZS 3003
12b9dcfe-041a-41d4-99e1-ce0183f19b72 | checkpoint | Item #2
25fc5ae5-db6c-4a20-b55e-e43a1d5fa851 | checkpoint | Light Fitting/s Installed
5051b531-b814-4ff1-97f9-5bc1b81a5906 | checkpoint | Light Fitting/s are the correct type
f07caee5-5760-47a2-a3b0-a8f18542161a | checkpoint | Installed in the correct location/s
0eed749c-06d2-4cd2-bfc4-75456e7229a2 | checkpoint | Are securely fitted
16129055-43ac-4973-8161-6728692ebcba | checkpoint | Item #3
065f996b-9c50-43c2-a3ad-0c8ee43a9c31 | checkpoint | RCD installed
a9075d8f-9b42-4cee-962e-986250cc1c3c | checkpoint | Installed at correct RL
dfc92ebd-8560-4563-be22-bb928b74b445 | checkpoint | Installed in compliance with architectural drawing/s
ecf0fad3-1284-475f-982a-15cd8bb34e3c | checkpoint | Installed in compliance with AS/NZS 3003
38f61e32-ecbe-4bbc-977a-69388d4a4918 | checkpoint | Item #4
caf5d9e8-eb83-481d-a62a-299f07076c1e | checkpoint | Socket-outlet installed in ceiling
c00d1d8e-aa4e-4c9e-93ec-fb06ca5fb9ff | checkpoint | Installed at correct RL
2855858e-569c-4e10-b409-04f9ea3d3356 | checkpoint | Installed in compliance with architectural drawing/s
0eebdcae-8330-4d59-b15d-4d9aebcc756b | checkpoint | Installed in compliance with AS/NZS 3003
6f5c8b3a-dd2e-47a5-a43d-25ec60019f2c | checkpoint | Item #5
b2dc4f1c-bf13-41ae-904f-caad81fd9409 | checkpoint | Normal Supply Socket-outlet (White) installed
d5defb71-02c1-40db-a22c-62da43375ee9 | checkpoint | Installed at correct RL
68fb46c0-2c07-4f8b-ab15-cd43e96a43e6 | checkpoint | Installed in compliance with architectural drawing/s
d9f474a3-daf8-4e9c-a017-79d29371f219 | checkpoint | Installed in compliance with AS/NZS 3003
dffe0af6-373a-4768-a09f-c7e93f4aba3e | section | Item #6
b578b3bc-b360-4963-99ae-4d61a03e1af9 | checkpoint | Essential Supply Socket-outlet (Red) installed
12b6c27d-e6cc-4a69-9fc9-eebf66e3ece6 | checkpoint | Installed at correct RL
919df8d1-c896-49b7-9840-bda86a70e4bd | checkpoint | Installed in compliance with architectural drawing/s
b7ce7bbc-12ae-4130-bf61-77e7beddd858 | checkpoint | Installed in compliance with AS/NZS 3003
2014b51a-59cb-49d5-aa84-acd31dc53cf4 | section | Item #7
3cd556f4-38e1-4407-9f45-f472e2d61d46 | checkpoint | UPS Socket-outlet (Dark Blue) installed
cc9b9072-ec3a-4482-b360-4d000b1e93a5 | checkpoint | Installed at correct RL
21b535d5-408a-4a71-b987-f0a51cf40768 | checkpoint | Installed in compliance with architectural drawing/s
4d5e71d0-d990-4b40-9ae1-743d5cf6ea19 | checkpoint | Installed in compliance with AS/NZS 3003
1fca4abf-dc14-4787-a6a7-632e3fa168ff | section | Item #8
ff133124-c3f5-416a-bfd0-3ffb4fb85380 | checkpoint | “Cleaning Purposes Only” Socket-outlet (Beige) installed
2d4e7b47-1163-4f28-b60e-8af79be7accd | checkpoint | Installed at correct RL
7fdaa9c2-64a0-4e9c-be8d-76d86faa92b1 | checkpoint | Installed in compliance with architectural drawing/s
64590c04-5f34-49b0-bbfe-8d37112b6dd7 | checkpoint | Installed in compliance with AS/NZS 3003
49a06317-d942-449c-a7be-6d141bed7518 | section | Item #9
138e2d76-4d7f-42d5-8263-da3de3d706d6 | checkpoint | Normal Supply Double Socket-outlet (White) installed
08f88ad4-933b-4d39-8ead-32963687f5e5 | checkpoint | Installed at correct RL
8b992ebc-cc5c-4b1e-b1dd-eba9c01a16e2 | checkpoint | Installed in compliance with architectural drawing/s
79062e0f-bc14-4cd6-a80c-869109358fe1 | checkpoint | Installed in compliance with AS/NZS 3003
b87f67dc-30bf-4a01-885e-9eb4a4ebcb4a | section | Item #10
057d89c6-1adb-4a21-bc3a-d8895eefe622 | checkpoint | Essential Supply Double Socket-outlet (Red) installed
88a1c36b-2aa0-426d-9bbf-63ac55eb2667 | checkpoint | Installed at correct RL
508fbd72-611b-4e7c-aee9-8835b9fc5566 | checkpoint | Installed in compliance with architectural drawing/s
f71f0a52-340e-44ed-9401-d16e137d1b3d | checkpoint | Installed in compliance with AS/NZS 3003
d9bf768f-4f2d-4fc0-8890-6dd83a9eabed | section | Item #11
379d1f28-bffc-413f-b13b-41522753af05 | checkpoint | UPS Double Socket-outlet (Dark Blue) installed
244b4826-c214-40b9-be2a-8a1c3d28a271 | checkpoint | Installed at correct RL
b96e33fe-f226-4d5b-81d3-b11158cde9db | checkpoint | Installed in compliance with architectural drawing/s
01ed8bec-9b83-4dbd-a242-d3ddd7014cc8 | checkpoint | Installed in compliance with AS/NZS 3003
fcdf2d66-2d35-4e54-98e4-b56291507516 | section | Item #12
32192b66-9b60-4dd7-916b-9b12ad33600a | checkpoint | Medical Services Panel installed
174cfe49-f4fb-4a3a-9288-0ec465cfa161 | checkpoint | Installed at correct RL
26ee7535-2259-4de6-85b5-f5e7df48235a | checkpoint | Installed in compliance with architectural drawing/s
bbb596ef-353d-4744-b915-5f2ccd10243e | checkpoint | Installed in compliance with AS/NZS 3003