## Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | ITP - Pavement Detail 'H' RAB | itp | ITP - Pavement Detail 'H' RAB | c5ae5522-f7f2-4e4a-ac60-cfd03c9e665f
| checkpoint | 1 - Existing Pavement
4110ad7a-77f4-41ee-addd-23a8f894a06b | note | Activity Task: Construction
2c5bda63-7cad-46f5-b581-0bf7e48eeadb | note | Acceptance Criteria: Visual inspection during shoulder check out works of entire project, including measurement of low areas or at least 25m intervals with a minimum of 3 per exposed area.
977e2c34-ec20-49aa-9ff3-5963b524aef0 | note | Certifying Documents and Frequency: 25m intervals. Engineer notification prior to commencement of pavement construction
40c004ec-59e4-41ae-962d-7918d7539674 | note | Engineer’s Representative: H
| signoff | HOLD POINT AUTHORITY
| checkpoint | 2 - Subgrade
9d307d61-1daa-4935-9a6c-2f69be83d13e | note | Activity Task: Construction
0ba80f38-5f38-45d6-afe6-ecceba91175a | note | Acceptance Criteria: Check insitu lower subbase is minimum of 150mm over a subgrade of Min CBR 5. If not undercut to 580mm and construct lower subbase 200mm with Gap65
16b350b2-4820-4d28-8a66-c9a6c2462b08 | note | Certifying Documents and Frequency: 1 Scala CBR Equivalent test per 10 m2 (minimum) and Engineer’s visual inspection at each dig out location. Scala Test sheetse
a9efc592-ba54-434a-acac-0fcf0ae816a9 | note | Supervisor, Foreman or Subcontractor: W
| checkpoint | 3 - Subgrade/Dig outs
cc6f4a90-5735-4116-b190-58685a0c8b27 | note | Activity Task: Construction/Test
72fb6962-f70b-4d16-afaa-2bb5e7eeb81f | note | Acceptance Criteria: Weak areas of subgrade to be cut out and backfilled where determined necessary: Check insitu lower subbase is minimum of 150mm over a subgrade of Min CBR 5. If not undercut to 580mm and construct lower subbase 200mm with Gap65, Inspection Check sheet
4460a5cd-5d23-4787-828d-4f71f18e9b4c | note | Certifying Documents and Frequency: 1 Scala CBR Equivalent test per 10 m2 (minimum) and Engineer’s visual inspection at each dig out location. Yes – prior to dig out, results required prior to payment.
2835080b-df7b-412b-a068-40f17d10b83e | note | Engineer’s Representative: H
| signoff | HOLD POINT AUTHORITY
| checkpoint | 4 - Proof Roll
2cdf64fd-d110-4c96-abe0-e40c836cc36b | note | Activity Task: Construction
eb4a4640-2917-4f32-8391-c0d6403e4b9d | note | Acceptance Criteria: Roll with 10T steel wheel roller in presence of Engineer
ad5698e6-362b-48d4-9de9-d683b0ea2bbf | note | Certifying Documents and Frequency: Any unsatisfactory areas which become evident during such testing shall be undercut 200mm and backfilled with GAP 65
| checkpoint | 4.1 - Subsoils
e2399b80-ceb2-46a7-bbf3-f703d2fffdad | note | Activity Task: Material Supply
dfe6f441-2bdc-4962-b804-b7cdce4dd84e | note | Acceptance Criteria: Subsoil drain materials shall comply with TNZ F/2:2000– Specification for pipe subsoil drains. Pipes for subsoil drains shall be slotted 110mm diameter corrugated HDPE.
2b18eb4d-2a1c-44ee-ac1c-12ee43612eef | note | Certifying Documents and Frequency: Compliance certification from supplier
| checkpoint | 4.2 - Subsoils
ef3bb461-3ae1-4cf8-92a5-dccf7edf60c6 | note | Activity Task: Construction
5cf03f74-2598-49ae-a106-abf117df7729 | note | Acceptance Criteria: Subsoil pipes for pavement drainage shall be in accordance with TNZ F/5:2000 except that the subsoil pipe may be placed immediately underneath the overlying granular pavement layer, with 50mm of drainage metal each side and below the pipe. Subsoil drains to be laid on hard pan below subgrade or otherwise governed by the height of stormwater outlets from CPs into existing Stormwater line. 20/7 drainage metal to be used
64171071-ed0d-4cd9-a3b2-0d1d1f0420c2 | note | Certifying Documents and Frequency: Photos and checklist
| checkpoint | 5 - Sub-base
0012d7ad-7169-44f5-b6b9-c43814b04bd6 | note | Activity Task: Material Supply
72afa857-d1f5-441f-8dd7-8a303f984d08 | note | Acceptance Criteria: Gap 65
| checkpoint | 6 - Sub-base
96415c76-6bb4-4950-8ab8-f49390f8d273 | note | Activity Task: Test/ Material Supply
bd0677e1-3585-4f48-bc75-41b781d45049 | note | Acceptance Criteria: Proportion of broken faces. Test to TNZ M/4 broken faces content, NZS 4407: 2015 Test 3.14 no less than 70%
96e4f4d0-511c-4b10-a849-8b0eda991460 | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
3cdee05e-6e0d-47a2-bd0b-b55e8715e776 | note | Project Manager or Delegated Person: R
| checkpoint | 7 - Sub-base
ddc6d472-0c7d-467f-8af1-d06004e8662b | note | Activity Task: Test/ Material Supply
5dfd18b1-e744-4893-bb5d-e7426bcb2518 | note | Acceptance Criteria: Sand equivalent to NZS 4407:1991 Test 3.6. Sand equivalent to meet specification
3f89314b-4883-4fbc-8d2d-2b94001c9161 | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
8999844c-2a62-4043-a20a-5683f26de4c4 | note | Project Manager or Delegated Person: R
| checkpoint | 8 - Sub-base
967bbd3b-79fb-4140-af75-85c6f537f100 | note | Activity Task: Test/ Material Supply
7047924b-4f14-4e32-bdc6-067a73e265a5 | note | Acceptance Criteria: Crushing resistance to NZS 4407:1991 Test 3.10.
1d152566-3743-42fc-9d55-75773a46778b | note | Certifying Documents and Frequency: Compliance certificate < 6 months old or test result on sample from site, per source (stockpile) and for every 1000 m3 delivered to site.
6cc43409-eece-49ff-a161-767c5fb246e2 | note | Project Manager or Delegated Person: R
| checkpoint | 9 - Sub-base
0470060d-4533-49ba-aa43-4225b2d86acd | note | Activity Task: Test/ Material Supply
11063b13-3d7b-4a69-8b96-616abacd4f5c | note | Acceptance Criteria: Weathering quality to NZS 4407:1991 Test 3.1.1 Compliance certificate < 6 months old or test result on sample from site, per source (stockpile).
5e83f876-f240-459a-be3f-adbb6a2d7d97 | note | Certifying Documents and Frequency: Prior to placement of subbase and base course
0bfccc44-f78b-4f66-b67c-ab2055801904 | note | Project Manager or Delegated Person: R
| checkpoint | 10 - Sub-base
9e6a9491-983f-4e25-a928-1360c1ed107c | note | Activity Task: Construction/Test
1af2714c-71a2-4519-8fec-63802fba4cb7 | note | Acceptance Criteria: Maximum Laboratory Dry Density (MDD) of aggregate at Optimum Moisture Content (OMC) to NZS 4402:1986, Test 4.1.3 Per source (stockpile) – to be undertaken on representative stockpiled aggregate.
efe2eda9-c8c9-4927-a02b-301c3c073689 | note | Certifying Documents and Frequency: A minimum of 5 samples is required for stabilisation lengths less than or equal to 400m
2a931fa4-3e1c-4717-b8b4-3ace503fe63d | note | Engineer’s Representative: H
| signoff | HOLD POINT AUTHORITY
| checkpoint | 11 - Lower Subbase
872a3bd8-c64c-428f-9158-445803f764aa | note | Activity Task: Construction
02ae493d-30f3-4969-840e-c2f037b74c14 | note | Acceptance Criteria: Check insitu lower subbase is minimum of 150mm over a subgrade of Min CBR 5. If not undercut to 580mm and construct lower subbase 200mm with Gap65. Nuclear densometer dry density tests to NZS 4402;1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20 m interval throughout.
ed6d34e2-55dc-4af3-ba82-7d7e35439e5e | note | Certifying Documents and Frequency: Mean value of density tests shall be not less than 95% of MDD, no individual test less than 92% of MDD.
107f7b53-f51c-4cd0-bd2d-55136ee5b8a4 | note | Project Manager or Delegated Person: P
| checkpoint | 11.1 - Upper Subbase
0268ce79-d03c-4bed-bdcd-3fc3de506db2 | note | Activity Task: Cement Supply
7b1b52a5-f4f9-4423-ae5e-54ff782fee2f | note | Acceptance Criteria: Application rate to be 2% as specified
98ab10fb-a0d3-42b2-8956-6e98a1c82f82 | note | Certifying Documents and Frequency: Application rate to be checked per 400 m2 of stabilisation.
| checkpoint | 12 - Upper Subbase
e4eb3601-a79a-46b8-9580-1bee564d0004 | note | Activity Task: Construction
2a747d5d-d00f-4640-975e-eabee78f5957 | note | Acceptance Criteria: 150mm Cement modified AP65 upper subbase
af2b1eb5-e599-449a-b60a-110836fc296c | note | Project Manager or Delegated Person: P
| checkpoint | 13 - Completed sub-base prior to placement of AC20
7145f854-50ee-49c8-afe5-bef6e3af0c2a | note | Activity Task: Test
5fd0cf98-a185-4c75-ac6a-d0c681bd0e3a | note | Acceptance Criteria: Nuclear densometer dry density tests to NZS 4402;1986 Test 4.1.2 (NZ Heavy Compaction) at randomly staggered transverse positions at 20 m interval throughout.
6671c9d6-2227-4008-990f-4784a2ebd890 | note | Certifying Documents and Frequency: Mean value of density tests shall be not less than 98% of MDD, no individual test less than 95% of MDD.
983fe555-1e69-49de-8ab1-38517248704c | note | Engineer’s Representative: H
| signoff | HOLD POINT AUTHORITY
| checkpoint | 14 - Completed sub-base prior to placement of AC20
462d7b35-fb93-40a4-b249-8a2cd5abfc11 | note | Activity Task: Construction
10ed2c82-ba33-4272-94c6-bfe3bfaa2436 | note | Acceptance Criteria: Straight edge checks on surface shape at randomly staggered transverse positions at 20m intervals throughout.
53615b9d-d0c4-47ad-8caf-3f39ca2178b0 | note | Certifying Documents and Frequency: No point on the surface shall vary more than 10mm from a 3m straight edge. No area of the completed surface shall pond water
3ca552ce-55c0-4c7e-9d46-4820b205ec8b | note | Supervisor, Foreman or Subcontractor: W
| checkpoint | 15 - Completed sub-base prior to placement of AC20
752d4a67-ab34-4eda-bcf4-7adfd5f82af1 | note | Activity Task: Construction
59f272d5-73ea-4769-82d7-15cda5bf749c | note | Acceptance Criteria: Provide a sound finished surface to line and level as specification. Surface shape matches design and minimum pavement depth provided.
996bf5de-12cd-48a6-b2a5-4c5920a34abd | note | Certifying Documents and Frequency: Visual inspection by Engineer. Surface to be as specified. Engineer to be informed when surface is ready for inspection.
01611e15-cce6-4ceb-aacf-0591cf72adfd | note | Engineer’s Representative: H
| signoff | HOLD POINT AUTHORITY
| checkpoint | 16 - Tack Coat
7598989f-db9e-4a4a-a198-1eced07925e0 | note | Activity Task: Construction
ea20250f-c5ba-468c-98f2-411c7a29e7f7 | note | Acceptance Criteria: Shall comply with TNZ M1 and TNZ M3. Apply Tack Coats between asphalt layers
45b37ac6-d1a6-495b-8ccf-72dbd9756180 | note | Certifying Documents and Frequency: Two samples per distributor load on Request. Refer to Subcontractors QA in separate ITP
| checkpoint | 17 - Asphaltic Concrete
bad0e199-a41f-4403-9959-0fee881c5aaf | note | Activity Task: Material supply
fb2f973a-7656-4eec-a9b3-722269591923 | note | Acceptance Criteria: As detailed in NZTA M/10:2014 specification
225bc549-172f-4b33-9de9-663ab620052d | note | Certifying Documents and Frequency: As detailed in NZTA M/10:2014 specification. Refer to Subcontractors QA in separate ITP
| checkpoint | 18 - AC20
30863a0c-9401-41c6-9494-984b5e18e996 | note | Activity Task: Construction
216115ad-87ca-43b2-8c29-255c173d0429 | note | Acceptance Criteria: 180mm AC20 to be laid in two layers
d513a6fb-9a8f-4da8-b2f6-66eceac82d87 | note | Certifying Documents and Frequency: Testing to be done. Refer to Subcontractors QA in Separate ITP
| checkpoint | 19 - A14
54f50d76-9181-4011-b2f4-8fdbb1a5a209 | note | Activity Task: Construction
0e61d885-2a38-415e-b269-7f429f50a172 | note | Acceptance Criteria: 50mm A14
a6f23a6b-7d06-4237-8f54-d47395d4e026 | note | Certifying Documents and Frequency: Testing to be done. Refer to Subcontractors QA in separate ITP
| checkpoint | 20 - As -Builts
23d89377-4fa3-45d5-aba6-089802a97036 | note | Activity Task: As -Builts
fdf71285-16c0-4f7e-ac5f-c6cc878bb27d | note | Acceptance Criteria: A complete set of as-builts as per Contract 792 Specification Document shall be provided on the completion of the project. This will include but not limited to
c8cfc826-0da5-4939-bf9d-d0e727f62e4b | note | 1. The subgrade under new pavement areas;
b3879031-f42e-492b-ac65-1a2d965d5b15 | note | 2. Road construction – including subgrade, thicknesses and nature of materials used, surfacing; j. Extent of formation;
350c37ac-7edf-43ca-a2a5-a17de0e07e24 | note | Certifying Documents and Frequency: Prior to placement of Structural Asphalt Refer to Subcontractors QA in Separate ITP
| checklist | ITP - Whangarei Odour Control Plant Upgrade Sewpercoat Spray | itp | ITP - Whangarei Odour Control Plant Upgrade Sewpercoat Spray | b427dbbd-7afb-4972-b31a-c28980e0a669
| section | Pre-construction
| checkpoint | 1 - Construction drawings and specifications from Designer(s)
8a06c185-c471-5ab1-8b6f-f220605bcbe4 | note | ACTION (Hold, Monitor, Witness) - H
76010f7c-f135-56fa-95dc-c4d4c32e9967 | note | Detail - Construction drawings and specifications from Client/ Engineer
f5ec0a6f-0fd1-5b7d-ac20-437c735715e9 | note | Frequency / Timing - Pre-construction
d194f21f-bb42-517f-993d-37d137cbdeb5 | note | Inspection / Test Method submission, visual inspection, testing, measure, - Document Review
a066bf30-5be7-5f06-924e-46ae795715c2 | note | Conformance Criteria - confirmation in writing
f26fa8f8-2d7b-58d0-9456-1d291520e897 | note | Records - Drawing Transmittal
ee23cedd-b9d7-5234-8c5c-0cf67c564c12 | note | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil
| signoff | HOLD POINT
| checkpoint | 2 - Pre-construction meeting
861e6012-a56d-50e2-a92c-f55240799028 | note | ACTION (Hold, Monitor, Witness) - H
8d86db2d-6bd6-5488-beb9-92c1d863b7c8 | note | Detail - Prior to commencing works, a pre-start meeting to be held with client to confirm
f31f2729-36d8-5ed5-81a0-245969f049e6 | note | Frequency / Timing - Pre-construction
47871087-b763-55d6-b8b4-0018a7a5607e | note | Inspection / Test Method submission, visual inspection, testing, measure, - Document Review
50c51cee-049f-5fba-baba-9b365de9e90c | note | Conformance Criteria - sewage isolation process agreed signed off
9014c142-f566-5df7-b6ff-1ecd4c39b894 | note | Records - Meeting Minutes/signed-off documents
de38bdd0-fb66-5765-a4c3-05adc25ee8d6 | note | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil
| signoff | HOLD POINT
| checkpoint | 3 - Pre-works Inspection
8238d3ac-a715-5a19-bff7-214ed899538b | note | ACTION (Hold, Monitor, Witness) - W
39b228d9-9680-58f4-a920-979c3c3bb853 | note | Detail - Contractor to arrange a joint inspection of the relevant areas, within and outside the working areas, with Engineer, Principal and relevant landowners/ occupiers
7254104c-d951-557c-b6a0-c4db2f0164b3 | note | Frequency / Timing - Pre-construction
9411fd22-445f-54d8-9bc3-1572fb24c2ab | note | Inspection / Test Method submission, visual inspection, testing, measure, - Visual Inspection
a13ef9d3-4cd2-555c-94eb-9c340b62d659 | note | Conformance Criteria - Confirmation in writing from all parties that the record is a true representation of the inspection
fe70713e-c899-52d7-b5d0-3594d9995486 | note | Records - Marked up Drawing
c42fef1f-adbd-5314-93f1-d423353115bb | note | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil
| checkpoint | 5 - Site access (1)
c60b5044-04a3-511b-b2eb-8190144cb909 | note | ACTION (Hold, Monitor, Witness) - H
487d8da8-5566-584a-b501-faf73d709793 | note | Detail - United Civil to grant site access to Contech
b4ae5321-33f7-546a-a92e-f910b4cddb70 | note | Frequency / Timing - Pre-construction
8520056c-e95c-5c00-b904-3741c0417a6d | note | Inspection / Test Method submission, visual inspection, testing, measure, - Document Review
ec317f9f-85b4-5453-ad72-18bf990c0338 | note | Conformance Criteria - Access Permits.
d696234f-d927-59ee-9e24-c22a1ea80671 | note | Records - Signed-off documents
249f2fae-9d79-5772-b4ef-e8c7395fde06 | note | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil
| signoff | HOLD POINT
| checkpoint | 5 - Site access (2)
cf2c30be-c609-5b3f-be12-52438dfb2926 | note | ACTION (Hold, Monitor, Witness) - H
1a97bd55-a88b-5ace-9113-ab02e104a58a | note | Detail - United Civil to erect a scaffold no more thsn 400mm from the workface
119d115a-89f5-5bd1-b0de-2443aec033a5 | note | Frequency / Timing - Pre-construction
80085cb2-c2be-57bc-9824-7f031fd14958 | note | Inspection / Test Method submission, visual inspection, testing, measure, - Visual Inspection
d228b5cd-9a2e-5d1b-8234-470f9ff98c21 | note | Conformance Criteria - signed off ready to use
797114e3-5b8e-51b5-8016-d479110fca74 | note | Records - signed off documents
b3b290e2-a3ba-599c-9874-c37e2de84541 | note | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil
| signoff | HOLD POINT
| checkpoint | 6 - Work instruction signoff
d0abc9a5-e3ae-5ea4-a4ad-4841442ecae1 | note | ACTION (Hold, Monitor, Witness) - H
a551da55-ee54-5707-9be9-3b6ebfd18b45 | note | Detail - Work Instructions produced for works
c334148b-782e-5beb-97e6-e148c1f65bec | note | Frequency / Timing - Pre-construction
3477fd1f-f884-5fb3-9637-f8369dfd3f92 | note | Inspection / Test Method submission, visual inspection, testing, measure, - Document Review
24bf16f4-d2f2-5878-8bd5-35f63baadd5b | note | Conformance Criteria - Staff to sign onto the JSA prior to commencement of work onsite
e89ea109-d87c-5d1a-84c4-e7ba00aa1dc3 | note | Records - Signed-off documents
41bfcb24-c54b-57f1-9177-81645df7f6da | note | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil /Contech
| signoff | HOLD POINT
| section | Materials and Procurement
| checkpoint | 8 - Sewpercoat ordered and compliant, and delivery to be timely
b0fbf6d1-140e-5cd7-8b33-42cb153b4621 | note | ACTION (Hold, Monitor, Witness) - W
330398da-e6fd-53df-9ce0-25c556fbb4b0 | note | Detail - Material to meet quality; be the right quantity and delivered on time
b7b20206-4d70-5a03-8e36-9440f837ee0f | note | Frequency / Timing - Pre-construction
f87bdaec-bffe-5457-9e3d-e4dd4075442c | note | Inspection / Test Method submission, visual inspection, testing, measure, - Testing
334fc497-efd0-5ffb-a035-c54201461e7e | note | Conformance Criteria - Cube Strength Results to be supplied
91643d19-dbe8-5abc-b50a-8a305413d5ba | note | Records - Lab Strength Testing Report
dc411384-07e7-545b-92a1-3b1d1951f933 | note | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
| checkpoint | 9 - Sewpercoat on site, and correctly stockpiled/Stored
4a2a9f6f-26c5-5e49-9abb-8e666904bdf4 | note | ACTION (Hold, Monitor, Witness) - W
87dbc868-2a38-56f2-82f1-8ca3776424b0 | note | Detail - Material to be stored on site in a dry area
c7b2bf98-6e95-5523-8b32-18bd32d26b8b | note | Frequency / Timing - Pre-construction
4d84e015-5c53-55d8-9e07-5830d02c45c7 | note | Inspection / Test Method submission, visual inspection, testing, measure, - Document Review
254c34ff-4101-5ccc-b6e7-b8a4e7a0a2b6 | note | Conformance Criteria - Material stored in Contech Warehouse until Required on-site, then Stored in Covered Location on-site
15fa77ed-9125-52b2-acec-2ce7ae9c3b4b | note | Records - Photos
aad023f0-c0d0-5407-806d-ff2551916998 | note | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
| section | Construction and Installation
| checkpoint | 10 - Concrete surface preparation
015104cb-c522-56cc-8f9b-1d561ea49682 | note | ACTION (Hold, Monitor, Witness) - H
d8e91dd1-60d7-5747-8ea5-226d06370a3a | note | Detail - Concrete surface preparation with hydroblasting to have an adequate profile roughness.
89a0dc0b-7886-5b6c-b06c-9d8843bf0443 | note | Frequency / Timing - Before start spraying
29c99207-e2eb-55f4-9f06-f4813a49fa06 | note | Inspection / Test Method submission, visual inspection, testing, measure, - Visual inspection
9f1aa82b-4dd8-54aa-aa26-d496b29a0316 | note | Conformance Criteria - The concrete surface must be prepared to have a minimum roughness equivalent to CSP 5 (ICRI)
48dda46a-5951-501b-92b4-9c1a70436259 | note | Records - Photos/Videos/ Record sheet
59b59b41-2460-5763-8197-c93a2eeb1ab5 | note | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
| signoff | HOLD POINT
| checkpoint | 11 - Sewpercoat lining thickness
7fa5162d-c179-5087-b623-c04b3dd0bcc1 | note | ACTION (Hold, Monitor, Witness) - M
7798b180-a354-52a1-93ab-b3808350ff10 | note | Detail - Sewpercoatlining thickness
52fde6d8-349f-52ac-b927-acfddfe13e50 | note | Frequency / Timing - Continuous Monitoring
c25e3632-33f3-587f-90f6-bb6d4e8d5623 | note | Inspection / Test Method submission, visual inspection, testing, measure, - Measurement
bc65bd82-b29c-5ab0-9736-7bb450295566 | note | Conformance Criteria - Thickness tests using caliper depth measuring blade, average thickness of 25 mm, no measurement less than 25 mm, above substrate (concrete surface)
564a9992-28c9-57a5-95ab-e27f5176f83c | note | Records - Photos/Videos/ Record sheet
6d6a937f-6373-5e50-aeb5-c49b12a1004e | note | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
| checkpoint | 13 - Pull-off (adhesion) testing
0c55bae5-c0a2-5799-b7d6-be5d0ee634f0 | note | ACTION (Hold, Monitor, Witness) - M
3d778953-e11e-5283-b6dd-6cba843203c5 | note | Detail - In situ Pull-off tests according to the Standard Test Method for Tensile Strength of Concrete Surfaces and the Bond Strength or Tensile Strength of Concrete Repair and Overlay Materials by Direct Tension (Pull-off Method) -
da7a2de0-e4d7-5a51-a436-532bb9e2b4c6 | note | Frequency / Timing - 2 tests in each structure
7cdec13c-bd87-57f9-b646-77cc222a92d9 | note | Inspection / Test Method submission, visual inspection, testing, measure, - Testing
34f99f54-b028-5062-a9fc-431f8f8bb12e | note | Conformance Criteria - Pull-off test to achieve a minimum of 1 MPa
fb459558-63ea-54a4-9d8c-0893fdb76cbe | note | Records - QA Sheet, photos
462aa658-3120-55a0-8c5b-18de69754835 | note | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
| checkpoint | 14 - Post Sewpercoat lining Survey
22e7fa26-c1ba-5098-9294-9679c42559dd | note | ACTION (Hold, Monitor, Witness) - H
9576ca1c-a0bd-505a-b453-2b1348781fa5 | note | Detail - video survey of the Structure to be undertaken post application of sewpercoat
c8d965c1-f53e-5e55-ab1a-225908c674cf | note | Frequency / Timing - After supepercoat application on each chamber
889eec52-6cc0-516a-af6c-86715511aad9 | note | Inspection / Test Method submission, visual inspection, testing, measure, - Visual inspection
0cdfcaac-ba27-5cea-9b7c-a04f41fffd72 | note | Conformance Criteria - Survey complete
a5becc3a-e808-5379-8439-cc20b24f9ab9 | note | Records - Photos/Videos
8e0e9287-16c8-5e4f-937d-2cdbf942e8a2 | note | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - Contech
| signoff | HOLD POINT
| section | Handover, Commissioning and Completion
| checkpoint | 15 - Close out QA/QC
5e4ba388-d755-52c4-ab9f-94f2c878673c | note | ACTION (Hold, Monitor, Witness) - M
e4032ce9-7663-5cf8-90c2-33390e0ef282 | note | Detail - Ensure all QA/QC is complete are closed out and recorded
34c7b9ed-3c61-5fd4-bd9a-087046d3425a | note | Frequency / Timing - After completion
81ccfc0b-9afa-54c1-b859-eff4a2b7077d | note | Inspection / Test Method submission, visual inspection, testing, measure, - Review
bebfb46f-b04b-5cce-9b40-68047dcff135 | note | Conformance Criteria - QA/QC Documents delivered, ITP Signed and Submitted
2437de44-af99-5e41-a20f-b89ade5a2165 | note | Records - Signed-off ITP, technical reports
611b1c31-098e-5e6b-ac07-c898f6805f1a | note | Responsible Organisation (Main Contractor, Client, Engineers Rep, Subcontractor, Supplier) - United Civil
| checkpoint-no-value | Comments and Non-conformances
a9551dc7-d1d1-504f-97d5-cca4f5435aa7 | textbox | Reference Documentation:
| checkpoint | Acceptance of ITP
0ce6f0f7-a38d-529c-a483-e345961fa6fd | note | Author
203ecdea-f2d1-5be5-a9a6-22cf9d80575c | date | Author - Date:
52eb9e43-3718-52c4-95c7-bd89c538b375 | textbox | Author - Name:
fa14cf6b-0e8e-5d0a-b46f-d53e403a82c2 | note | Project Manager
af84cbed-5176-5019-b1aa-5f1982903d2c | date | Project Manager - Date:
9018316d-8aaf-5387-ac72-bf309828716d | textbox | Project Manager - Name:
c8946d9d-ef74-5c5c-983a-8fd3c389607a | note | Client
5eafb8e0-040e-5193-8628-eecf0a54dcb7 | date | Client - Date:
cb488564-decd-5f8c-84ac-d24b1c4209f8 | textbox | Client - Name:
| signoff | Signature
| checkpoint | Authorised Signature and Initials Register
1fba065f-7cc4-573f-a640-12de3d62560d | textbox | (1) Name:
7979162e-227e-5e75-bbab-a8ffbd304c2b | textbox | (1) Initials:
568f3509-6880-5114-a861-16743b4d5fe3 | textbox | (1) Organisation:
9f31f6af-c237-5d06-b124-667e52369620 | date | (1) Date of Final Sign Off:
2aac7620-0a53-56a3-a9a9-4587180ec957 | textbox | (2) Name:
193bfae4-b473-5815-b808-d335dc39e1b2 | textbox | (2) Initials:
0b5e9bcf-4c1f-595d-81d7-3cff025f81c4 | textbox | (2) Organisation:
98f73bcb-7ff3-5365-9686-deb864d14da0 | date | (2) Date of Final Sign Off:
64b57912-8c06-5ffd-ad58-ed9571b33292 | textbox | (3) Name:
d6167d78-4bf2-5efa-aa6a-10f6ca4a6e3b | textbox | (3) Initials:
8d84e962-077c-50d9-a6f7-c843c5a502f2 | textbox | (3) Organisation:
9c5a50cc-2351-5d49-af62-53227090a1e4 | date | (3) Date of Final Sign Off:
| signoff | Signature