## Table 1
Inspection and Test Plan – Whangare WWTP - Biofilter & Fan Slab Works
Item No. | Quality Activity | Controls |  |  |  | Responsibility |  |  | Remarks
|  | Specification | Records Required | Acceptance Criteria | Timing/Frequency | SBC | UCCL | Consultants
1.1 | Survey - Set Out | Drawings | Survey set out | Engineers approval | Following survey, but prior to works commencing onsite |  | R, S | R, A
1.2 | Timber Poles | Hazard rating | Delivery Dockets | As per specified hazard rating and grade. | Following procurement | R, S | R, S | R
1.3 | Concrete | Drawings | Concrete delivery dockets |  |  | S | R, S | R
1.4 | Concrete Cover - Piling | Drawings | Engineers inspection | Engineers approval | Prior to each pour | H | H | I, A
1.7 | Timber lagging | Drawings | Delivery docket. | As per specified hazard rating and grade. | Following Delivery of Timber | R, S | R, S | R
1.8 | Reinforcing Steel | Project Specifications | Mill Certificates | Grade 500/300 | Following procurement | S | R, S | R, A
1.9 | Concrete Cover - Slabs | Drawings | Engineers inspection | Engineers approval | Prior to each pour | H | H | I, A
Key
H | Hold Point
W | Witness Point
I | Inspection / Test / Monitor
A | Approve / Comment
R | Review Documents
S | Submit Documents
Q | Complete QA document/ Checklist