## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Whangarei Biofilter & Fan Slab Works | itp |  |  |  |  | ITP - Whangarei Biofilter & Fan Slab Works
section | Biofilter & Fan Slab Works
checkpoint | 1.1 - Survey - Set Out
label | Specification - Drawings
label | Records Required - Survey set out
label | Acceptance Criteria - Engineers approval
label | Timing/Frequency - Following survey, but prior to works commencing onsite
label | UCCL - R, S
label | Consultants - R, A
checkpoint | 1.2 - Timber Poles
label | Specification - Hazard rating
label | Records Required - Delivery Dockets
label | Acceptance Criteria - As per specified hazard rating and grade.
label | Timing/Frequency - Following procurement
label | SBC - R, S
label | UCCL - R, S
label | Consultants - R
checkpoint | 1.3 - Concrete
label | Specification - Drawings
label | Records Required - Concrete delivery dockets
label | SBC - S
label | UCCL - R, S
label | Consultants - R
checkpoint | 1.4 - Concrete Cover - Piling
label | Specification - Drawings
label | Records Required - Engineers inspection
label | Acceptance Criteria - Engineers approval
label | Timing/Frequency - Prior to each pour
label | SBC - H
label | UCCL - H
label | Consultants - I, A
holdpoint | HOLD POINT
checkpoint | 1.7 - Timber lagging
label | Specification - Drawings
label | Records Required - Delivery docket.
label | Acceptance Criteria - As per specified hazard rating and grade.
label | Timing/Frequency - Following Delivery of Timber
label | SBC - R, S
label | UCCL - R, S
label | Consultants - R
checkpoint | 1.8 - Reinforcing Steel
label | Specification - Project Specifications
label | Records Required - Mill Certificates
label | Acceptance Criteria - Grade 500/300
label | Timing/Frequency - Following procurement
label | SBC - S
label | UCCL - R, S
label | Consultants - R, A
checkpoint | 1.9 - Concrete Cover - Slabs
label | Specification - Drawings
label | Records Required - Engineers inspection
label | Acceptance Criteria - Engineers approval
label | Timing/Frequency - Prior to each pour
label | SBC - H
label | UCCL - H
label | Consultants - I, A
holdpoint | HOLD POINT