## Sheet1
type | description | value
section | Air Sealing Installed
Checkpoint | Air sealing installed and signd off
section | Cavity Flashings
checkpoint | Cavity battens installed and signed off( sign off when all below has been completed)
bool | Correct material ordered
bool | Arrived onsite and protected
checkpoint | Flashings Critical Lines
text | Number,Location , elevation
checkpoint | Cavity flashings QA issued to Hawkins, reviewed
checklist | Cavity flashings Spot check with Hawkins -Installed/fixed in correct place
holdpoint | Cavity flashings request signoff -Architect /Façade engneer
checklist | Cavity Flashings Archtiect /Façade Engineer Sign oof
bool | Façade engineers remedials done and signed off
bool | Architect remedials completed and signed off
section | Firetherm Rainbar
checkpoint | Firetherm Rainbar installed correctly.QA issued to Hawkins for review
checkpoint | Firetherm Rainbar spot checks carried out with Hawkins
checkpoint | Third party inspection Signoff
checkpoint | Fire Engineer Signoff
section | Hilti in Sto Projections
checkpoint | Hilti in Sto Projections Installed correctly
checkpoint | Hilti installed correctly.QA issued to Hawkins for review
checkpoint | Hilti spot checks carried out with Hawkins
checkpoint | Third party inspection Signoff
checkpoint | Fire Engineer Signoff