## Work Lot Mapping Spreadsheet
n | WORK ACTIVITY | DESIGN PACKAGE NUMBER | c | c2
3 | Piling (Bored Piles) | MRP-DPK-052-00-CBR-0030-0 - Bridge Substructure | MRP-DPK-052-00-CBR-0030-0 - Bridge SubstructurePiling (Bored Piles) | 0
18 | Piling (CFA Piles) | MRP-DPK-052-00-CBR-0030-0 - Bridge Substructure | MRP-DPK-052-00-CBR-0030-0 - Bridge SubstructurePiling (CFA Piles) | 0
21 | Pile Caps (Abutments and Pier) | MRP-DPK-052-00-CBR-0030-0 - Bridge Substructure | MRP-DPK-052-00-CBR-0030-0 - Bridge SubstructurePile Caps (Abutments and Pier) | 0
27 | Walls (Abutments, Blade, deflections) | MRP-DPK-052-00-CBR-0030-0 - Bridge Substructure | MRP-DPK-052-00-CBR-0030-0 - Bridge SubstructureWalls (Abutments, Blade, deflections) | 0
28 | Pier columns | MRP-DPK-052-00-CBR-0030-0 - Bridge Substructure | MRP-DPK-052-00-CBR-0030-0 - Bridge SubstructurePier columns | 0
29 | Pier crossheads installation | MRP-DPK-052-00-CBR-0030-0 - Bridge Substructure | MRP-DPK-052-00-CBR-0030-0 - Bridge SubstructurePier crossheads installation | 0
30 | Material inspections | MRP-DPK-052-00-CBR-0030-0 - Bridge Substructure | MRP-DPK-052-00-CBR-0030-0 - Bridge SubstructureMaterial inspections | 0
31 | Repairs | MRP-DPK-052-00-CBR-0030-0 - Bridge Substructure | MRP-DPK-052-00-CBR-0030-0 - Bridge SubstructureRepairs | 0
33 | OHLE -Foundations (Bored Pile) | MRP-DPK-052-00-CBR-0060-0 - Rail Overhead and Structures | MRP-DPK-052-00-CBR-0060-0 - Rail Overhead and Structures OHLE -Foundations (Bored Pile) | 0
36 | Bearing and Pedestals (Abutments and Pier) | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure Barriers | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure BarriersBearing and Pedestals (Abutments and Pier) | 0
38 | Girders Installation | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure Barriers | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure BarriersGirders Installation | 0
42 | Pre-cast Kerb installation | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure Barriers | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure BarriersPre-cast Kerb installation | 0
44 | Pre-cast Barriers installation | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure Barriers | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure BarriersPre-cast Barriers installation | 0
48 | Deck pour | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure Barriers | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure BarriersDeck pour | 0
51 | Water proofing and expansion joints (Bridge) | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure Barriers | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure BarriersWater proofing and expansion joints (Bridge) | 0
53 | Approach Slabs installation | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure Barriers | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure BarriersApproach Slabs installation | 0
55 | Water proofing and expansion joints (Approach Slabs)) | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure Barriers | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure BarriersWater proofing and expansion joints (Approach Slabs)) | 0
59 | Friction Slabs (Bridge) | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure Barriers | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure BarriersFriction Slabs (Bridge) | 0
60 | Friction Slabs (Fairfiels Street) | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure Barriers | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure BarriersFriction Slabs (Fairfiels Street) | 0
64 | Steel Railing, edge fence and anti throw installation | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure Barriers | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure BarriersSteel Railing, edge fence and anti throw installation | 0
65 | Repairs | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure Barriers | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure BarriersRepairs | 0
66 | Materials inspection (Precast items and Fabricated steel parts) | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure Barriers | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure BarriersMaterials inspection (Precast items and Fabricated steel parts) | 0
68 | Road Drainage | MRP-DPK-052-00-CDR-0012-0 - Road Drainage | MRP-DPK-052-00-CDR-0012-0 - Road DrainageRoad Drainage | 0
77 | Road Drainage - Material Inspections | MRP-DPK-052-00-CDR-0012-0 - Road Drainage | MRP-DPK-052-00-CDR-0012-0 - Road DrainageRoad Drainage - Material Inspections | 0
137 | Road Drainage - Pit Installation | MRP-DPK-052-00-CDR-0012-0 - Road Drainage | MRP-DPK-052-00-CDR-0012-0 - Road DrainageRoad Drainage - Pit Installation | 0
193 | Road Drainage - Pipe Installation | MRP-DPK-052-00-CDR-0012-0 - Road Drainage | MRP-DPK-052-00-CDR-0012-0 - Road DrainageRoad Drainage - Pipe Installation | 0
203 | Road Drainage - Subsoil installation | MRP-DPK-052-00-CDR-0012-0 - Road Drainage | MRP-DPK-052-00-CDR-0012-0 - Road DrainageRoad Drainage - Subsoil installation | 0
223 | Subgrade Preparation | MRP-DPK-052-00-CPT-0013-0 - Road Pavements | MRP-DPK-052-00-CPT-0013-0 - Road PavementsSubgrade Preparation | 0
243 | Capping Layer | MRP-DPK-052-00-CPT-0013-0 - Road Pavements | MRP-DPK-052-00-CPT-0013-0 - Road PavementsCapping Layer | 0
263 | Subbase Layer | MRP-DPK-052-00-CPT-0013-0 - Road Pavements | MRP-DPK-052-00-CPT-0013-0 - Road PavementsSubbase Layer | 0
273 | Basecourse Layer | MRP-DPK-052-00-CPT-0013-0 - Road Pavements | MRP-DPK-052-00-CPT-0013-0 - Road PavementsBasecourse Layer | 0
281 | Asphalt Basecourse | MRP-DPK-052-00-CPT-0013-0 - Road Pavements | MRP-DPK-052-00-CPT-0013-0 - Road PavementsAsphalt Basecourse | 0
289 | Asphalt Intermediate Course | MRP-DPK-052-00-CPT-0013-0 - Road Pavements | MRP-DPK-052-00-CPT-0013-0 - Road PavementsAsphalt Intermediate Course | 0
293 | Asphalt Weraing Course | MRP-DPK-052-00-CPT-0013-0 - Road Pavements | MRP-DPK-052-00-CPT-0013-0 - Road PavementsAsphalt Weraing Course | 0
297 | Guard Rail Installation | MRP-DPK-052-00-CRG-0010-0 - Road Alignment and Barriers | MRP-DPK-052-00-CRG-0010-0 - Road Alignment and BarriersGuard Rail Installation | 0
305 | Kerb Installation | MRP-DPK-052-00-CRG-0010-0 - Road Alignment and Barriers | MRP-DPK-052-00-CRG-0010-0 - Road Alignment and BarriersKerb Installation | 0
308 | Pits and Conduits temporary works (Trench) | MRP-DPK-052-00-CSR-0066-0 - Combined Service Route (Temporary) | MRP-DPK-052-00-CSR-0066-0 - Combined Service Route (Temporary)Pits and Conduits temporary works (Trench) | 0
310 | Pits and Conduits Permanent works (Trench) | MRP-DPK-052-00-CSR-0066-0 - Combined Service Route (Temporary) | MRP-DPK-052-00-CSR-0066-0 - Combined Service Route (Temporary)Pits and Conduits Permanent works (Trench) | 0
311 | Pits and Conduits Permanent works (Bore) | MRP-DPK-052-00-CSR-0066-0 - Combined Service Route (Temporary) | MRP-DPK-052-00-CSR-0066-0 - Combined Service Route (Temporary)Pits and Conduits Permanent works (Bore) | 0
313 | RSS Retaining Wall 1 | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining walls | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining wallsRSS Retaining Wall 1 | 0
318 | RW01 Pre-Cast Panels installation Checklists | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining walls | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining wallsRW01 Pre-Cast Panels installation Checklists | 0
320 | RSS Retaining Wall 2 | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining walls | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining wallsRSS Retaining Wall 2 | 0
329 | RW02 Pre-Cast Panels installation Checklists | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining walls | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining wallsRW02 Pre-Cast Panels installation Checklists | 0
331 | RSS Retaining Wall 3 | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining walls | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining wallsRSS Retaining Wall 3 | 0
339 | RW03 Pre-Cast Panels installation Checklists | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining walls | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining wallsRW03 Pre-Cast Panels installation Checklists | 0
341 | RSS Retaining Wall 4 | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining walls | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining wallsRSS Retaining Wall 4 | 0
347 | RW04 Pre-Cast Panels installation Checklists | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining walls | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining wallsRW04 Pre-Cast Panels installation Checklists | 0
387 | RW1 and RW4 (West) Fill Checklists | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining walls | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining wallsRW1 and RW4 (West) Fill Checklists | 0
442 | RW2 and RW3 (East) Fill Checklists | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining walls | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining wallsRW2 and RW3 (East) Fill Checklists | 0
482 | Material inspections (Pre-cast Panels) | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining walls | MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining wallsMaterial inspections (Pre-cast Panels) | 0
484 | Electrical Rail Crossing Bore | MRP-DPK-052-00-CUT-0063-0 - Electrical Rail Crossing Bore | MRP-DPK-052-00-CUT-0063-0 - Electrical Rail Crossing BoreElectrical Rail Crossing Bore | 0
485 | Water Rail Crossing Bore | MRP-DPK-052-00-CUT-0064-0 - Water Rail Crossing Bore | MRP-DPK-052-00-CUT-0064-0 - Water Rail Crossing BoreWater Rail Crossing Bore | 0
486 | Telstra Rail Crossing Bore | MRP-DPK-052-00-CUT-0065-0 - Telstra Rail Crossing Bore | MRP-DPK-052-00-CUT-0065-0 - Telstra Rail Crossing BoreTelstra Rail Crossing Bore | 0
497 | Ground Preparation | MRP-DPK-052-00-AUD-0071-0 - Landscaping | MRP-DPK-052-00-AUD-0071-0 - LandscapingGround Preparation | 0
507 | Planting | MRP-DPK-052-00-AUD-0071-0 - Landscaping | MRP-DPK-052-00-AUD-0071-0 - LandscapingPlanting | 0
510 | Ground Preparation | MRP-DPK-052-00-AUD-0082-0 - Carpark Landscaping | MRP-DPK-052-00-AUD-0082-0 - Carpark LandscapingGround Preparation | 0
513 | Planting | MRP-DPK-052-00-AUD-0082-0 - Carpark Landscaping | MRP-DPK-052-00-AUD-0082-0 - Carpark LandscapingPlanting | 0
514 | On-Structure Street Lighting | MRP-DPK-052-00-CLT-0020-0 - Permanent Lighting | MRP-DPK-052-00-CLT-0020-0 - Permanent LightingOn-Structure Street Lighting | 0
515 | Off-Structure Street Lighting | MRP-DPK-052-00-CLT-0020-0 - Permanent Lighting | MRP-DPK-052-00-CLT-0020-0 - Permanent LightingOff-Structure Street Lighting | 0
516 | Western Carpark OCS | MRP-DPK-052-00-CLT-0081-0 - Carpark OCS | MRP-DPK-052-00-CLT-0081-0 - Carpark OCSWestern Carpark OCS | 0
517 | Eastern Carpark OCS | MRP-DPK-052-00-CLT-0081-0 - Carpark OCS | MRP-DPK-052-00-CLT-0081-0 - Carpark OCSEastern Carpark OCS | 0
518 | Existing Western Carpark OCS | MRP-DPK-052-00-CLT-0081-0 - Carpark OCS | MRP-DPK-052-00-CLT-0081-0 - Carpark OCSExisting Western Carpark OCS | 0
519 | Western Carpark Street Lighting | MRP-DPK-052-00-CLT-0083-0 - Carpark Lighting | MRP-DPK-052-00-CLT-0083-0 - Carpark LightingWestern Carpark Street Lighting | 0
520 | Eastern Carpark Street Lighting | MRP-DPK-052-00-CLT-0083-0 - Carpark Lighting | MRP-DPK-052-00-CLT-0083-0 - Carpark LightingEastern Carpark Street Lighting | 0
521 | Existing Western Carpark Street Lighting | MRP-DPK-052-00-CLT-0083-0 - Carpark Lighting | MRP-DPK-052-00-CLT-0083-0 - Carpark LightingExisting Western Carpark Street Lighting | 0
524 | Light Pole Installation | MRP-DPK-052-00-CLT-0084-0 - Station Street Lighting and Electrical Relocation | MRP-DPK-052-00-CLT-0084-0 - Station Street Lighting and Electrical RelocationLight Pole Installation | 0
525 | Rail Drainage | MRP-DPK-052-00-CPW-0061-0 - Rail Track and Civil | MRP-DPK-052-00-CPW-0061-0 - Rail Track and CivilRail Drainage | 0
526 | Rail Drainage-Material Inspections | MRP-DPK-052-00-CPW-0061-0 - Rail Track and Civil | MRP-DPK-052-00-CPW-0061-0 - Rail Track and CivilRail Drainage-Material Inspections | 0
533 | Rail Drainage Pit Installation | MRP-DPK-052-00-CPW-0061-0 - Rail Track and Civil | MRP-DPK-052-00-CPW-0061-0 - Rail Track and CivilRail Drainage Pit Installation | 0
539 | Rail Drainage Pipe Installation | MRP-DPK-052-00-CPW-0061-0 - Rail Track and Civil | MRP-DPK-052-00-CPW-0061-0 - Rail Track and CivilRail Drainage Pipe Installation | 0
540 |  | MRP-DPK-052-00-CRG-0080-0 - Carpark Civil | MRP-DPK-052-00-CRG-0080-0 - Carpark Civil | 0
541 |  | MRP-DPK-052-00-CSF-0034-0 - Miscellaneous Structures | MRP-DPK-052-00-CSF-0034-0 - Miscellaneous Structures | 0
542 |  | MRP-DPK-052-00-CSL-0011-0 - Signage and Pavement Marking | MRP-DPK-052-00-CSL-0011-0 - Signage and Pavement Marking | 0
543 |  | MRP-DPK-052-00-CSR-0067-0 - Combined Service Route (Permanent CSR) | MRP-DPK-052-00-CSR-0067-0 - Combined Service Route (Permanent CSR) | 0
544 |  | MRP-DPK-052-00-CSW-0032-0 - Pre-Cast Retaining Walls (non-RSS) | MRP-DPK-052-00-CSW-0032-0 - Pre-Cast Retaining Walls (non-RSS) | 0
547 | Electrical Road Crossing - OC Method | MRP-DPK-052-00-CUT-0021-0 - Electrical Asset Relocation | MRP-DPK-052-00-CUT-0021-0 - Electrical Asset RelocationElectrical Road Crossing - OC Method | 0
548 | Electrical Commissioning | MRP-DPK-052-00-CUT-0021-0 - Electrical Asset Relocation | MRP-DPK-052-00-CUT-0021-0 - Electrical Asset RelocationElectrical Commissioning | 0
551 | Water Road Crossing - OC Method | MRP-DPK-052-00-CUT-0022-0 - Water and Sewer Relocation | MRP-DPK-052-00-CUT-0022-0 - Water and Sewer RelocationWater Road Crossing - OC Method | 0
552 | Water Testing and Commissioning | MRP-DPK-052-00-CUT-0022-0 - Water and Sewer Relocation | MRP-DPK-052-00-CUT-0022-0 - Water and Sewer RelocationWater Testing and Commissioning | 0
554 | Sewer Manhole Decommissioning | MRP-DPK-052-00-CUT-0022-0 - Water and Sewer Relocation | MRP-DPK-052-00-CUT-0022-0 - Water and Sewer RelocationSewer Manhole Decommissioning | 0
557 | Sewer Line Decommissioning | MRP-DPK-052-00-CUT-0022-0 - Water and Sewer Relocation | MRP-DPK-052-00-CUT-0022-0 - Water and Sewer RelocationSewer Line Decommissioning | 0
558 | Telstra Relocation & Commissioning | MRP-DPK-052-00-CUT-0025-0 - Telstra Relocation Design | MRP-DPK-052-00-CUT-0025-0 - Telstra Relocation DesignTelstra Relocation & Commissioning | 0
559 | NBN Relocation & Commissioning | MRP-DPK-052-00-CUT-0026-0 - NBN Relocation Design | MRP-DPK-052-00-CUT-0026-0 - NBN Relocation DesignNBN Relocation & Commissioning | 0
560 | Gas Commissioning | MRP-DPK-052-00-CUT-0027-0 - Gas Relocation Design | MRP-DPK-052-00-CUT-0027-0 - Gas Relocation DesignGas Commissioning | 0
561 |  | MRP-DPK-052-00-ETN-0060-0 - Rail Overhead Wiring and Structure | MRP-DPK-052-00-ETN-0060-0 - Rail Overhead Wiring and Structure | 0
562 |  | MRP-DPK-052-00-GSG-0050-0 - Rail Signalling (Enabling Works) | MRP-DPK-052-00-GSG-0050-0 - Rail Signalling (Enabling Works) | 0
563 |  | MRP-DPK-052-00-GSG-0051-0 - Rail Signalling (Final SAP) | MRP-DPK-052-00-GSG-0051-0 - Rail Signalling (Final SAP) | 0
564 |  | MRP-DPK-052-00-GSG-0051-1 - Rail Signalling (Final Excluding SAP) | MRP-DPK-052-00-GSG-0051-1 - Rail Signalling (Final Excluding SAP) | 0
565 |  | MRP-DPK-052-00-GSG-0052-0 - Testing and Commissioning Plan (Enabling Works) | MRP-DPK-052-00-GSG-0052-0 - Testing and Commissioning Plan (Enabling Works) | 0
566 |  | MRP-DPK-052-00-GSG-0058-0 - Rail Signalling - Stage 2 | MRP-DPK-052-00-GSG-0058-0 - Rail Signalling - Stage 2 | 0

## Sheet1
Tier 1 | Tier 2 | Tier 3
Structures | MRP-DPK-052-00-CBR-0031-0 - Bridge Superstructure and Off Structure Barriers | Bearing and Pedestals (Abutments and Pier)
Girders Installation
Pre-cast Kerb installation
Pre-cast Barriers installation
Deck pour
Water proofing and expansion joints (Bridge)
Approach Slabs installation
Water proofing and expansion joints (Approach Slabs))
Friction Slabs (Bridge)
Friction Slabs (Fairfiels Street)
Steel Railing, edge fence and anti throw installation
Repairs
Materials inspection (Precast items and Fabricated steel parts)
| MRP-DPK-052-00-CSW-0033-0 - Proprietary RSS Retaining walls | RSS Retaining Wall 1
RW01 Pre-Cast Panels installation Checklists
RSS Retaining Wall 2
RW02 Pre-Cast Panels installation Checklists
RSS Retaining Wall 3
RW03 Pre-Cast Panels installation Checklists
RSS Retaining Wall 4
RW04 Pre-Cast Panels installation Checklists
RW1 and RW4 (West) Fill Checklists
RW2 and RW3 (East) Fill Checklists
Material inspections (Pre-cast Panels)
Civil | MRP-DPK-052-00-CRG-0010-0 - Road Alignment and Barriers | Guard Rail Installation
Kerb Installation
| MRP-DPK-052-00-CUT-0064-0 - Water Rail Crossing Bore | Water Rail Crossing Bore
| MRP-DPK-052-00-CUT-0065-0 - Telstra Rail Crossing Bore | Telstra Rail Crossing Bore
| MRP-DPK-052-00-AUD-0071-0 - Landscaping | Ground Preparation
Planting
| MRP-DPK-052-00-AUD-0082-0 - Carpark Landscaping | Ground Preparation
Planting
| MRP-DPK-052-00-CLT-0020-0 - Permanent Lighting | On-Structure Street Lighting
Off-Structure Street Lighting
| MRP-DPK-052-00-CLT-0081-0 - Carpark OCS | Western Carpark OCS
Eastern Carpark OCS
Existing Western Carpark OCS
| MRP-DPK-052-00-CLT-0083-0 - Carpark Lighting | Western Carpark Street Lighting
Eastern Carpark Street Lighting
Existing Western Carpark Street Lighting
| MRP-DPK-052-00-CLT-0084-0 - Station Street Lighting and Electrical Relocation | Light Pole Installation
| MRP-DPK-052-00-CUT-0021-0 - Electrical Asset Relocation | Electrical Road Crossing - OC Method
Electrical Commissioning
| MRP-DPK-052-00-CUT-0022-0 - Water and Sewer Relocation | Water Road Crossing - OC Method
Water Testing and Commissioning
Sewer Manhole Decommissioning
Sewer Line Decommissioning
| MRP-DPK-052-00-CUT-0025-0 - Telstra Relocation Design | Telstra Relocation & Commissioning
| MRP-DPK-052-00-CUT-0026-0 - NBN Relocation Design | NBN Relocation & Commissioning
| MRP-DPK-052-00-CUT-0027-0 - Gas Relocation Design | Gas Commissioning

## WBS
Completions Work Breakdown Structure (WBS)
Camms Rd
METROPOLITIAN ROAD PROGRAM ALLIANCE COMPLETIONS WORK BREAKDOWN STRUCTURE
WBS Area | [22 empty] | WBS Area
Camms Rd (052)
Segments | [22 empty] | Segments
[5 empty] | 1 | Rail | [12 empty] | 2 | Non-Rail
WBS Sub Area | [22 empty] | WBS Sub Area
| 1.1 | Facility | 1.2 | Track |  | 1.3 | Stucture |  | 1.4 | ICT/OCS | 1.5 | Electrical | 1.6 | Signalling |  |  | 2.1 | Bridge Structure | 2.2 | Roads | 2.3 | Area Wide
Component/Elements | [22 empty] | Component/Elements
| 1.1.1 | Corridor - civil elements | 1.2.1 | Formation |  | 1.3.1 | OH |  | 1.4.1 | Operational Control System (OCS) | 1.5.1 | OH Wiring | 1.6.1 | Centralised Train Control System (incl SCC (Signal Control Centre)) |  |  | 2.1.1 | Piling | 2.2.1 | Road civil works | 2.3.1 | Enabling Works
| 1.1.2 | Embankments | 1.2.2 | Trackbed (ballast or slab) |  | 1.3.2 | Eyebrows |  | 1.4.2 | CCTV |  |  | 1.6.2 | Local Train Control System |  |  | 2.1.2 | Retaining Wall/ Ramp/ Deflection wall | 2.2.2 | SUP / Footpath | 2.3.2 | Landscaping
| 1.1.3 | Retaining walls / Ramps | 1.2.3 | Sleepers |  | 1.3.3 | OH Dropper |  | 1.4.3 | CSR |  |  | 1.6.3 | Interlocking |  |  | 2.1.3 | Substructure (Pile caps, Piers, headstock) | 2.2.3 | Landscapng | 2.3.3 | Environment / Sustainability
| 1.1.4 | Carpark Civil Infrastructure - incl carparks, ashphalt, kerb, signs & linemarking | 1.2.4 | Rail |  | 1.3.4 | Lighting & Camera Poles |  | 1.4.4 | FLS |  |  | 1.6.4 | Wayside (conventional) |  |  | 2.1.4 | Superstructure | 2.2.4 | Furniture / Lines / Signs | 2.3.4 | Utilities
| 1.1.5 | Facility Electrical inc switchboard | 1.2.5 | Fixings |  | 1.3.5 | Drainage |  | 1.4.5 | PA System |  |  | 1.6.4.1 |  | Signals |  | 2.1.5 | Abutment | 2.2.5 | Drainage | 2.3.5 | SUP / Footpath
| 1.1.6 | Landscaping | 1.2.6 | Monuments & Signage | [8 empty] | 1.6.4.2 |  | Object Controller |  | 2.1.6 | Miscellaneous Structure | 2.2.6 | Crossovers | 2.3.6 | Furniture / Lines / Signs
| 1.1.7 | Drainage | [10 empty] | 1.6.4.3 |  | Signal Enforcement |  |  |  | 2.2.7 | Civil Works (Pavement etc) | 2.3.7 | Drainage
| 1.1.8 | Fencing | [10 empty] | 1.6.4.3.1 |  |  | TPWS |  |  | 2.2.8 | Stairways | 2.3.8 | Crossovers
| 1.1.9 | Walkways | [10 empty] | 1.6.4.3.2 |  |  | Train Stop |  |  |  |  | 2.3.9 | Civil Works (Pavement etc)
| 1.1.10 | Parkiteer | [10 empty] | 1.6.4.4 |  | Railway Crossings | [5 empty] | 2.3.10 | Other
[13 empty] | 1.6.4.7 |  | Track Vacancy Detection
[13 empty] | 1.6.4.7.1 |  |  | Axle Counter
[13 empty] | 1.6.4.8 |  | Signal Power
[13 empty] | 1.6.4.9 |  | Equipment Housing /Location Boxes
[14 empty] | 1.6.4.10 | Cabling
[14 empty] | 1.6.4.11 | Signage
[14 empty] | 1.6.4.12 | Signal Equipment Room (SER)
[13 empty] | 1.6.5 | CSR