## PROJECT STRUCTURE
Folder Structure |  |  |  | Checklists
FLAT BUSH SCHOOL
EXTERIOR
SITE WORKS
|  |  | UNDERGROUND SERVICES | SITE WORKS - UNDERGROUND SERVICES
BUILDING
|  |  | LIGHTING | BUILDING - EXTERIOR LIGHTING
INTERIOR
CONTAINMENT
|  |  | ROOM GO1 - CIRCULATION | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G02 - FLEXIABLE | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G03 - TEACHERS RESOURCES | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G05 - FLEXIBLE | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G06 - BREAKOUT | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G07 - PROJECT/WET AREA | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G08 - FLEXIBLE | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G09 - BREAKOUT | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G10 - TEACHERS RESOURCES | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G11 - FLEXIBLE | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G12 - DB CUPBOARD | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOMS ( G13,G14,G17,G18,G20) - TOILET | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G16 - COMMS CUPBOARD | CONTAINMENT - CATNERY WIRE INSTALL
|  |  | ROOM G21 - FLEXIABLE | CONTAINMENT - CATNERY WIRE INSTALL
CLASSROOM
|  |  | ENTRANCE | CLASSROOM - ROOM
|  |  | ROOM GO1 - CIRCULATION | CLASSROOM - ROOM
|  |  | ROOM G02 - FLEXIABLE | CLASSROOM - ROOM
|  |  | ROOM G03 - TEACHERS RESOURCES | CLASSROOM - ROOM
|  |  | ROOM G05 - FLEXIBLE | CLASSROOM - ROOM
|  |  | ROOM G06 - BREAKOUT | CLASSROOM - ROOM
|  |  | ROOM G07 - PROJECT/WET AREA | CLASSROOM - ROOM
|  |  | ROOM G08 - FLEXIBLE | CLASSROOM - ROOM
|  |  | ROOM G09 - BREAKOUT | CLASSROOM - ROOM
|  |  | ROOM G10 - TEACHERS RESOURCES | CLASSROOM - ROOM
|  |  | ROOM G11 - FLEXIBLE | CLASSROOM - ROOM
|  |  | ROOM G12 - DB CUPBOARD | CLASSROOM - ROOM
|  |  | ROOMS ( G13,G14,G17,G18,G20) - TOILET | CLASSROOM - ROOM
|  |  | ROOM G16 - COMMS CUPBOARD | CLASSROOM - ROOM
|  |  | ROOM G21 - FLEXIABLE | CLASSROOM - ROOM
BONDING
|  |  | STRUCTURAL BONDING | BUILDING STRUCTURAL BONDING
DISTRIBUTION
|  |  | MAIN SWITCHBOARD | DISTRIBUTION - MAIN SWITCHBOARD
|  |  | DISTRIBUTION BOARD | DISTRIBUTION BOARD DB-A
COMMISSIONING
|  |  | COMMISSIONING - MAIN SWITCHBOARD | COMMISSIONING - DISTRIBUTION - MAIN SWITCHBOARD
|  |  | COMMISSIONIG - DISTRIBUTION BOARD | COMMISSIONING - DISTRIBUTION BOARD DB-A

## CHECKPOINTS
TYPE | NAME
CHECKLIST | SITE WORKS - UNDERGROUND SERVICES
CHECKPOINT | POWER DUCTING INSTALLED INCL MAG SLAB AND DANGER TAPE
CHECKPOINT | COMMS DUCTING INSTALLED INCL DANGER TAPE
CHECKPOINT | UNDERGROUND PITS INSTALLED, LEVELLED AND DUCTING SEALED
CHECKPOINT | DRAW TAPE INSTALLED AS REQUIRED
CHEECK POINT | CORRECT QUANTITIES OF PIT INSTALLED AS[ PER UPDATED ELECTRICAL DRAWINGS
CHEECK POINT | CORRECT QUANTITIES OF DUCTING INSTALLED AS PER UPDATED ELECTRICAL DRAWINGS
CHECKPOINT | CORRECT DUCTING SIZE INSTALLED INTO BOXING FOR MSB PLINTH FOR MAINS CABLE
CHECKPOINT | CORRECT DUCTING SIZE INSTALLED INTO BOXING FOR MSB PLINTH FOR MAIN EARTHING
CHECKPOINT | CORRECT DUCTING SIZE FOR RELOCATED SUBMAINS INSTALLED INTO BOXING FOR MSB PLINTH
CHECKLIST | BUILDING - EXTERIOR LIGHTING
CHECKPOINT | DAYLIGHT SENSOR CABLED TO SUITABLE LOCATION
CHECKPOINT | EXTERIOR CLASSROOM WALL LIGHTING PREWIRED
CHECKPOINT | CABLE SEAL APPLIED PRE CLADDING
CHECKPOINT | EXTERIOR CLASSROOM WALL LIGHTING INSTALLED AND CONNECTED
CHECKPOINT | LIGHT FITTINGS CLEANED AND SEALED AGAINST WATER INGRESS
CHECKLIST | CONTAINMENT - CATENERY WIRE INSTALL
CHECKPOINT | WOOD EYE ANCHORS INSTALLED AND CORRECTLY FIXED ONTO TIMBER WALLS
CHECKPOINT | SUFFICIENT CATENERY WIRE SUPPORTS INSTALLED AT APPROX 1.2M INTERVALS
CHECKPOINT | CATENRY WIRES INSTALLED AT HIGH LEVEL AND MEETS CLEARENCE FROM OTHER SERVICES
CHECKPOINT | TURNBUCKLES IS TIGHTENED AND CATENERY WIRE IS WELL SECURED
CHECHLIST | BUILDING STRUCTURAL BONDING
CHECKPOINTS | STRUCTURAL BONDING CABLE 1/3 SIZE OF DB-A SUB MAINS CABLE
CHECKPOINTS | CORRECT SIZE EARTH CABLE INSTALLED
CHECKPOINTS | CORRECT SIZE EARTH CABLE LUGGED AND BOLTED ONTO STRUCTURE
CHECKLIST | DISTRIBUTION BOARD - MAIN SWITCHBOARD
CHECKPOINT | NEW UPGRADED MAINS INSTALLED AND TERMINATED.
CHECKPOINT | NEW MAIN EARTHING INSTALLED
CHECKPOINT | MEN LINK INSTALLED AND CONFIMRED
CHECKPOINT | SUFFICINET EARTH STAKE INSTALLED AND MAIN EARTH GROUND READING IS GOOD
CHECKPOINT | MAIN EARTH INSPECTION PIT INSTALLED
CHECKPOINT | STRUCTURAL BONDING CABLE TERMINATED AT SWITCHBOARD.
CHECKPOINT | DB SCHEDULE COMPLETED
CHECKPOINT | DISTRIBUTION BOARD TEST SHEET COMPLETED
CHECKPOINT | DB SCHEDULE INSTALLED
CHECKPOINT | CLEAN OF ALL DEBRI AND MARKS
CHECKLIST | DISTRIBUTION BOARD - DB-A
CHECKPOINT | CABLE TRAY INSTALLED BELOW DB-A
CHECKPOINT | SUBMAINS CABLE CABLE TIED ONTO CABLE TRAY
CHECKPOINT | DISTRIBUTION BOARD INSTALLATION COMPLETED AND SECURELY MOUNTED
CHECKPOINT | SUBMAINS TERMINATED
CHECKPOINT | SUBCIRCUITS TERMINATED INCLUDING LABELLING/FERRULES TO ALL CORES
CHECKPOINT | EARTHING/BONDING TERMINATED
CHECKPOINT | STRUCTURAL BONDING CABLE TERMINATED AT SWITCHBOARD.
CHECKPOINT | DB SCHEDULE COMPLETED
CHECKPOINT | DISTRIBUTION BOARD TEST SHEET COMPLETED
CHECKPOINT | DB SCHEDULE INSTALLED
CHECKPOINT | CLEAN OF ALL DEBRI AND MARKS
CHECKLIST | CLASSROOM - ROOM
CHECKPOINT | SETOUT + FLUSHBOXES INSTALLED/COMPLETE
CHECKPOINT | LIGHTING PREWIRED
CHECKPOINT | LIGHTING INSTALLED AND CONNECTED
CHECKPOINT | LIGHTING CONTROLS PREWIRED AND COMPLETE
CHECKPOINT | EMERGENCY LIGHTING PREWIRED
CHECKPOINT | EMERGENCY LIGHTING INSTALLED AND COMPLETE
CHECKPOINT | EXIT LIGHTING PREWIRED
CHECKPOINT | EXIT LIGHT INSTALLED AND COMPLETE
CHECKPOINT | POWER CABLING INSTALLED
CHECKPOINT | POWER OUTLETS INSTALLED AND COMPLETE
CHECKPOINT | SUBCIRCUITS PREWIRED AND TIED ONTO CATENRERY WIRES BACK TO DB
CHECKPOINT | CONDUIT INSTALLED WHERE REQUIRED
CHECKLIST | COMMISSIONING - DISTRIBUTION - MAIN SWITCHBOARD
CHECKPOINT | MAIN SWITCHBOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | DB SCHEDULE COMPLETED, INSTALLED AND ADDED TO DROPBOX
CHECKPOINT | MAIN DISTRIBUTION BOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | DB SCHEDULE COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | MAIN SWITCHBOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | MAIN SWITHCBOARD DISTRIBUTION BOARD CHECK SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | MAIN EARTHING TEST SHEET COMPLETED
CHECKPOINT | MAIN EARTH PITS INSTALLED
CHECKPOINT | MEN LINK INSTALLATION CONFIRMED
CHECKPOINT | BOARD FREE FROM DEBRI, NO MARKS, ALL ACCESSORIES INSTALLED
CHECKPOINT | LABELLING COMPLETED ON ALL FIELD OUTLETS, SWITCHES AND ISOLATORS ETC
CHECKLIST | COMMISSIONING - SWITCHBOARD DB-A
CHECKPOINT | SWITCHBOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | DB SCHEDULE COMPLETED, INSTALLED INTO DB AND ADDED TO DROPBOX
CHECKPOINT | DISTRIBUTION BOARD TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | SUBCIRCUIT COMMISSIONING RESULTS SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | DISTRIBUTION BOARD CHECK SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | EARTHING TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | EMERGENCY LIGHTING TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | TIMECLOCK TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | BOARD FREE FROM DEBRI, NO MARKS, ALL ACCESSORIES INSTALLED
CHECKPOINT | LABELLING COMPLETED ON ALL FIELD OUTLETS, SWITCHES AND ISOLATORS ETC
CHECKPOINT | EMERGENCY LIGHTING TEST SHEET COMPLETED AND ADDED TO DROPBOX
CHECKPOINT | SUBCIRCUIT COMMISSIONING RESULTS SHEET COMPLETED AND ADDED TO DROPBOX