## Table 1
Client: | [11 empty] | Project No:
Site Address: | [11 empty] | Date Issued:
ITP ITEM No. | INSPECTION / CONSTRUCTION ACTIVITY |  | INSPECTION / TEST / METHOD / STANDARD / SPECIFICATION |  |  | STAGE OR FREQUENCY OF SAMPLING |  |  | ACCEPTANCE CRITERIA |  |  | RECORD OF CONFORMITY |  |  | TYPE |  | RESPONSIBILITY |  | CHECKED / VERIFIED BY (INITIAL & DATE)
[19 empty] | GC CIVIL | TfNSW | OTHER
PRELIMINARIES & PRE-START
1 | Submit copy of Executed Contract |  | Desktop review As per Conditions of Contract, & Tender |  |  | Per contract |  |  | Return of copy of Executed Contract |  |  | Document - Contract |  |  | IP |  | GC Project Manager
2 | Provision of Security |  | Desktop review 2% and 4% of Contract as per Conditions of Contract |  |  | Per contract |  |  | Cash, bank cheque or unconditional undertaking (bank guarantee) |  |  | Document – Bank G’tee |  |  | IP |  | GC Project Manager
3 | Proof of Worker’s Compensation Policy |  | Desktop review As per Conditions of Contract |  |  | Prior to commencing works on site |  |  | Copy of Certificate of Currency from Workers Compensation Provider |  |  | Document – Cert. of Currency |  |  | IP |  | GC Project Manager
4 | Proof of Motor Vehicle & Mobile, Plant Insurance Policy |  | Desktop review As per Conditions of Contract |  |  | Prior to commencing works on site |  |  | Copy of Certificate of Currency from Insurer |  |  | Document – Cert. of Currency |  |  | IP |  | GC Project Manager
5 | Quality Management – Inspection & Test Plan |  | Desktop review |  |  | Staged Submission 14 days prior to commencement of staged works |  |  | Submission and approval of controlled copy of Inspection & Test Plan |  |  | Document – ITP |  |  | IP |  | GC Project Manager
6 | WHS Documentation |  | Desktop review |  |  | 10 days prior to commencement of work at the Site |  |  | Submit WHS Plan / Safe Work Method Statements and documentation |  |  | Document – WHS Plan and SWMS |  |  | HP |  | GC Project Manager
7 | Environmental Documentation |  | Desktop review |  |  | 10 days prior to commencement of work at the Site |  |  | Submit Environmental Plan and documentation |  |  | Document – Environmental Plan |  |  | HP |  | GC Project Manager
8 | Traffic Control Plan |  | Desktop review TFNSW TCAWSM |  |  | 3 days prior to commencement of work at the Site |  |  | Submit TCP, and any ROL, SZA obtained |  |  | Document – TCP, ROL, SZA |  |  | HP |  | GC Project Manager
9 | Fisheries Permit |  | Desktop review |  |  | 10 days prior to commencement of work at the Site |  |  | Apply and obtain Fisheries Permit |  |  | Document – Fisheries Permit |  |  | HP |  | GC Project Manager
10 | Public Notification |  | Desktop review Site inspection |  |  | 10 days prior to commencement of work at the Site |  |  | Distribute written notification to businesses and residents affected by the proposed works Establish VMS signs |  |  | Document – notification |  |  | IP |  | Client Project Rep
DESIGN
Document No. and Title: |  |  | GCITP013 Construction of Bridge |  |  | Revision: | [13 empty] | 1
Authorised By: |  |  | Craig Simpson |  |  | Date: | [13 empty] | 2022-02-24
Client: | [11 empty] | Project No:
Site Address: | [11 empty] | Date Issued:
ITP ITEM No. | INSPECTION / CONSTRUCTION ACTIVITY |  | INSPECTION / TEST / METHOD / STANDARD / SPECIFICATION |  |  | STAGE OR FREQUENCY OF SAMPLING |  |  | ACCEPTANCE CRITERIA |  |  | RECORD OF CONFORMITY |  |  | TYPE |  | RESPONSIBILITY |  | CHECKED / VERIFIED BY (INITIAL & DATE)
[19 empty] | GC CIVIL | TfNSW | OTHER
11 | Global Bridge design & approach roads |  | Desktop review AS5100 Client review required |  |  | Before commencing fabrication or manufacture |  |  | Drawings and certification of design |  |  | Drawings Document – Engineer certification |  |  | HP |  | Fairlight Engineers
12 | Design of Inquik bridge superstructure |  | Desktop review AS5100 Client review required |  |  | Before commencing fabrication or manufacture |  |  | Drawings and certification of design |  |  | Drawings Document – Engineer certification |  |  | HP |  | Inquik
MATERIALS PROCUREMENT
13 | Production of Concrete |  | Desktop review |  |  | Before initial production of each strength grade of concrete for the project |  |  | Submission of Concrete mix design AS 1379 The specification and manufacture of concrete AS 1012 Methods of testing concrete |  |  | Document – Concrete mix design |  |  | IP |  | Concrete Supplier GC Project Manager
14 | Reo cage manufacture |  | Shop Drawings Structural Drawings |  |  | Prior to transport to site |  |  | Provide Reinforcement Schedule and Certificate of Conformity |  |  | Document – Reinforcement Schedule and Certificate of Conformity |  |  | IP |  | Reo supplier GC Project Manager
15 | Inquik Bridge units |  | Structural Drawings Inquik shop drawings AS5100 |  |  | Prior to transport to site |  |  | All bridge units / components to be inspected by Engineer |  |  | Document – Engineer Inspection report |  |  | HP |  | Inquik GC Project Manager
SITE ESTABLISHMENT & START-UP
16 | Service & Utilities Search |  | Site inspection DBYD services plans |  |  | Each worksite prior to commencing any groundwork’s, |  |  | Dial Before You Dig search on underground services drawings |  |  | DBYD |  |  | IP |  | GC Project Manager
Document No. and Title: |  |  | GCITP013 Construction of Bridge |  |  | Revision: | [13 empty] | 1
Authorised By: |  |  | Craig Simpson |  |  | Date: | [13 empty] | 2022-02-24
Client: | [11 empty] | Project No:
Site Address: | [11 empty] | Date Issued:
ITP ITEM No. | INSPECTION / CONSTRUCTION ACTIVITY |  | INSPECTION / TEST / METHOD / STANDARD / SPECIFICATION |  |  | STAGE OR FREQUENCY OF SAMPLING |  |  | ACCEPTANCE CRITERIA |  |  | RECORD OF CONFORMITY |  |  | TYPE |  | RESPONSIBILITY |  | CHECKED / VERIFIED BY (INITIAL & DATE)
[19 empty] | GC CIVIL | TfNSW | OTHER
[6 empty] | excavation or drilling of test pit / holes All personnel involved in excavation works must be signed onto SWMS prior to commencing groundworks. DBYD information is to be renewed every 6 months |  |  | Locate all underground and overhead utilities or services that are present near the proposed works
17 | Set-up of Site Compound |  | Desktop review |  |  | Prior to On-site establishment of Contractor’s compound. |  |  | Submit documented location, size and relevant approvals for Contractor’s compound. |  |  | Document – layout plan |  |  | IP |  | GC Project Manager
18 | Induction Training |  | Desktop review |  |  | Commencement of initial construction work |  |  | Attend pre-construction meeting Verification that the site personnel have been inducted |  |  | Document – Meeting minutes and induction records |  |  | IP |  | GC Project Manager
19 | Dilapidation Records |  | Photographic record |  |  | Prior to Commencement of construction activities. |  |  | Take photographs prior to commencement of construction activities to record the conditions of all existing structures, areas, adjoining properties, etc. Liaise with the owners before commencing construction |  |  | Document – Dilapidation Records / photos |  |  | IP |  | GC Project Manager
20 | Erosion Controls |  | Environmental Management Plan (EMP) Site Inspection |  |  | Before commencing any excavation work on site |  |  | Installation of erosion and silt controls as per EMP |  |  | Document - photos |  |  | IP |  | GC Project Manager
EXCAVATION - PILING
21 | Set-out Survey |  | Drawings, survey, field set-out |  |  | Each Lot, prior to commencement of pier drilling/excavation |  |  | Location, level and offset reference points Use adequate recovery pegs and survey markers to accurately set up location and alignment for each wall and pile. |  |  | Survey Records, Verification Checklist |  |  | IP |  | GC Project Manager Surveyor
Document No. and Title: |  |  | GCITP013 Construction of Bridge |  |  | Revision: | [13 empty] | 1
Authorised By: |  |  | Craig Simpson |  |  | Date: | [13 empty] | 2022-02-24
Client: | [11 empty] | Project No:
Site Address: | [11 empty] | Date Issued:
ITP ITEM No. | INSPECTION / CONSTRUCTION ACTIVITY |  | INSPECTION / TEST / METHOD / STANDARD / SPECIFICATION |  |  | STAGE OR FREQUENCY OF SAMPLING |  |  | ACCEPTANCE CRITERIA |  |  | RECORD OF CONFORMITY |  |  | TYPE |  | RESPONSIBILITY |  | CHECKED / VERIFIED BY (INITIAL & DATE)
[19 empty] | GC CIVIL | TfNSW | OTHER
Centre of pile positions to be pegged at least one day prior to drilling rig being set up. Datum levels for top / bottom of pile to be provided. At least two (2) working days’ notice of the date the set-out will be completed.
22 | Excavation/Pile Drilling |  | Structural Drawings |  |  | Per lot / pile |  |  | Notify Engineer that pile excavation is complete & pile hole/s inspection required prior to reinforcement placement. Check that the plan position, size and alignment is within tolerance Dimensions and depth as per drawings, base clean All loose material removed from the pile hole. Provide Engineers Certificate for inspection and adequacy of load bearing capacity Pile must bear on granite bedrock ~2000KN |  |  | Verification Checklist |  |  | HP |  | Design Engineer GC Project Manager
FOOTING CONSTRUCTION
23 | Concrete Placement |  | Structural drawings |  |  | Prior to first Concrete pour & placement on this project |  |  | Develop a concrete placement Method Statement detailing:  Delivery rate  Placement method and rate  Equipment Bridgeworks concreting operations shall be supervised by a person holding a TfNSW Bridgeworks Concreting Grey Card. |  |  | Verification Checklist |  |  | IP |  | GC Project Manager
24 | Pre-Pour planning activities |  | Weather forecast |  |  | Each concrete pour |  |  | Ensure the following are in place: Weather forecast considered NATA lab tester arranged |  |  | Verification Checklist |  |  | IP |  | GC Project Manager
Document No. and Title: |  |  | GCITP013 Construction of Bridge |  |  | Revision: | [13 empty] | 1
Authorised By: |  |  | Craig Simpson |  |  | Date: | [13 empty] | 2022-02-24
Client: | [11 empty] | Project No:
Site Address: | [11 empty] | Date Issued:
ITP ITEM No. | INSPECTION / CONSTRUCTION ACTIVITY |  | INSPECTION / TEST / METHOD / STANDARD / SPECIFICATION |  |  | STAGE OR FREQUENCY OF SAMPLING |  |  | ACCEPTANCE CRITERIA |  |  | RECORD OF CONFORMITY |  |  | TYPE |  | RESPONSIBILITY |  | CHECKED / VERIFIED BY (INITIAL & DATE)
[19 empty] | GC CIVIL | TfNSW | OTHER
Concrete pump arranged (where required) Concrete type & volume established & coordinated with the supplier
25 | Pre-Pour Check |  | Visual Structural Drawings |  |  | Every lot before placement of concrete to pier |  |  | Level, alignment, clearance and member designation as per Drawings Do not place concrete during rain Check delivery dockets to identify correct mix is being used, time quantity & slump recorded. |  |  | Verification Checklist |  |  | IP |  | GC Project Manager
26 | Inspect the progress of concrete pour; placement of Concrete to footing |  | Structural Drawings Inspect delivery and compaction |  |  | Every delivery |  |  | Check addition of water to a batch Temperature at point of delivery to be 5C min 35C max. Placement of concrete – not in water, one continuous operation Maintain placement records |  |  | Verification Checklist |  |  | IP |  | GC Project Manager
27 | Test Concrete for Slump & Strength |  | Structural Drawings AS 1379 AS 1012.3.1 AS 1012.9 |  |  | Slump: Each batch Comp: 1pair/25 m³ |  |  | Check frequency of field testing & sampling correct. Check and record the slump of the concrete within 45 minutes of batch time Slump within ±20mm for 100mm slump (or ±40mm if using a tremie mix with nominated slump ≥ 220mm). Compressive Strength @ 28 days one pair of cylinders per 25m3 or part thereof |  |  | Document - Tester Field Sheet |  |  | TP |  | GC Project Manager
28 | Obtain and check concrete test results |  | Structural Drawings AS 1379 AS 1012.3.1 AS 1012.9 |  |  | Per lot |  |  | NATA test certificates received, reviewed and confirm the conform to minimum strength requirements |  |  | Document – Test Report |  |  | IP |  | GC Project Manager
DEMOLITION & SCOUR PROTECTION
29 | Demolition of existing bridge superstructure |  | Desktop review Structural Drawings |  |  | Before demolition commences |  |  | Plan demolition activities Consider WHS hazards and risks |  |  | Risk Assessment & SWMS |  |  | IP |  | GC Project Manager
Document No. and Title: |  |  | GCITP013 Construction of Bridge |  |  | Revision: | [13 empty] | 1
Authorised By: |  |  | Craig Simpson |  |  | Date: | [13 empty] | 2022-02-24
Client: | [11 empty] | Project No:
Site Address: | [11 empty] | Date Issued:
ITP ITEM No. | INSPECTION / CONSTRUCTION ACTIVITY |  | INSPECTION / TEST / METHOD / STANDARD / SPECIFICATION |  |  | STAGE OR FREQUENCY OF SAMPLING |  |  | ACCEPTANCE CRITERIA |  |  | RECORD OF CONFORMITY |  |  | TYPE |  | RESPONSIBILITY |  | CHECKED / VERIFIED BY (INITIAL & DATE)
[19 empty] | GC CIVIL | TfNSW | OTHER
Existing piles and abutments to remain.
30 | Scour protection |  | Visual Structural Drawings |  |  | Each lot |  |  | Shape earth filled batters to 2H to 1V Place A39 geotextile Place rock sized ~250-500mm sized, fill voids with smaller rocks |  |  | Verification Checklist |  |  | IP |  | GC Project Manager
INQUIK BRIDGE UNIT INSTALLATION
31 | Delivery of Inquik bridge units |  | Visual Structural Drawings |  |  | Each delivery |  |  | Check for qty Check for length / size Check for any damage |  |  | Delivery Docket |  |  | IP |  | GC Project Manager
32 | Craneage of Inquik bridge units |  | Desktop review |  |  | Before any lifting operations |  |  | Undertake a lift study to plan the lifting of each unit |  |  | Document – Lift Study |  |  | IP |  | Craneage subcontractor GC Project Manager
33 | Installation of Inquik bridge units |  | Visual Structural Drawings Inquik drawings |  |  | Every unit |  |  | Check member, length, R.L Level, alignment, vertically, spacing, clearance and member designation as per Drawings. Install tie bars as per Inquik drawings |  |  | Verification Checklist |  |  | IP |  | GC Project Manager
34 | Install deck panels |  | Inquik design manual & Drawings |  |  | Prior to installing deck panels |  |  | InQuik Bridge Panels can be placed on the abutments and cast when the abutment concrete compressive strength reaches a minimum of 25MPa. |  |  | Document – Test Report |  |  | IP |  | GC Project Manager
35 | Construction traffic using new bridge |  | Inquik design manual & Drawings |  |  | Prior to construction traffic using the bridge deck |  |  | As per SMEC certificate, traffic can be allowed on the bridge when the superstructure concrete compressive strength reaches a minimum of 30MPa where the traffic volume is less than 150 vehicles per day |  |  | Document – Test Report |  |  | HP |  | GC Project Manager
CONCRETING OF INQUIK ABUTMENTS, BRIDGE DECK, APPROACH SLABS
Document No. and Title: |  |  | GCITP013 Construction of Bridge |  |  | Revision: | [13 empty] | 1
Authorised By: |  |  | Craig Simpson |  |  | Date: | [13 empty] | 2022-02-24
Client: | [11 empty] | Project No:
Site Address: | [11 empty] | Date Issued:
ITP ITEM No. | INSPECTION / CONSTRUCTION ACTIVITY |  | INSPECTION / TEST / METHOD / STANDARD / SPECIFICATION |  |  | STAGE OR FREQUENCY OF SAMPLING |  |  | ACCEPTANCE CRITERIA |  |  | RECORD OF CONFORMITY |  |  | TYPE |  | RESPONSIBILITY |  | CHECKED / VERIFIED BY (INITIAL & DATE)
[19 empty] | GC CIVIL | TfNSW | OTHER
36 | First pour – abutments |  | Inquik design manual & Drawings |  |  | During first pour and prior to second pour |  |  |  Abutments to be filled in 400mm increments to nominal 1.6m high, and concrete is to be allowed to cure to 25mpa prior to installing the deck panels.  50mpa concrete to be used |  |  | Verification Checklist |  |  | WP |  | GC Project Manager
37 | Second pour – abutments & bottom of deck beams |  | Inquik design manual & Drawings |  |  | During second pour and prior to third pour |  |  |  Fill abutments a further nominal 0.5m high  Fill both centre deck beams from centre out  Fill both outer deck beams from the centre out  Concrete is to be allowed to cure to 25mpa prior to pouring deck.  50mpa concrete to be used |  |  | Verification Checklist |  |  | WP |  | GC Project Manager
38 | Third pour – Bridge Deck |  | Inquik design manual & Drawings |  |  | During third pour and prior to traffic |  |  |  Once the deck beams have cured then fill abutments and deck slab to top of side form.  50mpa concrete to be used  Broom finish |  |  | Verification Checklist |  |  | WP |  | GC Project Manager
39 | Concrete Placement |  | Structural drawings |  |  | Prior to first Concrete pour & placement on this project |  |  | Develop a concrete placement Method Statement detailing:  Delivery rate  Placement method and rate  Equipment Bridgeworks concreting operations shall be supervised by a person holding a TfNSW Bridgeworks Concreting Grey Card. |  |  | Verification Checklist |  |  | IP |  | GC Project Manager
40 | Pre-Pour planning activities |  | Weather forecast |  |  | Each concrete pour |  |  | Ensure the following are in place: Weather forecast considered NATA lab tester arranged Concrete pump arranged (where required) Concrete type & volume established & coordinated with the supplier |  |  | Verification Checklist |  |  | IP |  | GC Project Manager
Document No. and Title: |  |  | GCITP013 Construction of Bridge |  |  | Revision: | [13 empty] | 1
Authorised By: |  |  | Craig Simpson |  |  | Date: | [13 empty] | 2022-02-24
Client: | [11 empty] | Project No:
Site Address: | [11 empty] | Date Issued:
ITP ITEM No. | INSPECTION / CONSTRUCTION ACTIVITY |  | INSPECTION / TEST / METHOD / STANDARD / SPECIFICATION |  |  | STAGE OR FREQUENCY OF SAMPLING |  |  | ACCEPTANCE CRITERIA |  |  | RECORD OF CONFORMITY |  |  | TYPE |  | RESPONSIBILITY |  | CHECKED / VERIFIED BY (INITIAL & DATE)
[19 empty] | GC CIVIL | TfNSW | OTHER
41 | Pre-Pour Check |  | Visual Structural Drawings |  |  | Every lot before placement of concrete to pier |  |  | Level, alignment, clearance and member designation as per Drawings Do not place concrete during rain Check delivery dockets to identify correct mix is being used, time quantity & slump recorded. |  |  | Verification Checklist |  |  | IP |  | GC Project Manager
42 | Inspect the progress of concrete pour; placement of Concrete to footing |  | Structural Drawings Inspect delivery and compaction |  |  | Every delivery |  |  | Check addition of water to a batch Temperature at point of delivery to be 5C min 35C max. Placement of concrete – not in water, one continuous operation Maintain placement records |  |  | Verification Checklist |  |  | IP |  | GC Project Manager
43 | Test Concrete for Slump & Strength |  | Structural Drawings AS 1379 AS 1012.3.1 AS 1012.9 |  |  | Slump: Each batch Comp: 1pair/25 m³ |  |  | Check frequency of field testing & sampling correct. Check and record the slump of the concrete within 45 minutes of batch time Slump within ±20mm for 100mm slump (or ±40mm if using a tremie mix with nominated slump ≥ 220mm). Compressive Strength @ 28 days one pair of cylinders per 25m3 or part thereof |  |  | Document - Tester Field Sheet |  |  | TP |  | GC Project Manager
44 | Obtain and check concrete test results |  | Structural Drawings AS 1379 AS 1012.3.1 AS 1012.9 |  |  | Per lot |  |  | NATA test certificates received, reviewed and confirm the conform to minimum strength requirements |  |  | Document – Test Report |  |  | IP |  | GC Project Manager
ROADWORKS
45 | Backfill abutments |  | Structural drawings |  |  | Each lot |  |  |  18mm Coredrain sheet at back of abutment wall  100mm socked ag-line at base of each abutment, draining to site sump. |  |  | Verification Checklist |  |  | IP |  | GC Project Manager
46 | Subgrade |  | Structural drawings |  |  | Each lot |  |  |  Use site won or imported material with min 3% CBR  compacted to 95% modified |  |  | Delivery dockets |  |  | IP |  | GC Project Manager
Document No. and Title: |  |  | GCITP013 Construction of Bridge |  |  | Revision: | [13 empty] | 1
Authorised By: |  |  | Craig Simpson |  |  | Date: | [13 empty] | 2022-02-24
Client: | [11 empty] | Project No:
Site Address: | [11 empty] | Date Issued:
ITP ITEM No. | INSPECTION / CONSTRUCTION ACTIVITY |  | INSPECTION / TEST / METHOD / STANDARD / SPECIFICATION |  |  | STAGE OR FREQUENCY OF SAMPLING |  |  | ACCEPTANCE CRITERIA |  |  | RECORD OF CONFORMITY |  |  | TYPE |  | RESPONSIBILITY |  | CHECKED / VERIFIED BY (INITIAL & DATE)
[19 empty] | GC CIVIL | TfNSW | OTHER
Verification Checklist Compaction records
47 | Subbase |  | Structural drawings |  |  | Each lot |  |  |  275mm thick  DGS40  Min 30% CBR  compacted to 98% modified |  |  | Delivery dockets Verification Checklist Compaction records |  |  | IP |  | GC Project Manager
48 | Basecourse |  | Structural drawings |  |  | Each lot |  |  |  100mm thick  DGB20  Min 80% CBR  compacted to 98% modified |  |  | Delivery dockets Verification Checklist Compaction records |  |  | IP |  | GC Project Manager
49 | Table drains |  | Structural drawings |  |  | Each lot |  |  |  Drain towards creek  2m batter 1 in 4 from road  1 in 2 batter up to existing surface |  |  | Verification Checklist |  |  | IP |  | GC Project Manager
50 | Approach slabs |  | Structural drawings |  |  | Each lot |  |  |  28 dia. Stainless steel dowel bars G250Mpa @ 250mm centres, Chemset 501 250mm embedment into deck panel  2 x N24 bars site welded across tops of all dowels  Pour hard against Inquik deck panel, and seal joint  300mm thick approach slab |  |  | Verification Checklist |  |  | IP |  | GC Project Manager
51 | Spray Seal |  | Structural drawings |  |  | Each lot |  |  |  Two coat flush seal  14mm / 7mm |  |  | Delivery dockets Verification Checklist |  |  | IP |  | GC Project Manager
52 | Guardrail |  | Structural drawings Safe Direction shop drawing |  |  | Each lot |  |  |  Thrie Beam barriers on bridge  Transition to W-beam Bridge approach guardrails  Fleat TL6 terminals |  |  | Delivery dockets Verification Checklist Compaction records |  |  | IP |  | Guardrail installer GC Project Manager
Document No. and Title: |  |  | GCITP013 Construction of Bridge |  |  | Revision: | [13 empty] | 1
Authorised By: |  |  | Craig Simpson |  |  | Date: | [13 empty] | 2022-02-24
Client: | [11 empty] | Project No:
Site Address: | [11 empty] | Date Issued:
ITP ITEM No. | INSPECTION / CONSTRUCTION ACTIVITY |  | INSPECTION / TEST / METHOD / STANDARD / SPECIFICATION |  |  | STAGE OR FREQUENCY OF SAMPLING |  |  | ACCEPTANCE CRITERIA |  |  | RECORD OF CONFORMITY |  |  | TYPE |  | RESPONSIBILITY |  | CHECKED / VERIFIED BY (INITIAL & DATE)
[19 empty] | GC CIVIL | TfNSW | OTHER
53 | Line marking |  | Structural drawings |  |  | Each lot |  |  |  Edgeline E1 – 150mm wide line  Dividing barrier line BB – 100mm wide line 100mm gap  Semi flexible guideposts as per TfNSW Delineation Manual Section 16 |  |  | Delivery dockets Verification Checklist Compaction records |  |  | IP |  | GC Project Manager
DISESTABLISHMENT & PROJECT CLOSE-OUT
54 | Disestablishment |  | Visual |  |  | Prior to disestablishment of plant from site |  |  |  All rubbish & excess materials removed off site  Areas graded with appropriate falls for natural drainage without undulation |  |  | Document - photos |  |  | IP |  | GC Project Manager
55 | Practical Completion |  | Visual Inspection Client inspection required |  |  | Completion of Works |  |  | Conformance to Drawings and Contract Documents including close out of any non-conformance Conduct a joint inspection, to be undertaken with Client to confirm asset completion and handover Any defects raised must be actioned prior to Final Completion item Confirm bridge concrete strength has reached 50Mpa before opening to public traffic |  |  | Document – Certificate of PC Test Reports |  |  | IP |  | GC Project Manager Client Project Rep
56 | Work-As-Executed Survey |  | Survey Measurement |  |  | Each lot |  |  | Survey of completed bridge structure location & level |  |  | Work-as- executed survey file |  |  | IP |  | GC Project Manager Surveyor
57 | Work-As-Executed Drawings |  | Drawings Site Records Measurement |  |  | Each lot |  |  | Mark up any changes to Design Drawings On completion of construction, provide the Project Representative with a set of “Work-as-Executed” drawings, incorporating approved modifications made to any details during construction |  |  | Work-as- executed drawings |  |  | IP |  | GC Project Manager
Document No. and Title: |  |  | GCITP013 Construction of Bridge |  |  | Revision: | [13 empty] | 1
Authorised By: |  |  | Craig Simpson |  |  | Date: | [13 empty] | 2022-02-24
Client: | [11 empty] | Project No:
Site Address: | [11 empty] | Date Issued:
ITP ITEM No. | INSPECTION / CONSTRUCTION ACTIVITY |  | INSPECTION / TEST / METHOD / STANDARD / SPECIFICATION |  |  | STAGE OR FREQUENCY OF SAMPLING |  |  | ACCEPTANCE CRITERIA |  |  | RECORD OF CONFORMITY |  |  | TYPE |  | RESPONSIBILITY |  | CHECKED / VERIFIED BY (INITIAL & DATE)
[19 empty] | GC CIVIL | TfNSW | OTHER
58 | Inquik Material Data Record (MDR) |  | Desktop review |  |  | Completion of Works |  |  | On completion of construction, provide Inquik MDR |  |  | Document – MDR, Inquik install checklists |  |  | HP |  | Inquik GC Project Manager
59 | Final Completion |  | Drawings and Contract Document |  |  | Completion of Contract |  |  | Conformance to Drawings and Contract Documents including close out of any non-conformance |  |  | Document – Final Completion Certificate |  |  | HP |  | GC Project Manager
Document No. and Title: |  |  | GCITP013 Construction of Bridge |  |  | Revision: | [13 empty] | 1
Authorised By: |  |  | Craig Simpson |  |  | Date: | [13 empty] | 2022-02-24
Client: | [12 empty] | Project No:
Site Address: | [12 empty] | Date Issued:
LEGEND AND SIGN-OFF
INSPECTION REQUIREMENT |  |  |  | RESPONSIBILITY | [5 empty] | RECORDS | [5 empty] | RECORDS
GC CIVIL
AP | Approval Point (Written or verbal approval must be given) |  |  | PM |  | Project Manager |  |  |  | CC | Contract Correspondence |  |  |  |  | HR |  | Hold Point Release
HP | Hold Point (work shall not proceed until the HP is released) |  |  | PQR |  | Project Quality Representative |  |  |  | CD | Contract Documents |  |  |  |  | MR |  | Maintenance Report
|  |  |  | CM |  | Construction Manager |  |  |  | COC | Certificate of Currency of Insurance |  |  |  |  | NCR |  | Non-Conformance Report
WP | Witness Point (give notice to allow inspect) |  |  | SM |  | Site Manager |  |  |  | CPC | Certificate of Practical Completion |  |  |  |  | PER |  | Permit
|  |  |  | TL |  | Team Leader |  |  |  | CR | Construction Records |  |  |  |  | PC |  | Proof Engineer’s Certificate
IP | Inspection point (Formal Inspection to be done and recorded) |  |  | CLIENT (XXXXX) | [5 empty] | DD | Delivery Documents |  |  |  |  | QCC |  | Quality Control Checklists
|  |  |  | CPR |  | Client’s Project Representative |  |  |  | DR | Structural Design report |  |  |  |  | QMP |  | Quality Management Plan
TP | Test point (Product compliance test to be undertaken and recorded/reported) |  |  | CSR |  | Client’s Site Representative |  |  |  | DWG | Drawings |  |  |  |  | ROL |  | Road Occupancy License
|  |  |  | SR |  | Superintendent’s Project Representative |  |  |  | DWR | Daily Works Record |  |  |  |  | SI |  | Site Instruction
|  |  |  | SO |  | Surveillance Officer |  |  |  | EC | Engineer’s Certificate |  |  |  |  | SV |  | Survey Record
|  |  |  | PROJECT CONSULTANTS | [5 empty] | EMP | Environmental Management Plan |  |  |  |  | SZA |  | Speed Zone Authorization
|  |  |  | RS |  | Registered Surveyor |  |  |  | ESCP | Erosion & Sedimentation Control Plan |  |  |  |  | TR |  | Laboratory Test Report
|  |  |  | GE |  | Geotechnical Engineer |  |  |  | FC | Final Certificate |  |  |  |  | TCP |  | Traffic Control Plan
|  |  |  | SD |  | Structural Design Engineer |  |  |  | GR | Geotechnical Report |  |  |  |  | TMP |  | Traffic Management Plan
|  |  |  | PE |  | Proof Engineer |  |  |  | BR | Building Report |  |  |  |  | VMP |  | Vehicle Movement Plan
|  |  |  | OTHER | [11 empty] | WAE |  | Work-As-Executed Drawings
|  |  |  | SUB |  | Subcontractor
|  |  |  | SUP |  | Supplier
|  |  |  | NL |  | NATA Certified Testing Laboratory
|  |  |  | TMC |  | TFNSW Traffic Management Centre
|  |  |  | PR |  | Client Project Rep
|  | Amendment |  |  | Date: |  | Reviewed: | Validation | [5 empty] | Acceptance
[8 empty] | I certify that the works have been constructed in accordance with this Inspection & Test Plan | [5 empty] | I have inspected and accept the completed works have been constructed in accordance with this Inspection & Test Plan
[8 empty] | GC Civil Representative: | [5 empty] | Client’s Project Representative:
[8 empty] | Signed: | [5 empty] | Signed:
[8 empty] | Date: | [5 empty] | Date:
Document No. and Title: |  |  | GCITP013 Construction of Bridge |  |  | Revision: | [13 empty] | 1
Authorised By: |  |  | Craig Simpson |  |  | Date: | [13 empty] | 2022-02-24
Client: | [12 empty] | Project No:
Site Address: | [12 empty] | Date Issued:
Document No. and Title: |  |  | GCITP013 Construction of Bridge |  |  | Revision: | [13 empty] | 1
Authorised By: |  |  | Craig Simpson |  |  | Date: | [13 empty] | 2022-02-24