## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-163-RAIL-SSB-Rail Delineation Permanent Fencing | itp |  |  |  |  | ITP-163-RAIL-SSB-Rail Delineation Permanent Fencing Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-163-RAIL-SSB-Rail Delineation permanent fencing
label | ITP Description: SSB-Rail Delineation permanent fencing
label | Discipline (e.g. CIV/STR/RAIL): 163-RAIL
label | Revision Number: 0
label | Revision Date: 10/05/2024
label | ITP created by: Yasna Nicker
label | ITP approved for use by: VM
label | 1.1 Non Dependent
label | Reference: IFC Drawings
section | Preliminaries-Materials
checkpoint | 2.1 Concrete Toe Beam and Head Beam
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Minimum of 60 MPa concrete shall be used as per IFC drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each Mix
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: HP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Certificate of Compliance
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 Steel components
label | REFERENCE: IFC Drawings AS41000, AS1163
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All Steel must comply with Australian Standards.
label | ○ Steel section sizes must be checked on site.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document review, Visual and Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: All elements
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: Supplier Certificate of Compliance
date | Date Completed:
section | Preliminaries-Documentations
checkpoint | 3.1 Excavation of toe and head beam
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Excavation for beams must not undermine track and comply with PTDT requirements.
label | ○ Follow asset owners guidelines for work around their service.
label | ○ Excavation must use Non Distructive Digging in the rail corridor
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY:
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Pre-construction / Pre-installation Activities
checkpoint | 4.1 Survey Set-out
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Survey to set out the following but not limited to: existing services, post locations, refuge bays
label | ○ Offset checked against the running edge prior to installation of posts.
label | ○ Engineer to verify alignment of posts using string line or equivalent.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual inspect
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Surveyor, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Construction / Installation Activities
checkpoint | 5.1 Ground Conditions
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: All post foundations/ beams to be inspected by the site team prior to installing the posts. All foundations are to be free of water and loose material.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each post
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.2 Toe and Head Beam Formwork Design and Construction
label | REFERENCE: IFC Drawings 614.04, 614.05, 614.06
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Designed and constructed in such a manner so it can be removed without damage to the concrete.
label | ○ Formwork to be rigid, watertight, braced, tied together & selected to achieve the required surface finish.
label | ○ Formwork shall not be placed where steel & fixtures cannot be inspected.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Document Review, Visual, Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each type of element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Temporary Works Designer, Proof Engineer, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
checkpoint | 5.5 Reinforcement Placement (Toe Beam and Head Beam Steel)
label | REFERENCE: IFC Drawings 611.06, 611.09, 611.10, 611.11, 611.12
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: The correct reinforcement grade, quantity, size, orientation, location and spacing as shown on the structural drawings.
label | ○ Projecting reinforcement is the correct length and location.
label | ○ The reinforcement surface condition is free from dirt, debris and damage.
label | ○ Minimum cover as shown on the structural drawings for each face has been achieved (including tie wire locations).
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure, Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed Off
date | Date Completed:
checkpoint | 5.3 Toe Beam and Head Beam Foundation
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Toe Beam Dimensions (Fencing Post Foundation)
label | ○ 600mm Depth
label | ○ 600mm Diameter
label | ○ 2405mm c/c Spacing
label | Head Beam Dimensions
label | ○ 600mm Depth
label | ○ 600mm Diameter
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each footing
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Concrete Toe Beam and Head Beam
label | REFERENCE: Site Sampling & Testing Procedure 610.16 (b)
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | ○ 0m³ to 10m³ = 1 sample
label | ○ 10m³ to 25m³ = 2 samples
label | ○ 25m³ to 50m³ = 3 samples
label | ○ 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
label | – For each additional 50m³ and additional sample shall be taken.
label | – Where IFC nominates minimum strength development, ensure strength is verified by additional cylinder or other approved method (such as maturity testing).
label | – Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | – Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Test
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: Concrete Tester, Foreman, SE/PE/SPE
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP Signed Off, Concrete Pour Record
date | Date Completed:
checkpoint | 5.3 Post Installation
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Maximum fence post spacing to be 2405mm
label | ○ Max. post height 1800mm above ground level
label | ○ Vertical Tolerance: ±20mm from the design line.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each post
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.4 Fence Panel Installation
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Galvanised fence panels 1820x2405x55 to be fixed to fence post with 25mm U-clip, using TEK screw. A minimum of 2 brackets must be used and fastened to each post.
label | ○ Minimum ground clearance under panels 50mm
label | ○ Maximum ground clearance under panles 150mm
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 5.5 Bracing
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: 48.3 X 4 CHS brace at end bays and corners fixed each end via approved proprietary post and rail clamps.
label | ○ Bracing to be installed on both sides of the fence at the fence corners
label | – – – – – – – – – – – – – – – – –
label | METHOD: Visual
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each element
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction / Post-installation Activities
checkpoint | 6.1 Fence Height and Track Clearance
label | REFERENCE: IFC Drawings
label | – – – – – – – – – – – – – – – – –
label | ACCEPTANCE CRITERIA: Posts are to be checked for verticality and ensure offset is not less than required from near face of post to centreline of track or as shown on alignment drawings.
label | – – – – – – – – – – – – – – – – –
label | METHOD: Measure
label | – – – – – – – – – – – – – – – – –
label | FREQUENCY: Each lot
label | – – – – – – – – – – – – – – – – –
label | CATEGORY: IP
label | – – – – – – – – – – – – – – – – –
label | RESPONSIBILITY: SE/Site Supervisor
label | – – – – – – – – – – – – – – – – –
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP