## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | CS-4083 - Bored Piling Inspection (to be used in conjunction with CS-4011) |  |  |  |  | Yes | CS-4083 - Bored Piling Inspection (to be used in conjunction with CS-4011) | 08d5233d-10a3-4b41-ab2e-d6f4dca5fded
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | Details
text | 10de927f-d3d2-534a-a669-837b08d4be88 |  | textbox | Pile no:
text | cd912342-9505-5920-89d9-c77bedd87993 |  | textbox | Address:
text | 5534d5ce-1928-5267-b715-534f70f0f85d |  | textbox | Area:
date | 36792f9d-a45b-529c-a421-a3d4d52720e4 |  | date | Start Date:
text | c892fef2-9697-5dc4-9aaf-a68235945adc |  | textbox | Start Time:
date | 956b2bb1-ac3a-5b35-8448-8822edbacf32 |  | date | Finish Date:
text | 0ca0095a-2663-5d26-b2c2-d7ddf73d661b |  | textbox | Completion Time:
checkpoint-group |  |  | section | Piling Bore Log
checkpoint-status |  |  | checkpoint | Pile Diameter (Circle):
text | 9f834270-36ff-5b81-ad33-3f26911f003d |  | textbox | Casing Length: |  |  | m
text | 4c4c80a2-f094-5308-be5d-71b3b3d4f1d4 |  | textbox | RL Ground Surface: |  |  | m
text | 90c217ea-6c67-5082-8162-d3248808a146 |  | textbox | RL Top of Casing: |  |  | m
text | a6ed394b-bc61-5db8-b6f3-e5c1d84267c7 |  | textbox | RL Bottom of Casing: |  |  | m
text | 59b46498-f3ae-574c-9a59-47bf5b1bbdd6 |  | textbox | RL Underground Water: |  |  | m
checkpoint-status |  |  | checkpoint | RL Founding Levels:
text | 0e1d4ae7-67d7-5df2-8e98-6bd25cb7423f |  | textbox | Constructed: |  |  | m
text | 0ccb810e-6dbf-5f28-a60b-3b910aa15538 |  | textbox | Design: |  |  | m
checkpoint-status |  |  | checkpoint | Shaft Length (top of casing to founding depth):
text | ee20f63a-80f3-51ce-ad14-56c17bf12aa7 |  | textbox | Constructed: |  |  | m
text | 66d8a9ee-cfdb-58fc-a3ea-170182a4da84 |  | textbox | Design: |  |  | m
checkpoint-status |  |  | checkpoint | Pile Inspection (Site Engineer):
text | 6d17c57e-502c-54c8-86d5-64faab8d7c0d |  | textbox | Name:
date | 538ee315-9b45-57b9-8172-167a86f468fa |  | date | Date:
text | e5754dec-df02-5f29-9110-c1bf2035578f |  | textbox | Time:
checkpoint-status |  |  | checkpoint | Pile Inspection (Design Engineer):
text | 1a48f354-65b1-5698-8fa4-0971f62fd111 |  | textbox | Name:
date | 479e1a14-51cc-50f4-b769-d96d432f95f4 |  | date | Date:
text | ec16a8ed-0ae4-503e-8262-ce1ce9ac34cb |  | textbox | Time:
checkpoint-group |  |  | section | Depth from GL
checkpoint-no-status |  |  | checkpoint | 1 - Depth from GL (m)
text | 22a5656a-a600-51dc-8dc5-6b7738e7bd1e |  | textbox | Depth from GL (m):
text | 7329b78b-eb40-522e-9818-dc54ec43f1b9 |  | textbox | Soil Description:
date | 2f8edb98-3aa8-52f6-89f4-bf7efd9ef5e9 |  | date | Date:
text | 9fdd20d6-743a-538f-b7c5-bf490b2a4f79 |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 2 - Depth from GL (m)
text | f7058d78-10c8-5d2b-b63e-be6f4c31f0ff |  | textbox | Depth from GL (m):
text | 5cee2b8e-bda2-518a-9687-665021d17f23 |  | textbox | Soil Description:
date | f198f946-c5d0-567d-8593-1a505185ace0 |  | date | Date:
text | be55a983-bf64-5abb-bc54-d04d8c1a6531 |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 3 - Depth from GL (m)
text | 8aeb60e2-d2f9-5451-a044-da5b44c93732 |  | textbox | Depth from GL (m):
text | bdd211cc-4c52-5f2c-9b49-7526de5543dc |  | textbox | Soil Description:
date | ac6c90d1-e90d-59bf-a165-66dbb5183fb0 |  | date | Date:
text | cee72102-3c3f-5af4-a3e5-92cf9879fb79 |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 4 - Depth from GL (m)
text | 2c40d7a7-8e6c-5194-8c07-095a599d0bff |  | textbox | Depth from GL (m):
text | 44e8494c-51e5-580a-b2ec-93e295cdccb8 |  | textbox | Soil Description:
date | de8a8758-27a3-5d38-8e57-8cee53601dc9 |  | date | Date:
text | 5b0a6845-462f-5fb1-8285-58c0e3b097f2 |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 5 - Depth from GL (m)
text | f612e08e-4b58-5a22-bba7-23f4b4eb6b95 |  | textbox | Depth from GL (m):
text | c39e60c3-ceba-5051-bacb-42fbd2726796 |  | textbox | Soil Description:
date | dda08e46-4ecd-5feb-8dea-fff3a1113d03 |  | date | Date:
text | 90e79c8b-ea6d-549b-8cfd-81aa7e1e42e2 |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 6 - Depth from GL (m)
text | 2016575f-7d19-5e4f-9d18-62118b4b5f21 |  | textbox | Depth from GL (m):
text | 57a8e140-ed27-5d58-9583-3227d62160fb |  | textbox | Soil Description:
date | 1665e8d7-d661-5133-99e0-75a345c135ba |  | date | Date:
text | 304dc4c9-461f-5b52-8141-5632da6e2630 |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 7 - Depth from GL (m)
text | 48356adb-aa31-5d3a-a993-984b427a71f8 |  | textbox | Depth from GL (m):
text | 7f8d6f64-b66f-5900-9b5d-e746689fa8ac |  | textbox | Soil Description:
date | 3d9f4687-e928-526a-95ac-a90c78317793 |  | date | Date:
text | 7e50ff3b-5e6f-51ff-b277-bb4f3c6740d6 |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 8 - Depth from GL (m)
text | 50d6a014-b96c-5aa2-97a7-c55a739ef198 |  | textbox | Depth from GL (m):
text | d330ace6-2b77-5414-b888-8804be7b15ee |  | textbox | Soil Description:
date | 1f4116d9-5180-5bb7-be5e-d07572482c49 |  | date | Date:
text | 7a516f0a-54c2-52c1-81d9-5c44fcbc8bca |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 9 - Depth from GL (m)
text | 7e01431e-dcc8-539f-aa2d-0dd33398c7ab |  | textbox | Depth from GL (m):
text | d747fd1f-aa15-55d7-80fe-38f6771dac08 |  | textbox | Soil Description:
date | 6fedc4b2-93f8-5835-b4a6-df0071e588b6 |  | date | Date:
text | 210fd396-a42d-5a7b-9e7e-f5816da1f851 |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 10 - Depth from GL (m)
text | a2c4b112-4bcd-5d75-b4ab-b354dcf7b129 |  | textbox | Depth from GL (m):
text | 8c0e972c-c467-55ca-bc7b-32679ff83d96 |  | textbox | Soil Description:
date | 5c03266d-386f-5130-99de-b338a1abfa4c |  | date | Date:
text | 1f347c9a-f320-5985-a3c0-ac48221f756e |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 11 - Depth from GL (m)
text | b3e5277b-4f69-5d1b-8fb7-7b43fdad63d0 |  | textbox | Depth from GL (m):
text | 73364af8-36b0-54fc-a952-c3b1db4e58c5 |  | textbox | Soil Description:
date | a432e99e-728e-5240-a861-13772284dc1b |  | date | Date:
text | e215830a-7fe2-5aa4-8003-8cd8fbd3bb1a |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 12 - Depth from GL (m)
text | 950e6cf6-0e14-5e10-ba8b-196d52aa42cc |  | textbox | Depth from GL (m):
text | f14cf022-1e57-5b79-82a8-e17d762e591f |  | textbox | Soil Description:
date | 7c43859f-edbc-5c7e-a639-bc2ea0c55329 |  | date | Date:
text | 3f9937b4-70a5-5512-ade1-8b68d8342615 |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 13 - Depth from GL (m)
text | 771201d3-5728-5b3b-be28-7119ab85b3bc |  | textbox | Depth from GL (m):
text | d32a9955-604a-5335-9aff-849c72cf8e70 |  | textbox | Soil Description:
date | a00fbc1a-4ba6-5180-82bc-262167543eb8 |  | date | Date:
text | b25f54ae-d7c2-5e2b-b7e0-2b431593b241 |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 14 - Depth from GL (m)
text | 236fd856-ec20-50f8-8116-e86137e75c3b |  | textbox | Depth from GL (m):
text | 43c138df-d7f2-5d00-a912-d4ef057fb89b |  | textbox | Soil Description:
date | 650bae03-867e-5ee8-b44c-84a37c7a5b1a |  | date | Date:
text | 2ad4e0e1-c1c3-5c40-a49a-8d33568c2ed4 |  | textbox | Time:
checkpoint-no-status |  |  | checkpoint | 15 - Depth from GL (m)
text | 0dcc6c6e-a026-5a81-a408-38cc10c9f3ab |  | textbox | Depth from GL (m):
text | d0c3eaba-22b8-5b09-8cb3-7a457b69e2bc |  | textbox | Soil Description:
date | dddc6ecf-c9d3-5e7c-9220-51a78e3f2982 |  | date | Date:
text | cdd55d82-c76b-5f44-8b6b-0ee05781e176 |  | textbox | Time:
checkpoint-group |  |  | section | Signoff
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | Piling Foreman Sign
text | 8378d77e-d4f4-51f4-a41f-a8bc48161db5 |  | textbox | Name:
date | a72457bc-6206-5ec9-a4ff-ae21f066e58c |  | date | Date:
holdpoint |  |  | signoff | SIGN
checklist-flat |  |  | checklist | ITP - C1503B - Mautaua Under Slip - Earthworks - Bulk Fill | itp |  |  |  | Yes | ITP - C1503B - Mautaua Under Slip - Earthworks - Bulk Fill | 0934ada7-6fab-45c4-ac41-de41d91a6b78
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 84d68b54-0866-5aae-8dab-379e5ebf82fe |  | textbox | CPS Eng.
text | 4fec42b5-dcc8-56a3-84b3-3343c942f492 |  | textbox | Site Engineer
text | d1f39e12-657f-58bb-a259-fa26c7a31eff |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 8a405b45-f783-53c4-a704-1eb47c3d51bd |  | note | ACTION (Hold, Monitor, Witness) - W
label | 749c5afe-aa40-507e-b4b0-b6643969008a |  | note | Detail - Set out extents of fill and check against design drawings
label | b4495282-05ce-5dca-866f-12689186972e |  | note | Frequency - Prior to commencement
label | 30fa9dc2-0bd2-5dd7-9a05-ec24551ce554 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 420ec524-d358-53e1-851d-7c11449e0738 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | eb8a0e1d-e7c4-55ad-b850-a0ee69480ce6 |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 2 - Topsoil Strip
label | 766419bd-70df-52fd-b108-9892b744a068 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 13878f56-1fb0-5fc1-912a-01724209e684 |  | note | Detail - Once all ESC controls have been installed & the Tree Felling & Vegetation Clearance has been carried out
label | 2fce38ea-a4e9-57e0-8970-7ae7d01f0aa0 |  | note | Frequency - Prior to commencement
label | dd320576-be72-5546-86d9-e00b8adc3e6a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 9d162547-63b4-54aa-9d99-0209a13210d8 |  | note | Records - QA-6002 Process Control PlanTree Felling &Vegn Clearance Check Sheet
checkpoint-status |  |  | checkpoint | 3 -
label | 0af8e15b-0631-56b1-8173-f8bad7f87005 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e7a935d3-b0db-5c3b-b686-1580b0fcad75 |  | note | Detail - Topsoil to be stockpile in an area approved by designer
label | dd44380f-288b-52b5-bdae-ffbb126d5de0 |  | note | Frequency - Prior to commencement
checkpoint-status |  |  | checkpoint | 4 -
label | c8d53881-d981-56e2-a22d-debf8938f0c1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9f34bd36-4292-563c-9ee6-eaa7143c60a6 |  | note | Detail - Inspect fill foundation
label | c618fc08-3abe-5660-8aa3-fee7b92f1fe5 |  | note | Frequency - At completion of topsoil strip, before Toe construction
label | 2028e762-4e77-5c43-9d8f-551a93b85bf9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | 02f4564e-69a4-5956-bef3-d31933d56dc9 |  | note | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
label | bc624d85-1084-5429-9e20-383a206df263 |  | note | Records - CS-4100 Subgrade Approval Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Ground Improvements
label | 3a33f4eb-4f70-57e0-9d7c-7f386a8d7cec |  | note | ACTION (Hold, Monitor, Witness) - W
label | e4da011b-6b67-530a-a101-940f7a886924 |  | note | Detail - Any area that requires Ground Improvements must be completed as per ACE-CS-6003 and be signed off and closed before bulk earthwork operations commence
label | dbc9e669-245c-5c1c-a72d-52865ae22d49 |  | note | Frequency - Prior to commencement
label | ac4ab536-c0f8-515f-a672-a05fa919f5c7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 5e9669c5-1241-5ddc-9117-1ecdf73635a6 |  | note | Records - QA-6003 Process Control Plan Ground Improvmts (Wick Drains) Check Sheet
checkpoint-status |  |  | checkpoint | 6 - Fill Material Compliance Testing
label | 69e9b3bf-f7df-5e4e-84a9-376e1258d05c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 35373171-7078-56e5-8096-2028eb947754 |  | note | Detail - Material to meet specifications dependant on material type selected
label | ced4a600-c411-5b83-bc1a-4141906f432d |  | note | Frequency - Each material used
label | 5b5fc94f-9597-5589-9882-bdbe657f6af9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 0b36e3d1-6a92-5b22-97b1-31b523b5967f |  | note | Conformance Criteria - Rock of GAP65, 100, or 150, GAP65 specifically within top 1.2m of buttress
label | 20b48e16-36eb-544f-83a1-f86ecb289068 |  | note | Records - CS-4020 Bulk Fill Earthworks Record Check Sheet, material receipt
checkpoint-status |  |  | checkpoint | 7 -
label | d1a4e612-5cab-5a03-9751-78fd47ec7ad0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6d33c8f1-353f-5613-a58c-23d98b59e494 |  | note | Detail - Fill Construction Material
label | 5f1d67f3-2206-5b56-88e2-d270b94cb338 |  | note | Frequency - Prior to commencement
label | 9198f6b8-9052-51c2-9461-697690c7eaf6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 3aef27bd-ca45-5f21-bc92-b67669678a78 |  | note | Conformance Criteria - Granular aggregate with broken faces
label | 3a358ff2-b134-50c8-8fcd-3734dfdf2d28 |  | note | Records - Lab Test Report
checkpoint-status |  |  | checkpoint | 8 - Filling Operation
label | cf4e7721-7211-54c7-9df1-4e1aa9b074de |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8492744a-9c25-5c99-90b5-b85705b3621c |  | note | Detail - Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately
label | 4cbb8dfb-0201-5c69-83aa-c407c692f852 |  | note | Frequency - Daily
label | 9fcb1007-4403-573b-b352-ebd4c0d0fc57 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
checkpoint-status |  |  | checkpoint | 10 -
label | e07024bc-1493-5443-9553-747ad88117f3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e0a87bbe-2129-52f8-b156-f77077a59b44 |  | note | Detail - Site Engineer to check embankment slopes for location, line and level as the fill progresses ensuring that batter faces are overfilled and trimmed back so that so that the fill is well compacted to the edge
label | 16db879a-787a-516e-98be-f460a77e5bcf |  | note | Frequency - Daily visual survey check
label | 11a84453-0654-5755-8db4-5d18c448228c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 852f2d94-960f-5e51-95c6-3617f833584f |  | note | Conformance Criteria - As built drawings
label | cc7d0b06-57f9-5587-9dfd-a14dac7e5fdd |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 11 - Filling Testing Requirements
label | fd533b34-844d-5eb5-90db-aa678442401f |  | note | ACTION (Hold, Monitor, Witness) - W
label | f22e22b2-2a42-52ba-a3b7-e493f02107d2 |  | note | Detail - Fill placed in horizontal layers no greater than 300mm and compacted. Site Engineer to instruct lab when and where to carry out testing
label | f5b46185-34bd-5169-b435-cf991110fbab |  | note | Frequency - 1 test per layer of fill
label | eb118f33-2791-5667-87f6-5e998964801d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Lab Testing
label | 2c830bdb-381f-53d8-be12-e32e44d1d98b |  | note | Conformance Criteria - Fill shall be compacted in accordance with NZ4431: 2022
label | 6171dc6a-bd1f-5ff9-9e24-693cd49a3123 |  | note | Records - CS-4020 Bulk Fill Earthworks Record Check Sheet
checkpoint-status |  |  | checkpoint | 12 - Survey As Built
label | 21957959-bd9d-55a1-bcdd-c85bbf11212c |  | note | ACTION (Hold, Monitor, Witness) - W
label | f9339d8b-652a-5a29-835a-4159c0c1adf3 |  | note | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
label | eff9a66f-6751-51c5-8f51-4ea79fc2031b |  | note | Frequency - Prior to placing topsoil/pavement/ finished surfaces
label | 5c09beea-9f24-52d8-9156-92101aa3f68d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 6c4a4064-83b7-55ed-9f4e-f70302d56be6 |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 13 - Confirm testing requirements met
label | 13a339f0-1b8b-535a-81d5-3645879299c3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | faad2d07-a86c-5e72-b17d-e6e4e7c44b4c |  | note | Detail - Ensure correct no. of test sets performed for fill testing
label | 20cf8b15-d713-5857-8678-e013f7eac0ad |  | note | Frequency - At completion of Lot
label | 10c07b54-d6df-51f4-a4b7-dc1c11ca0d7d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 2ba59505-d613-5c3f-9145-950a89565cbd |  | note | Conformance Criteria - GAP65 testing, Compaction testing
label | c8176cb6-ec36-5863-b5bb-8bd484b4249a |  | note | Records - Test results and calculations of fill volume
checkpoint-status |  |  | checkpoint | 14 - Lot Number QA File
label | 42712020-a79f-5ec3-a096-133c60b766d0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d044671d-1a1b-5d7d-a555-7305d76e4a8d |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 82a9f730-ad15-55a3-a049-712018733876 |  | note | Frequency - At completion of Lot
label | 5ede5a98-a68e-5bcb-9da1-c6b7c6ac9946 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 12c8d129-397a-55e6-85c8-2925781f2f82 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 10880ce2-35aa-5c3e-9947-93c67d39e04b |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 15 - As-builts
label | 00050ef5-fbcb-587d-8c60-9f624d5fb537 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9cb3a5fd-5bf3-5c47-9fde-acdac88636e0 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | aea053b5-4686-5fc7-a372-d7ed34b439ea |  | note | Frequency - At the completion of the Lot of work
label | 5cb96b6e-fc7d-5979-bf12-b7a56c10b34c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | d145a3d5-0f76-59a3-8bdc-fdf9b10b74df |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | CS-4072 - ITS Pit Inspection Record |  |  |  |  | Yes | CS-4072 - ITS Pit Inspection Record | 0be314d4-7a12-42e3-a2d2-ed50c0facd4b
checkpoint-no-status |  |  | checkpoint | ITS Pit Inspection Record
text | 27545b23-c8a2-5d0e-b7a4-cab56a932fbe |  | textbox | Project No.
text | a4828e3c-147d-5cb6-a5ca-0a0fee16278f |  | textbox | Drawing No (& Rev No):
text | b6d4c5f3-305e-5c29-b553-a1660f19cfa5 |  | textbox | Pit #:
checkpoint-status |  |  | checkpoint | Pull Pit/ Joint chamber set out by surveyor
text | 2e94c050-40a5-57fe-9493-e1c42bb2e679 |  | textbox | Initials:
date | a1d79651-337b-5182-b49a-e30ff129eb0e |  | date | Date:
label | 91fe9537-4cd0-599d-a59a-a4786db6531f |  | note | Comments: Survey Receipt
checkpoint-status |  |  | checkpoint | All existing services exposed and identified before trenching
text | 0e656944-54c7-5919-93ff-5b11b32f00e3 |  | textbox | Initials:
date | 14587adf-e5c0-51f2-87b8-d4976c7d603c |  | date | Date:
checkpoint-status |  |  | checkpoint | Depth shall be determined prior to excavating
text | 8a6dc1b8-b4b0-5d12-b611-5154f5bbc073 |  | textbox | Initials:
date | cfcf2c8b-663f-5c04-b3fb-3adb316c4542 |  | date | Date:
label | cc999534-0a10-5f53-9fb0-8445d8ff9db5 |  | note | Comments: Grass/Concrete/Asphalt areas – Lid must be flush to FL
label | b201b745-f34e-52c4-9a84-495a924382be |  | note | ○ Planted areas – Lid must be 100mm above ground level with a sloping concrete apron
checkpoint-status |  |  | checkpoint | Slopes >30 lid shall be 100mm above GL on the upper side. Slopes 10-30 lid shall be flush with the GL on the upper side.
text | 08702d78-db03-5bdb-ad6a-7b7f28e8714e |  | textbox | Initials:
date | c125a91f-8952-53a1-a5fa-94c300d749e2 |  | date | Date:
checkpoint-status |  |  | checkpoint | Bedding shall be 150mm of GAP65 compacted
text | e88d9e89-9891-5acd-a943-a5a678cd4d2d |  | textbox | Initials:
date | 97be2193-67a7-5110-bb82-a690db695a40 |  | date | Date:
checkpoint-status |  |  | checkpoint | Ducts shall be connected perpendicular to the chamber wall.
text | 166d8906-eeda-5eff-8501-5c0806826437 |  | textbox | Initials:
date | 2194521a-e898-54e7-8195-bf5c7e0c2a6b |  | date | Date:
label | 267acfb6-5f77-5c00-bd93-fd5bc14527ad |  | note | Comments: Ducts must not protrude more than 100mm into the chamber
checkpoint-status |  |  | checkpoint | Seal ducts using suitable epoxy resin (outside) to ensure water tight
text | 117aa79d-b831-530c-8ce1-d58a3040515c |  | textbox | Initials:
date | 14944f0d-7cb3-52f3-bf77-8c34e6aef00b |  | date | Date:
label | 26df48dc-6a81-5a54-8467-244a6e08a3d9 |  | note | Comments: All joints must be smoothed off to form a fillet between the duct & chamber wall
checkpoint-status |  |  | checkpoint | Ensure all ducts are capped inside the chambers to keep water tight
text | 7a2a7bcd-d7e7-5245-a523-4b88bd7243e9 |  | textbox | Initials:
date | faa62a9a-9fc0-50bb-9655-df2b5d381624 |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure backfill material is correct and compacted
text | 82f50fb4-f68f-5fd0-a11b-7dbcc9b16241 |  | textbox | Initials:
date | 0c2d91bb-1840-5df6-a527-207246508efe |  | date | Date:
label | 8aa237c3-094c-554d-8cbe-1c0f73d8b45e |  | note | Comments: Berm – sand/excavated material 200mm lifts CIV of 8
label | d73ff4fc-76ee-54b7-ae3a-84cfa5aad9b0 |  | note | ○ Carriageway – GAP65 200mm lifts 95% MDD
checkpoint-status |  |  | checkpoint | Top 300mm of the chamber shall be concreted to a width of 150mm around the lid
text | d155baac-5ce6-59d8-aa10-4b36694d687b |  | textbox | Initials:
date | a409490c-2c7a-58aa-80dc-93ee350492b1 |  | date | Date:
checkpoint-status |  |  | checkpoint | Roof, collar & lid installed to manufacturer’s requirements
text | b42ac898-c20e-56b7-8b63-745040afa3c2 |  | textbox | Initials:
date | 6049b382-e0b8-5a2e-ba68-b57454bb7161 |  | date | Date:
checkpoint-status |  |  | checkpoint | Clean out jointing chambers at completion.
text | 3bb35d4a-305e-5a8e-b34c-99032f53369a |  | textbox | Initials:
date | bf59e9ed-ef1a-5c87-878a-bc61da9c543e |  | date | Date:
label | 09e0c4c2-d71f-5c67-a49a-3b6467fff2ba |  | note | Comments: Remove any construction materials or contaminates from Pit
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
text | e6b859e0-18b0-5642-a94c-2e5a466b0594 |  | textbox | Name:
text | a1ac0a6a-fc42-589e-8972-d00e77c0dbd2 |  | textbox | Position:
date | fc0534ca-c4d6-528b-82a2-598598648279 |  | date | Date:
holdpoint |  |  | signoff | Sign:
checklist-flat |  |  | checklist | CS-4029 - Concrete Pump - Permit to Pump |  |  |  |  | Yes | CS-4029 - Concrete Pump - Permit to Pump | 0c6981e2-01f2-4b00-9cf3-d3ea5044cd7b
checkpoint-no-status |  |  | checkpoint | Concrete Pump - Permit to Pump
text | bb14db63-5665-52fa-b0e7-24343a08b66d |  | textbox | Project No.:
text | 67182570-da4d-5316-a368-1116b7e54e89 |  | textbox | Location:
checkpoint-status |  |  | checkpoint | Pump Operator Pre-start Checks Completed
text | 0faed893-9007-5c9d-b8e5-549ba80efffc |  | textbox | Initial:
date | 10f87204-2e6b-5fb7-8d4e-5c86fcbf3b1b |  | date | Date:
checkpoint-status |  |  | checkpoint | Pump set up level
text | 60c67941-3284-5c29-ab95-74755e5d62ad |  | textbox | Initial:
date | f9ed0ce0-4e61-5cf7-aefb-577ef1368159 |  | date | Date:
checkpoint-status |  |  | checkpoint | Steel delivery line in good condition
text | b68846f3-18d5-586d-82db-e1b77a96907e |  | textbox | Initial:
date | 75f608ba-a2c3-5723-831d-3e395c5049e1 |  | date | Date:
checkpoint-status |  |  | checkpoint | Rubber Delivery hose in good condition
text | f9d38fd6-86f9-5d4a-a8ba-4cd11050a7fa |  | textbox | Initial:
date | f95605fe-2f3e-5d56-93d1-5c3c6aefdc7c |  | date | Date:
checkpoint-status |  |  | checkpoint | Delivery Line Adequately Supported
text | 33a3f6e7-e6c1-53b3-ac66-3420aa75bdb1 |  | textbox | Initial:
date | 1eeeb33c-3319-584f-9ffb-52134816f7d9 |  | date | Date:
checkpoint-status |  |  | checkpoint | Delivery Pipe Connections correct & Locking Pins Fitted
text | 4efd07ec-af94-5719-a13f-17489ee99f38 |  | textbox | Initial:
date | a504f108-4fc9-55c2-aeca-912b43078f65 |  | date | Date:
checkpoint-status |  |  | checkpoint | All radios are working satisfactorily and communication checks have been carried out
text | 318dc680-e4e1-5881-9b13-c8b1fcf739f0 |  | textbox | Initial:
date | 59972174-c41a-5f7a-9516-2e53a70b1374 |  | date | Date:
checkpoint-status |  |  | checkpoint | Concreting Crew briefed on Work Instruction
text | bcd55050-6a2d-5260-874c-9b2244431999 |  | textbox | Initial:
date | eaf232a1-f988-579a-81d8-ffb0429c421c |  | date | Date:
checkpoint-status |  |  | checkpoint | All crew have correct PPE, skin fully covered (arms and legs)
text | d01e491f-351f-515e-9052-1477cf2793ad |  | textbox | Initial:
date | 2a417f6e-8579-5615-a4a7-12fd01730a25 |  | date | Date:
checkpoint-status |  |  | checkpoint | Permit to Pump
radio | b14bd997-0cc6-5d4b-96f1-63b446c5958e |  | radio | Permit to Pump – Issued / Rejected | Issued,Rejected
label | 7da3bde1-fd22-54e8-a447-f73f24776e86 |  | note | Project Engineer / Construction Manager / Superintendent
text | afc36c88-6956-5142-9326-94658f4530e5 |  | textbox | Name:
date | 1bccb197-1ab8-5e94-8049-1975cff89dc3 |  | date | Date:
holdpoint |  |  | signoff | Signed:
checkpoint-status |  |  | checkpoint | Prior to Cleaning Lines
label | 9c94c144-dd94-5ca2-8179-e77b31130f69 |  | note | Reducer and Hose removed
checkpoint-status |  |  | checkpoint | Permit to Clean Lines
radio | 08b1faad-7927-54d5-9e30-b2df127076d8 |  | radio | Permit to Clean Lines – Issued/Rejected | Issued,Rejected
label | 0a0218c0-3e15-54ac-bccb-9fd07980b336 |  | note | Project Engineer / Construction Manager / Superintendent
text | 24144a33-8450-5a11-be4f-1e2ae2803a28 |  | textbox | Name:
date | 05dd378d-bf0d-5fc6-9ea6-4cb530ddba3f |  | date | Date:
holdpoint |  |  | signoff | Signed:
checklist-sectioned |  |  | checklist | CS-4012 - MSE Wall Geogrid Checklist |  |  |  |  | Yes | CS-4012 - MSE Wall Geogrid Checklist | 0cf0a44b-bf77-4bfe-a833-8a2a8db7af20
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | b39615ed-ca36-576a-a5b6-01d43de86c78 |  | textbox | Work Area:
text | aa0b1db0-2ea5-5fd3-9e28-9d0492629cd2 |  | textbox | Sub Work Area:
text | 2f4f4f5d-2818-547b-9911-2697bd75643c |  | textbox | Lot:
text | 4345301b-25a6-5d86-81db-017099feb81a |  | textbox | Sublot:
date | 06e21f11-53b5-506e-bd92-6381c36e8c07 |  | date | Document Date:
text | 711df4e3-0ba3-5e40-a0f9-ff9e3b9cede6 |  | textbox | Created By:
text | 0d0e3c17-4615-5ad2-ac70-cb83567ecee8 |  | textbox | Structure Name:
text | 5ac60602-1f32-54dd-8b85-132f0b96852b |  | textbox | Drawing No:
text | 298a6b1a-8999-5ffb-9bb9-732aaabf3abd |  | textbox | Grid Layer Number:
text | c531df9e-e246-5dd5-a5ee-ec4546c0b46e |  | textbox | Structure Location:
text | 6d93a72b-6eb0-593e-8c5e-b050c5795807 |  | textbox | Drawing Rev No:
text | 0b803267-2087-5ed0-96d2-50f0e756114f |  | textbox | Grid RL:
checkpoint-group |  |  | section | Conformance Criteria
checkpoint-status |  |  | checkpoint | Check installation of each course
label | 4730043c-6c32-542f-9163-6e2381b3b093 |  | note | No gaps between adjacent units, max. vertical height prior to backfill is 2 units, min. pin connections per block is 2 upper and 2 lower.
text | 878844ec-4a75-50a3-abe0-c926ceea3ae2 |  | textbox | Initials:
date | 104436a9-3c5b-5065-abb4-a54cccf219bc |  | date | Date:
checkpoint-status |  |  | checkpoint | Confirm front face alignment in each course is within the allowable tolerance
text | 99047743-c32f-5a29-968c-a686b6243feb |  | textbox | Initials:
date | 931fb30f-1842-5840-b13e-661014db7fa2 |  | date | Date:
checkpoint-status |  |  | checkpoint | Inspect wall batter, wall batter to be within 2 degrees of design batter.
text | 8cd10c59-27a9-5736-9e19-5fb4801c1164 |  | textbox | Initials:
date | 06042f97-ac65-52ae-a756-2d64e977aadd |  | date | Date:
checkpoint-status |  |  | checkpoint | Confirm density results before placing Geogrid layer
text | 61094e78-91bd-5841-9596-a64b2e55ff1f |  | textbox | Initials:
date | 0a376df2-6e5f-5d12-9a42-33d585627c15 |  | date | Date:
checkpoint-status |  |  | checkpoint | Confirm the type of Geogrid
text | fb4393f6-e131-5485-8ad4-f1281e543d10 |  | textbox | Initials:
date | e3dd3da0-99f7-50b1-9f78-cbfcef78f37c |  | date | Date:
checkpoint-status |  |  | checkpoint | Confirm the correct length of Geogrid
label | 28f0a5d2-9d8b-5876-adb2-65ff10983daf |  | note | Inspect bodkin joints (where used) to join shorter pieces of Geogrid, 1 max. per length of Geogrid.
text | aeef92e5-5526-5e68-b4dd-5c0934f4c856 |  | textbox | Initials:
date | 61102109-039a-5e06-9bcb-510e486e00f3 |  | date | Date:
checkpoint-status |  |  | checkpoint | Confirm the correct elevation of Geogrid.
label | 75c9a8b7-2f63-5c7e-a313-7e7e97d5ded6 |  | note | Place within 75mm of design elevation
text | 2c53dc92-128b-5431-85c7-a39963f7833f |  | textbox | Initials:
date | b686d15c-4874-5f66-93b7-bcbaf1a21429 |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure Geogrid is placed flat on top of the compacted layer
text | 4ba7d7b0-51b5-5784-8d7b-57224505a20b |  | textbox | Initials:
date | fcd67576-74f3-58d4-8e8b-6e202d7cc6ab |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure Geogrid is connected correctly to the block pin connectors.
label | f289f007-3214-5e9d-b089-ec1491da6196 |  | note | Max horizontal distance between geogrids at wall face is 10mm
text | 6148a117-d923-5a85-86f1-c6bbca540639 |  | textbox | Initials:
date | f2166962-0732-5a20-b3a4-b7a89507bf43 |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure plant does not track over Geogrid
text | e3dfd10e-838d-5070-9df8-6f58e4a9a5c8 |  | textbox | Initials:
date | e7545898-518e-5096-82fb-7b0630fd5d1e |  | date | Date:
checkpoint-status |  |  | checkpoint | Tension geogrid and peg to hold geogrid tight
text | e8bb800b-8554-5a04-a3e1-385f00fcd2c6 |  | textbox | Initials:
date | 75344517-df24-54b7-a85f-41b8e8ad6e18 |  | date | Date:
checkpoint-status |  |  | checkpoint | Place backfill across the geogrid, plant can track onto geogrid when 150mm min backfill has been placed
text | 866016a6-ee48-5ffe-9942-8715bd9783af |  | textbox | Initials:
date | f9865ece-2487-521f-8e3d-2d9c64951fbc |  | date | Date:
checkpoint-status |  |  | checkpoint | Monitor plant and equipment keep 1m from front face of wall.
text | 165618d0-a52c-5d56-b8b8-8c28394b4361 |  | textbox | Initials:
date | 93fb4603-805d-5fd5-8454-7bf05bf27cdd |  | date | Date:
checkpoint-status |  |  | checkpoint | Design Engineer inspection?
text | 43919a70-541d-55aa-bf7c-5fd2fe14218c |  | textbox | Initials:
date | df448d69-d32c-5cb4-af42-472e03304f74 |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | ecadfd50-16bc-597e-9784-43ee3dc7517d |  | note | Position: Site Engineer
text | 100930c7-5bb7-52bc-9273-a77b37626466 |  | textbox | Site Engineer - Name:
date | bf9d52b2-e321-5222-9c8c-ab39e9d65584 |  | date | Site Engineer - Date:
label | e0d757b4-1d9d-503d-b703-e87f54e22f91 |  | note | Position: Design Engineer
text | 8b78ac64-e5aa-5086-8139-f62bd108b631 |  | textbox | Site Engineer - Name:
date | 06c26342-ba0b-5aa0-a21e-38b45973acc3 |  | date | Site Engineer - Date:
label | 08a09304-edba-5408-be5b-076fba74e186 |  | note | (Note: Attach a sketch showing grid on a separate sheet as necessary)
holdpoint |  |  | signoff | Sign
checklist-sectioned |  |  | checklist | ITP - B1101A - Te Ngarue Bridge - Scours Asphalt | itp |  |  |  | Yes | ITP - B1101A - Te Ngarue Bridge - Scours Asphalt V2 | 0d04d2e0-3ff5-4777-b70f-a37f59f54c15
checkpoint-group |  |  | section | 1 - Milling Operations
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 09847663-c7ce-550d-aa98-915a297dea66 |  | textbox | CPS Eng.
text | c98707ff-ff0d-50c4-933a-def70ee9f98f |  | textbox | Site Engineer
text | 6f381376-03f4-5f3e-afa4-2b31c1a0409c |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Survey Setout - Milling
label | 8a7c79a5-54e2-5e0f-a89e-50ebc0da92f6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8ffb1962-c0f3-59ff-bea4-1044bb714c06 |  | note | Detail - Confirm site extents by checking what’s marked on the road matches the job sheet / Design Report
label | 4fdb9593-e254-5efb-82a8-122988265e0c |  | note | Frequency - Prior to commencement
label | d80184c7-a931-5978-bdb5-e991654a535a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, Survey
label | 8d3585c0-54ad-5f99-a02c-b0f6e234657a |  | note | Conformance Criteria - Mark out on site, confirmed by CPS Engineer
label | 3d797218-ec2c-5885-b7ef-7ea7531bf6c1 |  | note | Records - Survey, Photos, COR
checkpoint-status |  |  | checkpoint | 1.2 - Milling Existing AC
label | 4dc67849-b8a1-5b65-bc5e-54f8aaeac922 |  | note | ACTION (Hold, Monitor, Witness) - M
label | b51d0aab-aa44-5dc4-9af2-25031329b373 |  | note | Detail - Milling undertaken to correct depth of 50mm ±5mm nominal thickness
label | ea25c596-38b4-57b3-8f8a-cf17d8b68f11 |  | note | Frequency - During operation
label | 02d59097-f7cd-58c8-9d09-9cc7334a8601 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Dip checks
label | dd200693-df6d-5e07-8c09-25fa8fb7ecfe |  | note | Conformance Criteria - Design Report, depth of milling confirmed by CPS
label | 0c35b98f-6820-514a-bd59-86d6928e7838 |  | note | Records - QA Records, Photos
checkpoint-status |  |  | checkpoint | 1.3 - Waterproofing Exposed Layer
label | 039256cb-f33e-54cc-a77f-606b4bad7bac |  | note | ACTION (Hold, Monitor, Witness) - M
label | f8c3518f-cbe8-5aa9-a10c-d48dd6d5f98f |  | note | Detail - Exposed Basecourse waterproofed / levelled
label | d8a9ecac-d131-5894-a9ce-aa111d36e463 |  | note | Frequency - Post milling, before asphalt
label | 76395e77-537d-58bd-b258-10b4e91215d9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 2d5faa86-2eb1-541b-85e8-2282c54fec88 |  | note | Conformance Criteria -
label | 8ba4302e-0d01-5735-92b2-454be6fef092 |  | note | Records - QA Records, Photos
checkpoint-group |  |  | section | 2 - Material Compliance
checkpoint-status |  |  | checkpoint | 2.1 - Binder Penetration Grade
label | 5aa3e481-84bd-592c-ba00-1b944b5622a2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ea5ea0ac-e4a5-5369-9b92-ea4d44a251c3 |  | note | Detail - To comply with NZTA M01: 2020 - Table 6.1 and TNZ P11: 2007 - Table 5.2 Lab Mix
label | d12bbd47-e97e-568c-be51-8920f9d6d9a2 |  | note | Frequency - Prior to commencement
label | 5e92a0d7-19d8-5f3c-b42d-31663e067f48 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | 14b1ded4-c378-586f-8d42-0fbc99471c56 |  | note | Conformance Criteria - NZTA M01: 2020 - Table 6.1 TNZ P11: 2007 - Table 5.2 Lab Mix Design Volumetric and Physical requirements
label | 21c96e78-fd28-510e-89a0-058061c93a33 |  | note | Records - IANZ Report
checkpoint-status |  |  | checkpoint | 2.2 - Coarse Aggregate Source
label | 77d9a518-4e51-55f4-b752-39b99dbb72f1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0c2c20bf-a395-560d-aab6-0db8b8f3d016 |  | note | Detail - To comply with TNZ P11: 2007
label | 8bb7e16c-45e9-5adb-b42b-232d8915c114 |  | note | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
label | 876a5cc3-809a-58f3-8999-5ab4d350ac32 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | 88fe4985-4c75-5c1a-af51-d584abd9c05c |  | note | Conformance Criteria - 230kN minimum Crushing Resistance, AA or BA Weathering Quality Index
label | 277234d7-d7c3-543e-95c0-09e0e4fae9b5 |  | note | Records - IANZ Report
checkpoint-status |  |  | checkpoint | 2.3 - Coarse Aggregate Production
label | 32e4718e-2ca3-5a51-ba72-ce315d459553 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d073c1f3-abe9-538a-9ade-2f8f8c12bd59 |  | note | Detail - To comply with SPC-21711902a-PVT-PV3006-H-01 + TNZ P11:2007 and RPT-21711902a-PVT-PV310-H01
label | 89760bec-b341-5210-b1ab-41dd1c331f2c |  | note | Frequency - Prior to commencement
label | d63a7974-8670-58da-b222-8183a46c2bd7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | af7c9e60-9692-5588-af5a-56f80baf0868 |  | note | Conformance Criteria - PSV: ≥ 58. (At least 85% by mass of minimum PSV) Table 3.13 for various sites
label | 354409f5-6d3c-5b11-8bb3-68227fc468a6 |  | note | Records - IANZ Report
checkpoint-status |  |  | checkpoint | 2.4 - Fine Aggregate Source
label | 0e99430c-be38-5b5c-95b5-3f1853e8d410 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 57515e84-bec6-5fd7-bd91-23eab047e8e7 |  | note | Detail - To comply with TNZ P11: 2007
label | bea7d6cb-fc75-56fa-9bb2-9662e1daeac5 |  | note | Frequency - 1/10,000m³ or 1/annum whichever is least. (RNZ 9805:2009)
label | 59af343b-5c2b-5bba-a6ee-8a58150d9f1a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | a6673a07-edcd-5f04-a743-e80b45b713a0 |  | note | Conformance Criteria - 130kN minimum Crushing Resistance
label | 221522fd-3edc-502f-a4e9-ba3d7f9e2fb7 |  | note | Records - IANZ Report
checkpoint-status |  |  | checkpoint | 2.5 - Blended Coarse Aggregate Production
label | b453b16b-8f9f-5837-b2be-3c9ce670a20d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9db91e05-3e9c-5a3b-9330-2e5a93e148d9 |  | note | Detail - To comply with TNZ P11: 2007
label | ef4d5b3f-7801-5250-83ed-b32d885acb41 |  | note | Frequency - 1/500m³ (Section6 of RNZ 9805:2009)
label | e05ed9cd-1dac-5438-aaa0-183867640e34 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | 689f9682-88f8-557a-9dda-c696defeac6a |  | note | Conformance Criteria - 2.25 Max Particle Shape
label | cd3e9658-6798-596d-af4a-9d53f969e0e3 |  | note | ○ 98% Broken Faces
label | 3887d104-f285-5a8b-93a3-c300f94e8743 |  | note | ○ Report Value - 5 minimum Cleanness Value
label | 13661301-2f5b-5c6b-900e-2452bfdc29e4 |  | note | Records - IANZ Report
checkpoint-status |  |  | checkpoint | 2.6 - Asphalt Mix Design
label | d75aa424-d085-5ae6-90c6-d73c044d1ec0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | fc7ca3c4-bd18-54c9-9310-18723992137f |  | note | Detail - Mix Design approved including peer review to comply with TNZ P11: 2007
label | ff2b588b-f229-57f5-b8e7-3400009a07b3 |  | note | Frequency - 10 days minimum prior to paving
label | c2659c6a-7e5e-58af-8a65-3486c32876b4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 9047101d-c58b-5701-a04b-506067af0458 |  | note | Conformance Criteria - TNZ P11: 2007 Table 5.1 Mix Envelop & 5.2 Lab Mix Design Volumetric and Physical requirements
label | f070fe00-1eda-53df-b073-27c30a861061 |  | note | Records - IANZ Report, Mix Design
checkpoint-group |  |  | section | 3 - Construction
checkpoint-status |  |  | checkpoint | 3.1 - Survey Setout - Paving
label | c7ee423e-e9f6-5f32-b18c-183b993bc79a |  | note | ACTION (Hold, Monitor, Witness) - W
label | d048bb33-fdf6-5d05-8e39-3ed3c94d4214 |  | note | Detail - Determine paving run start/stop locations
label | 38014465-bc27-52d5-b591-adad74ffcf7b |  | note | Frequency - Prior to commencement
label | 9081a92c-89cc-58bc-8d26-2984d07fae0b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
label | 9aec2b6f-1a3a-597e-9dca-e112c90b4477 |  | note | Conformance Criteria - Ensure accurate survey setting out is in place.
label | 9281ffe8-3e6a-510a-959d-ed825e9a9afd |  | note | Records - Survey Record
checkpoint-status |  |  | checkpoint | 3.2 - Weather Check
label | 7b509b82-c3df-5430-8602-de7763a80d45 |  | note | ACTION (Hold, Monitor, Witness) - W
label | eca038b6-61d4-56e5-a4d7-bbaf562ab0e6 |  | note | Detail - Ensure weather conditions are acceptable for work to proceed
label | fc2ed29f-0bbe-5d72-bd85-6ced7ebd93dc |  | note | Frequency - Prior to commencement
label | efb6aedd-b033-5bf1-84fa-c775a0ba17a6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Weather Forecast
label | d0dd1508-c956-50fc-8fd9-6bef159aa6f1 |  | note | Conformance Criteria - Not foggy or raining or wet surface. Base Temp ≥ 7ºC (25 – 75mm layers)
label | 0e491b82-b99a-5df4-9670-ce8df7ff76fd |  | note | Records - Forecast Records, QA Records
checkpoint-status |  |  | checkpoint | 3.3 - Surface Preparation
label | f8839a99-e277-548c-847f-547fbb084818 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4e9c65ae-94c4-5376-a112-0e8f6ec4bd34 |  | note | Detail - Ensure previous layer is broomed clean.
label | 3b8f844e-479d-5e75-ae4f-b3d69e0f0d1c |  | note | Frequency - Prior to commencement
label | 08b850fb-343f-5ecb-8f66-85ec31c55820 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 6548f8c4-c3a2-5f12-af89-8afeee21c140 |  | note | Conformance Criteria - Truck broom to have been used and surface approved by CPS Engineer
label | d94a0a6f-b5fd-5450-b754-27575a915d62 |  | note | Records - QA Records, COR
checkpoint-status |  |  | checkpoint | 3.4 - Tack Coat
label | 61e99cce-bbed-5713-b59e-556837dddaf0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | de96aae3-fa74-5321-b644-152adf7f0cc6 |  | note | Detail - Apply tack coat
label | f1e82e9c-9921-5fc0-987b-a3e4b94f61c1 |  | note | Frequency - Prior to asphalt
label | 65c166ff-da05-5192-a3be-d745c0bd3b09 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Spray sheet, QA records
label | dfdfa26e-31c2-5362-a2cd-01b22ab5fef2 |  | note | Conformance Criteria - TNZ M/10 2020 - Section 9.3.1
label | fdd832de-a714-5dc5-a3eb-86e8a3680632 |  | note | Records - Spray sheet, QA records
checkpoint-status |  |  | checkpoint | 3.5 - Production Property Test - Grading
label | 460b1db4-451c-52d0-a8d5-64c6598c86ea |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3b47d7c4-1ab0-5743-97a0-bad139d2db17 |  | note | Detail - To comply with SPC-2171902a-PVT-PV3006-H-01
label | 5ed5061c-9a5c-574d-ad1a-7cee4ee59e11 |  | note | Frequency - 1/>30mimutes production run and 2/>5 hours production run
label | 69188654-6cdf-5801-b103-4e91f57b3c0c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | 40405b4f-f7c8-5799-9c04-9b8ae7bdd815 |  | note | Conformance Criteria - Approved JMF + Table 7.1 - Mix Control Tolerance Note: ±0.4% rolling ave of four
label | d927f8d2-c27b-5d38-949f-f95d2d247769 |  | note | Records - IANZ Report, QA Records
checkpoint-status |  |  | checkpoint | 3.6 - Production Property Test - Binder Content
label | 1b217baf-8640-5742-921b-1c62f796a86a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9315ba01-b05b-5934-9195-294fa842c24a |  | note | Detail - To comply with SPC-2171902a-PVT-PV3006-H-01
label | 7785ef8b-c4be-58e6-bd82-3ccd5f785a51 |  | note | Frequency - 1/>30mimutes production run and 2/>5 hours production run
label | 01fc5ef8-7080-5254-9cd7-4c105a763d6e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | 93a201a6-5879-5ecb-a0c9-73fdf47c6611 |  | note | Conformance Criteria - Approved JMF + Table 7.1 - Mix Control Tolerance Note: ±0.4% rolling ave of four
label | 772cb7a2-982e-584a-9cae-d20a142abbdf |  | note | Records - IANZ Report, QA Records
checkpoint-status |  |  | checkpoint | 3.7 - Production Property Test - Maximum Specific Gravity
label | 9f4aff70-cb52-549f-b15c-729c99910425 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 09a98b0c-d2d0-5a6c-9d32-38932ae6ca70 |  | note | Detail - To comply with TNZ TM6002:2006
label | f7041634-f276-57bb-9336-7dd37bf3e112 |  | note | Frequency - 1/>30mimutes production run and 2/>5 hours production run
label | b69e76b1-a03f-53c0-a0a5-ba95fe060831 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Property Test
label | 6c26b0d8-a29a-5697-b2b5-39e220600720 |  | note | Conformance Criteria - TNZ TM6002:2006 Report Value
label | 3e0a5524-83d2-5e17-8e02-2ed048084278 |  | note | Records - IANZ Report, QA Records
checkpoint-status |  |  | checkpoint | 3.8 - Production Property Test - Avg Temperature
label | 7285886a-23c7-5b06-8019-341f7d9f2549 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 071cf91d-0303-599f-8614-2eea761c2604 |  | note | Detail - Check temperature of Asphalt for every truck entering the paver.
label | ad454e0f-28d1-58e8-ae3b-084911c8619f |  | note | Frequency - Any truck load
label | 482f5eb4-6cb6-5017-9ae6-593105364fd1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Temperature Check
label | f1624867-e727-57f1-9ca8-bc089b67f30e |  | note | Conformance Criteria - TNZ P11: 2007
label | ecb1893f-5395-5832-9697-820727c0a134 |  | note | ○ ±10 oC from recommended mixing temperature
label | dbc24c32-dd06-5fee-9497-482c322b1588 |  | note | Records - IANZ Report, QA Records
checkpoint-status |  |  | checkpoint | 3.9 - Asphalt Construction - Layer Thickness
label | 6cfaba1f-3e66-555f-81ce-0e2fc6792d5b |  | note | ACTION (Hold, Monitor, Witness) - M
label | 585f5061-23e6-51cb-bca4-0b20dafd395d |  | note | Detail - Ensure asphalt is laid at correct thickness of 50mm to comply with SPC-2171902a-PVT-PV3006-H-01.
label | 45dac390-6fe2-553b-ac9b-8269f239aad8 |  | note | Frequency - During paving operation
label | 81e6e95a-984a-574b-849f-3504a363d89f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 70f7684d-2449-52e2-9cda-4b27a63954bc |  | note | Conformance Criteria - ±5mm nominal thickness as shown in the Drawings, Plans and/or Specifications
label | b3f69ae2-8794-5ce5-8765-ac832f2fc42a |  | note | Records - IANZ Report, QA Records
checkpoint-status |  |  | checkpoint | 3.1 - Asphalt Construction - Surface Shape
label | 1e4be2b2-893c-56e7-9614-72c8febcd205 |  | note | ACTION (Hold, Monitor, Witness) - M
label | cea514f0-ba0a-5a12-ac4a-ff1c545dd3ed |  | note | Detail - Ensure asphalt is laid to correct shape to comply with SPC-2171902a-PVT-PV3006-H-01.
label | 2ab70f32-be8d-5b54-b588-66479e6a9217 |  | note | Frequency - During paving operation
label | 546ad15e-ca84-5a41-a134-3b42d0a2793e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - 5m straight edge
label | 09c0133d-5215-5d74-ab8c-bf4668ee3d50 |  | note | Conformance Criteria - SPC-2171902a-PVT-PV3006-H-01.
label | 9b20401c-7f25-5d12-bc7d-aa26c24e0c22 |  | note | ○ ≤5mm (Visual Inspection)
label | 54f3d20b-c13a-5a2b-8f46-f4c90e4106f8 |  | note | Records - QA Records
checkpoint-status |  |  | checkpoint | 3.11 - Asphalt Construction - Surface Texture
label | 8ad24679-0c9c-5e0f-9d09-d1034ce5df3b |  | note | ACTION (Hold, Monitor, Witness) - M
label | a3279356-20ae-54f5-abd5-cbd4114c181d |  | note | Detail - To comply with NZTA M10: 2023
label | fe225e84-b5e9-58a2-8da9-3f93e84440b2 |  | note | Frequency - Every 10 metres
label | 031bf56b-4f26-5ba8-af09-4a2ce482aace |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Laser Profilometer
label | ea40e03e-8111-5aa2-9534-1a41850f0d58 |  | note | Conformance Criteria - NZTA M10: 2023 Table 3
label | 4e2d037e-57a1-5ab4-b01e-6cd696e847f8 |  | note | Records - IANZ Report, QA Records
checkpoint-status |  |  | checkpoint | 3.12 - Asphalt Construction - Compaction
label | 9c3cbf70-c9f4-5fca-aff2-e0f663181a94 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a0c28b5a-6321-5940-9113-395c06e3841e |  | note | Detail - To comply with NZTA M10: 2023
label | 1cbbd1be-4191-56ae-9f3b-62035bbf9580 |  | note | Frequency - One test per 50m2
label | 1d012bbb-6c57-58c6-97ce-731d2bcb9b55 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM for Quality Control Only
label | 49aa3f1f-f1c4-5ee9-b4d6-8db005a3e3a3 |  | note | Conformance Criteria - NZTA M/10: 2020 - section 9.9.3
label | b32916b0-aa67-5421-a675-62a7288764e1 |  | note | Records - IANZ Report, QA Records
checkpoint-status |  |  | checkpoint | 3.13 - Ride quality
label | 4c56552a-b278-5bf6-ac67-3d89353d8886 |  | note | ACTION (Hold, Monitor, Witness) - M
label | df688d69-3d61-55a2-8a07-5f0b68fe0038 |  | note | Detail - Upon 100% completion of OGPA layer and at expiry of defects liability period
label | a0020189-3bd1-5874-99c4-0c5c3a733952 |  | note | Frequency - Prior to Opening to Traffic
label | acfabbe7-930e-5123-b8a0-5547a8ca41b1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NAASRA
label | 61e7df59-39e5-5267-954b-7051e4659e86 |  | note | Conformance Criteria - 10. Appendices to Principal's Requirement: 50 NAASRA count as a 95%tile for every 100m rolling section
label | efd6a033-fb1d-5300-af67-de15267f4fbf |  | note | Records - IANZ Report, QA Records
checkpoint-status |  |  | checkpoint | 3.14 - Surface finish visual inspection
label | 275baf9c-ba1c-58ea-9782-b31e6ab8fc72 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 76ac8f13-0a6c-555a-b4dc-b97c0b80f10a |  | note | Detail - Site walk over
label | 00b0b2cc-fdde-5d88-b5df-6abc93dcb144 |  | note | Frequency - Post Construction
label | 841ab86d-af8b-5e57-952a-56ad7440fa92 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | bd6ca1c9-d1e9-51fa-a621-4b0d0d42e874 |  | note | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
label | 4c8626cc-52a1-5dc3-ad27-d5be7f89754c |  | note | Records - QA Records, COR
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4 - Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 4.1 - Final Walkover (Snags)
label | c9fb9d67-ed81-5ed4-b221-a9fb396f8b71 |  | note | ACTION (Hold, Monitor, Witness) - H
label | df72ad0b-a682-5c8a-ad64-e59f77f521a0 |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | f77a8488-2e2c-5789-9d7d-ea718c4ee5cf |  | note | Frequency - At the completion of the Lot of work
label | 47f0a676-274d-5552-a003-dd7caf8af0a2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | 14dd018f-d376-53a6-9fea-ab165ef2b0e1 |  | note | Conformance Criteria - Completed report
label | 1d430b0b-f558-51c1-96ae-4bc039c62156 |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Survey As-builts
label | 892ca46f-8eae-540e-8bdd-1a144e23129e |  | note | ACTION (Hold, Monitor, Witness) - H
label | fe301b49-c8ec-51ee-a30d-c6a3018e6bd2 |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | 0e111037-d804-5a11-a283-6c256202e9da |  | note | ○ A survey as-built of completed work must be provided
label | 6e615034-34df-54fb-b6bc-86d9bf83d4f0 |  | note | Frequency - At the completion of the CWP of work
label | 1747552d-a5c9-54b4-9584-4ae1a00ccc21 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 86fc6063-ebe4-5a9d-b40c-98078203d58a |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | e281ea92-70c8-524d-b5cd-8ae6f8bc2d1a |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Quality Assurance Deliverables
label | 502b8a9c-d2fe-5102-adc6-3cf1adb98691 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f5835484-1943-59a5-82aa-9fd5e7d135cd |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | 7b84dfe1-fded-57a8-ac56-2eebb67f908b |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | fd74244b-b5c5-56e1-9990-fc4b81ff3c93 |  | note | Frequency - At the completion of the CWP
label | 35417a3c-39f2-57db-8fed-d59b4fd6cf71 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 35185a1c-995d-51ad-a0e7-c11a9d331cf4 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | d97d1df7-263c-5d1f-b3b2-7a575914ebde |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 4.4 - Final Approvals
label | d1e93a99-0ffb-5bc8-acc6-6829e48a6872 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 28e41e73-2310-57b7-b3b3-d469a6d060ad |  | note | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
label | 211dcfba-4e22-5804-9254-d36f4d7f509c |  | note | Frequency - At the completion of the CWP
label | d772f37d-07d0-50bb-b465-6af7182dd533 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 2ed54d51-0bc2-5b90-85ae-5592662976cf |  | note | Conformance Criteria - Ensure all parties have signed and approved ITP
label | 42446ec0-d601-5d93-8a77-55642f34c129 |  | note | Records - Signatures
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - E1401A - Captain's Culvert Inlet Remediation - Master ITP | itp |  |  |  | Yes | ITP - E1401A - Captain's Culvert Inlet Remediation - Master ITP V2 | 0fb9dcb8-e398-4018-a935-65ebe47e4c8d
checkpoint-group |  |  | section | Master ITP
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 45a7ccc8-e61d-549f-8435-0bea0ee8046a |  | textbox | CPS Eng.
text | a13a82e2-0df4-5be7-bee5-d69fd66c5ed6 |  | textbox | Engineer
text | c40e70d9-166d-5e14-825f-753d2c701b14 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Debris Clearance
label | 34a13748-e9dd-5aec-8529-a7af52c5958c |  | note | ACTION (Hold, Monitor, Witness) - H
label | b0cac6cb-db32-5c11-9c04-1d4d87147de2 |  | note | Detail - Need to inspected by the engineer to determine whether rip rap reinforcing is required around the inlet.
label | 53d2a460-a098-571a-9018-319a9fe8b356 |  | note | Frequency - After clearing debris
label | e17b2271-9c8f-5568-a32d-e0194d7cfb33 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 0065ae33-7499-591b-9ad1-ea14aafadabe |  | note | Conformance Criteria - Confirmation from the Engineer
label | f9e9b8ea-3244-5bfe-87aa-4cc9077c4b0f |  | note | Records - Site visits, emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Stream and Bank Regrade
label | 3db1529c-5502-53c7-89ca-4b8593b40c74 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ceaf7680-c884-5f9d-9712-07fa4ae8da5f |  | note | Detail - Location and extent of bund is to be confirmed on-site with the engineer.
label | 91f55be9-565b-5e2b-a4cb-71b3b192b7a9 |  | note | Frequency - After clearing debris
label | a4b29d48-debf-5806-a3ae-cd555777f84c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 1dd1de15-2bd9-50f4-be1c-6315b95a4f61 |  | note | Conformance Criteria - Confirmation from the Engineer
label | e76f5034-3e14-5c26-874e-3568bb414d3f |  | note | Records - Site visits,Photos emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Stream training
label | ad3be08b-f60f-5d73-8c25-831576cf9f00 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e09c1d36-cdc7-5374-90a7-7a00a6458f68 |  | note | Detail - Stream training is required at the mouth of the gorge with the extent to be confirmed onsite with the engineer.
label | 24011bd8-ac24-579e-9f11-299401e9fa11 |  | note | Frequency - After clearing debris
label | f00a3093-db58-5a2c-a070-7860fd62523c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 2d278b0b-50e2-5944-aa25-0a20bc4bd2e0 |  | note | Conformance Criteria - Confirmation from the Engineer
label | d1e511f1-c589-5627-91bf-42d6aacd3ea1 |  | note | Records - Site visits, emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Gabion basket installation
label | f3306661-b424-5bc0-a9f5-26859b912fc7 |  | note | ACTION (Hold, Monitor, Witness) -
label | 4322dedb-e00f-5081-b746-53dafa4fba06 |  | note | Detail - separate ITP provided
label | 8dfeec16-2c05-5cec-ac6c-0cfd8ae47012 |  | note | Frequency -
label | 8dfc4d70-0f77-51f2-98bd-371de36c2a78 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | 13d545da-5c39-5fbb-b4a1-b24b5cda390f |  | note | Conformance Criteria -
label | d51cb77f-eeaa-59d1-886a-5bb1c3a8ce54 |  | note | Records -
checkpoint-status |  |  | checkpoint | 5 - Rock Armourt installation
label | 8f9b3a8f-1b95-5744-870d-3d0891788598 |  | note | ACTION (Hold, Monitor, Witness) -
label | 5cfd2908-c6b3-5c66-9918-9febcddab383 |  | note | Detail - separate ITP provided
label | 69fcd58f-0aa4-5e51-811c-f0a6217f0c7e |  | note | Frequency -
label | 8d74b5a5-84e5-5c09-9b8c-2da113568787 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | e744d34d-b824-5a97-b378-d3c4fe327ff1 |  | note | Conformance Criteria -
label | d11308c6-4a15-593d-8278-3a5362c66e05 |  | note | Records -
checkpoint-status |  |  | checkpoint | 6 - Subsoil Drain
label | dbce5a0c-8afb-5ec4-9cc0-9e73b64b20b8 |  | note | ACTION (Hold, Monitor, Witness) -
label | f086a508-53c0-569c-a844-1ae6550120cf |  | note | Detail - separate ITP provided
label | 8d3b951e-3093-50ae-b1b7-9521c4cfe67b |  | note | Frequency -
label | 834e62f6-8567-5d65-a133-bbb27ae0996c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | 773af2ca-74cc-55d9-aa13-2d19b6927962 |  | note | Conformance Criteria -
label | f588f401-3bbe-5d22-8bf6-e3e8ae629b3d |  | note | Records -
checkpoint-status |  |  | checkpoint | 7 - Parking bay construction
label | e9a88361-1958-5b9b-aee2-7da9756c7f6c |  | note | ACTION (Hold, Monitor, Witness) -
label | 2d48dcce-af3d-5dc0-9ae6-220724e56ccd |  | note | Detail - separate ITP provided
label | eae8a39c-8eb7-5bf0-8e2b-209a79231a42 |  | note | Frequency -
label | a8010d11-9a07-5945-af4a-3364d70fbcc7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | 9c90cd21-674d-5dcf-8509-9e015fe623e8 |  | note | Conformance Criteria -
label | 1849c986-8d46-5dc4-a8f0-4823de2b47fb |  | note | Records -
checkpoint-status |  |  | checkpoint | 8 - Kerb and Channel
label | c919f4eb-1865-52d7-ac18-c43bac6d60ff |  | note | ACTION (Hold, Monitor, Witness) -
label | ab6a7419-90ff-5f08-a0c5-0b4b3b3514da |  | note | Detail - separate ITP provided
label | 047b0d76-826a-5f88-9c11-31b311ba5df1 |  | note | Frequency -
label | f7be5fe0-7516-56d3-9c74-82a7137114c2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | f7857ebf-34f6-5f78-989b-71a572f041f6 |  | note | Conformance Criteria -
label | f12b247d-fec9-5632-8f80-b0eec7ed40ad |  | note | Records -
checkpoint-status |  |  | checkpoint | 9 - GuardRail
label | 491578a8-d276-5757-9b71-f2e08c266ea8 |  | note | ACTION (Hold, Monitor, Witness) -
label | b42ff3ce-92f2-516d-8e28-fda0423d2bc0 |  | note | Detail - separate ITP provided
label | e6a32fa4-8156-5337-874c-67d2de2fe214 |  | note | Frequency -
label | bda2f8d0-0c58-58b2-9a75-d9bc8d8aa459 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review -
label | 2f53dc5d-55fc-5e59-a342-d6fac4a4f33c |  | note | Conformance Criteria -
label | 56199acb-f451-5149-9f19-68d9deb08d6c |  | note | Records -
checkpoint-status |  |  | checkpoint | 10 - Swale Inspection
label | 58427056-b1c9-53cc-8252-fc3ac1322b25 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2c85c73d-40a6-5b9e-ba14-6fe08f888c5d |  | note | Detail - The Engineer needs to inspect and adjust the transition and swale if needed.
label | 3b969a28-2e3a-5c6f-97df-d8e398f18ae8 |  | note | Frequency - Once the swale is set out.
label | 96b02e05-c5d5-53ce-a910-376a1f9927b7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 33b542f6-8179-50cb-9b16-9fed5ae2aba1 |  | note | Conformance Criteria - Engineer acceptance
label | f6ff9854-0160-54f8-a197-6ecf150c644b |  | note | Records - Site visits, emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Berm Demolising
label | f63ef5a4-4981-551d-93d0-865e678bc212 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f9e8d03f-6361-5abc-ab4e-3429c64dff48 |  | note | Detail - Final inspection to be done before berm demolision
label | 0966a4a2-a3f8-59f5-8e4d-1bd4e4ae869e |  | note | Frequency - Before Diverting back the River
label | 415febc2-d024-5d0d-b909-56cbffa84e46 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 32582daa-5490-58bd-9430-1379218e8636 |  | note | Conformance Criteria - Engineer acceptance
label | 10710ceb-3e27-5866-a9b3-f51294bde6bc |  | note | Records - Site visits, emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Planting Process
label | 88bddaa5-f0e5-5e1d-b0f9-9670a9ef730f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 31ae583e-7788-54fd-9eb4-a9cbc5342828 |  | note | Detail - The Engineer shall be notified of any key stages throughout the planting process and afforded the opportunity to inspect and adjust as necessary.
label | 4cb43045-4cda-5f40-b09c-d38faadbf05d |  | note | Frequency - During planting
label | d78f73a2-b03b-5402-a6a2-74ba5b048caa |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | f6935acb-2c6b-5075-868d-b82c7a9aefec |  | note | Conformance Criteria - Engineer acceptance
label | 128af767-6a43-598a-b706-0a814d5d9fbb |  | note | Records - Site visits, emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 13 - Final Walkover (Snags)
label | ac506f7a-c09e-5d42-b8cb-99db25075e56 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d55501f9-002f-5288-aac5-736fdde3d96d |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | 66451397-1198-5a56-a429-d1b189b62343 |  | note | Frequency - At the completion of the Lot of work
label | d30b7d07-baba-512a-a4c3-0d0bc5833df5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | 3865c2f9-4239-50a5-8357-9031551568a6 |  | note | Conformance Criteria - Completed report
label | f08ad7a9-a41b-53c8-818c-3bd940022a1f |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Survey As-builts
label | 7bacf22e-e052-54ee-86d5-08feb7b1e49f |  | note | ACTION (Hold, Monitor, Witness) - H
label | af013ef9-f970-5c7a-9936-9a7455ff8887 |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | 87f683e1-f808-506c-9291-c002a7f6cd96 |  | note | ○ A survey as-built of completed work must be provided
label | 7651c91d-6e6a-5ea2-b009-27b7ce3e5ba8 |  | note | Frequency - At the completion of the CWP of work
label | ff1bb492-ec96-59f6-a8ba-cfd7f1c96018 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 2f87e3a4-7e5d-5056-a9e8-273f520e431f |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated
label | 40f02686-eee3-5af3-9282-c9c31a4e5d90 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 15 - Quality Assurance Deliverables
label | f3894fda-17bb-5aca-b4d8-4d79b9a28722 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3eda4559-5a0f-54b4-815a-71c2c89497b4 |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | 990cc14a-7e38-5fe4-a7cf-d23bde764fa4 |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | 7c839158-0c67-56cb-ad43-34e431040a77 |  | note | Frequency - At the completion of the CWP
label | c3eb1ad8-5c89-5917-a846-72c76eeed2a9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 68eb9c51-618f-53fb-b1d5-cc83fe6a848d |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 57d559f2-69c2-550c-8abf-a265b16543ea |  | note | Records - As-builts, NCR's and RFI's
checklist-sectioned |  |  | checklist | ITP - B1004F - Tangoio Falls Steep Underslip - Kerb & Channel | itp |  |  |  | Yes | ITP - B1004F - Tangoio Falls Steep Underslip - Kerb & Channel V2 | 0fc5c6f1-0c06-4185-bc2b-075e2b9573c7
checkpoint-group |  |  | section | Kerb & Channel
checkpoint-status |  |  | checkpoint | Project Site reps.
text | dbb22b29-9e52-5acf-9668-ea63d148f258 |  | textbox | CPS Eng.
text | 9d599114-ef0c-5e22-904d-6acd5b11a4d3 |  | textbox | Site Engineer
text | 882dbeed-d21f-5283-8388-9e51f3d55706 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | b5b45492-7e8d-5ec8-b13e-cd2cfe8838a2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 55b6b305-2d61-5360-9fde-77e46cc8920d |  | note | Detail - Set out kerb line and level at 1m offset to EOS
label | eac8e00b-c49f-5f5c-982b-59c6e8378387 |  | note | Frequency - Prior to commencement
label | 231d2ea0-f29c-510f-b813-bd558d3e9600 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Measurement and Visual inspection
label | 97ce3e3c-3d7c-5c96-a9fd-39c41fd98ec7 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | cac702a4-4712-5a67-bd63-af9cdfc43c04 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Material Compliance
label | ba3592bb-7dfc-5284-be97-21129fa188fe |  | note | ACTION (Hold, Monitor, Witness) - H
label | c2a60710-998d-5c26-8982-00eaebbe5da5 |  | note | Detail - Ensure the Concrete Mix is as per the Kerbing Specification
label | ae16e2b8-2331-5217-9972-2be6f6c26f03 |  | note | Frequency - 1/600m3, minimum of 1 per source
label | 7b4508f1-fa96-5c34-a070-d0fce1322353 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Lab Testing
label | 73fddc50-8101-5051-ad47-768773400e94 |  | note | Conformance Criteria - 20MPa at 28 days
label | 1980bb65-7a1c-51ed-9ca7-517d9465cf5c |  | note | Records - Concrete Delivery Dockets and lab test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Material Compliance
label | ff76586d-1cc5-59e6-b287-082879e1c622 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9a91e578-6a3e-5e7e-83c0-5fea3b7f0074 |  | note | Detail - Ensure the slip form moulds match the dimensions of the design kerb
label | d55f1b74-8135-5ddf-9c68-16dc7684b615 |  | note | Frequency - Prior to commencement
label | 547ed728-5859-5215-81c2-708522861169 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | 15d6622f-ef33-5e85-b4ac-84b7cb33b755 |  | note | Conformance Criteria - Measurements match the design kerb dimensions
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Kerb Foundation
label | 2bee1d83-9dcd-5575-8fbd-637335794dd9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 971c0d65-b7ae-5969-b3aa-094eb6dc6ed4 |  | note | Detail - Ensure Sub base construction is completed
label | 53439be2-3d2f-555c-86f5-a076a5de6fcc |  | note | Frequency - Prior to commencement
label | 6dd3559b-cf62-5b50-86fb-c643f2b523a3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | f6d949e9-a0c0-5269-9f5b-300b85153883 |  | note | Conformance Criteria - Pavement depth and type under the kerb varies depending on location
label | 794abf86-015d-5ea3-8de0-4b8f3445564d |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Stringing
label | e90bc948-64fc-5c65-a7e4-5a784dae3aa2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1420e126-5fb9-5d97-86ed-94344e05bfaf |  | note | Detail - Check weather forecast and avoid adverse conditions
label | d4301282-d9ac-519d-91e1-e99d71a0b281 |  | note | Frequency - Prior to commencement
label | e49b1cd0-4efa-544f-8c41-54709730972f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 6f5cd9f2-f89a-5d7f-b062-19166f446211 |  | note | Conformance Criteria - No concrete to be placed in adverse weather conditions
label | b4e61546-fc1b-5503-af55-75853a5413e5 |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint-status |  |  | checkpoint | 6 - Stringing
label | eb44be04-1902-52fe-a1c6-b4c58e1e756f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 17fc42bf-be91-53f8-87c6-b67e830c1701 |  | note | Detail - Kerbing Subcontractor to set out steel pins and string line to design levels and identify catchpit locations
label | 34f5c519-e05d-58dd-b28e-a1800a24f325 |  | note | Frequency - Prior to commencement
label | ab096e13-1826-5cc4-b5b7-e89b36025a2c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | 575b2961-bae0-58ef-b6e8-0caa5b7b13dc |  | note | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
label | 005c20ad-efdc-56c3-8f7b-27f7e3790b40 |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint-status |  |  | checkpoint | 7 - Stringing
label | 413812ba-a609-529c-926d-072dd442ec6b |  | note | ACTION (Hold, Monitor, Witness) - W
label | 59113092-3879-5449-a1d0-c3c41ca3528e |  | note | Detail - Subcontractor String line to be checked by Site Engineer to ensure Horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits.
label | e8c33dda-2a2b-502c-8f53-3906c40bda3d |  | note | Frequency - Prior to commencement
label | a16f566c-04b2-5f89-adc0-1d63d40573eb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | fcf66c9c-02b4-5bb1-a8e2-58ad8185fe57 |  | note | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
label | f0c4dbc2-dbc5-556f-8862-41d9354306a1 |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint-status |  |  | checkpoint | 8 - Slip forming
label | bb678dac-2e52-56fd-864e-bf230ea6159c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9daa5f3c-4ba5-5a28-9f87-6d7519e81f8a |  | note | Detail - Check correct Kerb & Channel profile is installed onto kerb Machine
label | 99d2be85-5d39-5a35-ae37-7bc49a37d840 |  | note | Frequency - Prior to slip forming
label | 9354c0d1-3dc1-555f-af40-7417720250f6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | a403a226-c195-5ddf-84f0-566be878fdbe |  | note | Conformance Criteria - To ensure the correct kerb types are installed at the correct locations
label | 915e5cff-4f92-591c-8ce4-646acd44b06e |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint-status |  |  | checkpoint | 9 - Slip forming
label | e0233fbe-982a-5989-9022-e69aed7b7ea2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0c62eefb-323c-55bd-8b67-d88ea2450549 |  | note | Detail - Kerbing Subcontractor to order concrete as per design Mix and to ensure the concrete is tested
label | ffcc5d0f-c155-5bc0-9c68-79e256d88690 |  | note | Frequency - During Slip forming
label | c1361e91-a2f6-58f0-a8fb-4818d4febfe0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 01a16861-b4b4-5241-bf40-353bdb1afc29 |  | note | Conformance Criteria - To ensure the correct concrete mix is delivered
label | 990d7f01-65ae-5115-add9-5f490acf5960 |  | note | Records - Concrete Delivery Dockets and lab test results
checkpoint-status |  |  | checkpoint | 10 - Slip forming
label | 71c7077e-f508-5c48-95c2-13a08829034b |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6c18ddba-b330-5c65-a792-52dd887e4fc3 |  | note | Detail - Expansion joints to be formed at 5m centres
label | d99c9dd4-50ff-5566-883f-5fb0fda39aaa |  | note | Frequency - During Slip forming
label | 7773ed64-1214-5256-87e3-dea6d13542ce |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | c758e18f-de23-52fa-8d7d-707d20ab68d6 |  | note | Conformance Criteria - Kerbing Specification
label | 28b1d204-4822-5d58-b10d-2defe0f57e95 |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint-status |  |  | checkpoint | 11 - Tie-in with pre-cast components
label | e8406d51-cf57-5b72-b71b-08878102427e |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5e3118f4-f13f-546d-a931-7aa01354aae7 |  | note | Detail - Subcontractor to ensure Slip form Kerb & channel to be cut and tied-in with pre-cast components.
label | 8b7820d2-b64d-51eb-bc1e-bdb47ce73fd7 |  | note | Frequency - During Slip forming
label | 32db712d-1b20-55e3-9f87-f53f9300b5aa |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | dde7d952-1800-5ae7-acc0-177f4679f813 |  | note | Conformance Criteria - Consistency with Work Instruction
label | 57ebc59e-252f-5586-9c27-32932835f70b |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint-status |  |  | checkpoint | 12 - Protection
label | 2d02e9a1-0399-59fc-9bfd-c434e568b5ed |  | note | ACTION (Hold, Monitor, Witness) - W
label | 18bd6483-1a7c-5ac4-ad7e-964f3c9a95ee |  | note | Detail - Backfilling behind kerbs to commence only after a curing time of 72 hours
label | 80f3fca1-8c48-51fc-a0fd-d3a113847998 |  | note | Frequency - Prior to backfilling
label | 90ac1a8b-d2d7-5eda-ab6f-249c883ccf90 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | bc1d703c-f3b6-5624-b8a8-b17be3a9d833 |  | note | Conformance Criteria - Backfilling to commence only after 72 hours
checkpoint-group |  |  | section | Post-Construction
checkpoint-status |  |  | checkpoint | 13 - Final Walkover (Snags)
label | 84242f67-1b4e-5376-ba5c-20f569da11cf |  | note | ACTION (Hold, Monitor, Witness) - H
label | b7078104-dd0f-5f9d-ba53-531ea0a99c52 |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | f8daacc7-7e59-5436-8a59-03ba728b6cae |  | note | Frequency - At the completion of the Lot of work
label | 119ea6d8-e7b7-54a2-bbd8-08b203b3a4b7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | f9c4d177-c341-5454-8621-d92d50f819d8 |  | note | Conformance Criteria - Completed report
label | b40a67a8-fb8d-5258-b66f-138d5fc41c52 |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Survey As-builts
label | c8ca1653-e55a-5ea5-90dc-3effc5f3f80f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 58149ac1-ba98-5c26-8397-9bc11b0f002a |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | 48a5af9c-9c88-54b6-a764-9fc2b66fe7d6 |  | note | ○ A survey as-built of completed work must be provided
label | c54cf4a5-ea53-5125-af4b-774540d22ff6 |  | note | Frequency - At the completion of the CWP of work
label | f64c3358-91eb-59f1-9a86-d5abf7180cbb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 23a928fa-633e-55a4-805b-999e00899e3b |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | b208d245-c1c4-58aa-b6e9-3d9547eeb0f4 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 15 - Quality Assurance Deliverables
label | 5b697eb5-9195-5448-b637-a49a816ac140 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a62d9604-3ca9-5d9f-9201-3e3aa75d6d27 |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | 4359709f-a866-538d-abd8-1b4d5fd50c2e |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | a9a9a2b8-a2fc-5010-bee9-72ed7b68259f |  | note | Frequency - At the completion of the CWP
label | b70daac8-0d4e-5d73-af63-531e82f0f7fa |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | c19c8a79-ec04-5897-81e9-491f7d701f3b |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 813bd9d3-57c6-5fbb-9c43-d10b06d33798 |  | note | Records - As-builts, NCR's and RFI's
checklist-sectioned |  |  | checklist | ITP - Mangahauini Bridge Scour - F3002H ID501 | itp |  |  |  | Yes | ITP - Mangahauini Bridge Scour - F3002H ID501 | 11e4bafe-5e72-4b7c-b205-8f6b9e52ca4e
checkpoint-group |  |  | section | Section 1: RECEIVING INSPECTIONS
checkpoint-status |  |  | checkpoint | Project Site reps.
text | bb8acee6-7ac1-5cbe-bec1-9cd5819e2760 |  | textbox | CPS Eng.
text | e57d3f40-0fb9-5508-926c-a46b4bbb0c56 |  | textbox | Site Engineer
text | f2c3d17f-5e91-5d26-a59e-b2642d34dacd |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Rock Armour
label | df0ecc16-1a4e-5489-8617-f5bc9bf6749a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 958bb8ea-8489-5c58-8d2d-9683bd4b5d2f |  | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | 845a8118-47c1-550c-8cb9-5d97e56e5dde |  | note | Frequency - Prior to commencement
label | f7b9b0ac-06ed-522d-8e3c-cd8aeb18662e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | bbc86290-706b-5e9e-b4bf-52deea0b0a3b |  | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall comply with Grading as per design (Rock Rip Rap Grading table) with a minimum specific Gravity SG of 2350kg/m3.
label | 55b0e522-b0e3-502e-862b-d08fd324e13f |  | note | Records - Material source test results, Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Class E A49 Geotextile
label | 69d584cc-0010-58a7-a822-4e55b7f941f4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f889611e-51e4-5c73-a1a9-38cb17b7a8a5 |  | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC, NZTA F/7
label | b2c4518c-f761-564a-a27d-dae357d48216 |  | note | Frequency - Prior to commencement
label | fd07b547-6b4a-5122-b274-182182f2c90c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | ef3e173b-0e75-5fee-966a-8b2aa7881d3c |  | note | Conformance Criteria - NZTA F/7 compliant before placing foundation material and engineered hardfill
label | bfbe614d-33b6-5c2a-9658-bfdba1eda367 |  | note | Records - Material certificate(s)
checkpoint-group |  |  | section | Section 2: IN PROGRESS INSPECTIONS (Buttress)
checkpoint-status |  |  | checkpoint | 2.1 - Survey Setout
label | 3f321a83-74cc-5182-bbe5-0dcb538339c6 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d01a25b2-ff2c-5f8a-8d17-2b1fd03fe5fd |  | note | Specification/Drawings Reference - Consistency with Construction Drawing
label | 195ff7b7-21aa-540f-8c69-9c77cf58a8e1 |  | note | Frequency - Prior to commencement
label | f59f2cbf-0267-5231-8d41-26c2bf92880e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | dbb0aee7-8743-5253-9d32-628f803cc277 |  | note | Conformance Criteria - Set out extents of fill and check against design drawings
label | de63e509-c45c-55e5-bc67-d0b84689a0ea |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | 1e362743-c9ed-52f6-a1ed-51f8280717f7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8354aea2-4248-5e47-a749-f03ac32af9e7 |  | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | 2851fd24-debb-5d31-8b7d-5af1f50e39ee |  | note | Frequency - Prior to commencement
label | ae6b7edc-31f3-53de-9d66-0aa154d74e11 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 390582f8-6cc0-5f5c-a34a-3b697361bbcb |  | note | Conformance Criteria - Remove and clear the vegetation
label | 6715ba3e-d538-5bd8-8df4-712b6c20b482 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.3 - Subgrade Excavation
label | 15d55333-6e6f-5dff-b371-f4a65f99f3ed |  | note | ACTION (Hold, Monitor, Witness) - H
label | 86322827-01e5-552b-a41b-a7a0781ada7c |  | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | 17474d21-482d-54e0-ad4d-46a5c4dcc236 |  | note | Frequency - During Construction
label | 5666076b-9777-5f97-9692-45986452cd4f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 682b5d02-9cc3-5536-ae16-6c0cceac1b56 |  | note | Conformance Criteria - Engineer to assess foundation material suitability
label | 50babbd9-3a35-5df7-9f74-888be5a58f9d |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Subgrade Inspection
label | be4095f7-2492-566a-aa25-95ac6ba304b3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 95d1b80c-8bde-5670-9d2b-38f114d4d9be |  | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | eed39a4b-f080-58ae-b7b4-2951b8c0cfc7 |  | note | Frequency - Per area as required
label | 046e667d-8264-5d34-8fba-e22ff62a5b42 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | 48b93d56-9fdc-5757-8729-59ddce38560e |  | note | Conformance Criteria - Inspect fill foundation.
label | ed457cf2-adf9-5990-be28-a1e81af2c089 |  | note | ○ Fill foundation must be approved, in writing, before filling commences
label | 43e0fc25-dcc7-5a03-a68f-d612b16a44f2 |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Form and cut fill batter as per design
label | 716ea1fa-ee54-56d4-8f8b-921a8a5c5e6f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0f096b9f-e54e-55f5-9e08-75f4718bf416 |  | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | 2af48bf4-5d0d-5d9a-9787-d1974f3fac02 |  | note | Frequency - During Construction
label | 2e44ef5a-d677-50df-b886-d1a65d1bd1bb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 06720ad0-d9d0-55a5-b0fa-9b3e68789828 |  | note | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
label | abcf48d6-328a-55e7-a301-9e659eb9ea2a |  | note | Records - Survey as builts
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Class E (A49) Geotextile placement along the face of fill batter
label | 6d091d36-435e-5e70-bc5a-b1335edc540d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 802b3c2b-c3a3-5ad9-8385-ca2d5bf0b8b8 |  | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | 00149a28-7064-584a-8961-f54ce1b48c00 |  | note | Frequency - During Construction
label | 167cfbb4-6d90-5dbe-b196-e479b33ac277 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3629a763-f8f1-5471-bf1f-d40aec4178b7 |  | note | Conformance Criteria - Class E geotextile to be placed between the rock armour and bulk fill
label | 114919e6-eca6-550d-9da1-d814a1ac0166 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.7 - Rock Armour placement along the face of fill embankment
label | 58eac124-111d-5ef1-8a0d-8d2afc9df245 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3e6a3927-047c-5813-9c7e-463c48ba6d36 |  | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | 9cc27e46-6e1b-5f45-b91b-a58e3d0eaa9b |  | note | Frequency - During Construction
label | 4fe301d0-b230-592e-8acc-a5e93dcbe047 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | 06625d57-ab86-5589-afb2-6ec9d79be780 |  | note | Conformance Criteria - Install Rock riprap as per design; material to comply with requirements set out in Rock Rip Rap Grading Table located in design documentation
label | 524677c9-f8ee-51da-b8f4-d2e704bc42a9 |  | note | Records - Photos, Survey as builts
checkpoint-status |  |  | checkpoint | 2.8 - Rock Armour key into ground
label | 48a5849b-b913-58b1-9e15-4a060802daf8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e98e16e5-08a0-53e1-b7e0-a54a81dc919c |  | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | 60c0939a-5b5e-59f6-9bc8-66506c05ca60 |  | note | Frequency - During Construction
label | 7c5f234c-173e-5ca6-bd92-5ba66f943544 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | cd59ccc3-0673-58f5-b8a4-e543d5811fcf |  | note | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer.
label | 46794dc9-2500-5568-8c89-2f33eac145ba |  | note | Records - CPS COR report and survey as built
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - As-built Survey
label | 4870ef4e-ad10-54fb-bc3d-17c85fa9e645 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 145110d5-9885-5f01-9cb8-4f2a58c2fdf9 |  | note | Specification/Drawings Reference - F3002H Mang Bridge No3 Repair Strategy IFC by SMC
label | 7ac32906-907a-5043-9e3e-6a23e27b5f6e |  | note | Frequency - At completion of Lot
label | addfc81a-56d8-528d-94c3-483177f961dd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | ceac6596-2bb9-5720-a7cc-bb2006b484a5 |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | 18f331b5-01af-55c8-9095-43b96827574b |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 3: FINAL INSPECTION & HANDOVER
checkpoint-status |  |  | checkpoint | 3.1 - Quality Assurance deliverables
label | 28e21f65-037e-5026-9482-7128ff3aaebf |  | note | ACTION (Hold, Monitor, Witness) - W
label | 10863d2d-8922-53cc-9517-0d7950a1eb88 |  | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 0a4e591b-64eb-513d-9313-d534fd285d46 |  | note | Frequency - At completion of Lot
label | 6f062dd5-be9b-56bc-91a9-2f8391f57828 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 1a87ee9c-530a-5dcc-8b89-80797d3d7561 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 1ee59ac8-b506-51ee-b553-d9734ba9fc60 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 3.2 - Completion Sign Off From Fields Below
label | f1f1d7a0-2e81-5bcb-b269-0e5527cb3adc |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | ITP - E3001 - SH05 SIP Generic - Guardrail | itp |  |  |  | Yes | ITP - E3001 - SH05 SIP Generic - Guardrail V2 | 1200b33f-c809-4ab4-8059-f814df22456c
checkpoint-group |  |  | section | 1 - Setout & Checks
checkpoint-status |  |  | checkpoint | Project Site reps.
text | cced162c-64d2-5efc-90aa-3b044f641676 |  | textbox | CPS Eng.
text | aef69642-1706-53cd-a2f5-9e37b3acdbf7 |  | textbox | Site Engineer
text | 1d5b771b-c7ac-5204-a1ca-3e64f12ab04e |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Design Check
label | f55b1984-6d0d-588a-8054-762a33dece0c |  | note | ACTION (Hold, Monitor, Witness) - M
label | 177051a1-3506-595f-bb5b-b27b189c278d |  | note | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | f52bb312-076b-561b-bfcd-7ce0dc5287a8 |  | note | Frequency - Prior to commencement
label | 04c50c9c-b709-55ad-93f2-9fbdcc77cdc0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 3c9d089b-9c8d-5e1b-b82c-6c13d495c85d |  | note | Conformance Criteria - National Standard for Traffic Signal
label | abc6a079-aa01-55ea-b05e-b202cbfc7c2d |  | note | Records - OFI or NTD/NTC
checkpoint-status |  |  | checkpoint | 1.2 - Survey Setout
label | d58a41be-0d8e-55e0-83f7-9dddfd91717d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0fa7bbb5-4b90-51d6-9e71-d4f13369826e |  | note | Detail - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
label | 32bd05f5-da2b-52dc-8829-fa1d931f0471 |  | note | Frequency - Prior to commencement
label | a4ab71c4-fbac-586f-9fa2-c32656d81bde |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 4cc17b83-43ed-53b1-b84a-28c1c0984790 |  | note | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | 3976877d-188b-5908-8651-baae92e7a860 |  | note | Records - Approved Construction Drawing.
checkpoint-group |  |  | section | 2 - Material Compliance
checkpoint-status |  |  | checkpoint | 2.1 - Barrier Compliance
label | 6642b0ee-467b-5a79-b2a4-165f8d013434 |  | note | ACTION (Hold, Monitor, Witness) - H
label | fb6250fd-1021-55f6-bd8b-467bc46d4ea0 |  | note | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
label | c11b72d7-da09-52de-9f79-6cfe258be655 |  | note | Frequency - Prior to commencement
label | 80e3d451-773d-565c-92a1-6ebf55337f2a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | dd9cbfe3-8e0d-5bdb-bb77-dd3f896ed60c |  | note | Conformance Criteria - TNZ M/23:2009
label | 62a4186d-cfbb-5db6-bf4f-401d19092eab |  | note | Records - Manufacturing certificates and delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Material Suppliers
label | ae7a70d1-5226-5090-b448-de63d47187e6 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 074215fa-0917-5d71-8332-b2a18eceff3b |  | note | Detail - All materials to be sourced from registered suppliers
label | 3acaba4a-ec2b-5741-935f-d6a5ece44544 |  | note | Frequency - Prior to commencement
label | 16dcfb4e-b048-559b-a5de-9ecaaa0e1726 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 7a66365a-7d74-52ff-823d-bc9d5c2c99bb |  | note | Conformance Criteria - Registered suppliers
label | 5e9394b5-2f67-525e-93ac-2696134895b5 |  | note | Records - Materials register
checkpoint-status |  |  | checkpoint | 2.3 - Galvanising Repair Methodology Approval
label | 5458f4ef-8ad2-55b6-97b9-80b56a22293d |  | note | ACTION (Hold, Monitor, Witness) - H
label | bb45e8f6-e4bf-53e8-8973-777656f5dc08 |  | note | Detail - Proposed galvanising repair methodology to be approved by Engineer
label | 09fe0ce7-c87d-5515-8e8f-a1864b11daa8 |  | note | Frequency - Prior to commencement
label | b344cd9d-507f-5320-b1fc-5f693ae0dcb7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 43c2e41c-6eed-505a-a8a0-f48d823f4f96 |  | note | Conformance Criteria - Best practice
label | b45f1bcf-f0ad-5ad5-b313-cc5361b57092 |  | note | Records - Approved / Signature
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Installer Certification
label | 2bf988d0-e6d7-57db-b0f5-da2c54c4ff86 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 38f4f582-aae9-5588-b09f-83aa42c6f346 |  | note | Detail - Certified Competent Installer. All roadside barrier work shall be undertaken by certified installers
label | 8407d565-4f9f-5c6d-9b8a-1a78020da663 |  | note | Frequency - On Procurement of installer
label | 2ed6ab0f-f8f9-5cc1-ab08-dd3b93aa0e57 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Written confirmation
label | 5043f194-ba45-5b63-a66a-70b1adac55f2 |  | note | Conformance Criteria - ASHTAS operative and installer course
label | 1d8c40ac-340a-534e-b0be-2bee538bf51a |  | note | Records - Attendance Certificate
checkpoint-group |  |  | section | 3 - Guardrail Installation
checkpoint-status |  |  | checkpoint | 3.1 - Guardrail Installation Locations
label | 9ab11576-eb0b-5230-a01f-7412ca3ac547 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 125dda90-41e1-568a-9db9-1d408fec3e67 |  | note | Detail - Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | f3c68533-2408-5ee2-bdfa-1bd9bb994b67 |  | note | Frequency - During installation and on completion
label | 31f05e85-4b2d-5ca3-99fe-642ca022de65 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | 3b221de2-71c4-5602-92a9-bcd83e09ae7f |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | 339a93f5-74e7-5661-8ec2-9455ec461a03 |  | note | Records - CS-4117 Guardrail Installation Checksheet
checkpoint-status |  |  | checkpoint | 3.2 - W-Beam Guardrail Installation
label | 2ae331d7-3bdf-5227-adde-9dbb5562585a |  | note | ACTION (Hold, Monitor, Witness) - M
label | 749e98f3-4830-55db-9df0-906d7dbdf65f |  | note | Detail - W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | 47ea6e08-30c2-5a18-8c43-a78322f1d499 |  | note | Frequency - During installation and on completion
label | 25607303-c40d-5d31-a16b-c65d1e8b4665 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | 8f916022-66f2-5fff-a690-f8f718dac095 |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | ab67f5a5-59ed-5e53-9389-0085ce9fa182 |  | note | Records - Installation Checklist
checkpoint-status |  |  | checkpoint | 3.3 - Leading & Trailing End Terminal Installation
label | db2bc873-2ab8-5b4d-92e7-54851c13b655 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a9780095-b39c-5e2e-af4c-8f2e599c733b |  | note | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | e26f156e-2adb-5df8-b083-f513698e407e |  | note | Frequency - During installation and on completion
label | e7b375a6-5b2e-54db-b01b-75c6289def34 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | db187f75-ba9f-55ac-a3be-92ae9db66293 |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | 3fdc85c9-6642-5868-8c20-64faa03b69d5 |  | note | Records - Installation Checklist
checkpoint-status |  |  | checkpoint | 3.4 - Fit for purpose Inspection
label | 81653748-fe4e-59e2-aa85-5dfc65f7dc96 |  | note | ACTION (Hold, Monitor, Witness) - H
label | be809af1-7a0f-58b6-8ec2-efe97bb63f7d |  | note | Detail - Barrier to undergo fit for purpose inspection by competent person
label | e0a8a8b5-b7c5-51fe-8b09-94786272a958 |  | note | ○ System checklists to be completed and co signed by contractor and CPS.
label | 548e6c03-e4be-5f98-85af-0d482162e159 |  | note | ○ All faults to be rectified before acceptance into network maintenance and RAMM
label | c9a8501b-fc6b-5a2e-9861-00a41da50ed1 |  | note | Frequency - Prior to trafficking,
label | 5179012d-de5f-565c-bdd5-94a972918e03 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | a381182b-331f-5750-b3d7-7dfac60abac9 |  | note | Conformance Criteria - Pass inspection
label | 09644748-d44f-5832-94fc-b603568c2796 |  | note | Records - Confirmation from inspector
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4 - Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 4.1 - Final Walkover (Snags)
label | 8c9cc89a-ee3c-5480-a10b-b52368125ce3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7b5aa7e1-c4df-53f0-848d-64b165c388c5 |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | 3f42e5a5-ab83-53fb-a8a1-ae5b977036d6 |  | note | Frequency - At the completion of the Lot of work
label | b29a55f9-ada7-5b9b-9ad5-ceba13309e12 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | 0942803a-602b-55a6-8105-80bcd1fa1e8e |  | note | Conformance Criteria - Completed report
label | 075d5e1e-2747-5f49-8170-a5cfcdd9e534 |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Survey As-builts
label | 8744d8c5-e4f7-59d9-83d0-16eea6296b51 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d1236711-7d5f-517a-a9a5-0e80155ed85d |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | 0c4f8a64-be53-5a7c-90d6-fc4a1ff4265e |  | note | ○ A survey as-built of completed work must be provided
label | f8a58bd6-76e1-5bab-a6f0-b5bb914dbeef |  | note | Frequency - At the completion of the CWP of work
label | 2edc01ab-4bee-530e-b917-115d1732a6a1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 1ff12ee5-faf1-59d0-a6e7-eb36c2ee8b9c |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | 333266ae-9282-5075-b672-5a6d8dcd3924 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Quality Assurance Deliverables
label | efc5e96e-0a34-593d-921a-dab98da168f5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | edaf7a61-3df7-50ee-b512-d960651f7eb1 |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | c4c767a3-1621-5e88-9529-deba8b5fcd1b |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | e2f731c1-645c-5c19-a342-4c0d792eed25 |  | note | Frequency - At the completion of the CWP
label | e7a22da3-7d7b-53a1-b926-29f2578c58bc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | c8cfbc51-4c54-5975-bb9d-04442f404870 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | f46dc4c1-27eb-5cfa-a51b-2023a17405bb |  | note | Records - As-builts, NCR's and RFI's
checklist-flat |  |  | checklist | ITP - G1302A Culvert 33 - SH38 RS179 RP5.805 - Compliance and Environmental | itp |  |  |  | Yes | ITP - G1302A Culvert 33 - SH38 RS179 RP5.805 - Compliance and Environmental | 12e678d8-bc59-49b5-bf5f-7447a11f0a2f
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 3f12448c-2050-5fba-a4fe-1b9ec272c02a |  | textbox | CPS Eng.
text | 0d16a946-a623-52e0-8f9b-c80e32b69c9e |  | textbox | Site Engineer
text | 54ff240a-43db-5134-b582-382379c04a23 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Approved Consents
label | 3f759ae4-b6c9-5154-9d50-88438b77ca17 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 2decdb38-689a-50da-9315-246e6abdb9b5 |  | note | Detail - Is a copy of approved consent(s) available on site
label | 0075176c-78b5-5dbd-8cc8-2f6b874f8c78 |  | note | Conformance Criteria - Check latest consents and SSESCP's are at each site office
label | a9794e5c-440f-522f-9257-71d212106843 |  | note | Records - This ITP
checkpoint-status |  |  | checkpoint | 2 - Internal ESC Pre-Construction
label | 15ad64e6-2445-5b5c-a26e-f62613539706 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ee572a2e-0768-5222-b550-1d3ae07d9860 |  | note | Detail - Internal pre-construction meeting held with E Team
label | c7ee2cac-ab33-5b04-ae81-456b04684d6f |  | note | Conformance Criteria - Environmental Advisor to organise
label | 5b36d0ee-e683-585b-99a5-c870d49decc2 |  | note | Records - This ITP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Type and Location of Erosion & Sedimentation Control
label | 83995358-ce2f-5735-b481-a596e0f47988 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 985dee99-0d37-5c15-9b0f-665735e27fc8 |  | note | Detail - Confirm type and location of erosion and sedimentation control, based on relevant drawing/s
label | 9a3b59aa-2d2f-5d20-9d9e-768064f9a414 |  | note | Conformance Criteria - Relevant ESCP drawing
label | bfe88daf-3b8e-5011-95eb-6fb64f1c0c98 |  | note | Records - This ITP
checkpoint-status |  |  | checkpoint | 4 - Channel Bund (if required)
label | 022652a8-98cb-5f81-80e8-91cb95ff1db2 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 5bbf3fbc-310e-5ab6-b63b-e82015ae892e |  | note | Detail - Bund is constructed in correct location; to agreed / specified dimensions and levels; and is firmly compacted.
label | 0fb4cee9-4517-5001-bdae-bab3047227fb |  | note | Conformance Criteria - Work Instruction, Drawings and Checklist
checkpoint-status |  |  | checkpoint | 5 - Silt Fence (SF) (if required)
label | 935be997-6950-5129-b0df-67c70b4fbd15 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 506a696e-f0bb-5cb8-98e9-b91037d23853 |  | note | Detail - Silt Fence or Super Silt Fence is constructed in correct location; to correct dimensions, and geotextile secured and waratahs located as shown on the WI and drawings
label | ab983ae3-60bd-52d0-b1fa-ff366b42f024 |  | note | Conformance Criteria - Work Instruction, Drawings and Checklist
checkpoint-status |  |  | checkpoint | 6 - As-Builts
label | ba768826-2b18-5df3-8b37-c623c173de04 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 67b3185f-101a-54ac-b175-2e43ed4cdc7c |  | note | Detail - Confirm as-built details of completed works
label | b93ac9d4-2500-5a20-b45b-cfaed0c19d5a |  | note | Conformance Criteria - Submit to Document Control/Environmental Advisor to issue to HRC within 24 Hours
label | bea21850-4785-5f93-96fc-eb0d0a662d17 |  | note | Records - This ITP
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Maintenance Inspections
label | 834d4d6e-e486-5575-af98-56696d0ad070 |  | note | ACTION (Hold, Monitor, Witness) - W
label | dffe944f-63de-50ef-866c-90d3abc052c9 |  | note | Detail - Undertake weekly inspections of all erosion and sedimentation controls and after > 5mm rain to identify required maintenance
label | d6e26a25-0949-5587-b120-336fb034b60e |  | note | Conformance Criteria - Approved ESC Plan. Complete weekly and upload to ConQA / Procore
checkpoint-status |  |  | checkpoint | 8 - Decommissioning of Erosion Sediment Controls
label | c4864943-93d6-540a-8953-b85834f228cc |  | note | ACTION (Hold, Monitor, Witness) - H
label | cab643ed-94b7-5ae6-a3f5-b37b0fc88d0d |  | note | Detail - Decommissioning Plan submitted to HRC for Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Decommissioning of Erosion Sediment Controls
label | 6ea3e572-fdba-59a5-857a-5bbf374bf244 |  | note | ACTION (Hold, Monitor, Witness) - H
label | afebc491-6127-586d-933c-7ebf4651a36e |  | note | Detail - HRC to issue an approval document so that Decommissioning works can commence
label | 5a26a986-ab35-55e1-864d-a482f1900e2c |  | note | Conformance Criteria - Approval for Decommissioning
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Lot Number QA File
label | 7178b4c0-3d59-5251-b739-3e0efa40a616 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a9f7d783-0c59-55e4-bd95-10ab54980bb9 |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 8cf53f56-dbb1-5546-81b9-0006477bc19b |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 5331eeb2-c5ba-504d-8858-73fd25f445fd |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checklist-sectioned |  |  | checklist | ITP - D2004A - ID173 - Tauwhatinui Bridge (BSN4593) | itp |  |  |  | Yes | ITP - D2004A - ID173 - Tauwhatinui Bridge (BSN4593) | 1311f536-be8a-42fc-b805-9e1a688e6afa
checkpoint-group |  |  | section | Section 1: RECEIVING INSPECTIONS
checkpoint-status |  |  | checkpoint | Project Site reps.
text | b993a132-8c2e-5295-8034-c20fb8737c31 |  | textbox | CPS Eng.
text | 09f2fa67-a944-5fd5-9376-199708a8254d |  | textbox | Site Engineer
text | 962e0022-e747-5105-9f47-a1077ed54885 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Rock Armour (D50=600)
label | 786c077e-d4da-590e-994c-1e34ad5c0918 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ad49f15b-8fb4-59a6-a441-1eeed7f4cb3c |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | df7daefe-4982-5063-ba5e-51cad1103ec9 |  | note | Frequency - Prior to commencement
label | 01dfbabc-bef0-5469-9a0b-b02046c38541 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Visual inspection
label | 05226156-64c9-56ac-bbb2-cc83b925b3a8 |  | note | Conformance Criteria - Traceability of material required.
label | c0cb3714-ea39-5123-aea0-9056d7555d91 |  | note | ○ Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 of 600 with a minimum specific Gravity SG of 2350kg/m3.
label | 1a2fb17f-0d34-5699-9e62-7863df6d6bba |  | note | Records - Material source test results, Delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Bulk Fill (AP65 or approved site won material) or similar
label | c31881da-7e78-591f-ae65-aae8c1d32f6a |  | note | ACTION (Hold, Monitor, Witness) - H
label | af5fa72b-7d52-5ce0-8025-0377f87ec442 |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202, Technical specification sheet 1 of 3
label | cc423387-12bb-501b-9914-a81e2746749b |  | note | Frequency - Prior to commencement
label | 89b9b059-ca03-5ac1-aabb-54c732f1f793 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Visual inspection
label | 407c84fb-6ffb-5d8f-8136-39eb7cc21d50 |  | note | Conformance Criteria - Traceability of material required.
label | 90c4f049-e5d1-52fd-a101-ea930f954e38 |  | note | ○ Should comprise clean granular aggregate and have broken faces.
label | b6999123-0097-56a5-9e22-3792eaba9b3e |  | note | ○ Comply with Sampling & testing in accordance with item 2.2.2 Sampling of materials & 2.2.3 Testing Requirements listed in Technical Spec sheet 1 of 3
label | b07f7cac-829e-589c-9d76-face669c9914 |  | note | ○ Maximum particle size of 65mm and not more than 5% by mass passing a percentage passing 75 micron sieve dry density water content relationship to NZS 4402 4.1.1 STD Compaction
label | db5b23a9-3f09-5554-a073-21829724e66a |  | note | Records - Material source test results, Delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Unaxial Geogrid RE540 or approved equivalent
label | c98c2a0e-c32d-51bc-b615-4c65e48a35dc |  | note | ACTION (Hold, Monitor, Witness) - W
label | 614d4439-bce9-5feb-bd40-49bd863de1a3 |  | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical specification Sheet 1 of 3
label | 895c21bc-dc7c-57c5-9322-883423d04c84 |  | note | Frequency - Prior to commencement
label | c6e4fabc-0977-52ef-a116-defe7bb9da70 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | a8ab80c3-ed22-541e-a965-f29016f93f55 |  | note | Conformance Criteria - Traceability of material required.
label | 173450c0-1725-5cd9-ae89-8b74566a56c9 |  | note | ○ All rolls of Geogrid are to be inspected & bar codes collected/photographed. Geogrid to remain in their protective wrappers until required for use. Any defective rolls shall be returned to the supplier immediately
label | d8bf9936-c743-5b22-8105-ab4f2aa4b7ec |  | note | Records - Delivery Dockets/ Storage photos, Material compliance cert
checkpoint-status |  |  | checkpoint | 1.4 - Geotextile Filter Fabric, Filter Class 1, Strength Class C
label | bec8ca27-c0fb-550e-8e6b-6fb26c63b030 |  | note | ACTION (Hold, Monitor, Witness) - W
label | bbd0bb14-12ee-5698-9fb4-368b3ca72bc4 |  | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical section and details, NZTA F/7: 2003
label | 11726ad6-8c0f-5fe3-afad-523f599dd03a |  | note | Frequency - Prior to commencement
label | 2efe51f9-fe6d-594a-a106-2bc845af9a57 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 1477f344-e254-53cc-ac47-da475985c874 |  | note | Conformance Criteria - Class 1, Strength class C in accordance with NZTA F/7:2003
label | e983156f-163f-52d9-91c5-31a2b8477bd0 |  | note | Records - Delivery Dockets, Material compliance cert
checkpoint-status |  |  | checkpoint | 1.5 - Green Terramesh
label | 3d409cd5-f0c9-57b7-9d39-5f8cae5c4d87 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 98099b19-9e52-52dd-83b7-4dcdcc5116e9 |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | b8719d9b-7de4-52d8-8834-ce580a0d6fed |  | note | Frequency - Prior to backfill
label | 5b3c6619-4a9b-5a8d-9141-9a65e610d0b9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | c4294c38-2d82-5021-897b-22ddf9ac81c6 |  | note | Conformance Criteria - Terramesh shall be manufactured from steel wire coated with a protective coating of zinc-aluminium alloy and a plastic erosion protective coating. Construction observation reports on cutting and approval
label | a76986b5-b267-5201-b7c1-d0f7cb225137 |  | note | Records - Material compliance cert, Delivery dockets, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.6 - Megaflow Strip Drain Or Drainage Blanket For Seepage If Encountered
label | f4f8cf89-3781-50b4-ada9-7b6b113fab82 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3f05be75-8b18-5079-9e42-ce803b99af8a |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | c1a7fee6-b300-5014-9ad6-2e4ac2ff6fe0 |  | note | Frequency - Prior to commencement
label | 2704ff59-d91a-5df7-812e-111da19153ef |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | a1691813-86e7-5a79-a1c4-ca99068366f8 |  | note | Conformance Criteria - Subsoil drain shall be in accordance with tnz f/2 (geofabrics enkadrain 5006h/2-2s/t110pp or similar). 110mm diameter novaflo subsoil drain, or similar approved.
label | e60b882f-caef-59fe-b8a1-a1bb014d44fb |  | note | Records - Material compliance cert, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.7 - Subsoil Drain Pipe
label | 74e8b824-4135-5e56-9a77-fe717dd9b69c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7a0850cd-2bc5-5934-ab9d-b47edf15a246 |  | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical specification Sheet 1 of 3, typical section and details
label | 66ef63be-e94b-5570-8da6-602faaf9df7d |  | note | Frequency - Prior to commencement
label | 71123442-7881-5863-bac5-4c29a5a84948 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | b92b5911-c118-5a2c-b69d-ed83bfeac144 |  | note | Conformance Criteria - 110mm Iplex smooth-Bore pre-wrapped Hi-way drain or similar approved
label | e21b2a2b-34e2-57a9-9808-a4e6e5235023 |  | note | Records - Material compliance cert, Delivery dockets, Photo's
checkpoint-status |  |  | checkpoint | 1.8 - Subsoil Drainage Material
label | 291d05dc-e38a-50db-b831-e7be2dea54ce |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5ad93c24-6cd3-517e-bdfb-c8bfec5555c0 |  | note | Detail - Ensure Material for Bedding, Side support and backfill are as per NZTA F/5:2013
label | 593414a7-a20f-52d6-b2bf-84b5668acdbc |  | note | Frequency - Prior to commencement
label | 74ec9a52-3a90-568b-b4f5-83007684631f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 85181bb3-fb10-5aed-804e-150ec47047c2 |  | note | Conformance Criteria - Traceability of material required. Comply with NZTA F/5:2013. Ensure clean drainage chip.
label | 616b31e8-2126-5e84-9d1c-9a71c31746da |  | note | Records - Material source test results, Delivery dockets
checkpoint-group |  |  | section | Section 3: IN PROGRESS INSPECTIONS (Earthworks and Terramesh wall)
checkpoint-status |  |  | checkpoint | 3.1 - Survey Setout
label | 880e9e2e-1677-5269-b63b-90028d27fa8e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0ceb2be2-bbbd-5de8-8060-30aa1baaa59c |  | note | Detail - Consistency with Construction Drawing
label | b40c6955-890d-553f-a761-dd87c8732fd5 |  | note | Frequency - Prior to commencement
label | c8c4af77-a555-5d77-b0f2-96342c464f81 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 1161c833-338f-5422-b5a4-13c31333e91d |  | note | Conformance Criteria - Set out extents of fill and check against design drawings
label | b46bf265-e832-5812-b45a-d2daf1362df5 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Vegetation Clearance And Removal Of Loose Debris
label | 64604e64-b89e-5dd9-839c-2eebaf0d18f4 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 53decfad-5868-5002-a15b-6cf209ce3942 |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | 8bddb085-a6be-5ca0-b920-d57e812f57a3 |  | note | Frequency - Prior to commencement
label | ade9eee8-08f9-5ab4-99e2-dd6f52276a7d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 28ed5b30-f699-5e91-b784-2c6267f11799 |  | note | Conformance Criteria - Remove and clear the vegetation
label | add3fda6-3eb6-58e2-94cd-48cb50b95934 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 3.3 - Subgrade Excavation
label | f3b62d18-34d1-588c-994f-14da539271b3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | da06bb8d-c0f0-5565-9323-49c0b7b6f30f |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | f61a5428-6309-5c02-a757-c021c951d296 |  | note | Frequency - During Construction
label | e87eb8ce-21af-5a61-835c-bab68e5cb30d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, testing
label | 0cac93bb-9847-57b8-af57-d3c15c4cca14 |  | note | Conformance Criteria - Engineer to assess foundation material suitability
label | 15d2cd11-ff86-587e-931d-3504aca87277 |  | note | ○ Hold point when excavation is 400mm above proposed level to do scala penetrometer testing to 1.5m below - minimum ultimate bearing pressure of 300 kpa i.e., readings of greater than 3 blows /100 mm
label | 069fe956-a50e-5a17-abff-63f89cc0d436 |  | note | ○ Hold point when excavation is at level
label | f21786f5-2666-57a9-b344-b168b3ba7161 |  | note | Records - CPS COR report, 1M Scala check sheet, Scala test reports
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Subgrade Inspection
label | 2cd48003-300d-538e-b60f-79731e7e89f5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b6f95a02-ca0a-5a84-9cd4-35f5c81f7bab |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | 7e54f28b-b8d4-5819-b584-68a3d8f69017 |  | note | Frequency - Per area as required
label | b9893e57-2772-5f6a-8c38-11b68d0e1b3d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 424c0d36-3023-51fa-8875-509474acf190 |  | note | Conformance Criteria - Inspect fill foundation. Fill foundation must be approved, in writing, before filling commences.
label | 7b117a68-5e87-5e66-9899-f3c584c4eea1 |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Megaflow Strip Or Drainage Blanket Installation Or 110Mm Novaflo In 300X300Mm Trench For Seepage If Encountered
label | 49b13c12-f11c-5d8c-9ccf-464cc43cd1e5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9da0a674-a4e7-5c19-8e36-dce75c8a4309 |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | 00f46be2-3981-5acd-bc89-1bb499bc33f9 |  | note | Frequency - During Construction
label | 35e7611a-f8b9-5c67-a9f5-b0cf7079328d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | f20ac08e-8780-5322-bd28-74c4b8579313 |  | note | Conformance Criteria - CPS Engineer to assess suitable drainage location(s) and confirm on site. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required.
label | ae60d379-7269-50be-917b-64608a16476a |  | note | Records - Photos, COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Bulk Fill Placement
label | 583359ae-fac9-5453-b1f7-e3776761bafb |  | note | ACTION (Hold, Monitor, Witness) - W,M
label | 887a15f8-612d-5fcf-a446-6e3ff523bd81 |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | de9ea40e-accd-5597-b42c-89bf71a13097 |  | note | Frequency - During Construction
label | deb01888-48f5-5a96-96b2-870bf4a77893 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | d7dd063d-2ffd-5457-8fd5-fc64908199a4 |  | note | Conformance Criteria - Granular backfill to be placed in layers of maximum 200mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill should be placed on dry subgrade.
label | 928306b2-b9a7-5996-952e-c6107c615948 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 3.7 - Bulk Fill Compaction
label | 18e22c4c-f992-54a3-af6b-eaebd5fe0e1a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 762c9a2f-26e8-5fa9-a643-d29002a2b361 |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | adda284b-b2b1-50a1-b084-0953e5dcd299 |  | note | Frequency - During Construction
label | 47e814a6-b9a5-5a3f-916a-41cb3d2376e3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | bfe941f3-59aa-50f7-959a-b0c11a75654c |  | note | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.1.
label | 41015099-031b-53aa-82aa-636dcf1332d8 |  | note | ○ 5 x Clegg hammer readings shall be taken for each terramesh unit lift of 0.6m with the addition of 5 x NDM tests evey 1.2m lift (i.e every second terramesh unit)
label | c3cab5b7-0447-5d02-8d3a-1e3fa3b4c0fe |  | note | ○ NDM Testing to be carried out by IANZ accredited lab and results witnessed by CPS Engineer as they become available
label | 7bb7446c-8f46-569e-80b7-8a07c1024ead |  | note | Records - Clegg and NDM test reports, Clegg calibration certificate
checkpoint-status |  |  | checkpoint | 3.8 - Form And Cut Fill Batter As Per Design 70 And 50Degr.
label | ee9e9b26-b3c1-5de3-a6a6-f324da05845e |  | note | ACTION (Hold, Monitor, Witness) - H
label | b0ef2ab6-81df-5f7b-811b-48883db6e486 |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | 9d9087f5-56bd-5e97-b67a-687d6cd54d07 |  | note | Frequency - During Construction
label | 95cc422f-5a73-567d-8621-e73843a8d8b3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 6f287e05-b38a-5c33-8312-7ee760a49972 |  | note | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance. Slope angle of buttress is to not exceed 70 and 50degr. Respectively.
label | ea64b642-b987-5dd8-ba74-8a1a1dd2a297 |  | note | Records - Survey as built
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.9 - Placement Of Geogrid / Geofabric / Terramesh
label | 7353a0d8-018d-5ec2-9830-e5f2463fc8a0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a7cef716-e0a0-5d5a-926a-0c37e351617a |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | 6bd8cf9e-83b0-5d0f-84ab-bbcd4248a517 |  | note | Frequency - During Construction
label | 872aaca0-62ae-542d-86aa-11a54bc41854 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | b2edd2be-a960-5a6c-8f03-bde2b8aeba72 |  | note | Conformance Criteria - Grids are cut to the length stated in drawings. Grids are placed in the right direction (high tensile strength perpendicular to face), Grids are overlapped (see manufacturer's spec of the specific grid/fabric), laid flat and undamaged.
label | cfc9c8cb-80e2-5863-9825-a2c1799264a5 |  | note | Records - COR or photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.10 - Filling Operation
label | 3ff74e00-b96e-5137-9c72-1723153495ef |  | note | ACTION (Hold, Monitor, Witness) - M
label | 2ef38b96-f548-544a-bce2-f1803d29a94b |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | edb69fa3-b03e-5019-a609-3209c8d59ce5 |  | note | Frequency - Daily
label | f6544185-bdc3-5e68-a74e-762cb5e60a5b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 37cfa254-6b83-5c5c-9b21-9fed2cf9c91d |  | note | Conformance Criteria - Geogrid protection - Minimum 150mm layer placed above geogrid before tracking onto it. Damaged grids need to be replaced
label | 96c15e50-5853-58dc-be9c-5f5db1bf1178 |  | note | Records - COR or photos
checkpoint-status |  |  | checkpoint | 3.11 - Fill Material Placement
label | 7fd277c4-de41-5a50-9057-9680668bd8e9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4ef0c31d-d278-5e6f-a364-aef3ef24e129 |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | 30796a0c-a390-56d5-9ecb-c8fdcf80db20 |  | note | Frequency - During Construction
label | 8d339513-a463-5b00-9d54-0cf561d50863 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | a13aeb7f-5962-5cc0-bebe-48411821be41 |  | note | Conformance Criteria - During placing of the initial layers of the facing and geogrid reinforcement, the engineer shall be given the opportunity to inspect the onsite construction methodology.
label | d26ede5d-1294-5ce4-bb82-1b1174192848 |  | note | Records - COR or photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.12 - Terramesh And Geogrid Inspection
label | 3ab94700-b98b-5910-babf-d866234ee547 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d397d610-6696-5f24-a70c-c67f26154d0d |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | 36cafaaf-a262-5889-9df2-250539542001 |  | note | Frequency - During Construction
label | fc12e459-cb27-5e99-82b9-772820bebfab |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | d367a046-d984-5f87-b518-2d7cbd5a5fb5 |  | note | Conformance Criteria - Once the installation of the terramesh green and the geogrid reinforcement have been completed, the engineer shall offered the opportunity to inspect the completed works.
label | 85da3cda-f38c-56d1-ba14-18807b511cd5 |  | note | Records - COR or photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.13 - Foundation Rock Riprap Placement
label | b5e44063-f935-567e-b7aa-0d6453112088 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 99e11f95-ca9e-5f8c-9f1b-a3f00c4e9ef0 |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | f3e4a5a9-e9c9-5519-a040-684db87bf192 |  | note | Frequency - Daily visual check
label | a3682e22-78d1-5ebc-a7f7-6c50ea1c8dfe |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 3cb068d4-d905-52a8-be7d-6a1a3b00bfbe |  | note | Conformance Criteria - Ensure that placement of rock material is done in such a manner to minimise segregation and avoid displacement of underlying materials.
label | 3b45c2aa-84ae-51a2-9499-019f462eb859 |  | note | ○ Oversize rock to be placed such to minimise voids.
label | 3d1f2966-3ff6-5e67-9ea8-f22e01ab2a88 |  | note | ○ Design Engineer given notice to visually inspect initial placement of riprap material.
label | de85cfc2-1735-5af3-a495-6a7d562f0b44 |  | note | ○ Rock riprap foundation thickness 1.20m and 3.70m wide
label | 1ea05dd7-df62-5d13-9cc3-8a4f0c1cdb55 |  | note | Records - COR
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.14 - Riprap Key Into Ground
label | c1cdfacb-6892-5aeb-8e38-f2eac52f6440 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 20965829-0fc5-5f2f-9b61-bae557667610 |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | 5e3652f1-a545-5a70-8dd3-0e7a52dfb613 |  | note | Frequency - During Construction
label | 31bc5e45-bd06-58f3-993f-2a4a9121b3e3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | 1ba67256-c2e2-53fe-bf4b-00e908382f6a |  | note | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 3m wide as per notes on drawing.
label | 6ab59b61-521c-5840-a8a8-89564681b0e4 |  | note | Records - COR, Survey as-built
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.15 - Subsoil Drainage
label | 861ec790-b0fe-51d3-b6f0-8e4571b666f9 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 911aae8b-0738-59ed-8962-5f2efcf80e83 |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | 0d1308cd-9f03-59ec-a3ac-5edce2834184 |  | note | Frequency - During Construction
label | 87389ed4-5f7d-58cb-bb78-e0864512a4ea |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | 5540a01c-c93e-5906-8f98-bd1b406c3cc0 |  | note | Conformance Criteria - Shall be installed as per manufacturers specifications & recommendations
label | cabc965d-08d2-572e-bf0a-c555c621eafe |  | note | ○ Drainage blanket shall be placed between the compacted fill and the excavated face to terminate at the subsoil pipe. 110mm smooth bore perforated top side subsoil piping and 110mm non-perforated HDPE outlet pipe with minimum pressure rating of 3.2 bar is required.
label | 63398945-2735-5c75-bd68-1288a9e95654 |  | note | Records - Photos, Survey as-built
checkpoint-status |  |  | checkpoint | 3.16 - Subsoil Trenching
label | 09e58d30-e0cb-5a2f-b2ca-a29d5062b140 |  | note | ACTION (Hold, Monitor, Witness) - M
label | a6ce695e-95d2-5962-a5e9-56d5b736e4e5 |  | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical section and details
label | 0f111f0a-46bf-530c-b610-234edb064916 |  | note | Frequency - 10m intervals
label | 6a997cd9-ce72-5148-bd44-14e54f2dd4f8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
label | bd7813ea-f536-58e0-a40c-419b7f2fbb24 |  | note | Conformance Criteria - Inspect trench profile and ensure it is 0.300m wide and 1.000m below Edge of Seal level.
label | eb4b072d-aab5-5128-9ebc-db3eb97c0c9f |  | note | Records - Photos with measurements
checkpoint-status |  |  | checkpoint | 3.17 - Subsoil Trenching
label | efc20360-68fb-5e91-900f-a7c92967d192 |  | note | ACTION (Hold, Monitor, Witness) - M
label | d196c6f8-977b-5c58-bacc-73e4c703f802 |  | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Technical section and details
label | aaaccc7c-8bf1-5369-a52b-1c204de881f8 |  | note | Frequency - 10m intervals
label | 9e7058de-e71f-51c0-a007-d87df2c48d68 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
label | 4e7ca109-8b91-57e2-bb2d-c6e78fa9bcc7 |  | note | Conformance Criteria - Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
label | 0e82f39d-6301-5fbb-b31f-b25960237c70 |  | note | Records - Photo / CS-4001 Subsoil Dip sheet Check Sheet
checkpoint-status |  |  | checkpoint | 3.18 - Subsoil
label | 956dec9a-2e00-5d4d-9100-73972d249f82 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ed558e4c-fefe-5d11-83bd-422acdd0e539 |  | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall
label | c852da83-fa4d-5f16-acc2-e4366e2340b4 |  | note | Frequency - As required
label | bc88fbfa-2898-5bbc-8d6f-b8c64f816aae |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 990b6148-0ac5-516f-9af5-f5de30a5b81f |  | note | Conformance Criteria - CPS Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
label | 900d6d01-5786-57a5-8d89-70731751927e |  | note | Records - COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.19 - Bedding, Pipe Installation And Backfill.
label | e8346ac5-a210-57bc-876c-90ee5fa0adac |  | note | ACTION (Hold, Monitor, Witness) - M
label | f4d706d7-d489-507a-87cb-7d23fc341be5 |  | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall
label | 405abaaf-bd58-5cef-a34a-cb693042c8aa |  | note | Frequency - 10m intervals
label | ffc9c373-45db-584e-ae69-3b75545dde5d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 8ff2d7f5-5142-5c06-9fdc-d0e15842d11c |  | note | Conformance Criteria - Upon completion of trenching Class C or similar approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material
label | bf1ca02a-70cb-59c9-b3bc-fc41bbe5c3d1 |  | note | Records - Photo
checkpoint-status |  |  | checkpoint | 3.20 - Bedding, Pipe Installation And Backfill.
label | 63830962-d91b-5753-9156-e436d761b7df |  | note | ACTION (Hold, Monitor, Witness) - M
label | 0698575c-dc18-596c-b44d-24e0360dbd61 |  | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall
label | 78968be7-2bae-572d-8c2e-bb9025ca114b |  | note | Frequency - 10m intervals
label | c42a08b9-5ccf-5778-8d6b-78f04a009952 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - 10m intervals
label | 2c34f94a-13cb-570f-92c6-8e0a2b963694 |  | note | Conformance Criteria - Comply with NZTA F/5:2013
label | 88dbbd69-7f6f-545b-83d4-26f3b4df99d7 |  | note | Records - Photo, survey as-built
checkpoint-status |  |  | checkpoint | 3.21 - Bedding, Pipe Installation And Backfill.
label | b1a4c6eb-f9aa-5bf0-95d3-f18676cc71f8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4dcfe16d-8a14-527f-9dbc-a44742f60f79 |  | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall
label | 5228e9d5-5fe0-50ca-83e4-aee25b198d8b |  | note | Frequency - 10m intervals
label | 04f2f99a-883e-51fd-b933-9277b2201330 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 4dc5f20a-390f-5f0a-a3cb-869ba85ba89c |  | note | Conformance Criteria - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
label | 7bc6b002-186a-5be8-949b-7e8f3f8426fd |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 3.22 - Bedding, Pipe Installation And Backfill.
label | c76f3d4e-b73f-530c-bc05-fa6e1faeebb0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8342cddb-04c3-54df-9139-6ecd7e0f6fc2 |  | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall
label | 30bf7f10-f865-5611-b269-e5500eee7b0d |  | note | Frequency - 10m intervals
label | 00b56c66-80bc-5a02-afdc-051891a620bb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | c246e9b3-f40a-597b-b883-48c51520c8b3 |  | note | Conformance Criteria - As built Survey the Pipe before backfill
label | 4174ba12-1551-5ad1-969f-0f0bae75f23f |  | note | Records - As-built receipt
checkpoint-status |  |  | checkpoint | 3.23 - Construct Terramesh Wall
label | 974100ad-2356-5847-a8a5-2c1fe91b7ad7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f9f6b32f-9f78-5460-89bb-b1bce0259885 |  | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Typical section and details
label | 9fbbc84b-9147-5ac3-bffc-c354b9e8f910 |  | note | Frequency - As required
label | 389a0df3-08ed-5cee-9723-717836c09f04 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual / Survey
label | bddba460-7f74-519d-8f18-fb2da55f5bd3 |  | note | Conformance Criteria - Install grid layers as per drawings and have Design Engineer signs off each layer.
label | 957b9ca0-e453-5d15-bbae-9c3f7c936199 |  | note | Records - Survey Receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.24 - Construct Terramesh Wall
label | 38e0c2a0-7f17-539f-bb27-76e3be698f5e |  | note | ACTION (Hold, Monitor, Witness) - H
label | cbd8da1d-10d1-5e01-ad3f-f5aa57111890 |  | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Typical section and details
label | 6b714461-1b65-5524-8a12-dd8036b04d60 |  | note | Frequency - As required
label | ebab8958-4d04-5c54-9440-a650f112d0d4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | a07c802a-7f2c-5049-945d-c0edbdbaf491 |  | note | Conformance Criteria - Install Tenax Rivel / Maccaferri Green Terramesh cages as per Manufacturers specs along the front face of layers to ensure correct line and level.
label | 9165f205-36b5-5fcd-89dc-8309e3ec3da6 |  | note | Records - Photo's and COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.25 - Construct Terramesh Wall
label | 0b8e1269-0575-52ee-9d5f-f62a16d135a7 |  | note | ACTION (Hold, Monitor, Witness) - M
label | b9d7cc37-b060-5b5e-82a6-90c3b54580d5 |  | note | Detail - S.H.2 R.5 R.P.443/16.29 - Tauwhatinui Bridge (BSN4593) Terramesh wall, Typical section and details
label | 50784016-4e5c-5b66-b9e5-9cfe6313c525 |  | note | Frequency - Each Lift
label | 84afb209-a865-5f2d-9d04-873562025b09 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | 9181a345-568f-5e95-9bb3-bd66d9b9568e |  | note | Conformance Criteria - Ensure line and level of front face is as per design
label | 118e55df-365b-5f59-a9f5-801cff189504 |  | note | Records - Photos, Survey as built
checkpoint-status |  |  | checkpoint | 3.26 - Rock Facing
label | 75913ec7-68e2-541f-89f6-ba1ac8392fde |  | note | ACTION (Hold, Monitor, Witness) - H
label | 87e08d4e-a5de-5b8a-a8e6-2dbc5f858f34 |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | fe6817de-1928-519c-a2f0-ffd7ea7228dc |  | note | Frequency - During Construction
label | 3ad4f771-e246-54b1-8eb4-84f90d0f9f4b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | 8f336803-494c-5119-ab06-f0fd74db8f90 |  | note | Conformance Criteria - Boulders to be placed in front of the terramesh wall. The extent to be confirmed with the CPS engineer.
label | 3614a115-510c-56a7-93e6-e2b79fa14162 |  | note | Records - Photos, Survey as built
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Rock Facing
label | 425b9895-4778-5c53-bb3c-77e6aec1ab39 |  | note | ACTION (Hold, Monitor, Witness) - M
label | d195ca5a-f5c1-562a-a6f0-a187082baee2 |  | note | Detail - 2-U3436.BM(24)_Tauwhatinui Brg_C000-C202
label | 081fab49-4acf-5ddb-8d5d-dc445351bc1b |  | note | Frequency - During Construction
label | fb463930-1e4f-55aa-a212-0d0238689990 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 98fd09d3-290f-5614-9414-6b5e50c8aa38 |  | note | Conformance Criteria - All Rock Shall Be Placed In A Stable Secure Position Utilising Three Point Bearing On The Underlying Rocks. Bearing On Smaller Rocks Which May Be Used For Chinking Voids Will Not Be Accepted.
label | fc19273b-4958-53a7-8270-a170ad60f7ad |  | note | ○ Local Surface Irregularities Of The Rip Rap Protection Shall Not Vary From The Planned Slope By More Than 300 Mm Measured At Right Angles To The Slope.
label | ea9e5575-7127-5c15-a2c7-9114e3ee76ba |  | note | Records - Photos, Survey as built
checkpoint-status |  |  | checkpoint | 3.27 - As-Built Survey
label | 32d83b69-2d5c-5253-ab57-11b580c8cb95 |  | note | ACTION (Hold, Monitor, Witness) - H
label | dd5fc96f-4398-5022-9cd6-f991144a2c19 |  | note | Frequency - At completion of Lot
label | b851404c-ccd1-5249-af6d-7fdfd46b7b5d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | 46b4f5ae-42b6-598e-9e43-7e6ed054e8eb |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | e823785c-3355-5b1e-8631-554bd70da03b |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 4: Final Inspection and Handover
checkpoint-status |  |  | checkpoint | 4.1 - Quality Assurance deliverables
label | c0ad5ee2-8a04-5c5b-913f-638f28960d04 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4615ed41-5d2b-54c3-8537-33ca4c290921 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 835c7171-51ab-59b6-a542-e2cde082b5e0 |  | note | Frequency - At completion of Lot
label | 59999a2a-4372-513e-bc96-3594d8a22e3f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 8d96ba58-039a-5f57-b5b2-86c18826f99f |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 53312613-c377-545c-b66e-ebf59cf477cd |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 4.2 - Completion Sign Off From Fields Below
label | 6c05bc33-ad66-5629-aa68-1a30afb1e06c |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | ITP - G1202B - Waikare Riverbend SH38 - Rock Armouring & Bulk Filling | itp |  |  |  | Yes | ITP - G1202B - Waikare Riverbend SH38 - Rock Armouring & Bulk Filling | 1452590a-4bf6-413a-8120-de21fbe63380
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 0c44dbcb-a284-5af2-a9e6-64ea7dcdd31c |  | textbox | CPS Eng.
text | 0682470e-7f3c-533e-8647-de0deeee9a2e |  | textbox | Site Engineer
text | 4158f4ab-b17a-5f3e-a32a-ff41e5cf5eb1 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 6e1d6436-ed72-5db4-8768-0eca50ce97fb |  | note | ACTION (Hold, Monitor, Witness) - H
label | 06958738-b638-5c82-82f0-a32af27b3156 |  | note | Detail - Set out lateral extents of buttress. Geotech Engineer to confirm extent of works
label | b0978575-c6be-5546-b740-9cf3b50b8361 |  | note | Frequency - Prior to commencement
label | 73ba85cf-3a32-58e1-b2a8-0ea1609b0a58 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | f6cc68db-78c6-56dd-b033-f1f2ab523874 |  | note | Conformance Criteria - Fault ID 529B - Underslip Recovery Remediation Design Report
label | a1415ee3-cf00-5ed4-8b5d-841a03746ffb |  | note | Records - Survey receipt / sketch markup
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | 0a259225-36ce-576c-adf5-36b9ea187156 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d8e3f95a-0de1-57a6-9e99-f036ddcda0aa |  | note | Detail - The buttress slope face angle should be 2H:1V. The buttress slope face angle may be steepened to no more than 1.5H:1V if required by site constraints, at Geotechnical Site Engineer's discretion
label | 6fc4fb2a-005e-5d67-9505-9f0bdbad0d8f |  | note | Frequency - Prior to commencement
label | 18c9fb5d-dc52-5297-a336-12d61487ce15 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 4893bab3-08ed-5261-90de-2403c05a66ab |  | note | Conformance Criteria - Fault ID 529B - Underslip Recovery Remediation Design Report
label | 52fe9713-359c-58b3-85da-2427cd678b70 |  | note | Records - Sketch
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Excavate to Sub-Grade
label | 911fea95-d1a5-550e-ad09-b80a3188e8a9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a1291362-35b2-5c46-b20e-b5a9c85f4ac1 |  | note | Detail - Excavation only to start once ESC in place as per ESC ITP. Inspect fill foundation.
label | dcc5e9a5-b8de-5608-a4f2-f5eccd3776ed |  | note | Frequency - Per area as required
label | 20ba246c-976e-5b32-8f5d-a23abb08fb49 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | e2bc1ac1-0201-5dec-b7a9-1cda797ae55e |  | note | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
label | 2691f704-d838-525a-9285-c299493767b2 |  | note | Records - CS-4100 Subgrade Approval Checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Excavate to Sub-Grade
label | 9b4b959f-8904-52f9-a367-1834abbe2d5b |  | note | ACTION (Hold, Monitor, Witness) - W
label | e92a244c-a231-590a-85dd-20f31a526ce8 |  | note | Detail - Foundation compliance. May be performed by site engineer or CPS as is specifically only for ground strength data for future review.
label | 5ff8630e-2816-50e8-931c-8bec24628337 |  | note | Frequency - Per area as required
label | 9d870814-0589-53c9-accf-d73af17400a8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
label | 071229a1-b748-5a0d-84ca-db9a225d4bcf |  | note | Conformance Criteria - >= 1 test per 10 linear metres, where access is practical and available
label | 1fc24bda-7466-50a3-98e1-070a3d7c3933 |  | note | Records - Engineer or Lab Test Report
checkpoint-status |  |  | checkpoint | 5 - Material Compliance Testing
label | 4bebe36e-231d-5645-baa3-34bb678f8443 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 52995b27-310b-52a4-8c31-ad45f1db3751 |  | note | Detail - Material to meet specifications dependant on material type selected
label | 5d58ca03-d56d-5759-bdc8-9a6005411bdb |  | note | Frequency - Each material used
label | 4200d30c-bec0-5601-8456-b61d7c58a0a3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 75949cf9-7bee-593b-b6de-cf6fe6d1036a |  | note | Conformance Criteria - a. GRADATION D85/D15 = 1.9
label | 07a4f063-7a70-50ae-8e16-551f685369d5 |  | note | b. D85 690 (MAX) AND 590 (MIN)
label | 46043b8b-e102-5798-af28-9a312653fa9c |  | note | c. D15 390 (MAX) AND 275 (MIN)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Material Compliance Testing
label | e9b9da3c-ad84-58b5-96e6-fb1a1b110387 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a74ae0d6-5a57-5801-92fb-a57038258bc0 |  | note | Detail - Rock Construction Material
label | 0a8947a9-a53c-56f4-ab4f-0976fff3cba7 |  | note | Frequency - 1 test per 1 000m3
label | 873bc116-db2c-5079-9f44-dae34fd6ca4d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | c8d06fb9-7275-532e-8ed0-21a47998a4d7 |  | note | Conformance Criteria - D50 OF 450 WITH A MINIMUM SPECIFIC GRAVITY (SG) OF 2,350kg/m3
label | 386a978e-7a13-5919-9e26-efa07575ca31 |  | note | Records - Lab Test Report
checkpoint-status |  |  | checkpoint | 7 - Material Compliance Testing
label | ce2dff68-90fc-5993-b3e7-6f0cbcfad31a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8886ed75-609a-5616-9cba-19398bdbfdc1 |  | note | Detail - Back Face Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A39 (Class D) or similar
label | 9228d9a2-928d-5ab0-ac69-30a740311bb7 |  | note | Frequency - Prior to commencement of placement
label | 12c4a93c-1ad2-58c4-ac56-40475efc7993 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | a22fd8d3-a192-51d9-a975-6a0b3f6d8d5a |  | note | Conformance Criteria - Conformance with Specification
label | 2aa9fd0b-40c2-50cb-87a8-bc511c7ab58a |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 8 - Material Compliance Testing
label | dc1bd04b-6404-5bfe-8402-43b3e8f00b00 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e5d40a2c-cce4-5ec5-9431-a4e3f24f5894 |  | note | Detail - Between Rock Armour and bulk fill Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49 (Class E) or similar
label | 17c3a3dd-7949-57e8-af80-83ea476bf2b3 |  | note | Frequency - Prior to commencement of placement
label | 9f66f6d7-bbe7-57ee-8813-a416bf9016e3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | baebd6c6-0914-5e92-ba0b-6121f3b83492 |  | note | Conformance Criteria - Conformance with Specification
label | e72d98f9-682a-5079-b137-601905aa38b3 |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 9 - Material Compliance Testing
label | ad224f25-5185-5b59-ac12-4178991431f1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ff3f3e55-422b-5e3e-a39c-2baa8cb0ccea |  | note | Detail - Bulk Construction Material
label | 7abf819e-bc0b-5a7a-9a5c-2a13c6a2d442 |  | note | Frequency - 1 test SET per 1 000m3
label | c8efebfd-bc40-56ee-a6fc-dc6fabc43a39 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing - OMC Standard Compaction; Grading Curve (wet sieve)
label | 53ed14cc-dd53-541f-9666-fd05d96acd84 |  | note | Conformance Criteria - All bulk fill comprising clean graded granular aggregate with broken faces AP65 (i.e. gravel).
label | 58322e43-87d6-5dbf-abe4-1af280455107 |  | note | Records - Lab Test Reports
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Geotextile Placement - Backface
label | 4df6e343-a6a0-57c1-93d5-7862f79a4629 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 852c2c8e-0eb4-5e7a-bfe2-e12a481397a6 |  | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | a7e3fc36-855e-5c67-a4f8-f5aae10dd21f |  | note | Frequency - Daily visual check
label | 284f8e57-3293-5593-80be-1612a7c14a25 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 11c6ce00-568b-57eb-a46c-72b2b9296911 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 11 - Backfilling of Engineered Fill Embankment
label | 5026a80e-09c7-523a-9a70-ca258fccb183 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b4243553-ca56-5f18-8647-cedf50375f5d |  | note | Detail - Engineered bulk construction material 250mm lifts with material and regular compaction testing
label | 3a58dab4-44a8-5a79-8c8a-36ee722c28d8 |  | note | Frequency - 1 test per 10m linear length (forming a test set). At least 1 test set every 2m fill height (minimum total of 3 evenly spaced test set intervals over total height of bulk fill).
label | be4b94e1-aa98-520e-b594-34868aacf8e6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing - NDM (required), supplemented with Clegg Hammer tests at discretion of site engineer.
label | 88c98214-4caa-5ef3-92c5-8b14132dfa6e |  | note | Conformance Criteria - 95% of MDD or clegg equivalent
label | 799bca98-57ab-586b-958f-b8e716f44d15 |  | note | Records - Lab Test Reports
checkpoint-status |  |  | checkpoint | 12 - Construction of Engineered Fill Embankment
label | 26165f01-da70-528f-b2c6-5467ff12efdf |  | note | ACTION (Hold, Monitor, Witness) - H
label | ade8082d-2f68-5f9e-b9a0-00cf38d88896 |  | note | Detail - Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap
label | 455085a8-75e9-5976-88fe-f17bdb965e4c |  | note | Frequency - Prior to commencement
label | 05a86ff5-4047-5e3a-a11e-37f972e3d772 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | ff715518-49b4-59d6-b3e4-34994946df36 |  | note | Conformance Criteria - ALL BULK FILL MATERIAL SHOULD COMPRISE CLEAN GRADED GRANULAR AGGREGATE AND HAVE BROKEN FACES AP65 OR SIMILAR MATERIAL.
label | 73e52732-dcad-5b4a-b4f0-5eb3596f6bc4 |  | note | Records - Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 - Geotextile Placement - Frontface
label | 5364dabc-b5d1-5dff-806f-0e9dd9b33afa |  | note | ACTION (Hold, Monitor, Witness) - W
label | 21cc58de-fdcd-5a3f-893e-a61f6e9c9e0d |  | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | 70eec4fe-9487-5d39-bb73-cb6d29519131 |  | note | Frequency - Daily visual check
label | f1e262c8-1a4a-5457-a126-51f22ac57bb2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | f4fd5606-6907-511f-88f5-85a9600151f2 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 14 - Riprap Placement
label | 9cb2cad6-27b6-5705-ae85-7857b7048d3f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8b1e479a-71f2-547d-8180-610022b1e858 |  | note | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. Design Engineer given notice to visually inspect initial placement of riprap material
label | f1c53bf2-0323-5436-87ac-72de46b77398 |  | note | Frequency - Daily visual check
label | 3d479750-866b-50d8-8fa2-6db77ded6560 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 696bd550-2ca0-5180-a302-19a3f5569241 |  | note | Conformance Criteria - Specification
label | 656e9eb1-08c1-53ea-b306-484d6ddc12d5 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 15 - Quality Assurance deliverables
label | 44d2f1fc-b80d-541e-98c3-6406c8b3a5f2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c33608c3-442d-5872-80d0-a72ab3d976fc |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 6e2fa082-51c1-57d7-871b-a55f8a830f5d |  | note | Frequency - At completion of Lot
label | 271baa8f-83b9-5751-8098-c59b02c0b9fc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review. Red line mark up notes of design plan.
label | 0b649d11-3747-513e-88e1-ce0f86b47354 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | f929f53f-be5a-599c-9b23-8ea7cea16efe |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 16 - Completion Sign Off From Fields Below
label | 35617f7a-73d8-5894-84d7-bc087b533e3d |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | ITP - F3002G - Mangahuini - Driven Pile and Concrete Buttress | itp |  |  |  | Yes | ITP - F3002G - Mangahuini - Driven Pile and Concrete Buttress | 16d67872-34dc-46d5-abd6-75d9f8e815e1
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Project Site reps.
text | b83b48a3-7df1-5d0d-afd3-d9b4ffe2c781 |  | textbox | CPS Eng.
text | a7fa664f-c6da-5edc-9061-190b7182fffe |  | textbox | Site Engineer
text | 4c1950af-ad1c-5e56-88ab-a2664afc00e2 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 4c1edf87-11fb-511c-9dac-b41434318ae0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9795616a-7b9a-59ef-9385-2dc7bb73db61 |  | note | Detail - Set out line of pile as per contract drawings and specification.
label | 45d83aec-5e11-5cb0-803f-98553899211d |  | note | Frequency - Prior to commencement
label | 2cb56425-4431-5a3f-a00d-2bacf87fbe11 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 00419cc6-2628-5442-bc22-2add6594ddfd |  | note | Conformance Criteria - Consistency with Construction Drawing
label | ea382de3-2719-522c-a8c2-dd61556f361d |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 -
label | 5b4b8db4-f585-5ea6-8a07-cd5467a88e1f |  | note | ACTION (Hold, Monitor, Witness) - W
label | b63f25e0-26fb-5b08-aae3-861ace5d3093 |  | note | Detail - Any services in the area are to be clearly marked before any work commences and to be potholed to confirm their location
label | 6af9e722-921e-5946-aec6-0879beb73edc |  | note | Frequency - Prior to commencement
label | c7672b76-6802-5254-a7c4-f1d70dc3fb73 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 93e488a8-5e38-51eb-a3ae-c3c3886681aa |  | note | Records - Site record sheet/Daily diary
checkpoint-status |  |  | checkpoint | 3 - Material Compliance
label | 63f18d8b-7adf-54e0-9be8-5909fba258cf |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0164a95f-3e7c-5138-9acc-302583d546a5 |  | note | Detail - Driven piles to be 310UC137
label | 14d7108b-c0c1-5be3-a2de-c2d7803cb4fa |  | note | Frequency - Prior to commencement
label | 121c1fa7-fd7c-5329-882d-b8ce26ad77c6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | bb66e546-d918-5182-9951-4594a49b6b4a |  | note | Conformance Criteria - AS/NZS3697.1 & NZS3404;1997
label | 2763e0ca-7038-56b1-adaf-3d6a4985f89b |  | note | Records - Data sheets and mill certificates
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 -
label | 4d9b4479-baed-5fe3-b7f1-98508bcdde0d |  | note | ACTION (Hold, Monitor, Witness) - H
label | e4eceb23-3cb0-5000-b225-88534f8c7b20 |  | note | Detail - Walers to be 200UC52.2
label | e5e77908-9cf6-530a-bbfa-c9ce6f8c8dd5 |  | note | Frequency - Prior to commencement
label | 50b7d8f6-c2a0-5dd5-be4d-2f8fbc8d91d4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 292d2729-8a76-562e-b0d6-9146c2e5d803 |  | note | Conformance Criteria - AS/NZS3697.1 & NZS3404;1997
label | ba50b2f5-ce12-56ee-9ec2-d52f698e6bbf |  | note | Records - Data sheets and mill certificates
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 -
label | 050bb266-aae9-56ae-990b-3e5eb69313ea |  | note | ACTION (Hold, Monitor, Witness) - H
label | e0c519ce-7b2e-56de-87f5-bd636c879b1c |  | note | Detail - Steel Reinforcement shall comply with AS/NZS 4671 & NZS3109 and shall be the grade 300 as shown on the drawings
label | d68d46fc-69ee-53d6-88e2-f7bdaed39d95 |  | note | Frequency - Prior to ordering steel
label | ac8114a7-68e4-5b60-9bfa-bdfb81d03018 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 2839fc17-743e-5a92-9659-f2be9b1b384e |  | note | Conformance Criteria - AS/NZS4671&NZS3109
label | bdb8bfd9-5e5c-516c-aac3-efd17849984b |  | note | Records - Detail Sheets and Mill Certificates
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 -
label | be0e4ae3-3d30-59c6-b8b3-4ba581853b40 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 70e126ed-2f22-5ad1-a821-2d2241add272 |  | note | Detail - Any welding or mechanical splicing to be approved in writing by the CPS Engineer
label | 697d9d95-238e-5a79-a817-7e0e830efed5 |  | note | Frequency - Prior to welding or splicing
label | a8c75b7d-878e-5119-862a-3f0948b1499a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 78240f4d-a604-57bb-8a92-8caa35c33292 |  | note | Conformance Criteria - AS/NZS1554 part 3
label | 4f288608-d45d-5042-a324-bbc31203f6b6 |  | note | Records - Mark Up As Built Drawings
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 -
label | ad9ffd7e-cf8e-5577-b74b-6218dd53e956 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e56014cf-f442-5fd3-9a8d-a90f5d72d769 |  | note | Detail - Any reinforcement requiring cutting or bending on site to be approved in writing by the CPS Engineer
label | d4028933-0996-5806-bcf1-e38ff6982e34 |  | note | Frequency - Prior to cutting or bending on site
label | 32359a3e-5f5f-5db7-8ac5-86e44e25ee7f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | acc50786-ec71-56ad-9e1d-6b9e3e56c426 |  | note | Conformance Criteria - NZS3109;1997
label | f0d7ad2c-7902-5f29-aa69-5cb44c976268 |  | note | Records - Mark Up As Built Drawings
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Pile Line
label | c265c885-d832-5792-8c5f-ada1a5f7ccea |  | note | ACTION (Hold, Monitor, Witness) - H
label | 514b539e-57df-5e1b-b541-6c2dedab05c6 |  | note | Detail - Check if the bench has been excavated/filled can accommodate the entire pile line
label | 77eceded-ef0e-5861-8b27-7ee3a7a9cc9f |  | note | Frequency - Prior to Commencement
label | b8bc6884-0008-5297-a8ba-ab52f9d76b31 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | f415db86-b807-5b3b-b7e7-8ddcd30ae6ef |  | note | Conformance Criteria - Relevant Drawing & Survey set Out
label | 14718fdc-de16-5e6c-89d9-00af409f75dd |  | note | Records - Site visit agreement
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Driving Operations
label | ce761580-9ede-53d2-9f71-a2d951cfb30f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 57c2d411-bb2d-591b-875f-2fd90db788ea |  | note | Detail - Check driving performance, verticality and position
label | 67479033-5940-5c62-99d1-0344e75337ac |  | note | Frequency - Each Pile
label | 32926d4d-c7da-5b60-b005-f2601706ca96 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 6cbfb8a1-a9e2-5851-8153-720320124aa4 |  | note | Conformance Criteria - Piles to be drive vertical checked with a spirit level
label | 77d9fac7-c4a5-5b5d-8044-1db5bfb0dbfd |  | note | Records - Piling Specification, Relevant Drawings, Pile Card
checkpoint-status |  |  | checkpoint | 10 - Testing
label | 2bd8d1fa-f9f7-5006-9022-6c9edca9e45f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7b0d71f4-4833-50ae-91aa-63b686337871 |  | note | Detail - Ensure penetration depth of 3.8m is achieved
label | 7b9da82f-c327-55ff-99a5-e513f8b07b8b |  | note | Frequency - Each pile
label | 7ce687c7-bfc1-575a-bc24-1a189856fc87 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - measurement/visual inspection
label | 1ddda249-ab24-5eb6-8c1c-64de161e1584 |  | note | Conformance Criteria - 3.8m embedment in river bed in acordance with Design Depth
label | 72136b54-bf8c-5876-a7f0-ef02be9413cc |  | note | Records - Pile Card record
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Reinforcement Cage
label | 1b336a26-ded0-5d41-b189-b6e811edb999 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ee223243-2d0b-543d-8481-65563eefa8e7 |  | note | Detail - Check supply and installation of reinforcement cage
label | 9a31dd6e-86ad-5299-a8a9-ac369355a1df |  | note | Frequency - Each cage
label | 47640df9-bcd5-5d45-b64a-afcca28aa09c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review & Visual Inspection
label | 005cb709-f6df-5c7e-8908-8973669b8d3b |  | note | Conformance Criteria - NZS 3109 and being in accordance with the drawings, ensure cover of 50mm from face of formwork
label | 77e02181-0546-55b1-bc6c-f3d00c73a2f5 |  | note | Records - Reinforce cage record and site photographs
checkpoint-status |  |  | checkpoint | 12 -
label | c6f87830-798a-5894-827a-01f04ef4d6a8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 98c60a6c-ae95-5a44-bf51-8df557b8b063 |  | note | Detail - Arrange for inspection of installed reinforcement cage
label | 8072c07e-7e94-5d47-bee0-0be089585c1a |  | note | Frequency - Prior to placing concrete
label | d6d57f61-b71c-5be1-8047-f2d7fd831d7b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | deaddb39-94da-5d58-9e8d-ab9e118aa30c |  | note | Conformance Criteria - In accordance with the drawings ensure cover of 50mm to formwork and 40mm cover to piles and waler
label | 54e624a9-29e9-52ea-9e66-d333655e5528 |  | note | Records - site photographs/ inspection report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 - Formwork
label | 15d2a0b3-b8fe-5db8-a1df-7f3a748fd8c7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9ce47331-ecac-50c7-847e-b0edcd4dc1f9 |  | note | Detail - Ensure formwork is competent to contain the required volume of concrete
label | 28f1d376-0b76-53d7-9794-206d711f839e |  | note | Frequency - Prior to placing concrete
label | 51454960-4e03-5502-a793-4c6b6f2840b9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3ecc90ce-c71b-527e-a5a1-627a3ebd2b1b |  | note | Conformance Criteria - 50mm cover to reinforcing. Formwork is straight and true
label | 62648827-de6c-5fc1-a5d6-34c4bc985cdd |  | note | Records - site photographs/ inspection report
checkpoint-status |  |  | checkpoint | 14 - Concrete Pumping Operations
label | b6eb8fd4-d073-5953-a81f-5a6fb89ada31 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ca9d3b58-a5f7-52b0-aa78-2c3e1e68f63e |  | note | Detail - Concrete required is a 30Mpa mix design required for a pump mix is 13mm aggregate for pumping
label | f99ed9e6-317c-5653-a068-801c58152a3a |  | note | Frequency - Prior to commencement
label | 7113ef0b-734c-5449-9c16-89caa11090c2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | d42376b8-45a5-5128-a503-0b342e030d2c |  | note | Conformance Criteria - Concrete Mix design acceptance
label | 77d37329-54f6-5411-b101-5a61923ef78a |  | note | Records - concrete mix design approval prior to comencement
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 15 - Concreting
label | f88e8def-645f-59c6-b031-117fbc8f4fcb |  | note | ACTION (Hold, Monitor, Witness) - H
label | c9c054fe-09a0-5e7d-b992-f3f1f51bc894 |  | note | Detail - Pre-pour inspection and check sheet is required prior to comencement
label | 31539dbf-229c-52af-8188-9a5e643a14a0 |  | note | Frequency - Prior to concrete pour
label | 6ce53a33-402e-5fb9-90ef-04c5ecbbcf69 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 11b84f34-fca4-58de-a1a8-7d104eda2c26 |  | note | Conformance Criteria - Concrete Inspection check sheet sign of
label | f7c60a78-de74-529c-94f9-a79b2145eadc |  | note | Records - Concrete check sheet signed off
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 16 -
label | 6b71a992-0f89-5fde-b9b3-8e272f5bb19c |  | note | ACTION (Hold, Monitor, Witness) - H
label | fd2d5ee9-1d7c-5c66-9705-8753c9d3f8ac |  | note | Detail - Concrete dockets checked for correct mix and concrete site testing undertaken. 1 sample set per 10m3, 10-25m3 2 sample sets, 25 to 50m3 3 sample sets
label | 83fb1eba-783b-502b-93f7-4faa36944f3d |  | note | Frequency - Prior to concrete pour
label | b85967ea-8a15-55dd-a879-9f504bfa192a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Test Results
label | 7aa6c9c9-bc7b-5e44-b3a0-0f97bfe6c940 |  | note | Conformance Criteria - NZS 3104
label | f13a9e4b-d7f4-5c2b-b5f9-5219c48ab0bf |  | note | Records - Concrete docket & Concrete test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 17 -
label | cf20a106-4b21-5289-9cb3-1446db16c311 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9ee2979d-5b97-5fc6-bba5-29779474aad2 |  | note | Detail - Post-pour inspection and Check sheet for concrete placement method and finish
label | 43c0e116-affc-5785-b1be-26e249a53434 |  | note | Frequency - At completion of pour
label | 6135e4cd-fd60-527d-85dd-adfad8db71d5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
label | e9c433f0-956c-5870-aba5-9c6204953368 |  | note | Conformance Criteria - Concrete Inspection Record
label | 6c46f996-1179-5d6b-8c24-d83fda4d2716 |  | note | Records - Concrete check sheet signed off
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 18 - As-builts
label | 76e9ca74-a2e5-5d7d-9386-52a5d53a837d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4e7a11f1-f795-5939-a0c3-c7353c5826b9 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 05427f48-a7f8-5a06-85de-4d974aa84720 |  | note | Frequency - At the completion of the Lot of work
label | 66ba4f71-c521-56fa-ab3c-3d54c4e14329 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 4f504f53-2dc4-5a82-93ba-60c4c19adcef |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 19 - Quality Assurance deliverables
label | 2e588117-a59c-5115-8248-49af172aa03a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 621757a6-cbae-574f-a206-76c60108518d |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | ac858838-1557-561e-9bc7-cf096c8c5920 |  | note | Frequency - At completion of Lot
label | 5f117cea-5b38-514f-b12c-7d32d067e8cc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 3bca6603-a25a-50aa-9f52-14a7de144f01 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 2cd137c8-ae57-57c1-85a2-a865dd536304 |  | note | Records - Asbuilts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 20 - Completion Sign Off From Fields Below
label | 970acaf9-ceb8-50d0-9fe0-0e6572edfd46 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b8293da3-1477-5297-9e66-3885aab032ac |  | note | Records - Signatures
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - F3202A - Culvert ID 614 | itp |  |  |  | Yes | ITP - F3202A - Culvert ID 614 | 198da203-19c9-4d91-875e-d1d8e191d2d4
checkpoint-group |  |  | section | Section 1: RECEIVING INSPECTIONS
checkpoint-status |  |  | checkpoint | Project Site reps.
text | f1c0b22f-bf16-5f5a-81ba-adf0948edef9 |  | textbox | CPS Eng.
text | 3e1ad4e6-bf4c-575d-9c2f-e926f7251ccf |  | textbox | Site Engineer
text | a4c2b72e-98e5-54a9-a612-23a0a9a345c8 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Rock Armour (D50=450)
label | 6c39692b-6961-5fbe-8572-d5d85ad6169b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6120b79a-254c-542a-9e08-0eee147e83f1 |  | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
label | 8e5a7e23-f3bd-599a-8ab1-f925d09dc4c2 |  | note | Frequency - Prior to commencement
label | 9ec585a5-5910-5e58-bb0c-c346ea58cc39 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | b2e6de74-3d6e-574d-80a0-dd5be51e2b9f |  | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material.
label | 7596ca68-bfb8-519a-9b5a-6ed7e5d2356d |  | note | ○ Shall have a D50 of 450 with a minimum specific Gravity SG of 2350kg/m3.
label | fae7f3ce-bfd7-5c5a-8296-f839bc095dba |  | note | ○ Rock size to be confirmed by CPS Engineer
label | c9667aa7-84e0-5cd3-9812-85d57406e8a5 |  | note | Records - Material source test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Bulk Fill (GAP65/GAP100) or similar
label | 82f33349-0f17-561a-95e5-5424abeebe3a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3ad961b3-435f-5829-aedb-2d7252d900e0 |  | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
label | 414cfcb9-86bd-5619-8040-7f16682cab7b |  | note | Frequency - Prior to commencement
label | 41b068d9-5d8a-5a33-aa2a-9bc9cb2f16b7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | b23ba344-d198-5250-9fc2-b249012a68dd |  | note | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
label | 19c36cc1-565a-5723-ab43-3197e2bd35a4 |  | note | ○ Material source testing
label | dcccfe01-d031-5ba0-8057-4dfa09eccd71 |  | note | Records - Material source test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Class D A39 Geotextile
label | dcad168a-067e-5371-9d7a-988c3a1c13b7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c4cb42ca-7bf1-5d4d-9c34-df63438f0273 |  | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001, NZTA F/7
label | 83b2cb8c-5ee5-5c0f-b525-991c04d67923 |  | note | Frequency - Prior to commencement
label | 40d12321-9574-5975-a0af-0bd071e1dad7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | da647e4f-eebd-5f8c-b5c1-34647f895649 |  | note | Conformance Criteria - Non-woven & NZTA F/7 compliant before placing foundation material and engineered hardfill
label | dfd37a2b-10a5-584e-87c9-6eeb93ceaf7c |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.4 - Class E A49 Geotextile
label | a2fb517d-e009-5c1d-a6e6-c683689ba8c4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | df719271-d7fe-5622-8ddd-d75c79e49879 |  | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001, NZTA F/7
label | 4b93207f-2635-525e-9271-1941e918aa11 |  | note | Frequency - Prior to commencement
label | 0fa11052-d5ce-567f-9332-48e55301c5d0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 8d3d3dbd-0fba-5a18-8cd6-d461a102fbfc |  | note | Conformance Criteria - Non-woven & NZTA F/7 compliant before placing foundation material and engineered hardfill
label | ee07ec4a-62b9-571c-9088-1aa0e1fca755 |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.5 - Megaflow strip drain or drainage blanket for seepage if encountered
label | e8c4a53d-e969-5abf-a3d8-c35d0e359798 |  | note | ACTION (Hold, Monitor, Witness) - W
label | cfb284ea-d555-5825-bd0e-acc2ded61ee1 |  | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
label | fa5347b0-5792-5f61-9f6c-8e8d828bfec1 |  | note | Frequency - Prior to commencement
label | 2b561ff5-c7f4-5015-93d7-e2b01eddf5ff |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 9c99aa59-f10f-521e-8356-8272055b51b0 |  | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
label | 3a6079a7-8a75-5d84-a036-9f5db52f5100 |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.6 - AP40 (Basecourse)
label | fa2a4822-bdda-5f61-bd01-7aebd39615b1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5b729a51-0086-5e04-95a0-2003af210767 |  | note | Specification/Drawings Reference - TNZ M/4
label | 7161d828-a3a4-57bd-8a8f-ef8448fb7149 |  | note | Frequency - Prior to commencement
label | 13213340-a379-539f-b909-f82ab45452b8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Testing
label | 5ab66b82-57e3-513d-bb27-3e3c1afdf249 |  | note | Conformance Criteria - Comply with TNZ M/4 specification
label | 5c375363-44fa-5294-962f-01fe32a13c09 |  | note | ○ Source property testing
label | 087ec782-cb70-5bad-ba25-0cdd5812da19 |  | note | ○ Traceability of all materials delivered to site
label | d4edb520-edd5-5708-b900-f0893362c00d |  | note | Records - Lab test reports, Delivery Dockets
checkpoint-status |  |  | checkpoint | 1.7 - AP65 (Sub-base)
label | 262396ef-681d-5a8e-aed6-c85ebcafcb9d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 464babcf-17c6-53c8-955e-4d2122679599 |  | note | Frequency - Prior to commencement
label | 43b8ed77-9274-596d-8054-57da8da9b888 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Testing
label | e74ef82b-cd20-5278-9f6a-c23898ecc9e4 |  | note | Conformance Criteria - Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak)
label | cc3c9ef9-6508-5d38-8027-daf63f3cb1b8 |  | note | ○ All fill material to approved by CPS Engineer
label | fed5a7ff-59df-57c2-baf9-073447a33533 |  | note | Records - Lab test reports, Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.8 - Grade 3/5 Chip
label | 2c275679-8a69-57cb-8ed7-bc34cb7e2ab3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d8676812-5959-5fa1-949b-56595589a287 |  | note | Specification/Drawings Reference - NZTA M/6
label | fb645473-11bd-5d38-a952-28f8ce4729b0 |  | note | Frequency - Prior to commencement
label | 0aa99ca2-e06d-53e6-929a-b4f2ab02923d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Testing
label | bb71ae60-c34c-5927-8de7-d350ff18989c |  | note | Conformance Criteria - Comply with NZTA M/6 specification
label | c6fcd170-77bc-5399-8b4f-46082412a0f5 |  | note | ○ Source property testing
label | 738ed4ee-ba3f-5447-bdd4-fadb3282ffb3 |  | note | ○ Traceability of all materials delivered to site
label | a97abd68-1197-5cee-b5ae-a7abfe799e24 |  | note | Records - Lab test reports, Delivery Dockets
checkpoint-status |  |  | checkpoint | 1.9 - Cement Material cert
label | 8a33b583-550e-5bd9-81e1-d401f06fa6cb |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1af6248c-61cb-5288-a81c-b8e181defc92 |  | note | Frequency - Prior to commencement
label | 22d6e878-dc90-5ad0-a9be-9532c6d3e93c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 936f45eb-ff43-5d3b-8fd1-ac4516763db8 |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.10 - Bitumen
label | 7c31e1f6-9287-5eb9-b92c-90e95cad4fe6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4ded7682-4281-53d2-ba41-6d96436548ec |  | note | Specification/Drawings Reference - TNZ M/1
label | e4429fb0-3a61-54f5-94f6-00229a8b0d11 |  | note | Frequency - Prior to commencement
label | 2a5be107-a666-53df-b947-7d1a8529b913 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 5ea3a2ea-c82f-571f-94a8-2a6261b1ae62 |  | note | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
label | 6b336a7e-4ef0-5c1e-a197-fb4b46a6052d |  | note | Records - E2 Certificate
checkpoint-status |  |  | checkpoint | 1.11 - Galvanised Traversable grate
label | ae6672e0-0ef8-5481-a46c-f2230441c640 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4e6d05b8-c105-53f1-8438-9c9015420321 |  | note | Specification/Drawings Reference - F3202A-Culvert ID 614
label | e471f33e-f114-566f-8bbf-f727c659818e |  | note | Frequency - Prior to commencement
label | 06941cb3-f26a-5526-acdd-4c0e84fb7051 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | a8eec299-82fc-5b7f-8384-32244c8a2f2d |  | note | Conformance Criteria - Galvanised Traversable grate mounted on headwall
label | deca79b7-e91e-5f18-9688-00798f0bf39e |  | note | Records - Manufacturer cert, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.12 - Precast Headwall
label | b253cc31-bffe-57e3-9082-bdc2d47f65cc |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0cb7f161-0746-589f-81d4-15b0ed125083 |  | note | Specification/Drawings Reference - F3202A-Culvert ID 614
label | d0094357-0399-577a-8d33-312cb334d22f |  | note | Frequency - Prior to commencement
label | a93ded59-5f15-55bd-8610-df2959012d56 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 4d63e31f-84d4-5ad7-8fc0-e1d24bfe633f |  | note | Conformance Criteria - Delivery Dockets are collected and signed before precast headwall materials are removed from the truck.
label | cefb5932-5f3b-53da-aed1-712aab064357 |  | note | Records - Manufacturer cert, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.13 - Precast RCRRJ 1050 pipe
label | f6e2dadb-150f-5c86-805e-9f0edafc0ea5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 355e22cc-1463-5d01-a1cf-72e7c421299b |  | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614, AS/NZS 4058
label | 030b2504-e114-55ed-b56b-c9f08432b945 |  | note | Frequency - Prior to commencement
label | 479f7a08-f921-5f8f-a892-421c553ab422 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 0f791c90-b6bf-5eef-a2c6-6dc06d253667 |  | note | Conformance Criteria - Delivery Dockets are collected and signed before precast pipe materials are removed from the truck.
label | 6e68e986-ab89-5214-95e1-a161a323bfc9 |  | note | ○ Class 4 RCRRJ 1050 pipe to comply with AS/NZS 4058
label | e832370a-bafe-5fcb-b3a7-e5a7c4c0e2c2 |  | note | Records - Manufacturer cert, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.14 - Precast materials
label | 432333d3-1491-5972-a27c-bdd3bccbd3f5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1afa993a-981d-57f7-95cf-404865155fec |  | note | Specification/Drawings Reference - F3202A-Culvert ID 614, F3202A-DS-GT-RP-0001
label | efb0c5e5-c7d1-57c9-b13e-615d9e3b3057 |  | note | Frequency - Prior to unloading
label | e9f70c07-265d-5053-a9e2-ddcc538c5ef8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 97dc428c-98ab-5798-be98-cb769b7cb5a8 |  | note | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
label | b02685d1-a4e3-55d7-a1a4-3f00cbdd72cb |  | note | Records - Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.15 - Rock Rip-Rap
label | 83eeecec-7fea-5bea-92a6-87f6806428a8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f2ecc357-15dd-5180-9b9f-da53c558c393 |  | note | Specification/Drawings Reference - F3202A-Culvert ID 614, F3202A-DS-GT-RP-0001
label | 831c62e7-4237-53c6-bd48-7f3e978a0176 |  | note | Frequency - Prior to commencement
label | c7a573cc-7e6e-5138-8a12-034cf20d13f2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | e409e545-8253-5150-907a-ef1e3534ab0e |  | note | Conformance Criteria - D50=150mm Rock
label | bafb839e-3f86-588f-9cb9-bcd4985be2f2 |  | note | ○ Rock size to be confirmed by CPS Engineer
label | 81f42940-9b1d-5797-9cd9-dcf5e790b1c3 |  | note | Records - Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.16 - Hydroseed
label | f337f0dd-db70-5988-aa81-e8bc58a97640 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 745a1e82-7e74-53ff-bc1a-0b3a77aa2f1a |  | note | Specification/Drawings Reference - F3202A-Culvert ID 614, F3202A-DS-GT-RP-0001
label | d274d7de-e95a-53b3-a6b6-e59b3f5044f5 |  | note | Frequency - Prior to hydroseeding commencing
label | 05e6efaa-6e96-56e0-a68d-6d54f02d2ff5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | a337dbb4-7b4b-5059-bf4b-fd21b3b164eb |  | note | Records - Delivery dockets
checkpoint-status |  |  | checkpoint | 1.17 - 35 Mpa Concrete
label | 564cdc50-2f87-5f92-b723-dc061cc42015 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 59e49571-7cca-5cac-b1fa-d17ce2b1748d |  | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | 62027ade-fe7e-5d38-aadd-42055dd1cb70 |  | note | Frequency - Prior to commencement
label | a7154dee-842c-5bdb-9aa0-c9c59de4c428 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 47abff10-9abc-5c9a-9238-12fbd03b09ea |  | note | Conformance Criteria - Mix design 35 Mpa concrete @ 28 days for haunching
label | dae89020-d6b1-5387-879a-b4324bd9b62e |  | note | Records - Mix design cert, dockets
checkpoint-status |  |  | checkpoint | 1.18 - AP20 (Bedding material)
label | ac506038-c7bd-5826-a53b-f34500417369 |  | note | ACTION (Hold, Monitor, Witness) - W
label | bc24ed6a-e0ca-5df9-99f1-70d1772b4029 |  | note | Frequency - Prior to commencement
label | 7792eab8-180b-5d3d-9a3f-340459391041 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 7bc7ec80-adc8-593d-905c-706393c00d09 |  | note | Conformance Criteria - Source property testing
label | 04a9f3e1-1d96-5c24-9e82-b267884083a9 |  | note | Records - Lab test reports, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.19 - D16 Rebar
label | d2f8f8d8-1d68-50ab-91c0-759a42abbcd6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 28220890-27dd-5912-9346-c5f46b86034c |  | note | Specification/Drawings Reference - AS/NZS 4671 & NZS3109, F3202A-DS-GT-RP-0001
label | 1d66e574-4676-5f13-aa3b-55299809d45f |  | note | Frequency - Prior to commencement
label | 7f2a7525-e3d2-5408-b74b-6ee5dc20a796 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | eec4fae9-bb1f-51e1-ba5b-75bb6cfd6083 |  | note | Conformance Criteria - Comply with AS/NZS 4671 & NZS3109
label | 93856b51-abe4-5653-8112-5e672324e152 |  | note | ○ Shall be D16 rebar for concrete pipe haunching as per design
label | 1a90154e-589b-5368-adcd-d022da94d2a7 |  | note | Records - Mill Cert, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.20 -
label | 551a028b-2d81-51f9-b193-4311dce17a1e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8de447fb-8d14-596b-aded-bcf51a884ac0 |  | note | Specification/Drawings Reference - AS/NZS 4671 & NZS3109, F3202A-DS-GT-RP-0001
label | db511828-e355-5548-abcd-dfd51b6cb1f7 |  | note | Frequency - Prior to cutting or bending on site
label | 3a2ca515-4ce1-58f0-9863-23a33fc8faab |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 3d0e0103-231a-594e-b3d7-05b2b62fa3ad |  | note | Conformance Criteria - Any reinforcement requiring cutting or bending on site to be approved in writing by the CPS Engineer
label | 6108c261-bb38-55f2-ba54-8de210bee954 |  | note | Records - Photo's, CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 2: IN PROGRESS INSPECTIONS
checkpoint-status |  |  | checkpoint | 2.1 - Survey Setout
label | 1f24fd03-c0e3-508f-a4e5-9535614c03f6 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b06f3ac8-71fc-50c8-be85-bd88695ebff1 |  | note | Specification/Drawings Reference - Consistency with Construction Drawing
label | 5a821973-8f71-57a0-9b96-e030d4b25ddd |  | note | Frequency - Prior to commencement
label | ad505b60-f4b3-57f7-8d58-3162c69547fe |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 98d1bc48-7a58-5fe6-8fc9-60f80a5e6564 |  | note | Conformance Criteria - Set out extents of fill and check against design drawings
label | a39e34a7-24ca-5ab1-b5b1-2afb2452ff4e |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | cf6aaef6-1638-5d29-b855-2d76b8ac1719 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ef34c6a4-c1cd-52fb-a669-eaca24ec3aa9 |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | b6ef889a-66c6-51cb-862d-eb2e2f5e7478 |  | note | Frequency - Prior to commencement
label | a9660176-3622-534a-b3a7-6980e135bead |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 8a74b099-5192-538d-b01e-6a6bbed7ca39 |  | note | Conformance Criteria - Remove and clear the vegetation
label | dc03ea5b-3741-59ad-86a9-fd501773841b |  | note | Records - Photo's
checkpoint-group |  |  | section | Section 3: CULVERT OUTLET EXTENSION
checkpoint-status |  |  | checkpoint | 3.1 - Foundation compliance
label | ea98b308-fb78-5677-a07d-d95923dc3f90 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 45cbc0ef-f096-5859-b030-4c6b7089b224 |  | note | Specification/Drawings Reference - F3202A-Culvert ID 614
label | dc77bcb0-a11f-5b74-84df-48dbf4fc6c6c |  | note | Frequency - During Construction
label | 962efecd-221e-5193-83f9-3fa5e4259107 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala testing
label | b448d67e-06b0-557d-a7ee-f3abddf88123 |  | note | Conformance Criteria - Bearing pressure >50 kPa (>= 2 Blows / 100mm Scala to >= 1m depth), to check if undercut is required
label | 7e06cf6c-c400-583e-ab49-18fb06b629ea |  | note | Records - 1M Scala check sheet (CS-4000), Scala test results
checkpoint-status |  |  | checkpoint | 3.2 - Foundation compliance
label | 7fbb4f93-1672-52a7-a04b-26be1e7beaf0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d6542715-e108-5beb-be06-75353a4386f0 |  | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | 9a4d94ff-a984-59dc-a6ab-b0cba8dfc96f |  | note | Frequency - During Construction
label | 4025bdd5-4512-5eee-9118-b06825d34aca |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | a7504bdf-c94b-546f-a23d-5bab68227b25 |  | note | Conformance Criteria - CPS to inspect and approve formation level at outlet
label | dcf50019-403b-53ce-8074-0972b2adac40 |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Trenching and Excavation
label | d87fae9f-d82c-5d35-9744-e39674f773e3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8ade21d8-c371-5e48-b06a-a66bf36b59a5 |  | note | Frequency - During Construction
label | 519a4b0d-9b14-52cf-8fb6-c615fe8b733a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 9dfc7d74-29f9-500b-9512-0f9503f9bf69 |  | note | Conformance Criteria - Ensure trench width is sufficient to provide enough space on either side of the pipe
label | 21c54a9b-2df7-54f8-beb5-d23c58a11590 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 3.4 - Trenching and Excavation
label | 86924117-55f4-51d9-9284-02309ab8cd96 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2ed7cc73-9859-5654-9fc0-83fcc3f695a3 |  | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001
label | ff95c829-efad-58b1-9b36-d62cefe3eccd |  | note | Frequency - During Construction
label | aeb32840-76e2-5f8f-aae4-c0649031a6f2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 0d114f7e-3485-5f39-bff1-466e25d409be |  | note | Conformance Criteria - Inspect trench profile and ensure it is correct to lines and levels as per design
label | 336c473e-cefd-5e2b-be70-1a8f6e34bb04 |  | note | Records - Survey As-Builts
checkpoint-status |  |  | checkpoint | 3.5 - Pipe and headwall Bedding (AP20)
label | cf0eeb1c-0b2e-5d6c-891e-fc73b662c4bd |  | note | ACTION (Hold, Monitor, Witness) - W
label | eca14051-2d6f-58cb-891e-4df54afa0c17 |  | note | Specification/Drawings Reference - AS/NZS 3725:2007
label | 4e996f9a-cd0d-55b0-8071-d8f850569362 |  | note | Frequency - During Construction
label | 9f8b4806-c199-5aa1-afe8-d2fab144c19d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 05b9ab78-2f30-50b5-9b81-34ea6f93dd86 |  | note | Conformance Criteria - Comply with AS/NZS 3725:2007
label | 658b96ff-391b-5720-be4e-ba18a85b847e |  | note | ○ Ensure correct thickness of bedding is placed and compacted.
label | 6f4e6212-4aba-51fb-b5e3-7c6ebcd99868 |  | note | ○ 100mm thick bedding for <1500mm dia pipe
label | 7fc98fe6-ae04-58df-8f0a-ffb4357b882f |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 3.6 - Pipe and headwall Bedding
label | 64ec5ec1-a821-5371-8765-4fa726e8621e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6b311e66-531f-5113-98c8-cf67c2170f18 |  | note | Specification/Drawings Reference - NZTA F3
label | 94629ad1-8e46-570b-8800-caf5c741f5a6 |  | note | Frequency - During Construction
label | eff703ba-babe-56c3-af40-ae3fb7eb14eb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | 361a38c0-23e8-597d-b791-2c023872689d |  | note | Conformance Criteria - Ensure bedding material is compacted by Clegg (TBC by CPS on-site)
label | c69448c6-3114-55c1-9fa9-96838fa1ade6 |  | note | Records - Test report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Pipe and headwall laying
label | f162f493-6cf5-56ba-8760-49f409a100f8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 970c8a4c-8c1b-51c9-aaad-f06ebd07929a |  | note | Frequency - During Construction
label | 6ba0cfbb-3f49-5745-a6dd-b3d9e1fe5cf9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | e9dfad7f-21dd-5e88-964d-d4166cab984b |  | note | Conformance Criteria - Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall have Vertical tolerance +/- 5mm
label | 357a3a9e-1bdc-5b36-be17-b68736e07ead |  | note | Records - Survey As-Builts, Photo's
checkpoint-status |  |  | checkpoint | 3.8 - Pre-Backfill inspection
label | 8a6e96da-1b76-5ed8-ace7-eea995f0db3a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 51714a7c-f155-543d-8890-ad18bbdf41d6 |  | note | Specification/Drawings Reference - NZTA F3
label | 7866d8ec-e7d4-5174-ba00-403bbf35c083 |  | note | Frequency - During Construction
label | 9ca221e0-928c-5ed3-9e37-740e60fb7784 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | b30c1815-b10c-595c-b23c-b0deb7e9062d |  | note | Conformance Criteria - Inspect pipes prior to backfilling to ensure they have been installed correctly and the finished joints are in place, watertight and present a smooth surface. Check for gaps and/or defects and check pipe alignment for straightness
label | a3d2dd75-6e18-58cf-ab1a-dc2f2fe3a8a8 |  | note | Records - Photo's, CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.9 - Backfilling (Haunching AP65)
label | 28380f48-ec4f-5961-b42a-c84aa4bb88b6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 02c0e60d-c77e-59b5-afe3-029b78f5fa14 |  | note | Specification/Drawings Reference - NZS 4402:1986, Test 4.1.3
label | 0d5d7292-9a37-5577-b952-717ea2d7a8dc |  | note | Frequency - During Construction
label | 0c664014-f0f9-5727-84dc-294dc711b060 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | 7177fa42-af0b-5eef-9cad-17ba6ab4da46 |  | note | Conformance Criteria - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms.
label | ee6dde5a-57d7-5654-8a20-564232b47dc1 |  | note | ○ Remainder of backfill to be done with excavated material.
label | 25fed3eb-03e6-553c-a11b-52073fa6c172 |  | note | ○ 95% of MDD shall be achieved
label | ffd8555d-ff89-57be-8be2-84563f413b65 |  | note | Records - NDM test reports
checkpoint-status |  |  | checkpoint | 3.10 - Existing road side Swale
label | f8fa7fb4-3aa7-5c88-afcb-ba22da79f1d8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 932ad419-199b-58c5-8261-8332a28002c0 |  | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | a92f71e2-01d3-5539-90e2-126a59f250ab |  | note | Frequency - During Construction
label | 18d5c32a-4ded-5eb4-a29c-b61a50fffc94 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 8ea8dd47-3444-5a3e-8f9e-2012f5c5a0c3 |  | note | Conformance Criteria - Reshape and form both ends of road side swale to match the rock chute invert.
label | ac1c0420-20f4-5d83-b7ca-93bfa58d0496 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 3.11 - Swale geotextile installation
label | 8ac743b5-71e7-52b2-ae5f-9639a59e59a1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2af00e94-f6e4-53b1-9fba-2e932b6c68cc |  | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | 633a1e16-5115-5327-b4ac-db6822103fad |  | note | Frequency - During Construction
label | fdb1379d-fbe1-5613-bcdd-ae84d11824bb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 118b0c9e-342c-589b-abf9-00b09a8633ed |  | note | Conformance Criteria - Class D geotextile to be placed in the swale prior to rock placement and be laid/overlapped as per manufacturers recommendations
label | 71bf46ec-6549-5de7-8826-cc13befe3172 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 3.12 - Swale rock line
label | 30a56a00-628f-5d37-8a65-bd85e3dcaeb2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b15728ab-4835-5d03-bde4-bcaf1ffae7a0 |  | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | e003d582-d1f9-50b1-b75b-5d336654bf32 |  | note | Frequency - During Construction
label | 3a6d6fef-9ac5-5a4b-96ad-0fdc59703acf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 8b802f0c-b898-5780-8d14-b3ad62fcc176 |  | note | Conformance Criteria - >1:50 slope rock line D50=150mm, 300mm minimum thickness over Class D geotextile to be placed
label | 9bd4ad5f-ce0d-565e-89e2-8e114538ca54 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 3.13 - Swale rock line alignment
label | 372f802a-f681-59dd-a80c-bb64f143487a |  | note | ACTION (Hold, Monitor, Witness) - H
label | cd250c76-0876-54ea-b7cb-eb0101d6a673 |  | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | 9a02f913-5b0d-53d7-89cb-d8f221152736 |  | note | Frequency - At completion
label | d7141539-1e31-52eb-8956-4723cbfd0bbf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 70ff1c02-ed5f-5e53-8c37-4e37954ccce5 |  | note | Conformance Criteria - Slope rock line should be >1:50 slope
label | e4516aec-57ce-5911-a173-0c50e9961e24 |  | note | Records - Survey As-Builts
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.14 - Outlet rock chute
label | b7b7e192-defb-5407-adc2-bae4abd5b18c |  | note | ACTION (Hold, Monitor, Witness) - W
label | a842527b-5a90-5647-aa12-47c61afd2347 |  | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | 212352a0-6f16-5f6c-bcba-4a946f5e9523 |  | note | Frequency - During Construction
label | bb11fa29-f4c3-5b64-bf05-9aa12c82d8d4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 2a2c025a-edb2-5bf7-bac9-01583f927b23 |  | note | Conformance Criteria - Angular rocks D50=450mm minimum to be placed. Thickness 2 x D50 minimum. Rocks should be placed to a length of 1800mm in front of the headwall.
label | 088d7114-5de2-5eae-827c-f7ac84d951ea |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 3.15 - Geotextile installation
label | c2e8d620-d84c-5fa9-9509-942912720d1e |  | note | ACTION (Hold, Monitor, Witness) - W
label | fc44896e-f8db-56d6-8b7c-2eb8926b1f55 |  | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | 637665d4-52f7-5ae2-9b78-4f0f06bea35a |  | note | Frequency - During Construction
label | 5517d667-de39-5e25-80e0-37248b6fe30d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 6e79032a-db58-519c-b4af-09f8a669b72e |  | note | Conformance Criteria - Class D geotextile to be placed prior to rock placement and be laid/overlapped as per manufacturers recommendations
label | cb4c537a-baf1-5afc-84de-d1aeaddc2eee |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 3.16 - Rock Riffle
label | 8ec1a5c2-e19b-508c-88ba-35c8af268731 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ec7185b1-c7c5-5972-9c15-f312ade0ba0c |  | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | 224767d6-9aae-58b9-858f-cf66dfee93e1 |  | note | Frequency - During Construction
label | 557fabd2-7596-5961-833a-9c910612f39a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
label | c9ce0c6e-90b8-5268-b934-97a05a6ebf8e |  | note | Conformance Criteria - Largest rocks 900mm to be installed closely to form an arc shape facing upstream.
label | dee7ee81-1edd-5a31-a686-ecaae350c45d |  | note | ○ Reduce grading of rocks towards the toe of the slope.
label | 89304abe-5564-5ef0-a206-8a34a9e5d6a0 |  | note | ○ Wash gravel/grit over to fill all voids.
label | 4f377e5a-dd0f-5aae-9ae1-bce271d10ec2 |  | note | ○ Rock riffle to be installed to approx. 1V:5H slope and tie into existing streambed minimum 200mm
label | e4d8c0d0-ea03-51e2-8a3f-aa23ba21d8a0 |  | note | Records - Photo's, Survey As-Builts
checkpoint-status |  |  | checkpoint | 3.17 - Slope above the rock chute
label | e8bf6cd2-c0fb-571e-9c4d-598ed923f569 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d28141ac-51cf-5f41-ac89-8c15bcb91e9e |  | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | a0ae3a9c-2d53-528b-b621-d5d0b427c044 |  | note | Frequency - During Construction
label | 7e97da32-f5e9-54c7-9cb0-7fe2ccb445a1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
label | f9e34b29-aa77-5f5b-b378-949ea512278c |  | note | Conformance Criteria - Daylight at maximum 1:2 existing ground and hydroseed / cover with pinned biodegradable erosion control mattting
label | 354c0575-af96-522c-9690-f20576f23ca1 |  | note | Records - Photo's, Survey As-Builts
checkpoint-status |  |  | checkpoint | 3.18 - Galvanised Traversable grate installation
label | daa144da-c470-51e0-b23c-ed9ee3ddfe15 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 83fc432a-d74b-5d75-beeb-603602453cf2 |  | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | 237fdc0c-2cc9-5fc0-b5d4-1f4cc7a5a1f7 |  | note | Frequency - During Construction
label | 721d5b24-b4f8-57c1-8d7f-25ec6f7d38d7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 5e10f704-3c76-593d-a78f-8999d46311a8 |  | note | Conformance Criteria - Grate mounted on headwall in accordance with manufacturer's recommendation
label | d7db07b4-63a7-54a1-9085-78328a70c8c2 |  | note | Records - Photo's
checkpoint-group |  |  | section | Section 4: BUTTRESS TYPE A
checkpoint-status |  |  | checkpoint | 4.1 - Class D (A39) Geotextile installation on the excavated face
label | de581656-a551-58fd-b7c2-c2c3661ae225 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a7318a93-f505-5cba-a4ba-8f3758f8e9c7 |  | note | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
label | b5c0405d-d85f-54ac-8d77-590317965227 |  | note | Frequency - During Construction
label | 5d0ede96-dc6d-5f07-b09c-c87fae6989f4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 52c60ed0-0558-5404-992e-899a10852e31 |  | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill.
label | 2c5af6a5-13bf-57ba-a373-94df7f8f3980 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.2 - Megaflow strip or drainage blanket installation for seepage if Encountered
label | 09bfd8e9-89af-5cb2-a7d5-cb11a796a3d9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6f9b3ae4-0b1d-5f83-b342-9840a4448688 |  | note | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
label | ff309149-9c14-5b02-aa1a-df00bd8ae534 |  | note | Frequency - During Construction
label | ac112e18-f6f3-52cd-bede-3d6816352bc6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | d0354f39-5fba-50ba-9bdb-c8b264b9d523 |  | note | Conformance Criteria - Engineer to assess drainage location suitability.
label | 3a94f429-a4c4-5222-aee2-82f9754d9cd5 |  | note | ○ Drainage positions to be confirmed on site by the Engineer. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required.
label | 4f10e92b-4228-5c1a-b151-4d26964acc2b |  | note | Records - Photo's, Drainage Line record check sheet (CS-4025)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.3 - Bulk Fill placement
label | 0b938f3b-4d5b-5289-b2fb-1cc62cfa2f1a |  | note | ACTION (Hold, Monitor, Witness) - M
label | 8da35694-c34b-5b31-9df7-d4e5c43d72e5 |  | note | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
label | 791da686-9e53-51e1-ac08-9dd5245b48ed |  | note | Frequency - During Construction
label | 333bf4ee-766e-5979-8f58-36cb6199a63d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 1308d5e9-a449-5eaf-95ea-56f90804b0b3 |  | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control.
label | e16bda47-aaea-50fe-a935-8a9fb32d937b |  | note | ○ Fill should be placed on dry subgrade.
label | 4d0a74c4-e4e8-53c4-9c4c-a405d2e70d41 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.4 - Bulk Fill Compaction
label | c788d06c-aecf-57e5-9f26-3246a1f21a3f |  | note | ACTION (Hold, Monitor, Witness) - M
label | f92e235e-b2e0-5167-96ba-0c4f3da4c1af |  | note | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
label | a1a8b684-7f10-5457-b567-4a7c6dfded86 |  | note | Frequency - During Construction
label | 9ac242e0-b22e-5b6b-aa76-a782d9b99a76 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | a8447ae9-b812-503a-9bd5-7e2a03e58b48 |  | note | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
label | 8ef0169a-843e-56a6-9618-4ced7436e7d8 |  | note | Records - Compaction test reports
checkpoint-status |  |  | checkpoint | 4.5 - Form and cut fill batter as per design 2H:1V
label | d9971979-c750-50c6-bcdb-5a8cba8399d5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0e2c7c86-022f-5c1f-87e3-808936839aea |  | note | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
label | 9582448f-d18d-5e81-ac5e-57dfcf0686be |  | note | Frequency - During Construction
label | b58e890f-c26e-5db9-8330-3e1368775cea |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 93bf8771-a602-5187-9e8d-cf5c2c0901f0 |  | note | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
label | b1857b78-bd75-5643-949e-0ab318718d0d |  | note | ○ Slope angle of buttress is to not exceed 2H:1V
label | 94c4a85d-70ca-518c-be60-0e56be400116 |  | note | Records - Photo's, Survey As-Builts
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.6 - Rock Armour Placement
label | 05c32811-6ed2-581b-ab82-d5a4151bb7b6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9076a82a-a16c-54e9-806b-268f0bddca05 |  | note | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
label | 49594781-c711-56e9-87f2-3fe4f1c62e6b |  | note | Frequency - During Construction
label | dea90abd-b012-5bdc-b00a-d2f74e43226e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
label | 8fbfe8d3-8da9-595b-9f31-03329a507497 |  | note | Conformance Criteria - 2 x Layers of Rock riprap (D50=450mm diameter)
label | 2dad5ffa-3e7f-527e-b0a4-ff39b875a7e6 |  | note | Records - Photo's, Survey As-Builts
checkpoint-status |  |  | checkpoint | 4.7 - Rock Armour key into ground
label | b72b383a-8738-5813-ba95-49392af416ce |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4de48aff-2c9f-558f-a3a6-083249689356 |  | note | Specification/Drawings Reference - Buttress typical details A and F3202-Culvert ID 614
label | 336845af-1fd5-576a-96d5-3176d2cdaa40 |  | note | Frequency - During Construction
label | 72efed0a-e1df-502d-b7f0-38e61165de30 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Visual Inspection
label | 7e78fba7-d5d8-558e-8bee-2b433516adc0 |  | note | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 1m to 2m wide.
label | 74bceb56-41fc-53bb-a25d-06b6c3c6312a |  | note | Records - Photo's, Survey As-Builts
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 5: CULVERT INLET EXTENSION
checkpoint-status |  |  | checkpoint | 5.1 - Foundation compliance
label | b5f8b102-fa00-5d2b-ae60-cc6119e7fb5a |  | note | ACTION (Hold, Monitor, Witness) - W
label | cbabf044-469f-5c26-8f23-8e41c69cbd69 |  | note | Specification/Drawings Reference - F3202A-Culvert ID 614
label | e061ae29-1433-50f3-a518-a9f74158f8db |  | note | Frequency - During Construction
label | b1326f39-1101-5dbb-a6b6-d704a8558cb7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala testing
label | b2c8a284-31f7-5cda-81d8-917ba5d80890 |  | note | Conformance Criteria - Bearing pressure >50 kPa (>= 2 Blows / 100mm Scala to >= 1m depth), to check if undercut is required
label | 13324ffc-aeb3-5758-9c06-61f6cdb23dab |  | note | Records - 1M Scala check sheet (CS-4000), Scala test results
checkpoint-status |  |  | checkpoint | 5.2 - Foundation compliance
label | 15a6996d-21d5-5a62-a8da-6c5edd878efb |  | note | ACTION (Hold, Monitor, Witness) - H
label | 18a76a60-002e-56d8-a935-09f91664d7d1 |  | note | Specification/Drawings Reference - F3202A-DS-GT-RP-0001, F3202-Culvert ID 614
label | bae720a8-5fbc-5802-a680-6567475d15af |  | note | Frequency - During Construction
label | 9dd896d5-da34-55c9-9f6a-c7fbc3d3e5e3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 11ae6c19-2ea1-5ecc-a1e6-3bc16bab0f22 |  | note | Conformance Criteria - CPS to inspect formation level at outlet
label | d23d9203-e8bc-5618-99ac-faad58daf9ca |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Trenching and Excavation
label | 0339ec87-257e-5317-a832-3ee75ea9bef9 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 14cfbcd5-3a3d-5982-b456-848474fee8ad |  | note | Frequency - During Construction
label | b2c2b34e-b06d-5b47-b7ee-3773d2df25d6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | bdfddba9-035a-5c79-9ed5-00bd154f7568 |  | note | Conformance Criteria - Ensure trench width is sufficient to provide enough space on either side of the pipe
label | e63432f6-d214-5c43-bb80-ce23ee956110 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 5.4 - Trenching and Excavation
label | 01e684a3-2e23-5581-875c-34d3d9798728 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 764e46e7-49eb-5012-b6d8-e67384983afd |  | note | Frequency - During Construction
label | 210616ec-96e8-5256-be8e-967bd8996ea1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 07a449ab-e06b-55ee-9dc0-1a4c3773a00a |  | note | Conformance Criteria - Inspect trench profile and ensure it is correct to lines and levels as per design
label | d7915013-9802-5c39-a1a5-bc5124cbb5db |  | note | Records - Survey As-Builts
checkpoint-status |  |  | checkpoint | 5.5 - Pipe and Bedding (AP20)
label | 72dd8861-25c9-5584-ae8c-403b93e089a9 |  | note | ACTION (Hold, Monitor, Witness) - W
label | acf9b0d3-a12b-5136-a91a-97119c643af3 |  | note | Specification/Drawings Reference - AS/NZS 3725:2007
label | 97bbf516-1340-52cf-abea-c812685858b0 |  | note | Frequency - During Construction
label | 4e2ee1ec-d521-5318-b61d-aaa6fb6b36a7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 686283af-b9ba-5a9e-b3e4-a0e56b34432a |  | note | Conformance Criteria - Comply with AS/NZS 3725:2007
label | 2cb2c166-ba51-5eb5-b247-d693327e4a77 |  | note | ○ Ensure correct thickness of bedding is placed and compacted.
label | 2a9457e0-890a-53f6-946c-612889122495 |  | note | ○ 100mm thick bedding for <1500mm dia pipe
label | dd9cc8b7-576b-5494-9c77-d8b5b72179ae |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 5.6 - Pipe and Bedding (AP20)
label | c7c2828f-3711-5359-bd76-d6f9e2c1f246 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7d285644-1238-5e93-a26d-805dd0ed1536 |  | note | Specification/Drawings Reference - NZTA F3
label | 891c5364-7bf2-567e-b76c-c22ed8812149 |  | note | Frequency - During Construction
label | 5d495be7-9a97-5e18-9f50-d6b34b6bc229 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | afe47449-70ed-517c-9dc6-914a49c91964 |  | note | Conformance Criteria - Ensure bedding material is compacted by Clegg (TBC by CPS on-site)
label | 1ab11dfd-dfb5-5d21-b66a-583503bf6119 |  | note | Records - Test report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.7 - Pipe laying
label | 16147e83-2117-54e8-a155-7f84a2bcfca2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8c9e7e91-39dc-5710-bff2-0a28b6b0677b |  | note | Specification/Drawings Reference - NZTA F3
label | b0a39fab-4de2-5d6a-ab3b-1d11aa57ddc7 |  | note | Frequency - During Construction
label | b80250f4-50db-5783-995a-9e88197617af |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 94b8fa21-2e0a-5a91-823e-8d68a026afe3 |  | note | Conformance Criteria - Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall have Vertical tolerance +/- 5mm
label | b8aff680-10b9-5b27-9339-cfcab6044189 |  | note | Records - Photo's, Survey As-Builts
checkpoint-status |  |  | checkpoint | 5.8 - Pre-Backfill inspection
label | 3bcf7eaf-98b3-5228-be37-2fc33347a536 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6677ff43-a889-5aa4-8eaf-e4df73f78ce7 |  | note | Specification/Drawings Reference - NZTA F3
label | e6d16257-95ea-5aaa-8649-fda822618a5e |  | note | Frequency - During Construction
label | ee88121a-98c7-5267-b172-69c1f9dc992a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | fa208e19-22d3-5d94-be32-dac95d75517c |  | note | Conformance Criteria - Inspect pipes prior to backfilling to ensure they have been installed correctly and the finished joints are in place, watertight and present a smooth surface.
label | e45ce26f-4ae2-5027-9494-f20ef8176c72 |  | note | ○ Check for gaps and/or defects and check pipe alignment for straightness
label | d9499017-12e6-52ec-a0c6-34f4833a32dc |  | note | Records - CPS COR report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.9 - Backfilling (Haunching AP65)
label | e6301a9a-8ef7-5a3e-accd-1ff1c270b378 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2363a7ca-0ba3-54ed-a4a8-41e752d0ec34 |  | note | Specification/Drawings Reference - NZS 4402:1986, Test 4.1.3
label | ed4911c5-bdc3-5d1b-8de8-b3782fc8b2a1 |  | note | Frequency - During Construction
label | 3144c195-062b-5029-b335-beb544da5312 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | 2fd73cd6-6415-58bf-913a-2f6e91667676 |  | note | Conformance Criteria - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms.
label | 617d6251-6ffa-5ea6-9d60-700480198fe5 |  | note | ○ Remainder of backfill to be done with excavated material.
label | 7996001f-feae-5a50-ba1a-a99063b66690 |  | note | ○ 95% of MDD shall be achieved
label | bb33acae-96ad-5f52-8e20-f79435fb3ccd |  | note | Records - NDM test reports
checkpoint-status |  |  | checkpoint | 5.10 - Concrete haunch around inlet
label | 8ffa810a-fbe5-55e8-9c4e-c1f5b1d98744 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 268797c3-3f22-5ff6-9050-92903527410a |  | note | Specification/Drawings Reference - F3202 Stormwater inlet details, NZS 3109
label | f16f482a-2455-5bc3-806a-7b10a5a168b2 |  | note | Frequency - During Construction
label | b4790978-c554-5da5-a8e4-11d958ca2e96 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing and visual inpsection
label | daa77120-f135-51e8-bc30-1f7a64c8b602 |  | note | Conformance Criteria - 300mm concrete apron to be poured around the inlet. 35MPa concrete @ 28Days.
label | 3b5b6001-701a-5f33-bb0f-34a8b80beec8 |  | note | Records - Concrete compression test results and Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.11 - Concrete haunch around inlet
label | f7dfaf14-d323-5362-a810-4271fde26159 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d702f6f4-0940-5108-b2d8-aa14cc88b6e6 |  | note | Specification/Drawings Reference - F3202 Stormwater inlet details, NZS 3109
label | f22e90cd-4bc1-54e1-a361-86ade67bf34f |  | note | Frequency - During Construction
label | 1af33502-fbbf-5f57-997e-c0358e958360 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 44b55ab6-c92f-5d18-9a79-c2b2509eba27 |  | note | Conformance Criteria - 300mm concrete apron around the inlet with D16 reinforcing bar centrally, 50mm NOM. Cover.
label | fd1a4196-939b-5f8e-b1c5-bf64b9ce59bb |  | note | Records - CPS COR report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.12 - Inlet pipe cut
label | 91e9ba1f-22b1-57a0-9bb4-771442ac0614 |  | note | ACTION (Hold, Monitor, Witness) - H
label | eaf8eb18-4456-5f34-a352-e010cf2ea1c3 |  | note | Specification/Drawings Reference - F3202 Stormwater inlet details
label | 94b65a1a-8aa8-5874-8193-8d9c83363302 |  | note | Frequency - During Construction
label | 5a75aec7-23ea-588d-8524-95612adabd05 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 588b38bf-97ee-522f-a407-7cd4493c284e |  | note | Conformance Criteria - Mitre pipe at 1V:2H. Grind back exposed steel 20mm and place bead of epoxy mortar on cut surface
label | 961a8887-ecd7-5057-8fd7-043e683d2bfe |  | note | Records - CPS COR report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.13 - Rock chute and rocks around inlet
label | d930776e-84fc-5d6b-bca9-ff3b4326282e |  | note | ACTION (Hold, Monitor, Witness) - W
label | 857802f1-966d-5b0f-8e7f-e06ce5d36d0e |  | note | Specification/Drawings Reference - F3202 Stormwater inlet details
label | baa6869d-6473-5fd3-9929-088167db1dad |  | note | Frequency - During Construction
label | 00f798fc-1a98-531e-a648-773f5f0f516a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 163e9414-bef3-5b58-9224-fd8744b26773 |  | note | Conformance Criteria - Angular rocks D50=450mm minimum to be placed. Thickness 2 x D50 minimum. Extend rocks to top of the embankment.
label | 3c341d77-42ff-5816-b489-8242cedb0ded |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 5.14 - Geotextile installation
label | 9e8514c9-cb5a-544d-a7fd-516004b8ad7f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2f67b0ce-1acf-5fe1-bf4b-6a6a0de14a0f |  | note | Specification/Drawings Reference - F3202 Stormwater inlet details
label | 8c4388f8-c679-55a2-8244-800563458505 |  | note | Frequency - During Construction
label | 9a71cd9c-3fd8-5ed7-b043-5bcafcba823c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 6decc480-42b0-5727-a5f6-ebe0d90dd379 |  | note | Conformance Criteria - Class D geotextile to be placed prior to rock placement and be laid/overlapped as per manufacturers recommendations
label | 4ebff999-f5dd-53e8-8b31-78443f0a3230 |  | note | Records - Photo's
checkpoint-group |  |  | section | Section 6: BUTTRESS TYPE C
checkpoint-status |  |  | checkpoint | 6.1 - Class D (A39) Geotextile installation on the excavated face
label | be0f2c7b-ab61-571c-a4ad-cf682ce72548 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d87a950c-5f03-54a8-b249-8b195b3504f2 |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | 1df3f2df-61ef-5d02-91fc-1c39ccc41a8f |  | note | Frequency - During Construction
label | b6108af1-809f-531e-ae24-5af5abfdd1fe |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 36748f2b-a8f3-579f-ab47-1c281e4f2bed |  | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill.
label | efc87a2a-d842-5cd3-96c9-b06b9e0c3c1c |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 6.2 - Megaflow strip or drainage blanket installation for seepage if Encountered
label | 69f1bc7f-8781-5da1-9105-c877001fd89d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 44ab7121-5ab3-5106-a41f-f393a5c7038f |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | 110dd5be-06d3-5bbd-aca1-641c5f539e57 |  | note | Frequency - During Construction
label | eccbb473-7e44-5e11-85de-707b2bbbdffb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 142a3a8d-cc79-5c8c-a8c4-86321c2dd0cc |  | note | Conformance Criteria - Engineer to assess suitable drainage location suitability.
label | f2a8782d-0959-5e2e-b1ce-258003c1c9df |  | note | ○ Drainage positions to be confirmed on site by the Engineer. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required.
label | 96ebb8d5-e689-50b0-bed7-378f352ee36e |  | note | Records - Photo's, Drainage Line record check sheet (CS-4025)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.3 - Bulk Fill placement
label | 68750eb1-8f88-5773-bcf8-8cd17fd90b41 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 5a642488-876e-5a99-9e89-8fb1cda6c0a6 |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | 0ec160f8-5a52-56ac-a42d-aba51090c8bc |  | note | Frequency - During Construction
label | 1e6188c2-e1cd-50ff-939a-9d93503bb8ad |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 11057674-ddfc-50e0-a8f0-f6a0e5ff0c35 |  | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control.
label | 32a60fbb-6b88-5410-861f-a584bd3ace75 |  | note | ○ Fill should be placed on dry subgrade.
label | d68a3bfc-7906-5ffd-a9be-f7771e96c2eb |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 6.4 - Bulk Fill Compaction
label | c6f20b86-9eef-5f4b-b726-67f08f8a4f63 |  | note | ACTION (Hold, Monitor, Witness) - M
label | e650e379-54f6-51b8-857e-99cf053c12ce |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | e02c87e2-7597-59a4-bc8c-d87cd5dd854c |  | note | Frequency - During Construction
label | f13babc8-68a2-5593-bb1e-841f105e58de |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 9f194ab2-1098-54ce-a8e5-5acc683c56dd |  | note | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
label | ef93eb74-faf7-5de1-a350-02915c3d6519 |  | note | Records - Compaction test reports
checkpoint-status |  |  | checkpoint | 6.5 - Form and cut fill batter as per design 2H:1V
label | abaff27a-d560-5c60-abfd-e3f45a5afce1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 439bc721-de61-5a28-8b06-a22649aecba8 |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | 763e690d-0f2a-5774-9508-5b7fa350d009 |  | note | Frequency - During Construction
label | 9bacbed1-81a3-595d-8b40-2a005f77c0d8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 6c3af3b1-cdec-53ff-a54b-8c0724c7bf40 |  | note | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
label | e49868bd-0bd3-50ce-9bed-2b8e034fe042 |  | note | ○ Slope angle of buttress is to not exceed 2H:1V
label | 9dba6b7e-3ad9-5e2c-9330-5c8cf7409a99 |  | note | Records - Survey As-Builts
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.6 - ClassE (A49) Geotextile placement along the face of fill batter
label | 4200f698-3912-580d-b43d-38ef1fdaa0e5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 69faecb3-91a3-53d4-ae4c-2a10e9fd5bb9 |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | 51f17acf-c224-5c58-b697-6f7f9903d311 |  | note | Frequency - During Construction
label | 7b1dc968-58e8-5859-abfb-2e2a99c1619d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 47f41dc4-d9fa-54da-be88-7c47e150951a |  | note | Conformance Criteria - Class E geotextile to be placed between the rock armour and bulk fill and be laid/overlapped as per manufacturers recommendations
label | 2920c35e-5ebc-5d51-8ef9-4ac1bc92a248 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 6.7 - Rock Armour placement along the face of fill embankment
label | c4d22971-afc5-57a8-bb03-bb3e868156b7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e7c3a6e5-a3d6-5696-8aa7-9405992bf2cb |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | edf57464-6137-5c85-9c17-ddd47fa00c12 |  | note | Frequency - During Construction
label | a9e20cf1-ce8d-5924-9415-389a70979b35 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Survey
label | 483c1724-a521-5863-8295-41ad00df24c3 |  | note | Conformance Criteria - 2 x Layers of Rock riprap (D50=450mm diameter)
label | 225f7095-cf38-5def-a3d5-49acefd3abf5 |  | note | Records - Photo's, Survey As-Builts
checkpoint-status |  |  | checkpoint | 6.8 - Rock Armour key into ground
label | c320ad12-2d15-51a5-a8d5-c653a6c77bae |  | note | ACTION (Hold, Monitor, Witness) - H
label | aaa0eed7-5fe1-5049-ab3a-412635dc39a1 |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | db4fa21d-2545-518f-ba32-b0f2aeb8c211 |  | note | Frequency - During Construction
label | a60383ec-acbf-562a-bc42-c49cb8ce4117 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Survey
label | 0dc90d7f-3c83-5753-beb7-8ed894007826 |  | note | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 1m to 2m wide.
label | ab57cfb7-8b5c-5d1c-9938-04165ff2924e |  | note | Records - CPS COR report, Survey As-Builts
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 7: IN PROGRESS INSPECTIONS (Pavement)
checkpoint-status |  |  | checkpoint | 7.1 - Saw cut existing pavement
label | 4f480534-25eb-52b3-8f84-48bc3e9743b9 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ab3e2226-d077-5e82-8e03-a54d6fdce8e8 |  | note | Frequency - Prior to pavement construction
label | 1a90bf2b-f47d-5054-8499-80f1c439045c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 607f8d4c-4e55-5664-b4da-e498ae7d0ff7 |  | note | Conformance Criteria - Smooth and straight saw cut
label | 7c3a0eed-b28f-5beb-bed5-83b717ad9ad2 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 7.2 - Subgrade construction
label | 949a9cb7-2349-5de3-a3ad-3d024331c68f |  | note | ACTION (Hold, Monitor, Witness) - W
label | cdf3fa5e-b3f3-53a6-a10d-5e2645e6476c |  | note | Specification/Drawings Reference - TNZ B2
label | 6794ab67-7c36-5039-a6d8-f7c2bae182a1 |  | note | Frequency - Every 20m
label | e4483e53-c344-5bf3-8c9a-1d95e2f6f3af |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | 6cc72c2f-9271-5d91-8b17-c8ef392a751e |  | note | Conformance Criteria - 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92%
label | 160ce483-89b9-5546-9fc3-99dd29d51487 |  | note | Records - Test reports
checkpoint-status |  |  | checkpoint | 7.3 - Subgrade Cement Application rate
label | 72747d9d-8635-569b-ab29-e19649b49910 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b19ee6d9-0a6e-572f-8089-d3b172272178 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
label | 7049826a-7160-5095-81af-b5dff7800003 |  | note | Conformance Criteria - 2% cement stabilisation at 250mm deep subgrade
label | a4a8de2c-91eb-59e5-9e92-24b4be0dd305 |  | note | Records - Bag test records
checkpoint-status |  |  | checkpoint | 7.4 - Sub-base construction
label | f707e496-3da3-5606-93d3-507da4100260 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ee4e14fb-b1d2-54c6-9908-6de571b83725 |  | note | Specification/Drawings Reference - TNZ B2
label | 46f80a4b-7af8-5c81-84c2-1632f78f2acb |  | note | Frequency - Every 20m
label | c316399a-c3c6-5f4c-ae36-06ffc153667e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | 86db5103-9748-5f82-a593-4df384eb6cb1 |  | note | Conformance Criteria - 200mm thick AP65 sub-base compacted to a minimum dry density of 95%
label | 8fae2177-ee99-532c-9584-8151b59ce854 |  | note | ○ Average 95% of MDD with nothing less than 92%
label | f3cd88ae-57e7-5f8b-9d7c-f4e0f9bcc82b |  | note | Records - Test reports
checkpoint-status |  |  | checkpoint | 7.5 - Sub-base construction
label | 0fa267e7-ab53-510d-9d7c-7909d4666123 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 86ed813f-b79b-532a-aa97-8fba5572d2b0 |  | note | Specification/Drawings Reference - TNZ B2
label | ba44fdbb-96dc-5199-a5e5-b766f2146b28 |  | note | Frequency - Every 20m
label | fe182b8d-a685-5f86-9ff4-43928ba470a9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | 2e2ec6c7-3d52-5e61-a4fe-3cb22cc29384 |  | note | Conformance Criteria - CIV>=25
label | 447be51e-4d03-534f-9a2d-c5f8bbf90d3a |  | note | Records - Test reports
checkpoint-status |  |  | checkpoint | 7.6 - Sub-base construction
label | 89a4583c-f980-5077-a060-82f9193c78de |  | note | ACTION (Hold, Monitor, Witness) - H
label | b46ca745-a92f-5b09-96bc-4e0857f24d59 |  | note | Specification/Drawings Reference - TNZ B2
label | 03eff594-a6d3-5386-876f-cdd7c484a75b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | b1409b13-4bbc-5019-8f19-ae305c96987d |  | note | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
label | e4060828-3b85-59bc-a0d7-71f905e1dc90 |  | note | Records - Survey As-Builts
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.7 - Basecourse construction
label | 8824e1ef-db2b-5411-9d0b-1b395f9180ef |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3014f08f-a566-5cf4-b922-330473a0c5da |  | note | Specification/Drawings Reference - TNZ B2
label | 80199d07-3c97-5216-9550-1fee977348e3 |  | note | Frequency - Every 20m
label | b3c1c2fa-80da-5ea6-bdd3-4dd1f049fe7b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | 13519bd7-14f7-5c60-9eb9-89fc1dbbcd3b |  | note | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%
label | 6d34c2c4-684c-5ee4-aa04-89e4e027ccb3 |  | note | ○ Average 98% of MDD with nothing less than 95%
label | 24b9995b-a739-5a8e-a059-1bad2f1d64cf |  | note | Records - Test reports, Photo's
checkpoint-status |  |  | checkpoint | 7.8 - Basecourse Cement application rate
label | d26a9460-0755-5ccb-b5b4-b992dcb6b8f1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 41ecbab9-2643-56d3-abda-d28fe780ae91 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
label | 290d9d52-0fc0-55c8-866d-355476d67c20 |  | note | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
label | 6fa3e494-3aa4-5bdf-9f3d-0e71773fdbed |  | note | Records - Bag test records
checkpoint-status |  |  | checkpoint | 7.9 - Basecourse construction
label | 5e17f39b-29a5-5174-bb23-a94754af75e8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7229e932-eae5-523f-8fa2-6e183374b022 |  | note | Specification/Drawings Reference - TNZ B2
label | 06ea7982-986d-5098-9c47-36417f5dd34d |  | note | Frequency - Every 20m
label | 54566d0b-5c10-5984-982e-8cf7188deea9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | f2a89ef0-39af-548b-b8ad-fa41419e8998 |  | note | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
label | 949186bd-3e0c-5552-8041-62db422c8b06 |  | note | Records - Survey As-Builts
checkpoint-status |  |  | checkpoint | 7.10 - Basecourse construction
label | 2680036a-598d-53e7-a24a-e3c0f27485d2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7368d677-6c52-50e3-9d1d-d05ba396b253 |  | note | Specification/Drawings Reference - TNZ B2
label | fc3fe1d1-3685-5b22-8599-ab0e4c4b91bf |  | note | Frequency - Every 20m
label | 1d305976-e556-59f5-a0a1-4ab44332d6fe |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | cc26249c-cc92-51ee-bc0d-276048fff722 |  | note | Conformance Criteria - CIV>=25
label | 9e81b123-d7e5-50b5-a294-57be0f4421b6 |  | note | Records - Test reports, Photo's
checkpoint-status |  |  | checkpoint | 7.11 - Basecourse construction
label | 49944b97-6ef9-597e-a318-3c1aa4231425 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3d440818-006b-5cf0-ac9d-dcb28eb461d9 |  | note | Specification/Drawings Reference - TNZ B2
label | 226b1c68-becf-5cb1-bb45-bdd2f4685b97 |  | note | Frequency - Before sealing
label | f5d0a4ae-e879-575e-becf-12a0ec9b503f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | 95430ea2-915d-516d-a72d-ee02d2727da2 |  | note | Conformance Criteria - Mosaic surface
label | 7e9a560a-a4ea-52ac-b153-039f9dd38b81 |  | note | Records - Photo's, Pre-seal checksheet (CS-4060)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7.12 - Applying Bitumen
label | 34eee98d-ec9e-5b41-b516-28e1605ad71a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 46cb6354-86ed-51c1-8a1a-ac7aae56dc31 |  | note | Specification/Drawings Reference - NZTA M/6
label | d9d661e1-9a34-5a8b-9c52-576ed47f6623 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 6f0057f7-5649-56b0-816a-9fde36473ead |  | note | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
label | 5875de6f-d0e3-5a1a-96d6-babb7377f56c |  | note | Records - Spray report, Pre-seal checksheet (CS-4060), Photo's
checkpoint-status |  |  | checkpoint | 7.13 - Degree of saturation
label | f1a1c7d5-1766-5072-b90d-3065b6d0abb7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c04bc189-ffc4-592c-88e9-25591e05d676 |  | note | Specification/Drawings Reference - NZTA M/6
label | 64e1ccea-c33f-5655-8b4d-1aeebac2160d |  | note | Frequency - Before sealing
label | 6280fc10-c30a-5e60-b0b9-80fbfc972c86 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | 22853b31-6807-5c92-841b-d1bdffeb8fee |  | note | Conformance Criteria - Degree of saturation should not exceed 80%
label | 9f8a8b3b-8432-520e-8e9e-3d787711fd2d |  | note | Records - Pre-seal checksheet (CS-4060)
checkpoint-status |  |  | checkpoint | 7.14 - Chip seal laying
label | b511c933-f31f-561a-8a91-470c488d8fda |  | note | ACTION (Hold, Monitor, Witness) - W
label | eb6075de-ec36-53a0-85da-9b5d2d16a6c4 |  | note | Specification/Drawings Reference - NZTA M/6
label | 70e7436a-b746-52c3-b010-b215e2149cd9 |  | note | Frequency - During Construction
label | 95ec2f71-3a75-54f6-9bda-1f3c9b643d0d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 161fe68b-9ccb-532c-a74b-82309f523a94 |  | note | Conformance Criteria - Grade 3 and 5 chip seal
label | a67e8de9-5a5a-5103-92fd-a7e63a3758d3 |  | note | Records - Material certificate(s), Photo's
checkpoint-group |  |  | section | Section 8: FINAL INSPECTION & HANDOVER
checkpoint-status |  |  | checkpoint | 8.1 - As-built Survey
label | 8cc4d18d-cc1d-5a59-99b1-73fab7162354 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 99bbfbf7-f5f8-557a-9b09-a9fee1d4dd0a |  | note | Specification/Drawings Reference - 2-U3436.BM(14) S01-S03
label | 3bab04bf-7dd5-5505-9c7d-be687155deb5 |  | note | Frequency - At completion of Lot
label | 66b0ba7c-e096-58b4-91b4-bd54bb4cd06c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | ce500299-2f7e-5078-8d11-bdcaba21f9fa |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | 40f65eb6-4e81-52af-adc1-729a1b92adf3 |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.2 - CCTV inspections of culverts
label | c569861a-2043-58ac-9965-637b5a4b5f34 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2ebf936c-daba-5a70-a7f3-b3c54999bd6b |  | note | Frequency - At completion
label | 293318be-541e-5894-9927-c15106fe2570 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - CCTV inspection
label | 2abe161f-d954-5f64-9ec6-e91e8f2443e5 |  | note | Conformance Criteria - CCTV to inspect the alignment, no defects, joints are sealed properly
label | cd9b6bee-c5c9-5b2b-bdaf-2d06cd234622 |  | note | Records - CCTV footage
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8.3 - Quality Assurance deliverables
label | 4016d3d9-2006-5f8b-9c32-996a62424071 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6b8c23a1-309b-5b8b-84bc-c302b0f125d7 |  | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 024398d1-3e06-5761-8520-137563706e96 |  | note | Frequency - At completion of Lot
label | a6afb4b0-8c59-57c9-b8ea-b420c6e9efb0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 4331519f-e908-5925-a3c6-e7e738f00722 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 9f0b6605-474a-5fb8-b396-4160c1bf901e |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 8.4 - Completion Sign Off From Fields Below
label | 8aeb759a-3655-5e47-9192-0ebd6e08dc36 |  | note | Records - Signatures
checklist-flat |  |  | checklist | CS-4073 - Drainage Structure Water Tightness Test Record |  |  |  |  | Yes | CS-4073 - Drainage Structure Water Tightness Test Record | 1d3e364c-4053-4b05-bdfb-15c002af783a
checkpoint-no-status |  |  | checkpoint | Drainage Structures Water Tightness Test Record
text | 34a53e1e-df86-5f88-8144-a112db748012 |  | textbox | Project No.
text | 9281bbc0-16e2-516f-9543-3631ab9c450e |  | textbox | Weather:
text | c8e01409-d63f-5e7c-b46c-5d5dabe60f97 |  | textbox | Location:
date | 14f4f67a-c442-515f-8383-ebcee37df6e0 |  | date | Date:
text | 99f47d91-36b2-583e-ab97-33512efc170d |  | textbox | Personnel conducting test - Drain Layer:
text | 8e4fdb07-77df-5ca1-a4eb-e54c565f6609 |  | textbox | Personnel conducting test - Design Team Rep:
text | f9302164-a4d2-5cf5-8c51-c82d8ea8c41f |  | textbox | Personnel conducting test - Site Engineer:
checkpoint-status |  |  | checkpoint | Structure type & Chainage
text | 5493c32f-8a2d-5707-a5c2-7a2b4d414187 |  | textbox | Size of structure (mm dia) |  |  | mm dia
label | b944c73e-6a8b-516b-a313-3845923b9968 |  | note | or
text | fe7ca78a-94a9-56d3-aeb9-e119ddf110d2 |  | textbox | Size of structure (mm x mm)
text | 284df117-f438-5590-a3e0-33ed546ac059 |  | textbox | Depth |  |  | mm
select | d03a27d8-be15-59c5-826d-73d59da12691 |  | dropdown | Drainage plugs used | Rubber & Aluminium Plugs,Rubber Blow up plugs
button | 3e9f1700-21a1-5d20-8efc-468646faa028 |  | button | Plugs Braced? | Yes,No
text | 771ffa90-9abc-57f8-88e4-e119fd9272c1 |  | textbox | Structure filled with water |  |  | am/pm
text | db5c0416-a6c2-5e01-8598-538f35b006d9 |  | textbox | Water absorption duration |  |  | hrs mins
text | a16ce9cc-ec19-5e83-ae96-7f49c2d5f9b5 |  | textbox | Test start time: |  |  | am/pm
text | 3c511fad-f95f-5c9f-9e2b-acfe74cf5543 |  | textbox | Test finish time: |  |  | am/pm
text | 7e0d2dd0-bcc8-5ed5-b380-d6170a6a8efc |  | textbox | Duration of test |  |  | mins
checkpoint-status |  |  | checkpoint | Acceptance level shall be no more than a 5mm drop of water level in 10 minutes
label | 0f9f04b3-f124-5602-9d5b-302aa5846062 |  | note | Measure water level from top of structure
text | 2eb336ca-d08f-5e36-86c3-b24fcfe90f08 |  | textbox | Start |  |  | mm
text | 00821b29-e152-58f9-860e-cd4d1e20d6b0 |  | textbox | Finish |  |  | mm
text | ee047539-cb80-55f0-8450-958cc3221472 |  | textbox | Water level drop |  |  | mm
checkpoint-status |  |  | checkpoint | Test Result
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
text | 4cdc433f-8eb3-59cc-920a-e708a5c73ce8 |  | textbox | Name:
text | 2b99ded6-9d90-5cc0-be27-63a231c1a78f |  | textbox | Position:
text | aca4a026-c6b2-5ef2-955e-a13f689ca160 |  | textbox | Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | ITP - Te Puia Subsidence Site - F3001B Fault ID609 | itp |  |  |  | Yes | Ω (Deprecated) ITP - Te Puia Subsidence Site - F3001B Fault ID609 (old version) | 20cd30fd-064c-4178-b260-ef0bfb10f11e
checkpoint-group |  |  | section | Section 1: RECEIVING INSPECTIONS
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 387737d1-6f89-5c2c-ade5-30221700306a |  | textbox | CPS Eng.
text | 4cb7b80e-8d0f-5700-81df-0383f8955348 |  | textbox | Site Engineer
text | a25aaa56-b259-52b2-a47e-a3a08d656df6 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Rock Armour (D50=450)
label | fd751104-a075-5b11-ae0e-74d85fb3bc11 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a26ef81e-5121-5097-91b4-d3092380b40f |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | 777e6bb8-6ff6-5505-942d-62f478595537 |  | note | Frequency - Prior to commencement
label | c9ff6e43-c882-5ad0-ac3a-f9e2449d6251 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | d48ce603-f661-57c0-bec2-d6998e675d46 |  | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious materail. Shall have a D50 of 450 with a minimum specific Gravity SG of 2350kg/m3.
label | 739d14cc-f89a-592e-9a67-718b29c0b88b |  | note | Records - Material source test results
checkpoint-status |  |  | checkpoint | 1.2 - BulkFill (GAP65/GAP100) or similar
label | c4cc4156-0e67-50f1-b353-941b69a337d9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 973e9a7e-ee40-5171-9022-30a476e0297a |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | 56986806-463a-592f-b833-fff5f0da9fa5 |  | note | Frequency - Prior to commencement
label | d009aacc-c874-5c42-ad92-1c89d4b09699 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | b28c5971-11dd-528b-a007-cb543128b4bd |  | note | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
label | 004c911e-7751-56b0-b244-f2edc66e72bc |  | note | ○ Material source testing
label | d2faf1f8-a6f5-5634-befe-126a8fb00ef4 |  | note | Records - Material source test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - TNZ F/2 drainage material
label | 67c8d7e3-28f0-5ea2-a69b-aef6e548cd85 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1e0d6420-6b3b-5ef1-86c1-b2d85811b3c4 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001, TNZ F/2
label | 0e13bc9b-e6c8-5ca6-ac68-0c486ca098a2 |  | note | Frequency - Prior to commencement
label | 20edff98-18c8-5d31-b2d2-8eedc3425889 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 408b133c-6207-5137-8987-21f0cd36bf2d |  | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
label | 6af6c48b-e7bf-5247-ac6d-feae285b8d96 |  | note | Records - Material source test results
checkpoint-status |  |  | checkpoint | 1.4 - Class D A39 Geotextile
label | 522366e7-d6c8-5dae-9b92-c79777ad79ad |  | note | ACTION (Hold, Monitor, Witness) - W
label | d7497e4e-57d5-5b2c-a845-1bfb67b71c1f |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | ab2c2ac4-cdfe-53e3-ab18-a37b58fd2a10 |  | note | Frequency - Prior to commencement
label | 8d3ed4fd-9d92-5d70-8100-b5b68aaf93d8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 5e8ed595-40c1-5cd1-bafd-d8f15546945a |  | note | Conformance Criteria - On dry bed below fill
label | 737594c9-a0e1-5b1a-83d0-929a2e3a24fe |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.5 - Megaflow strip drain or drainage blanket for seepage if encountered
label | d9cd11ac-7df5-5157-a865-a45f7f48e156 |  | note | ACTION (Hold, Monitor, Witness) - W
label | abd81951-2642-5bff-84fe-24d1fec1d374 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | eadd19ab-40f1-52aa-8757-24e2f6a40f19 |  | note | Frequency - Prior to commencement
label | 7b83b49a-9c17-5199-bd96-f96fed967e91 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 5609ae32-516e-5404-8c33-7e4f379a8871 |  | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
label | e3fb31ca-4569-5079-9533-bafd262bc529 |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.6 - Biocore erosion control matting
label | 301307e0-922e-54eb-9e6f-2c1b40c3d1bb |  | note | ACTION (Hold, Monitor, Witness) - W
label | ede3573b-d139-5eb1-b78c-f4f80c8f2073 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | b0236efa-e03e-5bb4-a5ed-d72baf8978b2 |  | note | Frequency - Prior to commencement
label | 444074dc-c97e-5566-add9-4f67e01340e1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | bc2b6686-91cd-5113-a577-80e3ef408a7b |  | note | Conformance Criteria - NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders
label | 37a7b7be-8e56-5290-b1f6-463c5808c933 |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.7 - Enkamat 7018
label | 92d8c535-1c63-5391-9840-249b9d925ef9 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 60875ead-888d-5991-a5ff-35cfd7885cf9 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | a377e86d-47f3-5195-9e95-388102027e61 |  | note | Frequency - Prior to commencement
label | 4d3f9f66-1392-551a-bc6b-62f2559d0773 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | a043d11a-80a8-5fab-868c-cab32d3b64f2 |  | note | Conformance Criteria - NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders
label | 291cde82-7661-5ab9-ae06-ca31120e5fa3 |  | note | Records - Material certificate(s)
checkpoint-group |  |  | section | Section 2: IN PROGRESS INSPECTIONS
checkpoint-status |  |  | checkpoint | 2.1 - Survey Setout
label | 29456b74-512a-54dc-9440-13ff561d9489 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8bd0c152-c8f6-5a93-8179-7b66f59f9477 |  | note | Specification/Drawings Reference - Consistency with Construction Drawing
label | 2ce8bf52-7fc5-5dea-a89e-c84b4ff5dd9d |  | note | Frequency - Prior to commencement
label | 86f1dbb8-61bd-5290-8156-b361697e49ee |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | bfd83c62-be95-5f08-9a09-84ff6595f9b1 |  | note | Conformance Criteria - Set out extents of fill and check against design drawings
label | 9f4a052e-eea2-580b-9fb1-e55ab24cb5e1 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | 5e12d260-e3aa-5c75-8448-909cb0082acf |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3e86b697-c26b-5f82-a300-9dcfdfa2f563 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | dc02935b-8058-54a1-859a-9a740ccc977c |  | note | Frequency - During Construction
label | 6cb5d342-b243-543f-97cf-97f741c45c6e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3810f695-3009-5a2f-b215-4ad5625b19c6 |  | note | Conformance Criteria - Remove and clear the vegetation
label | a1db5fd6-08ed-584a-b45f-dd46cf985220 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.3 - Subgrade Inspection
label | bdfd71a4-b3ad-5949-af1c-525eceba6660 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c3f41507-6103-57ad-872b-270dbe5d0f83 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 5eff28e2-c0bc-5414-b1dd-44d4b62ca814 |  | note | Frequency - Per area as required
label | 24d8c89e-6fb3-5eac-bef9-414973509634 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager or representative
label | 0034614a-f248-5de7-a846-ab568e49bb44 |  | note | Conformance Criteria - Inspect fill foundation.
label | 2ad396c6-3ffc-582e-84cb-6eae59ae070c |  | note | ○ Fill foundation must be approved, in writing, before filling commences
label | 46fa74db-4b7b-53c5-8221-ad5c40c76b08 |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Ground Improvements
label | a9fa913e-e7aa-53cb-b03b-0c69ab4e8418 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 229e2fa6-2625-5e70-a532-2282e6ec13de |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 1448d6c2-2048-5c99-8092-313af21a3e7f |  | note | Frequency - During Construction
label | bcb3fae2-41b8-5500-878d-41178d6fd599 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 9848809c-dfa8-5c86-b3ea-556310267dfc |  | note | Conformance Criteria - Any area that requires Ground Improvements must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence
label | 44a30e8a-57cc-596e-9e30-9ecb61efe5ca |  | note | Records - Photo's, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Class D (A39) Geotextile installation on the excavated face
label | 9ccfa142-6a09-52d6-b275-33fae0a6b8b4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2993367b-c6ad-5c6e-9384-8b868fe521d4 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 8c6faf6f-9bfa-5942-aab0-1fbf32b52e0f |  | note | Frequency - During Construction
label | 54ed3fd1-fa4b-55c9-a091-a5f826975636 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | e2df4d15-252a-5449-976e-91076397cc5d |  | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation materail and engineered fill.
label | bd2b65fe-26cd-5e48-9777-22126bfd8c62 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.6 - Sub soil drainage
label | 93207115-da8c-5d01-9860-386a8172b371 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9a9e1b8d-60ab-51e7-a744-06e392533a72 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0002, TNZ F/2 or approved equivalent
label | 0973a1e5-e3aa-5ef0-a017-70ad46aa6703 |  | note | Frequency - As works progress in agreement with the engineer
label | 86f5ce2f-39fc-5570-a177-ddfeb7af7846 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b50ba4f1-75e3-557f-9197-774ade71e41b |  | note | Conformance Criteria - Engineer to assess suitable drainage location and confirm drainage positions on site.
label | 418b0bf1-274e-5fad-b619-366347815adc |  | note | Records - Photo's, Drainage Line Record check sheet (CS-4025)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Megaflow strip or drainage blanket installation for seepage if Encountered
label | 847c6f88-f8d7-5426-aa36-0565bf156c28 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4a7d2846-2d44-5f05-929b-c00f6130f311 |  | note | Specification/Drawings Reference - Buttress typical details A and F3001B-DS-GT-RP-0001
label | d4c28b34-850b-5400-b70d-fb408e620cfd |  | note | Frequency - During Construction
label | 77cd5ccc-a9fd-5d07-9925-425264a26d35 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 53545623-1cf3-52c7-a162-30e2788d546d |  | note | Conformance Criteria - Installed in accordance with manufacturers recommendations
label | 011f95e9-b158-5019-a996-788608f67d6c |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.8 - Bulk Fill Placement
label | 608faabf-9206-54e6-94c3-1fd3dd01cc0a |  | note | ACTION (Hold, Monitor, Witness) - M
label | f9c64c66-e7a4-5834-a562-5849f9557918 |  | note | Specification/Drawings Reference - Buttress typical details A and F3001B-DS-GT-RP-0001
label | 027eb05a-db06-50c1-b98c-fbb1936950ba |  | note | Frequency - During Construction
label | b1b90da0-d10a-5f43-9c07-09d494ad27d9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | de00e51c-edb1-5312-80df-9f3e115d03fe |  | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on dry subgrade
label | 392da913-e13a-5cac-a56e-904762747785 |  | note | Records - Photo's, Bulk Fill Earthworks Check Sheet (CS-4020)
checkpoint-status |  |  | checkpoint | 2.9 - Bulk Fill Compaction
label | fc6badb0-1e26-5ed6-83c1-413512eb1e0f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 3d09ba4f-fe44-5a57-a79a-f476c9fd6f8f |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | cad8da2f-13ef-5ff5-855c-4fc7edd07f44 |  | note | Frequency - During Construction
label | b54af2fe-10b1-571a-974f-77fe4be250ac |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing (Clegg 100kpa)
label | 7153015c-eedc-55a8-89a3-51690f942e94 |  | note | Conformance Criteria - A target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
label | 0519493a-f937-5801-b3f1-96f42ccb03ed |  | note | Records - 1M Scala Check sheet (CS-4000), Lab test report
checkpoint-status |  |  | checkpoint | 2.10 - Form and cut fill batter as per design 2H:1V
label | 7c51cf76-5002-5afd-935f-83ed9853126a |  | note | ACTION (Hold, Monitor, Witness) - H
label | f0242da0-8c7b-546f-9767-ecf51b6bbb91 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 48a2d9ee-377a-56da-99d3-709a828cc2f9 |  | note | Frequency - During Construction
label | 94041f71-59dd-5a16-94dc-942091de5c56 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | fb70153d-f58f-5431-8515-22ad1426f619 |  | note | Conformance Criteria - Erosion control matting to be placed and pinned on the face of the fill in accordance with the manufacturers recommendations
label | ea1a5c5d-d2e4-504c-bc7d-6d9e9226b099 |  | note | Records - Site inspection on completion, Survey as builts
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11 - Rock Armour (50-450dia) placed on the toe of the slope
label | c582850a-fb75-5c34-95b9-dc7ed15dd466 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 76e3b22c-c37e-5152-a1ef-82b0e4035086 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | e775bda3-206d-533a-a01b-5b9e63467d8e |  | note | Frequency - During Construction
label | aeffda59-5db2-545b-8134-b0b25220ce2d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 14115f65-ae3f-5554-86a7-a5a3b45cd74f |  | note | Conformance Criteria - The buttress to be keyed in to natural ground as required and agreed with the engineer. Rock armour to be added to the toe as required
label | 67263a22-5014-502e-8f8b-33c35cf980d1 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.12 - Verge Reinstatement
label | 7a7ddabc-03ad-5c66-b719-bc657a791781 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e8a617ba-5e31-578f-beaa-8305e46ee16c |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 96cbc927-d5be-5782-b8c9-8fffc1b9f96d |  | note | Frequency - During Construction
label | 9bd12995-2b09-5ed2-8f7c-4db862789d0d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | d97d8bef-5aa8-5ca8-b66a-be1f23b1ea89 |  | note | Conformance Criteria - Verge reinstatement as per site instruction by Engineer
label | bdefba70-24dc-5685-9088-e8cb0c951944 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.13 - As-built Survey
label | f1bb4c30-4b7e-551a-b170-3e9419e9755a |  | note | ACTION (Hold, Monitor, Witness) - H
label | f4f5c5cf-6db2-5d24-9dbd-20ccc45a367f |  | note | Frequency - At completion of Lot
label | 7f37d804-35d8-576d-b074-2efe2279fc82 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | 7e0b8903-b48d-511e-9848-7e2875295576 |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | ec742a71-2c43-58ab-9442-96cbb774e916 |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 3: Final Inspection and Handover
checkpoint-status |  |  | checkpoint | 3.1 - Quality Assurance deliverables
label | 791510b3-e069-5a7d-b62d-b27d9b952043 |  | note | ACTION (Hold, Monitor, Witness) - W
label | eaaa695e-7a52-51d1-9274-c93fffe8fea5 |  | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 08078da2-8a9d-5352-b4c5-f14a9bf181fd |  | note | Frequency - At completion of Lot
label | 5e0e1d9c-9e5b-57dd-a5f1-633f8f8480d0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 490b8c3a-93f6-5611-9b90-4060c36628c7 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | ce8d2010-6c81-53a2-ac9d-0c438ecc7dd0 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 3.2 - Completion Sign Off From Fields Below
label | dc6d04ec-9559-512d-a102-d49c78919c9e |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | EN-4011 - Environmental Field Inspection Record |  |  |  |  | Yes | EN-4011 - Environmental Field Inspection Record | 22ff7a12-3fe5-464b-a241-fffdda73d7db
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | 4b0ec9f6-4104-5853-a95e-1127d540f1fe |  | textbox | Project No.
date | b0dc60ca-3f5e-598d-8109-d0b97d73abe1 |  | date | Date of Inspection:
text | c157da85-cca2-5ba7-8295-3bb2cfb733ec |  | textbox | Time:
text | 7f23108a-fd30-592e-9018-5175a3c95921 |  | textbox | Zone / Area:
text | 2da44594-5600-5368-9684-c9fbbf70d133 |  | textbox | Weather:
text | b214cb71-78ea-5a0f-905e-19cfad9f9b47 |  | textbox | Person Contacted During Visit:
checkpoint-status |  |  | checkpoint | Copies of Inspection Sent to
text | b84b6845-fc44-5793-8e73-9d433608dc25 |  | textbox | Sent to (1):
text | 156ab345-9103-595e-b3ad-e147e80adaf1 |  | textbox | Sent to (2):
text | 36d892b9-d885-5370-b030-8886a67a7c6c |  | textbox | Email (1):
text | 0ced78d1-5b8f-54c5-8527-4cac38cc7e73 |  | textbox | Email (2):
text | e26ea8ec-42ed-56dc-a273-58443d6119b0 |  | textbox | Company (1):
text | 484e28f9-447a-5272-9f42-7cc8ac47a396 |  | textbox | Company (2):
text | 6b5542e5-4669-51ca-80b9-9cfffe017a94 |  | textbox | Inspected by:
checkpoint-group |  |  | section | Works Required
checkpoint-status |  |  | checkpoint | Item No: 1
text | ca680c93-5d67-5398-aa93-3ee5ac60576b |  | textbox | Responsibility:
date | 0f651d70-8ccd-5220-88a6-d00ae858a727 |  | date | Date to be Completed by:
text | 9c63d9f0-3224-53f8-abde-abdbafde888d |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | Item No: 2
text | 6c1b5cbd-1b3b-5409-b3e1-b167dcaddcd4 |  | textbox | Responsibility:
date | b3fe172d-a7e8-57c5-a8bf-f3df5c04993c |  | date | Date to be Completed by:
text | 6c29e124-b3ea-58b8-bd78-4bb6f25ee2a3 |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | Item No: 3
text | d43273cb-d53f-5210-9eca-3565875b7bb9 |  | textbox | Responsibility:
date | 17891a12-50db-5af0-b7e2-ccf06b95a930 |  | date | Date to be Completed by:
text | 39619e82-4e05-5400-a7d0-52f151d8bea6 |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | Item No: 4
text | c2f6ab64-a56c-5747-a658-1b08370adac6 |  | textbox | Responsibility:
date | 23df679e-4baf-5ef5-bff4-7878748be033 |  | date | Date to be Completed by:
text | 37aff62b-42b6-5e6e-bbbd-fbf6cd7567f0 |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | Item No: 5
text | cb59319d-02ed-5c70-9c23-0679ef08c5a0 |  | textbox | Responsibility:
date | 76f39f8e-57e4-5d69-aa1b-e69fea3e80bf |  | date | Date to be Completed by:
text | e0365fc1-036a-531a-94d5-7ee54082d3ad |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | Item No: 6
text | b7ec42bf-f59c-57a0-a29d-e133ae596cea |  | textbox | Responsibility:
date | e9d3851d-7409-5801-b53f-7db310991770 |  | date | Date to be Completed by:
text | 337789a5-2969-5cd5-9af2-016470a1168b |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | Item No: 7
text | 90e9a7e6-eec1-5bbd-85b3-c199bfb416df |  | textbox | Responsibility:
date | c0638a84-877d-5ee9-8ff5-49635e880173 |  | date | Date to be Completed by:
text | 5f18a6a5-55d1-528f-91c0-679a24e25ee0 |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | Item No: 8
text | fac239d7-6ae0-5550-b10b-f0c88de20414 |  | textbox | Responsibility:
date | 3e8360ef-8726-5e91-886c-f68b45ee9a67 |  | date | Date to be Completed by:
text | 255b0e23-723d-5693-9216-5724b63052b2 |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | Item No: 9
text | ac8d9e0a-3474-5de0-925a-cb2450680c92 |  | textbox | Responsibility:
date | a7e9fd60-dc1c-50c7-b517-125029a7bea0 |  | date | Date to be Completed by:
text | d605a6d6-1e4d-5a1b-a184-3781da001942 |  | textbox | Closed Out Signed Off:
checkpoint-status |  |  | checkpoint | WORKS REQUIRED HAVE BEEN INSPECTED AND APPROVED
text | 20adc666-f875-57ab-a07b-fa959de3fd8e |  | textbox | Site Supervisor:
text | 94bc12e1-60b2-5659-8a5c-7b72b7c45f39 |  | textbox | Construction Manager:
date | 421f28af-c43f-5957-b3c8-037f0c15e253 |  | date | Date:
checklist-flat |  |  | checklist | ITP - C1503B - Mautaua Under Slip - Subsoil Drainage | itp |  |  |  | Yes | ITP - C1503B - Mautaua Under Slip - Subsoil Drainage | 250b0a90-79df-40ce-ad7b-f9574acb0824
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 518547c4-4814-5532-9f94-bf9bcd80a4d1 |  | textbox | CPS Eng.
text | 14cc70c9-af48-592a-ac79-388f0865b3c9 |  | textbox | Site Engineer
text | d530125b-909f-542e-8997-ee009cf70568 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | d9e383c2-7a71-5945-836d-d65cf5b0dca8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3c45f520-d40f-59df-b59f-448aaf27e4d7 |  | note | Detail - Set out Edge of Seal to 1m offset. Setout and mark all known services along the line of the Sub-soil Drain.
label | 56d42fee-019d-566c-bc60-70322f054d89 |  | note | Frequency - Prior to commencement
label | 8adef0d4-10e4-5aec-b187-d55713795500 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | af6c91bf-10fc-5210-8537-4a4a13adf5e3 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 7d5803b0-5ba7-5f94-b7be-5e11e8eb5114 |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 2 - Material Compliance
label | 24278092-7420-5f84-9c36-df3679a03255 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 23485923-cb56-5e81-81da-e14fe316768f |  | note | Detail - Ensure Subsoil Drainage pipe is TNZ F2 Grade and 100mm diameter
label | 83a8555b-fdd8-5fd2-87d1-c6593f5d6fcd |  | note | Frequency - Upon delivery to site
label | 40db272d-fadd-5ac5-a7e1-64da1e1f0aa6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | f58c3047-d14a-567c-8ee5-962d9e279a35 |  | note | Conformance Criteria - 100mm diameter Drain flow TNZ F/2 Grade pipe
label | 400162e9-6fd5-57e5-94eb-82ef602b0060 |  | note | Records - Delivery docket
checkpoint-status |  |  | checkpoint | 3 -
label | e553f369-b132-5ef5-8188-54eeaaf4ec70 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 25dac27e-b01f-558b-a8ea-2fe1aa10b90d |  | note | Detail - Ensure Material for Bedding, Side support and backfill is 3 to 7 Clean Drainage Chip (Reject Chip)
label | 58c757c3-6e69-5894-b356-10554df7497a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 9b45b5c2-149c-545a-9ad8-08514e80798d |  | note | Conformance Criteria - In accordance with TNZ F/2
label | 2bee2370-0a69-5dac-aaf4-76a03ca43c83 |  | note | Records - Delivery docket
checkpoint-status |  |  | checkpoint | 4 -
label | c46c962b-fd08-506d-9ec2-d4c64b4802bb |  | note | ACTION (Hold, Monitor, Witness) - W
label | ba9b76dd-b925-5098-a9f6-8ac90a4ca626 |  | note | Detail - Ensure the bidim material is A19, Class B.
label | 1ce9d3f9-7cea-5db4-899b-d07bdf23356c |  | note | Frequency - Upon delivery to site
label | f0409eea-2499-56f0-a51a-ca34b1b8ee84 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | 9e08d9f1-9663-572c-b976-e964399d5f81 |  | note | Conformance Criteria - Ensure geotextile is approved for use
label | db0ad907-1ecf-574a-9c6f-cb238f6786fd |  | note | Records - Delivery docket
checkpoint-status |  |  | checkpoint | 5 - Trenching
label | 146eb9a2-9600-5591-affe-51de8dec9f17 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 72ef3bdf-db4c-5f77-b086-811702c92cf7 |  | note | Detail - Design Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
label | 406724a7-3366-5801-8ac0-81ded2b6db70 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | d5de1f84-d252-59ef-8444-56e640f6c13a |  | note | Conformance Criteria - Design Engineer to instruct action and record on dip sheet and as built drawing
label | 337c658d-9011-5cea-bc75-4f7e63d95bf4 |  | note | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Bedding, pipe installation and Backfill.
label | 60cf15bd-56e7-58b6-9b46-faf04a95b11c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 35311b4d-9b36-5224-97e0-24d6dd2ee99a |  | note | Detail - Upon completion of trenching approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material
label | 749b3153-a047-55a9-8b10-7999ef7cb388 |  | note | Frequency - 10m intervals
label | 47e42812-bacc-577d-9acc-611543b27711 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | bb928e98-b21a-527a-b0b4-97d721aab1aa |  | note | Conformance Criteria - Ensure material covers the trench and is pinned in place
label | a754a727-9563-5995-8672-1231513a6d39 |  | note | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 -
label | 6e9aaad7-c0d4-507a-bf84-6bad0d3c1b50 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a4aa2e7a-4778-5e36-ad89-bf4e51002550 |  | note | Detail - Ensure 100mm thick 3 to 7 Clean Drainage chip (Reject Chip) bedding is placed in base of trench.
label | 1d05e76a-2bcd-5426-a504-4c7be23d94d3 |  | note | Frequency - 10m intervals
label | 1c006e6f-fbda-5982-a9c0-de85efb0a362 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | d122e852-db4d-5b64-8248-3b723e472c4d |  | note | Conformance Criteria - Record levels of top of bedding on dip sheet
label | c9c22caa-a5fa-574a-9e30-f9315de49c20 |  | note | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
checkpoint-status |  |  | checkpoint | 8 -
label | 87f750ff-02e6-5476-8297-7b172ced93df |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3ef662a4-785e-580a-8fca-7ccbd186c09a |  | note | Detail - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
label | 5cc7eaf1-e44e-5f94-a021-598df3a041d0 |  | note | Frequency - 10m intervals
label | 5f08a244-589f-5ce9-a946-ea88d750c4ad |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 06cb943a-fbc4-5dff-b610-92abddd40a0f |  | note | Conformance Criteria - Consistency with Subsoil Details
label | 69305cf7-8f4d-59b8-93a8-94d99aee8903 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 9 -
label | 98a42d01-d10d-5184-b310-4ca1e06151aa |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3b869e05-519e-53a3-9a57-a997e842ca8f |  | note | Detail - Backfill by tipping 3 to 7 Clean Drainage chip (Reject chip) into the trench
label | 98e34fd7-ad81-541f-b0d9-9c89d2525357 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 08a2822d-a396-58ae-9fc6-6389ed86add6 |  | note | Conformance Criteria - Ensure good coverage
label | d3bac1bc-1e40-5eb7-9458-498530c27b74 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 10 -
label | f2607903-bfb5-5d4c-9a07-bcb6bc34c8a8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | caa0e245-b89b-5de3-bc19-8d99ded0a535 |  | note | Detail - Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place
label | 5f17e6ce-7594-5d2b-acd0-57f6d5e56eb8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
checkpoint-status |  |  | checkpoint | 11 - Outlet to any open areas
label | 5306d9d9-200c-5108-99f0-63583c6f2238 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 05d45edc-f5d1-57ad-8910-23ba4ada99e0 |  | note | Detail - If a subsoil drain outlets to a swale drain/grassed area ensure that a concrete plinth is construction and a marker post is installed - survey to pick up immediately
label | fb6e68a7-e0e9-5203-8839-81c1042147af |  | note | Frequency - As required
label | 5587b5c8-65d2-5bcc-98f9-eca2fdf57a58 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | de777e7d-b2a6-5684-b4fc-c554edcab8de |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Survey As Built
label | 8b715dc8-8c01-561f-802e-bed3198a7163 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b45a30de-5a5d-50d9-94e8-d6b3d2fa828d |  | note | Detail - Ensure all subsoil drainage lines comply with design prior to carrying on with next construction process
label | c3588d61-1ae5-5dd7-a010-9307620e9912 |  | note | Frequency - At completion of sub soil drainage line
label | 031eea27-445d-5187-8878-26d5ecf3e790 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 5c6215ae-2e16-540e-b5fa-204c314efbdd |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 - Lot Number QA File
label | b1551c7a-afa9-5c3f-925e-d4c81fe66374 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d5a4576e-3b2d-50e0-88e5-489ddc2b6715 |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 541978a6-27d1-5e71-9ba8-a51a9d5a1e1b |  | note | Frequency - At completion of Lot
label | d93a94b4-8263-5275-9213-73cf251ca389 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 978a7468-025f-5a47-85ee-d89ef795f6fe |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 0af46dec-3912-5497-b2e3-3b8c51dd0087 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 14 - As-builts
label | 7fc82291-ed8c-5a47-9f7c-1d07622a4843 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 175d8fc6-c4bb-504b-816d-1f7092b4ee23 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 2c360225-4a26-5239-9d7c-3de4f1dd7a21 |  | note | Frequency - At the completion of the Lot of work
label | 400c4195-91fe-50d4-b299-5d34fe459c05 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 5a3af319-0613-5621-a0f8-4c4b1f64936c |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | CS-4025 - Drainage Line Record |  |  |  |  | Yes | CS-4025 - Drainage Line Record | 26247330-10f0-47e8-b60a-09588da32d21
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | 0c5d6127-78b4-58b5-a8d0-91083dd8e213 |  | textbox | Drawing No (& Rev No):
text | 145b37bb-96cd-5ff0-ba75-a198d906f012 |  | textbox | Drainage Line:
radio | c2637935-9f15-5d61-98a9-7d529e6ef347 |  | radio | HS3 / HS2 / H2 | HS3,HS2,H2
date | d7b34307-34b7-59c1-81c9-ac73f3bbf275 |  | date | Date:
checkpoint-group |  |  | section | Inspection Stage
checkpoint-status |  |  | checkpoint | Set out by surveyor & handover to subcontractor completed
text | adffbf67-dc02-5780-b824-dd72032b7057 |  | textbox | Initials:
date | fcc40515-027a-5fc3-b698-2a25063c9949 |  | date | Date:
checkpoint-status |  |  | checkpoint | Start point (i.e. manhole/headwall) checked for line & level prior to commencing this drainage line
text | dfd2a1f9-4012-5a49-9609-ce0e00c42274 |  | textbox | Initials:
date | 406112a8-20e1-545b-a379-16123f0ce9ba |  | date | Date:
checkpoint-status |  |  | checkpoint | Foundation Undercut Compaction base of trench subgrade Scalas taken every __m
text | cb8b8c3f-c430-5e93-a051-3443197ecd48 |  | textbox |  |  |  | m
text | a06609e8-80c4-5b8e-8ee8-038eb4826f12 |  | textbox | Initials:
date | db48a335-70f4-51af-b5eb-5c91ab728ba7 |  | date | Date:
label | d4c2cb1c-d8cf-5f6a-8425-9b6ef4d208cc |  | note | Comments:
radio | 44b8e20c-b089-53b3-915e-c80d6d868f91 |  | radio | Under cut required? | Yes,No
text | 0a864b57-e5a9-56d9-b727-0eca2bbe2a5a |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Bedding Zone Compaction Testing every __m
text | 513f9568-9d31-5fb4-9349-928f25395f31 |  | textbox |  |  |  | m
text | e2975bb6-3fec-56e6-b2a3-89f3bdfdf057 |  | textbox | Initials:
date | ce7f8049-a90e-5cfb-a7c2-12ca788960e1 |  | date | Date:
label | 1805aecf-e21b-58e2-989f-61df5de376ea |  | note | Comments:
text | 175d5744-54a3-5285-8440-0649615fdc20 |  | textbox | Material:
checkpoint-status |  |  | checkpoint | Engineer to inspect base of trench
text | 6311f38c-2c2d-5a29-9493-d7f92673abdb |  | textbox | Initials:
date | a89f824d-53a4-5c49-aa9d-8e3a0c13b54c |  | date | Date:
checkpoint-status |  |  | checkpoint | Trench width per __m culvert line
text | e36d297a-dd14-541b-b8c7-f1a90a74fc71 |  | textbox |  |  |  | m
text | cbfe1706-866f-55d9-ab8c-d953e3120be0 |  | textbox | Initials:
date | a6bc2885-eb96-59d4-84f7-30b58df91338 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pipe Laying Inspected and approved by Site Engineer
text | 4402fd30-23eb-5aaa-8614-5cefb3454d15 |  | textbox | Initials:
date | 923ce5c9-6da2-5afe-8884-f83a45a138e3 |  | date | Date:
checkpoint-status |  |  | checkpoint | All Connections completed and inspected as per specifications
text | 39021d6c-025e-522f-925b-d88d103ce4bc |  | textbox | Initials:
date | 52ab09ce-abdc-5897-9e6b-3dff61162de5 |  | date | Date:
label | ffb999ab-59f4-59d8-b6d2-0cd3df13ce10 |  | note | Comments:
text | 04ec6440-8eb8-5d52-82d6-cfa553994f0f |  | textbox | Structure (In):
text | 81beccc9-3384-5640-9fda-088e4901ff3c |  | textbox | Structure (Out):
checkpoint-status |  |  | checkpoint | Haunch Zone Compaction Testing every __m
text | d2fedda1-f2e6-5662-8e29-345ac7a797c4 |  | textbox |  |  |  | m
text | 60707f67-779f-5564-bdbc-507b08daa438 |  | textbox | Initials:
date | 7034140e-6da1-5c3e-8c1e-e542e7dc70f8 |  | date | Date:
label | 4edf3b54-1f61-5627-a8e4-306ae5876cec |  | note | Comments:
text | fb8ea3dd-5278-56ed-b971-4952ab3dd791 |  | textbox | Material:
checkpoint-status |  |  | checkpoint | Side Zone Compaction Testing every __m
text | 507671d9-e64b-56d3-9552-6c715e5751d5 |  | textbox |  |  |  | m
text | 752c92a2-7a94-5747-8c47-a368b559e27d |  | textbox | Initials:
date | dea3f652-07b6-55e0-8c68-e32ce8a31965 |  | date | Date:
label | 17735552-b87a-5df2-8e8d-bc60dc051b16 |  | note | Comments:
text | 70f65033-f0f9-5435-ab6e-835ace6b84ea |  | textbox | Material:
checkpoint-status |  |  | checkpoint | Manhole Conections to Pipe Joints Haunched/Concreted/Epoxied
text | f3ef914b-83a3-5d28-afee-da93dc0bbcd0 |  | textbox | Initials:
date | f04afab7-281e-5e2d-b517-1a205c11f319 |  | date | Date:
checkpoint-status |  |  | checkpoint | CCTV Completed and passed
text | d3ebdfa7-92b0-50f5-9946-726377a16a64 |  | textbox | Initials:
date | 44cd82ec-d9f1-5e39-81dd-2e19ad1fa60d |  | date | Date:
checkpoint-status |  |  | checkpoint | Water tightness test passed
text | cbaeb8b3-d79a-5290-ab8f-b8d35bded2da |  | textbox | Initials:
date | e51d4aa8-f9e0-5d01-a4d0-80846ceae429 |  | date | Date:
checkpoint-status |  |  | checkpoint | Final visual Inspection Completed and approved by Engineer
text | 2ae58565-bec5-5da9-b88f-e0fad80f2f49 |  | textbox | Initials:
date | ee55922b-aa34-57a8-b00a-df6e91f5c5ec |  | date | Date:
radio | 8e7ff41e-0a5d-5a1e-863a-33b925052ecf |  | radio | Invitation to inspect: | Accepted,Declined
label | 0f97f531-8fd2-5d05-b468-96f49ba14299 |  | note | Design Team
text | 64e73c5a-a0b5-5bc2-a197-1e67c9d17426 |  | textbox | Design Team - Rep:
date | 5388e586-be70-51f9-9d04-9566b30563cc |  | date | Design Team - Date:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
text | d32a8d8d-3ad3-5bc6-8379-a9aeafe4f008 |  | textbox | Name:
text | 13a33226-0565-5a36-9c2e-b783397382a0 |  | textbox | Position:
date | 7b00a828-bc8e-5d13-8626-d708377a7ccb |  | date | Date:
holdpoint |  |  | signoff | Sign
checkpoint-group |  |  | section | Drainage Line Record
checkpoint-no-status |  |  | checkpoint | Direction of Flow
radio | 2da348a6-8e4a-5351-83ec-cea5aa6347d8 |  | radio | Indicate Direction of Flow | <,>
checkpoint-no-status |  |  | checkpoint | Invert Level (In)
text | 79f08d7e-7ad6-57ca-86a0-484e65eabfe9 |  | textbox | Design:
text | b6099b91-3e21-5aa9-9302-f2a72a3e1b2c |  | textbox | As-Built:
checkpoint-no-status |  |  | checkpoint | Invert Level (Out)
text | 4096eb62-29ff-5919-b476-c60a224cd220 |  | textbox | Design:
text | 40c26859-73df-5cd6-8f2b-e29b97237f62 |  | textbox | As-Built:
checkpoint-no-status |  |  | checkpoint | Structure (1)
text | db817c6c-449f-5efd-b3a7-7aadb37f0199 |  | textbox | Structure Name:
label | b069142c-82b2-5123-a887-42c264838cb2 |  | note | Status: New
text | 97221a99-f854-5246-87e7-7246aee4e87b |  | textbox | (New) Dia:
label | 2f509de6-f65b-537f-9253-cebe4af03482 |  | note | (New) Type: MH
text | 0993a8f6-6a38-5f73-bea1-87d17e8d49ba |  | textbox | (New) Distance to Flexi Joint:
text | 6287677e-def9-5d11-9bbf-d25636b5149c |  | textbox | (New) Epoxied:
text | 77425fd1-3d37-5a75-b7a2-ece3bbb9d50c |  | textbox | (New) Water tight:
text | c5b57682-16ea-5cb4-a733-8b474de13779 |  | textbox | (New) Depth: |  |  | (Measured from MH Base to underside of Concrete Lid).
text | aff135dc-b6ec-5498-b46a-76262dd9a187 |  | textbox | (New) Throat Depth: |  |  | (Measured from underside of concrete lid to finished final lid level (FSL)).
label | 34fb05b8-e4d3-5f24-8923-2f2a54533bae |  | note | Status: Existing
text | 702e92b0-ae5f-5574-856c-177476016ebb |  | textbox | (Existing) Dia:
label | dec68ef7-bb8a-5d0e-8e72-764ff7601f64 |  | note | (Existing) Type: WW
text | 4a061243-6cf2-5879-8055-ed1540fee5d9 |  | textbox | (Existing) Distance to Flexi Joint:
text | 3611c4ff-434a-5c63-a000-46d953342404 |  | textbox | (Existing) Epoxied:
text | 1b78cfba-4cab-533c-8a30-7dd7a1da6cc1 |  | textbox | (Existing) Water tight:
text | 4130868c-6d47-55df-8220-0674d24693bd |  | textbox | (Existing) Depth: |  |  | (Measured from MH Base to underside of Concrete Lid).
text | 38913c00-a962-5b2d-8da8-dae26046a16c |  | textbox | (Existing) Throat Depth: |  |  | (Measured from underside of concrete lid to finished final lid level (FSL)).
checkpoint-no-status |  |  | checkpoint | Pipe Details
text | a0b466a4-7a40-503b-86a7-60eb25f9470c |  | textbox | (1) Dia:
text | 14fe9134-de3d-5d14-a45b-f2b3b6e97d3e |  | textbox | (1) Length:
text | 68378fbe-6e7b-55d6-8c85-f2fa6abe88cc |  | textbox | (1) Material:
text | f433a4d2-5b9e-5f6f-ab50-30019969454e |  | textbox | (1) Class:
date | 006f301b-561c-5ddc-979c-e167042a848b |  | date | (1) Test Date:
label | 9cce8d1c-74db-55ca-918c-650116b0846b |  | note | (1) Air test: Pass
text | 891cff38-6f9a-532e-95ec-8854fd74df09 |  | textbox | (2) Dia:
text | b55d9575-c333-549f-a0f6-17a6e67463c6 |  | textbox | (2) Length:
text | a8c5614f-8db9-58c8-a585-0c36b4a625e7 |  | textbox | (2) Material:
text | 78aa5230-b960-5504-83d8-81327a42dfd3 |  | textbox | (2) Class:
date | 0040d829-8d82-5c8a-8934-f4b3d46daa0c |  | date | (2) Test Date:
label | 4e18e058-b9c6-550b-a46b-2a87d392c1e5 |  | note | (2) Air test: Fail
checkpoint-no-status |  |  | checkpoint | Structure (2)
text | fc6a9bc2-ba73-5581-a434-ef75df3bd576 |  | textbox | Structure Name:
label | 3a7e81c9-7278-5b5f-b3f9-9066a2c56c7f |  | note | Status: New
text | 87d52c63-2db3-580f-afb1-e5a1b7303345 |  | textbox | (New) Dia:
label | 70c632dd-4870-5471-bced-9ec2320bcdba |  | note | (New) Type: MH
text | 2f993353-3554-5cc2-944e-91084c85561a |  | textbox | (New) Distance to Flexi Joint:
text | bd3359ca-14fa-52b0-856f-68f9b4dc06d5 |  | textbox | (New) Epoxied:
text | ea1384ff-edf9-5fb3-bf6f-9dcbeb6ef3c7 |  | textbox | (New) Water tight:
text | d1af8d87-e26f-50db-9a1c-0c3cd22a9844 |  | textbox | (New) Depth: |  |  | (Measured from MH Base to underside of Concrete Lid).
text | d5d222a5-04b3-5fdd-a6ad-ca022db01695 |  | textbox | (New) Throat Depth: |  |  | (Measured from underside of concrete lid to finished final lid level (FSL)).
label | bbdefad2-90f2-59e0-8623-ce87ca8d2705 |  | note | Status: Existing
text | 5d215534-9ef9-560f-8ebc-3e4cd04aeb81 |  | textbox | (Existing) Dia:
label | 1371f3b5-b946-5136-9a36-7cdb8421a258 |  | note | (Existing) Type: WW
text | db07b648-fc28-507a-bf1e-64c8f6ac3dbf |  | textbox | (Existing) Distance to Flexi Joint:
text | b9310563-f08e-5755-a95c-d83394bc39d4 |  | textbox | (Existing) Epoxied:
text | 16605c85-508e-5a5b-8b6c-234e910d7f33 |  | textbox | (Existing) Water tight:
text | d348d85f-628a-5e20-9660-756c8fa1d0e9 |  | textbox | (Existing) Depth: |  |  | (Measured from MH Base to underside of Concrete Lid).
text | 6a0be341-065d-5a46-af9a-301884a080dc |  | textbox | (Existing) Throat Depth: |  |  | (Measured from underside of concrete lid to finished final lid level (FSL)).
checkpoint-no-status |  |  | checkpoint | MATERIAL TYPES AND SOURCE
text | 63037b72-0aa5-5977-8fc2-45118c782e47 |  | textbox | Undercut Depth:
text | 5526a46c-ca4b-5858-9f36-f5505014ed32 |  | textbox | Undercut Depth - Type:
text | ee3b6ea2-3bf6-5d6b-a879-6f136642d3f8 |  | textbox | Undercut Depth - Source:
text | 506c04ce-9bd3-51ec-a79c-a5cea6c3336c |  | textbox | Bedding, Haunch & Side Zone Depth:
text | b29d8135-aaa6-5cf3-8ba6-6c1c7bb8a013 |  | textbox | Bedding, Haunch & Side Zone Depth - Type:
text | 862544f2-ea0c-5df8-8c1f-618ae37317b0 |  | textbox | Bedding, Haunch & Side Zone Depth - Source:
text | d32cd969-160a-59cc-996e-b5c0e68c396d |  | textbox | Backfill Depth:
text | 32919aba-d05c-5991-b041-104d90d2fcd1 |  | textbox | Backfill Depth - Type:
text | 7a60b8f0-391b-5f6c-9aa4-7055d4662e30 |  | textbox | Backfill Depth - Source:
text | 944f4863-427e-5e4d-845a-c94b4d8299fd |  | textbox | Design Grade:
text | 4645005f-2a77-59c7-82e8-e892db77eeb8 |  | textbox | As-Built Grade:
checkpoint-group |  |  | section | Connections
checkpoint-no-status |  |  | checkpoint | 1
text | 913c3b70-68d7-51bd-8ea5-3ea5d7c83c9d |  | textbox | Distance (m)
text | d15ee320-a258-5a0f-ae77-56ef344abfed |  | textbox | Dia (mm)
text | c91f9043-b307-5dae-8a8e-cdbb9102bc83 |  | textbox | Depth @ BDY
text | 6e7540dc-fa4e-5ed3-a584-eabb4a8c5caa |  | textbox | House / Lot No.
text | b58f9f60-0333-5357-91de-b1a510d0fde3 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 2
text | 17cd1fb5-a3d0-585d-bd8d-6f7d152c1052 |  | textbox | Distance (m)
text | e65ac463-b3fc-52a4-bbcd-0d4c84761045 |  | textbox | Dia (mm)
text | bcb09cc7-609f-5ea9-86cc-14cb36ecb4b0 |  | textbox | Depth @ BDY
text | c69dc52c-e47a-543b-aac3-a2439fac21bd |  | textbox | House / Lot No.
text | 092851d0-9ee0-5974-b442-6a14270cb575 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 3
text | 64d2a7f9-d899-5f2f-bb46-ab85115b1ef3 |  | textbox | Distance (m)
text | 3b316a71-46b7-5c4c-9fb1-bfa83fdd3d32 |  | textbox | Dia (mm)
text | e78709dd-ba3d-5354-80fa-db6e9027f8eb |  | textbox | Depth @ BDY
text | b7f7e614-d991-54d3-98ff-64acbd2f5656 |  | textbox | House / Lot No.
text | adc25e9f-29a5-5520-ad9f-2533e085aa09 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 4
text | ea5270bd-02d3-5446-87ab-a727f7d85464 |  | textbox | Distance (m)
text | 6e09a6b1-6eca-5e59-b885-110bbff730de |  | textbox | Dia (mm)
text | 5a0eb003-ef55-537e-b4f7-4d9e606d0a82 |  | textbox | Depth @ BDY
text | 2e197542-dd0a-532e-b81f-eaeb61d5e601 |  | textbox | House / Lot No.
text | d53ba8cf-47ef-59d7-8f71-30b491f3b673 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 5
text | cf4707f5-ed5a-556e-8d6d-a3664b2bf863 |  | textbox | Distance (m)
text | 65d0a008-8dba-5e7f-90f8-ad77a0f2f812 |  | textbox | Dia (mm)
text | 077b7f5e-31a2-5942-965a-0175c84ed90b |  | textbox | Depth @ BDY
text | 07c0449f-33f3-5d5f-b6cf-23b6ec46a3e1 |  | textbox | House / Lot No.
text | c62f6645-7dd4-5e72-9311-b9919b60a0d5 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 6
text | b5327f1e-0359-533f-8f0e-8af28c85b507 |  | textbox | Distance (m)
text | b65e3ba4-0031-50ee-99ff-427d1c24fb06 |  | textbox | Dia (mm)
text | d5a38a2d-2305-59a3-bc63-eab0d99af8a3 |  | textbox | Depth @ BDY
text | 0cb075cf-4d61-56e3-92d0-04a5e5b3bb95 |  | textbox | House / Lot No.
text | b1ef9271-ab33-5438-95f9-cc30a8d9bed9 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 7
text | c868f531-672a-5cd2-ae46-cb0a71758f67 |  | textbox | Distance (m)
text | d0d6199b-0ade-5a08-80f5-31391b6b1019 |  | textbox | Dia (mm)
text | e0631ed8-fc94-5afc-b7fe-31b63851f94d |  | textbox | Depth @ BDY
text | 9acb3fac-d727-522d-86ca-85016dbfef53 |  | textbox | House / Lot No.
text | 411a39b8-8cff-5b6c-a70c-c999d33a41fc |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 8
text | db80b4f4-0c66-54d7-a56b-1efe8065f902 |  | textbox | Distance (m)
text | f7c9694e-9a9d-52c5-a21d-7a2b27e8a3b9 |  | textbox | Dia (mm)
text | 715a8650-28bb-51d7-8adb-bf0d7e731a53 |  | textbox | Depth @ BDY
text | c3ecb601-d2f3-52b8-9ffa-08a14ba57da9 |  | textbox | House / Lot No.
text | d8dec1a6-997f-51ba-9aa4-ab5169afc2cd |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 9
text | d6804b4b-6e9a-5912-9ba9-e3ba8d110136 |  | textbox | Distance (m)
text | 81a38b7c-4090-5913-8a8d-1124d14f91fe |  | textbox | Dia (mm)
text | 95045bfb-e17a-5bd7-a16a-2bf916804e1f |  | textbox | Depth @ BDY
text | 00845fb9-8b07-5152-97fd-4f5986002330 |  | textbox | House / Lot No.
text | b8dac593-196d-5dd9-b909-9b9a39787096 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 10
text | 017d7759-bc60-57c5-a1c8-d5202fdd35e1 |  | textbox | Distance (m)
text | 1f910339-fd13-5d3e-8698-1feb001e68f0 |  | textbox | Dia (mm)
text | 7cc59f79-c177-5119-b57d-8898d39554b5 |  | textbox | Depth @ BDY
text | dfff53d4-ee42-542c-8e9d-a468e1cc943a |  | textbox | House / Lot No.
text | a223fafa-19a7-50b1-963c-859dccc918f7 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 11
text | 968aaa51-cfbd-5b1a-94e8-5b2f01325bb3 |  | textbox | Distance (m)
text | f6cc3ab1-c0b5-5ec1-9fbe-8fdd47fa12bc |  | textbox | Dia (mm)
text | 5edab82d-6bc3-5dbf-963d-391e944ec359 |  | textbox | Depth @ BDY
text | 502c0e4a-5618-57ec-b532-67a8e6791055 |  | textbox | House / Lot No.
text | 379ec4b0-6bac-5126-b4a2-f3c92e00a0c4 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 12
text | 4cb8decf-d8cb-5033-aa5f-d1fa78f954b5 |  | textbox | Distance (m)
text | f2ff50a7-cf69-5de7-ab14-a7e129645da1 |  | textbox | Dia (mm)
text | 11dd974c-0388-5512-aacc-1333a23679d2 |  | textbox | Depth @ BDY
text | 211ea1d0-7766-5bf8-89e1-01b93494aec5 |  | textbox | House / Lot No.
text | 865788d1-0724-5955-97b8-f7820c968359 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 13
text | 31ec441a-1c92-5d0a-8206-4392d12ca805 |  | textbox | Distance (m)
text | 45f00a77-abae-528e-a139-1d671499f111 |  | textbox | Dia (mm)
text | de7e2300-8387-5760-882f-e471e37c9eb1 |  | textbox | Depth @ BDY
text | b1fd54a6-7fec-5005-aef2-0064403cd3a2 |  | textbox | House / Lot No.
text | ae9f7269-70ac-5832-b8fd-83b1a7f70230 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 14
text | 558f826e-de8c-5f17-aa92-f87971013f9c |  | textbox | Distance (m)
text | c7caf070-81da-5874-a08d-dd88a7d6df1b |  | textbox | Dia (mm)
text | 66715f32-aace-5153-bdfa-1f2f83f8de05 |  | textbox | Depth @ BDY
text | 2b10f561-a123-5b44-af68-ff113b3d015f |  | textbox | House / Lot No.
text | 09d14c9c-dbd8-5a1c-91e2-e4d65992ad6c |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 15
text | 7c4cd16e-fdd1-5cab-a73f-e2928a2b3ec1 |  | textbox | Distance (m)
text | d4ae31d8-c436-59b7-8f46-e0329448a9fa |  | textbox | Dia (mm)
text | 3a435483-95bb-5886-8237-8dfc51643dad |  | textbox | Depth @ BDY
text | c6a4f541-d66a-599f-9dbd-c05c1784c409 |  | textbox | House / Lot No.
text | 71cc4cc3-1747-552d-a98b-a13f7caa846b |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 16
text | 0390f42e-6e55-5527-8b7f-cea87f258fcd |  | textbox | Distance (m)
text | fb876221-0136-5707-bfbc-1c27b6e1600f |  | textbox | Dia (mm)
text | 337dbcd6-b5f7-5fa4-805e-1e7a4d9e95d6 |  | textbox | Depth @ BDY
text | 5c1c6892-7350-56ee-aa2b-3c1dbd4c27fe |  | textbox | House / Lot No.
text | 30d2d81d-5f90-5a19-b555-47aa7c3de578 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 17
text | ab0fc8fc-cdca-54aa-9360-4e5e8423f1b1 |  | textbox | Distance (m)
text | 2bb9f5ce-fc2e-5d80-96d4-1ae474760217 |  | textbox | Dia (mm)
text | 12ba9643-ccf1-5406-802c-2abfc2edc46b |  | textbox | Depth @ BDY
text | e09f2bf4-0106-5bbe-847e-7f556a4fb418 |  | textbox | House / Lot No.
text | 3ab2a9a0-c351-50c6-9773-b4f90f8716d7 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 18
text | 3a6dd7a3-422a-57a3-9cd9-5983abb941c6 |  | textbox | Distance (m)
text | 0ce36aef-bd26-5f68-8ad2-eb15464a345c |  | textbox | Dia (mm)
text | 49bbf4d9-32b9-57d9-8f24-b513ce58cf5f |  | textbox | Depth @ BDY
text | 7b454a67-1425-5104-9b1f-02939223401e |  | textbox | House / Lot No.
text | 4ebd4dd4-739f-5bf5-8770-5d8d88f127b5 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 19
text | 3d32fc93-0b2f-5f22-ad37-2db465065a8e |  | textbox | Distance (m)
text | 2ea17b6c-6ce6-5f22-8e56-0f141d11c515 |  | textbox | Dia (mm)
text | 3983b05d-208a-555a-a0ea-db3d4fb67c5c |  | textbox | Depth @ BDY
text | 665ad2d8-11a2-52e0-9f9b-9e5e74feef54 |  | textbox | House / Lot No.
text | 3d103bab-c569-5bd8-8c1a-0ebe3a2050ae |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 20
text | 65e498ea-6fe7-5dcb-a6a1-29acb535fa68 |  | textbox | Distance (m)
text | 5760fc10-c5ad-5fd2-a6ad-609ac9e265cc |  | textbox | Dia (mm)
text | 5aa2bc46-6e29-5753-86fd-cdf04e5d1ac1 |  | textbox | Depth @ BDY
text | 42bb5fe7-1115-5800-b988-2c27919163db |  | textbox | House / Lot No.
text | e21a5295-80a5-542e-a30d-5b1b9a62997f |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 21
text | 2f369ec2-8ca0-525c-aded-14fbd16cbad2 |  | textbox | Distance (m)
text | f390574f-5728-5fcb-846e-6f36747abc9f |  | textbox | Dia (mm)
text | feaf5a64-1d07-56b6-9d73-5366db8ffc51 |  | textbox | Depth @ BDY
text | fdd51b7a-e8c5-5f7f-85e4-a996aaf1b2d2 |  | textbox | House / Lot No.
text | 84e02ed2-1ac8-5ff6-9d42-3a202b36f84b |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 22
text | c32c75b1-056f-5ef0-bba8-a4f67deba8be |  | textbox | Distance (m)
text | 84f4cf6e-f11f-5116-a3d6-f6b36c00cba7 |  | textbox | Dia (mm)
text | fcd69b63-1959-5385-a071-96d9b1620e05 |  | textbox | Depth @ BDY
text | 9d611918-8268-5f84-82a1-6ea389ce3331 |  | textbox | House / Lot No.
text | a2696705-3212-56df-a813-3d086f3b4eac |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 23
text | 2e951a61-729b-5941-bfcb-c86051e05ec9 |  | textbox | Distance (m)
text | 2ddfccc3-08e9-5161-a135-5288067a9027 |  | textbox | Dia (mm)
text | 8123cb26-6150-5292-95b9-272712895913 |  | textbox | Depth @ BDY
text | 4f0ee8db-7501-5a62-ba50-bf669cdad9f5 |  | textbox | House / Lot No.
text | c6c2c395-3669-5b72-9cc4-1b76a5c62f5e |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 24
text | be45ef54-1145-58d6-9a19-bc309ba80b42 |  | textbox | Distance (m)
text | 7aeab5c2-6b38-5aba-8b30-12e37eb98fe2 |  | textbox | Dia (mm)
text | a9b7afcc-e4d9-5b30-8d56-fa085b407810 |  | textbox | Depth @ BDY
text | 6625a72e-d8c6-59db-ae46-fbbf117405f7 |  | textbox | House / Lot No.
text | e40117d7-8ccd-5b18-b33a-bf3b906768a8 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 25
text | aef43bb6-535a-55d0-80be-4492a38dc38a |  | textbox | Distance (m)
text | 7964e8d7-8418-50d0-bbaa-97c44374199c |  | textbox | Dia (mm)
text | ff805161-228b-5997-aed3-d3e27015b953 |  | textbox | Depth @ BDY
text | 334086f7-85bb-5145-ad73-e182350dea9c |  | textbox | House / Lot No.
text | acb72fa9-69e4-5a3e-8dbf-6950615abeef |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 26
text | 8b479ebb-f537-5215-8e57-4b116649903b |  | textbox | Distance (m)
text | 52ae4f62-38fa-5622-b262-98dc7701e580 |  | textbox | Dia (mm)
text | d3e4c07c-2cf3-5227-9e24-f41ca745a073 |  | textbox | Depth @ BDY
text | d6486b7b-babc-5ece-bc3e-839d068a9b9f |  | textbox | House / Lot No.
text | 914173d9-6d43-5e48-82b2-2f52059719e8 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 27
text | 10418255-0d3f-5943-a80f-28b7edfcad6e |  | textbox | Distance (m)
text | 446dcdda-0ffa-5026-a7d8-ac69d2ae97b1 |  | textbox | Dia (mm)
text | 05643edf-559e-596c-a8b2-fae65ecccde9 |  | textbox | Depth @ BDY
text | f641733f-d324-5533-a6d2-650e30c4a6c1 |  | textbox | House / Lot No.
text | 42878d9c-b2c3-53bd-a080-8d40edb3899f |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 28
text | f4fbe76b-159f-5851-aaad-1a72e4fff56f |  | textbox | Distance (m)
text | 33c7c439-24b1-594f-b4a4-cd3afd87938c |  | textbox | Dia (mm)
text | 179ff8db-8bc2-5b88-8a35-c84d6540b371 |  | textbox | Depth @ BDY
text | cb9e2b08-30f9-5729-a7da-7d407fc9fad0 |  | textbox | House / Lot No.
text | 7edff57f-a99f-5987-9e9c-e65bc21dd218 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 29
text | f0e09622-75fe-5a75-a04e-c3f294f33c6f |  | textbox | Distance (m)
text | 5a626ddd-aee2-588a-8580-19d0da229848 |  | textbox | Dia (mm)
text | 7251f4e6-090f-53e0-a2d7-fe4d1d8056f5 |  | textbox | Depth @ BDY
text | 57383fe5-8628-573d-a92c-e069075a1d21 |  | textbox | House / Lot No.
text | 3214e671-6d13-5fbe-8240-768d80fe8ce4 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 30
text | b126e041-1798-5a05-97e5-5bcbd742fc12 |  | textbox | Distance (m)
text | 7158c2a9-8acb-57ff-ae56-61b85657f0f9 |  | textbox | Dia (mm)
text | b9531fed-44da-528b-8aa0-3874690be6a4 |  | textbox | Depth @ BDY
text | 72a4f36d-c574-5ac4-bf83-2e413c571aaa |  | textbox | House / Lot No.
text | 8f7107c5-efb4-576d-9493-57395bee8b7d |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 31
text | 0ee82c0c-3a8f-554d-9285-3fcc3ff12184 |  | textbox | Distance (m)
text | d6715079-44cc-5f39-9963-01dcd084bb0f |  | textbox | Dia (mm)
text | dfb12442-2d38-5cfc-a932-828a0f1ddba3 |  | textbox | Depth @ BDY
text | 49d0ad8d-6d08-5be0-b43b-694ede7d1bac |  | textbox | House / Lot No.
text | 44369c13-c33b-5dd4-9431-a13c21ad2f54 |  | textbox | Length (m)
checkpoint-no-status |  |  | checkpoint | 32
text | 0cb7093e-c95e-5785-a696-824ce398e9f7 |  | textbox | Distance (m)
text | 67a04ff1-d1f7-506f-887d-e018412e34cc |  | textbox | Dia (mm)
text | e9e720e2-0f6c-575e-b475-5de526dd2b64 |  | textbox | Depth @ BDY
text | fccf21c7-9cce-5ee4-b17a-3e7bd0a8fcfa |  | textbox | House / Lot No.
text | 98981a96-41bf-5aeb-a49e-d25d846977f4 |  | textbox | Length (m)
checklist-sectioned |  |  | checklist | ITP - G1202B - Waikare Riverbend SH38 - Network Drainage | itp |  |  |  | Yes | ITP - G1202B - Waikare Riverbend SH38 - Network Drainage | 278c81bb-4d4f-4adb-b710-ac401c0efb8c
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 83c2b61b-686d-541e-a752-93d5dd1e620b |  | textbox | CPS Eng.
text | 7ffc959e-cc33-5539-aa45-55a0a462c9fb |  | textbox | Site Engineer
text | 98ece4f7-f3f5-547b-8410-80cd2bbc285c |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Locate existing services by hand digging/hydro excavation
label | e0bb53ac-6a34-56ec-99ed-7399258a248a |  | note | ACTION (Hold, Monitor, Witness) - W
label | dd593447-0195-5452-a2ec-264b31a5e049 |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging/ hydro excavation
label | dbc5a343-ec37-5256-908a-be4f9be831b7 |  | note | Frequency - Prior to commencement
label | ace2912c-3aaa-518a-bb61-3cb36b6ce7e9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | f5e7c0b0-d176-519b-b422-cbddb4cffeff |  | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As-built all services
label | 63dbcabe-26dc-5d39-8533-ec97087a30fb |  | note | Records - As-built Drawings Doc. Review
checkpoint-status |  |  | checkpoint | 2 - Trenching and Excavation
label | bd2ea02d-b559-54fa-8295-d9334b6e459b |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1c032eeb-2753-5c27-a192-731761584cd8 |  | note | Detail - Inspect trench profile and ensure it is correct to minimum drainage standards
label | a4ef3a7d-177e-5538-9bee-8fab350513fb |  | note | Frequency - Daily
label | ab07cf42-9530-5bda-a983-7608ca30700a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | f60406fa-744e-5c6b-80e0-c01c6ca415b8 |  | note | Conformance Criteria - Line and level is correct
label | 4ba7939d-e82f-52b0-a6f4-e08d3e7bc51b |  | note | Records - CS-4025 Drainage Line Record Check Sheet
checkpoint-status |  |  | checkpoint | 3 - Trenching and Excavation
label | 2e0e08e3-7139-5b14-b539-38dd38a702d0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3d130484-cc91-5bd0-832b-e745a0081ef2 |  | note | Detail - Ensure trench width is sufficient to provide enough space on either side of the pipe
label | 46aee52e-cb5c-593a-97ad-ac45dce59c16 |  | note | Frequency - Daily
label | d89ff2a8-5a24-5d48-b26a-02085f166d63 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | 29ef5f9b-d714-58c3-90c2-6745c53150e1 |  | note | Conformance Criteria - D/6 or 150mm whichever is greater on either side of the pipe
label | 5454c43c-d6b7-5b30-a1b1-f3e2bf763fa0 |  | note | Records - CS-4025 Drainage Line Record Check Sheet
checkpoint-status |  |  | checkpoint | 4 - Foundation Compliance
label | 9b0d3f93-9a98-57eb-8ebc-7179b81600eb |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8aa101af-1bdf-5b27-873b-18b97e305864 |  | note | Detail - Test formation level on completion of excavation to check if undercut required
label | 03c373d3-833c-5afd-adb5-0b80f7c80039 |  | note | Frequency - One test per 20 linear metres
label | 55568fca-c706-5a09-a1be-92f3ae57b1f3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
label | f0093bf0-338f-58d2-9c1b-750765d2d192 |  | note | Conformance Criteria - If CBR is less than 50kPa , advise Engineer
label | 85641b5d-43ca-5e16-a472-1c4358060127 |  | note | Records - Scala Record
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Pipe Bedding Material Compliance
label | b5c9cbb1-b412-5c5b-8dd7-f126db27c542 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d406634b-a818-5440-8b44-038cbc001bbc |  | note | Detail - Material to meet specifications dependant on material type selected
label | 3b17e624-c25d-577f-a29b-65859a5f75af |  | note | Frequency - Each material used
label | 74b89660-7344-522e-9bd2-08229a6f6ae0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 42000391-6509-52f6-bedb-5758ee09c215 |  | note | Conformance Criteria - Bedding material
label | 78c0d71e-a951-5119-8417-0e1be5daee5b |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Bedding
label | fb0f3ec3-64f5-5f65-8cf2-f8dcdd4312dd |  | note | ACTION (Hold, Monitor, Witness) - W
label | 362f5dcc-096f-578c-ba1c-1b6960d7c09b |  | note | Detail - Bedding - Ensure correct thickness of bedding is placed and compacted
label | e253a934-ead3-5b45-966a-b98bf10f9ef7 |  | note | Frequency - Daily
label | fd06c4aa-57c0-5874-a73d-15617dc7bf06 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | 18cccd35-4a64-5085-b088-a8f166ee0474 |  | note | Conformance Criteria - 150 mm thick bedding for all mm dia pipe
label | f8998b60-ee9b-5a5c-9874-3b5c6c0c6038 |  | note | Records - CS-4025 Drainage Line Record Check Sheet
checkpoint-status |  |  | checkpoint | 8 - Pipes and Precast Units
label | 6d1069f1-641a-595b-8588-84691e1fc735 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f8f6eab2-c956-54de-b76f-3bf6ecc4aba4 |  | note | Detail - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | e290701c-91ea-5711-9062-240851a9cfcf |  | note | Frequency - Per pipe
label | 61b39941-9cd6-5b97-a155-77a277067949 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | 857d40cd-1b19-57a6-bea1-a547211a0755 |  | note | Conformance Criteria - Pipe - Diameter & Class, Wingwalls, Manholes, Cesspits etc.
label | c3b5e74d-24e5-5cf6-ba74-bd069998387e |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 9 - Pipe Laying
label | 7428c96a-bbfb-59d4-87a1-634d6a4748b7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 73eb6ab4-5fcb-5f45-820f-4167d478cfbe |  | note | Detail - Pipe Laying - as only replacing section on outlet of existing pipe, grade is to follow existing levels
label | 4d3e8a39-a125-5e63-aaf7-ec86d018d64b |  | note | Frequency - Prior to backfilling
label | 4a182d4a-00ba-5019-baca-e48f7fbcefa4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | eafd7411-3fe9-5d41-b44f-f9bc248fe434 |  | note | Conformance Criteria - Invert level following pre-existing grade
label | ff4c4e26-6b29-5cf6-a080-42f73844e3a8 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 10 - Pipe Laying
label | eaa43e51-b6e5-5125-a7b0-7e8fd01beedf |  | note | ACTION (Hold, Monitor, Witness) - H
label | e608d849-5817-5fe1-9431-191dfb10e55e |  | note | Detail - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | db9736d6-bb83-5bf2-b6ad-47627472d83a |  | note | Frequency - Prior to backfilling
label | 6e663473-c7ee-5e8f-8a4a-fb0bf9fac07e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | 38fa2111-6242-56b1-bb01-d05f4620049c |  | note | Conformance Criteria - No defects/ gaps / pipes are aligned correctly
label | 85d586f6-78de-5fa5-9427-27583499fd3f |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Pipe Backfill Compliance
label | d5d584bb-4f73-57bd-b0e6-af47d9788885 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 913a7156-9e27-56c5-9df3-0eb67d2c6fee |  | note | Detail - Material to meet specifications dependant on material type selected
label | 9da8a5e2-7ebf-59e8-bbd0-6ed85fcadb5d |  | note | Frequency - Each material used
label | dddf959a-0afd-5494-83b6-90f13f129e19 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 64e60532-d655-53ba-ba07-8f1f5c31b363 |  | note | Conformance Criteria - Compliance with requirements from Specifications
label | 218eb4f3-6771-5626-9bb1-3656edb0a244 |  | note | Records - CS-4025 Drainage Line Record Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Pipe Backfill Compliance
label | 99e00f60-91e0-53eb-b593-e4eb082cb77b |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8923c915-cdd8-580e-a467-52496ce4502d |  | note | Detail - Backfill Construction Material
label | c8d4c0da-24a8-52b7-b1c9-e76334edcd51 |  | note | Frequency - 1 test per 50m
label | 072c4a07-48cb-5045-a513-a7033583977b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | db607949-0da1-5694-ad01-895b6a72a036 |  | note | Conformance Criteria - CLEAN GRADED GRANULAR AGGREGATE AND HAVE BROKEN FACES AP65
label | d0db4f11-d1bd-53be-9755-aaf742fc24ff |  | note | Records - Lab Test Report
checkpoint-status |  |  | checkpoint | 13 - Backfilling
label | 211f895f-b24b-5c38-aea9-ca4cdf742d26 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 61e19ca4-1f71-5a09-9e2f-85a6632411a7 |  | note | Detail - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms. Remainder of backfill to be done with excavated material.
label | 67525203-5067-5956-a8ba-b9885809c1ed |  | note | Frequency - 1 test per 20 m length of trench per 300mm lift
label | 4ea1ee7b-832b-5821-ba96-27ac6e2aaa59 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 6c1eb88a-2aac-5002-bef3-6a9e51ae2af2 |  | note | Conformance Criteria - 97% (under carriageway) or 95% (under berm) of MDD or Clegg equivalent
label | b44d0670-426c-590b-b52e-66b6deecd613 |  | note | Records - Clegg or NDM Test Results
checkpoint-status |  |  | checkpoint | 14 - Quality Assurance deliverables
label | ff2cdf8e-86f2-52d2-a652-fa105709e91d |  | note | ACTION (Hold, Monitor, Witness) - W
label | a7011c74-7f91-50a4-b65d-1a32839fab8f |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 3c50f37c-7597-5cd2-a1f9-cfcafce1e8fc |  | note | Frequency - At completion of Lot
label | b096f740-1bc0-5af6-b206-679b095181a7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | d641badf-38d8-52b7-a634-4014de9bf5a3 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 845ac51f-3d03-5559-8985-c378d52058b1 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 15 - Completion Sign Off From Fields Below
label | bbb86b69-867e-5408-89a1-54027189c114 |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | ITP - H1501A - Tupiko Stream Bridge - Reinforced Slope (Rock Bolts, Soil Nails) | itp |  |  |  | Yes | ITP - H1501A - Tupiko Stream Bridge - Reinforced Slope (Rock Bolts, Soil Nails) | 2973051b-ac2f-47a6-b7ed-f70f24c0cc9f
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 61b6dafa-db5c-5c0a-8ea7-d3b4295dc8f4 |  | textbox | CPS Eng.
text | b72b271c-7529-531e-a0d3-0800fb14a89d |  | textbox | Site Engineer
text | 0f5c32b8-effb-52ee-bff0-f84024d16ef8 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Dimensions and Set-out
label | a64dbdcf-6680-5a09-a682-ad9827df9c80 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 24397a8f-573b-57a4-ab34-2d63a3c6794f |  | note | Detail - Once on site the Contractor shall confirm the condition and dimensions of the structure.
label | b6db4162-af0b-58e3-bf05-fc7705857383 |  | note | Frequency - Prior to commencement
label | 252c203c-f3e9-53eb-a7b9-3fcc41e8379e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 4c4542d8-2ec0-55e3-959e-5c251291ddb1 |  | note | Conformance Criteria - The CPS Engineer shall be informed immediately if any conflicts in dimensions are encountered.
label | 1df77485-8393-5487-952f-7c5fbb7be8e2 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Erosion and Sediment Control
label | b80758fe-6da6-558e-8bba-650cc8b60800 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3afd3f18-4941-5d72-8ee6-8216a9c1a472 |  | note | Detail - ESC measures shall be designed and maintained by the contractor during the period of the works
label | 9f52852b-a7d2-562b-991e-e64fee30ae73 |  | note | Frequency - Prior to commencement
label | adfd8738-3cd7-5509-ba22-18e36c3e506c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 73c7d4bb-25d5-542b-a918-761cc249fb46 |  | note | Conformance Criteria - Ensure no surface runoff flows over temporary excavations
label | 5f7b9486-3f63-53d4-a1b1-a7531041c35f |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 3 - Clearing & Earthworks
label | 781513fb-81af-5f38-a451-f291795ccfcf |  | note | ACTION (Hold, Monitor, Witness) - W
label | 93397ef7-f133-5acc-a7c7-36dabb31d356 |  | note | Detail - Before setout of the reinforced slope method the bank along the full length of the abutment shall be trimmed/excavated to remove all loose material.
label | 03c43d5d-7dc8-5412-9188-592d1d9af36e |  | note | Frequency - Prior to commencement
label | c156eb21-74eb-5f77-81ea-44a0c6e47afd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b7ed888a-b0a7-588a-ad81-856e77571f28 |  | note | Conformance Criteria - Keep excavation to a minimum
label | b4fcda9f-7b71-5b3b-b7dd-8a64efbf3fae |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 4 - Clearing & Earthworks
label | 60086fd0-f7cc-52e1-8a04-1b449c84bcda |  | note | ACTION (Hold, Monitor, Witness) - H
label | 20261151-393d-54f6-8f27-4c44037841ae |  | note | Detail - Founding materials shall be inspected and verified by a geotechnical Engineer on site
label | 444c8c31-8068-57ed-a592-5a4b912a75ea |  | note | Frequency - Prior to commencement
label | c3ae8484-911b-5311-a047-1c6dd9bcc39e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 89b1dbff-9407-5f56-b146-83264ec1d8ca |  | note | Conformance Criteria - Any soft or unsuitable soil shall be excavated and replaced with lean concrete (minimum compression strength of 10MPa at 28 days)
label | 59353310-c245-5436-9f0b-3c7627bdfbae |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Clearing & Earthworks
label | 66336d1d-7309-5c0b-8625-232dfdd42436 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8ddc0d9d-4c8c-540c-a5a2-eafb23a61977 |  | note | Detail - Contractor shall submit their construction methodology for the trial anchors to the CPS Engineer at least 3 days prior to anchor installation.
label | 7db13927-56e3-5e02-bb92-40c43e3dd425 |  | note | Frequency - Prior to commencement
label | 073d7f92-6238-5e53-b752-b6ec24ea841d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 026e6bcc-ffc2-5b72-a895-e1ecf52e517c |  | note | Records - Methodology
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Reinforcement Compliance
label | def812c9-2f61-56f6-8de6-1f0a06def7ce |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8e01e86f-5592-54a6-9892-89a57c92f15a |  | note | Detail - All reinforcement shall meet design specifications
label | c7ae2ed0-3ee4-5afe-8377-5733a4032111 |  | note | Frequency - Prior to commencement
label | 6c96fb6b-095a-5e6b-a573-a9e06dfa7fc3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | bdb0cc7a-d610-5ba7-a200-4a48782b1181 |  | note | Conformance Criteria - Grade 500E and shall comply with AS/NZS 4671
label | 477cca65-1307-50ab-84cd-3729fb625c02 |  | note | Records - Delivery Docket
checkpoint-status |  |  | checkpoint | 7 - Anchor Ties Compliance
label | 21723f27-2463-53b0-9146-81fbaa605c20 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 10b52d56-9b24-5f1b-bc58-772a890c5c4a |  | note | Detail - All steel solid bar anchor ties are to meet design specifications. Alternative anchor systems will be considered provided they achieve the intent of these works
label | 24f62f80-bfd2-530b-9180-e826abd4ca77 |  | note | Frequency - Prior to commencement
label | 9835f9ef-97c6-55cb-9655-bfb0b3100149 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 3f7efbc9-8d0c-5614-a693-88e8673903cd |  | note | Conformance Criteria - 20mm diameter grade 500E Reidbar or similar approved, and hot dip galvanised in accordance with AS/NZS 4680:2006. Damaged bars are to be rejected.
label | 76fda56b-0cbc-5a4f-a37b-d6b055efe231 |  | note | Records - Delivery Docket
checkpoint-status |  |  | checkpoint | 8 - Bearing Plate Compliance
label | e57edbda-f8da-549c-adb8-380dc28313f6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e566b97a-ff8d-5d67-87eb-68e889d0c7a4 |  | note | Detail - Bearing plate steel, coupling hex nuts and other accessories must meet design specifications.
label | 8350c2ec-c629-58ce-b5ca-077fb5543104 |  | note | Frequency - Prior to commencement
label | 7f23538f-b2e7-53c4-8ee2-b427c59ea823 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | c018fe2d-650a-586a-83bd-a12fb18ecebe |  | note | Conformance Criteria - Bearing plate steel: Minimum yield strength of 250MPa, min 200x200x12mm. All galvanised to HDG600
label | 85830fd5-8832-53c0-a7a6-b7aaec418531 |  | note | Records - Delivery Docket
checkpoint-status |  |  | checkpoint | 9 - Concrete Compliance
label | 2d254a89-8a37-5b44-bb8a-f56cd6359bb1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d16d4bad-ec40-51b4-8a2a-d09b520c55f7 |  | note | Detail - All concrete to meet design specifications
label | 22f46fbb-9eb3-535b-b489-65e110bec52e |  | note | Frequency - Prior to commencement
label | 65d6fe1c-54fc-5423-bd50-7d29a84dced7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 6bbb2e11-35bc-5459-b71a-8136f2ad7c78 |  | note | Conformance Criteria - Workmanship in accordance with NZS 3109 and meets minimum 28-day compressive strength of 30 Mpa
label | f9efd58c-6d6a-5b08-948b-dc87536cb37e |  | note | Records - Delivery Docket
checkpoint-status |  |  | checkpoint | 10 - Grout Testing
label | aad260fd-5347-5664-8930-d5061c558508 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1092d73e-839b-53bf-8548-3d6bd6dedeea |  | note | Detail - Contractor should employ an IANZ accredited laboratory to perform one compressive strength test for every anchor at 1,7, and 28 days in accordance with NZS 3112.4. Test results shall be supplied to the CPS Engineer within 24 hours of testing.
label | 3d83061d-dcd6-5eea-9293-8297791ac0a6 |  | note | Frequency - Prior to commencement
label | 36fcd6a1-35c9-5a3e-b777-30bd62917222 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 84fc82e0-fa32-5093-971d-b56ed7ab2841 |  | note | Conformance Criteria - Anchor grout shall be Sika grout 212 or similar as approved by the Engineer and is required to achieve minimum characteristic strength of 20MPa at 7 days and 30MPa at 28 days.
label | d46e8de0-f026-5200-b7a1-5e30d2cdcaf5 |  | note | Records - Lab test results to CONQA Procore
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Anchor testing
label | d9764a9c-c914-5265-909b-c9535d8648f9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5445173b-0ba5-5f8c-b2b5-250b0364b747 |  | note | Detail - Three sacrificial soil nail tests are required by the Engineer. Location will be agreed on site with CPS Engineer. Testing may only commence once the grout has reached 30MPa as confirmed by grout cylinder testing.
label | 982055cc-744d-5a92-9a70-aadfbac59060 |  | note | Frequency - Prior to commencement
label | b699b075-0102-5ab6-bba6-fbb9de4da660 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 0e4e0231-c80b-583a-b44f-3b8e63fb1a80 |  | note | Conformance Criteria - Grout test results to be provided to the CPS Engineer prior to nail testing.
label | df63da1c-000f-59e6-a077-b8b65b9a33a4 |  | note | ○ Test equipment certificates and calibration certificates submitted to CPS Engineer prior to testing.
label | 61feef2d-7986-55ef-8160-ef25a4e28c41 |  | note | ○ Sacrificial test anchors and production anchors shall comply with Section 3.4 Table 1.
label | ba358700-35fb-500e-903f-ebe1e465c1c4 |  | note | ○ Test results shall be provided to the CPS Engineer for approval within 24 hours of testing
label | e9d7c9fe-b882-504d-a552-131a3226cf68 |  | note | Records - Lab test results to CONQA Procore
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Anchor testing
label | d17221e0-7832-5af5-8670-5fa237035f06 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 08db4a33-1dbf-5bcf-8607-cd0bb41d1520 |  | note | Detail - Three production anchors shall be proof tested in a location agreed with the CPS Engineer. All remaining production anchors shall be acceptance tested.
label | d71e2fc7-2fe0-5731-888c-0b3ba7a3d928 |  | note | Frequency - Prior to commencement
label | abb72d86-fe12-5aab-b18a-95b566a3df01 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 8dbb96ea-7fc3-5844-a50a-b11a0b215ae5 |  | note | Conformance Criteria - Testing done in accordance with Section 3.5, test results provided to the CPS Engineer for approval within 24 hours of testing. Rejection of anchors in accordance with Section 3.6
label | 43c7fa96-2d07-5106-8cf6-e74b77aef884 |  | note | Records - Test results to CONQA Procore
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 - Anchor Installation
label | f3e0b869-00ea-5d24-a4ce-ac66282555c1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 765c15f8-1299-5ad0-a2b0-0391269069f3 |  | note | Detail - Anchors shall be installed in accordance with the lines, lengths and levels shown in drawings.
label | 05d819fa-d9b7-51ce-99aa-0a9d8cb522ec |  | note | Frequency - During Construction
label | 322a9ce4-7939-5f8d-ab89-5f2af1a5072a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 011c112d-cc8b-5b65-bf68-f7c59dbf486e |  | note | Conformance Criteria - Bonded length of anchors is minimum 4m. Upper row installed at 10 degrees downward from horizontal. Lower row installed at 35 degrees downward from horizontal.
label | 54c2ca9a-9285-5601-9d5a-2fde766915e7 |  | note | ○ Anchor drilling, hole cleaning, anchor installation and grouting shall be completed within 24 hours of commencement. No holes are to be left open overnight.
label | 7e7e2c5e-13d7-5382-a070-b22cb51b01d8 |  | note | Records - Photos identifying anchors and installed locations
checkpoint-status |  |  | checkpoint | 14 - Anchor Installation
label | d5a21151-eaef-5a89-9e96-c0f91c30e1c8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9e77940a-66b8-5480-be58-78f1f7939801 |  | note | Detail - The contractor shall keep a record for each individual ground anchor and submit these to the CPS Engineer
label | 1748fd55-1f84-530a-8552-a1edbd9ec9bf |  | note | Frequency - During Construction
label | 2eef8604-4446-5c05-8edf-be3cfac5fea8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 9437a323-8cc9-52d1-b0a6-3386ceadf677 |  | note | Conformance Criteria - Record must include:
label | cbce56a1-c8f4-5e42-ab58-60573b0c0943 |  | note | – Type of drill bit
label | 0a8f3082-debe-5e2c-a97a-8a191582ebfc |  | note | – Drilling rate
label | f22a5e78-5468-527d-9901-113951aacd0f |  | note | – Grout pressure
label | ec21193f-b3e3-59ac-ac18-6b6a96a4866d |  | note | – Grout volumes
label | 3216220f-b3a1-5666-8b98-5cb9e72ff2cd |  | note | – Ground conditions encountered
label | d9bcc73c-b231-5672-b112-289bbf21e43e |  | note | – Unforeseen conditions
label | c32394fa-edb7-5dc2-bdb3-d4d11ac34908 |  | note | – Prestressing steel manufacturer's mill test reports for the solid bars incorporated in the installation
label | 7af8ade8-4b73-588f-b6a9-f2021e154caa |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 15 - Anchor Installation
label | 8e66edce-b332-586b-ae0e-c0088810b9e3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 69025681-99c7-511d-a422-5fa9fb97529d |  | note | Detail - Install grout
label | ef4b95d6-86a9-567e-ae8a-641124987cbb |  | note | Frequency - During Construction
label | 4604783e-c81c-58f6-ae35-24b6655557e1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 26307d67-8eef-5327-ad5d-63fb809c95e2 |  | note | Conformance Criteria - The entire length of the nail should be grouted without voids, intrusion of soil, or gaps in the grouted column. Grouted columns are not to be leaded for at least 72 hours after grouting.
label | c8ed386a-b270-5371-9069-7503ea26aeb2 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 16 - Anchor Installation
label | 76535ba0-9a2d-5a7b-b684-7eb0aad001f5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c38e9ba5-3ba2-55da-95c2-d6466bf81405 |  | note | Detail - Install bearing plates and washers/nuts
label | 51af8499-08c8-561b-8c98-c870d8f110fd |  | note | Frequency - During Construction
label | 33d4d4aa-4b82-5539-ac22-a84824418647 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | d4b78b7e-0ce4-5562-9334-a4bb7b0238a1 |  | note | Conformance Criteria - Bearing plates (anchor heads) are required to be buried within the mass of the skirt concrete block.
label | d6fc4907-3444-5530-8407-c866b551b8af |  | note | ○ Tie rod nuts are to be snug tightened only to remove any slack.
label | e771364b-0420-54ee-aaad-09561866b6cd |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 17 - Reinforced Steel
label | 8029afe6-7bb5-5379-b37e-b1f21690032c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2d353360-460b-51bc-931e-e1001c366c50 |  | note | Detail - Reinforcement shall be installed in accordance with Section 3.8.
label | fc04ed8d-b1a7-5592-8d70-22fb83fb6d2b |  | note | Frequency - During Construction
label | 53142556-6ee7-589d-b7fa-4b114c8fdbad |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 0dfa4a6d-f87c-5959-90c6-c33576acbea8 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 18 - Drainage Installation
label | 969ee0b6-8f95-5196-b798-8d3d07630e4f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 031f7c03-f1dc-5347-8ca5-d98698128237 |  | note | Detail - Sub horizontal filter wrapped slotted pipes to be installed as shown on design plan. Outlet pipes shall be installed along the front face of the concrete block to form weepholes as per construction drawings.
label | 33802c43-ab8b-512e-b32b-4cbc31fa7975 |  | note | Frequency - During Construction
label | 19e36804-cabe-5fa5-a5ee-57275f3626b9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 988c57d2-de53-5aee-8e42-10808c8b9b12 |  | note | Conformance Criteria - Drains shall be installed in 65mm diameter drilled holes at 10 degrees upward from horizontal.
label | 38d276c0-6984-547c-b1dc-b5418df348b8 |  | note | Records - Photos, Subcontractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 19 - Drainage Installation
label | 12b73158-5559-5296-af2b-bcb75e44e9b5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5c8b86a0-c635-545e-84fd-2e3648d5e22a |  | note | Detail - When completed the subdrains shall be inspected by a geotechnical Engineer on site
label | c83d2ad0-2637-51c6-8820-c04d1c9d14e6 |  | note | Frequency - During Construction
label | fa0bfac0-5a4b-5608-b61e-62d9a29cae10 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3c298e1f-3d87-561d-a3cc-dc574fe04e42 |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 20 - Concrete
label | 91093201-4725-525e-89da-638586f6ac32 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e2b2bd76-d773-5322-b09c-bc8985c612d0 |  | note | Detail - Ensure any cavities and surface is clean prior to application of concrete
label | ac34b36f-3831-5e4a-b245-d68544b62182 |  | note | Frequency - During Construction
label | 475411af-e3c9-5e7f-a783-001274123c46 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 1b1f12bc-3024-5ab9-8847-6e9688b91e9e |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 21 - Concrete
label | e395dad1-9179-5a1b-8a5e-6a1c260df19e |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7abf1e6e-8557-5d16-a72c-ed62fd802f3a |  | note | Detail - Apply concrete in specified locations
label | 16c9234e-bd1e-5eb9-b2e1-54195c585d41 |  | note | Frequency - During Construction
label | 9681c65e-9693-5d11-84bb-4950d5c363b4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 9935e282-1e28-5609-b30a-01eb037e44ae |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 22 - Concrete
label | 117f151e-ce76-558c-80af-957cfc6e7036 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d22bac8c-7ab4-5844-aeaf-1f227f26f79b |  | note | Detail - All concrete shall be properly cured for a period of seven days or until specified strength is obtained.
label | bcd20ef1-2aad-5eab-8287-fd584da7af86 |  | note | Frequency - After Construction
label | 7bc62d26-8340-5790-a13d-2d6bb5853283 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 72227e85-5b5b-5aa8-9cfb-94b5179bc9c6 |  | note | Records -
checkpoint-status |  |  | checkpoint | 23 - Concrete
label | 30aea42c-e6cf-5cd1-ae75-b686f2e96317 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b8222e74-ce8f-5727-9b28-fbaaf69104e9 |  | note | Detail - Once the concrete block has been completed, the CPS Engineer must be offered the opportunity to inspect the completed works.
label | e0bd43b8-cf7d-57ba-81aa-f9f16a7c4048 |  | note | Frequency - After Construction
label | ef18d935-25f4-50d8-97a9-c0dca9fa076c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b715c0a0-889e-595e-9888-4a3bd314c092 |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 24 - Bank Reshaping
label | d6d8fc20-083c-57b7-b7a2-ad89493b7223 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 02c9bf96-36ba-5e90-8980-13ed9f4fd695 |  | note | Detail - After completion of the works, the existing banks shall be shaped to match with the new bank.
label | 21cc8ba6-92c3-50ed-b450-b161fb5ea979 |  | note | Frequency - After Construction
label | 8221f9c3-6d17-51ac-a0a9-51a3b235c094 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c35b7438-0803-593f-a029-d5dddbcc1924 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 25 - Topsoiling and Grassing
label | 845b5b09-bab6-5bf3-8e4b-4ee2e76aa4e1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b918ec27-386f-535b-8b8c-a5b6d4c6905e |  | note | Detail - All areas disturbed by the works shall be topsoiled and grassed except as noted.
label | 1217ea96-e75b-5cdc-9153-844c6e28aee8 |  | note | Frequency - After Construction
label | 28718e2c-42a5-5a0c-b086-20912c2a3efc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 2fbcc6ae-21cf-59d0-bb98-67a6ad4c7de7 |  | note | Conformance Criteria - Topsoil shall be spread at a nominal thickness of 100mm, but no less than 50mm and no more than 120mm. Batters steeper than 2:1 are not to be topsoiled. Topsoil is to be tamped down to a firm state (minor indentation when stepped on).
label | 5ffa5832-f1f2-5c7f-8ebc-18a0b4a5e371 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 26 - Topsoiling and Grassing
label | 643ae454-de7e-5b7d-b5b1-097774fb299d |  | note | ACTION (Hold, Monitor, Witness) - W
label | da758f87-28ac-5ae2-b497-f9eb95c4be83 |  | note | Detail - Grassing of topsoiled areas shall be a to a mix agreed with the CPS Engineer on site.
label | 9b69f6a0-a894-5f0d-9b16-7786a891111c |  | note | Frequency - After Construction
label | 5aa98177-acfa-5130-984c-973671d669d3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 8cf03860-2b53-5a78-bc4f-ba49f3b7b583 |  | note | Conformance Criteria - Contractor shall apply 50 grams per square metre of superphosphate.
label | d8f19c5d-a34b-5e96-b162-252e447ed555 |  | note | ○ No seed is to be sown until preparation work has been approved by the Engineer.
label | 23e0cb66-5b13-5637-8f67-9dfb369ecf59 |  | note | ○ The grass seed mixture shall be sown at a rate of 25 grams per square metre bare seed weight.
label | 5c3808ba-1b19-5011-8926-e8eae3260394 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 27 - Lot Number QA File
label | 3dbd762e-5c0f-59e7-bd56-dbc7d6667f47 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c617aeff-6251-55d3-a359-05af650558ea |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 98b71dd0-2224-5f5c-84b1-125e46b9532a |  | note | Frequency - At completion of Lot
label | 0ed8cf18-4273-5772-b24c-26af964c68ee |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 66622252-00de-5792-ba1f-f06202c90919 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | ddc770b3-acb3-5bcc-9797-889194bb1289 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register, Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 28 - As-built
label | 54150ace-afc5-55cd-8b64-c138a33c86a8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 73abac7b-9573-57a7-ba23-1c3098f0d81a |  | note | Detail - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red line mark up drawings to be included in QA file
label | 4dfa45a8-9d5a-51ea-ac08-be0e790ec028 |  | note | Frequency - During and at completion of work.
label | e244ef21-8883-5d56-932e-7e610e554080 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | da39950c-a64f-5769-9fcf-0531968f5649 |  | note | Records - Survey receipts, As-built plans
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 29 - Completion Sign Off From Fields Below
label | aa5a6249-48bb-51bb-b813-600710e36c97 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 41c7b7b1-dca7-5357-90db-fae6897481b9 |  | note | Detail - Below sign-offs to be Captured in CONQA / Procore
label | 6289426d-40cd-5c81-8565-e3963b0da183 |  | note | Records - Signatures
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | CS-4010 - Services Relocation Checklist |  |  |  |  | Yes | CS-4010 - Services Relocation Checklist | 2c2e451a-0a87-4e56-9ba5-3a6217f9d91b
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | 5761a12c-45fa-54cb-8212-cbf977526d82 |  | textbox | Drawing No:
text | 296ae92e-7954-534b-9db5-671078a154de |  | textbox | Rev No:
text | 92c412fa-af3f-575d-97bb-c338ec09daee |  | textbox | Chainage:
checkpoint-group |  |  | section | Inspection Stage
checkpoint-status |  |  | checkpoint | 1 - Set out by surveyor & handover to Site Engineer completed
text | 20a55293-cb3c-5778-a8e4-f2cb9f35cea8 |  | textbox | Initials:
date | 4305bc84-4987-53b3-a393-e7f55d3ed4ee |  | date | Date:
checkpoint-status |  |  | checkpoint | 2 - All existing services exposed and identified before trenching
text | 3385db79-9c0a-5b4a-aa4e-6ca01befba93 |  | textbox | Initials:
date | 642a5bbb-558c-59e4-be3e-7f2ebfdde245 |  | date | Date:
checkpoint-status |  |  | checkpoint | 3 - Trench line and profile as per IFC drawings and as set out by surveyors
text | 08842556-f8e9-50ac-ac44-ba5c66618b21 |  | textbox | Initials:
date | a90d81c4-da36-5f5b-8a10-76d912b52e01 |  | date | Date:
checkpoint-status |  |  | checkpoint | 4 - Trench must be made safe before any person may enter the trench
text | 099c1d5e-4269-5b86-9ad6-3bc11eaada6e |  | textbox | Initials:
date | f02d016b-5778-5128-9ed8-086155a58394 |  | date | Date:
label | c1b7b889-b3c0-5434-aeb0-cb9e97bc111f |  | note | Comments: Trench depth > 1.5m must be shored or battered.
checkpoint-status |  |  | checkpoint | 5 - Base of trench inspected and tested if required.
text | 09f8e2e2-b883-5c4b-ab72-53b6f17d9331 |  | textbox | Initials:
date | 23094f99-9c2d-50cd-9dc1-a3112695de4a |  | date | Date:
radio | a577650a-8b7e-57b6-a5cf-80f2d8624464 |  | radio | Under cut required | Yes,No
checkpoint-status |  |  | checkpoint | 6 - Ensure sufficient protection layer is placed around the new services cable
text | d4ee6671-77cb-59d7-99a9-d97f3b7433fe |  | textbox | Initials:
date | dfce6a2b-db82-5f48-b31f-9495b371ac33 |  | date | Date:
text | 0aac06af-0118-51dd-9cec-40cf7b5801da |  | textbox | At least: |  |  | mm
checkpoint-status |  |  | checkpoint | 7 - Ensure warning tape and/or magslab is laid at the correct cover over the new services cable
text | 44ed1af4-e075-5fbd-9aec-8a4559fc86b6 |  | textbox | Initials:
date | e07b8c02-9dbe-5142-b594-2c67ddf37dbb |  | date | Date:
checkpoint-status |  |  | checkpoint | 8 - Ensure backfill material is suitable and un-contaminated
text | 1b135aad-2fcc-5d4f-8021-0b1045f6d1ed |  | textbox | Initials:
date | 5935b910-9df9-5c49-aa90-6f8e9c71cbea |  | date | Date:
checkpoint-status |  |  | checkpoint | 9 - Backfill compaction tested at every ____mm lift
text | f78090c0-761b-5c1b-a39a-4d35aa03669d |  | textbox | Initials:
date | 9bcdfe57-7de7-5cb0-9dc0-869df12860a4 |  | date | Date:
checkpoint-status |  |  | checkpoint | 10 - As-builts updated and surveyed when required
text | da05e4c8-51b8-54a7-9853-a915a6b13fb3 |  | textbox | Initials:
date | 80dc4140-06cb-5420-a795-aae9b23ea412 |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | b0b9f74b-13a6-540c-8696-122c27c72d81 |  | note | Position: Site Engineer
text | 1e7c620d-5f5a-5890-98e9-e85f0d128676 |  | textbox | Site Engineer - Name:
date | 1515e99e-62f9-5ce7-9b29-126755baa3ad |  | date | Site Engineer - Date:
label | 29a7f362-b3c4-53b3-9dc3-5f4672753d8e |  | note | Position: Design Engineer
text | c3949b2d-2658-5efb-a26c-6a85fdc2c6cb |  | textbox | Design Engineer - Name:
date | 11f34087-32d9-55fe-8b31-a2a3c259604b |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | Sign
checklist-flat |  |  | checklist | CS-4101 - Water Main Line Record |  |  |  |  | Yes | CS-4101 - Water Main Line Record | 36284c84-51a0-4b69-ac2b-b1b61614c55d
checkpoint-no-status |  |  | checkpoint | Details
text | 5372b781-6871-563c-9ed1-43aa2204392f |  | textbox | Drawing No:
text | 53509fb3-18b6-5e91-92f3-964ff3dc1671 |  | textbox | Rev No:
text | 49300774-af3f-5dd7-a488-23d1f62dbc22 |  | textbox | Chainage:
checkpoint-status |  |  | checkpoint | Set out by surveyor & handover to Site Engineer completed
text | ecea9723-e6a9-58e8-a172-36f0a967061f |  | textbox | Initials:
date | 5fcd1050-3468-5eb5-aeeb-3d2408849522 |  | date | Date:
checkpoint-status |  |  | checkpoint | All existing services exposed and identified before trenching
text | 417ed235-f894-5302-b55d-feb425edd24d |  | textbox | Initials:
date | a54c9618-e459-5b86-8ff5-4b3a094801f2 |  | date | Date:
checkpoint-status |  |  | checkpoint | Trench line and profile as per IFC drawings and as set out by surveyors
text | 0a135c0a-7592-57f6-b227-9a59946b470f |  | textbox | Initials:
date | d5f22d7a-71c4-56a8-a0b3-a978fd2c4c69 |  | date | Date:
checkpoint-status |  |  | checkpoint | Trench must be made safe before any person may enter the trench
text | ba33f621-a7f6-50e1-a5b7-383c3a32ecb1 |  | textbox | Initials:
date | ef734f43-49ee-5ed0-a1b1-e67db68583c7 |  | date | Date:
label | 5034dc60-d39c-572c-8c3f-11992b47959a |  | note | Comments: Trench depth > 1.5m must be shored or battered.
checkpoint-status |  |  | checkpoint | Base of trench inspected and tested if required.
text | 559a00f7-17c2-564f-b368-a21b1130cbd8 |  | textbox | Initials:
date | 14656864-7c9e-52ff-a1c1-74deb4b6598f |  | date | Date:
label | 96695184-17f3-5c9a-9e55-acb44a474b56 |  | note | Comments:
radio | 2ad4debb-a26b-5e57-a597-41516dc67841 |  | radio | Under cut required | Yes,No
checkpoint-status |  |  | checkpoint | Bedding is to be tested
text | eef9d435-9bdd-5947-8bf1-b345d51d87e4 |  | textbox | Initials:
date | 4a1d36d2-fd73-5718-af6f-124b188cfd16 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pipe is laid with appropriate clearance to other services
text | dab1a130-23df-56d9-89b4-857d18aa5d77 |  | textbox | Initials:
date | 6703dfe0-dbd2-5215-82a3-cb49c9d36622 |  | date | Date:
label | f8f95474-5922-5e8f-b18c-4fdde271931f |  | note | Comments: See “Table 5: Clearances from underground services”
checkpoint-status |  |  | checkpoint | Survey to asbuilt top of pipe before backfilling commences
text | ca2f715c-6e34-596a-912e-e9283c046b61 |  | textbox | Initials:
date | 0e37e489-8ce7-5209-a07f-7e2f6e62f62a |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure warning tape and/or magslab is laid at the correct cover over the new pipes
text | be6e2c0b-10d1-5996-8b73-9579cdb725f5 |  | textbox | Initials:
date | 9fe1c78b-22b2-501f-935d-31c9b7738a54 |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure backfill material is suitable and un-contaminated
text | 2af265fa-3338-5a57-8f61-3fc9f20c365e |  | textbox | Initials:
date | 0e6af950-d751-50f9-b414-b01da2ca2162 |  | date | Date:
checkpoint-status |  |  | checkpoint | Backfill compaction tested at every __mm lift
text | 712f7b76-ba9e-5a10-95ab-14df3bd4ecaa |  | textbox |  |  |  | mm
text | 862caf65-c86d-52c2-81fc-66d66f0a03d9 |  | textbox | Initials:
date | aeaa653c-3dd5-55f2-bb30-f60ab32ecd38 |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | 1d7fe412-4e7c-5969-82ae-8ffbb7c646a3 |  | note | Position: Site Engineer
text | 09b884eb-8573-5001-87f2-b690c4f1c5c7 |  | textbox | Site Engineer - Name:
date | af43b6ce-16e7-5bc1-a478-9be1a2cd179b |  | date | Site Engineer - Date:
label | 32dda21d-3b52-577d-99a6-0b52d5cc92e1 |  | note | Position: Design Engineer
text | fa5eacb2-7064-5711-a41c-bb0b624ffa9d |  | textbox | Design Engineer - Name:
date | 98d225ff-34ea-57ae-b72f-2cf54175aba2 |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | SIGN
checklist-sectioned |  |  | checklist | CS-4045 - Kerb Construction Record |  |  |  |  | Yes | CS-4045 - Kerb Construction Record | 39344d5d-e102-46ac-95c0-3011968e639a
checkpoint-group |  |  | section | Kerb Construction Record
checkpoint-no-status |  |  | checkpoint | Kerb Construction Record
text | 035bf10d-9636-50b1-b12d-56b6b5da817d |  | textbox | Description of Pour:
text | ab39e840-d74d-5156-b772-1450bba7eedf |  | textbox | Kerb Type & Dimensions:
text | 7f01f1ae-f5df-5117-9975-7404e27af200 |  | textbox | Weather conditions:
text | 2423da15-a769-57a2-857d-299d0abd8be7 |  | textbox | Concrete Qty:
text | 4a075089-54fc-5759-a23f-166e72ea968e |  | textbox | Concrete Grade: |  |  | MPa
text | ab91d7d1-312c-5034-9303-965a110dc222 |  | textbox | Dwg No/Rev:
checkpoint-group |  |  | section | Formwork Mould
checkpoint-status |  |  | checkpoint | Cleaned and oiled
checkpoint-status |  |  | checkpoint | Correct profile/dimensions for Kerb Type
checkpoint-group |  |  | section | Subgrade
checkpoint-status |  |  | checkpoint | Ensure subgrade construction is complete and suitable for kerb
checkpoint-status |  |  | checkpoint | Cesspit protection in place
checkpoint-group |  |  | section | Survey Set Out
checkpoint-status |  |  | checkpoint | Check survey set out
checkpoint-status |  |  | checkpoint | Check subcontractors string lines for machine
checkpoint-status |  |  | checkpoint | Vertical levels correct to design +/-5mm vertical tolerance
checkpoint-status |  |  | checkpoint | Horizontal alignment correct to design. +/-30mm profile tolerance but the width between parallel kerbs +/-20mm
checkpoint-status |  |  | checkpoint | Crossings / kerb transitions set out
checkpoint-status |  |  | checkpoint | Engineer to mark kerb types at crossings and kerb transitions
checkpoint-status |  |  | checkpoint | Ensure channels fall towards catchpit locations
checkpoint-group |  |  | section | Miscellaneous
checkpoint-status |  |  | checkpoint | Construction joint roughened & clean
checkpoint-status |  |  | checkpoint | Correct mix ordered
checkpoint-group |  |  | section | Pre-pour check – HOLD POINT
checkpoint-status |  |  | checkpoint | Site Engineer
text | a6f2c401-790d-5e1d-816d-2ab077fa60dc |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Design Engineer
text | d39aa5da-77ec-5fc2-ab1f-80d253514c2b |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-group |  |  | section | Concrete Checks
checkpoint-status |  |  | checkpoint | Correct mix delivered?
checkpoint-status |  |  | checkpoint | Correct slump (within tolerances)?
checkpoint-status |  |  | checkpoint | Concrete Supply Dockets collected?
checkpoint-status |  |  | checkpoint | Batching Plant Records received?
checkpoint-status |  |  | checkpoint | Kerb meters completed in m
text | 0c1f03b6-b580-567b-9be9-277a26fd53cc |  | textbox | Kerb meters: |  |  | m
checkpoint-group |  |  | section | During Concrete Pour Inspection
checkpoint-status |  |  | checkpoint | Ensure correct kerb type is being installed in the correct location(s)
checkpoint-status |  |  | checkpoint | Constantly check levels and line to ensure kerb is within design tolerances
checkpoint-status |  |  | checkpoint | Ensure protruded kerb has U4 finish
checkpoint-status |  |  | checkpoint | Ensure Expansion joints are installed
checkpoint-group |  |  | section | Concrete Infill Islands
checkpoint-status |  |  | checkpoint | Ensure F3 finish and the concrete level is no higher than the top of the kerb that forms the median/island
checkpoint-group |  |  | section | Tie ins to pre-cast elements
checkpoint-status |  |  | checkpoint | Aprons to be formed around pre-cast elements
checkpoint-group |  |  | section | Pour Time
checkpoint-no-status |  |  | checkpoint | Pour Time
text | 61602469-ad6c-5160-aa23-4ae4c08cc9ba |  | textbox | Pour Start Time:
text | 4fc780be-04a3-5f07-9c8d-840115651bc8 |  | textbox | Pour Complete Time:
text | 0fbb082c-d88e-59ff-8bfa-6cc710e4661d |  | textbox | Volume Placed:
checkpoint-group |  |  | section | Protection
checkpoint-status |  |  | checkpoint | Warning tape to be placed over kerb to prevent any damage
checkpoint-status |  |  | checkpoint | Backfilling to commence after 72 hours curing time
checkpoint-group |  |  | section | Post Concrete Inspection
checkpoint-status |  |  | checkpoint | Surface Finish and levels acceptable
checkpoint-status |  |  | checkpoint | Expansion joints satisfactorily completed
checkpoint-status |  |  | checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
checkpoint-status |  |  | checkpoint | Site Engineer
text | cdebd896-549a-5596-a6ee-a114836fafdc |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Design Engineer
text | 02766cb5-2a3c-513c-8077-e5c969856be1 |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Ensure surface varies no more than 5mm when checked with a 3m straight edge
checklist-sectioned |  |  | checklist | ITP - E3001 - SH05 SIP Generic - Pavement Construction | itp |  |  |  | Yes | Ω (Deprecated) ITP - E3001 - SH05 SIP Generic - Pavement Construction (old version) | 3a1d22fe-c551-4a3f-ae0f-be3fdd2243c4
checkpoint-group |  |  | section | 1. Setout & Saw Cutting
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 6ea2e9b0-3e99-515b-8af7-0ff1cc351d4d |  | textbox | CPS Eng.
text | a1ccf71d-377d-59ec-a75e-937d152a07fc |  | textbox | Site Engineer
text | 24b53b5e-8359-54ba-90f2-0bf1919c2e02 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Survey Setout
label | 0ee1be7d-466b-5bb0-bda2-fb13d54353a7 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 30a17514-b305-5d91-95b4-1c6d1d56b912 |  | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
label | 252d7dc2-2808-547a-84ab-e2a8fde743bd |  | note | Frequency - Prior to commencement
label | ca1c2cd4-99d7-5431-a2a4-bec2573cf7f1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 8e8dc048-fefc-5e77-a938-15b5f5fea317 |  | note | Conformance Criteria -
label | 72a7b585-b5ca-5d22-aa57-24497eee6a17 |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 1.2 - Saw cutting
label | 895c7822-c09b-5446-bf04-565f7b21b767 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 18983e90-1ada-5aa0-b14d-d3e6023a6578 |  | note | Detail - Proposed Sawcut line to be inspected by the engineer
label | 8e05daa0-c3c9-5855-a441-ededb80ba7ea |  | note | Frequency - During construction
label | c923999d-0696-5e2f-b60e-cdea5b012567 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 215687a8-f104-504d-84df-0947cfe76e7a |  | note | Conformance Criteria - Project Specification 6.6
label | 9d626d29-a8b2-5f2d-8174-015bf2fc6ed5 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2. Material Compliance
checkpoint-status |  |  | checkpoint | 2.1 - Sub Base Material Compliance
label | b6018eea-16a5-574e-8472-911419491cd2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 682ce5b7-8519-5217-a57d-aee6c4127020 |  | note | Detail - Aggregate material compliance for Sub Base stockpiles
label | 9b14de80-269d-5959-9d8c-2195501696d4 |  | note | Frequency - Prior to commencement
label | 1c688bb0-7482-59e9-8369-16d1f71cb5e2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 3dd00bb4-298f-5653-96ca-d468c67cadd3 |  | note | Conformance Criteria - Comply with TNZ M/3 Specification.
label | 93887794-75b2-58c6-bc4b-e3596c7d5ac8 |  | note | ○ NZTA B/2 Specification Lab test for MDD at OWC
label | 81b800f1-6a6c-5813-ba2e-4b8de6e9fd41 |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Base Course Material Compliance
label | b51447ed-eb37-51b4-a6af-2f8c5e8484dd |  | note | ACTION (Hold, Monitor, Witness) - H
label | 063e5cf1-bddb-583e-99f4-4b2617b4a1ee |  | note | Detail - Aggregate material compliance for Base Course stockpiles
label | 94526e72-d168-5bfb-ac84-77a4686b82b9 |  | note | Frequency - Prior to commencement
label | b36ecc74-8ff8-5f1c-91fc-e494307d2ad5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 2b71edbc-3376-55b3-9e5d-c2911961c706 |  | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
label | 0e9e8491-caf6-51e4-a636-af6f3e4d9bf6 |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Base Course Mat Sample Testing
label | 99f9ff7b-4ed2-553b-b6d2-fcd8ebc1537a |  | note | ACTION (Hold, Monitor, Witness) - H
label | ff0679ab-f699-54e1-8909-833171f8d034 |  | note | Detail - Mat sampling of Basecourse Material
label | 72b25cb6-8795-5ab8-9ed7-900f72514fc1 |  | note | Frequency - 1 mat sample for the job. Pavement CPS Engineer for further instruction
label | 7cde541c-7ea7-576f-808a-9d0f142c3668 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab testing
label | 6fd03ea9-009d-5679-847a-3fa7e4fdbd74 |  | note | Conformance Criteria - Grading to comply with specification
label | b6021767-392d-53aa-ad87-25ef4de60c2e |  | note | Records - Mat sample lab test result
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Chip Seal design
label | 6cb76005-ed6a-5b71-9b4e-a401467f532c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 18a64b26-47b9-5b09-831d-ab9204f52645 |  | note | Detail - Seal design to be reviewed prior to sealing.
label | 37eeb198-4f90-5ef3-b157-014f36c8bf17 |  | note | ○ Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer.
label | 78eaa47c-f9e0-58da-8115-9f85a223f672 |  | note | Frequency - Prior to Sealing
label | 96fcfd5e-5c5b-5d59-b37e-662741d7538a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | f7dafc8d-a89e-5413-b156-695121c19b3d |  | note | Conformance Criteria - The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995.
label | 51776416-837c-5e3c-92c0-81751a00c3f6 |  | note | Records - Emails/NTE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Sub Grade Construction
checkpoint-status |  |  | checkpoint | 3.1 - Sub Grade Strength
label | ae64bb17-e97d-5506-9b11-2f58eaee14a1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | cc7399ba-26fe-56b8-a4ef-994e4ca4abf6 |  | note | Detail - Determine Bearing strength of Sub Grade
label | a351a4a3-1fda-52b5-a489-f4a0fd20e655 |  | note | Frequency - After Dig out, every 5m
label | da115f0f-fa99-52b2-910c-408e78f5c754 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 7898c6e9-a567-5a75-baff-fba901c57fc5 |  | note | Conformance Criteria - Min. 2 blows /100mm
label | 68b7e438-a634-5b5c-abd6-638ded287e59 |  | note | ○ 2 blows = 4 CBR
label | 27a2b633-bcae-5404-bb27-86ff5c7600ce |  | note | Records - QA measurement Sheet, CS-4000 1m Scala
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Proof Roll of subgrade
label | b8946c21-8e0f-57ff-8b66-049307f9ef4f |  | note | ACTION (Hold, Monitor, Witness) - H
label | e5a44703-1ef6-5e00-bb0a-6ac84c81f4a4 |  | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
label | ca054a18-e63b-54ca-b637-4de0b2b8765c |  | note | Frequency - Prior to Sub Base Construction
label | ad86e5c6-fab0-59ab-a466-93da00a6aeac |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | d88e0662-448a-57b7-a3c3-d25958f5a551 |  | note | Conformance Criteria - Engineers Acceptance
label | d5783548-4fd3-5b62-9958-3ec294c8cd87 |  | note | Records - Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Sub Base Construction
checkpoint-status |  |  | checkpoint | 4.1 - Sub Base Aggregate Delivery Checks
label | 90a61496-bb5d-5408-8fff-882fc7731f67 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 02a946bb-66a3-546d-b95a-4746ffa5ce7e |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | d83812b1-5250-5635-b968-b73a5b22b190 |  | note | Frequency - During construction
label | 7aeb445e-3f00-5999-8968-399aec327010 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | 5e7eb728-afdb-539e-b59e-b76394498146 |  | note | Conformance Criteria - Comply with TNZ M/3 Specification.
label | 26ab1f2d-ffa7-5968-9b3c-a8a9c3995f83 |  | note | ○ NZTA B/2 Specification
label | 54836ac7-06f3-5157-9abb-3f7627977f71 |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 4.2 - Sub Base Material Contamination Checks
label | bb08d263-81f2-5548-9161-fa2e6c82e9ed |  | note | ACTION (Hold, Monitor, Witness) - M
label | fad86ded-c37e-5764-9c17-877f72d7c361 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | d9f8382a-af29-5f95-b49b-ed792fd77995 |  | note | Frequency - During construction
label | 165c3b73-5b09-5250-83c2-752bc08110e6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | f1652b3e-e7f0-5098-b957-98417ef27f82 |  | note | Conformance Criteria -
label | 50eec905-5274-50f9-8c16-6e1014ac2412 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 4.3 - Sub Base Trimmed Level Checks
label | 05a03da3-4468-50ea-9058-85092c9b892b |  | note | ACTION (Hold, Monitor, Witness) - M
label | 64acba90-39ec-5ec7-89c7-96cea54bf112 |  | note | Detail - Carry out a Level Check on the trimmed Sub base
label | 72aac000-e52a-5329-97e4-96f71d84bff7 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | 86f9dd8a-9f23-5cae-ad8d-70c5e22b7973 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 0725ca40-7792-52fc-af1b-c11a6e146afe |  | note | Conformance Criteria - TNZ B/2
label | fe9c2327-8ad1-5fc0-9ce1-fd447a3f8c3a |  | note | ○ Tolerance = -25mm/+5mm
label | 6914bc45-8ab6-5b59-b08e-861cf1540a89 |  | note | Records - QA measurement Sheet, CS-4100a Subbase Approval
checkpoint-status |  |  | checkpoint | 4.4 - Sub Base Compaction Lower
label | 9f376486-aacf-584d-a65b-025ee3d382a6 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6dbb00e2-e26f-5d32-9e48-8138b0855984 |  | note | Detail - Degree of Compaction.
label | e19580b3-71d5-5b1a-9640-ab3b0ee2864f |  | note | ○ The subbase shall be constructed in two layers.
label | 067055a3-8a5d-54bd-8d1b-daaf2c051bbd |  | note | ○ Lower subbase results must be approved before construction of upper layer.
label | 6cbc8cf1-67d0-5a57-93b9-0e85774b836c |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | b9911019-0976-5c3e-884c-7eb3bd659ae4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | dcd1e9cd-e4e4-5714-b7cc-68e879489eac |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | 910139be-b2b4-5b17-ac06-956749fe91dd |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Sub Base Compaction Upper
label | 698c8699-81a1-55f5-82d8-95567c907031 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 50a54336-831f-5867-9752-2faade92565c |  | note | Detail - Degree of Compaction.
label | 0eee789c-4be8-55e6-8b06-537c1367a6f5 |  | note | ○ The subbase shall be constructed in two layers.
label | a27921f1-caeb-563c-a303-343ca7c24b87 |  | note | ○ Upper subbase results must be approved before construction of basecourse.
label | a4358bd3-a241-56ad-a2f6-7ccc7641e744 |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | 432e36fe-def3-5e02-b8d3-17e838591c57 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | 8e67e332-e320-5880-9346-876b04a9f5b3 |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | 5fbb47ca-306c-529d-8ea0-b936ed89fcdf |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5. Base Course Construction
checkpoint-status |  |  | checkpoint | 5.1 - Base Course Aggregate Delivery Checks
label | 0e655c31-5121-59a4-9ad8-ab8d33bad0b5 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 0efe8526-ca6d-5232-9388-2769f1d8a0c3 |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | 92a11ca4-adc6-597e-8684-47a9b485c8e4 |  | note | Frequency - During construction
label | 0611c7f9-c68a-52b3-8091-98b5c7edf8d1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | 4063ac84-5e5a-5ecd-8ef9-8e8791b13f62 |  | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
label | 14350f2a-c720-5f6c-9d5a-d784641fe57e |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 5.2 - Base Course Material Contamination Checks
label | 646c831a-ebaa-5764-8452-0531550227ef |  | note | ACTION (Hold, Monitor, Witness) - M
label | 03057e0c-35a6-5eb6-a374-1ef8fd237751 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 9575eb34-3e23-535b-9cc1-06f7acbb58ad |  | note | Frequency - During construction
label | cb588cbc-5c2c-5c62-84f6-1e609b0ef0e3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | fb2c983b-cdaa-5713-8d9e-a9783647cef8 |  | note | Conformance Criteria -
label | 0849127a-5d25-5273-abda-b01fa3e1b165 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 5.3 - Base Course Trimmed Level Checks
label | 0ea7d093-7aa3-5ee6-a394-085f362883b2 |  | note | ACTION (Hold, Monitor, Witness) - M
label | dd53081e-7111-5338-829a-04f1fbbf9b34 |  | note | Detail - Carry out a Level Check on the trimmed Basecourse
label | 69b5cc46-cdde-5c5b-b1e9-5d885d5d2f59 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | dee576d0-61fb-542a-9287-4f8ffec5c634 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 27107afd-68d8-5606-97b6-d27b3c127408 |  | note | Conformance Criteria - Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm
label | 2c4c703b-7aac-5183-97d9-03aa4acaeeee |  | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
checkpoint-status |  |  | checkpoint | 5.4 - Base Course Compaction
label | 9cc77dd4-2d79-543f-a0f7-cb53f9158c4d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1bf4d2b7-d308-5fa2-8659-a6d3182da809 |  | note | Detail - Degree of Compaction
label | d1ddf990-4365-5740-9066-a50160d0a047 |  | note | Frequency - 5 per Lot
label | 14a2bcaf-022f-53da-b97a-b3f1532626a3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | 32fea6b3-8a4d-54f2-ae30-1da69957f536 |  | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | 59aba317-3e2f-545d-8239-f2e8e36dc133 |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Base Course Surface shape check
label | 4fa7dd78-583b-5e96-8b47-78377ef45724 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0a95c74d-92ab-5fea-afd1-82f3c91f003b |  | note | Detail - Surface shape check
label | a1d5ab5d-0506-5bb3-af25-d5abc6548db5 |  | note | Frequency - Prior to sealing
label | 0ea633e9-0b81-555d-aa0a-b53ea929e7cc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 9ff8d790-2783-5d38-812a-657cd28c169e |  | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | 163d5a1a-3908-55d2-afd3-86cf85a52d4f |  | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Base Course Surface finish check
label | ff9cd5ee-eff3-564a-aeb6-7500757b6981 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d6bc956d-c1ee-50d7-8e03-f286b32fc7b8 |  | note | Detail - Surface finish check
label | e8924a93-4ae0-51eb-98fd-86a5b683f095 |  | note | Frequency - Prior to sealing
label | f9baefac-7955-56ed-a83d-9d8f27fe2040 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | 8a2c9c49-661e-50de-a385-6c97fdbd6be5 |  | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | b095856c-23e0-57ab-9870-0d89374998b7 |  | note | Records - Site photos, Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6. Sealing
checkpoint-status |  |  | checkpoint | 6.1 - Location/Size Confirmation
label | c399061b-2739-525a-9154-ed0adb2802fc |  | note | ACTION (Hold, Monitor, Witness) - W
label | 18f05878-56aa-5ff3-8bf6-af9d43a29a41 |  | note | Detail - Mark up extent of Chipseal
label | 7f4ee690-8323-5e62-80b7-d014e9c7d21e |  | note | Frequency - Prior to Sealing
label | 13abd30c-5421-5926-935c-f9369708816a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
label | 3f1fe611-0081-536d-9d1a-ab13935d173c |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 6.2 - Surface Cleanliness
label | c7e6eb72-009a-5b1a-9441-e5b50e0841a6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 32487b15-225f-5de7-8e8f-ca1bbe87f9e9 |  | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
label | 20e1c398-29a1-5b67-87a0-52a437fa1207 |  | note | Frequency - Prior to application of binder
label | ad033c84-bd93-532d-bd1f-85462f63dff8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 4c3aa560-6110-59a2-9f26-d05dc954c43c |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 6.3 - Binder Application
label | ba5de36b-c8b0-527a-ab9e-77f5fbe848a3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d4a15de7-53d4-5f9d-8c9a-bfda00411c3b |  | note | Detail - Ensure the Binder application is according to the seal design
label | 92867935-84aa-5dec-8092-7af1c0231117 |  | note | Frequency - During sealing
label | ddb8af94-5f39-53ca-a413-c29d73a77963 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | af9398ae-369d-5d37-82f9-aa685db9b5cd |  | note | Conformance Criteria - According to seal design
label | 74498145-30e2-5af1-9d47-d94ba22e7ce6 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 6.4 - Chip Application
label | e389d6bb-6f45-5ab1-b10f-9b74eb95b389 |  | note | ACTION (Hold, Monitor, Witness) - W
label | df676853-d375-5069-adc0-9aab01f082b0 |  | note | Detail - Ensure the Chip application is according to the seal design
label | 2db41e56-7a32-5923-8c49-3aaaa776beb7 |  | note | Frequency - During sealing
label | ab130ae3-bf29-5f20-9f70-bb2b99a6fd76 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | a7a06eb8-8d26-5f77-b001-5c5e7d2e5d9b |  | note | Conformance Criteria - According to seal design
label | d538e32e-104d-542a-a853-230a96f89d5f |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 6.5 - Compaction
label | a73973bc-15af-5c94-ac57-baa4806f9a40 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 16f961dd-135e-5d2a-bbc6-900d6fc52ddc |  | note | Detail - At completion of rolling
label | 9d8dcae7-0637-5dbd-aa49-767aa03bcaec |  | note | Frequency - During sealing
label | d12c285e-8a28-53cd-a1be-23211a9a8c65 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 2ea7a3bb-bdd2-5d62-8baa-764574daa9e4 |  | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | 202ab1f6-88ef-58ed-9f12-1405b5d316f3 |  | note | Records - Photos, QA measurement Sheet
checkpoint-status |  |  | checkpoint | 6.6 - Removal of excess chip
label | 4baef4f6-2e6e-5846-9e5c-22e9572c410c |  | note | ACTION (Hold, Monitor, Witness) - M
label | 8923bc8a-a675-57e9-b94d-0a78da9be64f |  | note | Detail - Removal of excess chip
label | 09e9dcba-cab0-55cd-80d3-f9ab06d72fba |  | note | Frequency - Within 48 Hours of Sealing
label | 1e3803da-43b7-5763-8e70-313c74d5f3e6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | ecacffd0-9af1-5265-aa01-a859daac1df4 |  | note | Conformance Criteria - Ensure all excess chip removed from site.
label | 9e25d188-06dc-5bcc-9f7a-f6b841c8399b |  | note | ○ No chip windrows left on site in Shoulders.
label | fbdef7e5-ba58-536d-8af9-01c239eb3d7a |  | note | Records - Photos, Site logs
checkpoint-status |  |  | checkpoint | 6.7 - Surface finish check
label | b0496b9c-76d6-5210-8d12-915ee13d3f10 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 35208f78-017b-52f6-959f-832f45df06dc |  | note | Detail - Surface finish check
label | 4a0cc324-9233-57bf-a277-3fdf34638cda |  | note | Frequency - After sealing
label | 3bea6c29-258e-566e-82c1-9cbc1900c868 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 94127224-b7d4-52cd-8081-af9e0a751039 |  | note | Conformance Criteria - Engineers Acceptance
label | 80d571f0-ecd3-5460-aacb-ac07c61dfcc7 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7. Road Marking
checkpoint-status |  |  | checkpoint | 7.1 - Road Marking
label | 14835991-4d51-5cd5-983f-5ce9a0abe4d7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2ce389ee-838f-5d0e-81bd-3dd906952987 |  | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
label | 62c6603e-32bd-51a4-a1f6-78d8d0859f0b |  | note | Frequency - Prior to the final line marking
label | 06b45db0-725d-5912-bbc5-4b00e54980e7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | aa0b4278-0aeb-56b6-83ce-13f52ea9496e |  | note | Conformance Criteria - Engineers Acceptance
label | 151ac3d7-05ee-5089-af42-baac5fcabc40 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 8. Hydroseeding
checkpoint-status |  |  | checkpoint | 8.1 - Hydroseeding
label | 5bd91a3e-afc5-55ed-a12b-0e6685153b02 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 05661e4e-e6a3-5c9b-a97d-6225b8578a34 |  | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
label | d6ba0565-ef35-5377-818d-265bd88824bb |  | note | Frequency - At the completion of the Lot of work
label | 885746cf-5489-5756-86ba-bbffc9a52886 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 78a1ca4d-1450-5092-9304-2d5c8c9c2586 |  | note | Conformance Criteria - Engineers Acceptance
label | fac8b7a1-91a5-5b08-8d96-124fdc400221 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 9. Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 9.1 - Final Walkover (Snags)
label | 19f6be86-a5df-55d5-8d44-45379cb22fa2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4459d765-aa11-5154-9b2a-ce8c8b37e36e |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | f80a2e4c-2146-51c4-90c7-069bccabf285 |  | note | Frequency - At the completion of the Lot of work
label | 55081097-a8e2-5643-9257-66ae49121a0d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | e16298eb-558d-58ac-99c5-5aa33e9987e8 |  | note | Conformance Criteria - Completed report
label | 2d47c780-4fd5-592d-ad75-b29f07898122 |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.2 - Survey As-builts
label | 0479ea7c-c60d-5ca1-aa71-b98bcb83f6ff |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7a5e63e2-34e9-5f2d-b779-6dbec2cff15f |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | bed34a48-c741-5dea-be95-5caa7ba7c19a |  | note | ○ A survey as-built of completed work must be provided
label | b008360a-1c88-51ad-b6aa-75493199ebce |  | note | Frequency - At the completion of the CWP of work
label | 025066a4-a42a-5dbb-a615-bd560df255d1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 154040db-ee46-580d-8578-7e417c84c30b |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded.
label | 0e0b2de3-628b-50d6-8a65-6de45aa86556 |  | note | ○ Signed and dated
label | d3ea43a5-2412-5ddf-aa49-f2bf843227f1 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.3 - Quality Assurance Deliverables
label | 5c053464-d4e4-5d01-ae42-eb8067d66dfe |  | note | ACTION (Hold, Monitor, Witness) - W
label | f8c5ce4e-42a2-524b-963d-a21ff1ad31d9 |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | f570f929-5577-5146-b86d-3d0735c05d26 |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | 9ada14f6-7ee5-5a89-95c9-6bc5ffc8accb |  | note | Frequency - At the completion of the CWP
label | 24ab9273-ec73-594f-a256-90210192c868 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 0a719fa8-fc36-5ee7-9c7b-d4fb8fc96860 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 5ca0768e-978a-5e2c-9eae-c81080a75bad |  | note | Records - As-builts, NCR's and RFI's
checklist-flat |  |  | checklist | CS-4100 - Subgrade Approval Checksheet |  |  |  |  | Yes | CS-4100 - Subgrade Approval Checksheet | 3b7199b4-1b1a-4289-87e1-6855b8354cca
checkpoint-status |  |  | checkpoint | Area completely stripped of topsoil & organics
text | 7bfe2918-46b4-5d64-9f88-6c6559edad2b |  | textbox | Initials - Design Engineer:
date | d22c6b83-e9ef-589a-88ce-4e6da2c69210 |  | date | Date:
label | cb03858e-9212-5022-95df-94c64b6a1fcc |  | note | Comments:
text | ba95f42a-77f6-5cfa-8dbc-54dac56abbe6 |  | textbox | Chainage Start:
text | dd89fe5f-5014-5b9b-a0cf-471b4206e98f |  | textbox | Finish:
label | 22764273-90aa-5ea7-a186-5eac30a123c0 |  | note | Photos of area are taken & kept with QA records
checkpoint-status |  |  | checkpoint | Topsoil strip topo survey carried out
text | 46bcfb22-4e70-559f-8b05-2bb992475ccd |  | textbox | Initials - Site Engineer:
date | 8d56e735-07bd-5482-88fc-2a5026a7ae63 |  | date | Date:
label | 0742bac2-0f9c-5e70-b0d0-039ea4e96a51 |  | note | Comments:
text | ff0a07c2-02bc-5235-a394-80ab6991f132 |  | textbox | Survey receipt #
checkpoint-status |  |  | checkpoint | Scala Penetrometer Test carried out
text | 5254847a-e29c-5cbe-b162-0a796aa73365 |  | textbox | Initials - Site Engineer:
date | c1631c80-f5bc-5b8f-a8df-5dac953b3e0e |  | date | Date:
label | 56b87487-8f28-5476-b7bc-df7215545554 |  | note | Comments: To the correct frequency & results captured on the earthwork lab testing register
checkpoint-status |  |  | checkpoint | Proof Roll carried out & witnessed
text | 5a99b4a7-27eb-5948-a710-8094a09a96a1 |  | textbox | Initials - Design Engineer:
date | 8f2c2640-98e0-5a1d-8014-8244de4c376a |  | date | Date:
label | f6c012bd-af4b-57fa-b2f9-992f135c86ff |  | note | Comments:
text | e96ec926-0eb5-5fa2-b6b8-9433eef39e02 |  | textbox | Equipment used:
checkpoint-status |  |  | checkpoint | Did Proof Roll pass
text | e501bb02-fd70-50f4-8a52-38901d9d55f0 |  | textbox | Initials - Design Engineer:
date | c8c7a24c-2d98-5e6c-911a-d146dd479b1a |  | date | Date:
label | b204c222-de14-5d4e-9ecb-a96e0755a818 |  | note | Comments: If yes moved to #10, If not undercut required continue below
checkpoint-status |  |  | checkpoint | Undercut area is to be marked out onsite by Design Engineer
text | 5d5806af-224e-56f2-913a-59c3a206ea5b |  | textbox | Initials - Design Engineer:
date | 35b0ae04-76e1-5fd9-89d3-1648a19a9732 |  | date | Date:
checkpoint-status |  |  | checkpoint | Undercut to be inspected before backfilling commences by Design Engineer
text | fe7e2612-9c9c-59f6-8e2f-cbcc0e93095a |  | textbox | Initials - Design Engineer:
date | 190e4daa-74fd-502d-875c-c5e299102014 |  | date | Date:
label | 8f1f9860-3345-5973-89e8-beee310dbd58 |  | note | Comments: To determine that all undercut areas are prepared to the specifications
checkpoint-status |  |  | checkpoint | Undercut area to be surveyed
text | be79a69a-2a50-5e47-8845-e8037f0d7b78 |  | textbox | Initials - Site Engineer:
date | 1fdaa733-9443-5010-9594-f27c88cc589b |  | date | Date:
label | 059f0c6f-00f8-5c5c-ba23-19906f2fa870 |  | note | Comments:
text | cfe30477-c749-504e-97a5-ee0109aed6c4 |  | textbox | Survey receipt #
checkpoint-status |  |  | checkpoint | Backfill material is approved to be used and is tested in accordance with specifications
text | 02bc2afd-7ec0-53ee-9a7c-4f0f729103d5 |  | textbox | Initials - Site Engineer:
date | 80b06d60-7319-53b0-88fb-2fa4544dcaf3 |  | date | Date:
label | d177b0da-2212-502d-830d-e62969035093 |  | note | Comments: Lab Test Result register
checkpoint-status |  |  | checkpoint | Site is prepared for bulk filling to commence
text | 7d7fd6d5-8009-550f-9e9c-dfb0b8e9536a |  | textbox | Initials - Site Engineer:
date | 708dc4c7-70fd-54b3-a9b2-360abf6042a1 |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | 696ec6ff-acd8-5e9b-be65-238c59ac7edd |  | note | Position: Site Engineer
text | 0fad1534-6057-5f20-98f9-8a465ea62264 |  | textbox | Site Engineer - Name:
date | 917aa6ca-3a84-5a73-a08f-464c63a9d9b4 |  | date | Site Engineer - Date:
label | 6ea61e86-5790-5fa4-a2ed-811de1589e7d |  | note | Position: Design Engineer
text | 0ceccf9c-4e4b-588d-9912-6bfbf2ea99d7 |  | textbox | Design Engineer - Name:
date | ad322a92-a770-50dc-bce5-0f6f78e88aea |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | SIGN
checklist-sectioned |  |  | checklist | ITP - E3001 - SH05 SIP Generic - Pavement Construction | itp |  |  |  | Yes | ITP - E3001 - SH05 SIP Generic - Pavement Construction V2 | 3bc16a59-7963-4a6a-b5e7-809f99a8c25f
checkpoint-group |  |  | section | 1 - Setout & Saw Cutting
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 5da27e37-9227-5bb1-a724-fbf532403a4f |  | textbox | CPS Eng.
text | dc9e46fd-eb2b-5473-9946-dd1dfb0a1aba |  | textbox | Site Engineer
text | 5a919999-991e-5160-9912-a294362d2c67 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Survey Setout
label | 3ef15018-6208-511e-8c82-d1183059d622 |  | note | ACTION (Hold, Monitor, Witness) - M
label | b8960be2-03b2-59ff-b4d8-752ba989392b |  | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
label | 4ebf3757-7862-55c8-99b3-72880d3f1c73 |  | note | Frequency - Prior to commencement
label | ecb94d98-9750-599d-b303-158d244625de |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | f269f329-a54a-5df0-9660-2e4daacc3c5d |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 1.2 - Saw cutting
label | 16ea99d8-ef40-59bd-8c5a-5f5ad20a5110 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ea533cdd-56ad-522d-9021-e49d7662d1f0 |  | note | Detail - Proposed Sawcut line to be inspected by the engineer
label | f3e10b10-6dab-5347-8aeb-febbad767d01 |  | note | Frequency - During construction
label | 286319d0-553d-54c1-b317-04b282f99c2e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | e5809d11-6015-5a46-bcff-54894ea5223c |  | note | Conformance Criteria - Project Specification 6.6
label | 187f0fd6-12c9-5321-acd6-623c638caa1b |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Material Compliance
checkpoint-status |  |  | checkpoint | 2.1 - Sub Base Material Compliance
label | afc0c0bd-da12-554d-aa42-a96305fe4320 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ae94212e-d0a2-59dc-a902-db67d176c2f7 |  | note | Detail - Aggregate material compliance for Sub Base stockpiles
label | 6021f4f4-d3c6-5bea-9179-9aaeb88b902d |  | note | Frequency - Prior to commencement
label | 9e64e8a1-0a37-5bd4-b685-b822f88f00e0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | ab7b2e55-1551-5fd8-985d-9094acab4a8b |  | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC.
label | ac9a0812-9c04-5ce7-90ec-c76cb17e20d1 |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
checkpoint-status |  |  | checkpoint | 2.2 - Base Course Material Compliance
label | 5f00bf43-8d7d-585a-8daf-f14e112b6230 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 94e8cb67-85e3-5453-ae90-b5beacb67bba |  | note | Detail - Aggregate material compliance for Base Course stockpiles
label | 910048a7-84d0-5605-91f3-e55d0427aec9 |  | note | Frequency - Prior to commencement
label | 34a94167-7f5f-5aae-965a-1157570982d9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 825117ee-e282-5ce8-a2fe-678e108c0a09 |  | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
label | df1c5b79-8441-528f-b877-ea5baba299a1 |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
checkpoint-status |  |  | checkpoint | 2.3 - Chip Seal design
label | 6242664b-32ed-53b6-a3ed-aeea5c5b0f3b |  | note | ACTION (Hold, Monitor, Witness) - H
label | b74310c5-c1c0-599c-a570-596cfd8df162 |  | note | Detail - Seal design to be reviewed prior to sealing.
label | 951e56e0-2725-5124-8564-95ff58370f78 |  | note | ○ Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer.
label | b57dd01e-989d-5b53-9e8e-9640c2257bdb |  | note | Frequency - Prior to Sealing
label | 31f6ccb1-de06-5196-b51a-defa7f1c713f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 47d962ce-af5a-5dfb-b1af-3e3e5b1eddcc |  | note | Conformance Criteria - The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995.
label | 1eaa35da-0f38-5de4-ac2b-ad95d8797e05 |  | note | Records - Emails/NTE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Sub Grade Construction
checkpoint-status |  |  | checkpoint | 3.1 - Sub Grade Strength
label | 9f98b8e7-cf56-5bfa-8271-39c4f3aa8879 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0243efe6-bd17-557b-88c8-845a3db28e60 |  | note | Detail - Determine Bearing strength of Sub Grade
label | ad87a623-204d-5161-aa18-282647c27b6b |  | note | Frequency - After Dig out, every 10m
label | d087639e-cdc1-5423-a4b4-332b524dee89 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 38629ae5-8331-582f-ac1d-83875c734bce |  | note | Conformance Criteria - Min. 2 blows /100mm
label | 68cf7310-e3a2-5b71-a125-73c6ac686c21 |  | note | ○ 2 blows = 4 CBR
label | 9a668e70-3dfc-56e3-895d-cd70e2854daa |  | note | Records - QA measurement Sheet, CS-4000 1m Scala
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Proof Roll of subgrade
label | 8dda20b6-e36b-530d-9288-89ffc93618d8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b71fb06d-af66-5baf-8773-10b17ae2bed3 |  | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
label | c954ded2-96e7-5af8-85c6-8a899101aa05 |  | note | Frequency - Prior to Sub Base Construction
label | 2d8a8f02-51f6-5430-8d53-686192d4fbed |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 9cd4191b-ab63-5b8a-a832-2be3f7bd5e7b |  | note | Conformance Criteria - Engineers Acceptance
label | 37b503a9-dd84-5465-8229-af1577b39778 |  | note | Records - Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4 - Sub Base Construction
checkpoint-status |  |  | checkpoint | 4.1 - Sub Base Aggregate Delivery Checks
label | 4040404c-e33a-57ab-8e0c-9e510ca0b66e |  | note | ACTION (Hold, Monitor, Witness) - M
label | 07c4f95a-1c8e-5117-909c-c59c6a29b847 |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | 9ee68f3d-4159-505e-8cf5-17f39abb6bd6 |  | note | Frequency - During construction
label | 507c5590-3f67-519d-a544-d0a37cb4d8f9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | ca92ccb4-644a-5403-91f7-21d24a95bb8b |  | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification.
label | 29d4a6ff-41e0-5fa1-8b27-5444a7254413 |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 4.2 - Sub Base Material Contamination Checks
label | 2ac3f7fa-7af8-549c-885b-b7c883addb17 |  | note | ACTION (Hold, Monitor, Witness) - M
label | c5d860c0-cc62-5398-a05e-06d3246cc065 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | cfcab3c5-c985-5dee-8a44-ab6c6b8d3113 |  | note | Frequency - During construction
label | e8d8dc0d-e5e9-54d5-9409-2c1fde4103f4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | adaad07c-7bcc-5635-9a28-c76b5c0fb511 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 4.3 - Sub Base Trimmed Level Checks
label | 74e426b2-2e49-5a32-873e-090e01d9080a |  | note | ACTION (Hold, Monitor, Witness) - H
label | a1d707ab-01c3-5683-80ba-d304fcecafb2 |  | note | Detail - Carry out a Level Check on the trimmed Sub base
label | c51c1567-cc37-5801-86a0-1474c7db4695 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | 28b40f97-5488-5e87-b9cd-4b8b51db9930 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 4320d227-1631-5656-bedb-032176d4b5a9 |  | note | Conformance Criteria - TNZ B/2 Tolerance = -25mm/+5mm
label | f0aa8f9e-aa5f-55ab-b00d-a02d9e9f5cd5 |  | note | Records - QA measurement Sheet, CS-4100a Subbase Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Sub Base Compaction Lower
label | 83156ea3-8204-5ebc-b059-aa6bb2996063 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5cf1ad09-96c1-54e1-a81f-cb6583e36f79 |  | note | Detail - Degree of Compaction.
label | 88f560c6-a8b5-5eba-a0cd-5c23834c6362 |  | note | ○ The subbase shall be constructed in two layers.
label | 3ff8a5fd-7a5e-5a0c-a9a4-9dbaa34fb280 |  | note | ○ Lower subbase results must be approved before construction of upper layer.
label | 451fe181-7218-5d50-82ec-456548e3a1fa |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | 2b8674bf-18fa-526c-b779-32b2192e5da8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | eb3be03a-56a6-55f3-bec0-41400956e24b |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | 1c3e1863-2578-5f19-a036-3815db278bc5 |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Sub Base Compaction Upper
label | 39a2f529-fb2d-5734-aa4d-0612ea21993c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4301bd6b-0072-5bf8-ae06-5ac2fdd6a9ec |  | note | Detail - Degree of Compaction.
label | 96688400-c1d3-599f-8f72-4655db3c738e |  | note | ○ The subbase shall be constructed in two layers.
label | e811e220-aaf9-5719-84cd-08e13f2ad804 |  | note | ○ Upper subbase results must be approved before construction of basecourse.
label | 492b1a19-728f-5cea-bf6e-20ea2fd3f6e0 |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | 96d81701-9dd5-5363-8751-83268f9630c1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | 2eac3e29-6dc2-57c4-b553-03fa86a1cadb |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | aab71665-6f34-5ecc-885e-4c778e3defd0 |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5 - Base Course Construction
checkpoint-status |  |  | checkpoint | 5.1 - Base Course Aggregate Delivery Checks
label | a9505cc9-d657-5d0d-9013-ab2f18821ed1 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 92f48eee-05e8-53ad-9199-c0d3493a373a |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | f8f8a5b1-41bf-5770-8fd5-c14e3ba0c648 |  | note | Frequency - During construction
label | 7f7168e5-a0aa-5225-a5bd-6a94acad8ae6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | 9aef1535-8d7f-5449-aa05-9416ce4d817d |  | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
label | 26fa8e8f-9ca2-5996-9859-30d768f362c7 |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 5.2 - Base Course Material Contamination Checks
label | 455a7bb4-2877-5879-befd-447ff47cd683 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 52b87140-99ed-5def-af1b-ba5836871a5d |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 83da7bc3-9eb5-5c40-9bf6-3a79c0c93442 |  | note | Frequency - During construction
label | db3561ae-16a3-5252-a5ec-07ab24948e07 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | abc8c789-c8ba-50cc-86fd-aa83851b6d93 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 5.3 - Base Course Trimmed Level Checks
label | ea7aabec-c7af-5eff-a2e7-ac1944cb3274 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 57681b45-f5f1-588d-a790-719b9037e9b9 |  | note | Detail - Carry out a Level Check on the trimmed Basecourse
label | f78a7bfe-40a0-54de-9eac-0d311f9fd842 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | 1c1e8ac0-6dfd-5aab-b8ed-327fa25a1e0a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 02636fff-f1ea-529f-b67a-8da418d46658 |  | note | Conformance Criteria - Tolerance = -5mm/+15mm
label | 2e4aa163-4cf7-5182-936f-0c1190506a7a |  | note | ○ if constrained (kerb) Tolerance = -5mm/+5mm
label | 2fe400b7-361e-5c15-a881-79134691646e |  | note | Records - QA measurement Sheet CS-4100b Basecourse Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Base Course Compaction
label | 7adbab00-8d87-5485-a1e0-2117e1b5f871 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5defd46b-293a-5b8c-bd17-9b32d463b084 |  | note | Detail - Degree of Compaction
label | 803620d0-d4d1-57f8-b00d-f3109f415968 |  | note | Frequency - 5 per Lot
label | 68bb47d5-4232-5f81-81a6-cab7c53e3021 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | ba7c8fbf-4ee6-5b05-82a7-9de90837f882 |  | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | 3f67cbb6-3129-55f2-b9b7-16b96c08926c |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Base Course Surface shape check
label | 624b10ac-6c8b-5771-a808-dc7ef81602d5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | de94c82c-f275-5889-b2e7-7e1897299fd4 |  | note | Detail - Surface shape check
label | 77d1f411-78ec-5059-8591-3bdd0d36c8a9 |  | note | Frequency - Prior to sealing
label | 8bbe0891-aff3-589e-93af-f3ab94f1b2e1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 85cda516-e41d-52b1-b739-7f0886a73f15 |  | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | 05ed5353-ec27-5be9-835d-bba72c42a0b6 |  | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Base Course Surface finish check
label | 0220ad22-0840-56d5-919f-a0c33498fc4c |  | note | ACTION (Hold, Monitor, Witness) - H
label | aebf525d-4ed8-5718-a98f-1ea627e85d36 |  | note | Detail - Surface finish check
label | b079aa92-77d3-5094-8b1b-a86b322adfa9 |  | note | Frequency - Prior to sealing
label | d9ac9732-5dea-5224-9f27-fa763908fb54 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | 3fa7dc4e-60bf-50a9-aeb4-217f1cf68970 |  | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | 12abd0a8-cb91-58b9-a8f9-e11618432643 |  | note | Records - Site photos, Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6 - Sealing
checkpoint-status |  |  | checkpoint | 6.1 - Location/Size Confirmation
label | 7485f261-d4f9-536b-8fdf-561601de76c2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c8d48b6d-db97-53fb-9758-4d4866adcbd6 |  | note | Detail - Mark up extent of Chipseal
label | cb8b1442-c99f-5f49-b1bd-e623891b21e3 |  | note | Frequency - Prior to Sealing
label | 739f9ab4-98f4-5175-a391-f34c4115690c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
label | 0948da8f-3868-588d-ab60-cc56197caa0a |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 6.2 - Surface Cleanliness
label | fb17b9dd-3a9c-5ae0-8483-0f7f73c208aa |  | note | ACTION (Hold, Monitor, Witness) - W
label | 79aa985f-289a-5c62-a926-0b250674f747 |  | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
label | 1f2a42d5-f130-5ef4-9d62-f4e07e20dfda |  | note | Frequency - Prior to application of binder
label | 88900a8e-f43c-5a99-8559-6dd471a283da |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | e6f8d306-45a8-5ad4-9639-9b6595ca4370 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 6.3 - Binder Application
label | 1422a60d-cd8d-5f49-b41b-d465972ef4fe |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1b4621f4-d8a0-53f2-bb18-1f9b358d2953 |  | note | Detail - Ensure the Binder application is according to the seal design
label | 2f077953-4c36-5d05-9d9c-a0db80e18ea9 |  | note | Frequency - During sealing
label | 9ba2946e-59bc-5470-9365-d7e27ce2acd7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | b6e772c4-0363-505a-8e8f-1239054c41bb |  | note | Conformance Criteria - According to seal design
label | f8648227-b271-5c91-ab7e-90f3439745a5 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 6.4 - Chip Application
label | b5a208fd-40f2-52e3-9cca-56711f730bed |  | note | ACTION (Hold, Monitor, Witness) - W
label | e72e3bf2-bda1-5f1a-b021-dbba356b5902 |  | note | Detail - Ensure the Chip application is according to the seal design
label | 911e46fa-d246-5b30-82b5-a6ce46568fe6 |  | note | Frequency - During sealing
label | d66906f6-16a5-57c8-89a7-4ce475e38332 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | e8882c91-dcb9-5df7-bf00-d8de68422cfd |  | note | Conformance Criteria - According to seal design
label | baa65324-b804-5379-a4b8-95d634b02604 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 6.5 - Compaction
label | e20e83ee-4700-5b84-802b-eb87a3f87c4d |  | note | ACTION (Hold, Monitor, Witness) - W
label | c87001d6-cc7e-513d-a15d-023ce0485788 |  | note | Detail - At completion of rolling
label | 7073d984-be08-5ff7-83e0-9f902fc2f7a3 |  | note | Frequency - During sealing
label | 6a86c290-5f38-581b-99d8-e986fb728f94 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 84ae9be8-6762-521b-97a6-13b1d5623ac0 |  | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | 6721c5da-b99d-5168-8f75-73e0995eec47 |  | note | Records - Photos, QA measurement Sheet
checkpoint-status |  |  | checkpoint | 6.6 - Removal of excess chip
label | d5c18bd0-667a-5346-a137-b810d639eb7b |  | note | ACTION (Hold, Monitor, Witness) - M
label | b5f3dfb8-3b48-5cbf-b61b-fa48d09663a0 |  | note | Detail - Removal of excess chip
label | 77e27586-729d-519b-a8f7-e5fb020fe37d |  | note | Frequency - Within 48 Hours of Sealing
label | 56722817-c9fa-5f36-b249-fd18e5ac83d1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 964a8ccb-f1d8-574d-8f28-e2cccbb0be65 |  | note | Conformance Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | 4b248657-8678-5a28-bb34-5addfc697508 |  | note | Records - Photos, Site logs
checkpoint-status |  |  | checkpoint | 6.7 - Surface finish check
label | 3f1b6df4-7b44-57d2-b3a9-15fa76642587 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 533c4c79-b617-5caf-bc14-d023edd661b3 |  | note | Detail - Surface finish check
label | 90dcc6c4-eade-54e3-9bc4-961129dbbf46 |  | note | Frequency - After sealing
label | 369264ef-d533-5e7f-9b79-c0a4cd5c456a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | a23abaf5-bf8e-5fdc-b686-71d39175140b |  | note | Conformance Criteria - Engineers Acceptance
label | bf63a106-238e-5a4b-9fb7-b25a2792b89f |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7 - Road Marking
checkpoint-status |  |  | checkpoint | 7.1 - Road Marking
label | 0ef3fc74-de5c-5ac1-a095-308ca8073025 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 51b9f79e-12a5-56c6-af31-7a848ff256ea |  | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
label | 00cc6976-2ce6-555f-aaf9-a95542f79ff7 |  | note | Frequency - Prior to the final line marking
label | d8b2e7a1-ce8f-5cfc-b218-85635199b90e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 255b4cce-c383-5c84-9b14-da016543a7db |  | note | Conformance Criteria - Engineers Acceptance
label | b5bd9f51-4f6b-5269-968a-7e0689ca743f |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 8 - Hydroseeding
checkpoint-status |  |  | checkpoint | 8.1 - Hydroseeding
label | b61e720a-f746-5e99-8c22-f0c969116f0b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2c7c1bd4-2667-5e03-9979-0d3697094659 |  | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
label | 0caf40e2-08fb-555c-8523-339f007b31a8 |  | note | Frequency - At the completion of the Lot of work
label | fa40d2df-0afb-558f-aad4-1237ac808457 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 39b44a5b-4b7d-5c2d-805f-d8d09fa4f680 |  | note | Conformance Criteria - Engineers Acceptance
label | f62e2122-ad8e-5238-92f4-0e05ec2196bc |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 9 - Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 9.1 - Final Walkover (Snags)
label | 7de9238b-1a82-5161-8d51-098bf31828ad |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0b7ef239-9499-5d42-b9b4-cc1a63f23e6d |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | 7e6937b9-79a1-51e7-8579-eab1f02ac151 |  | note | Frequency - At the completion of the Lot of work
label | 5a2bc79f-d0cb-5cd9-a680-9673075515a5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | bbbc28a7-af8a-5ec5-a7d1-06a900682b58 |  | note | Conformance Criteria - Completed report
label | 719704c9-1130-5a5d-acac-368e46c466ff |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.2 - Survey As-builts
label | 734e3d95-654f-5b81-82f8-b9d64a879923 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ef15707e-fe22-56e7-87c8-34a64ac4757c |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | 82d4a511-2815-5af5-8da5-d1c508bb0a13 |  | note | ○ A survey as-built of completed work must be provided
label | f5b03f3f-1e8b-55ae-9d2f-4b1ce0d7d12b |  | note | Frequency - At the completion of the CWP of work
label | b993bd80-b41b-55d8-8f97-c5031b30e84b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 2438aa1b-a84c-5a31-a735-61f723bafcbd |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | 8a8d5207-5b2f-586d-a02b-2e19065886d9 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9.3 - Quality Assurance Deliverables
label | ed06dd4d-f370-5f63-8ac9-aae4f6a5ef1b |  | note | ACTION (Hold, Monitor, Witness) - W
label | d8df4bc2-80b4-560d-b9bc-42e1479f532e |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | 771cd758-4ead-5454-88a8-d990b48dbda0 |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | 531faa74-5e4e-5f16-bddc-c3798b50ab54 |  | note | Frequency - At the completion of the CWP
label | 31bfad75-8b62-5423-a0c3-50940d0d7582 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 0755f4d6-f60e-566c-ae3b-09bfc793a11b |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 7c069f27-d304-5884-9994-f289940a2f88 |  | note | Records - As-builts, NCR's and RFI's
checklist-flat |  |  | checklist | CS-4074A - Low Pressure Air Test Record for PVC pipes |  |  |  |  | Yes | CS-4074A - Low Pressure Air Test Record for PVC pipes | 418d1cb2-4cb9-46aa-ac13-78801005ba68
checkpoint-no-status |  |  | checkpoint | Details
text | b1e8308d-2060-5676-93f3-cc31f7d7be4e |  | textbox | Work Area(s):
text | d172910e-3473-5cce-b7d7-67544c3ea669 |  | textbox | Sub Work Area(s):
text | bea861fd-fd4d-5f85-90d1-fb7e533299c0 |  | textbox | Lot(s):
text | d3d2ce9c-a5dd-5ba8-bb10-4f08a5f29f4d |  | textbox | Sublot(s):
text | 349ba8f8-b571-57d2-a113-a55c7a792446 |  | textbox | Document Date:
text | f6b5a4b6-fe42-51a3-813f-08eab7b69a62 |  | textbox | Updated By:
text | f5daa23d-af28-53c3-a151-90a1dd4452ec |  | textbox | Area:
radio | f4e1ca2e-6ce9-5ec2-b1d0-6b74b3a27d1f |  | radio | Weather: | Fine,Overcast,Showers,Rain
text | 4b21e02a-0259-5594-ba12-90a9dad80115 |  | textbox | Location:
date | 9f84189b-2132-56cf-8eb3-c0a75215fff3 |  | date | Date:
label | 47eb5451-28e6-53af-bff7-28a303fe6a10 |  | note | Personnel Conducting:
text | a7508bb1-cfb5-56ef-a682-212d10b57749 |  | textbox | Drain Layer:
label | 123a0dfb-2ba7-56ef-9d89-b823cba155fa |  | note | Witnesses Requiring Notice of Test:
text | 6f1b7a5f-6064-513c-9b86-feaba4f288e2 |  | textbox | QLDC Rep:
text | 18f601c4-878f-5ff8-9549-800ecbacb1d8 |  | textbox | CPS Engineer:
text | dbc2441f-e4bf-5653-978b-bb55809e0d03 |  | textbox | Site Engineer:
checkpoint-no-status |  |  | checkpoint | Pipeline
text | c3dd3d8c-e76e-5c4e-881b-4eb57ffc6ffa |  | textbox | Pipeline:
text | cac3dc3c-37fe-5cf9-9ada-38e947069c94 |  | textbox | US MH Number:
text | 18e60d72-8149-5135-a114-7401e2eba7f4 |  | textbox | DS MH Number:
text | b38d36f3-0299-5c90-811a-26c006755102 |  | textbox | Drainage Plugs used: Rubber & Aluminium Plugs, Rubber Blow up plugs
radio | 74b4d9bc-eb7f-510d-b264-ab8d434365e6 |  | radio | Plugs Braced? | Yes,No
checkpoint-no-status |  |  | checkpoint | Pipeline Material (non-concrete):
text | f822dcfd-ffca-5be0-b17f-adeaa04ac22d |  | textbox | Pipeline DN (mm):
text | 29214f6b-caa5-5954-a4d2-0ba0d967d324 |  | textbox | Pipeline Length (m):
text | 97f5ab81-dbd4-5e8f-9321-dde6cd29e6bc |  | textbox | Test Time as per Table C1:
checkpoint-no-status |  |  | checkpoint | Prelim Checks:
radio | 937bad76-123a-5852-bf92-518f16d6c203 |  | radio | Line at pressure and maintained for 3mins? | Y,N
radio | 3013ed4d-dc19-5c24-a81f-dcd6dfa4580a |  | radio | No Leaks Detected? | Y,N
checkpoint-no-status |  |  | checkpoint | Start Pressure
text | 14a16915-fe3a-5b76-812a-45017639b14b |  | textbox | kPa:
text | 8bc70906-d5ec-5380-885c-bb8c8a197074 |  | textbox | Time: |  |  | am/pm
checkpoint-no-status |  |  | checkpoint | End Pressure
text | 7171e6d8-609f-5a9f-91f8-7df740a6be0e |  | textbox | kPa:
text | cb60fd17-e183-5429-a2fc-53874b4255d7 |  | textbox | Time: |  |  | am/pm
checkpoint-no-status |  |  | checkpoint | Pressure Drop:
text | a5095dbe-4ddf-586e-8ef2-2c23ef82c6d1 |  | textbox | kPa:
text | 1bb7496f-7cbf-5421-90af-31db30d7ba9d |  | textbox | Duration of Test: |  |  | Mins
checkpoint-status |  |  | checkpoint | Test Result
label | b8d17228-eb1c-5f63-85e7-5d634dd60b60 |  | note | Acceptance where the gauged pressure has dropped less than 7 kPa for the time interval shown in table C1 after the shut-off of the air supply.
label | 1bca50f5-a931-5239-ae67-e313062977be |  | note | ○ The test length shall be acceptable where the gauged pressure exceeds 18 kPa (or not more than 7 kPa less than the pressure at the start of the test) for the time interval shown in table C1 after the shut-off of the air supply.
label | ec45793a-cf74-5cea-aa8e-eb16aaf1504f |  | note | ○ Table C1 is based on an air test pressure of 25 kPa (in excess of any external hydrostatic pressure due to groundwater)
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions for the purpose of this test
text | 59ffdca4-af5b-502d-b9ef-b2344712883a |  | textbox | Name:
label | 40db0f3e-c885-54f5-b158-4015de7c35ec |  | note | Position: Site Engineer
date | 67d2f95c-cfd6-59d5-8f48-f1c12f52651e |  | date | Date:
holdpoint |  |  | signoff | SIGN
checklist-sectioned |  |  | checklist | ITP - E3001 - SH05 SIP Generic - Pavement Construction incl Culvert Extn | itp |  |  |  | Yes | ITP - E3001 - SH05 SIP Generic - Pavement Construction incl Culvert Extn V2 | 466f43bf-47cf-454d-8ff3-ce59a4db76b9
checkpoint-group |  |  | section | 1 - Setout & Saw Cutting
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 5eaf96ef-4314-51c3-9f83-46a410df3f49 |  | textbox | CPS Eng.
text | eb8a8ba7-f086-5223-9612-7ac0edbff6f1 |  | textbox | Site Engineer
text | 9a84afa8-eced-5584-ada9-eca26ae76aff |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Survey Setout
label | a327c703-085e-5291-8f76-e7375d4857be |  | note | ACTION (Hold, Monitor, Witness) - M
label | 2e934403-7ebd-51ae-afea-f103c9f552e4 |  | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
label | e9ff245b-7286-5d4b-9839-bb9cc1e28c0b |  | note | Frequency - Prior to commencement
label | 479d5542-d8cb-56ee-a74b-93ed89cd546b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | aaff4b60-b2b0-5ec2-a86e-65984f21282c |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 1.2 - Saw cutting
label | af8e8bf1-aee7-5314-84ec-67565e76df60 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a17ca7eb-a599-5e81-aed6-08c529d3ce7d |  | note | Detail - Proposed Sawcut line to be inspected by the engineer
label | bb0712ce-9ca7-52a5-84db-48293a9c2f69 |  | note | Frequency - During construction
label | 39cbab90-9b5f-5d75-bac9-3714bbad40c2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 264e3216-1680-5f8e-9fb8-6573a7657f9b |  | note | Conformance Criteria - Project Specification 6.6
label | 49fd88d4-3a20-5afd-a98a-abddfef0b226 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Material Compliance
checkpoint-status |  |  | checkpoint | 2.1 - Sub Base Material Compliance
label | 2a8c3ff1-c437-52b2-bfed-50738f176076 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f0af23a2-65bf-504d-977d-dcf88525ee1f |  | note | Detail - Aggregate material compliance for Sub Base stockpiles
label | 43f666e3-039a-553b-9866-faaec8eb0f49 |  | note | Frequency - Prior to commencement
label | b90dc7f4-d876-5911-9d1c-e3b513dbce91 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 7944c8b5-35d8-5348-8436-7fb5dd10acc7 |  | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC.
label | e720a913-2a22-55b7-ba62-8f8870e5ef32 |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
checkpoint-status |  |  | checkpoint | 2.2 - Base Course Material Compliance
label | 6b6260c8-7793-5168-b343-7f9539bd4124 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 14a42186-465c-5eb5-a26b-f33498e0e989 |  | note | Detail - Aggregate material compliance for Base Course stockpiles
label | ed3c1cb2-3569-56cc-aa60-2f611febf9a8 |  | note | Frequency - Prior to commencement
label | 32f9fcf6-1e06-5390-b6d6-6a946444b21f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | d5ee02ab-6a30-51d8-bd3b-03e9eae098ef |  | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
label | dc94aa75-d136-503c-86bd-264aa84ff144 |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
checkpoint-status |  |  | checkpoint | 2.3 - Concrete Pipes
label | e18f87a3-ee2d-5531-9690-8c38700cf570 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 12c6dbe7-22e4-5d41-8f7e-151478f73434 |  | note | Detail - Specification Compliance
label | c3398cf4-48d3-53cf-bbea-dd08600a5a85 |  | note | Frequency - Each delivery to site
label | 94e12109-2f98-54a3-b1ac-afe2e119dd95 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
label | f4a57f3f-30b3-5a09-ba4d-1791ac9a6980 |  | note | Conformance Criteria - All concrete pipes shall comply with the requirements of NZS 3107 "Precast Concrete Drainage and Pressure Pipes".
label | fb7e03e4-3874-568c-9c50-1f7f1f7bd425 |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 2.4 - Pipe Bedding Material Compliance
label | 45c2faaa-1cc5-5c8f-8d2e-f5075d861d90 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 97f80f13-4bc9-50cd-9bb0-6cf77668d9d2 |  | note | Detail - Material to meet specifications dependant on material type selected
label | 5c7b252a-7c35-5ff5-bc78-9fcc54b5ab2c |  | note | Frequency - Each material used
label | 77456db3-b046-553c-996d-94d7cd62810b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 14f0c562-51bc-5f3d-8b48-55f4e8fb144a |  | note | Conformance Criteria - Compliance with requirements from Specifications
label | dcb5452b-0c64-5900-b8ee-47fe2c628d2b |  | note | Records - Lab Test Report
checkpoint-status |  |  | checkpoint | 2.5 - Pipe Backfill Compliance
label | bd71a89c-0d9c-50f1-a142-0f251eb51d48 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 81c61c7b-7b32-5881-8b31-85985c49a6ee |  | note | Detail - Material to meet specifications dependant on material type selected
label | 6924d00f-d2c6-5b6e-935b-c07aa745c786 |  | note | Frequency - Each material used
label | 8c1aab0d-c47a-54ad-93c4-02391d673db7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | bba74deb-b5ee-5e58-b330-cdf1bd3a0fa0 |  | note | Conformance Criteria - Comply with grading specification
label | ba8afc2f-e634-517a-9faa-6719cebb1e9a |  | note | Records - Lab Test Report
checkpoint-status |  |  | checkpoint | 2.6 - Chip Seal design
label | 7141d653-f61e-5e65-8ee1-e4c6cf2f8e7e |  | note | ACTION (Hold, Monitor, Witness) - H
label | daba90c3-9c1d-5493-adc7-0aa6c541e2e7 |  | note | Detail - Seal design to be reviewed prior to sealing.
label | d615fe85-08f2-578b-b97f-10ba6a61eff0 |  | note | ○ Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer.
label | 0c531b49-e418-5649-aafb-165f41a25c52 |  | note | Frequency - Prior to Sealing
label | 5948742b-e801-502d-823d-0030621557d8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 5b6b7248-0e3e-576c-9780-d7ea1662327d |  | note | Conformance Criteria - The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995.
label | 8b778e6c-0702-535b-97fa-c9b87151ca2a |  | note | Records - Emails/NTE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Sub Grade Construction
checkpoint-status |  |  | checkpoint | 3.1 - Sub Grade Strength
label | 6da4f943-ed44-5248-b125-a8138ae14835 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7ae36348-7b5b-5809-84a6-ad818a7b53e5 |  | note | Detail - Determine Bearing strength of Sub Grade
label | 9f3df29c-d1a6-50e8-b30f-cd6a8c38ade9 |  | note | Frequency - After Dig out, every 10m
label | a6c2692a-a6d5-5048-8e7b-358d61167c0e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 0669672d-7551-55d5-b87a-73cedecc637d |  | note | Conformance Criteria - Min. 2 blows /100mm
label | 77774cb8-1dbe-51e2-8491-6b21972f37e7 |  | note | ○ 2 blows = 4 CBR
label | ad96bdd9-c4d7-56d9-a5cc-c249aef9a2cd |  | note | Records - QA measurement Sheet, CS-4000 1m Scala
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Proof Roll of subgrade
label | 02a6fab6-b897-5ef0-8131-7f9b29a90f71 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6848d3a6-7bd7-5433-9f5e-ca343e66a3a7 |  | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
label | 2050be43-53f0-50f0-a944-1241417d1979 |  | note | Frequency - Prior to Sub Base Construction
label | ff5f84f7-d1f8-562b-b0e1-dc5e4e478fd1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c8cf295b-8a28-5e8a-82fd-fe210e1c815c |  | note | Conformance Criteria - Engineers Acceptance
label | ac640f9f-79e0-57be-ac63-2111bdb40728 |  | note | Records - Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4 - Sub Base Construction
checkpoint-status |  |  | checkpoint | 4.1 - Sub Base Aggregate Delivery Checks
label | 750ebec3-5826-5019-bdd2-76bb74fcc738 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 16825082-e306-5463-9e9b-738179d634d7 |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | dc5d245e-72b8-5809-8cab-518892dde74a |  | note | Frequency - During construction
label | 7976a289-eecd-5b93-bfb2-7d8cf7823d4f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | e0443362-6eb8-560e-84d1-b500d80a6fab |  | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification.
label | 9e82593e-ae23-5c5b-a87d-f11825e3818e |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 4.2 - Sub Base Material Contamination Checks
label | d2478fe4-5000-5dbb-9d0f-479195678693 |  | note | ACTION (Hold, Monitor, Witness) - M
label | f49750e8-8e08-5afd-93c2-a41ef5eaff95 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 0cf51bfe-a5a9-5961-b227-5a72f6ab9705 |  | note | Frequency - During construction
label | 2494f8f1-f3a1-55fb-8672-6b81acc3a31b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c34fd02a-e77c-5f8f-b6f1-970f9f27c8de |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 4.3 - Sub Base Trimmed Level Checks
label | bbb7fe81-b8a9-5137-8051-029aecbd9146 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e20dd6ef-75da-5e34-811b-c8b15907e95b |  | note | Detail - Carry out a Level Check on the trimmed Sub base
label | c7a22507-4e88-5871-a565-92f8fc1f3047 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | e84acccc-ceee-50b3-ad3b-11c28a142a25 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | ba4b7aa9-4117-554c-8fd0-faed860d4946 |  | note | Conformance Criteria - TNZ B/2 Tolerance = -25mm/+5mm
label | 8deaceaf-cf49-55d0-88fa-8e0fedfcf84d |  | note | Records - QA measurement Sheet, CS-4100a Subbase Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Sub Base Compaction Lower
label | 1a2a17e2-01d1-5e4d-96e4-ea4dc2192782 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7822b78a-b01b-5af9-a3e1-77c5b247d3c4 |  | note | Detail - Degree of Compaction.
label | 9aa73e5e-813b-5307-804c-23f7b6b1995a |  | note | ○ The subbase shall be constructed in two layers.
label | 6fd37884-d8f4-53fc-a590-0c091e8faf3c |  | note | ○ Lower subbase results must be approved before construction of upper layer.
label | 36c0306e-f542-51bc-b547-d92addeb1de6 |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | 2caf7788-df59-5bd3-82fa-b0b35bbc5775 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | 754ec960-82dd-588c-8a08-c007e6a39b30 |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | daf1d0f2-95cb-5f14-83d9-4556cc5e577d |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Sub Base Compaction Upper
label | 492a1cca-0cb8-5ef1-855c-34c84ec92dc9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 444f0157-c8ad-5d14-a257-2c7004bcbeba |  | note | Detail - Degree of Compaction.
label | 3f95f327-68f0-5374-8e20-69baa4fb9510 |  | note | ○ The subbase shall be constructed in two layers.
label | 4011a8e7-e723-58ca-84fe-b429afa87a4e |  | note | ○ Upper subbase results must be approved before construction of basecourse.
label | 6e712283-22db-5cfb-9a1f-a1d627dc73c1 |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | 0aa83a10-ed8d-5b91-8882-7036d07a7b67 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | 2f606761-eac4-581a-8029-71cb66dfa5d1 |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | 81ca589f-fa8e-5310-88ca-71a77ec549eb |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5 - Base Course Construction
checkpoint-status |  |  | checkpoint | 5.1 - Base Course Aggregate Delivery Checks
label | 0772191b-7f19-58d2-94fa-6d90443d2b76 |  | note | ACTION (Hold, Monitor, Witness) - M
label | f2d64243-230f-5e6e-85b3-2c3ca5bf1582 |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | ac23a20c-d36d-5e1f-9dd3-f8c0f59da4d2 |  | note | Frequency - During construction
label | cc812f2d-cd46-5b53-80f8-ba78ed98564f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | efd5e964-acc1-58fc-bfde-bf2c7c47fabb |  | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
label | e012b8ab-c0fa-568c-a74a-2e5d991fa9a9 |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 5.2 - Base Course Material Contamination Checks
label | 00924602-560d-56d4-a2db-b7d452d599c1 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1d7e339e-0819-5061-a6b0-dd0e71fe9a1e |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 56708092-193b-5039-a5af-5d1d71ae2fca |  | note | Frequency - During construction
label | 9b9b8925-2062-59b3-8e3b-09fb2864f924 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c5076003-747e-577e-bfdf-190979f5172c |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 5.3 - Base Course Trimmed Level Checks
label | dfe83787-9637-5c75-991a-d25b77dbe45b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1c28a6cd-7ea8-52ee-9330-ceabb6ae0325 |  | note | Detail - Carry out a Level Check on the trimmed Basecourse
label | f584e00d-55e7-51e4-af82-78a4a20431a8 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | b3a249c6-d695-59aa-a5c7-cc6006f6aa19 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | ed407575-8c65-556b-9e1f-564b0c09adaa |  | note | Conformance Criteria - Tolerance = -5mm/+15mm
label | 8ffc541d-8b9f-5390-b2ac-d9168fbf9852 |  | note | ○ if constrained (kerb) Tolerance = -5mm/+5mm
label | cde82869-37d8-57da-b71f-4e40ac9c477d |  | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Base Course Compaction
label | a0ada81b-16b1-5e14-9d23-7ad45b9845ef |  | note | ACTION (Hold, Monitor, Witness) - H
label | f9641131-5270-5435-8310-f616117a381d |  | note | Detail - Degree of Compaction
label | 1573ccad-0a0f-5da4-a6f5-8690af76728f |  | note | Frequency - 5 per Lot
label | 8d475302-e142-584b-a85b-1de3ad4cb850 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | 14ded284-de5f-5657-88af-0f64908b785f |  | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | 3c812792-602e-5392-bca9-45820752b78c |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Base Course Surface shape check
label | 960b0fb5-cad2-5880-b8a7-f32323baea14 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8a919f01-7cce-5a87-b390-0e44d9ef3fdb |  | note | Detail - Surface shape check
label | 0052f421-f971-5292-bd73-fdf22a7ef3c4 |  | note | Frequency - Prior to sealing
label | 203cfeb6-cb7d-5e6a-b5de-e7f8239b01a6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | f7bd6331-a35e-5fd6-9e35-7934927ca97b |  | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | 52c6be31-0f19-5580-9c91-533e3160d1cb |  | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Base Course Surface finish check
label | f9b075ae-23a5-550b-84c4-664fa5ad8ccc |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2dcc09d6-2fbc-5364-9e42-4485b5b88a58 |  | note | Detail - Surface finish check
label | 6fffd42b-c3b6-5c80-bf40-775f44f2b679 |  | note | Frequency - Prior to sealing
label | 3f00703f-b254-5468-af17-b05e0384f2bf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | 3b0260df-6d16-54ba-8f96-06af05ac97fc |  | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | c4718534-551a-547a-891a-3d199aa89730 |  | note | Records - Site photos, Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6 - Extension of Culvert
checkpoint-status |  |  | checkpoint | 6.1 - Foundation Compliance
label | 45be92dc-8806-5427-8e2d-a61bb1a803a3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b27544d3-1dc4-581c-986d-97f3f6c4d77d |  | note | Detail - Test formation level on completion of excavation to check if undercut required
label | 797a5bab-64ed-5ebd-b1a6-d550e665a434 |  | note | Frequency - One test per 5 linear metres
label | c7b969e6-eaf2-52df-a98c-14a744769917 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
label | aef78195-05bc-5d9f-8e8a-9bd0c23c2d46 |  | note | Conformance Criteria - Min. 2 blows /100mm
label | 98cdcf13-72b3-53bc-bb1f-137930572c63 |  | note | ○ 2 blows = 4 CBR
label | 889981e6-d9a9-565f-8fca-5bc6e70dcf22 |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 - Levels Compliance
label | 0e2b22cb-6aef-5430-b39a-5a96de8d206f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6059d5df-b1a6-5ee1-bef0-1a05ae073aa9 |  | note | Detail - Inspect formation level on completion of excavation to check if further excavation is required to achieve levels
label | f562a4f2-6922-5d86-8de6-961416598880 |  | note | Frequency - As stated
label | ae8b43c7-1d00-519f-b37c-25dab3bcf642 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 608cd521-7adc-52ae-a207-f12c90b70182 |  | note | Conformance Criteria - Designer to inspect formation level at outfalls / inlets.
label | da79f9b2-1ded-5f99-91cd-3d12e814d437 |  | note | Records - Photos, Visual
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7 - Sealing
checkpoint-status |  |  | checkpoint | 7.1 - Location/Size Confirmation
label | 55e08f24-1e4b-5d9c-be07-45d63498b79b |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9ecb35f0-62f4-50f8-9937-62d87be0acf9 |  | note | Detail - Mark up extent of Chipseal
label | 68db4614-41ac-53dc-a59b-50603435e345 |  | note | Frequency - Prior to Sealing
label | 49ed456f-5ee1-5ec2-839b-93fd0b4509fc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
label | 606927db-485d-576b-84a1-99605c8ad3f0 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 7.2 - Surface Cleanliness
label | 1bcf7106-ce4b-5321-98b3-26d13274b4f6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6b72b169-48d4-5935-a1f0-a6d9a1e5dfce |  | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
label | 630628cf-6b4c-5690-82bf-7ddba21ca546 |  | note | Frequency - Prior to application of binder
label | e3244862-29af-5af8-935e-3048754b079c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 2fe5ae57-bfb7-52f5-b56d-f1bf26b8e8cd |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 7.3 - Binder Application
label | 8fc402e7-21cf-502b-9e5c-150d090f97b1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | aca03926-84bb-5f6e-b782-e646503ae1fe |  | note | Detail - Ensure the Binder application is according to the seal design
label | 6654e618-64cb-5483-a29d-c43214056299 |  | note | Frequency - During sealing
label | b2aba300-f0b7-5f09-a1b5-aaa16153b7f2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 7289c1c3-55fb-55fe-8f86-ef8340775f63 |  | note | Conformance Criteria - According to seal design
label | f62cabb9-28a2-5a13-bac4-69086d8820f2 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 7.4 - Chip Application
label | c59768f7-979c-571a-911c-7d8177946b91 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1cde60dd-1b29-59ad-849d-7466a299c173 |  | note | Detail - Ensure the Chip application is according to the seal design
label | 24668de1-5505-55d6-9021-9099a8de0441 |  | note | Frequency - During sealing
label | da92bd03-998a-5a39-8230-894cb3f44542 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | bf968687-d8a1-578c-b698-5f8df0dd1f42 |  | note | Conformance Criteria - According to seal design
label | 02d6a1aa-bb79-5ec0-9e8d-a0cc5916f006 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 7.5 - Compaction
label | a239f1d7-efaa-5ab2-b804-52788389a8a4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a389fb1b-0761-5cf4-a645-7055cd1806d3 |  | note | Detail - At completion of rolling
label | fa1cbf5d-98f5-5ad9-be59-95901da3904b |  | note | Frequency - During sealing
label | 8e557790-feac-5f84-b8e2-4e53412f0a5d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | f03ac157-d2c7-51e5-8d8f-d6fbdded7dc3 |  | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | bf719e1b-6fcf-5636-afd2-54c82a6259f6 |  | note | Records - Photos, QA measurement Sheet
checkpoint-status |  |  | checkpoint | 7.6 - Removal of excess chip
label | 4834dd61-983c-5bed-8f13-b10937d9dba0 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1407b561-6856-5e0a-9d85-113220284617 |  | note | Detail - Removal of excess chip
label | 8dd17909-414e-534c-8936-334525b8f346 |  | note | Frequency - Within 48 Hours of Sealing
label | e2c30be3-b24f-56c9-9612-1f85bf8d09d1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 905bd7bc-c118-5c94-8005-a6401a5b5100 |  | note | Conformance Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | 82ff8530-8763-5d12-b66f-782aa3c6c8a7 |  | note | Records - Photos, Site logs
checkpoint-status |  |  | checkpoint | 7.7 - Surface finish check
label | 2dea07ed-a233-5107-a8d2-320baf3d9ca7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 82156e54-aeb5-57a7-97c7-55bfe1f39781 |  | note | Detail - Surface finish check
label | b641dec9-2a5f-5cfe-a0e1-2a0fd9b89d0a |  | note | Frequency - After sealing
label | c2e31100-0f81-5b00-9a39-69146fb84c0d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 26806c68-067d-5216-bcb7-b3268a370267 |  | note | Conformance Criteria - Engineers Acceptance
label | e1a7bfdf-97bd-527f-b3db-d12009b1b569 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 8 - Road Marking
checkpoint-status |  |  | checkpoint | 8.1 - Road Marking
label | 7948cc8f-6d46-5536-b77a-8a3956ce71e5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | bd5a1ede-71e5-59b7-9294-4bd1851cbc80 |  | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
label | eb713895-21a2-5c41-ab4e-9bb0c40bc96c |  | note | Frequency - Prior to the final line marking
label | 19ab4798-0e0f-58d5-89ed-1c3c095b43c9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 19c31483-9a4e-56e2-ac94-03a703cb092a |  | note | Conformance Criteria - Engineers Acceptance
label | 49c95b7a-cd66-54d5-ae1c-5ceb4d26aa17 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 9 - Hydroseeding
checkpoint-status |  |  | checkpoint | 9.1 - Hydroseeding
label | fcf8aaef-026e-5b9f-97e4-253efba6fc98 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d7cea0e9-ef80-5992-824c-85b2b44e012c |  | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
label | bf1d6a3c-9f59-5a8f-a2e8-69c9e5dbab22 |  | note | Frequency - At the completion of the Lot of work
label | 407258fe-f443-52ff-b1f2-7fe5993c18c6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | e00d4925-9bf1-5fba-a9c7-6e8c63ff19d6 |  | note | Conformance Criteria - Engineers Acceptance
label | 8dc2e0f2-b37c-5cc0-abfd-9ea5abf664be |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 10 - Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 10.1 - Final Walkover (Snags)
label | 982ff868-c2dc-5490-8bc2-67f7bad93854 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 654640ab-95c1-53b3-b22e-df1313e2a73e |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | 1ea94dee-7077-5903-bd4e-ad811867b177 |  | note | Frequency - At the completion of the Lot of work
label | 6aea82d3-d905-56eb-beb2-fb213708a934 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | bd2deeb8-ece0-59ea-a3aa-cdc98ff854c9 |  | note | Conformance Criteria - Completed report
label | 1a35418b-9150-5fd0-afe9-1c25026c59ad |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.2 - Survey As-builts
label | 5fa849e6-ff29-5444-a20c-1d6c6b055be9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9f3f221b-0d43-5f59-852a-e6be3f9a04d7 |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | 70bcab5e-2444-50a1-8c5a-9309b58e50b1 |  | note | ○ A survey as-built of completed work must be provided
label | a61a8f18-38b3-56c7-b898-2fbb816415da |  | note | Frequency - At the completion of the CWP of work
label | 6696f226-c05e-5b52-996c-7c6cb8ef6788 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | cfdffd97-8bc8-5110-9bf4-51bd7c641ce8 |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | b6896e51-ee19-577f-9d69-28578241d0cd |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.3 - Quality Assurance Deliverables
label | 2b200a92-58ff-531c-82bc-864915f65f49 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6d9a762f-49ad-5f0d-b927-6c501348f290 |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | 6dc7d01b-418b-535a-b225-a18817c22999 |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | 72e06a66-74d4-50e9-93f9-667a3483d7f5 |  | note | Frequency - At the completion of the CWP
label | c216d9a2-e74b-5efb-83bc-dcc963c463ee |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 28497fbf-1038-50e0-a395-6e4fbad63998 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 8b89c2d8-45c4-5a79-9258-621c7893e9aa |  | note | Records - As-builts, NCR's and RFI's
checklist-flat |  |  | checklist | ITP - E1401A - Captain's Culvert Inlet Remediation - Gabion Basket | itp |  |  |  | Yes | ITP - E1401A - Captain's Culvert Inlet Remediation - Gabion Basket | 4691bc5c-891f-4887-aec2-a2dbd86e25da
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 88038049-386e-5235-ad1b-16cfd9267b0d |  | textbox | CPS Eng.
text | 6bf43416-0a02-5aa5-8b89-57c19b956e19 |  | textbox | Site Engineer
text | 15889b4c-22ce-59a1-b238-8df09be77574 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 5c8049c2-f071-54ab-9108-8575c9cf4172 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 158b0a3d-d62a-57f3-ae28-c24c58730302 |  | note | Detail - Set out the base of the Gabion basket
label | 46b8bd94-a1b1-5f23-ad96-4eddd38dd67e |  | note | Frequency - Prior to commencement
label | 349dd400-1b48-5944-a942-13ef676616a1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Markout
label | 2d2282e0-9422-56b8-8d1d-1d8769d6155a |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 99536bd5-2113-553a-8d14-be6bd0ef4aa5 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 2 - Procure Gabion Baskets Materials
label | fc512c57-614a-5e73-ae26-9ebafc3c9a42 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 15f8e314-785d-5c97-8d81-c2bce7e0a499 |  | note | Detail - As per Project Specification
label | 5750a604-a004-5c3f-8971-3463198eeabf |  | note | Frequency - Procurement
label | 182b68be-2da9-5ab9-b6c2-f95513018b98 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 9642bbc0-9e9c-5df8-9503-c7f5a3c8f296 |  | note | Conformance Criteria - Zinc aluminium, plastic coating mesh size, selvedge wire Stainless steel rings
label | 30b4a683-cb2d-534e-a8a9-9b01072c0363 |  | note | Records - Product spec sheet
checkpoint-status |  |  | checkpoint | 3 - Gabion Baskets
label | 84905685-7d6d-598d-b5e2-d67a842c3de1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 136b89fb-bd9f-51bc-a975-b1c3140ce45f |  | note | Detail - 2.0m x1.0m x1.0m Gabion baskets
label | b00336e7-160c-5461-901b-2f9bb8968ec8 |  | note | Frequency - Prior to commencement
label | c890f85b-f63e-5180-92c0-d73139ffa9e9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | 4af74f12-fb4a-54f9-b597-bbea846793d6 |  | note | Conformance Criteria - Any defective baskets are NOT to be used in the wall construction - return to the supplier immediately
label | cfd71625-516c-5cc0-a974-bf6ab58dcc35 |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 4 - Gabion Rock Material Diameter
label | 71c2601b-fd8b-5794-b51e-0b64cc8dd171 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5ce8739c-c5ce-5e78-a891-a7aceaedb549 |  | note | Detail - Rock Infill shall be 100mm minimum and 250mm maximum particle size based diameter
label | 5bab5ed9-f907-5399-83da-d494fc5bb060 |  | note | Frequency - All material used
label | 339f5c44-836f-57dc-96a0-5d4f8386429d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | 4c39975a-8501-55ad-9a6d-601b97704bfc |  | note | Conformance Criteria - Compliance with requirements noted on bulk fill checksheet
label | 57b1a05e-f399-55aa-98b7-34be7c6d7999 |  | note | Records - Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Excavate Base of Wall
label | 6296eea2-015e-557c-9028-50f8a1e54ae6 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 56b863db-78c9-51ff-83a0-62485b32e0f3 |  | note | Detail - Excavate footprint of the wall area to the correct line and level and ensure area safe to work in.
label | a4e62e38-3266-5530-8151-b0caf50f4804 |  | note | Frequency - As required
label | b0e1e4dd-311c-5e93-80fc-2113d5570afc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 9a03ada4-0569-5ccd-9be1-a784a7b4007a |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 953ad28b-e67f-5b3b-9442-925f1d0e6213 |  | note | Records - Survey Receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 -
label | 4a27e0c1-173f-5c77-b8f5-f016bb1ddbb2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f8433124-4fba-575a-bd32-5d40b762a3ee |  | note | Detail - Base of excavation to be checked by Geotech engineer / CPS Engineer
label | 2085a4ce-8fc4-5de2-a509-31157df6f7e9 |  | note | Frequency - After excavation
label | e27d4ce9-82e1-566e-9ccb-9b8a91ff223f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 51708661-e814-5b76-b8a7-188b506e4b33 |  | note | Conformance Criteria - Confirmation from the Engineer
label | 379c70a7-b381-561f-a2a3-1dc1de66e290 |  | note | Records - Site visits, Photos emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 -
label | adc9ba18-aa73-5d9f-b0fe-c1723ebba26f |  | note | ACTION (Hold, Monitor, Witness) - H
label | beb51646-5392-52b3-935a-3cfc073eb511 |  | note | Detail - Clegg Test the base of the excavation after placing 250mm AP65.
label | 390c2346-1988-5999-a654-3d360d9c25bf |  | note | Frequency - Prior to construction of wall
label | ab1c2c8f-4058-58bb-a0ca-bd372727eef4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 528f72d7-1e93-5656-9f96-3d613f36a8a8 |  | note | Conformance Criteria - Confirmation from the Engineer
label | 40aadb68-a255-5f1f-8c35-9541d1b19b50 |  | note | Records - Lab test result
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Subsoil Drainage
label | 231b1c49-c619-5976-b8e0-a0dc8042a5aa |  | note | ACTION (Hold, Monitor, Witness) - H
label | e9b2ea33-d19c-5b8f-8a2f-c5b43fd03485 |  | note | Detail - Subsoil drainage is required for this wall construction then follow the ITP for Subsoil Drainage
label | 6ccaf676-2f40-5c70-8979-b5beacfac806 |  | note | Frequency - Prior to construction of wall
label | 7a330f9d-24e0-5693-93de-5a66fd6426af |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | b46eceec-b4d1-52df-b0c9-6fde0a0003b9 |  | note | Records - ITP Subsoil Drainage
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Construct Wall
label | b1849d0f-bd14-5308-a62f-4c2adbee2239 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f9ed5fd2-ac68-577e-9e2e-a2d4c71253e5 |  | note | Detail - Erect the first level of baskets as per Manufacturers specs along the front face of layers to ensure correct line and level.
label | 63f20618-9a4c-5455-8e4b-98e0cb51ffa5 |  | note | Frequency - As required
label | df5a02df-016f-5da1-8950-e46f1a2b8786 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | fdb5f37d-90d7-5c50-86ca-5ba344df11a8 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 10 -
label | 02cffe05-5f77-5cc7-a189-7e1416d3721c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7841951a-f8d3-5ea8-a566-3f95c6338f4b |  | note | Detail - Tie the first layer of baskets together using Manufacturers specs for tying baskets
label | 4c96a861-2409-59fc-8dfa-4db69d630274 |  | note | Frequency - As required
label | 20a32742-3ebd-5245-9d0f-41c7e20f26ec |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | df5c5bce-ceb1-5bc9-8b13-5511730fee43 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 11 -
label | 2e49c378-998a-5b42-8993-77963177a921 |  | note | ACTION (Hold, Monitor, Witness) - W
label | adcfb548-c0b1-5384-a292-d0cfa5631d0a |  | note | Detail - Place Gabion material into baskets ensuring the outside facing the flat side of the bigger stones are placed by hand to ensure that the baskets are kept square
label | c5422e21-26a4-5eca-8678-9dcaa678dfbf |  | note | Frequency - Every basket
label | 8566bbea-9248-5163-8720-62182e9bac90 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | cc40c03f-4f4b-5a47-b257-64b597953b2a |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 12 -
label | 589a2719-0f76-5fc8-8ac4-b0c525e42fe3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1046e7d6-3534-5b65-bfcb-5ed6a0d70eb7 |  | note | Detail - Tip Gabion material slowly into the baskets to fill the voids as much as possible
label | 71a9c15d-ce82-512a-9f1f-8e6110fa756f |  | note | Frequency - Every basket
label | 1249575f-a386-50ce-9c2c-840c97d72714 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
checkpoint-status |  |  | checkpoint | 13 -
label | 740353d8-a1e9-5da7-a2a6-c034561dc361 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4e94aded-9ff1-5b50-9802-8249043a2e4c |  | note | Detail - Ensure line and level of front face is as per design
label | cedcd934-4e27-5fe5-9bd0-0d2171b21a26 |  | note | Frequency - Each Lift
label | a7d4fa53-d1de-5884-9c59-d5921a972ac3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
checkpoint-status |  |  | checkpoint | 14 -
label | 8bb2b955-c0ef-5977-b1e8-4d8cdae686dc |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2c21d2eb-b356-5975-ac0f-3e83b44c5b6d |  | note | Detail - Tie next layers of bottom to the top of the previous layer to ensure that they wont move when rocks are placed inside & complete the basket filling process again
label | 5900e065-b9e3-5121-8a9d-22f36fcdfbee |  | note | Frequency - Every basket
label | 5a9f4fec-ab25-5ba4-9838-0a9d3444d589 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
checkpoint-status |  |  | checkpoint | 15 - As-builts
label | 5a12d48d-92d6-56cd-946c-f89cc86463c1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 527768ab-2f84-581b-8ce6-9166770a5d79 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 94761c58-872b-50bd-907b-80127912bd97 |  | note | Frequency - At the completion of the Lot of work
label | 5121cab5-2b3c-568b-be5b-13e7ad97bf71 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 15546a3f-096d-5aa5-af66-c617be8d5709 |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | CS-4041 - Bearing Installation Record |  |  |  |  | Yes | CS-4041 - Bearing Installation Record | 46fc521b-5106-434a-80e0-8612e9d7b49a
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | 83a7191d-9cb6-5bce-9db3-e15e985e4989 |  | textbox | Project No.:
checkpoint-group |  |  | section | Pre – Installation
checkpoint-status |  |  | checkpoint | Abutment/Column surface level survey within tolerance
text | 682b1f9b-a099-5cab-90b9-b141eea9367a |  | textbox | Initial:
date | 21e7520b-5050-5e25-be92-ddcd6795baa5 |  | date | Date:
checkpoint-status |  |  | checkpoint | Bearing pockets cleaned and free from debris
text | a17895ec-ffa1-55a1-8789-8952652ac7a7 |  | textbox | Initial:
date | f8768ec0-0e24-5a1e-9a48-9b58f0c9e083 |  | date | Date:
checkpoint-status |  |  | checkpoint | Bearing pockets in correct position
text | 57fdac7a-f0f7-56d3-bc27-e4010eac8fa4 |  | textbox | Initial:
date | 411a0d46-8eee-5389-a1e2-b825795f2f59 |  | date | Date:
checkpoint-status |  |  | checkpoint | Abutment/Column under bearing surface roughened, cleaned and free from debris
text | 60af7d61-5f7e-564e-9a91-119f3ee07a2c |  | textbox | Initial:
date | 7c027ebc-eeaa-5730-ac49-86e1918d7cd5 |  | date | Date:
checkpoint-status |  |  | checkpoint | Centre lines clearly marked on pier head
text | 7036a97e-e2ca-51c5-9086-0131972da083 |  | textbox | Initial:
date | dc2e32a0-f37b-5858-854f-83fcaecfaebf |  | date | Date:
checkpoint-status |  |  | checkpoint | Plastic shims positioned and levelled correctly
text | 19153599-68d5-565b-9af7-73da924318d0 |  | textbox | Initial:
date | ea4b27ef-551d-5634-a42d-7ba74552bc87 |  | date | Date:
checkpoint-status |  |  | checkpoint | All GEWI bars firmly attached to bottom and top, plate and anchor plates fitted using RIC500A epoxy mortar
text | 56f8b08c-27be-5794-99bd-d5997af5093b |  | textbox | Initial:
date | a5683698-75e5-5cf3-82c1-034d705cb9ce |  | date | Date:
checkpoint-status |  |  | checkpoint | Approval to lift and position Bearing Unit
text | 735cfa0d-4667-550f-883d-8bd0d95a2829 |  | textbox | Site Engineer - Name:
date | 96daccc7-5f84-50d3-b6cd-2c5463b2532b |  | date | Site Engineer - Date:
holdpoint |  |  | signoff | Sign:
checkpoint-group |  |  | section | Post – Installation
checkpoint-status |  |  | checkpoint | Top of bearing level checked on all corners
text | e836322a-6467-5047-8b1d-2e1707ae76e1 |  | textbox | Initial:
date | 269451c1-7273-5fc2-9bca-db4476d604cf |  | date | Date:
checkpoint-status |  |  | checkpoint | Bearing orientated correctly (B o/s North G,H o/s South)
text | 9f9964f9-61eb-5b8a-afb4-d9a8d25bd5a7 |  | textbox | Initial:
date | e0588156-37cf-5948-bc57-cb0708e93492 |  | date | Date:
checkpoint-status |  |  | checkpoint | Surveyed centre line of bearing within tolerance
text | 86581710-a0bd-5bdd-a75b-ccf6581bc8c5 |  | textbox | Initial:
date | ab2fe3ce-0858-5a32-b6bc-eb8f1e8d61dd |  | date | Date:
checkpoint-status |  |  | checkpoint | Sufficient space for grouting under bottom plate
text | 83da8dcb-1049-52c0-887a-aa8f433fe1e6 |  | textbox | Initial:
date | 113a61f9-773d-5459-b5ec-96bc2b243f09 |  | date | Date:
checkpoint-status |  |  | checkpoint | As built survey carried out
text | 248c13ef-6afc-515a-ad86-d5cba8df8d7b |  | textbox | Initial:
date | 8181d87f-866b-5a7d-9eb3-ea74477b793b |  | date | Date:
checkpoint-status |  |  | checkpoint | Bearing covered and pockets sealed to prevent filling with debris and water
text | 204911fc-88ce-5fd1-ac48-b37cb69035a4 |  | textbox | Initial:
date | d8eb7ad5-af2f-5d96-a313-208428e0c344 |  | date | Date:
checkpoint-status |  |  | checkpoint | Bearing completed & approval to commence given by Design Engineer
text | fa42f8a8-5717-520e-8f09-3dc59ffd589b |  | textbox | Site Engineer - Name:
date | 37c2d89b-ffd5-582e-aec2-5aba7c05a187 |  | date | Site Engineer - Date:
text | 81f42388-a435-589d-b6c6-2019ec68a8f5 |  | textbox | CPS Engineer - Name:
date | e7371299-0dc5-5515-88f4-0ae62f9452a5 |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | CS-4099 - Watermain Disinfection Checksheet |  |  |  |  | Yes | CS-4099 - Watermain Disinfection Checksheet | 4a54b130-9546-48ad-b300-6c1bcd69f539
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | Details
text | 3f2308a4-c998-571b-b054-0dc5ff2f8f63 |  | textbox | Work Area(s):
text | 68938c0e-10f4-5da1-b2f4-1816fac15257 |  | textbox | Sub Work Area(s):
text | df2608d1-ca5d-5811-9c2c-48752ccc601f |  | textbox | Lot(s):
text | d68165fc-a55a-5831-8613-5d73d17d53b3 |  | textbox | Sublot(s):
date | 2832b049-fab3-5bce-b62f-d6a47f51dcf4 |  | date | Document Date:
text | 52ec5eb5-4b34-5704-ae29-f4b62f73a21d |  | textbox | Updated By:
checkpoint-no-status |  |  | checkpoint | GENERAL INFORMATION
text | de1b5769-42f3-5d9e-89e0-608f73eeb4bd |  | textbox | Contract No. or Resource Consent No.:
text | 8fd22751-16c8-5ad1-893b-262edbacd498 |  | textbox | Contractor:
text | ab99772c-964c-5248-895a-33bf2495f041 |  | textbox | Site Supervisor:
text | 10eb0496-3ae9-55e9-9717-8943b581b137 |  | textbox | Site Location:
date | 6e12b559-3a5c-5e26-acd7-2acbc0aefe58 |  | date | Date:
text | ae6ab4ec-2a3e-5da0-91fc-a0a79d239a3b |  | textbox | Time:
text | 50afeceb-b559-5299-b709-084381f6342c |  | textbox | Pipe ID:
text | e3e92790-e967-54cf-8ee4-0a9978fc665f |  | textbox | Chlorine Type Added:
text | cdb93f53-69cf-5ddc-9f16-3b393bbd51a0 |  | textbox | Pipe Diameter:
text | acb19b0b-a431-547c-96bd-02ac9a6c74ce |  | textbox | Pipe Length:
checkpoint-group |  |  | section | TEST RESULTS
checkpoint-no-status |  |  | checkpoint | Table 1 Acceptable Laboratory Test Results
label | 1b5ae033-337c-55af-912d-a0610c5850ec |  | note | Parameter ¦¦ Acceptable Value
label | 88e38055-0564-5d43-8101-88870bdcf897 |  | note | – – – – – – – – – – – – – – – – – – – –
label | f102dbe5-dcfe-5e11-94e5-0e814b4177b4 |  | note | Residual Chlorine ¦¦ Between 0.5 and 1.0 mg/l
label | 2c86e7b8-7168-5d71-bee1-67b96b65f7aa |  | note | Turbidity ¦¦ <1 NTU
label | e2304e94-ff84-5a38-a3cb-cbaa8867949e |  | note | E. coli ¦¦ <1/100ml
checkpoint-status |  |  | checkpoint | Test Point (1)
text | 898d7427-6ca9-58f1-82fc-c6e2bba5f0f9 |  | textbox | Test Point:
text | 6b6a537c-be9b-5a23-9f14-9fdbd91b6368 |  | textbox | Initial (mg/l)
text | bcf1c549-6474-5255-af0d-1d317a0d0202 |  | textbox | 24 Hours (mg/l)
checkpoint-status |  |  | checkpoint | Test Point (2)
text | a54d1428-dc89-5542-ba2a-1d7a4b04a79f |  | textbox | Test Point:
text | f37689ba-9b65-59c1-a88b-7c96194720ab |  | textbox | Initial (mg/l)
text | ed9afa36-14ff-5dbc-8ab7-c9822ced7d0e |  | textbox | 24 Hours (mg/l)
checkpoint-status |  |  | checkpoint | Test Point (3)
text | b87e528a-442e-5d6c-a956-e90e66c4466f |  | textbox | Test Point:
text | a1585fce-29cc-5a6c-8520-9395d59a365a |  | textbox | Initial (mg/l)
text | 71040a08-155e-508f-9c4d-64bfa3099fb8 |  | textbox | 24 Hours (mg/l)
checkpoint-status |  |  | checkpoint | Test Point (4)
text | 61a5d15e-865d-51a7-abde-6ffa80adf4d3 |  | textbox | Test Point:
text | 3e75e1e3-919d-58e8-af0e-a0211124b2f8 |  | textbox | Initial (mg/l)
text | b7f87fcd-dfdb-5647-857c-19ae1adc3d0a |  | textbox | 24 Hours (mg/l)
checkpoint-status |  |  | checkpoint | Test Point (5)
text | f4e58de9-cbe6-506c-a7a8-b10db0dd9a00 |  | textbox | Test Point:
text | 268347bc-c40f-526b-9eaf-2c9339f85507 |  | textbox | Initial (mg/l)
text | b358cac8-e4c8-54b1-8a58-467d0d2dccb5 |  | textbox | 24 Hours (mg/l)
checkpoint-status |  |  | checkpoint | Test Point (6)
text | 6fa306fa-0689-54e3-a15e-1680ac072056 |  | textbox | Test Point:
text | 3ebfc969-cc42-5672-84f7-595a2fdcf19f |  | textbox | Initial (mg/l)
text | 1b9fabb2-d1e2-57d8-9154-dc687087b372 |  | textbox | 24 Hours (mg/l)
checkpoint-status |  |  | checkpoint | Test Point (7)
text | 1b063779-0cce-5c04-bb85-2565b69fa462 |  | textbox | Test Point:
text | 144a67cb-86f3-50fa-8793-e5935d22d2bf |  | textbox | Initial (mg/l)
text | 980b74a0-cc29-5d7e-afd7-62ce60fbb893 |  | textbox | 24 Hours (mg/l)
checkpoint-status |  |  | checkpoint | Laboratory Results Acceptable (Attach)
text | 864a6465-80d0-5e44-a15b-a587cdf484cb |  | textbox | pH Reading after 12 hours:
checkpoint-status |  |  | checkpoint | Signed:
text | afceeaeb-f7af-50c3-b8a9-f8000e21e5f7 |  | textbox | Print Name:
holdpoint |  |  | signoff | SIGNED
checkpoint-status |  |  | checkpoint | Signed CPS:
text | e1c8f929-28b7-5f4e-955f-0aec0ae5137a |  | textbox | Print Name:
holdpoint |  |  | signoff | SIGNED CPS
checklist-flat |  |  | checklist | ITP - E1401A - Captain's Culvert Inlet Remediation - Master ITP | itp |  |  |  | Yes | Ω (Deprecated) ITP - E1401A - Captain's Culvert Inlet Remediation - Master ITP (old version) | 4bdfc2f9-d444-4927-8bc0-f8f80ec25e59
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 1ada93f4-c708-5341-9c25-0e79dd74edf5 |  | textbox | CPS Eng.
text | 260594a3-bd8b-53a0-b7cc-e383ec9e1b41 |  | textbox | Site Engineer
text | cda3c0b8-07fb-5265-b8ba-76a6c1ab8483 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Environmental Controls
label | 308f647f-f405-57cb-90ea-29ead3c21977 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4c741b73-aa6c-5f22-ab02-80a5b69f6c88 |  | note | Detail - Contractor to ensure all the environmental Controls are in place as per EMP
label | a047754d-53d7-528c-b7c2-f826873f8286 |  | note | Frequency - Prior to commencement
label | f47ed79a-1177-54b0-acfc-a87f70bcc773 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | f8968fe7-2d30-5825-9144-0bd2cf02b8d7 |  | note | Conformance Criteria - EMP
label | 39b6be00-c4c1-50e3-84b9-456b8f618cd4 |  | note | Records - Photos, Site log
checkpoint-status |  |  | checkpoint | 2 - River diversion (Temp) and Control Drop Installation
label | 2b2ed4d8-f9f1-5bd3-b2c1-619a874482f0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 31c3a7e4-53cf-58c5-80b2-32a595e43f29 |  | note | Detail - Engineer to accept the methodology for construction of the Control Drop point
label | 3f49cada-d25a-5112-ad81-d3aebe3cd138 |  | note | Frequency - Prior to commencement
label | 2d921a6c-6bdc-57b2-a5f1-80f1a990f8df |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 51191c40-c53c-52ff-9153-dfb19ea3d8c3 |  | note | Conformance Criteria - Confirmation from the Engineer
label | daacf54e-daa9-5690-bca7-bc1c48f2586d |  | note | Records - Emails and site visits
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 -
label | 846a4bc9-7c53-5ef4-a3a0-d45500ce2111 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 43e3c801-fb84-5640-ace5-a43ce493177a |  | note | Detail - Location to be confirmed with the Engineer
label | fc73a85f-2fb0-5559-a8aa-58cdb8df7c40 |  | note | Frequency - Prior to commencement
label | dea508fd-0810-549e-a9fa-a06d54ff2f71 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Markout
label | a428450f-61fd-5980-bc0b-49899a0f09fc |  | note | Conformance Criteria - Confirmation from the Engineer
label | 7028b2ba-3934-534d-9233-b687978212e2 |  | note | Records - Photos, Site log
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 -
label | 01f17779-e3b7-55e1-9221-3a45fc3dcffb |  | note | ACTION (Hold, Monitor, Witness) - W
label | d0954251-9914-5a97-9f95-09444af97241 |  | note | Detail - Locate existing services by hand digging
label | f31f9438-2b7a-5cff-9bda-ed98e63c2a9c |  | note | Frequency - Prior to commencement
label | f1887144-0642-57cc-9828-bed4f8172da8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | 34d6c3a0-e1e3-5fd1-99f7-cbb12a8f5f48 |  | note | Conformance Criteria - All conflicts have been located
label | ddebdf34-85f9-50db-8d94-ea82b2bd4c72 |  | note | Records - Permit To Dig
checkpoint-status |  |  | checkpoint | -
label | b96ce061-f877-5a6c-884a-d28f98bb78cf |  | note | ACTION (Hold, Monitor, Witness) - H
label | bb683435-62bb-50d2-9131-e47c9a76a60f |  | note | Detail - After regrading, Engineer to determine location and number of controlled drops
label | 0213c11f-9607-5ffd-93b1-3ecb559cc666 |  | note | Frequency - During Construction
label | eaecadab-ea73-5024-ab87-72cf82720bb6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 8e6ef822-d060-5919-b37d-e75fd250a6b7 |  | note | Conformance Criteria - Engineer acceptance
label | eda0c4ab-ea25-53a1-8226-2b10d10a8797 |  | note | Records - CONQA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 -
label | d6517e2f-6b2c-5086-8a58-dced3e927d57 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 13e50283-d676-5dee-8874-2ab24a9b18a0 |  | note | Detail - The engineer shall be notified and afforded the opportunity to be onsite and to direct as necessary as the construction of the control drops
label | 40938287-9705-536e-bb9d-a6d8dc39241d |  | note | Frequency - During Construction
label | 326489d6-deba-509e-a5ef-c5467fe79b07 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 344ee9b2-2ccb-543b-8117-113152249fc6 |  | note | Conformance Criteria - Engineer acceptance
label | cebb7328-ccc1-5668-a6d2-f9cf8b13af92 |  | note | Records - CONQA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Debris Clearance
label | ff08be04-aba9-5ea8-a5a1-06025ad1b55c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 29689732-0e68-5c32-9a07-dd8564b55eec |  | note | Detail - Need to inspected by the engineer to determine whether rip rap reinforcing is required around the inlet.
label | 04c80320-82e2-5ab8-bc60-3916d6aad96c |  | note | Frequency - After clearing debris
label | 53712a70-0902-50ed-8636-23b5ace73a36 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | f53f08d1-d610-59bb-8705-ffd0e0af580f |  | note | Conformance Criteria - Confirmation from the Engineer
label | 87dc847a-671c-542a-b160-5eb07a71d883 |  | note | Records - Site visits,emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Stream and Bank Regrade
label | 46e5f81e-71be-577b-8738-3bf3e1d485cf |  | note | ACTION (Hold, Monitor, Witness) - H
label | b7cb7664-0db0-570e-a505-9254a1516ed6 |  | note | Detail - Location and extent of bund is to be confirmed on-site with the engineer.
label | f258f56f-b7d3-5da3-9668-071c27126f49 |  | note | Frequency - After clearing debris
label | 2db244fd-c4e2-51de-9689-ee8e401a13ed |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 75d4b918-f353-5782-8aed-4bdf88969199 |  | note | Conformance Criteria - Confirmation from the Engineer
label | 014d6792-575a-5cae-af56-a2522ebdd277 |  | note | Records - Site visits,Photos emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 -
label | f9962e4d-16ac-50db-b97e-a3fe42aeb6fb |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5df2bdf2-5251-5ca2-8fee-f801e91ebe5f |  | note | Detail - Stream training is required at the mouth of the gorge with the extent to be confirmed onsite with the engineer.
label | a5aff2ee-2d19-5939-92a9-ba0a42be8165 |  | note | Frequency - After clearing debris
label | f885acac-319d-5177-b9d0-2a6a5b333075 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 4b1b9fd7-8f46-518c-bf85-dc292d95278f |  | note | Conformance Criteria - Confirmation from the Engineer
label | 0d50eaaf-58e3-5f70-a5bc-62d2204bd918 |  | note | Records - Site visits,emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Gabion Basket Installation
label | 68ebc367-49ad-5274-b2d3-7de69440d4ce |  | note | Detail - separate ITP provided
checkpoint-status |  |  | checkpoint | 10 - Subsoil Drain
label | 2584ebfe-eb8e-5b8c-991c-1561262573cf |  | note | Detail - separate ITP provided
checkpoint-status |  |  | checkpoint | 11 - Parking Bay Construction
label | efc15218-475a-5937-a47e-bb830aa5f826 |  | note | Detail - separate ITP provided
checkpoint-status |  |  | checkpoint | 12 - Kerb and Channel
label | 055bd6ab-b59b-5f30-8539-3654ab898d3e |  | note | Detail - separate ITP provided
checkpoint-status |  |  | checkpoint | 13 - Guardrail
label | 893e3bd2-fc05-5a84-a2a2-ee9b5c2db686 |  | note | Detail - separate ITP provided
checkpoint-status |  |  | checkpoint | 14 - Swale
label | 445184a9-2783-54bc-9099-372bfd8e18db |  | note | ACTION (Hold, Monitor, Witness) - H
label | e57d80dc-e54c-5054-b3b3-12bd8a1ffb47 |  | note | Detail - The Engineer needs to inspect and adjust the transition and swale if needed.
label | ffe37c95-8f4b-567b-a5ca-210a252938da |  | note | Frequency - Once the swale is set out.
label | bb9bee5f-9409-581c-900f-b030e8d9eaf7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 90e6506c-1afa-5a8a-9ccc-adc9c740879c |  | note | Conformance Criteria - Engineer acceptance
label | 5d95c1f0-892c-5355-83e1-f7bf8133fa52 |  | note | Records - Site visits, emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 15 - Berm Demolising
label | 36e65d45-034b-5d75-b80c-bea20c0ae497 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c6d65483-6eb5-5015-ae4c-9ba163d5ea25 |  | note | Detail - Final inspection to be done before berm demolision
label | 6354fed4-6e40-594c-871f-08c2157769b4 |  | note | Frequency - Before Diverting back the River
label | ccfba7c3-5594-554b-8e1d-9245228ddbee |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 51627757-8054-58ab-8b2c-ec39f769f3c7 |  | note | Conformance Criteria - Engineer acceptance
label | 6749d0a9-fbd9-5361-970d-234b1fac1da2 |  | note | Records - Site visits, emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 16 - General Planting
label | 18fe958f-e078-5938-a059-cf8577a6b452 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2d43b1a5-fd5b-577b-81f0-4b7beb7eda62 |  | note | Detail - The Engineer shall be notified of any key stages throughout the planting process and afforded the opportunity to inspect and adjust as necessary.
label | 0134c1d2-2741-5af8-8d01-1ebb0c123d9b |  | note | Frequency - During planting
label | 1048f3b2-aa90-55c4-892a-9bc6cfbfbb49 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 14951d1e-de69-5fdd-b6d1-28f767de6b0e |  | note | Conformance Criteria - Engineer acceptance
label | f1ef8259-05ee-58ad-9027-5226bb2f28e7 |  | note | Records - Site visits, emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 17 - Site Clean Up
label | e23ad1d2-3525-54de-81a2-2be3316f8c74 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e5a03010-2248-56d1-8f18-e20e2083cd59 |  | note | Detail - Confirm site clean up is done regularly and all rubbish and trays are taken away.
label | 26fb1c8d-70c4-58c8-9953-1823bccfb9d5 |  | note | Frequency - As required
label | 0c47ddc9-3dc3-528d-bb04-51e4b7f0a29d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 45ac34cd-eae9-5fb2-9684-c5f60c86eca2 |  | note | Records - Photos, Site log
checkpoint-status |  |  | checkpoint | 18 - Lot Number QA File
label | 44a06009-386e-5993-a45e-d083f9ebad82 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 71424502-3897-5a57-86a9-78a6a85ced40 |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | ab2bb467-e49f-553d-8c54-f51f399a8365 |  | note | Frequency - At completion of Lot
label | 66d9fdca-c437-5072-a17b-1ea8f7af6497 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 75509e4e-5b21-5b05-9fe5-915278c192f5 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 811605d6-e438-5d99-a9fe-5a88a4d4e4f2 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Registe
checkpoint-status |  |  | checkpoint | 19 - As-builts
label | a94ae467-f6bc-5303-bde4-a599b8479286 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 925b95ec-9efc-5166-89da-8f5a82865682 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | ff1c8bb8-81f0-543d-9295-ca131fdd87ee |  | note | Frequency - At the completion of the Lot of work
label | 03ef5f47-f8eb-56f8-8f56-3d1c69de8ef5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | dc887fb3-0744-52da-bcfe-bbfb11789200 |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | CS-4077 - Light Column Installation Record |  |  |  |  | Yes | CS-4077 - Light Column Installation Record | 4beeb9c7-0350-43be-b9c6-b88f47167947
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | 873f0c2c-e7b0-5db7-9a44-0f48b1b84660 |  | textbox | Drawing No:
text | f77fdbc5-938a-55fb-a49d-a4213cd0b97b |  | textbox | Pole No:
checkpoint-group |  |  | section | Column Foundation
checkpoint-status |  |  | checkpoint | Confirm Light Pole Locations are as per latest Drawing revision and does not clash with other Services.
text | 89cc4514-c0f5-56b6-abab-4c16f80a3da6 |  | textbox | Initials:
date | f2aab44a-aa76-5a38-a205-19a1d76f2bad |  | date | Date:
label | e932da65-ac31-553b-b907-eaf4aafcf0fb |  | note | Comments: Design Engineer to approve if the location needs to be moved.
text | 4cc2124f-b4ad-5462-b994-af9ba67377a6 |  | textbox | OFI No:
checkpoint-status |  |  | checkpoint | Check Survey Setout and Setbacks are to the dimensions as detailed on drawings.
text | 291a55a4-ea5f-5811-a93f-005253c11caf |  | textbox | Initials:
date | 1a053c7b-cc06-5225-910e-f8a4a31fcb27 |  | date | Date:
checkpoint-status |  |  | checkpoint | Confirm Foundation Type i.e. Ground plant, Barrier mount etc.
text | 107e12ea-b1aa-56ef-99b8-89d6545283fb |  | textbox | Initials:
date | 623c46ae-345c-5615-9889-022bae6f0897 |  | date | Date:
checkpoint-group |  |  | section | Excavation
checkpoint-status |  |  | checkpoint | Pothole existing services within close proximity to the foundation.
text | e708f5c8-7acb-512c-a274-bfd6f362e8be |  | textbox | Initials:
date | 98977842-b948-56c8-a365-91589a87e36b |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure permit to dig is in place.
text | a4fbfc8b-0c2d-526e-af72-d76fcaa2bb96 |  | textbox | Initials:
date | a80501e1-b5c1-5661-a85b-b0112b307d76 |  | date | Date:
checkpoint-status |  |  | checkpoint | Check depth and diameter at completion.
text | 86abfb09-38f8-5acc-b07c-be6871b35ad0 |  | textbox | Initials:
date | 408f05f4-c3e0-5be1-ba59-9f79fc69804f |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure base of shaft is clean and dry.
text | a8ea4779-73d5-57c3-98de-826707de5f26 |  | textbox | Initials:
date | 1e147060-9672-5a76-b7a3-81a72e75413c |  | date | Date:
checkpoint-status |  |  | checkpoint | If fixing onto barrier ensure bolts drilled to correct depth.
text | 4d5c58f2-af6b-50d8-9bd5-d39c2fb52c0b |  | textbox | Initials:
date | 137d5be9-5860-5a83-885c-be9e82995670 |  | date | Date:
checkpoint-group |  |  | section | Concreting & Backfilling
checkpoint-status |  |  | checkpoint | Check the location, orientation, level and verticality of foundation prior to pouring/backfilling.
text | 941e79a3-dd23-5b27-ac25-b981dcec6166 |  | textbox | Initials:
date | c3e85975-0594-5234-9e8d-72b1be25c213 |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure 1 x 65mm dia flexi duct is installed and taped off at each end.
text | baf1203d-2f56-543c-b0b5-63b2c6c2564f |  | textbox | Initials:
date | cd288b86-a203-54c4-9a9f-a252a92d890a |  | date | Date:
checkpoint-status |  |  | checkpoint | Design Engineer inspected the foundation prior to pouring
text | 869da131-1e5f-5d7a-8bcd-e6c082cd48e5 |  | textbox | Initials:
date | 4d4d17b3-e915-5888-853c-c67597e6aafe |  | date | Date:
checkpoint-status |  |  | checkpoint | Order concrete for shear base, ensure correct mix delivered, correct slump, concrete vibrated, dockets collected
text | b301461c-e600-5b00-8602-161c1954a354 |  | textbox | Initials:
date | 5227e498-9852-5717-afe7-2603b461489b |  | date | Date:
label | 9ac140dc-a17f-54c8-bd9f-013b863d150d |  | note | Comments:
text | c432e3e0-6242-5804-9e6a-f731018eb011 |  | textbox | Concrete strength |  |  | Mpa
label | 5d57298b-4320-50c7-ad51-6ce046af7d34 |  | note | Attach delivery dockets and write the road light column numbers on the docket
checkpoint-status |  |  | checkpoint | Suitable backfill material to be placed and tampered for compaction
text | aa314288-816a-5909-aa6c-d23f52e91513 |  | textbox | Initials:
date | 3550f66b-7957-5cda-86e7-7a36a4fae4ac |  | date | Date:
checkpoint-status |  |  | checkpoint | Concrete/backfill placed to just below the shear base and concrete splashes onto column washed off.
text | a571e483-4c8c-5e96-af6b-17560627610c |  | textbox | Initials:
date | f95765fb-d56d-50e1-9d10-afaca88a4494 |  | date | Date:
checkpoint-status |  |  | checkpoint | At the completion of the concreting/backfilling check the foundation location, level, verticality and height from FRL.
text | 384a9928-0234-50f8-ba7a-2992c5a4acf8 |  | textbox | Initials:
date | 2a9bf407-719f-5bc1-97cc-fc07e78c0ef7 |  | date | Date:
label | 0940d880-e9b0-5139-9938-be8b89883cf0 |  | note | Comments: Foundation may have moved during concreting/backfilling
checkpoint-group |  |  | section | Installing Column & Outreach
checkpoint-status |  |  | checkpoint | Ensure concrete foundation has been left for min. 3 days before erecting road light column
text | 9fc757d6-d0e6-5542-8e0f-0db0e4efc3f5 |  | textbox | Initials:
date | cd50385c-2111-5888-960b-0f0ae9fbbe20 |  | date | Date:
checkpoint-status |  |  | checkpoint | Check road light column for any damage
text | c976416f-6864-5712-95d2-6b5a805b84b3 |  | textbox | Initials:
date | 8b10bbe9-f39c-5693-b440-fad7d3bc5dc9 |  | date | Date:
label | 41c8d6a3-0c9f-5d6c-89a0-87e398bf59c4 |  | note | Comments: Do not install if damaged
checkpoint-status |  |  | checkpoint | Assemble Light column on the ground (protect column by blocking off the ground)
text | 6dd80247-aefa-5d25-a460-dd3673858a35 |  | textbox | Initials:
date | c8d8b63a-eb91-5ed6-b2f5-66c0ca0a0613 |  | date | Date:
label | 8c1f267d-a372-57c3-afca-da0ee6e758f8 |  | note | Comments:
text | 21eaec4a-b955-529c-9eb0-c18ddaa311da |  | textbox | Column Type:
text | 0c89a19b-adc6-56b9-8073-ce734f83d683 |  | textbox | Outreach Type:
text | f337001b-b873-55a4-9f94-ff265e8e7584 |  | textbox | Outreach Length:
text | 22b5edc4-7d78-5a5d-b423-c9b8ff442455 |  | textbox | Luminaire Type:
checkpoint-status |  |  | checkpoint | Check all bolts on shear bases have been torqued
text | 0f95db62-9c28-55cc-aed4-129221396bc0 |  | textbox | Initials:
date | 7b54e42b-3679-5bcb-8359-fa1d7382a613 |  | date | Date:
label | 2cf554a7-b1cb-53cc-99aa-b86b312ebefc |  | note | Comments: Adjust column to ensure vertical
checkpoint-status |  |  | checkpoint | Check orientation of road light column and outreach
text | b561d803-45f2-575b-99ab-a5c1564b880d |  | textbox | Initials:
date | be87da82-f17a-5028-80da-17a4f16154ca |  | date | Date:
label | b9bbfdc6-b730-5956-8f74-b27e811c96fe |  | note | Comments: Torque to 200kPa, check the bolt and slack back to 100kPa
checkpoint-status |  |  | checkpoint | Check the internal wiring of the road lighting column. Ensure 2.5mm2 cables, 2 core NS
text | 74c58516-7d03-5fab-82ab-c51d217a242e |  | textbox | Initials:
date | 1ea60bdd-9784-5c69-acaa-30f22b204a75 |  | date | Date:
checkpoint-status |  |  | checkpoint | Check Connectors & Earth Conductors have been installed
text | d20d4465-83b7-5ed7-990b-8e539ca44283 |  | textbox | Initials:
date | 201ad988-7a09-58d5-9021-2b8b1fc4398a |  | date | Date:
checkpoint-status |  |  | checkpoint | Danger Live Wires sticker on gear door
text | 8920a82e-2ae5-5379-ba6e-c1f9d41c36fb |  | textbox | Initials:
date | a65b2f2c-551b-5f7f-9594-cdb97641daec |  | date | Date:
checkpoint-status |  |  | checkpoint | Check that the Road light is installed to the design height above road level
text | bd3414cd-ffda-52ee-bd6e-e9df71faff7f |  | textbox | Initials:
date | 8ebd5df7-41bb-5631-9adb-bcae9b8754be |  | date | Date:
label | bfd95cc6-15c1-540e-a075-0b9a90d5be2e |  | note | Comments:
text | 3abba789-1f27-5bed-830d-4e8a2cd94795 |  | textbox | Laser Measurement:
text | fc7995f2-3507-5b63-9c3b-bfc985095792 |  | textbox | Design Measurement:
label | c31f5401-07e1-512f-98c8-4103ff31249a |  | note | Tolerance = +/-500mm
checkpoint-group |  |  | section | Signoff
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | ef480904-c20a-5001-8aac-119589b0e6ca |  | note | Position: Site Engineer
text | 65b6a23b-faea-50e6-98a0-3ce694a64b18 |  | textbox | Site Engineer - Name:
date | 00ac1830-6ca0-522e-8675-09c83c26f473 |  | date | Site Engineer - Date:
label | b4782375-475b-5e92-8d3e-958e9ffcac9b |  | note | Position: Design Engineer
text | 2664c17e-1820-5e84-b1e7-250ca35b4594 |  | textbox | Design Engineer - Name:
date | e5769e75-3b22-583e-8f33-72d2ea28828b |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | SIGN
checklist-flat |  |  | checklist | ITP - Waikare Gorge Descent - C1603A - Ground Anchor | itp |  |  |  | Yes | ITP - Waikare Gorge Descent - C1603A - Ground Anchor | 4c352ada-8bb8-4301-a3c3-d998d7d962f8
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 23268b9b-9119-556b-8205-fa154e0babb6 |  | textbox | CPS Eng.
text | 2190b7d2-d1c2-5b6e-996e-5888b338140f |  | textbox | Site Engineer
text | eebd02a7-5ea2-50bf-86a3-e0205dcf4236 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Test Anchor Setout
label | bbb0f351-09aa-55f5-b634-687bccbbd8f1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 821768a7-bd88-541d-8d0a-4c9e59ba6aa8 |  | note | Detail - Location of the tests (to be agreed with the Engineer, two tests shall be completed), and 1 pull test location.
label | af029eb6-fd67-5c83-99f0-f3809988b74d |  | note | Frequency - At least 1 week prior to Testing
label | 3b1cd78e-4ee2-5970-9013-128c86e48335 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 6a06a246-44e1-5439-b551-acb0ae954fdf |  | note | Conformance Criteria - Consistency with Construction Drawing and agreed with Engineer
label | fc789738-5e33-5654-962c-5f075eedb04e |  | note | Records - Design Engineer Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 -
label | ffe2582b-c47d-5315-8e7c-03b47ca43a7f |  | note | ACTION (Hold, Monitor, Witness) - M
label | e3825050-d1a8-5750-b9ef-ffc1a2e04e9e |  | note | Detail - Any services in the area are to be clearly marked before any work commence.
label | 28db5995-0e4b-5d4e-9e9d-d44915089874 |  | note | Frequency - At least 1 week prior to Testing
label | f58a6714-0d12-5d2b-8648-35f2b11593cb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Service location
label | b45f83ee-dcb1-5d22-8b23-75cbbec89485 |  | note | Conformance Criteria - Service location conducted by asset owner, marked out with dazzle on site.
label | 5da6e55d-f3e5-5e8d-a6ed-4a94b9b9d346 |  | note | Records - Asset owner report, site inspection
checkpoint-status |  |  | checkpoint | 3 - Steel Anchor Rod Material Compliance
label | 2881fe03-ff04-588d-9435-ce44066664ac |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6d76b4a3-dbc8-5766-b5ff-afcf187b245a |  | note | Detail - Design Life of 30 years
label | acc7b316-5fa7-516d-9fed-fca864a8ef63 |  | note | ○ Design Working Load (DWL) per Anchor: 168kN
label | 23681ecc-fe9d-5dba-b2ba-74508c294e99 |  | note | ○ Anchor rod diameter: minimum 25mm threaded bar, with a minimum yield strength of 500 Mpa
label | 82a9e9d0-82d6-5fe2-9381-30bd5e9b37e6 |  | note | ○ Minimum anchor rod length: 12m
label | 1f372ea4-83aa-522c-9fbd-5e5497865a8b |  | note | Frequency - At least 1 week prior to Testing
label | c39c36f8-e2b7-5f61-b6e1-78543e7bf077 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 58201b60-6e76-56a1-bbdf-c77f2865c385 |  | note | Conformance Criteria - Design Working Load (DWL) per Anchor: 168kN
label | 6b7fd233-0ade-5d47-8cd3-527adcd10fcb |  | note | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
label | 8910bcb9-1e97-5a50-ac97-dd4c02057537 |  | note | Records - Materials receipt
checkpoint-status |  |  | checkpoint | 4 - Steel waler Material Compliance
label | db375b06-22a4-5513-9776-895cd6a20522 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 717dfcaf-951a-5971-b136-41806e787193 |  | note | Detail - The steel structural sections for the Waler assemblies shall be primed with ethyl silicate or alkali silicate zinc rich primer in accordance with AS/NZS 4680, ASNZS 2312 Part 1 Paint Coatings and NZTA S9 respectively.
label | c4de7caa-0566-5d72-a93d-7f2b5d2b31cf |  | note | Frequency - Prior to Install
label | 3c303fff-921f-56e3-9031-cebc944037d1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 6a774218-2f10-5bbd-ba92-f71cb65556be |  | note | Conformance Criteria - AS/NZS 3679.1, AS/NZS 4680, ASNZS 2312 Part 1
label | ebbfd09f-2a4d-5d4e-b28c-1da06122b770 |  | note | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
label | e07317d9-7667-50db-9a88-124bae974ead |  | note | Records - Materials receipt
checkpoint-status |  |  | checkpoint | 5 -
label | 171c6894-c006-5007-a03a-490b45d55e7f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 49d9d488-f686-5f29-9489-988a867e147f |  | note | Detail - The Contractor shall provide the engineer with test certificates giving the tensile and yield strengths of the steel used to manufacture the structural steels and steel plates at least seven days prior to the fabrication of waler.
label | 7f41fa5b-25d8-50fc-8570-e9554bd0bbdc |  | note | Frequency - Prior to Install
label | 6217d645-fc4d-5427-9a0f-fb9d95634bff |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 5485e335-4634-5c64-ab3c-eded6bdca952 |  | note | Conformance Criteria - Test certificates of tensile and yield strengths, 7 days prior to installation, 150 mm x 75 mm PFC WALER BEAM
label | a6c8bb3f-eebc-5985-bda2-684c1ba67b28 |  | note | Records - Materials receipt, test results
checkpoint-status |  |  | checkpoint | 6 -
label | 2a9e6d54-ca73-555c-bfaf-41065b82c40e |  | note | ACTION (Hold, Monitor, Witness) - M
label | 5a29f75d-d691-5fe4-9a51-418144d00bea |  | note | Detail - Confirmation of waler dimensions
label | 2d354958-401d-5bae-a402-509b8567812a |  | note | Frequency - Prior to Install
label | fb4c8a52-3ddb-575b-84c3-641e911edd2d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | a657737b-338f-5b17-9fbb-43aa1385ddc0 |  | note | Conformance Criteria - 150 mm x 75 mm PFC WALER BEAM
label | ce3ec849-bf72-5797-b1b5-bf12b6e003a2 |  | note | Records - Materials receipt
checkpoint-status |  |  | checkpoint | 7 - Bearing Plate Material Compliance
label | 29e83b48-0501-5327-9df9-27baa121f9b5 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 67b7f40f-8ff6-5219-be20-6107b0964950 |  | note | Detail - Bearing plates shall be steel with a minimum yield strength of 350MPa and the final size and thickness shall be confirmed by the Contractor in conjunction with the anchor supplier.
label | 9b9967c2-58fd-5094-a958-44f762736f3e |  | note | Frequency - Prior to Install
label | f49231ce-cf64-5382-9fc1-adecce0e49a8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 0b2ac64b-76aa-525b-b41d-870aad53947b |  | note | Conformance Criteria - minimum yield strength of 350MPa
label | 99b29078-56fa-5f1f-a2b0-1e01a28e3ffd |  | note | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
label | 95dfd25b-fe7f-530f-b458-19b71c660238 |  | note | Records - Materials receipt
checkpoint-status |  |  | checkpoint | 8 -
label | db386b6d-5287-5fa1-bb7d-09490c6784e4 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 9ae4cf23-39d9-571d-8e82-3049258e5374 |  | note | Detail - Confirmation of plate dimensions
label | 1ecf9133-a2bb-5f9d-819d-d8eb69f3c2b1 |  | note | Frequency - Prior to Install
label | 5208c752-e5ed-5e34-ac91-c1fa02225ec4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 2dc2ce37-68dc-583e-b49e-dfa2c9ebbb61 |  | note | Conformance Criteria - 16mm stiffener plates
label | c169f88d-57db-5b3f-9cc0-25c264a5c5fb |  | note | ○ 150x150x20 plates
label | a339a983-f2bf-5075-8250-ff7e45e39b18 |  | note | ○ 200x80x6 plates
label | ed6c4ff4-2910-5b6d-b60a-1117ad5b06e5 |  | note | ○ 250x300x16 plates
label | 13637350-c496-5523-b29a-fe86e6b99b6f |  | note | ○ 250x250x16 plates
label | a73ca856-0b0c-56bc-aba7-85a9e9a22584 |  | note | ○ 100x100x6 washers
label | 088193a0-2316-5164-9a24-d0b6abd9ad55 |  | note | ○ 200x80x6 plates
label | 785d8dfa-4145-540f-bf14-f0f6b4033b06 |  | note | Records - Materials receipt, test results
checkpoint-status |  |  | checkpoint | 9 - Hex nut/ Washer Plate Material Compliance
label | 15c05c19-ce66-5cfa-b747-8a2e381609d8 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 0aa129a5-9f8c-55e5-a45a-657b50a42f91 |  | note | Detail - Shall be standard, heavy-duty, high strength, structural quality only, flat base, machined from steel, designed for use with the all-threaded anchor rod.
label | 55d0ff13-7e17-5440-983c-4873223e1f62 |  | note | Frequency - Prior to Install
label | 3b7cc288-1394-5cd0-821c-6f3005300556 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 45c996e5-e927-54b4-b58f-59934ab91b45 |  | note | Conformance Criteria - conforming to Grade AS/NZS 1252
label | ca17e480-cbe7-5e72-ae38-c1e0c1ea8e7b |  | note | ○ Develop more than 125% of the yield strength of the anchor rod & ultimate strength of not less than 100% of the guaranteed ultimate tensile strength
label | c55f67e1-4424-5315-8bb2-236e171ca682 |  | note | ○ Hex nut/washer shall be hot dipped galvanised.
label | ee28f67f-ee15-5771-98db-71532599ed9e |  | note | ○ Certified mill test results
label | 927f074f-53fa-57da-8021-1a0aaabd2bea |  | note | Records - Materials receipt, test results
checkpoint-status |  |  | checkpoint | 10 - Mechanical Couplings Material Compliance
label | 0c654219-c5a6-58ef-a97e-250527def15f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 24ae8b56-7f1d-5641-ba84-52e7a63c4cf9 |  | note | Detail - Mechanical couplings, when required, may be used to splice the anchors.
label | c713d6fe-ef6e-5c11-a6f4-b1077647f6e3 |  | note | ○ The couplings shall be stainless steel and wrapped in Denso Tape to satisfy double corrosion protection requirements.
label | 42ef2dca-af78-5b55-a117-a033b82b2976 |  | note | ○ Grub screws or locknuts shall be installed and mechanically tightened either side of the mechanical couple
label | 5994f9a2-9407-5741-973c-541a760633c0 |  | note | Frequency - Prior to Install
label | d974c640-507f-5640-b91b-d976794aa6cd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Inspection
label | e31f50ea-4468-5cda-a5b1-63ca2b4d2496 |  | note | Conformance Criteria - 100% of the guaranteed ultimate tensile strength of the anchor rod
label | c9f33b96-bf38-5f46-a81b-54c645b65324 |  | note | ○ Steel conforming to AS/NZS1252.
label | 03486d38-f075-5473-b3ca-c308e07aa5cb |  | note | ○ Certified mill test results from each heat specifying the ultimate strength, yield strength, elongation, and composition
label | 6e6b9d39-03da-5f63-818b-0acf04660b4f |  | note | Records - Materials receipt, test results
checkpoint-status |  |  | checkpoint | 11 - Anchor Construction Submittals
label | 08caede1-931b-581e-8a9c-73129681492d |  | note | ACTION (Hold, Monitor, Witness) - H
label | c16cace3-8921-569d-880d-24f68a3531c4 |  | note | Detail - The Contractor shall submit a construction plan and detailed construction sequence to the Engineer at least 1 week to commencing pull-out testing
label | 969f9b56-ba14-5bbc-acf9-6b438cf64ed9 |  | note | Frequency - One week prior to install
label | aaa32728-769a-55ba-b134-215d948d3576 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 1261313e-fa4e-5cc8-aee2-7d941f5c19ab |  | note | Conformance Criteria - Document outlining Start date, working drawings, methods, manufacturer certificates, detailed construction sequence
label | 8cf53d19-e777-5e5c-ba57-1af8e4634060 |  | note | Records - Submitted documents
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Anchor Construction Submittals - Working drawings
label | 674ca231-a2b8-51ed-a92c-a34c028be208 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1b8c4d0f-09a6-5d9d-b25f-1f0b4c5f627d |  | note | Detail - The contractor needs to supply working drawings which outline the details and location of the pull out tests
label | e3f95039-07af-55b4-92a2-ad9a142ffc11 |  | note | Frequency - One week prior to install
label | ecf78379-0e0c-5278-9144-f195648aa957 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 6937a615-93d9-5be3-8597-787c9a454857 |  | note | Conformance Criteria - Installation method
label | 5cd4dec9-2d21-5d0d-9d25-0aa25221c8c3 |  | note | ○ Location of the tests (approved by CPS)
label | c2554208-24e0-52d5-90e3-34658909ae3e |  | note | ○ Testing methods and equipment
label | 44d9dec0-4195-57ba-a4c9-20259650d678 |  | note | ○ Ground anchor Schedule
label | 5708a8c2-6666-541e-8361-549073c681d5 |  | note | Records - Document
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 - Anchor Construction Submittals - Ground Anchor Schedule
label | 644e173e-fd26-5095-a320-45c2f61047fc |  | note | ACTION (Hold, Monitor, Witness) - H
label | 171d590e-e83f-592b-97da-1c2adedeeb0b |  | note | Detail - The contractor needs to supply a ground anchor schedule which outlines the strength and detailing requirements:
label | eeaa3124-5340-5017-8f0b-5cb93297fb80 |  | note | ○ Ground anchor number
label | e8e52a15-8a9f-5a3b-8801-9d39079938f9 |  | note | ○ Ground anchor DWL
label | 67472420-7116-542b-9fb9-2141a7447a68 |  | note | ○ Ground anchor DUC
label | 5758c266-b610-555c-9504-e3c66c0bae1c |  | note | ○ Ground anchor capacity reduction factors for rod & pull-out
label | 04312f16-2fc8-5693-a95b-c8509791d28e |  | note | ○ Type and size of anchor rod;
label | e5ec270e-f8c2-54fd-83d8-1a23abf5b0bf |  | note | ○ Anchor inclination;
label | c48a2a8b-204a-53ce-8dd4-f8900098e978 |  | note | ○ Minimum total anchor rod length;
label | 398ec44a-7727-5426-965a-689b0ccdc971 |  | note | ○ Corrosion protection system.
label | 9035a750-cf27-5bfe-ad16-b84bafab5b62 |  | note | Frequency - One week prior to install
label | 5371abeb-dc5b-5c86-ab46-ee1b829a54bd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | c6429465-b09a-5462-b9f1-a4088ba003d4 |  | note | Conformance Criteria - Anchor submittal Document outlining strength and detailing meets specification
label | eead5b9f-e09f-5d97-a77a-c8546ecb0f73 |  | note | Records - Document
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Anchor Construction Submittals - Testing Methods
label | 2e0b110b-879a-5de7-a49e-589481fbb9af |  | note | ACTION (Hold, Monitor, Witness) - H
label | b4350c98-cce4-51b6-95a5-fd609cac7e41 |  | note | Detail - Details of the jacking frame and appurtenant bracing.
label | b99d5479-fac2-5291-a921-2730cab0c574 |  | note | ○ Identification number and certified calibration records for each test jack and pressure gauge and
label | e233ec5e-23ec-5559-96f9-6c79c9107b48 |  | note | ○ load cell to be used. Calibration records to include the date tested, device identification number, and the calibration test results and shall be
label | d2f6c338-f338-5b2a-ac17-72849a704570 |  | note | ○ conducted by a qualified independent testing laboratory within forty-five (45) working days prior to submittal
label | 1873e010-7e79-5ec6-af90-3d3dede1deb2 |  | note | Frequency - One week prior to install
label | c3792b9c-72bd-5f41-937d-faacbf992882 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 0f7596c6-6772-5a3e-9746-73d5f1e497d7 |  | note | Conformance Criteria - Anchor submittal Document outlining strength and detailing meets specification
label | b73b697e-65fc-5893-a548-de525dc5c509 |  | note | ○ Certified for an accuracy of at least 2 percent of the applied certification loads
label | 9ff8786b-72eb-57e1-8a84-7b6f4f47ab18 |  | note | Records - Document
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 15 - Anchor Construction Submittals - Testing equipment
label | c141fa6b-7d39-52be-8f5c-31c0bb60a500 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 90c0f665-fccc-5806-99cb-aebd306be804 |  | note | Detail - Testing equipment shall include dial gauges, dial gauge support, jack and pressure gauge, electronic load cell, and a reaction frame. Contractor shall provide the description to the Engineer prior to testing.
label | 16e1d5cf-adf0-5e1b-a2e7-4a3cf48f52b8 |  | note | Frequency - One week prior to install
label | 77ee96dd-9c54-5b5b-859f-9bde894d5340 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | ccedf6b6-15e8-592f-a78d-983c74944b95 |  | note | Conformance Criteria - description of test setup and jack, pressure gauge and load cell calibration curves
label | 5976ee00-bb9e-5fa2-b213-475b905b1f1f |  | note | Records - Document
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 16 -
label | 34fb898a-59b6-5847-9e73-40f889f019f9 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 00bb3889-454c-56fa-9612-fc9bdca93702 |  | note | Detail - The testing reaction frame shall be sufficiently rigid and of adequate dimensions such that excessive deformation of the testing equipment does not occur.
label | f400be07-be73-5757-affc-5f4319371219 |  | note | Frequency - One week prior to install
label | 8c257f5e-1041-5c0d-a993-13ea51bc4d7f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 1123c46f-d8c0-5d16-a4ef-15206b89eb1c |  | note | Conformance Criteria - Reaction frame sufficiently rigid
label | fd021c52-adb9-56cb-90fc-01f4aac3afbc |  | note | ○ Support and centre jackover anchor rod
label | 0f389d6c-0391-5f7f-ba32-fc352ecfb3f2 |  | note | ○ Jack, bearing plates and stressing anchorage aligned with rod to as not require repositioning during test
label | 5e99158c-1995-5771-8439-31275149f66c |  | note | Records - Anchor Test log, photos, submittal doc
checkpoint-status |  |  | checkpoint | 17 -
label | a2f098f1-aa76-5a78-9a04-5e601f61b8a1 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1c21ebb8-984f-5dca-b845-16ee522fed01 |  | note | Detail - Test load shall use hydraulic jack and pressure gauge. The pressure gauge shall be graduated in 500 kPa increments or less. The jack and pressure gauge shall have a pressure range not exceeding twice the anticipated maximum test pressure.
label | 1432fb0a-5b29-50bb-938b-ac04c15a6f2c |  | note | ○ Monitor the anchor load during the pull-out test with both the pressure gauge and the load cell. Use the load cell to maintain constant load during the creep test portion of the pull-out test.
label | 885a62a2-3027-5da6-925d-df8dd248954b |  | note | Frequency - Prior/ during testing
label | e5f62759-28c4-50da-84a3-ba57f1bfb5bc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, visual inspections
label | 13fd0bdb-9e3e-5693-bbb7-1aec83f73f01 |  | note | Conformance Criteria - Jack and pressure gauge shall have a pressure range within requirements
label | 30091e8b-0e19-5a81-877d-214ee8e31aff |  | note | ○ Gauge graduated in specified increments
label | 4c900274-e152-5412-b576-8ba2a1a60b9b |  | note | Records - Anchor testing submittal, Anchor testing log
checkpoint-status |  |  | checkpoint | 18 -
label | f6168c51-f37e-5dd2-ac01-cc7261aec8d1 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 9048c0cb-4bcc-54cc-bd07-79139b50e552 |  | note | Detail - Measure the anchor head movement with a dial gauge capable of measuring to 0.025 mm. Use two dial gauges when the test setup requires reaction against a soil cut face.
label | 87aecb4a-2152-5052-b502-7da47346ad71 |  | note | Frequency - Prior/ during testing
label | 1b45dade-62e3-5318-96c8-d6704c89519a |  | note | Conformance Criteria - Gauge capable of 0.025mm used
label | 3eb18229-a642-5924-a8f0-414764b09674 |  | note | ○ Sufficient travel to conduct test
label | ee7efd73-96c2-5c76-9a9d-c137a67fbb41 |  | note | ○ Visually aligned gauge parallel with axis of anchor
label | 863a400a-02f7-5dac-bd54-c5c67a93b17e |  | note | ○ Two gauges used during reaction against a soil cut face
label | 993d4cb4-24cb-589f-ba76-0d01d611eb61 |  | note | Records - Visual inspection, photos, Anchor testing log
checkpoint-status |  |  | checkpoint | 19 - Anchor Construction Submittals - Ground anchor report
label | a8f80b50-6fbd-57f7-ae9d-43f761a1df49 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0cc17bf4-f2bb-59aa-8d5f-fd48249d6c23 |  | note | Detail - As-built drawings showing the location and orientation of each ground anchor, anchor capacity, total anchor length as installed. Ground anchor test results, graphs and supporting interpretation
label | 8fcec186-1e61-512e-99fc-f9ba97b01dd7 |  | note | Frequency - within twenty (20) calendar days after completing installation
label | 26bb232e-3c33-525b-9370-a31de5b3f6e6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 5b596424-9236-5139-afdc-98873f5c478b |  | note | Conformance Criteria - Ground anchor report sent to engineer within twenty (20) calendar days containing:
label | c1dd6ba8-9b1c-5631-9a77-08c5339b4275 |  | note | ○ Ground anchor test results
label | 8edac8f1-1aa3-57fc-9496-715088d50f1f |  | note | ○ As-built drawings
label | 6b36af88-20ea-5011-a99a-0b1c3ed592e1 |  | note | Records - Report, document
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 20 - Ground Anchors
label | 812e1059-496d-549b-9c23-63af2ffb1070 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 870c146a-3538-564d-9f62-bd5a57766188 |  | note | Detail - store steel and accessories without damage or contamination. All materials shall be stored on timber pallets on hard ground in a secure area, clear of any construction operations.
label | a0197b22-5c12-5c85-9ad3-1a2ca9af644b |  | note | Frequency - Throughout works
label | caf48723-0ae9-5a65-9aa8-40fc93a03fee |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - inspection
label | 9a1519c9-8717-5773-8261-939ad1691d50 |  | note | Conformance Criteria - Stored on timber pallets
label | 0c0317d0-1690-5436-8486-3f2c9c89913c |  | note | ○ Hard Ground
label | 08fffe2a-3be6-579f-9b5a-9da0c250f8f6 |  | note | ○ Secure Area
label | 8ca9df54-f519-5a32-af66-ce7c8f82593a |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 21 -
label | 17084e57-53f7-5de2-aa89-88db92b5edd4 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 08099199-2b0f-5da8-a900-36bd7a3173fe |  | note | Detail - Anchor components incorporated in the wall shall be free of corrosion and physical damage at the time of placement
label | e57c2564-eceb-53e7-8794-be28ae09cb66 |  | note | Frequency - Throughout works
label | 23d929c5-378c-5c86-ab54-5c0a80285646 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - inspection
label | 3bca332b-4e7e-5ec1-9a51-11c10c4cb6fc |  | note | Conformance Criteria - Free of corrosion and physical damage, Placed so will not damage ground
label | 9100991a-d393-5b1c-a146-fdae07f25234 |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 22 -
label | 67627495-25c7-5dab-8290-c3f0d5383b7f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 079a7785-163b-58eb-8b33-8197ec624d59 |  | note | Detail - Works shall be carried out in accordance with NZGS (2023) Ground Anchors: Design and Construction Guideline. Should any discrepancies between the relevant codes and standards contained in the above Guideline and this Specification arise, they shall be brought to the attention of the Engineer
label | 4c93151c-4767-5371-998e-b273a0dcac9a |  | note | Frequency - During Installation
label | 6ed1c0fa-7cff-552b-b7f6-b68f1f078b28 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - inspection
label | 5ac424d5-c8b4-5b28-9442-aa90bfcdb54b |  | note | Conformance Criteria - NZGS (2023) Ground Anchors: Design and Construction Guideline
label | 5fb2f3f0-938d-5708-85e8-e96e6b4a7b37 |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 23 - Ground Anchors - Tolerances
label | 7cd3c381-9cee-5d01-92ce-af4bd92c8de9 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 2bdf4b5f-5091-5797-b5b8-cf02253ef743 |  | note | Detail - Anchors shall be installed at an angle within ±2 degrees of the angle of the theoretical centreline and shall be located horizontally on the face of the wall accurately
label | ff78d446-9746-5295-8f12-da50b42bafa6 |  | note | Frequency - During Installation
label | da596ff6-dad6-5fa7-8ebe-74230605f81a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | ff8fe1eb-1ea1-5d5b-bfc9-400a20f84db1 |  | note | Conformance Criteria - Angle within ±2 degrees of the angle of the theoretical centreline plus or minus 25 mm from the position shown on the drawings.
label | 64ab86d9-4ba2-5152-a4be-17b23d7c55ac |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 24 - Ground Anchors - Anchor Testing
label | cc11aeed-e605-5701-881d-64fff80a4adb |  | note | ACTION (Hold, Monitor, Witness) - M
label | 5b54be5c-6b22-5c35-a459-915d54964f53 |  | note | Detail - No-load greater than 10% of the design load can be applied to the ground anchor prior to testing. The maximum test load shall not exceed 80% of the specified minimum ultimate tensile strength of the anchor rod.
label | 6172d9ea-ff60-5409-81e3-71d1b87cf311 |  | note | Frequency - During Installation
label | f475ab1a-696f-5c51-9694-ad993d3a766e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection,
label | 8df0d540-2d12-5926-9764-513f6d86abdf |  | note | Conformance Criteria - Pull-Out Test Schedule <80% min ULT load
label | 9052ffb9-42c5-5bfe-a01c-ad4b83521739 |  | note | Records - Pull out test log
checkpoint-status |  |  | checkpoint | 25 - Ground Anchors - Pull out Testing
label | c0848f19-1c47-53e7-ad59-32e2a7a140fe |  | note | ACTION (Hold, Monitor, Witness) - H
label | fc4b9612-9c78-592a-9177-d7758092dee1 |  | note | Detail - Pull-out testing shall be carried out on one sacrificial ground anchor, The pull-out test shall be done at a location and elevation agreed and approved by the Engineer.
label | 0ccc369a-e70f-502b-90b7-dab263676976 |  | note | Frequency - Prior to installation of anchors
label | 23165f9b-d872-563f-ac15-7c1d39a6f02a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | 51df7fbf-9c25-5ee7-8e3d-0c1f0eb4c433 |  | note | Conformance Criteria - Conducted prior to installation, Location approved by CPS Engineer
label | 8f9da01f-59a0-54b0-9285-b3f3f439dc29 |  | note | Records - Pull out test log, Submittal
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 26 -
label | 1b4cd79b-d010-5c72-ac02-fbb12db6e73b |  | note | ACTION (Hold, Monitor, Witness) - M
label | a4b9f5d4-5e26-5dc5-96ae-d9c561ad62fb |  | note | Detail - The pull-out test shall be carried out to 150% of the Design Working Load (DWL) and the contractor shall supply a larger anchor rod (if required) to safely accommodate the maximum test load. Anchor movements during the Creep Test shall be measured and recorded.
label | 542c89c1-b9e4-5dcf-959d-71a265c19e44 |  | note | Frequency - During Pull out testing
label | 2c5fd92d-0527-586a-8b0d-bbebe831b383 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | de4e9419-72a2-580f-aff3-aeebf5858960 |  | note | Conformance Criteria - Refer to the Pull out test schedule
label | 3c0c90d1-80ba-571f-8ab9-6a58625b8386 |  | note | – – – – – – – – – –
label | 7b3e90b5-8f1a-57d4-8dc1-5d422810f2f0 |  | note | Pull-Out Test Schedule
label | f9892107-25ef-5ca5-a7ae-ceea6e51dd8c |  | note | – – – – – – – – – –
label | 7470e92b-8d1f-5640-b9a0-0f6f599116cf |  | note | Load ¦¦ Hold Time
label | d8b17642-48dc-5c4b-903a-900a3ec5154e |  | note | – – – – – – – – – –
label | 2f6e071a-8fc2-5117-9d0d-1bdd134f8dd8 |  | note | 0.05 (DWL) ¦¦ 1 minute
label | 8829115e-7466-5f6b-a2af-ba6c7e439892 |  | note | 0.25 (DWL) ¦¦ 10 minutes
label | 831c2d3f-01f0-5aaf-9076-953572340431 |  | note | 0.5 (DWL) ¦¦ 10 minutes
label | fbf79713-e465-5a23-a91c-14548ebf65ac |  | note | 0.75 (DWL) ¦¦ 10 minutes
label | 5c490679-4bdf-511b-b15e-5f1b92ebb615 |  | note | 1.00 (DWL) ¦¦ 10 minutes
label | 0ac3d99a-3a8a-57d8-a573-df0d7389105d |  | note | 1.25 (DWL) ¦¦ 10 minutes
label | 7a37a96a-f911-5060-acca-926afca8d64b |  | note | 1.50 (DWL) ¦¦ (creep test) 60 minutes
label | 18bd9e0e-07cb-5b71-a553-b8b617cbf99f |  | note | – – – – – – – – – –
label | 1a9e7757-097c-538d-88ed-abb69aa7b7b1 |  | note | ○ Recorded at 1, 2, 3, 5, 6, 10, 20, 30, 40, 50 and 60 minutes
label | f9c3414b-f49b-52ab-9216-77e1aef85beb |  | note | ○ Maintained within 2% of the intended load
label | 1862245d-736c-560d-a421-6d15ddfc86d0 |  | note | Records - Pull out test log
checkpoint-status |  |  | checkpoint | 27 -
label | ddb258e7-bcb2-5cbe-9fbd-fbe79e6a2f10 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 121764b5-38a9-5b61-a6b5-86c0bd7b0f15 |  | note | Detail - The alignment load (AL) should not exceed 5% of the DWL. Dial gauges should be set to zero after the alignment load has been applied.
label | 12e384e0-a4ce-5ce3-9f79-d8aa2bd4a43e |  | note | Frequency - During Pull out testing
label | 1d54a500-1ed7-56d1-b9ef-5581f5dacc4f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | 689b321a-59ae-5654-aa0e-d50470ef67f8 |  | note | Conformance Criteria - AL not exceed 5% of the DWL
label | 16e597a6-f366-51e3-912f-e2577f6a242b |  | note | Records - Pull out test log
checkpoint-status |  |  | checkpoint | 29 -
label | 6264c0bc-19ff-5244-b4d8-ef3d180442db |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2c1b77bc-8df5-5ced-afb3-80c54f103604 |  | note | Detail - The results of the pull-out test, along with calculations and their interpretation shall be forwarded to the Engineer
label | f20d9c7f-e9ba-5f3a-a95a-24301428d3c7 |  | note | Frequency - During Pull out testing
label | 73d046cf-3f09-5a0d-93e6-08ab74afca09 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | 48660374-2d8b-5db0-ba74-fa7f79370313 |  | note | Conformance Criteria - Engineer to send through approval within 48 hours of receiving results
label | f8e1f522-2fea-5dc3-8eed-b03062cdbad3 |  | note | Records - Pull out test log
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 30 - Ground Anchors - Proof Testing of Anchors
label | 16635a30-06b1-54ce-92d7-0d4c117b3d10 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6fbec8f5-31df-5715-9af2-da94df6a6fe7 |  | note | Detail - The proof tests shall incrementally load each ground anchor in accordance with the Proof Test Loading Schedule and in conjunction with the specifications 5.7.3.3
label | 0b4520d1-c3e3-57ea-b3c5-0ea02d570d36 |  | note | Frequency - During Proof testing
label | eabf1fd8-93be-5153-b05d-3e566676e974 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | 80d9320b-83ff-5b38-9c1e-82d52ba140e0 |  | note | Conformance Criteria - Proof testing completed on two anchors as selected by the Engineer
label | d1a8ad24-6401-5a1e-9a09-91f4f8f96650 |  | note | Records - Anchor Proof test log
checkpoint-status |  |  | checkpoint | 31 -
label | 44418fca-a711-5994-92dc-8fc3e1eecc7c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 464ad6a3-4af4-5aec-ad3d-567b106cee7d |  | note | Detail - The maximum test load in a proof test shall maintain a constant load. The load-hold period shall start as soon as the maximum test load is applied and the ground anchor movement with respect to a fixed reference shall be measured
label | fc9f46c9-605d-548c-bb38-03a1e2b8cd59 |  | note | Frequency - During Proof testing
label | 76ee0662-0767-5519-bafb-42245bd4e6c4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | ed3cc313-4ce9-5ce3-bd08-91a89bc93899 |  | note | Conformance Criteria - recorded at 1, 2, 3, 4, 5, 6 and 10 minutes. If creep test up to 10 minutes exceeds 1 mm, the maximum test load shall be held for an additional 50 minutes
label | eee934ef-9c31-5b2a-98b2-700f9f11bcc3 |  | note | Records - Anchor Proof test log
checkpoint-status |  |  | checkpoint | 32 -
label | 11a818b3-cb13-53fd-a3f2-ed3ee19e35f1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 39266888-6081-5583-b508-7616133a308c |  | note | Detail - The remaining anchors should also be tested to the same methodology up to 1.00 of the DWL unless approved otherwise by the Engineer.
label | c1033b36-6f86-5ce5-8939-463d123f08eb |  | note | Frequency - During Proof out testing
label | 368ce410-e02a-5a3f-a867-426df28cfc2e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - testing, measure
label | 884d8ec3-4d52-5049-afff-2f5c03036420 |  | note | Conformance Criteria - Total movement within the 10 minute hold is less than 1 mm between 1 and 10 minutes.
label | e30f5b3c-bdbc-532b-9c5b-bc7e49b3918a |  | note | Records - Anchor Proof test log
checkpoint-status |  |  | checkpoint | 33 - Survey As Built
label | e048e06a-612a-50fd-bd7d-d5f01d1b9a15 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 8ead4107-8a60-52db-ac2d-05806a6a219e |  | note | Detail - Survey final position and R.L. of each anchor, produce As-Built drawings
label | ff5c8b89-b6cf-5e6e-a0e8-9ea18f27d811 |  | note | Frequency - Each anchor
label | 17bb6571-bdb1-54ed-9c8a-f8bb81c500eb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement / Survey
label | 254ec04e-6f45-5e54-88c1-a8d0a09a1df0 |  | note | Conformance Criteria - As-Built Drawing
label | 151042a5-92e3-57c1-8f90-effe2db75a6b |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 34 - Lot Number QA File
label | 6b639507-409f-5a70-8258-46d9dc5ade30 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 6caca58d-f01f-5f81-8431-dc1cb59eb796 |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 50367b3c-6403-5f06-aff3-bd713d19f811 |  | note | Frequency - At completion of Lot
label | 462cc030-b92b-5de3-8d3f-b618f543ed24 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 4cdaca21-67b6-5f12-a594-c76f0ba91de0 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | f41a7b0b-add1-52b1-849b-cf063436b679 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 35 -
label | b25338ad-0609-5c85-8e42-1b868b72aa02 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 67656e4e-dcd0-5368-897f-3a65ac79baf8 |  | note | Detail - Check all anchor records are completed and signed by the relevant signatory.
label | 3e56608d-10a8-530d-ad23-c5096ef8d8f8 |  | note | Frequency - At completion of Lot
label | b3d5e95f-60e1-5441-bbd7-9866314ad191 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 67759f6e-b607-5ab8-b293-c55b43d994e8 |  | note | Records - Document Review
checkpoint-status |  |  | checkpoint | 36 - As-builts
label | a41a1fac-b9ee-52c4-958d-fdb2c096e4d6 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 701d61cd-9257-5d57-be02-51e40e66f052 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 8ecbb795-857e-5fa9-a3f8-3ce3978a18df |  | note | Frequency - At the completion of the Lot of work
label | 9a0b2271-28bb-5de4-95ab-a01b4ef12178 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | b6b6abae-4cdb-5872-849a-97f2f780c9de |  | note | Records - As-built Drawing
checklist-sectioned |  |  | checklist | ITP - F3002D - Mangahuini Long Drop Site - Guard Railing | itp |  |  |  | Yes | ITP - F3002D - Mangahuini Long Drop Site - Guard Railing | 4db5d008-47c7-4541-93a2-e3491da36cc1
checkpoint-group |  |  | section | Inspection & Test Plan / Checklist
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 07a6729d-3354-5ae8-89c7-ecc01cf58b18 |  | textbox | CPS Eng.
text | 2f595288-c6fd-52e2-8d20-cca647d4056e |  | textbox | Site Engineer
text | 829a885f-2d1b-5e55-af1c-167e81d6ad20 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 -
label | 4e6c1dc4-d073-59bf-8b34-328eff7f1b11 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f669b5c0-712f-5cbe-900e-16d3f57097ed |  | note | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | 71b319ad-ddfd-5b10-a656-196edd0d3a51 |  | note | Frequency - Prior to commencement
label | 85826c6c-e534-59e5-97fc-8b875c2fa2bd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | b89b421b-9fc4-55ec-891a-eae14e182b60 |  | note | Conformance Criteria - National Standard for Traffic Signal
label | 4bc90ce3-a993-5ac9-ba87-b388e99a693c |  | note | Records - Site pics, NTE/NTC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | be4ce099-9316-563f-8098-707e68d1c379 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 90f6732b-e65a-5ba2-880e-b6788a6f74b6 |  | note | Detail - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
label | f66824e8-b6c9-5c26-a11b-f68cebfa1762 |  | note | Frequency - Prior to commencement
label | a7330349-2659-5676-acd1-fcf3e26be2db |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 9bf7b259-243e-5727-8f04-10ee9d4ac4bb |  | note | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | b593c1e7-5926-5e84-ac03-3e7fc17ea298 |  | note | Records - Approved Construction Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Material Compliance
label | 922a4fb9-0e18-5856-91a4-d455bd3d9944 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 34c00366-d726-5cb1-9c36-b7a91b8a9220 |  | note | Detail - All roadside barriers shall comply with TNZ M/23:2009. Only NZTA mash TL3 approved systems to be installed as specified in the specification & guidelines for road safety hardware and devices, Appendix A: permanent road safety hardware.
label | 15493f96-ad48-5d9e-8d89-d8a96270eefb |  | note | Frequency - Prior to commencement
label | 599e79eb-8058-5a72-b4bf-50016c38cb1e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | bd15e27c-d53b-567c-b402-de4dd7d6af4a |  | note | Conformance Criteria - Comply with TNZ M/23:2009. NZTA mash TL3 approved systems only
label | 8beecbc3-02b6-5774-bd21-de71e55ce68f |  | note | Records - Manufacturing certificates, delivery dockets
checkpoint-status |  |  | checkpoint | 4 - Guardrail Installation
label | 7251bb61-9ef5-5928-b9a8-844da40500e2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4ea47c23-93b4-5902-b5b0-afa072354fc6 |  | note | Detail - Guard railing shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications. Laps to be in direction of traffic
label | 79dc4a94-8885-5e19-a5c4-f7d08ad2b6c0 |  | note | Frequency - During installation and on completion
label | eade38ee-2737-5585-9ae3-345370f9ba53 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | 6dae757d-7734-5f09-b1ef-9a5212750d88 |  | note | Conformance Criteria - Each section inspected to comply with manufacturers specifications
label | 9380abed-ffe9-5f18-8d40-e95f917cbec8 |  | note | Records - Guardrail Installation Record (CS-4117), Photo's
checkpoint-status |  |  | checkpoint | 5 -
label | 14cc0fe4-ce0e-51b3-a60f-bd7b816e3444 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 979b79e7-e5ed-5d41-aa8e-79fe3958f4d6 |  | note | Detail - Hazard markers to be installed at terminal ends. Edge markers posts to be secured to the guard rail. Guardrail to be a minimum of 1.2m from white line. Engineer to confirm min of 1m support width behind the barrier
label | 41d775a3-910c-545a-9cd2-db93f5ab0980 |  | note | Frequency - During installation and on completion
label | 8caf8533-a031-510b-be7d-5f4c019e384d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | ee1fb88d-25f9-5253-b45d-5170556e2680 |  | note | Conformance Criteria - Each section inspected to comply with manufacturers specifications
label | f6752a78-a87f-55d9-b864-b054fbceb26f |  | note | Records - Guardrail Installation Record (CS-4117), Photo's
checkpoint-status |  |  | checkpoint | 6 -
label | 9362a151-fde6-5bdb-b055-f177deca18de |  | note | ACTION (Hold, Monitor, Witness) - W
label | e04302e3-1e7a-520a-a14f-66ef1c7a6d60 |  | note | Detail - Barrier face to be max clearance of 200mm from kerb face where kerbed. Design speed 100Km/hr AADT <1000 V/D run out length 64m. Existing signs to be placed behind the barrier. Offset of fence is to be confirmed to ensure there is sufficient room for barrier installation
label | 7fbb6aca-dc56-50e4-890b-35975bd57688 |  | note | Frequency - During installation and on completion
label | 9b00fb02-4ff7-5cba-963a-870f49ec5be1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | e8724f78-286f-574b-8872-1f76b027dbbd |  | note | Conformance Criteria - Each section inspected to comply with manufacturers specifications
label | 62581f40-4214-5abd-a2c5-e042a45b3280 |  | note | Records - Guardrail Installation Record (CS-4117), Photo's
checkpoint-status |  |  | checkpoint | 7 - As-built Survey
label | 9c6ff1e7-e9d3-5e5d-80ab-9297b281419b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 08086838-913b-5ba1-b213-d8a7d9a01e22 |  | note | Frequency - At completion of Lot
label | 9a3af4d5-fd0e-5f0c-8429-222290592161 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | cf5d4669-d962-5806-b36c-79e8d6a4508c |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | fd97d86a-9e41-555d-bb98-5a6158d1f04d |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Final Inspection and Handover
checkpoint-status |  |  | checkpoint | 8 - Quality Assurance deliverables
label | 8cb59d57-1730-5047-9df3-3c48da8e6fbc |  | note | ACTION (Hold, Monitor, Witness) - W
label | f13bae89-03e7-5567-ad7a-8c0916e316bb |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | c5f09f82-70db-5323-905c-4e8aab4c5b73 |  | note | Frequency - At completion of Lot
label | 3a61c0b8-cbc1-520b-9487-a4e88ca16cb2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | bee2b8ec-ace0-56a8-a2e7-f1c66d935dd9 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | e4a32095-9132-59ad-a6a6-3631acdd12d5 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 9 - Completion Sign Off From Fields Below
label | 3ae7ef04-75c0-5bdc-99d2-9c98e01b087c |  | note | Records - Signatures
checklist-flat |  |  | checklist | CS-4100a - Subbase Approval Checksheet |  |  |  |  | Yes | CS-4100a - Subbase Approval Checksheet | 4fc6edcb-2972-4fc8-8184-4fe3b88628e8
checkpoint-status |  |  | checkpoint | GAP65 material mat testing - PSD(Grading), Sand Equivalent >=25; and Plasticity Index<8 (IANZ Test Reports required)
label | dad77b8a-afba-59fa-a53d-75533bdebc17 |  | note | ○ Note 1: Test frequency as per ITP
label | 7bc1a5d8-dd03-5804-a268-e961288c26b3 |  | note | ○ Aggregate material compliance for Subbase stockpiles – CPS Hold Point
text | c5c4dbd9-178a-5a69-b9b3-c18866090f8b |  | textbox | Initials: CPS / Design Engineer
date | fc8a8883-28f8-51cb-bce1-a0d035cd19c8 |  | date | Date:
label | b3b01d0a-fb8c-518d-ac7b-d3acb6b6da6a |  | note | Comments: Material Test Report – Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab Test for MDD at OWC
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Subgrade final trim inspected, and a proof roll witnessed by CPS/Designer – CPS Hold Point
text | 350090fd-416e-53dd-95a3-66f677cf8a26 |  | textbox | Initials: CPS / Design Engineer
date | 5520fdc1-06e6-55d2-8899-10bbcb013ed5 |  | date | Date:
label | 4add1324-b7f4-5b12-81e4-94b1dc6963bb |  | note | Comments: Visual Inspection
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Subbase Compaction - NDM tested (Mean>=95% of MDD; Minimum>= 92% of MDD) – IANZ Test Report required – CPS Hold Point
label | cbe4039f-0e09-5d6c-9e70-5f2334bcad21 |  | note | ○ Note 1: To test every 30m of road per lane, staggered at 15m
text | b224eb82-13a4-53ef-bce4-3e6837b70184 |  | textbox | Initials: CPS / Design Engineer
date | acd1abdf-9c55-5d7e-940d-653ed2320571 |  | date | Date:
label | c49868f8-6718-595c-8ffe-515571b97690 |  | note | Comments: IANZ Test Report
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Saw cutting – proposed Saw cut line to be inspected by the Engineer – CPS Hold Point
text | b745a7ce-cf05-570d-b151-ef24718b8abe |  | textbox | Initials: CPS / Design Engineer
date | f7908cd4-5856-5acb-9e18-03519ac31678 |  | date | Date:
label | 8c71081f-f6db-5d70-856f-92a813e69869 |  | note | Comments: Visual inspection – Project specification 6.6. Photos provided
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Surface shape check prior to Basecourse construction - stringing line checked and no point of the surface shall vary more than 10mm over a 3m long straight edge – CPS Hold Point
label | 7367d667-e8cd-5a2d-95d0-5ef3a6f7cf74 |  | note | ○ Note 1: To check every 10m both parallel and perpendicular to centreline
text | 3e08785f-00aa-5aae-9fb8-d292dff16878 |  | textbox | Initials: CPS / Design Engineer
date | 950e856c-4536-5d1d-abee-86dd22848506 |  | date | Date:
label | c0f8a32f-9101-5822-a6c6-716b6fe7d838 |  | note | Comments: Measurement Stringing line Record Sheet
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Subbase as-builts: Width, Levels and Crossfall within tolerances:
label | 9c3fa2e6-4115-5b6b-9e78-72d282214a97 |  | note | (a) Width: Unconstrained: –20 mm +100 mm; Constrained: Zero
label | 97fbd82c-a01b-5132-b86a-76418b126ad6 |  | note | (b) Level: -25mm +5 mm
label | 713302ea-a6bc-598e-94e0-8579e7128dc9 |  | note | (c) Crossfall: no depart from the design crossfall by more than 0.5%
label | f0901d8b-d2b8-53c3-8ee2-380626c59630 |  | note | ○ Note 1: To survey 1/10m intervals
text | 1b85b6c9-cfb5-50c1-92b5-d887dc250c56 |  | textbox | Initials: Site Engineer
date | 5f684db6-4314-5bff-932d-3b72febde5d7 |  | date | Date:
label | 0955b3a7-434c-574b-940d-4c69d69e3795 |  | note | Comments: Survey Record Sheet
checkpoint-status |  |  | checkpoint | Final Inspection - a proof roll witnessed by CPS/Design prior to basecourse (Deflection no greater than 10mm, and no visual cracking or deformation remaining after pass) – CPS Hold Point
text | 891bcb4d-89ac-5a35-a826-5c1144fd853b |  | textbox | Initials: CPS / Design Engineer
date | e32dad61-70f6-5e89-beaf-bf9faa9be236 |  | date | Date:
label | 51c91594-4fa8-5c80-9e86-1fde9038ceec |  | note | Comments: Visual Inspection
holdpoint |  |  | signoff | HOLD POINT
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | fee3cd76-d91c-56db-99f4-e19a15f6e14b |  | note | Position: Site Engineer
text | 7d0bc603-2a91-584f-a340-c14740445f48 |  | textbox | Site Engineer - Name:
date | 8f8c37da-221c-5702-9335-b52cdb00c6b3 |  | date | Site Engineer - Date:
label | 800527e2-5de3-561d-88d0-67845b6ac0fc |  | note | Position: CPS / Design Engineer
text | 62e4f3de-1abe-5848-8091-3fa102cad7dd |  | textbox | CPS / Design Engineer - Name:
date | 194df51f-449c-56ff-92c7-14e750d732b0 |  | date | CPS / Design Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-flat |  |  | checklist | ITP - Mangahuini Sheet Pile Wall - F3002G - Earthworks - Bulk Fill | itp |  |  |  | Yes | ITP - Mangahuini Sheet Pile Wall - F3002G - Earthworks - Bulk Fill | 53a7e31a-58e7-41f4-be59-b3a5b3b43ae8
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 9767d015-034e-50b4-95bf-5cd9dd0fa1d8 |  | textbox | CPS Eng.
text | 1f58d06f-615a-5451-898c-6bea68c80135 |  | textbox | Site Engineer
text | e3481929-0aab-5860-8677-a15b94fbbe9b |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 28a70587-8e08-5e9f-b0b8-dc9d5b37bd29 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a39f5a16-a7fb-50ce-b60e-bf85ef3c13a7 |  | note | Detail - Set out extents of fill and check against design drawings
label | 29df25c8-d1ec-5b59-9244-72f865510e69 |  | note | Frequency - Prior to commencement
label | 0a89cfd5-f4ee-50cb-8bc9-91f03d6696c5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 57bef4bc-a651-50d9-b0e3-8c53b19a9708 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | bc9e18cc-bc68-504c-bef3-2c8ab3091f28 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Ground Improvements
label | 1437883b-e844-5ac2-8a16-8a24bd6769da |  | note | ACTION (Hold, Monitor, Witness) - H
label | c3490e56-6b3a-5705-a67a-ddd83ca62686 |  | note | Detail - Ground Improvements / Dig Outs for soft areas
label | 60c620e5-2078-5abf-a242-07faa5168ee7 |  | note | Frequency - Prior to commencement
label | 613e8a49-1e8c-50a1-89f8-16978bb839d7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 7ac2f59a-bb00-58da-85c3-7c79fbf3ce2b |  | note | Conformance Criteria - Must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence
label | 9e3cdbed-71e1-51ca-a6ea-d20c13504756 |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Granular Fill (AP65)
label | e0ac56ba-b8db-5f7a-aabb-83cf3fcfa4c3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d08c775e-8850-572a-9c32-8e0177c4f280 |  | note | Detail - Granular fill material to fill any voids in the batter slope shall be crushed AP65 material
label | 222259b9-68fd-5d34-9575-0892ba663d37 |  | note | Frequency - Prior to receiving rock rip rap
label | 4e1983bb-ebac-5f20-bb0c-a17100f7b6dc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 92b25a71-2777-5ab5-bcf2-edf4cfe0ce28 |  | note | Conformance Criteria - AP65 shall be a hard, durable, well graded, free draining material with a maximum particle size of 100mm and 65mm respectively and not more than 5% by mass passing a 75- micron sieve. The fill material shall be free of organic fines and vegetative matter.
label | bf9dacaa-9ddd-585a-956a-a8812c5413f6 |  | note | Records - Delivery Dockets, Material certificate(s)
checkpoint-status |  |  | checkpoint | 4 - Subgrade Testing
label | 80dfb72e-8d5d-5aee-86e6-02b0c01ad38a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1fba8111-3e5d-5384-abe4-65b73d2e5a33 |  | note | Detail - Subgrade Cut and Fill Construction
label | 21428e23-073c-5d2c-b9af-7bf6dc377baa |  | note | Frequency - During construction
label | c6716d1d-38e3-5aeb-a345-256d34b38559 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 30e33850-7fb0-5563-9201-cb62fb9d9650 |  | note | Conformance Criteria - Ensure clearing and topsoil stripping does not extend past survey & clear the site with organic material / unsuitable soils
label | c3725273-d242-57bc-8a24-d17aca91da99 |  | note | Records - CS-4100 Subgrade Approval Check Sheet
checkpoint-status |  |  | checkpoint | 5 - Filling Operation
label | fe26c607-d10c-5617-ae45-93005c4fff45 |  | note | ACTION (Hold, Monitor, Witness) - W
label | aa95c2c2-7d92-5089-b2e8-6b1dac8be65d |  | note | Detail - Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately
label | ee14ea73-f12e-5e56-a032-0455aef34f81 |  | note | Frequency - During construction
label | 3fc58e8b-ce7c-5281-8598-ab8f540e5966 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 9500c0d3-002f-5bf8-9aab-dfb2bda774cd |  | note | Conformance Criteria - Any voids larger than 300mm to be filled with 100 to 300mm diameter chinker rock
label | f7f67166-d5cf-582d-a2e9-b8e7ebc7eb9f |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 6 -
label | ee1a031e-de18-5a86-870c-db1c5e23819c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 63f13e77-0a9f-511b-b2f6-fb77daea4cc8 |  | note | Detail - Granular Fill (AP65) used in voids for batter slopes shall be placed in layers not exceeding 200mm loose thickness and be compacted
label | b8f804a9-48b3-5e86-a6c6-1711bb0bbb16 |  | note | Frequency - During construction
label | a07752c5-757f-59da-8878-66f3b32195c9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 8829495c-42cf-5f48-9d6c-69ea21a41588 |  | note | Conformance Criteria - The material shall be compacted by using hand-held mechanical tampers achieving 95% of the maximum dry density as determined by NZS 4402 1986 Test 4.1.1.
label | f1cceb38-5ba5-5021-91b5-37df359a2321 |  | note | Records - Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - As-built Survey
label | f02dcad3-567a-581e-ad71-9a34945e27bb |  | note | ACTION (Hold, Monitor, Witness) - H
label | e5ae8868-f9e7-56e3-b3b6-d2317d076c9b |  | note | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
label | 41392891-d43e-5db6-8f75-56bcdbacc36b |  | note | Frequency - Prior to placing topsoil/pavement/ finished surfaces
label | 3360f140-f1e3-5ac0-a92f-999e77051176 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | 51369fe1-c189-5c63-97db-a2f867b835b2 |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | 516ffe34-4144-5c58-997a-8d02b00c9783 |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Quality Assurance deliverables
label | 03d287d2-28a1-520f-86a9-4694c8cb02fb |  | note | ACTION (Hold, Monitor, Witness) - W
label | 36de4ec3-a6d5-5177-878f-d3adfa90d729 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 095faf89-c219-5a19-9e65-035cd187839e |  | note | Frequency - At completion of Lot
label | 0bf97d4a-03ca-5b03-940d-7b7814c091d7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 12ab9b67-ddc3-566f-aa5c-7d8f8683b705 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 979151bf-acb2-57b9-9ca0-5ec3d398f80e |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 10 - Completion Sign Off From Fields Below
label | 84c43040-bd86-5bbd-a6e1-d7340582c311 |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | ITP - B1004F - Tangoio Falls Steep Underslip - Guardrail | itp |  |  |  | Yes | ITP - B1004F - Tangoio Falls Steep Underslip - Guardrail V2 | 55202a61-8adc-463d-9d6e-a561a18f7c95
checkpoint-group |  |  | section | Guardrail Installation
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 84bcda9f-cb71-5c76-aca2-a018423528b8 |  | textbox | CPS Eng.
text | def4f8a9-8da7-5610-94d8-b904ba1024f2 |  | textbox | Site Engineer
text | 465c107a-d49e-56b6-90e2-a894dd211b63 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | a00b1d58-523a-5444-818b-cb4132d3fa65 |  | note | ACTION (Hold, Monitor, Witness) - H
label | dfe031f8-250f-5fac-b52c-2c587fac3c4d |  | note | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | fcc668fe-642b-5b6e-9834-d04eda6361fd |  | note | Frequency - Prior to commencement
label | c8b981c5-d1a7-536c-9ecb-f691949e60ac |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | c65af77b-929c-5520-bd1b-bfb5d001651c |  | note | Conformance Criteria - National Standard for Traffic Signal
label | a56db5d3-b797-55b4-9bf7-6f0717b47223 |  | note | Records - OFI or NTD/NTC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | dacc620c-7509-5403-9a32-92ef1fe80ba9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9809afa9-3e72-5ceb-b878-5f05f921a170 |  | note | Detail - Surveyor to mark 20M Chainages on the bridge from which Start and End Point of Barriers will be referred.
label | 34519b57-a17d-5e82-8765-ac34d4475090 |  | note | Frequency - Prior to commencement
label | 3f59ce4f-a81e-5509-9b99-665991f42cd4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | b66113fa-f599-5be7-9c1d-b37edef0257c |  | note | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | a7d0b712-2d8a-57d4-9301-37b4cc66dc81 |  | note | Records - Approved Construction Drawing.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Material Compliance
label | 14ed9500-a196-5234-9706-59e1d6fd1642 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 13777ff1-0741-54eb-9cbe-c519cda07831 |  | note | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
label | 88b11f0a-ac0c-5ece-be2a-56b86b2ae4db |  | note | Frequency - Prior to commencement
label | 3036809b-ee42-52b4-b3de-034bc1a69e92 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | bdbc51c4-ed3d-58b6-8dfd-8de7bebe96c6 |  | note | Conformance Criteria - TNZ M/23:2009
label | 4af21f72-e1fb-5788-ab37-9e63e16c09f4 |  | note | Records - Manufacturing certificates and delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Guardrail Installation
label | 0ad75034-1e75-53e4-a92a-c5a3f5ebc76c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 11bf54da-dc76-5f72-a68b-d34a3ab92649 |  | note | Detail - Ezy-Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | 336ab228-65c5-5573-ac03-b3ad26ccdd49 |  | note | Frequency - During installation and on completion
label | c5aa9bd9-15b0-5bb9-891c-9260ecd303b9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | 1700ea8f-549b-564b-b945-0fc282728c97 |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | fe707625-df85-5b1f-aef1-2ed02531b593 |  | note | Records - CS-4117
checkpoint-status |  |  | checkpoint | 5 - Guardrail Installation
label | e0854348-e7b9-55e1-82a0-e69d90b213f7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ad637255-a479-5762-8276-cc97ecc4397f |  | note | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | b1a0c518-26d9-589f-bd96-010209adc186 |  | note | Frequency - During installation and on completion
label | 005798a0-4e73-5431-a18c-ca16adf645bb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | cf9970c9-3e52-5aad-a9a4-d57c7e8e228b |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | 8baa1438-1fef-5c33-a837-6d020bfc3d70 |  | note | Records - CS-4117
checkpoint-status |  |  | checkpoint | 6 - Guardrail Installation
label | f1f5a120-d6f2-5b36-9858-35a55cd8a48a |  | note | ACTION (Hold, Monitor, Witness) - W
label | d4470976-9a52-5425-9168-c9abcc19d363 |  | note | Detail - Thriebeam shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | ad40fd65-7be2-5940-9f09-8684dc350f96 |  | note | Frequency - During installation and on completion
label | ca1540e4-2360-582e-a8c6-b16a83d25cb5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | df1dc594-d6aa-5886-a79c-ac90f8773602 |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | 31a84553-b69f-5d79-8b13-c94e13314a88 |  | note | Records - CS-4117
checkpoint-status |  |  | checkpoint | 7 - RSHDS Inspection
label | 91a411ac-3aa1-5bff-996f-c083b2a2fa2b |  | note | ACTION (Hold, Monitor, Witness) - H
label | ecf6c798-47ca-5a5a-b511-70a086680fbf |  | note | Detail - Inspection of constructed safety barrier to confirm compliance with NZTA M23 and the IFC Drawings
label | c7dcbbd0-30b4-5bcd-a685-99f5cfe9545b |  | note | Frequency - At completion of Safety Barrier Installation
label | 21c46ba9-99ac-5a24-b125-7da52adcbd8b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | fd8d289b-995d-560e-9de2-a19660c72519 |  | note | Records - RSHDS Audit Form
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-Construction
checkpoint-status |  |  | checkpoint | 8 - Final Walkover (Snags)
label | 8753b4fe-8b51-562f-a5f0-1c324cad9120 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6651a55e-edd3-5f9e-b8a8-0e06da684337 |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | 9b965300-0d14-551e-8378-79c22dc8fb2c |  | note | Frequency - At the completion of the Lot of work
label | e9b5bc9d-ed9a-51e7-956e-87c1841108a4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | 35c47a8e-1105-53af-a586-36af199db417 |  | note | Conformance Criteria - Completed report
label | 4be9afe3-3ff1-514e-bcf3-efeef0edf772 |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Survey As-builts
label | 0cef8774-07a4-538e-9f01-7a19f60c1a84 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 92f2e754-f8de-50cb-9bd5-1db3e15e44c0 |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | faa1c20a-e519-56f2-90e7-21ce46d1c02e |  | note | ○ A survey as-built of completed work must be provided
label | 7ebc6ffb-f07d-526d-9085-cc990d3876f8 |  | note | Frequency - At the completion of the CWP of work
label | c5732c3f-431e-5db0-a031-03ce2219040f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 5cc3b071-c09a-5fcb-8c31-38449a81e143 |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | ffbd2eb2-91b2-5d2e-a374-193b4e20db69 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Quality Assurance Deliverables
label | 9b509e5a-c473-5640-88e5-bc83e2bc0bd7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 790941d1-79de-5bab-bb3d-dd0c2022c59d |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | 5dc63dd9-c92f-598d-ba8c-a7d2b2594b3d |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | 050e5ed2-50d7-5510-81bb-ac5575699606 |  | note | Frequency - At the completion of the CWP
label | 5134840e-3163-53f7-913f-a631ca69609c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 8dfaf052-04b3-59fa-ba8f-c0bc638b265f |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 0d016bb1-d3ae-500b-93c0-6e9543358bc3 |  | note | Records - As-builts, NCR's and RFI's
checklist-sectioned |  |  | checklist | CS-4015 - Shop Drawings Checksheet |  |  |  |  | Yes | CS-4015 - Shop Drawings Checksheet | 553045a9-49bf-44d4-9c85-240e4af806c4
checkpoint-group |  |  | section | Shop Drawing Check Form
checkpoint-no-status |  |  | checkpoint | Shop Drawing Check Form
text | 4fe9501a-f07a-55c1-9d0d-9cd7d48efc93 |  | textbox | I |  |  | (name)
text | e3ced5d4-e201-5d51-848b-61653de2e971 |  | textbox | of |  |  | (firm’s name)
label | 697186a3-e0c9-53bd-a164-3f23703aa571 |  | note | being the Construction Team’s designated person responsible for the preparation of the shop drawings required by specification C0600.7, certify that the drawings listed below have been prepared, reviewed, co- ordinated and checked prior to submission to the Design Team in accordance with the requirements of C0600.7.
checkpoint-status |  |  | checkpoint | 1.0 - Shop Drawings prepared to an acceptable presentation standard
checkpoint-status |  |  | checkpoint | 2.0 - Shop Drawing revisions noted and clouded
checkpoint-status |  |  | checkpoint | 3.0 - Dimensions:
label | df05dc17-d6ab-5277-8093-7743dc2a18f5 |  | note | Relevant dimensions indicated
label | ed80597b-6572-5ca7-a139-ddca832f7517 |  | note | Site measurement noted and checked
label | da43abfc-e307-5f55-879d-9dfa37709d6b |  | note | Dimensions co-ordinated and checked with the requirements of the Contract documents and other trades
checkpoint-status |  |  | checkpoint | 4.0 - Drawing numbers and revisions from which Shop Drawings have been prepared noted on the Shop Drawing
checkpoint-status |  |  | checkpoint | 5.0 - All relevant contract information including specification requirements indicated on Shop Drawings
checkpoint-status |  |  | checkpoint | 6.0 - Shop Drawings checked and co-ordinated with the requirements of all Drawings and Specifications (e.g. Architectural, Civil, Structural, Building Services, etc)
checkpoint-status |  |  | checkpoint | 7.0 - Shop Drawing checked and co-ordinated with the requirements of other trades Shop Drawings
checkpoint-status |  |  | checkpoint | 8.0 - Drawings checked for corrections prior to re-submission, where required by Design Team to be re-submitted
checkpoint-status |  |  | checkpoint | 9.0 - Shop Drawings approved by the Construction Team for fabrication, signed and dated
checkpoint-status |  |  | checkpoint | Signoff
text | 6be40e3d-6af0-58cb-9505-1b53747c401b |  | textbox | POSITION:
date | 3a2ce306-e3e5-5573-94dd-a7661171096b |  | date | DATE:
holdpoint |  |  | signoff | SIGNED
checkpoint-group |  |  | section | Drawing Numbers to which certification applies are listed on the following page
checkpoint-no-status |  |  | checkpoint | 1 - Drawing
text | 80dcb018-5d2f-5d2f-8a82-da9a89ec0cf9 |  | textbox | DRAWING No.
text | e386bcfd-62c0-58f9-91e5-1f67d07a25cd |  | textbox | REVISION No.
text | 84a08ebc-0f8e-5083-9098-eefa02add343 |  | textbox | TITLE:
date | 5207036b-4f05-58fc-945b-3dad3099f802 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 2 - Drawing
text | f5942e0d-b327-5a9d-b22d-557f9053470a |  | textbox | DRAWING No.
text | 3643f208-91a6-5f99-8dc9-f24221f0ee52 |  | textbox | REVISION No.
text | 640c12a0-0107-531c-b825-8de8d5839f4a |  | textbox | TITLE:
date | 967aa5a5-5fe3-51d3-9533-7cc1d78f00d5 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 3 - Drawing
text | a3c164fe-2856-5589-bf77-f3d3e18b2685 |  | textbox | DRAWING No.
text | b5b04439-e1f2-5ea3-a5ab-6af0d5f54fce |  | textbox | REVISION No.
text | b00b9617-b49a-5da6-aa7f-513c5223fcae |  | textbox | TITLE:
date | 2c778624-c3de-50d2-a8a4-6b6350b7ab00 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 4 - Drawing
text | 5f8d666b-5961-5e7d-b7e7-0a319648053a |  | textbox | DRAWING No.
text | 2f4eebc7-3074-5f0f-b15a-613cd4b5b57f |  | textbox | REVISION No.
text | 37d7be72-4916-52d0-8250-824f6bf5c0b1 |  | textbox | TITLE:
date | fe1bf8e6-9222-58be-8b8d-1ff3619ad069 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 5 - Drawing
text | c1d2c86c-6db9-5af7-9942-96166da25f9c |  | textbox | DRAWING No.
text | 79633d11-9c54-5da8-8630-d5f737261a86 |  | textbox | REVISION No.
text | 666ce751-985d-59fc-b42f-288bdd92e85e |  | textbox | TITLE:
date | ca86c4d9-b76b-55cb-bc83-69f641690021 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 6 - Drawing
text | b0ee6211-ce22-5da9-8991-23f12aa88724 |  | textbox | DRAWING No.
text | ff51ec07-09db-5a7c-839e-3a2d07a8e5c1 |  | textbox | REVISION No.
text | 6016a80f-9755-5009-9aa1-8520a48813af |  | textbox | TITLE:
date | 6bf5220b-0ae3-5093-bad2-802a70f2afd6 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 7 - Drawing
text | 7fe44aee-cd88-5752-9ff5-063bc839988a |  | textbox | DRAWING No.
text | 4e7fa5a3-1e1b-5fe0-93bd-06aab7db72dc |  | textbox | REVISION No.
text | ca4d1989-da34-5367-81dd-08dd61188722 |  | textbox | TITLE:
date | ad31fd6f-891f-5e7e-81ee-50b10257cc3a |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 8 - Drawing
text | 55bdd112-1b9b-55f2-9aa7-c699908fe1b8 |  | textbox | DRAWING No.
text | ace3e155-97d6-5b0f-bdd3-e0f7a57592ab |  | textbox | REVISION No.
text | b8bd8c73-9033-5ce4-aa1c-81f5e7a60d8f |  | textbox | TITLE:
date | b5e336ad-2d5e-5a06-aba8-88e51096c7b0 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 9 - Drawing
text | 31513f91-f8c4-508d-9ed7-94946e4981bf |  | textbox | DRAWING No.
text | 6529e285-9964-5c1e-b440-e032fad07e67 |  | textbox | REVISION No.
text | b81d1683-5e72-57ef-8e90-7286915426ca |  | textbox | TITLE:
date | 39001a81-73b5-5194-811b-b55254c46d42 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 10 - Drawing
text | 27208a17-9708-5422-a7a0-acec846ddb98 |  | textbox | DRAWING No.
text | f3421ffe-18e9-5e79-9e3a-73a06666964a |  | textbox | REVISION No.
text | 93bde16e-0541-507d-b538-9925900a878c |  | textbox | TITLE:
date | e550298e-1fa6-5350-9f80-160362a7ad11 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 11 - Drawing
text | 9c8f286b-8dce-5b24-b790-eef9d16da429 |  | textbox | DRAWING No.
text | ab1b0003-c8e5-588b-83c7-0d0efdca89a2 |  | textbox | REVISION No.
text | aeb138a9-20d8-5bf5-a401-9cc7e6d714e3 |  | textbox | TITLE:
date | 3e90cb3f-9fbc-57e1-abc6-a8ad6dcf905a |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 12 - Drawing
text | 59664347-5e6a-57f2-ae9d-46387eac9893 |  | textbox | DRAWING No.
text | 0e21b7c3-c5e6-5a39-82a8-b139983693e2 |  | textbox | REVISION No.
text | 8a2d86bc-9bbe-5504-9982-7e9d78059fa0 |  | textbox | TITLE:
date | 69400165-e34a-51ec-8a0d-c78d77c4da51 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 13 - Drawing
text | 6550018a-cc40-5e84-b520-3e250ec643a0 |  | textbox | DRAWING No.
text | 794278e9-3cf6-5167-947e-4d239a1c5402 |  | textbox | REVISION No.
text | 79569e96-2b46-5a5e-a2b3-4381b09bd253 |  | textbox | TITLE:
date | 96eefbfe-5b96-5d73-a64e-1a462fa19879 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 14 - Drawing
text | 33e266c6-8aa5-521f-9964-3775122ad12e |  | textbox | DRAWING No.
text | 24fa910a-55e2-58fc-a940-52023d50ed86 |  | textbox | REVISION No.
text | cea063a6-398f-5762-b70e-847c154cc216 |  | textbox | TITLE:
date | 78cde60f-48aa-5c96-8fbf-a7cd762acbce |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 15 - Drawing
text | 91dc82a1-736b-5a79-a81b-575b62f11001 |  | textbox | DRAWING No.
text | 8edef60f-7be9-5cd9-9fa6-8e93347e0e92 |  | textbox | REVISION No.
text | c544b40f-1bec-574e-8a8c-921cfc8994c5 |  | textbox | TITLE:
date | a9a75981-24ba-5bce-ad42-5848ac669421 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 16 - Drawing
text | c0f62ab4-2521-5b6c-b5f7-401202cf6abd |  | textbox | DRAWING No.
text | f2c773fe-2ceb-596f-896b-6123599c6066 |  | textbox | REVISION No.
text | 52079202-3ac7-5091-b8f9-6e9e529c3688 |  | textbox | TITLE:
date | 64efed31-4cd3-5136-bb0f-54f7900ca22e |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 17 - Drawing
text | 1f11de49-fae0-592c-b0fd-5f2bfa2c0953 |  | textbox | DRAWING No.
text | bfbf0c78-8444-5648-914c-411dd10c1d4c |  | textbox | REVISION No.
text | 67afd59c-7491-5c35-86dc-68415784040b |  | textbox | TITLE:
date | 77bfdd00-a4a3-531a-8df9-e0d3c1e69e5a |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 18 - Drawing
text | 61ded373-fa10-5710-9144-ad423c1380bd |  | textbox | DRAWING No.
text | ebc6743e-83ab-51c6-953b-ae67dd15be10 |  | textbox | REVISION No.
text | d3b74d0d-92b6-5d69-82b2-80efb9d6faec |  | textbox | TITLE:
date | 24e22327-276e-5a1c-a23a-8582b3febc32 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 19 - Drawing
text | 10582985-1228-58c9-963e-c8964d52ce4b |  | textbox | DRAWING No.
text | 798f9f5b-47c4-5456-81b1-2b0926d9c012 |  | textbox | REVISION No.
text | 6faebebe-eb68-547d-a5a1-3da5d8b88118 |  | textbox | TITLE:
date | 62ea176f-a109-56e5-a3b5-ed339ec7c89e |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 20 - Drawing
text | 6d24aa17-0066-5b88-bddd-7bc976625d98 |  | textbox | DRAWING No.
text | d865c7ac-9852-5b7d-b42c-ee7676f36bfb |  | textbox | REVISION No.
text | b3ec07c7-22ce-5080-a2c4-bcc6cbbe4e15 |  | textbox | TITLE:
date | e78cb2c5-526d-5aa3-8023-0495e6f5bd40 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 21 - Drawing
text | a162abc4-3bb3-5d0e-8943-34cf7407fcbd |  | textbox | DRAWING No.
text | ca57626e-24b8-5902-b481-61f8f38ffccc |  | textbox | REVISION No.
text | c4871b37-dc25-5036-879d-f9189b942fd7 |  | textbox | TITLE:
date | 1ec33f29-a1ba-5c16-b2d6-df8f0d19a197 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 22 - Drawing
text | b841ccee-6b2a-52fc-b396-e9fb0105ba2c |  | textbox | DRAWING No.
text | a58d9d4d-14d5-5172-a0ca-193628a84927 |  | textbox | REVISION No.
text | 6d59254b-9cee-5070-8934-f27e74acb8c7 |  | textbox | TITLE:
date | fc16cd8e-6d8a-5a66-bb7e-4f728420a711 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 23 - Drawing
text | dba12262-47a1-5630-a8c2-1abc8e011eea |  | textbox | DRAWING No.
text | d728a2b7-df74-5e09-b319-b7f4cec9b611 |  | textbox | REVISION No.
text | d873f0b7-955a-51a9-bbc6-37f6b98cf577 |  | textbox | TITLE:
date | 17aedf0d-9774-5047-a2e2-dff790296e0c |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 24 - Drawing
text | 79785695-29f6-5d4b-be48-074cb1f51514 |  | textbox | DRAWING No.
text | 05c0c2d2-f0ed-5ddc-ad9a-a00fb1f8e4e3 |  | textbox | REVISION No.
text | ad356df0-1ddd-513c-8e00-1012202024d3 |  | textbox | TITLE:
date | 723b2523-5ccb-515e-8466-ef652149245d |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 25 - Drawing
text | 79184994-b490-5589-b5b4-789d074017a2 |  | textbox | DRAWING No.
text | caaa36b8-17d2-517a-a092-a7ab39ebb103 |  | textbox | REVISION No.
text | ca421437-16fa-5e7d-83a3-3a099db07197 |  | textbox | TITLE:
date | c0e88bad-956d-5d97-bfe7-22fb4efd1433 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 26 - Drawing
text | 76bd4922-0f3e-59d8-9203-346f0a961bf8 |  | textbox | DRAWING No.
text | 92d4d2b6-f4a4-5ac4-9ddb-93185e72f8f1 |  | textbox | REVISION No.
text | 1da85a81-653b-57e8-95ce-90f8f349a18f |  | textbox | TITLE:
date | 156b82a3-d916-570d-ae30-00694a22e597 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | 27 - Drawing
text | e28a1344-5d4d-5760-9732-751cb09372a9 |  | textbox | DRAWING No.
text | 032991e6-88d7-5c8a-b455-17f5acf157de |  | textbox | REVISION No.
text | 0b848017-1ff6-5d23-ae4d-dc41a55cc924 |  | textbox | TITLE:
date | 763c8d60-8389-5140-aaa1-955b05fdefd6 |  | date | DATE ISSUE TO DESIGN TEAM:
checkpoint-no-status |  |  | checkpoint | Note: A completed copy of this form shall accompany all shop drawing submissions to the Design Team.
checklist-flat |  |  | checklist | CS-4095 - Spunlite - Pile Foundation Checksheet |  |  |  |  | Yes | CS-4095 - Spunlite - Pile Foundation Checksheet | 5547a0ee-db46-4cfb-b0f9-a73f70e3197b
checkpoint-no-status |  |  | checkpoint | Details
text | a59bf57d-9856-569c-99a0-d1d9be880e06 |  | textbox | Project Area:
text | 3f8f2f4a-6a1e-59dd-b284-8209dd2c3514 |  | textbox | Supervisor:
text | ce17e9dd-9f39-5a0f-8e9e-10a670aa1870 |  | textbox | Site Engineer:
text | afb8bf91-ffaf-53f3-83ac-3af4a545f1ba |  | textbox | Pile Number:
text | 5b536e48-6856-5895-a6ea-4367bdf78386 |  | textbox | Location Reference:
text | b6d21f4f-c320-5eb0-99e2-a9e7e7a03c68 |  | textbox | Service Investigation:
checkpoint-status |  |  | checkpoint | PRE-PILING SUMMARY
text | 023f72f9-953a-5fcc-a77b-b7042ff04491 |  | textbox | Piling Foreman/Supervisor:
date | 4017c347-ed4f-5066-8d43-a90b52fd713a |  | date | Hydro-excavation Date:
text | d89483b6-c481-59a8-8607-dd44de438388 |  | textbox | Casing Length:
text | fc1dc8e6-82b1-5d0c-808c-b06a00c65de2 |  | textbox | Cage Length
text | f0ef38d1-8860-5966-9a6a-2c9ca9983dcf |  | textbox | Design Pile Depth (min):
text | 471baed3-a8a2-5955-a358-b756e258164d |  | textbox | Design Pile Diameter (min):
text | ab93f221-8ecf-5c27-a319-9ddc3bb87b43 |  | textbox | Casing Diameter:
text | 9eeeb2a5-d2f0-5bf1-8adb-2a912a9a25b7 |  | textbox | Cage Diameter:
radio | 8c8279d1-00c3-528f-a301-101f6b4230b7 |  | radio | Pole Type / Socket Type: | Standard – RS168 x 750DF,Catenary – RSe273 x 900,Short – RS115
checkpoint-status |  |  | checkpoint | DRILLING AND PRE-POUR CHECKS
text | 95699d57-ae12-53ed-acc0-73523be1d76a |  | textbox | Services check (depths and offsets):
date | 7555d502-b50c-5785-a74e-40db4ffc504c |  | date | Casing Install Date:
text | 644230b2-fec3-5f5e-8336-1aae5ef2675a |  | textbox | Piled depth:
radio | fc2b2efe-f9e2-5b53-9ee9-7b1cfd9998ed |  | radio | Plug Type: | Soil,Concrete,Not required
radio | 31c35dc5-d2a8-5775-821d-79e1db527cd3 |  | radio | Top of casing to FL check: | 90mm (Catenary),110mm (Standard)
label | 8baad9d3-ce3d-55c8-88b1-ea2ef8e33eb2 |  | note | Pre-pour checks
boolean | 4057e2c5-373f-53cc-923f-b17bfde0cb23 |  | tickbox | Speed form
boolean | 4ae64325-8074-5f9d-b126-b30605a649a8 |  | tickbox | Cage placed (75mm cover to reo)
boolean | 44cb10e2-0f32-5226-a15e-3f34b7500eeb |  | tickbox | Socket set in place (check pole centre)
boolean | 9438ffb3-8d3c-5f85-b6c8-1150504fefc6 |  | tickbox | Socket plumb check (pre-camber check for catenary poles)
boolean | 98f62c18-551f-54a8-b2fd-7caa03f15872 |  | tickbox | D16 starters installed
text | 319ae8d4-534f-58aa-9ae6-cf633149a97a |  | textbox | Concrete Mix Type:
text | b422f03c-a424-5f38-a1bc-137c0cd53923 |  | textbox | Docket number
date | e1b05ee6-b8ea-5d8f-a19c-ec40a84542fa |  | date | Tremie Pour Date:
checklist-flat |  |  | checklist | ITP - G1302A Culvert 33 - SH38 RS179 RP5.805 - Network Drainage | itp |  |  |  | Yes | ITP - G1302A Culvert 33 - SH38 RS179 RP5.805 - Network Drainage | 55b5d343-05dd-44a2-94d9-bc79056fcc1c
checkpoint-status |  |  | checkpoint | Project Site reps.
text | f545cc4f-208b-5ca1-b5c1-0f2a9892027e |  | textbox | CPS Eng.
text | d213dc9b-a30c-59a4-a578-59a396b477e5 |  | textbox | Site Engineer
text | d079e68c-7e45-5cc1-a881-df73e498c343 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 16575ef2-04bd-54a0-a818-089de7556a73 |  | note | ACTION (Hold, Monitor, Witness) - H
label | dd57d66f-c7e4-54f7-bf38-895874e85954 |  | note | Detail - Setout inlet & outlet points with inverts as required by Contractor to construct to design
label | 6ab8dad9-5700-5bea-a657-e29da4edcc96 |  | note | Frequency - Prior to commencement
label | 776c3cec-8b42-5939-91b6-16fbb519c250 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey (As agreed with Engineer)
label | 6e30d5d3-6be1-5c03-b906-e73e09ffa1cb |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Locate existing services by hand digging
label | e132ff9c-0ddd-5298-b124-c3096cd53f36 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7038c967-e212-5c3d-bd9f-44e268bbfc67 |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging/hudro excavation
label | 1f040c64-d850-5c95-a4d6-a86cef7d2fc7 |  | note | Frequency - Prior to commencement
label | dd0201ed-5184-58c4-9674-7d92e88cc33c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | 76bfdf77-50fc-5fd5-b168-56f9a46c78b2 |  | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As-built all services
label | 948cdb2c-9273-5583-8431-d25d395a4a91 |  | note | Records - As-built Drawings Doc. Review
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Trenching and Excavation
label | 3e8b8de4-4ef9-5f56-b762-e202896a8fc8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d8d323f4-1741-536b-b6f8-089785e6d482 |  | note | Detail - Inspect trench profile and ensure it is correct to lines and levels to design
label | bbd9ba36-eeda-57d4-927d-4dbb3a377ebc |  | note | Frequency - Daily
label | 06d75a3a-213b-51de-b797-317146870553 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | 292a4ab0-c38d-5d2b-8a05-a6a3938f9e17 |  | note | Conformance Criteria - Line and level is correct
checkpoint-status |  |  | checkpoint | 4 -
label | b682dee9-166b-5197-8ccd-c9ca01f3023c |  | note | ACTION (Hold, Monitor, Witness) - W
label | b46d3709-6546-5155-bc92-2bb0d097f9bd |  | note | Detail - Ensure trench width is sufficient to provide enough space on either side of the pipe
label | 4d067bbb-8c5b-577c-aeed-f3b603c7824c |  | note | Frequency - Daily
label | db8f8579-44d5-5e7b-9700-a395dc9cc665 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | d05ffd38-9e88-579c-9f3c-b0d0b89c5ca2 |  | note | Conformance Criteria - D/6 or 150mm whichever is greater on either side of the pipe
checkpoint-status |  |  | checkpoint | 5 - Foundation Compliance
label | 3b22f58e-6031-51ce-98ed-a5ff19920cbc |  | note | ACTION (Hold, Monitor, Witness) - H
label | ec884a26-f836-593a-b7dd-ec159062ffb8 |  | note | Detail - Test formation level on completion of excavation to check if undercut required
label | 69e8aaf1-4775-548f-9675-0571cced996a |  | note | Frequency - As stated
label | f210f1e7-33d0-5c20-95e1-27751f0307eb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection by Designer
label | d2ba1132-1de0-5702-8da1-92d7b689add7 |  | note | Conformance Criteria - Designer to inspect formation level at outfalls / inlets.
label | e9f7ed52-bc43-5119-ae79-23357961d649 |  | note | Records - CS-4025 Drainage Line Record Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Pipe Bedding Material Compliance
label | 6749cb88-5222-5e9f-9365-956f2c1f7c1b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2b99929e-c842-52b8-bee3-00f1461861e0 |  | note | Detail - Material to meet specifications dependant on material type selected
label | 211d8ccd-3d11-500b-8ca7-64929e545c0c |  | note | Frequency - Each material used
label | ed87da44-eddb-5dd3-88ad-40d72f88b5d9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 243a642d-0d76-5f40-935c-dff226d80b4b |  | note | Conformance Criteria - Compliance with requirements from Specifications
label | 5dfc7e30-7960-5af4-9a19-5677c0b1733e |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 -
label | 39731e4c-883e-51f4-9068-65ff655ec998 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 80018f50-928d-5d24-b374-e9d4cac89a81 |  | note | Detail - Backfill Construction Material
label | 8586469e-6bed-5594-8f4d-9f3a105644a6 |  | note | Frequency - 1 test per 50m
label | 0bcbd37a-da05-5ff3-af89-5ea7300e3ad1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | e4c93179-8a29-52af-a83a-c5ab664377d8 |  | note | Conformance Criteria - Solid wall pipe – Pea Metal < 7mm
label | 89076ff8-da2f-5207-ac75-be4adfe3f441 |  | note | Records - CS-4025 Drainage Line Record Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Bedding
label | 78cc7594-88df-5de4-bda9-dffcd88ce87a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4e78b5d0-ce13-5d5e-b3d2-33a842704068 |  | note | Detail - Bedding - Ensure correct thickness of bedding is placed
label | 0652095b-b427-51c7-aed8-d5232dc1ece9 |  | note | Frequency - Daily
label | 866f2b7f-7a30-5c7c-9547-28eb7935f31d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | 7b351f5f-616f-543e-afd7-2b0c66eeb1fa |  | note | Conformance Criteria - Type 3 support as per drawing
label | c79feeb5-92b8-5309-9534-c669c6d39cd2 |  | note | Records - CS-4025 Drainage Line Record Check Sheet
checkpoint-status |  |  | checkpoint | 9 - Pipes and Precast Units
label | 653b9662-6453-56a3-808e-f64495548ffd |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7fb7ebe3-0c65-50f8-af51-7b9d7b6d56f8 |  | note | Detail - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | c733131e-844d-5745-8738-8b29cd65038d |  | note | Frequency - Each delivery to site
label | 23f4bf35-09a1-51c3-b867-a0e40db7571c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
label | f5c7662a-95c0-5860-b5c8-d2d7ef269e0d |  | note | Conformance Criteria - Comply with Section 3 AS/NZS2566.2
label | 48104b3d-615b-555c-8893-542327ef90a3 |  | note | Records - Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Pipe Laying
label | f1bb784b-41d4-5492-8f7f-5f635cc3c16b |  | note | ACTION (Hold, Monitor, Witness) - W
label | ef80c2f2-8547-5396-b24b-dc65b1e7a06a |  | note | Detail - Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall be less than 3mm
label | 9400ffc4-d8d7-50c6-8019-d2d6020e7de3 |  | note | Frequency - Daily
label | 216a6b00-2293-5343-bc28-3b0a366670c4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | 0b8a25d0-c28d-51c3-b81e-744f2f0c9ecd |  | note | Conformance Criteria - Line and level to follow existing pipe
label | 025c67b7-7ca1-58c4-b33a-e9381dcfd029 |  | note | Records - CS-4025 Drainage Line Record Check Sheet
checkpoint-status |  |  | checkpoint | 11 -
label | 53c46a92-a0ac-5c7e-a19f-174f0f1b685d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4a69946b-eeb4-5598-ace1-d59b2847534d |  | note | Detail - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | b31e3dd5-29ec-5b36-8320-e35dd24f7c2b |  | note | Frequency - Prior to backfilling
label | 152ae4e1-3659-5c06-8f94-b0c5cc5d1d97 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | a9f4368e-61a8-5775-8179-2fe77702b67b |  | note | Conformance Criteria - No defects/ gaps / pipes are aligned correctly
label | 913d68bb-9dc3-54e4-8e1e-19608f29569c |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 12 -
label | 40aa9ccd-e19f-519c-bd20-48a893a3e5ae |  | note | ACTION (Hold, Monitor, Witness) - W
label | 473af6a9-1e1a-5756-bde8-871fd662f0df |  | note | Detail - As-built survey of pipes installed
label | 2b72b4e5-79b1-5bb2-9a60-02b57c0093f3 |  | note | Frequency - Once line is completed between 2 structures
label | 7033a7f4-a514-5568-959a-e797b9e039ee |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 8a39abe4-8b42-5940-81be-a5e801482500 |  | note | Conformance Criteria - Invert level <= 5mm and grade <= 3mm from design levels
label | 160a218a-87b7-5ba4-8593-24647437f3e0 |  | note | Records - Survey Receipt
checkpoint-status |  |  | checkpoint | 13 - Design Engineer Pre backfill Inspection
label | 26b7c0e9-0d90-5e1e-b024-96e2ba39869d |  | note | ACTION (Hold, Monitor, Witness) - W
label | a0d9b730-bd3a-5d41-891f-7d76f67b1c4d |  | note | Detail - Inspection of pipes prior to backfilling to ensure they have been installed correctly and that the joints are sealed. Check for any gaps.
label | 859de29f-8940-5d54-8f29-a082dc11c932 |  | note | Frequency - Daily
label | 60398078-9ae3-5c47-9c50-b856e32742c6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | f2516b49-da8b-5611-967d-95353bf191b9 |  | note | Conformance Criteria - Compliance with the Specification
label | 3f9f6dc3-1ed2-5788-af25-8d9a355ae033 |  | note | Records - CS-4025 Drainage Line Record Check Sheet
checkpoint-status |  |  | checkpoint | 14 - Pipe Backfill Compliance
label | bc7f84da-b4d3-58c5-8767-9ae369953dfa |  | note | ACTION (Hold, Monitor, Witness) - H
label | a79eb23a-ca54-51b4-897f-b544e398d70f |  | note | Detail - Material to meet specifications dependant on material type selected
label | 9152e1c9-59c4-5d4e-9ba3-3f6d1476baf1 |  | note | Frequency - Each material used
label | 72ed1fad-4145-5f3b-a842-66d8a1bd3458 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | e263650e-5638-51f4-a7f6-f367fee9c31b |  | note | Conformance Criteria - Comply with grading specification 100% pass 50mm at least 45% pass the 19mm sieve, and not more than 10% pass 425 micron sieve, CBR not less than 40 and SE of not less than 40
label | f49a5256-1690-5c04-89a8-108f2f0241b2 |  | note | Records - CS-4025 Drainage Line Record Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 15 -
label | bfc5326e-f57f-5d19-847b-92ff09c5595d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 235822f5-df57-5fae-934d-ab3719476045 |  | note | Detail - Backfill Construction Material
label | 79255d63-09ef-56e0-86e3-87464bb9478a |  | note | Frequency - 1 test per 100m
label | 2ec54c99-d88d-5cd9-ba21-e2ec3a3fdd40 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 56ca5a48-f53c-59de-a66d-7cca267f888a |  | note | Conformance Criteria - Comply with grading specification 100% pass 50mm at least 45% pass the 19mm sieve, and not more than 10% pass 425 micron sieve, CBR not less than 40 and SE of not less than 40
label | 029c04a4-35a7-5b18-be88-74bcf208fe7e |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 16 - Backfilling
label | d19ac24c-b231-5f5c-b815-654a11d50484 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ce0c1df5-9f6c-5503-b408-88c7d83295dc |  | note | Detail - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms. Remainder of backfill to be done with excavated material.
label | 18c0f984-e5d5-5418-9f43-1aae0dbf4ad2 |  | note | Frequency - 1 test per 20 m length of trench per 300mm lift
label | b4224ab9-bb4d-5664-9933-23ccd6d04e82 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 3dc9bfbd-cdc4-5373-93ff-c2c99ea963b6 |  | note | Conformance Criteria - 97% (under carriageway) or 95% (under berm) of MDD or Clegg equivalent
label | 370f1dac-2028-5096-ba84-0b5e0e78c3d3 |  | note | Records - Lab test results
checkpoint-status |  |  | checkpoint | 17 - Structure installation (Manhole, Catchpit, Wingwall)
label | 5bc7a3df-dcd0-51c0-a34e-255795c4810f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 26c60ec5-f9b9-5a9e-999b-87282fa14255 |  | note | Detail - Structures to be installed to the design survey location and level
label | e13a2d5d-0926-5591-bc5a-6e42d30ee8d3 |  | note | Frequency - During structure construction
label | a43ca19c-90ab-59d2-8f67-32678118181c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | d3f1fbaa-58da-5ad8-bfc4-d7a17c5eab12 |  | note | Conformance Criteria - As Built Survey
label | 44f5b7f5-75ce-5bba-9522-d2df10350614 |  | note | Records - CS-4006 Manhole Catchpit Board Check Sheet and Survey receipt
checkpoint-status |  |  | checkpoint | 18 - Survey As Built
label | 5e635146-034b-5aef-8de6-ee4b2faff1af |  | note | ACTION (Hold, Monitor, Witness) - W
label | e5581a26-d7a5-529b-953f-5766b333d131 |  | note | Detail - Arrange as-built survey of the structure and all invert levels
label | 87b87545-6273-5df8-afcf-7a16f28e4c57 |  | note | Frequency - Once installed
label | 1f9a9c04-cd8e-5855-b040-70247e94edba |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 6a34a104-9bd9-5510-acf6-c12de56e9c07 |  | note | Conformance Criteria - As Built Survey
label | dcbad85a-a77f-5956-a1aa-8e25fbd5b5b6 |  | note | Records - Survey Receipt
checkpoint-status |  |  | checkpoint | 20 - Lot Number QA File
label | 1e42318d-35d2-5e5e-bb21-42f2c7b4c822 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 46beed26-57bd-5594-aec3-505907c734c4 |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 7cd8e859-a5a9-5289-b029-884fb787e707 |  | note | Frequency - At completion of Lot
label | 1a5843f7-02ab-56c0-a84f-d4db60150701 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 82d3381b-6694-505b-afcf-b24ecb6a6d88 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 787443a7-7bcf-53f1-a6d2-6e920577d6ce |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 21 - As-builts
label | e5d2c777-d5c4-5550-a904-ca7ae6f11a1d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 18aa13e9-d7d4-5205-9044-f4fb3fe63b22 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | ddd07923-2f18-5bbd-9cae-225668548751 |  | note | Frequency - At the completion of the Lot of work
label | f5787a4a-27b6-5a75-a052-ed2e8a579c7c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 14333cb1-6589-5728-a2b9-8fb729b8c2de |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Maraetaha Bridge 5 - D2102A-ID1507 | itp |  |  |  | Yes | ITP - Maraetaha Bridge 5 - D2102A-ID1507 | 576460f8-072f-412f-bf4a-eb21bfd70cac
checkpoint-group |  |  | section | Section 1: RECEIVING INSPECTIONS
checkpoint-status |  |  | checkpoint | Project Site reps.
text | f88199f0-f6c1-51c4-a017-defc66b7e08c |  | textbox | CPS Eng.
text | 316bd405-13e1-504d-ad54-34ab280d0ec5 |  | textbox | Site Engineer
text | a38f8463-b9d9-50e3-b778-65e744b5639a |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - 2t Ecogreen/Kyowa bags
label | 5265307e-b107-5e3c-8f03-8227cdd7d2cc |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1c2df015-5591-5721-9fac-84c9550a40fd |  | note | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3436.BM(14) S02-S03
label | 9099b30c-04fb-5e55-8983-7cfe19b3e5b7 |  | note | Frequency - Prior to commencement
label | d6227ae5-e418-55be-899c-ad16311a97ec |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | b6349a32-d48d-57bb-be31-d38ffb3d57b9 |  | note | Conformance Criteria - Purchased from Bluemont or similar approved
label | 309b8b80-5a8f-5bdc-a53a-bbcf604a8756 |  | note | Records - Material cert, delivery dockets
checkpoint-status |  |  | checkpoint | 1.2 - Class D A39 Geotextile
label | 7aeba7d8-1a02-52de-82eb-15b3d6e88258 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f4a76730-ab63-5c4c-8519-180ed5fee44a |  | note | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3436.BM(14) S02-S03, TNZ F/7
label | f5a113ee-7bdb-55af-bb47-9b842542e214 |  | note | Frequency - Prior to commencement
label | ab890e93-1f8c-5a94-91e2-e646c0228f3c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 5b2a2d0c-da5b-5b49-97d6-fbd89b5f3682 |  | note | Conformance Criteria - TNZ F/7 filtration class 1 strength Class D
label | 1f30795a-3975-51a8-831a-3dbc5322fd40 |  | note | Records - Material cert, delivery dockets
checkpoint-status |  |  | checkpoint | 1.3 - Granular Backfill AP65
label | da86400f-44a8-5d3b-96a0-da6680eacfb3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1340db44-4782-572c-bb24-4669e2ead6bd |  | note | Specification/Drawings Reference - SH2 R5 461/7.78 - Maraetaha Bridge No. 5 (BSN4688) Pier Protection works 2-U3436.BM(14)-S2-2
label | cda9c819-d746-52fd-8c18-b9df0421556b |  | note | Frequency - Prior to commencement
label | 74d141d7-7af2-5364-ba5d-33a971cf8688 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Material source property reports
label | 402f5d66-2818-5053-8b94-2ca86734722b |  | note | Conformance Criteria - AP65 shall be hard, durable, well graded, free draining material with maximum particle size of 65mm and not more than 5% by mass passing a 75-micron sieve
label | b0b85316-24fe-5300-b748-a9ecc5465dad |  | note | Records - Material cert, delivery dockets
checkpoint-status |  |  | checkpoint | 1.4 - Rock Infill for Eco-Green Rock Bags
label | 26e5c963-9b29-570b-b8eb-58deb7295338 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 321b164e-4c7d-5eb5-a5d2-33177b588479 |  | note | Specification/Drawings Reference - SH2 R5 461/7.78 - Maraetaha Bridge No. 5 (BSN4688) Pier Protection works 2-U3436.BM(14)-S2-2
label | 5830bdf1-c4e1-570d-9f96-5b6e1fa1d7c9 |  | note | Frequency - Prior to commencement
label | b3b1cd16-9db9-5ac8-86ec-845a7c5ca975 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Material source property reports
label | a39b691b-730e-537b-a54b-926246f966e0 |  | note | Conformance Criteria - Sound, hard, durable rock resistant to weathering shall be used as rock bag infill material.
label | 2b4d12b3-ceba-5551-a258-b56cb8c0b128 |  | note | ○ Sized from 50mm up to 175mm but not exceeding 200mm. Should be round in shape and not flat.
label | 646f9e3e-a015-5c78-a7a5-3835eb9efdfd |  | note | Records - Material cert, delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 2: IN PROGRESS INSPECTIONS (Buttress)
checkpoint-status |  |  | checkpoint | 2.1 - Survey Setout and joint site visit
label | 4ae8d08b-c296-5851-a9b0-62075acef384 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f2116009-de21-5f2d-b43c-ab8020092839 |  | note | Specification/Drawings Reference - Consistency with 2-U3436.BM(14) S01-S03
label | 1982ed7f-fee5-5bbf-a86c-4d975c5e2e1f |  | note | Frequency - Prior to commencement
label | 37f8af29-9cce-544d-9e30-7bee427ffa83 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 1205cbbf-fce4-5392-9e68-e04e8d2a631d |  | note | Conformance Criteria - CPS Engineer to confirm and agree the extent of works including rock bag placement and survey set-out
label | a004e19b-6129-5dfa-8b88-153144b63813 |  | note | Records - Survey receipt, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | cef717a0-2dd2-5ba3-9570-79709c643dfc |  | note | ACTION (Hold, Monitor, Witness) - W
label | 92aac839-2d1f-517b-875f-3be508681daa |  | note | Specification/Drawings Reference - 2-U3436.BM(14) S01-S03
label | 9dabdb08-45f1-5c31-bcbc-1c0f665d492e |  | note | Frequency - Prior to commencement
label | bc571fae-ca47-59e9-b448-a53af6cf760b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 5a6554d5-34a6-5450-b22e-3be8402da686 |  | note | Conformance Criteria - Remove and clear the vegetation
label | 645ff52f-aa92-58d3-9370-b488dc25c307 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.3 - Subgrade Excavation
label | 0aa144ad-8a91-56dc-86c5-f60d53ce4d70 |  | note | ACTION (Hold, Monitor, Witness) - H
label | aa161853-bf8e-5e77-a95e-a917493f1c6a |  | note | Specification/Drawings Reference - 2-U3436.BM(14) S01-S03
label | 991e8f47-58ec-530d-9d6f-f31f3f296db3 |  | note | Frequency - During Construction
label | 7136d1dc-8373-5546-8033-50994e5480c7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 014af4a2-4a34-5757-a200-3f0a4847deab |  | note | Conformance Criteria - CPS Engineer to inspect foundation level when required depth has been met.
label | 955487b2-62c2-56c4-9a5b-2123d1e9cfe9 |  | note | ○ Scala check sheet (to 1.5 metres)
label | b579a155-83de-50e1-9acc-1402b07180c6 |  | note | Records - Scala Check sheet (CS-4000), CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Ground Improvements
label | a3ca6e82-0033-5ea5-b7eb-0fcf87da93d0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 78985c2b-67a1-54f3-8f55-727d0444a663 |  | note | Specification/Drawings Reference - 2-U3436.BM(14) S01-S03
label | b6be57ec-f261-5482-aaff-1b0756882226 |  | note | Frequency - Prior to commencement
label | be4f7dd4-cc4b-562e-b51b-de58b17579a7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 0afdcb93-4452-58c2-982b-07baac6de572 |  | note | Conformance Criteria - Any area that requires Ground Improvements (i.e. additional undercuts) must be completed as per CPS Engineer requirements and be signed off and closed before bulk earthwork operations commence
label | 0faf4ceb-dc81-5e90-b25b-71125162b2f0 |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Granular Backfill AP65
label | 764dee92-d5e8-5f83-ac98-c97db19d011b |  | note | ACTION (Hold, Monitor, Witness) - H
label | e778f6d5-e84a-5e2f-a7f0-589c7f5a4034 |  | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3436.BM(14) S01-S03, TNZ F/1
label | 09c5ac0e-e09b-5577-9f30-4b5ad58dfe30 |  | note | Frequency - At 5m intervals max taken at mid point between the rock bags on each 600mm thick layer prior to placing next layer
label | ce9ddad8-b5d5-5dc4-ad2a-fbf5a66c4c08 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg hammer or NDM testing
label | d5a334d2-24b8-5230-b08c-9ff22dac5aca |  | note | Conformance Criteria - Comply with TNZ F/1.
label | 3c6ca403-da9a-571d-ad37-b8fad2ad044f |  | note | ○ Well graded AP65 compacted to Minimum of 95% MDD. Compaction test results submitted to the CPS Engineer for approval prior to placing the next layer
label | bc6221a1-c2f4-524f-adfa-31d58a3d2be4 |  | note | Records - Test Reports, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Class D (A39) Geotextile
label | 940b8c68-2440-56fb-ab8d-6abcd2857f92 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b44980db-8c69-57ea-9b48-48e8e8702432 |  | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3436.BM(14) S01-S03
label | bb22eb1d-8832-5c15-b3c0-39c9886d03dc |  | note | Frequency - During Construction
label | 0f814ad9-73ec-54d1-936b-e0b7db134724 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 56f06f58-ea12-50db-bcbc-e0ceb3f44466 |  | note | Conformance Criteria - Installation between the AP65 fill and rock filled bags.
label | 6a2a0553-7a8d-52e4-be45-1ea9666237c9 |  | note | ○ The fabric shall be laid and overlapped as per manufacturers recommendations
label | d7697ced-d7a6-58b2-a7ab-93f8e42a4a3d |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.7 - Rock Bag installation
label | 964424b4-fcda-56ec-a419-13319fca90be |  | note | ACTION (Hold, Monitor, Witness) - H
label | 91ef3d50-ade5-5ae4-8da4-4aac4c95074f |  | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3436.BM(14) S01-S03
label | 17ed43f4-a2c9-5a0b-b048-d3b8d2bac2ea |  | note | Frequency - During Construction
label | ba75ee0d-b2e2-519d-8fe3-6ec8980e7778 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b38a8ced-24a0-5693-b2e1-048262eac3b9 |  | note | Conformance Criteria - Rock bags to be filled and placed in accordance with the manufacturers specification and are to be stacked so that the average angle is no steeper than 2H to 1V.
label | c305703f-0797-54e7-bfb2-662cdc418dd5 |  | note | ○ The final layer will be determined by the CPS Engineer on site
label | 4b93600f-5ab3-5b20-a2b8-f067f2eaf335 |  | note | Records - Photo's, CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Bulk Fill Placement access roads
label | 47918e7c-4832-5d9c-93cd-f30ba3d8728a |  | note | ACTION (Hold, Monitor, Witness) - M
label | 63970332-eda7-5b5c-8c86-02428f66982d |  | note | Specification/Drawings Reference - Consistency with Construction Drawing 2-U3436.BM(14) S01-S03, NZS4431:2022, TNZ F/1
label | 314b2502-e498-5adc-ae8f-2a485104ee02 |  | note | Frequency - During Construction
label | 3ee204ce-53d1-5f6b-b01e-3ae7d5c61da6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 17d7d943-0407-50d0-ac02-b6d9e0410373 |  | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade
label | e1564bdb-089f-575b-91bb-c48bab421037 |  | note | Records - Bulk Fill Earthworks check sheet (CS-4020), Photo's
checkpoint-status |  |  | checkpoint | 2.9 - Topsoiling
label | 71f813c5-059d-5874-985f-ca0280918f9f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 76f41463-eb51-50cc-b9c4-0a4b0cc4a8db |  | note | Specification/Drawings Reference - 2-U3436.BM(14)-S03
label | 50a854cd-643e-59d8-b82c-8b6dcce840bb |  | note | Frequency - During Construction
label | 2b9961bf-b6d3-5aaa-9db0-9997f9412da2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 42e14763-6e32-59b0-8c50-30674ad1c2fb |  | note | Conformance Criteria - Topsoil shall be spread out on the disturbed area at a nominal thickness of 100mm but not less than 50mm nor more than 120mm.
label | f0d3eff9-e7b3-57f5-91b1-db4b813ed57d |  | note | ○ Batter steeper than 2:1 are not to be topsoiled.
label | 3a2ed85c-ac51-5244-b95d-6ddcbed47929 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 2.10 - As-built Survey
label | 3a12d179-7e26-5acf-af0c-d00c412d5b15 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4dec2ab3-057f-5eab-a379-e7223c1b259f |  | note | Frequency - At completion of Lot
label | c50109a0-53c6-5a12-b68d-e9c10802dcf6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | a0fc7970-40c8-5d20-a033-4cc287d693d5 |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | 26dd2d89-9de6-5931-b5bc-1d64f8bb3bfe |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11 - Grassing
label | 58f8c33a-30f1-5a0a-8770-f22ab3e4c1a0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 78af3432-d58e-5201-b25b-76ef5f435254 |  | note | Specification/Drawings Reference - 2-U3436.BM(14)-S03
label | 185557c2-c41a-5180-bc8d-423048378aa8 |  | note | Frequency - During Construction
label | a04d144f-830b-5a99-9158-56aebcc207d0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 363755af-9773-5049-9d3b-f0013d634d27 |  | note | Conformance Criteria - Grassing should be superphosphate at a rate 50grams per square meter, Grass seed shall be sown at the rate of 25 grams per square metre bare seed weight
label | 7fb21fce-5334-51b5-9e18-7ed12fdf210b |  | note | Records - Photos
checkpoint-group |  |  | section | Section 3: Final Inspection and Handover
checkpoint-status |  |  | checkpoint | 3.1 - Quality Assurance deliverables
label | fa2f6bb6-152f-55a0-98bd-7d056c87ecd3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 491d7a35-c203-5766-9de7-b34cd9b54d7a |  | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 96d26f3c-99b3-5ccb-85df-a950b87260a8 |  | note | Frequency - At completion of Lot
label | 1ef120a1-6022-5095-bafb-9978029ba9a8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 1fe0778c-e96d-5166-a639-cdeaaac832bb |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | de7ad251-6ede-5270-bf29-4f9c6b5424bb |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 3.2 - Completion Sign Off From Fields Below
label | 6f76877a-f223-5691-adc4-e6d743f20ab0 |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | CS-4096 - Bottom Driven Pile Record |  |  |  |  | Yes | CS-4096 - Bottom Driven Pile Record | 5bf70c6c-cfd6-4bee-80c8-ad362c5d7322
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | 56f8a64d-8121-545c-adf7-018163cc04cd |  | textbox | Project No.
text | efa30fb0-2e1c-56d0-8668-af9419e07218 |  | textbox | Drawing No:
text | ddee42e4-395b-5ade-b65b-11a64f1f4ef0 |  | textbox | Concrete Grade: |  |  | MPa
text | b9286685-7cf0-57bf-9fe8-eb1c662ea8dc |  | textbox | Pile No:
text | f0ec3c9b-61bb-5c92-9311-4b59c59f3557 |  | textbox | Diameter: |  |  | mm
text | a938f315-98e4-5a9e-9867-3e33a9e88c0b |  | textbox | Pile Depth Required: RL:
text | edec43f5-c961-5919-a797-b5724c724386 |  | textbox | Pile Depth Achieved: RL:
text | b4c8ffa8-2310-5b4e-8bde-2e8339bf6524 |  | textbox | Ultimate Bearing capacity required: |  |  | kN
text | 26e50fe0-0fe3-53bc-b178-4fd5c89f46f5 |  | textbox | Ultimate Bearing capacity achieved: |  |  | kN
label | 0c169e39-1622-5772-9047-b10ff773e0ca |  | note | (Note problems experienced during construction on a separate sheet and attach)
checkpoint-group |  |  | section | Set Up
checkpoint-status |  |  | checkpoint | Piling Platform Compacted & Level
text | 778b119f-9bd3-5408-867d-38cd40bd4eb7 |  | textbox | Initials:
date | c2fbdb65-a4e2-5485-b530-7380de0cbc76 |  | date | Date:
checkpoint-status |  |  | checkpoint | Permit to Dig Obtained
text | e9cac86d-24bb-56e1-ae03-3529a0d70986 |  | textbox | Initials:
date | 6ac6e382-f77b-546f-a2cf-7ba676c48381 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pile Set Out & Checked
text | 2efe18d8-f212-516b-9f60-15c1504d9c22 |  | textbox | Initials:
date | 62db6e73-cf0d-5f89-a1ff-7e35aeffe5d6 |  | date | Date:
checkpoint-status |  |  | checkpoint | Erosion & Sediment Controls in place
text | aaf765a9-d823-53ce-9923-0ba3110fa202 |  | textbox | Initials:
date | e60fdbd1-4634-58f3-95bd-25f1629ad24a |  | date | Date:
checkpoint-group |  |  | section | Driving
checkpoint-status |  |  | checkpoint | Design Engineer Notified
text | 714aa699-5850-52d6-aa0f-61af268e789b |  | textbox | Initials:
date | 2a7cf3c1-5fb2-5d19-b1c0-195754eccd6b |  | date | Date:
checkpoint-status |  |  | checkpoint | Hammer drop measured within 500mm of pile set
text | db425fcb-1a7b-5457-ad42-651e94e55998 |  | textbox | Initials:
date | f1ca8125-eefa-5c45-8a69-29ddfc6fa0e1 |  | date | Date:
checkpoint-status |  |  | checkpoint | Damage observed
text | 5a456ef7-bc00-58c7-862f-d83b8e29ccd5 |  | textbox | Initials:
date | ee37d3af-8ba2-50a3-9ac7-9737dedb4d88 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pile Driving Record attached
text | 5ba009ce-e375-55e1-9a46-64f6ae0a4e0c |  | textbox | Initials:
date | 8221f13e-464c-5831-94d3-f2ceb518c026 |  | date | Date:
checkpoint-status |  |  | checkpoint | Rebound card attached
text | b99774e1-8777-5c40-bf74-2e313620d3c5 |  | textbox | Initials:
date | 13ff7907-546e-5880-89ac-e826276b87da |  | date | Date:
checkpoint-status |  |  | checkpoint | Last blow less then mean set over last ten blows
text | d6b85c75-7523-505b-a4d5-2557af563276 |  | textbox | Initials:
date | bf6fadfd-2adf-5d62-9aeb-134bbdd7ea49 |  | date | Date:
checkpoint-status |  |  | checkpoint | Any Interruptions to driving
text | e7434178-5987-53ba-80ec-d54f465e9b97 |  | textbox | Initials:
date | 595932d1-bcea-5ef7-b58d-a75d81848157 |  | date | Date:
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | Reinforcement Content, Grade and size
text | eb6d749a-ee7a-5d2e-8dc0-c2d55e9b1957 |  | textbox | Initials:
date | d1dc52c3-93e4-5523-8559-7e8025a45c28 |  | date | Date:
checkpoint-status |  |  | checkpoint | Placement, tolerance, clearance
text | 439303c6-da8a-51f6-833c-d489f9601226 |  | textbox | Initials:
date | 58917b5e-1a38-5441-8aed-8cc158515b20 |  | date | Date:
checkpoint-status |  |  | checkpoint | Rigidity and cover spacers fitted
text | 02da2fbd-cd83-5b67-b925-31a4056f5abc |  | textbox | Initials:
date | 4c3b0435-ff30-5b75-a19e-80d8005dbc4a |  | date | Date:
checkpoint-status |  |  | checkpoint | Clean steel
text | 765107bb-7d9a-591a-8efd-3d836d1d2f05 |  | textbox | Initials:
date | 834be037-4ce9-5b13-ab5c-45a3c75409c4 |  | date | Date:
checkpoint-status |  |  | checkpoint | Lap location and lengths
text | 4f5908c1-3304-5d39-bdd5-ccd503106c34 |  | textbox | Initials:
date | 515cf93e-56a2-59fb-be0a-90c50e576095 |  | date | Date:
checkpoint-group |  |  | section | Splice Welding if Applicable
checkpoint-status |  |  | checkpoint | Visual Scan 100%
text | cef6b366-fe52-5935-9c23-30fc39b345e0 |  | textbox | Initials:
date | fe69d11e-b375-5415-8744-5a808c2d8982 |  | date | Date:
checkpoint-status |  |  | checkpoint | Visual Examination 100%
text | df2b7c79-29d2-5e4f-b4f4-47a4ee0bd092 |  | textbox | Initials:
date | ba5a9027-8f33-535b-ab50-440ee5b81499 |  | date | Date:
checkpoint-status |  |  | checkpoint | Radiography
text | b8c0e3ca-63da-544b-a358-9b3ad49060c0 |  | textbox | Initials:
date | 387d0f28-ef01-5f03-8baa-2fe78542b3b8 |  | date | Date:
checkpoint-group |  |  | section | Pre Pour Check
checkpoint-status |  |  | checkpoint | As-Built Survey Complete and Within Tolerances (50mm in plan, 2% rake)
text | b717c01b-8dbd-5430-8651-fdde133774ed |  | textbox | Initials:
date | db471fec-50f4-596e-ae5a-f2f5c2b1bd32 |  | date | Date:
checkpoint-status |  |  | checkpoint | Correct mix ordered
text | e452e684-c198-573e-88f9-d728eb27e769 |  | textbox | Initials:
date | 77920363-8b5a-5a4e-b61f-5253fbfff16d |  | date | Date:
checklist-sectioned |  |  | checklist | ITP - C3001 - Mangaturanga Bridge Repair - Bridge Deck Repair | itp |  |  |  | Yes | ITP - C3001 - Mangaturanga Bridge Repair - Bridge Deck Repair | 603ba293-9bd7-4ac8-9b04-134dbc4a3749
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 7182dd8a-0886-5d49-ade2-c008734e248b |  | textbox | CPS Eng.
text | 1dd6ece5-4abc-5d36-b67e-897c724ca1f4 |  | textbox | Site Engineer
text | 65e9486a-f8f2-55ba-bda7-27c74468d785 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Dimensions and Setting Out
label | ec54b638-347f-5941-a439-649f21a09400 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e0e4d00d-be6f-5446-a318-064e7b1ef53d |  | note | Detail - Dimensions of concrete breakout on bridge deck must be agreed with the CPS Engineer
label | 11282eed-a28a-5690-836d-425cbd0f117c |  | note | Frequency - Prior to commencement
label | 035aa413-3bb8-5fd0-a9e6-da0ec47833de |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 7e34a8b1-79fb-5dc9-9225-cb4892fde711 |  | note | Conformance Criteria - Dimensions at top deck and deck soffit agreed upon
label | aa8f5481-34d6-5636-927f-728d9bf6bafb |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Materials
label | 600ba5aa-7417-5f43-bd2a-6d71102a16c6 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f865baa3-4ae2-5459-908e-7fc59d2aa9bc |  | note | Detail - Contractor must provide a list of all proposed repair construction materials with any technical data sheets available for each material for CPS Engineer approval.
label | ebfd6d25-5f51-593a-9ddb-ecb65e7830de |  | note | Frequency - Prior to commencement
label | 6dc78a3f-465d-5118-964c-785b295cdab0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 04dc720a-9022-5cb8-a66f-611a117143d1 |  | note | Conformance Criteria - List of all materials and technical data sheets
label | fd3a4412-cac4-5852-a92a-93561152ba23 |  | note | Records - Materials list, Data sheets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Concrete break out
label | 6f3924da-8fe7-5773-b1ab-3636692af6ab |  | note | ACTION (Hold, Monitor, Witness) - H
label | 591fa236-3137-5362-b635-6ffd9d5e5704 |  | note | Detail - CPS Engineer to inspect the areas broken out to inspect surface edge preparation
label | 68cc52f1-ac77-541a-af05-11912f7e8d17 |  | note | Frequency - During construction
label | c16529f0-2688-567e-a425-7707207c3d5d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | a3fddfff-c1d8-5725-82c6-0229b1d5e9c8 |  | note | Conformance Criteria - 45° taper cut on all 4 edges, no damage to existing reinforcement and shear cleat.
label | 9a0b4c48-d8ec-5c5e-a5e6-afd228348295 |  | note | Records - Photos, Site visit record
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Concrete break out
label | 4d7a0704-d703-5a48-a1ce-9866774012c0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 545d954e-6023-5aa3-92a7-ace6ed4e7d57 |  | note | Detail - Exposed and accessible (top and bottom) reinforcing steel must be power tool cleaned to SSPC SP3 standard. Other areas cleaned to SSPC SP2 standard
label | 9769319a-5b67-5092-9534-e9fa03567e44 |  | note | Frequency - During construction
label | a4d05ebd-51bc-5d45-b9e1-18506a4445f2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 60131695-c6c9-5619-ba7a-2ac4f04e502d |  | note | Conformance Criteria - SSPC SP3 and SP2 standard.
label | 852f38f5-e0ef-5f4a-94c3-e742fb01bf96 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Reinforcing bars
label | 81bcb288-c111-5ea3-8546-30518996686f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 7c4eaa49-3f42-5160-9391-f2beb404832e |  | note | Detail - HD10 longitudinal bars to comply to design
label | 1b655471-9ac7-597d-a972-857c9c56d12c |  | note | Frequency - During construction
label | 1a1812d3-3b0a-5c9d-aac9-cd30ce73ae40 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | ffdfd2c3-c9a4-5d70-8cda-3adae251427d |  | note | Conformance Criteria - Ensure all new and existing reinforcement bars are coated with a cement-based polymer modified coating material containing silica fume. Ensure all surfaces are fully coated
label | 1e4596f1-fb63-5ea3-acfd-bfd12a004e8f |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 6 - Reinforcing bars
label | 2d01fb72-bd7f-5c00-a6d5-dec4cb0eafc6 |  | note | ACTION (Hold, Monitor, Witness) - M
label | c00eb49e-9e6b-5c65-917a-6de50eee923e |  | note | Detail - Straight bars
label | 3d2c6d9c-4dab-59be-8c8a-7c751559e849 |  | note | Frequency - During construction
label | 3dbad1a7-959d-5f2e-9d1f-796162ad3111 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3715e333-6b34-5665-ae06-ffb9986a7026 |  | note | Conformance Criteria - HD10 hooked straight bars, crs 150mm, to form closed loop with hooked bent bar, embedded minimum 150mm, distance between 45° breakout face to be between 20-30mm
label | f6c425f0-1e39-500a-8ea2-e89ba0bc809a |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 7 - Reinforcing bars
label | 734c4ff9-5b64-5817-8248-7dfbde63644b |  | note | ACTION (Hold, Monitor, Witness) - M
label | cfe0e5f6-1ba7-5f35-a7d4-b6432f78cc74 |  | note | Detail - Bent bars
label | 95900161-f9c9-5f05-8f3b-5c9d56706c1b |  | note | Frequency - During construction
label | 1bc3735b-497e-5933-89e1-0c78ce25bccd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 7002ac85-f0b2-55cd-867f-87b170af30b0 |  | note | Conformance Criteria - HD10 hooked bent bars, crs 150mm, to form closed loop with hooked straight bar, embedded minimum 150mm with chemset, distance between 45° breakout face to be between 20-30mm
label | 504a71de-1a11-57fd-a1df-ec48d14ff35f |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 8 - Reinforcing bars
label | e57235a2-c2bd-508d-aaa6-099a4e9021f2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1dc519a1-7944-5102-a079-08d10e430620 |  | note | Detail - CPS Engineer to inspect placement of reinforcing steel after it is fixed in position
label | 04282662-5410-590c-94b2-3b07a24f23ec |  | note | Frequency - During construction
label | 7338548b-5e18-571d-b4fe-18861df0d871 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 947482b2-8b4c-5f94-aa10-56358c0ad6a6 |  | note | Conformance Criteria - Hooked bars tied with 2mm wire as per construction drawings
label | 932ae344-75bd-58de-ab52-980b8ad0b1f0 |  | note | Records - CS-4040 Concrete Inspection Record & Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Concrete casting
label | 185dd50f-9013-5f69-8195-a816a3a7a14c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4ba1426c-8c16-5d63-b351-0d2e88f666d5 |  | note | Detail - CPS Engineer to inspect formwork before casting
label | d276271c-72e3-5f8f-a37b-495d35fa51f5 |  | note | Frequency - During Construction
label | 35c5bd93-2a6d-5fd4-83e8-81bd9655ebf7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 50f0aa93-d706-5c90-8446-da0923466578 |  | note | Conformance Criteria - Forms must have sufficient rigidity and strength to prevent distortion due to pressure from the concrete. Formwork to remain in place until concrete reaches a compressive strength of 30MPa
label | d500bbed-09e6-540b-846a-4a0150a2e2fb |  | note | Records - CS-4040 Concrete Inspection Record & Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Concrete casting
label | 8d367dd6-e203-59cc-a183-6f0823f63535 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9ddde7cd-a3a1-5d97-b393-d9471fc42e8a |  | note | Detail - CPS Pre-pour inspection
label | 62b15874-17c0-509e-83e6-771c574dbe8c |  | note | Frequency - During construction
label | 822b9a35-04ce-57cd-9dd0-6b28f2d624e1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 07b4757c-c269-57bf-be1d-caccddadd6c8 |  | note | Conformance Criteria - Ensure exposed concrete edges are free from dust and loose particles
label | c04b654b-419c-53d4-82de-fc99fc074930 |  | note | Records - Concrete pre-pour checklist, Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Concrete casting
label | c4947249-e5b8-5c36-a25e-f107369d224c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 135c2738-eb42-5e2e-9ec2-2ee30d68bf5c |  | note | Detail - Site Engineer to witness casting of concrete deck repair
label | 83561413-1b3c-5f2c-81a3-4905306cad65 |  | note | Frequency - During construction
label | d53a2a5a-3f57-55f6-ba55-62b8bb199eab |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 7f79cc53-339f-577f-844f-bbeb4caa6b4c |  | note | Conformance Criteria - All concrete used in deck repair must be in compliance with T-CES 101. Surface finish in accordance with NZS 3114. Deck top surface - U3. Exposed soffit of deck - F5.
label | ddd4f9f6-b023-55c1-b0ee-36d5609e2925 |  | note | Records - Concrete pre-pour checklist, Photos
checkpoint-status |  |  | checkpoint | 12 - Concrete casting
label | d23bac96-63e1-59ad-9436-ac0cd796c0c3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | df7b0875-eafc-51e6-b769-554b1639f7bd |  | note | Detail - Contractor to provide minimum of 9 concrete cubes for laboratory material compressive testing
label | effd5925-a427-5c86-b698-27b60c6dc5b1 |  | note | Frequency - During construction
label | b9abe3d0-9632-5c4f-9b73-082bee5e04c2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 471f495c-4251-502d-8580-dbee5bc47765 |  | note | Conformance Criteria - Minimum compressive strength of:
label | cc989eb6-8fb6-5dd5-8f02-b2f80d488008 |  | note | ○ 25MPa (1 days)
label | a40e537f-d7de-53d0-b219-3cc7e270bff6 |  | note | ○ 50MPa (28 days)
label | 63b2b4f9-c6e6-588c-8e47-f4436a2cda9a |  | note | – Patchroc C (Fosroc) or equivalent should be used.
label | e9bf172f-e83c-59cc-b137-e519b418e202 |  | note | – All concrete supplied shall comply with NZS 3109
label | 28200b1d-c25b-5dc0-a926-ab93e3567ec7 |  | note | Records -
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 - Concrete curing
label | 6bfe44f0-1ff9-5e91-a878-37e2bbe1d583 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8c26c577-53e0-52d2-b950-753930ddb204 |  | note | Detail - Curing
label | 94f3c1ad-7733-5a60-8bb4-7ce6fc5ab27c |  | note | Frequency - During construction
label | f3be1c6f-1130-5c6e-88e9-4c237f9dfd4b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | d9e43337-24f9-5d3b-a6b1-408fc620dcfc |  | note | Conformance Criteria - Contractor to provide details of the proposed measures intended to protect the concrete during curing
label | 9063b20d-1c22-541b-9bbc-da9abaa21692 |  | note | Records - Proposed Methods
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Concrete curing
label | c1d5c589-5db6-5a28-ba1d-6cc302c7bdb9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1b535b4a-6299-5fe2-92a7-1ef85a90a338 |  | note | Detail - Prior to resurfacing, CPS Engineer to inspect the newly cast deck repair and make the decision whether crack injection is required
label | d7ba1673-688b-5e56-ad86-e3873a725ca8 |  | note | Frequency - During construction
label | 61abc09e-8c07-53ab-91b7-ca05c00dd0b9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 8e752cd8-28c3-5594-86b4-a0929d3c2cb4 |  | note | Conformance Criteria - Crack injection required if crack between newly cast concrete and existing deck exceeds 0.3mm. Sealant strip will be applied instead of crack injection
label | 7deeccbc-111b-57e7-a490-19e87492ec99 |  | note | Records - Photos prior and after sealant
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 15 - Reinstate surfacing
label | bb515f94-9253-5162-8225-e99a8a098df7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8503f52b-1c54-5b2d-b99b-e038f8d09841 |  | note | Detail - Road surfacing reinstated to be consistent with rest of deck surfacing (Grade 3/5 racked in Chipseal). Contractor to provide methodology for resurfacing
label | 317de8ef-a82f-5f80-b12d-acdede16ec28 |  | note | Frequency - During construction
label | d05c2379-dd8f-515e-936e-9c99cb5d2924 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 212b0f10-a071-5689-b790-429693fee310 |  | note | Records - Methodology, Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 16 - Completion Sign-off
label | bbcc5ae7-6947-557e-8391-319730a3f83b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 778f142c-3abd-5f40-96e0-ee4b4e481def |  | note | Detail - Upon completion of works, Site Engineer to inspect works to confirm it is completed to required standard for sign off
label | 12f41545-6796-50df-bf67-deb956e06efa |  | note | Frequency - At completion of works
label | d2cf42d2-d9b0-5c4f-a16e-2b52b6b5e771 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | e656ae5e-3db7-549c-a885-de983cb33ca7 |  | note | Conformance Criteria - Signatures from Site and CPS Engineers
label | 89a28d01-e80b-5a13-8be6-a4784c5f8315 |  | note | Records - Signatures
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 17 - Quality Assurance deliverables
label | 74bbbdc6-5207-5981-aaaa-b0adc8436648 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0e8c5f17-6f42-5ad8-9267-75daf32f0f63 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 3b3af966-7c58-594e-b29e-c3ef04adac43 |  | note | Frequency - At completion of Lot
label | fdae4f78-191f-5e1c-9902-fc775220d1ae |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | c468a4e2-ec16-5e20-8d20-4d50192916f0 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 39bed653-72dc-5bbb-b3a0-555451d73f32 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 18 - Completion Sign Off From Fields Below
label | ab3e990f-12f2-587b-bd8d-5e7ce5b9705c |  | note | Records - Completion Sign Off From Fields Below
checklist-flat |  |  | checklist | ITP - B1004F - Tangoio Falls Steep Underslip - Kerb & Channel | itp |  |  |  | Yes | Ω (Deprecated) ITP - B1004F - Tangoio Falls Steep Underslip - Kerb & Channel (old version) | 61fb0043-01fa-4c72-802b-95b80aa741a9
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 2068c3a5-d340-578f-9ed5-8d470d533164 |  | textbox | CPS Eng.
text | ebd1b16b-14c2-53ef-af80-496e7c371c0b |  | textbox | Site Engineer
text | c6882f25-ecf7-5955-b49f-560ae08a5412 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | c811ce24-3dad-56a1-9f4a-3aece818902a |  | note | ACTION (Hold, Monitor, Witness) - H
label | d932d3b5-e629-5fca-bb07-6e365e432cd1 |  | note | Detail - Set out kerb line and level at 1m offset to EOS
label | 0ea94e7b-68e0-5441-ba55-a88140bf18cc |  | note | Frequency - Prior to commencement
label | ce38bafe-ecdf-5cf1-87e9-14aa3ce5e0c9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Measurement and Visual inspection
label | 6b618bca-ae7e-51a4-b359-e6b65bf054ea |  | note | Conformance Criteria - Consistency with Construction Drawing
label | b26f78a5-951d-5bab-a5a2-a9766cc1f814 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Material Compliance
label | ea6b5fc4-e799-541c-a0f3-1d68d296043e |  | note | ACTION (Hold, Monitor, Witness) - H
label | d82ade8d-4f6d-5a57-b60b-7b9a1d1bd996 |  | note | Detail - Ensure the Concrete Mix is as per the Kerbing Specification
label | 91ff5a31-51f0-5804-99b6-b9addb8300e3 |  | note | Frequency - 1/600m3, minimum of 1 per source
label | a34469e8-1418-569b-81c0-9997027ba93f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Lab Testing
label | a0cc8f9b-b5c9-5b7f-9505-89ef120709f9 |  | note | Conformance Criteria - 20MPa at 28 days
label | 6b7caa11-8d17-5744-a015-414a10de6491 |  | note | Records - Concrete Delivery Dockets and lab test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 -
label | 02479aac-3ec5-5a40-b2e5-da3b71fcde3c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 21505e53-e4c5-5eaf-ad4d-4aaa74421776 |  | note | Detail - Ensure the slip form moulds match the dimensions of the design kerb
label | 5b30ceac-6f8b-55e4-a493-063bdc6966ab |  | note | Frequency - Prior to commencement
label | 1acd2ba3-6971-5b01-9873-be06c9861ed3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | c883785b-c7af-5527-b359-90eb9c585284 |  | note | Conformance Criteria - Measurements match the design kerb dimensions
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Kerb Foundation
label | 94091e79-3d19-5b02-ab15-af8aa4ce7499 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2b5b3535-b26a-597d-939b-724c26ba06ef |  | note | Detail - Ensure Sub base construction is completed
label | 29aebc11-61ee-5685-ab01-47350539ab15 |  | note | Frequency - Prior to commencement
label | 285ab1fc-b214-5f5e-939f-962fcf922b3f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 779d61c0-42b2-5305-bcc5-fe57ab272084 |  | note | Conformance Criteria - Pavement depth and type under the kerb varies depending on location
label | 6ed7938e-f167-5c29-92fc-fe076c2292f1 |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Stringing
label | ef6aeaa9-533f-5198-8c5e-60c26368db4a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 90a0a50b-248b-5ede-9de5-149818062a0c |  | note | Detail - Check weather forecast and avoid adverse conditions
label | 15ff8af8-7c56-5ab0-8c77-18a828be5ac2 |  | note | Frequency - Prior to commencement
label | 8e739954-e216-5b1a-abb9-dd8ba2a39b4e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 18d243e8-7237-5c17-a9ae-b55a648a6608 |  | note | Conformance Criteria - No concrete to be placed in adverse weather conditions
label | 76d956bd-0ae5-5c5a-bebc-edf500c16334 |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 -
label | c1b09587-634b-5ef9-9543-c8bfa13e8ffa |  | note | ACTION (Hold, Monitor, Witness) - W
label | 67c82388-b619-5b2e-b2e2-2caf9524b276 |  | note | Detail - Kerbing Subcontractor to set out steel pins and string line to design levels and identify catchpit locations
label | f203367b-f8b8-5d55-a626-f6b0b7fb1d7b |  | note | Frequency - Prior to commencement
label | f12ace9e-07a6-5f1e-8a6f-1209bcfb4743 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | d1f89205-0ea0-5fda-b827-ea9dbfdea9c0 |  | note | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
label | 3bc572a5-e9b4-5d0f-916a-0a896a028565 |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint-status |  |  | checkpoint | 7 -
label | 82796926-c960-5ed5-be47-cfe624593f25 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f4a03c9b-f2c2-57d4-b1b3-e4b7bfc216dc |  | note | Detail - Subcontractor String line to be checked by Site Engineer to ensure Horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits.
label | 43c35cad-df23-55eb-9b4f-3cf8f65c7916 |  | note | Frequency - Prior to commencement
label | 1e6a0494-6207-5ae5-ac16-9497064f47d4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | e3c3d5a5-4115-57f3-80c7-e8809700c09e |  | note | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
label | cf20fddd-a4cb-5e6a-bd0e-5ec10d0fc07c |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Slip forming
label | 68126dbb-f9cc-5fe5-878e-91cd074893dd |  | note | ACTION (Hold, Monitor, Witness) - H
label | d28efda9-f1b9-554f-9106-0c008e1f3b9e |  | note | Detail - Check correct Kerb & Channel profile is installed onto kerb Machine
label | 5c7f7a7c-c7db-515e-b2da-edc50e301ed8 |  | note | Frequency - Prior to slip forming
label | d0050eb6-121f-5f49-9553-9537f0efc9b3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | 10f62909-cf2a-5176-8405-0f9b87937e41 |  | note | Conformance Criteria - To ensure the correct kerb types are installed at the correct locations
label | fa39b0b0-bd8b-5764-bde8-6c98172074af |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 -
label | d04f3a92-a6ac-5a94-93e2-8d6f956f9931 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 271dda04-c147-5b73-8063-c04d143233dc |  | note | Detail - Kerbing Subcontractor to order concrete as per design Mix and to ensure the concrete is tested
label | 6d8e2dc0-c10a-5d43-b31d-627bd005f50f |  | note | Frequency - During Slip forming
label | 480c22fd-30d4-5e7a-af44-4c3f27fc629e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 5218d382-78b3-5d86-a972-68edaf0f62e1 |  | note | Conformance Criteria - To ensure the correct concrete mix is delivered
label | 6ce66b10-8223-5e74-980f-d29c1a60b3d9 |  | note | Records - Concrete Delivery Dockets and lab test results
checkpoint-status |  |  | checkpoint | 10 -
label | df408c63-170e-517d-8832-ce7572900434 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4b7d689c-f5c8-5f7b-b542-3adb7e269f8e |  | note | Detail - Expansion joints to be formed at 5m centres
label | 561c56e4-a48a-5d9b-8def-fdcb47a790dc |  | note | Frequency - During Slip forming
label | ca9aa79b-d557-50e2-9613-c53b4ce98c86 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 4563ef5f-700b-5792-a378-50a22f806706 |  | note | Conformance Criteria - Kerbing Specification
label | ba4b8b07-cc5b-5b1d-abfb-c5129c1752c2 |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint-status |  |  | checkpoint | 11 - Tie-in with pre-cast components
label | 8f98a052-decb-549f-a18c-702f2bfb08db |  | note | ACTION (Hold, Monitor, Witness) - H
label | c34dfcc9-0f67-565f-8423-dc35a72a0856 |  | note | Detail - Subcontractor to ensure Slip form Kerb & channel to be cut and tied-in with pre-cast components.
label | 0d0b7377-715a-536e-94d6-87f0ee8d8060 |  | note | Frequency - During Slip forming
label | c9ec5894-a6f6-59ac-b142-437d4c6c403e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 65f7dc66-2fc0-54c1-afec-aaf8f419f320 |  | note | Conformance Criteria - Consistency with Work Instruction
label | b1cb43b5-531a-5326-a58b-fc599f2421c8 |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Protection
label | c884ad58-3d7e-5d2b-af00-bb718932d275 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c318eecc-fec5-58f0-bcd7-caaf0d46be7b |  | note | Detail - Backfilling behind kerbs to commence only after a curing time of 72 hours
label | a79321b8-685f-59a9-8826-1fa5a3a821a2 |  | note | Frequency - Prior to backfilling
label | 82e7d284-4875-50a3-bad6-e465a6f6e1de |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 024fb1f5-0fbb-5309-9030-0aa4d252d3b7 |  | note | Conformance Criteria - Backfilling to commence only after 72 hours
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 - As-builts
label | 940c45ba-beb8-54c9-a630-d1810802fe54 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3fd34caf-c625-523b-89a7-0f20cb0a836a |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 29ff40f2-53c2-5d90-8e80-3ad862353796 |  | note | Frequency - At the completion of the Lot of work
label | fa6564b4-f659-584b-ac9b-d67749252084 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 9f4822a5-7d91-5171-b499-df7cefac04db |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Completion Sign Off From Fields Below
label | a806c201-1e08-5bcf-8ac2-e604f5e63f3e |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | ITP - B1004F - Tangoio Falls Steep Underslip - Stormwater | itp |  |  |  | Yes | ITP - B1004F - Tangoio Falls Steep Underslip - Stormwater V2 | 65ebef39-f04f-4380-b48a-0346fd4e743b
checkpoint-group |  |  | section | Pre-Construction
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 6220c117-c015-51fa-8c9e-77cb300afcaf |  | textbox | CPS Eng.
text | 6aa861b5-db44-513b-af43-7da6d5b079a2 |  | textbox | Site Engineer
text | e08f5f1b-51f6-5ccd-9377-4e9ff265159d |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Drawings and Specification
label | 9d747c6d-442c-5824-a75e-73d05a6a91c0 |  | note | ACTION (Hold, Monitor, Witness) - M
label | a81ba1f7-fcee-527f-a5ad-1773fd9e2766 |  | note | Detail - Check drawings and spec are the latest version.
label | 21125791-5d53-581a-ae15-e0fca20d9cc0 |  | note | Frequency - Prior to commencement
label | de8f8ce0-db4f-5edf-9ce5-33d3e14c77ce |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | 1d8697d2-0bc3-5772-b2cb-23e5035f77b4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 58b27af7-8c8b-57bd-b575-405399e9685e |  | note | Detail - Set out as per design
label | 8ae68ba1-27aa-595c-9e34-9359a7e9b13d |  | note | Frequency - Prior to commencement
label | 25977267-24a3-5099-99e4-1a182dfd4560 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 45d3b2e0-58fb-51f6-baf3-688d60b5ba10 |  | note | Conformance Criteria - Check against plans for any discrepancies
label | c958387f-e254-5516-b5ff-a1c64c9e0c2d |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 3 - Material Approval
label | 917d99e1-4d86-5e3a-8a34-a402a70ea7a6 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 0e977ee3-5b07-5056-830d-6675f7c14fb4 |  | note | Detail - Materials as per design
label | 05c416d4-e773-5598-80c2-72216a53d144 |  | note | Frequency - Prior to commencement
label | 02d98666-240f-569a-8317-16b1892f1d0d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | b8a0e1d6-a1d3-567d-8531-feea647ddf8a |  | note | Conformance Criteria - Only require approval if proposing an alternative material than that specificed in the drawings
checkpoint-status |  |  | checkpoint | 4 - Location of underground services
label | 3a8ea60b-309a-59a9-b984-0653d01d7c44 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 80aa3ca5-9ce0-537f-9420-b5283ce3e9c5 |  | note | Detail - Ensure underground services are positively identified and asbuilt. If the service conflicts with the design confirm resolution with CPS
label | ccf67b87-a4f8-5301-aa6d-879700752e27 |  | note | Frequency - Prior to commencement
label | b2124213-f235-5e91-9794-61a878454449 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Drainlayer Qualifications
label | b25c39f2-f98f-5310-a2e9-6e5716deb4ea |  | note | ACTION (Hold, Monitor, Witness) - W
label | e5a88de2-5465-5521-867b-e25b8b28eacc |  | note | Detail - Drainlayer to be appropriately qualified and skilled to undertake work
label | a92c4cdb-3226-56cf-b1ad-82d5b52ff011 |  | note | Frequency - Prior to commencement
label | 61fd68ba-11cf-52de-a016-4d0ef7cf25da |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 6aec0071-c2c0-5cde-b39f-00b85b374e33 |  | note | Conformance Criteria - Drainlayer Certs
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 6 - Trench and excavate for pipeline to design subgrade
label | 98776d47-8abc-58dd-ad54-30588b8ff976 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a6af873c-0dbc-524e-9636-341d496f910e |  | note | Detail - Check subgrade with visual inspection and
label | 2e2cb3d3-f74b-5764-a457-b2102f82ac9c |  | note | Frequency - During Construction
label | a11ac627-c1db-53ca-9d66-e2c18c125210 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
label | 16a50f5c-47f5-521c-929e-2ae6109c9cf7 |  | note | Conformance Criteria - Delivery temperature, mat thickness before compaction, mix temperature during compaction
label | 47b1a5ed-4006-5833-847f-57272f7fdb61 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 7 - Surface finish visual inspection
label | 4e2ddf35-8221-5e4b-8db7-89caf33b8f67 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ec33dd3d-716c-5054-9175-fa8ee1586eba |  | note | Detail - Site walk over
label | 82314387-cf26-5d15-8b49-4b93ab1d0931 |  | note | Frequency - Post Construction
label | 3c6e9ff2-44fa-5134-8588-b81ac40ed1ce |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 8d3732f1-e2a4-5afa-b3d2-1e02a0ceb5cf |  | note | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
label | 7810ed82-37fc-5cb9-85c9-b4a6acfa3675 |  | note | Records - Subcontractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-Construction
checkpoint-status |  |  | checkpoint | 8 - Final Walkover (Snags)
label | a86ae5ca-e65b-536c-adba-3ea64a1d1b22 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2dab9dd6-a1e9-599e-b4f2-fe1f38437a6d |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | f9b4497a-5779-5903-874c-7567231522bb |  | note | Frequency - At the completion of the Lot of work
label | 1beea9fc-ab98-53d3-8f0c-afec2401dc01 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | 9b89cd32-2f5a-57a9-af9f-9d39adc7caa9 |  | note | Conformance Criteria - Completed report
label | 199975a0-f1e6-5723-bbd9-e5a6a95f4385 |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Survey As-builts
label | 1739a0bc-0f92-5ea5-bfba-93f4e0d17b15 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5a068a1e-d4d6-549b-9085-3e4f2c4be294 |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | f15d03a6-3915-59ae-99e2-5ae412c46577 |  | note | ○ A survey as-built of completed work must be provided
label | 5e1f749b-20e3-5640-9688-fd939b34ec46 |  | note | Frequency - At the completion of the CWP of work
label | 4646584e-da72-5436-9de5-b0c6ca49a052 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 76aae6dd-efe0-5a31-952f-4a69c13d17a7 |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | 4a3dda18-8e34-510f-ad26-22b50aec4538 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Quality Assurance Deliverables
label | 17d68903-6821-59e8-afe6-8bcb9e7ab26b |  | note | ACTION (Hold, Monitor, Witness) - W
label | f8a8daab-1911-5567-8111-a62887ebc49d |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file.
label | f0acf346-f8e4-5825-9636-a81415c976a5 |  | note | Frequency - At the completion of the CWP
label | 3e1380ec-d731-59fd-8197-6192552013af |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 92c99287-201a-5afd-84a3-ac923a449d95 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | c3bfca17-e614-55a2-bcfa-974ff5d2285c |  | note | Records - As-builts, NCR's and RFI's
checklist-sectioned |  |  | checklist | CS-4020 - Bulk Fill Earthworks Record |  |  |  |  | Yes | CS-4020 - Bulk Fill Earthworks Record | 6932ebc3-ad5d-47a8-9591-3095ac765773
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | 33c61299-5975-5ed5-b796-76d30d695b78 |  | textbox | Work Area:
text | 262f4907-4c8c-5444-a19c-11336a897edb |  | textbox | Sub Work Area:
text | d22bbfda-6ea3-5179-b966-de47f5021041 |  | textbox | Lot:
text | 1e1bddad-d9d5-5c12-9dc6-ee3741cfedf7 |  | textbox | Sublot:
date | f84e9adb-3ad3-517e-9144-1c5b343b2a9d |  | date | Document Date:
text | 80c8db88-34d6-57ce-8dc8-b0198d55a694 |  | textbox | Created By:
checkpoint-group |  |  | section | Pre-Construction Phase
checkpoint-status |  |  | checkpoint | 1. First 1st lift - Ensure underlying layer has been signed off by Design Engineer – CS-4100
checkpoint-status |  |  | checkpoint | 2. For subsequent layers - Ensure Underlying layer has been signed off by the Site Engineer and/or Design Engineer as well
checkpoint-status |  |  | checkpoint | 3. Ensure previously constructed fill has not deteriorated from required fill standards before placing new fill
checkpoint-status |  |  | checkpoint | 4. All source testing completed in accordance with Specification XXXX – (Example - 1 x PSD completed @ 3000m3)
holdpoint |  |  | signoff | Site Engineer Verification Signature:
checkpoint-group |  |  | section | Construction Phase
checkpoint-status |  |  | checkpoint | 1. Batters to be overfilled by 250mm – Specification XXXX
checkpoint-status |  |  | checkpoint | 2. Visual inspection of fill for contamination, segregation & oversize particles
checkpoint-status |  |  | checkpoint | 3. Minimum dry densities: Example – 95% MDD - MDD = 2200 kg/m3 - Specification XXXX
checkpoint-status |  |  | checkpoint | 4. Scala/Shear Vane/Clegg limits: Example Scala – 2 blows per 100mm (Type 1 material) – 4 blows per 100mm (Type 2 material) – Specification XXXX
checkpoint-status |  |  | checkpoint | 5. Measure Lift thickness and confirm applicable roller and passes are applied in accordance with embankment trial results
checkpoint-status |  |  | checkpoint | 6. Vibratory roller to operate at 3km/hr (or less)
holdpoint |  |  | signoff | Site Engineer Verification Signature:
checkpoint-group |  |  | section | Bulk Fill Earthworks Record
checkpoint-no-status |  |  | checkpoint | Details
text | 4cdbd42a-2609-5ba5-963a-03af2807e52e |  | textbox | Weather conditions:
text | 46d8190a-de59-5d01-9d3b-afa766fd21c2 |  | textbox | Supervisor/Foreman Name:
checkpoint-status |  |  | checkpoint | 1
text | bffe3869-efbb-5a43-a0a5-cbcb5ccaa414 |  | textbox | Lift #:
text | 17c40300-52f6-5f5a-8b8c-f38bbfda0cd5 |  | textbox | Chainage From:
text | 7847dbf7-d3ed-56a1-8dbb-0d4d0c9f50b4 |  | textbox | Chainage To:
text | dac8d8dc-bf9a-5dd1-b997-d72d8ed9c6c4 |  | textbox | Test Spec:
text | bbffcd61-9a72-5461-bb6b-6226721dcef8 |  | textbox | Material Visually Inspected:
text | 681ec4f3-ec21-55a0-a2b9-1b660f5bb166 |  | textbox | Extent of overfilling checked:
text | d401cf3a-efb8-5c8b-a4be-48c31fe74678 |  | textbox | Lift thickness (mm):
text | 77f0d2b9-b9e0-52c4-ab31-34893ac4a391 |  | textbox | Roller type:
text | 88db9b4d-7a4b-563b-8f1b-df5175786973 |  | textbox | Minimum Passes:
text | 7fc047b3-fe59-531c-97bb-5f7b487d72d5 |  | textbox | URN test numbers:
date | da80fc0f-f3ab-58cf-90d4-5eaa27b0bed4 |  | date | Date Completed:
text | aa2708f5-1a71-53c2-b66c-30ec2de791e7 |  | textbox | Site Engineer Initial:
text | 9c3867b5-da80-59be-8d2a-19dc7ddfa709 |  | textbox | Design Engineer Initial:
checkpoint-status |  |  | checkpoint | 2
text | b8d3df83-7605-5e21-850a-c11da815c0ff |  | textbox | Lift #:
text | b6ead5e0-a999-5061-bbd9-11bba5b6b904 |  | textbox | Chainage From:
text | a56627ab-9e41-563b-a265-7467668490f3 |  | textbox | Chainage To:
text | a1edc8a4-1631-5d92-a783-5d16f001bcf5 |  | textbox | Test Spec:
text | 5d2aa102-b4e2-5b2e-ab8c-f8b3dec09092 |  | textbox | Material Visually Inspected:
text | 80edcfcb-c11c-5b33-8289-995b71ed09ba |  | textbox | Extent of overfilling checked:
text | 9137d4fd-c5db-5534-ae07-031bfdd17140 |  | textbox | Lift thickness (mm):
text | 1420c83d-119a-57c5-9df9-153485b8a618 |  | textbox | Roller type:
text | d51d146d-5f69-5cb2-b180-9713f8f9039f |  | textbox | Minimum Passes:
text | 84a48825-157d-54e4-b6a3-c200e836212f |  | textbox | URN test numbers:
date | 527cbc07-3143-5cf6-9fd5-3fb966b6815a |  | date | Date Completed:
text | fe7bc47e-6828-5012-a643-3b56dbacb2f9 |  | textbox | Site Engineer Initial:
text | be13c86a-7c09-51be-ae4e-1315ce808340 |  | textbox | Design Engineer Initial:
checkpoint-status |  |  | checkpoint | 3
text | 809d888a-f54c-5592-9158-02c769b06077 |  | textbox | Lift #:
text | 223c76a7-88b9-5835-8d3c-07ffb76af4d1 |  | textbox | Chainage From:
text | 13e57155-8c4c-5dde-919f-23ac353229c0 |  | textbox | Chainage To:
text | ca00d41d-96cd-5eae-bb1d-1018e1f66f3b |  | textbox | Test Spec:
text | 9434e824-8737-550e-8679-628882f5d943 |  | textbox | Material Visually Inspected:
text | 13cd072b-a9b0-511b-b90e-965666896bf9 |  | textbox | Extent of overfilling checked:
text | ecf6b8f5-da17-5298-b9ca-f21e1a836edd |  | textbox | Lift thickness (mm):
text | c113194b-3daa-5937-8d6b-6daa1831a5cb |  | textbox | Roller type:
text | 9aff87ad-d364-5583-b007-3b473e19cc30 |  | textbox | Minimum Passes:
text | df0e7f33-6956-5026-9f8c-95191e448513 |  | textbox | URN test numbers:
date | 4d105b3f-b6e7-5a40-bb33-bcd0313b7739 |  | date | Date Completed:
text | 74ef4c82-3ba7-53ff-9b42-92cb3b69c93d |  | textbox | Site Engineer Initial:
text | ed8bc25b-9d19-5532-a329-27491c439b2e |  | textbox | Design Engineer Initial:
checkpoint-status |  |  | checkpoint | 4
text | 8077316a-924a-5723-b26c-66b5aa1d221f |  | textbox | Lift #:
text | d16c5712-5888-5bb5-8a91-dfbc0a58c1b6 |  | textbox | Chainage From:
text | 17e58831-72bf-5942-93b4-6397607dac08 |  | textbox | Chainage To:
text | 2af899f1-8321-5c09-935f-5e60deb6fa7f |  | textbox | Test Spec:
text | 7c1bd028-5e17-59a3-9b57-319efcabb49a |  | textbox | Material Visually Inspected:
text | ee75520c-a5d2-54c2-b27e-9206aed72e00 |  | textbox | Extent of overfilling checked:
text | 03aae791-f4d5-57b2-bb1b-f3a6d78643c6 |  | textbox | Lift thickness (mm):
text | b31a3097-21ee-5580-8788-190e239023f8 |  | textbox | Roller type:
text | a0eff3aa-41ab-5499-956d-dd48455e1aef |  | textbox | Minimum Passes:
text | 3d14f800-043f-5a57-b5d7-b50dc612aa5a |  | textbox | URN test numbers:
date | 46513f17-c8b5-50e6-b6a4-be1a8af2ee13 |  | date | Date Completed:
text | f4a6e0ac-32af-596e-81e2-9906afe0f934 |  | textbox | Site Engineer Initial:
text | 22b78e40-dff7-5f0d-8a40-1ed0ec217ef8 |  | textbox | Design Engineer Initial:
checkpoint-status |  |  | checkpoint | 5
text | feed230d-769d-5393-9f20-f11a34425cd2 |  | textbox | Lift #:
text | 121af6ca-eb15-52d9-988f-d4404ce4ac34 |  | textbox | Chainage From:
text | 8cf934ed-9d37-550e-9657-23ee394c8999 |  | textbox | Chainage To:
text | d9ad439b-7b5d-52b4-a317-c4c5ed84fcf8 |  | textbox | Test Spec:
text | e37a6d9f-84c7-565b-aa46-5f371e60f1ae |  | textbox | Material Visually Inspected:
text | d700e1f4-a409-55c3-a64e-d7bcdf936787 |  | textbox | Extent of overfilling checked:
text | 37839b77-f375-57fd-846f-1392dff6e3b4 |  | textbox | Lift thickness (mm):
text | 86e0d77d-5c68-5e8e-a962-5bee047be0a5 |  | textbox | Roller type:
text | eae1d818-119b-51a0-b84b-82076ab50a73 |  | textbox | Minimum Passes:
text | 69e45a2c-568f-5435-8b6f-5a732e33d286 |  | textbox | URN test numbers:
date | 7d2f9d43-9251-53ba-918e-a51d8886a022 |  | date | Date Completed:
text | 1d414bcb-f545-56da-92a0-e8fed9a6ff16 |  | textbox | Site Engineer Initial:
text | 3d51cac3-0fd9-536f-aeac-64755c9ef930 |  | textbox | Design Engineer Initial:
checkpoint-status |  |  | checkpoint | 6
text | 6f46f34e-a814-596d-8225-4dbf80f72d08 |  | textbox | Lift #:
text | 3f41b25b-9275-5c1d-a49f-46b0f1ab68e0 |  | textbox | Chainage From:
text | 7e2049a3-00ef-5ed4-a895-89e3a59c8aa9 |  | textbox | Chainage To:
text | 91f65ae1-d1a4-5cd6-85ba-b4c7ab082c7f |  | textbox | Test Spec:
text | 18ce08f2-5d0f-5d4b-8510-24e7e49eb319 |  | textbox | Material Visually Inspected:
text | 535825bd-ddfc-5d94-b6fe-3e0b9be0a2b4 |  | textbox | Extent of overfilling checked:
text | 7908abb8-4c93-5eaf-bc2f-b6e6d556797e |  | textbox | Lift thickness (mm):
text | 602ba918-d022-52dc-9fe3-ec2132fd0951 |  | textbox | Roller type:
text | 4c4c2e96-6ff4-5645-a941-019ebcd39b0a |  | textbox | Minimum Passes:
text | e20d3760-1884-5f13-a8ed-6e3948d472b2 |  | textbox | URN test numbers:
date | 6c70ff31-b160-564b-b8b2-13a9a8cc42bf |  | date | Date Completed:
text | 84a156cd-42c3-5d23-9d52-6719e801b70a |  | textbox | Site Engineer Initial:
text | af3778dd-8d01-5229-bbb7-47b3262d3f96 |  | textbox | Design Engineer Initial:
checkpoint-status |  |  | checkpoint | 7
text | bf342122-acf5-5b88-abb1-0882755cebe6 |  | textbox | Lift #:
text | 701e09e2-742b-515a-ada0-9ba8ee1eaf9e |  | textbox | Chainage From:
text | ac78a5a2-0487-541f-9d4a-0f0f2e8d2aa9 |  | textbox | Chainage To:
text | f7842dd2-5b9b-5055-8b92-4946960f3909 |  | textbox | Test Spec:
text | 81b46446-0b80-587e-8231-7372c06a644c |  | textbox | Material Visually Inspected:
text | cf1dd190-b1be-5b76-b15c-5ff4f018f9bc |  | textbox | Extent of overfilling checked:
text | 34f030fb-3077-5349-847e-7a358417f401 |  | textbox | Lift thickness (mm):
text | db01edba-0938-5b03-9fe7-563dcabbd3b7 |  | textbox | Roller type:
text | 97684b7f-de12-51fc-8581-5af7e9f39bb9 |  | textbox | Minimum Passes:
text | 34f54142-b7d7-537d-8328-3ad80cb84556 |  | textbox | URN test numbers:
date | f1d5d2b3-5ba5-5a7d-817b-6ffde948fa87 |  | date | Date Completed:
text | a2f3ca32-d898-55fc-942d-55b45126df93 |  | textbox | Site Engineer Initial:
text | 538837c1-9270-5fb5-ae78-de310314abf6 |  | textbox | Design Engineer Initial:
checkpoint-status |  |  | checkpoint | 8
text | 53f5bfda-d156-5a84-b29d-852114e4b0cc |  | textbox | Lift #:
text | e5679e57-44e9-5fc2-b6db-61a7318c0bc3 |  | textbox | Chainage From:
text | 7c19714c-a1e4-5449-b7ac-73716f384dae |  | textbox | Chainage To:
text | 124c63e3-3956-52eb-ae40-867b3958b7b2 |  | textbox | Test Spec:
text | 4dd122cb-5b73-5939-ae51-f42876294953 |  | textbox | Material Visually Inspected:
text | 437e7de6-edc4-587b-ae6c-04bed3862a14 |  | textbox | Extent of overfilling checked:
text | e0fe27b1-b62f-54ae-9070-a11e236f8411 |  | textbox | Lift thickness (mm):
text | b17f1eec-8fe4-5994-8677-fdb9d3b110a9 |  | textbox | Roller type:
text | 73560968-d4e1-5b1d-8fac-609f5fc8832b |  | textbox | Minimum Passes:
text | 363803d2-0004-5ae2-825a-475fa41936de |  | textbox | URN test numbers:
date | 2110cb1c-c66f-5045-9d38-96353c1de932 |  | date | Date Completed:
text | fcaf2af5-aa1f-52fb-8e98-1b4b46cb19cb |  | textbox | Site Engineer Initial:
text | e1d2e8c7-589a-5949-af52-45b07f36bdc8 |  | textbox | Design Engineer Initial:
checkpoint-status |  |  | checkpoint | Signoff
text | e3abeab6-e3f8-59cc-8ec4-63f5abb74efa |  | textbox | Site Engineer:
date | 14b33eb6-21f4-506c-a2af-7b65e7c468b6 |  | date | Date:
holdpoint |  |  | signoff | Signature
checkpoint-no-status |  |  | checkpoint | Other Information/Comments (photos, survey records, sketches etc.)
label | 93cf1999-d406-513f-a26d-5addc69a3faf |  | note | Additional Information please document
text | 542b633b-6aa8-5b87-b6ae-3f9e38262ee7 |  | textbox | Quality Manager:
date | 3e95b62e-c71b-5412-b85d-d1f725be83f1 |  | date | Date:
holdpoint |  |  | signoff | Signature
checklist-sectioned |  |  | checklist | CS-4078 - Signal Pole Installation Record |  |  |  |  | Yes | CS-4078 - Signal Pole Installation Record | 6d92f20e-40b5-49f1-9ae0-c276e933d0b9
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | 9e9a2fe2-30d3-5057-a3d7-08115eb20b53 |  | textbox | Drawing No:
text | f2586c43-8371-503a-a8a4-06747d9f29ac |  | textbox | Pole No:
checkpoint-group |  |  | section | Pole Footing
checkpoint-status |  |  | checkpoint | Confirm signal pole locations are as per latest Drawing revision and does not clash with other Services.
text | 9d03cd2a-14ac-527d-9f13-e901b5b185e9 |  | textbox | Initials:
date | 49ddd6a6-abc0-58bf-8f2f-987b95b48b9f |  | date | Date:
label | 53b23ea3-88e8-547d-af98-e9c26fa38a97 |  | note | Comments: Design Engineer to approve if the location needs to be moved.
checkpoint-status |  |  | checkpoint | Check Survey Setout and Setbacks are to the dimensions as detailed on drawings.
text | c95011e0-ef62-5346-9d26-6eac9d57c666 |  | textbox | Initials:
date | 2eeb0dbe-4537-50cc-8d80-f15969e9641b |  | date | Date:
checkpoint-status |  |  | checkpoint | Footing Type
text | 4dfc91df-0b7d-5448-b662-4e9a70c3561c |  | textbox | Initials:
date | 3a8a1ec7-8388-5f84-8859-630f75b7f105 |  | date | Date:
label | 9d9cda6b-1641-511c-b9c6-4b64c65149ce |  | note | Comments:
label | 7350c073-2934-59ee-b825-8504f84018b3 |  | note | ○ RS 115
label | 7adb0634-d8bb-569e-964d-ebc794f10d55 |  | note | ○ RS 168
checkpoint-group |  |  | section | Excavation
checkpoint-status |  |  | checkpoint | Pothole existing services within close proximity to the foundation.
text | 3702a2b5-d66c-5f56-a958-2e4996d98970 |  | textbox | Initials:
date | dbd66311-a8ed-5c15-b517-f0fa60a83320 |  | date | Date:
checkpoint-group |  |  | section | Socket / Flange Installation
checkpoint-status |  |  | checkpoint | Ensure duct is connected to socket.
text | 7743ce8f-d20b-5964-ac0a-6db9f52a7785 |  | textbox | Initials:
date | 6caa5888-8a2e-58a2-96d7-dd8b64f78db9 |  | date | Date:
checkpoint-status |  |  | checkpoint | Design Engineer inspected the foundation prior to pouring
text | 2ae7b829-fd3a-5f50-add6-0c8aa9b1a4fb |  | textbox | Initials:
date | cc634604-711e-5037-86d0-e9928b36a2d7 |  | date | Date:
checkpoint-status |  |  | checkpoint | Prepour checksheet completed
text | 2ffbd20c-018a-593e-b6d6-dd35c2467721 |  | textbox | Initials:
date | c81cda03-58d0-5352-b48e-4ad6e1b3ed69 |  | date | Date:
checkpoint-status |  |  | checkpoint | Order concrete for footing, ensure correct mix delivered, correct slump, concrete vibrated, dockets collected
text | 70cb625f-224f-53f5-9d91-0d12ed948b18 |  | textbox | Initials:
date | a7c3b076-97c3-5b94-9d09-988855f7cdc0 |  | date | Date:
label | 01f7f4e5-054b-5aa4-9f3e-e9cf27292b3f |  | note | Comments:
text | 810c7963-93fc-55a9-ac66-93e259cd68b8 |  | textbox | Concrete strength |  |  | MPa
label | e1f62601-6d15-5a18-8b2f-81f51e102692 |  | note | Attach delivery dockets and write the road light column numbers on the docket
checkpoint-status |  |  | checkpoint | Use a stump pole to check verticality and height from FRL.
text | 28606092-1b62-5b62-879a-ce0f80212e87 |  | textbox | Initials:
date | f70a984c-2d56-571e-9d3f-ba06498877ce |  | date | Date:
checkpoint-group |  |  | section | Installing Signal Pole
checkpoint-status |  |  | checkpoint | Ensure concrete foundation has been left for min. 3 days before erecting signal pole
text | 8928edca-4840-5d67-845b-fe29a9a86040 |  | textbox | Initials:
date | 0d2404db-71ef-553b-b6c1-15696b1c3e5f |  | date | Date:
checkpoint-status |  |  | checkpoint | Check signal pole for any damage
text | 62def01f-9fa1-57e7-8ffc-5de84fa5cb05 |  | textbox | Initials:
date | 66269824-4422-5224-b1c4-3836d0201ddc |  | date | Date:
label | 0aea941d-b549-50bf-8f12-2ceb30ed3d81 |  | note | Comments: Do not install if damaged
checkpoint-status |  |  | checkpoint | Assemble signal pole on the ground (protect column by blocking off the ground)
text | 4594b8dc-e435-5e96-860f-0ab28d2e68cb |  | textbox | Initials:
date | 83f5abc7-cce7-57dc-85bc-ea95b9cb1f15 |  | date | Date:
label | 2d7c1417-2f9c-515f-8497-360639ec9286 |  | note | Comments:
text | 11b4679d-9003-57a2-b02c-42532df2461a |  | textbox | Pole Type:
text | 945eede7-1678-554d-873d-39ef3cf1862a |  | textbox | P43 DWG:
checkpoint-status |  |  | checkpoint | Check orientation of signal lanterns
text | 8878c701-021a-5e0b-aed7-e156c2f4a206 |  | textbox | Initials:
date | f42f7010-7ea1-52b0-ac76-18564869d856 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pole identification completed
text | 3463b7fe-0a9e-541b-a34b-f20fe99ca7e1 |  | textbox | Initials:
date | b7acab82-d025-56b2-aead-f5d1498eb1d4 |  | date | Date:
checkpoint-group |  |  | section | Signoff
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | e7026ce3-eff6-5595-ab8c-423ee30bc17b |  | note | Position: Site Engineer
text | b83e017d-c80f-525c-948a-d5634930a5fa |  | textbox | Site Engineer - Name:
date | 1558d237-c5dc-588e-8511-1ecba51b006a |  | date | Site Engineer - Date:
label | 03038dca-6782-5c60-9c1d-36ecb14cb23e |  | note | Position: Design Engineer
text | 8e3a8dd4-9e53-5abf-98bc-75c5a004f4ba |  | textbox | Design Engineer - Name:
date | 554edbef-0883-5f6d-8283-9d2c868812cf |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | SIGN
checklist-flat |  |  | checklist | ITP - B1001F - Devil's Elbow - MSE Wall and Ancillary Works | itp |  |  |  | Yes | ITP - B1001F - Devil's Elbow - MSE Wall and Ancillary Works | 6efdad45-2af0-4f82-86a7-2306bb896d31
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 3137e59c-562f-57c5-84ec-3cb23aad058a |  | textbox | CPS Eng.
text | 572fdb2f-d487-554b-aaa6-6896d474b915 |  | textbox | Site Engineer
text | 84216fbd-5695-5436-bd92-50b4596428de |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 0efe38c1-8cb7-5228-992a-eae0ad949622 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 67c57292-2aeb-58d4-9b58-ffa2501a1708 |  | note | Detail - Set out Base of Wall to 1m offset. Setout and mark all known services along the line of the Retaining Wall.
label | 9c549896-b740-53fa-9d88-8258d828b46e |  | note | Frequency - Prior to commencement
label | 82d275c8-5884-5006-94bd-6ce59a9a3df2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | df797c94-f776-5ad8-8571-ebf786a0fd00 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 7ccf43d5-2551-5733-ab24-45b6ea20c7d7 |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 2 - Material Compliance (Rock Works)
label | 543d2ad0-7120-53de-9307-de780dcd309c |  | note | ACTION (Hold, Monitor, Witness) - H
label | c2128041-d5fe-5ae1-b62d-68254b745831 |  | note | Detail - Material to meet specifications dependant on material type selected
label | 16f1ce5b-aa1f-5a5e-8306-3b1a90e7fb13 |  | note | Frequency - Each material used
label | 94438825-dde0-5e8c-9c12-955b57a505c1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 4b766bd9-6ce6-50da-bbf6-183fe1407706 |  | note | Records - Lab Reports
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Material Compliance (Rock Works)
label | b3b6b3e2-70ac-56d9-9be0-c7dbc4b76082 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 96bb56d5-d517-5c5d-9aba-f2e06fa9fde8 |  | note | Detail - Rock Construction Material - consistency though construction
label | a215f152-d1bf-582e-9925-76668c88ebb4 |  | note | Frequency - Each rock source
label | db73cb39-1397-5d3a-860b-6aeaf2841ffe |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 94c71316-00b1-5021-b96a-ea8c879cc967 |  | note | Conformance Criteria - Visual inspection for consistency of rock from the source should be undertaken throughout works, if variation is noted additional testing should be undertaken
label | 2a5fa48b-1c49-58d0-818c-d3bf26eca791 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 4 - Material Compliance (Geotextile)
label | 5c38672d-2799-5cb3-a127-37d1276cabef |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6d5916ee-09c9-5d27-81e4-b6fcf9bfc35a |  | note | Detail - Geotextile for rock works - Rolls delivered and delivery dockets gathered. Compliant with Terratex 750k or similar approved
label | 6f4393b5-b98d-5df1-8c71-2155a634f16e |  | note | Frequency - Prior to commencement of placement
label | 2c770e31-9980-5be0-ad08-3b1d76196fa1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 1953fd6d-68ab-54cb-837c-a55e530d1ef4 |  | note | Conformance Criteria - Conformance with Specification
label | 43843e6a-269c-5a2a-a70f-8951180e3980 |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 5 - Material Compliance (Geotextile)
label | 6ca6def0-3b6b-59db-b82f-021aadca365d |  | note | ACTION (Hold, Monitor, Witness) - W
label | ead8eb9c-e7ad-556f-891d-d9308501baf9 |  | note | Detail - Geotextile for back of excavation - Rolls delivered and delivery dockets gathered. Strength class C, Filtration Class 2
label | 42bc0e05-8353-57be-b8c2-90dabbe95c6a |  | note | Frequency - Prior to commencement of placement
label | 49307e0e-0591-5556-91e8-1ed5933827bb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c5e11a35-abd7-5639-912c-e51f18de6a72 |  | note | Conformance Criteria - Conformance with Specification
label | 325dba8f-f012-5de1-a5b8-a5cdd5d52273 |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 6 - Material Compliance (Geogrid)
label | b6bcb43b-c8bd-5397-8ad3-72ebdd14a8aa |  | note | ACTION (Hold, Monitor, Witness) - W
label | e02c98a4-fa2e-5f46-9915-36aeda6f8737 |  | note | Detail - All rolls of Geogrid are to be checked and left in their protective wrappers until they are required for use
label | 36f32d66-4467-5c22-9b5f-b4a562aabec3 |  | note | Frequency - Prior to commencement
label | 66e7e001-8a7d-5657-b1dd-d56c0433204d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 5dd97ae4-d1b5-5759-bc99-2e0b8c876354 |  | note | Conformance Criteria - Any defective rolls are NOT to be used in the wall construction - return to the supplier immediately
checkpoint-status |  |  | checkpoint | 7 - Material Compliance (Geogrid)
label | bd130123-97f9-52da-bb6e-16672fa10b5e |  | note | ACTION (Hold, Monitor, Witness) - W
label | f9499758-a71a-58cd-a703-86177c4e8e03 |  | note | Detail - All rolls bar codes are to be collected and attached to the rest of the QA Documentation
label | e36de997-478e-54de-bed5-99074e522ce4 |  | note | Frequency - Prior to commencement
label | 1739b61f-94da-56a2-9a73-a496135d1832 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | fae52fa6-f4c1-5415-a9bd-1635b7b85d6b |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 8 - CTV Culvert
label | 3e3f6c74-dadd-504d-afa1-c224a301a607 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c15afd9a-c3a6-507f-ab28-a148a02d0137 |  | note | Detail - CTV existing culvert to confirm it should be repaired rather than replaced
label | bc5775a5-7284-5813-ac3b-4bfb5a2fb180 |  | note | Frequency - Prior to commencement
label | d5b30e20-2789-5f79-bb7c-2e09f02dc334 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | dc8c9375-657c-53f3-b728-a909ad29d78c |  | note | Records - Inspection Video
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Culvert Extension
label | cf583fc6-2e1f-531b-a60c-719e480fec56 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 61067676-3ad5-534b-9236-d90f8cf0a94d |  | note | Detail - Confirm extension connection methodology with CPS Engineer
label | 4ef1dabe-5b39-5ef1-94aa-b64eacae6221 |  | note | Frequency - Prior to commencement
label | 83bb1d19-220b-55d7-8baf-cb19cc96678b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - submission
label | 62e45de4-b2e8-56b5-bf62-f8d211511938 |  | note | Records - Subcontractor's method statement
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Material Compliance (Anchors)
label | c07a63e2-bafa-5480-b0eb-8a26cf5366fe |  | note | ACTION (Hold, Monitor, Witness) - H
label | c8a4363b-bd5a-544d-910c-9a7a73be670d |  | note | Detail - Ground Anchors and proprietary components (plate and lock nuts) - Manufacturer’s test certificate for each batch of anchors. Testing shall be undertaken in an Australian / New Zealand Telarc certified laboratory.
label | dd5d9e5d-eac1-58b7-8809-867545686c93 |  | note | ○ The required minimum physical material properties information are as follows: Diameter; Steel area; Ultimate load; Proof load at 0.1%; % of Elongation at yield load; Modulus of elasticity; Relaxation after 1000hr. Refer to specifications and drawings, including proof of coating galv and epoxy.
label | 0196a104-6eae-55df-b509-9889c21e01fd |  | note | Frequency - Prior to commencement
label | a9de789d-c4f7-5a05-99e4-f4607f4e2d06 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 0d9f9efa-072d-5d7a-9f79-c3a951a7b83d |  | note | Conformance Criteria - Manufacturers compliance test certificate with relevant delivery dockets
label | 3b6b945d-4841-518a-aee0-73cae73f1222 |  | note | Records - Supplier Certificate, test results and delivery docket
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Material Compliance (Anchors)
label | 67f8dd90-577f-500e-b7cc-936291d3b0d3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ef0815a4-58c4-5a02-b013-693136393f78 |  | note | Detail - Grout mix - Approval of grout mix design. Include method of batching and mixing and previous test results for pumpable cement grout mixture. Refer to specifications and drawings for grout details.
label | fc104a07-66d0-5971-a47d-a21ddbec61db |  | note | ○ The water-cement ratio shall not be less than w/c = 0.40 and no more than w/c = 0.45. The grout shall not be subject to bleeding in excess of 4% of the initial volume. Admixtures which can control bleed or retard set of the grout shall be used only when approved.
label | 39d74a2c-7277-5737-8d94-dae45e7aefae |  | note | Frequency - Prior to commencement
label | 681cea4e-fb87-58e8-94b5-952386060fb6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 488a2d06-984c-5a85-8acf-5dd83226fc17 |  | note | Conformance Criteria - Approval of Mix Design
label | 6ed739ed-43e0-5afa-8ed3-7e83887ed3bb |  | note | Records - Grout mix and test results within subcontractor's method statement
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Material Compliance (Anchors)
label | 1eb77e36-73f9-5e5c-b90b-51cdd2f3ae37 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f03d7ef0-8e35-5868-a4fc-fecf1ae5ec82 |  | note | Detail - Anchoring methodology - CPS has reviewed methodology including location, drilling method, grouting procedure, stressing and testing methods and reaction frame details
label | e8ac7ab2-3506-5775-a3b3-97ca26b92757 |  | note | Frequency - Prior to commencement
label | aeb327ed-db75-555e-b96d-efedfbd71858 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 46d06781-9aec-5639-ab73-c85719823afb |  | note | Conformance Criteria - Approved subcontractor's method statement
label | 1017ed5a-b5ff-5747-9124-ce2db3e8815e |  | note | Records - Subcontractor's method statement
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 - Material Compliance (Walls)
label | 65b72d5f-0415-50f6-aa8f-885aaf9fb908 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 38b36c02-55e7-5562-a969-3e1a8abec3be |  | note | Detail - All blocks that are delivered are to be approved for use and are compliant with the Specifications
label | aa97b219-d8a6-591a-8b06-10c92336d2c2 |  | note | Frequency - Prior to commencement
label | 141b9b01-c3cf-5681-ba4e-eae40014ca33 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 514f06d2-e69f-5e9e-8877-c9c1424a464a |  | note | Conformance Criteria - If patterns are used on walls then ensure that the correct colour blocks are ordered and instruction given to teams
label | 02b64a08-9dc9-5c74-9d55-111ed9e88252 |  | note | Records - Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Fill Material Compliance
label | d42b8b6b-7639-576a-b6e6-cb52f0690a1f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6c156218-6ea1-5f9d-b931-8c768d35c01d |  | note | Detail - Material to meet specifications dependant on material type selected
label | 293673fd-16b2-5c33-90fc-3df0b768c8a6 |  | note | Frequency - Each material used
label | ea120a3e-8c94-5fe5-abcf-85708f3d089e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | d5ac925e-c93e-5f60-8593-542fcc952a3b |  | note | Conformance Criteria - Compliance with project specification
label | 6e720974-59a4-5464-83db-0bb752caa3a5 |  | note | Records - CS-4020 Bulk Fill Earthworks Record
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 15 - Fill Material Compliance
label | a3d2658b-646c-5142-9a3d-769370e95f32 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9a5433fe-d0b5-50e3-aaff-ee4132cb3c6c |  | note | Detail - Fill Construction Material
label | eaed13ef-522d-52ca-a09a-e528094af94a |  | note | Frequency - Each material used / borrow pit
label | e344952e-5a40-5a35-8868-c80787f06377 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | e9819085-37c6-53ec-96c2-3e1a27e3cb21 |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 16 - Repair and Underpin Box Culvert
label | 1d660711-0e30-5864-83db-ebb148aef021 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1389cbd5-1c6e-5ca1-8915-db23e3bc9d72 |  | note | Detail - Repair as per drawings and specifications
label | 55d64c54-3f5b-5f94-a2f7-d2845150fa91 |  | note | Frequency - As required
label | 1a02c060-9917-52af-8d59-41bce6b7694b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 98273bf0-2a5d-5cba-88a0-a94048bd9323 |  | note | Conformance Criteria - As per specification and ecology requirements
label | fd29d97e-c799-54c0-855d-d40a310b0fdf |  | note | Records - Photographs
checkpoint-status |  |  | checkpoint | 17 - Excavation / remove temporary fill material
label | f6f1fe73-1ae2-53b7-a71a-ef2a5c59699c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 64be7a08-8523-508e-8087-11b9acb668ec |  | note | Detail - Ensure that all top of batters are rolled over preventing erosion & slips during/after constructions. Road seal may need to be cut where it is undermined.
label | 33a422f5-dcc0-562f-a129-799488db1830 |  | note | Frequency - During construction
label | ec4461ee-e2cd-5e12-a1dd-729882c4a86e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | dd46237a-edf6-588e-9cee-037aab5d11fe |  | note | Records - Photographs
checkpoint-status |  |  | checkpoint | 18 - Excavation / remove temporary fill material
label | 4de5d0a4-2fc8-5f4c-986e-8731ed3a2b15 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ece43a07-0a9a-5ac6-8c35-06c7d1e34dd3 |  | note | Detail - Cut inspected by Geotechnical Engineer when conditions/material type change
label | e0fc5988-3f1b-5b05-b9e5-5c163cf77eaf |  | note | Frequency - During construction
label | 2da77dbe-cd9a-5ee0-b3d8-030b314c740a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint-status |  |  | checkpoint | 19 - Excavation / remove temporary fill material
label | c63c03e3-d709-5e64-878c-ea65fb089c2f |  | note | ACTION (Hold, Monitor, Witness) - M
label | df97b6c5-0082-5e8e-8533-2b23ec058b96 |  | note | Detail - Ensure cuts are staged. The slope should be trimmed in stages to maintain stability rather than cutting entire slope in one hit
label | 4d4ae65b-b534-56e7-8297-f53e45bf8447 |  | note | Frequency - During construction
label | 7fbae0c4-d7e7-5caf-b113-96aba2da1884 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint-status |  |  | checkpoint | 20 - Excavate Base of Wall
label | 2e2b7811-b1a3-5403-a850-602191a8b7cd |  | note | ACTION (Hold, Monitor, Witness) - W
label | 78fdf854-659e-59d4-99d3-478ad2a984c6 |  | note | Detail - Excavate footprint of the wall area to the correct line and level and ensure area safe to work in.
label | bb879450-efac-5d93-bc7c-6449e1cfe72e |  | note | Frequency - As required
label | 42bca4aa-8496-5044-b8f0-b25e23fcc7ad |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 9379ac16-e85d-5f83-a296-f07f84d16174 |  | note | Records - Survey Receipt
checkpoint-status |  |  | checkpoint | 21 - Excavate Base of Wall
label | 6c797fd2-c3c2-5ef4-8b13-b6581b871d1f |  | note | ACTION (Hold, Monitor, Witness) - H
label | f9e4500a-d110-5947-b756-f875b986c38c |  | note | Detail - Test the base of the excavation to ensure it meets Specification.
label | bfbd1ff9-62b5-57cc-9034-10ba32c3636d |  | note | Frequency - Prior to backfilling, as per specification
label | a7b9fd32-bf48-503c-8c11-8c701430636c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala and Shear Vane
label | 7e93245d-6609-58b4-85f8-b3dfeca525c7 |  | note | Conformance Criteria - In accordance with specification
label | fc133c33-6324-5587-acf8-02f759023622 |  | note | Records - Lab test result
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 22 - Excavate Base of Wall
label | 3567d1e1-32ce-5a60-ac31-85f9a1d1760a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 00662ab0-7961-5035-af89-7ff4bd4cb5ba |  | note | Detail - Base of excavation to be checked by Geotech engineer / CPS Engineer
label | 3b1a305f-3493-5396-aa4e-fe34a1a7b1ce |  | note | Frequency - As required
label | 2a482da3-0e94-54b7-9728-13f3247234ac |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 72c89d3b-b4c8-5ef3-b83f-f626fd0f97f0 |  | note | Records - CS-4100 Subgrade Approval Checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 23 - Dewatering
label | 30cc9d36-d545-5180-ab23-c22b760c1eed |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1ceac54c-3afa-5860-8da7-03b03e399e0c |  | note | Detail - works shall comply with the relevant consents and the projects Environmental Compliance Requirements
label | 1fb60fe8-0c93-58d2-a264-61918c7dedd6 |  | note | Frequency - As required
label | f686a5b6-0606-5ec6-831e-e3214f9e23b1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 5bb30772-4fe8-53f9-bef5-dd57bf49d021 |  | note | Conformance Criteria - Dewater in order for construction requirements
checkpoint-status |  |  | checkpoint | 24 - Undercut in areas deemed unsuitable
label | 45b02a34-180f-5cfd-8273-d9045c52b280 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a5b94438-0d3b-5915-b8ac-e6a3770d7f9e |  | note | Detail - Cut to waste as required
label | 447d3787-f6eb-57d8-bbf1-eeb3fdf9c601 |  | note | Conformance Criteria - As required by specification and CPS engineer
label | 47091562-6fe1-5f35-b57e-73b9377f71d5 |  | note | Records - CS-4100 Subgrade Approval Checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 25 - Geotextile Placement
label | 910eb600-9506-5c4b-9242-a73f3da405c0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6b8f1375-b2e8-5677-886b-d1fcc8bb9cf7 |  | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | 1affba71-c385-54b2-92c7-a20787c8546c |  | note | Frequency - Daily visual check
label | 43792f9c-a0da-5db0-a0fb-5d597c0a9e4f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | ec036213-3d4c-5231-bf23-2f63e65d5ad9 |  | note | Conformance Criteria - Specification
label | e60c1236-4244-59a6-9c6a-0d7c1b2119f9 |  | note | Records - Photographs
checkpoint-status |  |  | checkpoint | 26 - Riprap Placement
label | deba4e57-af6a-5446-a89b-f305c41a08c0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b328aaa0-8bf6-5f98-9e8f-fe2b78b6c59d |  | note | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. It should be well interlocked. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material
label | c8b80128-b6c5-5708-852c-c6cacd8c88d7 |  | note | Frequency - Daily visual check
label | a1f59599-19ed-57ba-9675-c0bf58da3ef8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 81c32246-cc5a-593e-acaf-5ed17d9787a8 |  | note | Conformance Criteria - Specification
label | d7ce471a-2688-5611-9cac-1e1f419b3db2 |  | note | Records - Photographs
checkpoint-status |  |  | checkpoint | 27 - Subsoil Drainage
label | 6a3489a7-2036-51a7-90eb-b192d4a7e10a |  | note | ACTION (Hold, Monitor, Witness) - W
label | db5bb35a-4e2f-51ce-ac2e-1d908b737a63 |  | note | Detail - Install subsoil drainage as required in accordance with specification
label | 6fdc6c11-5dec-5eca-b574-c3c8dfcb6e0a |  | note | Frequency - Prior to construction of wall
label | fdb50df3-59cc-5217-9161-bf113e5bba01 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 04bcdf19-751c-54cc-a5df-1546d18555ef |  | note | Conformance Criteria - Specification
label | db43226e-379d-5de8-a4b2-1634eef92857 |  | note | Records - Photographs
checkpoint-status |  |  | checkpoint | 28 - Construct MSE Wall
label | 2d72fcba-2d29-5772-9957-e473f5c52635 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 44de7b73-8a60-559f-8a7b-11c1598a91ea |  | note | Detail - Place concrete foundation including grouting starter bars as per specifications/drawings
label | 31569aac-909c-50da-875c-e451fd4e2757 |  | note | Frequency - Prior to construction of wall
label | 4743b562-280f-52bd-917a-5b0415340a75 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | ab5e8b36-2c5a-5ca6-974d-520a5133d1ce |  | note | Conformance Criteria - Concrete to meet the specifications, collect all delivery dockets
label | 2233ff98-d576-5420-a662-13d23c24986a |  | note | Records - Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 29 - Construct MSE Wall
label | 3a4ca5a2-7b3c-5dfd-a3c6-abef4dd7bd1d |  | note | ACTION (Hold, Monitor, Witness) - H
label | e02958fc-a58c-5e22-8f51-24c3b37b287b |  | note | Detail - Confirm with CPS Engineer extent of MSE Wall vs Anchored Section
label | 41be8be1-0131-5b5d-b9ac-43f0536fd0fc |  | note | Frequency - Prior to construction of wall
label | f6107d6b-ee5e-58e8-9c79-83e9bbfef757 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 24071834-72aa-5014-8ac2-4337f0da1a55 |  | note | Records - Submission Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 30 - Construct MSE Wall
label | 254b2522-e3da-58d2-a0e9-487449fc8a17 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6b2b8ed6-91d5-590d-bb2b-94106aaba994 |  | note | Detail - A Permit to Lift has been issued to the contractor carrying out the works and there is a Lift Plan available
label | 6ff4dd1f-50bb-5466-9966-f541910cc108 |  | note | Frequency - Prior to construction of wall
label | 1bae1e98-b1a7-5198-94e0-dd63acc62f82 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 10767bfc-7a39-5b36-8bc3-735c32c33906 |  | note | Records - Permit to Lift
checkpoint-status |  |  | checkpoint | 31 - Construct MSE Wall
label | a0c99e86-0b5f-55c9-83c8-74a8ac041578 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4dbcc38c-fec3-5791-a17f-da88e57081fb |  | note | Detail - Install Mass Blocks as per Manufacturers specs along the front face of layers to ensure correct line and level.
label | e9ec4f48-0ba7-57cf-8d37-44121aa545fa |  | note | Frequency - As required
label | a84b785c-7f96-503c-9c8b-08cd1922424a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | f1a6da0f-8443-56fc-b64d-e47afb138364 |  | note | Records - CS-4012 MSE Wall Geogrid Checklist and Photo's
checkpoint-status |  |  | checkpoint | 32 - Construct MSE Wall
label | b29918b4-36d4-512f-9cd8-c4fbd6675f60 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b85d7fc4-b179-5dd0-a7bb-89495c18048f |  | note | Detail - Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately
label | 0efc1591-2eaf-5958-a334-ce4ca6b43471 |  | note | Frequency - Daily
label | 1ede7997-b47f-58fd-9b70-02bc0ad9a915 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 844849bc-5bd5-5d02-a966-af3dab9e5e52 |  | note | Records - Photographs
checkpoint-status |  |  | checkpoint | 33 - Construct MSE Wall
label | d5ba0742-3f33-5a63-ad63-7109c174a861 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c5cd9910-c5d9-50e9-ad45-207ed9583f87 |  | note | Detail - Install Drainage Blanket as shown on Drawings
label | 3aa46e99-2c45-5943-af61-0df7a5dc7f71 |  | note | Frequency - As required
label | 06100635-2693-522d-9edc-c9e7e3f077e5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | ecec5d98-06f9-54e8-843d-76c2e7eff424 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 34 - Construct MSE Wall
label | 3aed1c86-44f4-564a-a8be-bf9c4d19f2db |  | note | ACTION (Hold, Monitor, Witness) - H
label | 59db43a2-dddf-5053-a2fb-b26b4283e472 |  | note | Detail - Install grid layers as per drawings and have CPS Engineer signs off each layer.
label | 54c1869b-a2ce-581f-a449-7457c49856c7 |  | note | Frequency - As required
label | c387776f-1e0a-53e0-8826-5847c9a9ccc4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual / Survey
label | b7397851-a8e9-5937-8850-c5d3a9c465f5 |  | note | Records - Survey Receipt and CS-4012 MSE Wall Geogrid Checklist
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 35 - Construct MSE Wall
label | 7dfc2f13-b77e-56ba-8be7-47a9b879ada3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7e90d148-46b4-58ec-b9f3-0b4b549d896e |  | note | Detail - Place fill material on grid layers as per drawings and compact to MSE Wall specifications and test.
label | e41d9e74-27ef-5ba1-b507-41637247e6cc |  | note | Frequency - Every lift
label | 77aba6d1-fb95-5be7-87b4-ef3f7b021dbc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 23844160-a9b9-5abe-8b6e-ec91551b899d |  | note | Conformance Criteria - As per specification
label | 46191cce-67fc-5e6f-a0e3-2fc393c735e2 |  | note | Records - Lab Reports
checkpoint-status |  |  | checkpoint | 36 - Construct MSE Wall
label | b5d14088-584c-5c33-b668-7f4b1291ecaf |  | note | ACTION (Hold, Monitor, Witness) - W
label | fe6fc8b3-e751-5f85-b62c-b3eb38c1bc30 |  | note | Detail - Ensure line and level of front face is as per design
label | c99ae914-0e5c-5ecd-8751-56e71b1023fa |  | note | Frequency - Each Lift
label | dc3af2e4-5266-5287-9239-f630176daeaf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
checkpoint-status |  |  | checkpoint | 37 - Installation of anchors
label | 50fa01de-d3c0-546a-a9a5-9cbbf9992854 |  | note | ACTION (Hold, Monitor, Witness) - H
label | be665be4-2071-5211-86be-b39454e786f6 |  | note | Detail - Install and test sacrificial test anchors, location to be determined with CPS Engineer, testing after 7 days when the Grout strength has reached 30Mpa
label | 1505a2db-49db-5020-ac75-b987438b299f |  | note | Frequency - After Construction
label | a2cac842-03ce-566f-a081-2a23a26f42d2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 697d7126-c507-545b-a7ee-aeb5abd05fc1 |  | note | Conformance Criteria - Load testing - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | ae5f2bb6-bb46-5891-a80b-7e4b5e1ab725 |  | note | Records - NTC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 38 - Installation of anchors
label | c45c5dc9-5c83-572d-9d00-a300684935f0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2e2b047a-0eba-54e6-85b6-47a4c80bc31b |  | note | Detail - Construct working bench, this will form permanent backfill
label | 70b472a6-f8da-5e75-a70f-ad2fb84c917e |  | note | Frequency - During Construction
label | 08e26c84-ed69-56fa-ab36-27fbd3838172 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 921192f4-9572-5695-aba7-221e608faea5 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 39 - Installation of anchors
label | d28d508b-51e3-5acb-bda7-0e97b2fa8007 |  | note | ACTION (Hold, Monitor, Witness) - H
label | bfc86560-54b2-52c2-b331-370044ec2d75 |  | note | Detail - Drill holes as specified
label | 3b483d8e-6642-50b8-8708-75eed815250c |  | note | Frequency - During Construction
label | 435bf875-0b5b-54a0-b8f2-94a14cbc2bd4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 39f9ca12-afc6-5151-a7af-cb7ae16f75bd |  | note | Conformance Criteria - Drill within +/- 2 degrees and +/- 100mm of position
label | f114fce4-b0ff-5ff0-92a3-10593e613b0b |  | note | Records - Subcontractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 40 - Installation of anchors
label | f1be3477-996e-5e52-afad-2622d5072868 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6e3283ab-2052-5003-be3d-4337262c28eb |  | note | Detail - Install anchors as specified
label | 08aaed4c-3bbe-581f-b660-2ee5f476d5af |  | note | Frequency - During Construction
label | 24854203-8d18-56b2-bfed-f78ae8ea3a8c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 0cb8a8e7-3b00-5fd8-9f33-1cf52e00ed6a |  | note | Conformance Criteria - Ensure lengths are that specified on the drawings, centralises in place
label | 54f5dd7f-efed-54b3-8091-b22a9db93245 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 41 - Installation of anchors
label | d86887d3-1bd9-5a21-9a4e-d77b9d5cd106 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ded0f554-af93-5ac5-9473-5a510f8e502f |  | note | Detail - Install Grout - take sample of each batch. Note holes not to be left open for more than 24hrs
label | 4d6cbae0-b6f0-55ab-af98-a070f8734d1c |  | note | Frequency - During Construction
label | 87140848-28a1-5032-8104-1bb8e53031b3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | a1a94c4f-b792-524c-a446-bbf6f5a3a354 |  | note | Conformance Criteria - Compression cylinders to be tested at Lab
label | b90d8b07-c65a-56b0-8d11-5b999c70856b |  | note | Records - Lab Test Results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 42 - Installation of anchors
label | 6f60960d-66cb-5524-88af-91fd86fe5761 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0730be2d-6f01-5d09-ba81-5a38b84eb884 |  | note | Detail - Test of Production Anchors - after 7 days when the Grout strength has reached 30Mpa
label | 376e36f9-6629-5965-b756-8e9edf68acc0 |  | note | Frequency - After Construction
label | 19b89412-607f-538f-9b15-2d056628c7d6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 785e6a09-30a5-568a-b3fd-c843a358f6ee |  | note | Conformance Criteria - Load testing - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | 78c1fa38-e6ee-5152-935b-6b1b2ed883f3 |  | note | Records - NTC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 43 - Installation of anchors
label | 37d049ba-58d6-5bdd-8bb4-095377fe156e |  | note | ACTION (Hold, Monitor, Witness) - W
label | 44710382-4632-5c71-89b3-594825c3f273 |  | note | Detail - Extend anchors to tie in with wall face and install washers, nuts, and corrosion protection as required
label | a290cfc9-685f-538f-8819-5175e6839c08 |  | note | Frequency - During Construction
label | 9e852cf1-4be9-5d50-aa08-9b84a6f92deb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | f52e8243-e303-5f9c-a4b9-a8fd7e75aa99 |  | note | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
label | 41875525-5d0e-57cc-80e8-680a7d4d896f |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 44 - Installation of anchors
label | f6703789-1138-5581-8ba5-9aa248ad8319 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2e7160ea-a47d-5f02-be52-84820a66f7a7 |  | note | Detail - Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails
label | 0fe9b384-acdc-551d-8e0b-4568d750307e |  | note | Frequency - After Construction
label | 748afbc4-8b3c-576f-a5a5-9fce86e19ee7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 33d1b9af-010a-51ba-8e70-5561e19fdf38 |  | note | Conformance Criteria - CPS Engineer to give approval via a NTC
label | 494c715f-640a-500b-ac46-99296aa205a9 |  | note | Records - NTC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 45 - Wall Reinforcement (anchored section)
label | cc996206-e7b0-598d-91be-4c6cf058185b |  | note | ACTION (Hold, Monitor, Witness) - W
label | 37cfe1d9-a132-5623-8499-556f5145c60e |  | note | Detail - Check supply and installation of reinforcement in wall
label | 5f5a3498-a53a-5aba-a6db-f8147a1789aa |  | note | Frequency - As required
label | d860807f-d525-5634-9d8d-a1e1a215068e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review & Visual Inspection
label | b7056cd5-7892-53a4-9d52-e75ec5caa114 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 46 - Wall Reinforcement (anchored section)
label | 8106273c-926e-5dec-b1bb-457ced577629 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d998a4d0-d15d-51c4-90ab-f1e1edc261e1 |  | note | Detail - Arrange for inspection of installed reinforcement
label | 1a10a070-60c1-5bd5-82e9-8914080116b0 |  | note | Frequency - Min 48 hours prior to pour
label | 8a0940e4-cef5-55c3-9901-7285e7f0e422 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 04fbee31-34fd-52c3-b75e-340ea0ea3a15 |  | note | Records - CS-4096 Bottom Driven Pile Record
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 47 - Slope Filling Operations
label | 80648372-7225-5782-97ac-596caff823da |  | note | ACTION (Hold, Monitor, Witness) - W
label | 41e0e1a8-0999-5963-8e3e-3c9fcaf58880 |  | note | Detail - Install grid layers as per drawings and have CPS Engineer signs off each layer.
label | 31d0b5be-f8c0-510d-9f20-1ca9d6169980 |  | note | Frequency - As required
label | e20c72c5-df8c-59e6-ad2a-914ad3cfe26e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual / Survey
label | ad29b1c8-f715-5684-923e-df671906be30 |  | note | Records - Survey Receipt and CS-4012 MSE Wall Geogrid Checklist
checkpoint-status |  |  | checkpoint | 48 - Slope Filling Operations
label | 6709cf61-ce82-5f42-a3f2-1e3251808556 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3b1f0c07-cc58-5fce-a026-87b89d58981f |  | note | Detail - Fill placed within 1m of structures or obstructions shall be placed with care using suitable equipment and shall be placed 100mm thick and shall be 1 lift higher than the level of the surrounding fill
label | 08f1c5be-370b-5a46-9867-54493d332638 |  | note | Frequency - During fill operations next to structures or obstructions
label | cbc77a84-1725-5eac-8f9f-2224b13efbb2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | aa756d0b-39a2-572b-a117-9d3b43746ef4 |  | note | Records - CS-4020 Bulk Fill Earthworks Record
checkpoint-status |  |  | checkpoint | 49 - Slope Filling Operations
label | d68b5832-a85f-52e2-9280-20f79b6e6ab4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 70cbbb01-5dec-550e-bd19-9a1c53131f82 |  | note | Detail - Site Engineer to check embankment slopes for location, line and level as the fill progresses ensuring that batter faces are overfilled and trimmed back so that so that the fill is well compacted to the edge
label | 65deb6f0-cc79-577d-82bc-acdd891d9d99 |  | note | Frequency - Daily visual survey check
label | 27b3916a-c0af-50b4-b4b2-c9abccbfdf6a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 2191dba4-9cbd-5cae-89b2-c60869720bec |  | note | Conformance Criteria - As built drawings
label | a3f6d199-89ce-516f-882b-6af8233a4de5 |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 50 - Slope Filling Operations
label | 1cd90cf9-661d-5812-ad7e-79c4655f7756 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d30cf8d2-4c32-5b38-ab7b-5cbeeee6f58b |  | note | Detail - Fill placed in horizontal layers no greater than 250mm and compacted. Site Engineer to instruct lab when and where to carry out testing
label | 85c72bb7-7cb1-5b42-9d4b-190098f7a8a8 |  | note | Frequency - As required
label | ed3f1f12-5a5e-5f73-81b3-a54f0fa534b6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Lab Testing
label | 0e3da47a-0d8f-55d5-b160-30a9587f09f8 |  | note | Conformance Criteria - In accordance with specification
label | c033f793-58f2-529a-a798-09d6b7e85c45 |  | note | Records - CS-4020 Bulk Fill Earthworks Record
checkpoint-status |  |  | checkpoint | 51 - Install Erosion Protection
label | 1bf23029-9b2b-55c0-9bad-a11508301f53 |  | note | ACTION (Hold, Monitor, Witness) - W
label | dbe65ab7-9b54-581c-8f60-f10062d3b1d0 |  | note | Detail - Install T-RECs tuff matting or approved equivalent
label | b5f965f6-5a8b-5a5e-bf72-91a43128d2e0 |  | note | Frequency - As shown on drawings
label | 81ddd361-979d-54fe-aa29-3144df007d7e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | dfc57650-7fb3-538a-be8c-d3511c18de91 |  | note | Conformance Criteria - In accordance with specification
label | 228da73a-88c0-5130-91a0-a565a26bb9d8 |  | note | Records - Photographs
checkpoint-status |  |  | checkpoint | 52 - Install Erosion Protection
label | 73713737-5c0f-51ac-9402-e803a68ea621 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 12cd1247-9175-5ed9-8bd7-d4f442f9febf |  | note | Detail - Install anchored erosion mesh as specified
label | e8424d5c-9b82-5055-aa7b-91dc13f80072 |  | note | Frequency - Details as per anchoring ITP Section
label | 9d4207a3-2a5b-5da1-9602-9555d858c698 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual, Measure, Testing's
label | fb4f26ad-b576-56f1-b62e-6156b3da88ec |  | note | Conformance Criteria - In accordance with specification
label | 9fb1a7ba-b5a1-532c-bc8b-211beec72199 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 53 - Install Erosion Protection
label | f8b69db1-47f5-5d30-be51-ff78e7468bbc |  | note | ACTION (Hold, Monitor, Witness) - W
label | c5a244dd-b19a-5187-b7fa-eae38dda31a6 |  | note | Detail - Mesh - Greenax steel mesh or similar approved product installed and joined as per manufacturers guidelines. Fixed to anchor heads correctly, and fix to wall
label | 450084db-5764-541a-8963-7a9b9819102e |  | note | Frequency - As required
label | 724263c0-0a59-5457-9968-2c3d1ca2d056 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - During installation
label | ad64122b-cd0f-5501-8ca2-ff24fec099c5 |  | note | Conformance Criteria - Visual inspection, extent to be confirmed on site with CPS Engineer
label | bc510f89-e24f-5390-8864-1a28dd28c150 |  | note | Records - Delivery dockets, Photographic evidence
checkpoint-status |  |  | checkpoint | 54 - Install Erosion Protection
label | 3c94e5b2-0293-5444-8f28-9208c643c72a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 33d82d7e-9c04-5dbe-ac86-ed42bb70572f |  | note | Detail - Ensure that placement of rock material on batters is placed in such a manner to minimise segregation and avoid displacement of underlying materials. It should be well interlocked.
label | 0478df86-4da5-52d8-846c-291007a6c78c |  | note | ○ Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material. geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | 282c6c12-64c0-593d-8058-2cfe47143031 |  | note | Frequency - Daily visual check
label | ca13898e-cd45-5964-bc54-f18fbc1da0e6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 61aff1d4-e76f-5ce3-b347-67157bd9f005 |  | note | Conformance Criteria - Specification
label | 79799cf3-75d3-54d2-921d-527a6d9dbcb5 |  | note | Records - Photographs
checkpoint-status |  |  | checkpoint | 55 - Pavement Construction
label | 59c98e56-12d3-553c-b7b6-577fb731a007 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 42209831-ce90-5054-a2f3-2a48b37bbbf1 |  | note | Detail - Pavement construction and tie in as per specification
label | 729316ce-0f60-53bc-a176-7db82aab43ce |  | note | Frequency - As Required
label | de40b8c9-4017-5e02-831a-b4910f23a76d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | a5eb3eb1-0ce5-54ea-aa1c-9e97c23c572c |  | note | Conformance Criteria - As per specification
checkpoint-status |  |  | checkpoint | 56 - Pavement Construction
label | 4e64076f-e73d-5bb0-8686-31b6ba8d9040 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 20ba0458-8cc0-5767-8e2a-01175e0a371a |  | note | Detail - Guardrail Installation installed as per manufacturers requirements
label | 2bd1c680-c805-5d5c-8cf0-31fd988f31b1 |  | note | Frequency - As Required
label | 34aca85e-c04e-50be-9197-5c6ce2673342 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | f270069c-353b-54ff-848e-20f5899ea855 |  | note | Conformance Criteria - As per specification
checkpoint-status |  |  | checkpoint | 57 - Survey As Built
label | 92238f9d-25be-542c-a38e-14fd19232225 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9c5b113e-0176-5055-b416-a44352b38ad1 |  | note | Detail - Ensure all works comply with design prior to carrying on with next construction process
label | 17300970-02a9-5c24-a542-28984bcf4054 |  | note | Frequency - At completion of sub soil drainage line
label | 20b0938f-17de-594f-abf5-5693594f0453 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 6f8c9907-65b2-5639-8aa6-4eff15b726be |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 58 - Confirm testing requirements met
label | ec5173e6-daf4-5d51-8806-c95cc2384c45 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e3de4b3d-394f-5510-95c6-c342247fb7b4 |  | note | Detail - Ensure correct no. of test sets performed for fill testing
label | 36c6ae7b-d2db-580c-9341-d0a4c739eb46 |  | note | Frequency - At completion of Lot
label | 9858d43f-5c9d-54d1-b81c-8c2aeb2f7d3b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 4c56c10c-5a99-5bff-a1de-d53e5500ecd2 |  | note | Records - Test results and calculations of fill volume
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 59 - Lot Number QA File
label | 9905a3ff-24ef-501e-99a3-a77ca2bcafdc |  | note | ACTION (Hold, Monitor, Witness) - W
label | 266b672d-4ee3-5001-ad44-dffedaf56b1d |  | note | Detail - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | ca12fbb1-f10d-52d7-8560-d4fa6962a6c3 |  | note | Frequency - At completion of Lot
label | b9ac2b24-faed-5ad1-88f3-2fb1afae33e0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | d66a8565-58a3-55fe-847c-3d6cda49c56c |  | note | Conformance Criteria - Ensure all QA is uploaded into M-Files
label | a935dc42-e83a-527a-8d50-37d46df1d37d |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 60 - Construction Report
label | 415dcb14-8a2c-5d34-a38c-17b6753209ae |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3b8c60c4-a1d6-5cd7-be9c-d56c9e4e61ae |  | note | Detail - Construction Report identifying the actual types of materials and methods of construction used throughout the Contract Works.
label | 81f2e026-b08a-51e1-9e64-774823df0d71 |  | note | a) Explain the problems and defects encountered during the construction of the Contract Works, and how these were overcome or put right;
label | 380f3391-c893-578e-ade7-633a847b6dde |  | note | b) Comment on the remedial and corrective actions taken;
label | 1350f4ef-a08c-552f-9c9f-443a9d21af37 |  | note | c) Comment on any construction outcomes that will impact on future maintenance;
label | 15ce5341-2fed-5438-ad7f-141d28f1459c |  | note | d) Include a complete record of all laboratory (and other relevant testing) information for all Materials used in the Contract Works;
label | f691588b-4e5f-50e5-8a7b-adb3fb9da934 |  | note | e) Include mill certificates for all reinforcing steel, pre-stressing strand structural steel and anchors used in the Contract Works;
label | 5921e714-55a3-53b3-88d3-c392054cc506 |  | note | f) As-built survey along the highway centreline, providing co-ordinates and levels of the highway, at maximum 10 metre intervals, certified by a Registered Surveyor. The survey shall be in terms of an established LINZ datum;
label | 5b27fb06-0d6e-5bc5-a8eb-f6e2b81b7889 |  | note | g) Material warranties;
label | 05e7fea4-0847-5da5-8599-945967d713f9 |  | note | h) All information pertaining to the construction of the Reinforced Soil Slope (RSS), MSE retaining walls and scour protection, and any future maintenance requirements.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 61 - As-builts
label | e1747d79-d1e4-5281-8e0c-63487d12b892 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f7a737c1-ad15-5901-b74a-de0847b4bfd3 |  | note | Frequency - At the completion of the Lot of work
label | d6c48777-c5a0-5423-bf43-e061dfd63ad1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 7b869b47-8cb9-530c-9eef-9a452e30b928 |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - E3001B - SH05 SIP Site 2 - Pavement Construction | itp |  |  |  | Yes | ITP - E3001B - SH05 SIP Site 2 - Pavement Construction | 7039ce80-9c90-4e12-b242-61337fbc3f7a
checkpoint-group |  |  | section | Survey Setout
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 6ae201c9-1d66-52f0-8380-ea730b29c656 |  | textbox | CPS Eng.
text | 47ac752c-9e55-5bc3-9376-2b5870f18b38 |  | textbox | Site Engineer
text | 9b3f78c7-290a-50d7-acdf-d1ecd7933f66 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 87f0cd87-3e2c-5845-9a8e-e3031f5aa52c |  | note | ACTION (Hold, Monitor, Witness) - M
label | 9a3b6972-bf41-56ca-986f-619aa0fe6332 |  | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
label | 7c3b3a16-c7e2-5c38-b1ba-8b4ee3234e49 |  | note | Frequency - Prior to commencement
label | 331b95d1-90fe-59e6-b9a9-f02a39d1b558 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 90edc683-0d9d-5d63-ab04-4bf84e3d9aa7 |  | note | Records - Survey receipt
checkpoint-group |  |  | section | Sub Grade
checkpoint-status |  |  | checkpoint | 2 - Sub Grade Strength
label | 24ceeb11-4bf7-5036-b147-e528347d93f1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 12348a14-8e3c-5acb-9229-ccc994c55b38 |  | note | Detail - Determine Bearing strength of Sub Grade
label | f93e51b8-0e6b-59a5-990e-75379795e8ee |  | note | Frequency - After Dig out Every 5m
label | de506733-17e4-53ac-b7e8-519037432548 |  | note | Conformance Criteria - Testing
label | da9d56a4-a1f7-51e1-81d6-1072dbd9142d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Min. 4 blows /100mm
label | 27c067d5-80df-5537-867b-19cf605280e9 |  | note | Records - QA measurement Sheet, CS-4000 1m Scala
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Proof Roll of subgrade
label | ee46b25c-570c-5438-94f3-28c2d1c52853 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5f32d64e-f09a-5ba0-9e72-f5e60cf6fd0b |  | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
label | 5a2928b0-d3bf-52f5-951f-6a6d1a7df40e |  | note | Frequency - Prior to Sub Base Construction
label | de5f0b61-9c7f-5dc9-911c-8820c61a9df1 |  | note | Conformance Criteria - Visual Inspection
label | de5700ae-423b-5cc4-94e4-c549e644586f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Engineers Acceptance
label | 4da94ced-0087-5e33-acb9-327737f9e3ed |  | note | Records - Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Sub base
checkpoint-status |  |  | checkpoint | 4 - Material Compliance
label | 1ab6e2d9-bc3f-532f-bc07-43b60b2418a7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1df9b4cd-120f-5087-91c7-77da29f3944c |  | note | Detail - Aggregate material compliance for Subbase stockpiles
label | 3155d271-f99f-5dc6-bf21-228ea3fbfb2a |  | note | Frequency - Prior to commencement
label | 93e83d88-2158-5148-8540-b2478892c2a9 |  | note | Conformance Criteria - Lab Testing
label | 5e7b1001-2103-5b1a-810c-499ef1714917 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC
label | d5765071-1356-5b6b-ae9a-b13e05af4bb5 |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Material Compliance
label | e8b60e6d-d5e8-5e77-804a-4769062e9622 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1b73c271-5b4d-5e08-97ce-dc798efe7500 |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | 760dc99d-00ea-5e5e-83ae-eeea77dfa057 |  | note | Frequency - During construction
label | 07e52da3-20b3-585f-bc16-221a28850e8a |  | note | Conformance Criteria - Measurement and recording
label | c215a95e-0150-5e08-a27d-b48c4742327b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Comply with TNZ M/3 Specification. NZTA B/2 Specification
label | 8aebe967-cd42-5394-adfb-7395a58716ab |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 6 - Saw cutting
label | dc3b1ab1-75df-5e7b-9c1e-fc08e220e834 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ccde8524-63d9-5980-9277-300cd359ec86 |  | note | Detail - proposed Sawcut line to be inspected by the engineer
label | 902b456e-fa77-537a-a423-4b3f5accd5a7 |  | note | Frequency - During construction
label | fbf425a4-f4c6-5c86-8549-c6a69d54267c |  | note | Conformance Criteria - Visual Inspection
label | 360c3b25-a41a-5079-8a07-12a0ff8e88f8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - project spec 6.6
label | 01e959d3-d21f-586f-9a20-0e83bb397f41 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Sub Base Construction
label | 85043001-0600-55dc-a939-9094d7e5a624 |  | note | ACTION (Hold, Monitor, Witness) - M
label | aafe8f14-3d32-5e3c-8454-9d4f4d08cd54 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 3388b6f0-c46c-59ca-9ae7-52a266526db0 |  | note | Frequency - During construction
label | 0ec0a2f1-5527-50f8-9770-0bedd43d100f |  | note | Conformance Criteria - Visual Inspection
label | 0aafab0f-d764-5fbb-ac11-cbe13a23bc09 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 8 - Sub Base Construction
label | 2e595bd2-bd61-5616-a111-8e87e8914ff7 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1662689f-0096-57b6-8993-13d90e13a6f5 |  | note | Detail - Carry out a Level Check on the trimmed Sub base
label | d81a6657-7a57-52eb-8888-36671e0cb544 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | 0c691550-060b-53f3-b46a-e4dedf47df01 |  | note | Conformance Criteria - Measurement
label | e39fa841-925a-50c6-8775-d61bddb88ce1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Tolerance = -5mm/+15mm
label | cec3812f-8302-56f8-b0f5-a34efc4feba1 |  | note | Records - QA measurement Sheet, CS-4100a Subbase Approval
checkpoint-status |  |  | checkpoint | 9 - Sub Base Construction
label | ffd904af-fc4e-5c73-ba76-165908ccbf14 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 8538a8d9-1f14-50de-9aa5-5dca3206c665 |  | note | Detail - Degree of Compaction
label | e24bd6d1-57e5-58fd-8fcc-638680f6e969 |  | note | Frequency - 5 per Lot
label | 02f25af1-8ad4-5be3-a0ef-c0f4599061e8 |  | note | Conformance Criteria - NDM Lab Testing
label | 4bc839b2-7037-5341-8cb2-174c4a4503ff |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Avg. >= 95% MDD and Min. >= 92% MDD
label | 9319f825-46de-53e7-ad47-b5a057bb90cd |  | note | Records - Pavement Lab Testing Spreadsheet
checkpoint-status |  |  | checkpoint | 10 - Sub Base Construction
label | 977d4364-9c1e-505b-9759-b1bb289763ba |  | note | ACTION (Hold, Monitor, Witness) - H
label | bab8518f-cf6a-5d3a-825b-03abc15c0a68 |  | note | Detail - Surface shape check
label | 5c5e330a-e81b-500b-b571-b4d4bfb189cc |  | note | Frequency - Prior to base course Construction
label | 7806fe89-1c89-5dac-86ff-58d5e3227dff |  | note | Conformance Criteria - Measurement
label | f492ee12-8aeb-5655-adc3-c3b46371e574 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | 4b61bf37-996d-5308-b0b5-4ec47be28f59 |  | note | Records - QA measurement Sheet, CS-4100a Subbase Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Base Course Construction
checkpoint-status |  |  | checkpoint | 11 - Material Compliance
label | f38e6867-129a-5ec8-8d6b-daff5bc88f58 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 27990f74-cbdd-551e-9a44-c46fb1ad28ca |  | note | Detail - Aggregate material compliance for base Course stockpiles
label | 8970fcec-4686-5a9b-9733-75f3219b3862 |  | note | Frequency - Prior to commencement
label | 65472436-d274-56e3-a22c-495bb45bdfc3 |  | note | Conformance Criteria - Lab Testing
label | df63ddd2-ffd6-57ba-b2ef-8bcfc7d09e9e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Aggregate shall comply with TNZ M/4
label | 6904d9cd-0a40-582f-8e51-7500af27a47e |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Material Compliance
label | 005bb68a-c030-5f09-90e6-b6dab9572ef2 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 7172b102-5b4c-5bde-b45a-ff21a244c659 |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | 4ff19556-6c3c-5057-a580-8e54e8fe9838 |  | note | Frequency - During construction
label | 0b48133e-2f3d-58ba-ab38-b79bb312555d |  | note | Conformance Criteria - Measurement and recording
label | 7a206615-fe1d-5f84-8d19-02ff3a535f4a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
label | 4dfc8f90-9bca-5932-8b01-7ed21af85013 |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 13 - Base Course Construction
label | 0800a305-6caa-559d-b3e5-49e36d193fbc |  | note | ACTION (Hold, Monitor, Witness) - W
label | c21f83a0-3405-5f51-9159-278cb8aced65 |  | note | Detail - Mat sampling of Basecourse Material
label | 521b9f63-15d6-5767-83cd-d81cb4c230bf |  | note | Frequency - 1 mat sample for the job. Pavement CPS Engineer for further instruction
label | 313531ed-87ab-5a4b-88af-78ebb40f6b44 |  | note | Conformance Criteria - Lab testing
label | 2d74a5e4-9225-59ae-8011-568e633510a8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Grading to comply with specification
label | f8698cc3-774b-51de-aa08-6e6117ff128c |  | note | Records - Mat sample lab test result
checkpoint-status |  |  | checkpoint | 14 - Base Course Construction
label | c2dfe403-6bd6-5a61-933b-f1cdc2bd8771 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 969bceb1-4882-512a-aab4-11f95f2a576f |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 0a0df35d-74ec-56f1-9832-7bf7b372a96b |  | note | Frequency - During construction
label | b5573015-6324-5701-8a71-e9e80e3ecfd0 |  | note | Conformance Criteria - Visual Inspection
label | 5575a6d1-958a-5e7e-aeca-af3b669df7b1 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 15 - Base Course Construction
label | e748c4b5-7246-5e59-bfda-537a218678fa |  | note | ACTION (Hold, Monitor, Witness) - M
label | be158a83-ce59-5617-ab41-e47311b84e02 |  | note | Detail - Carry out a Level Check on the trimmed Basecourse
label | 01234e45-a9a8-5f7b-88ee-e10d95405be4 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | 1987d9f5-0027-5652-a46f-d59c421a2027 |  | note | Conformance Criteria - Measurement
label | 76a92f01-1265-5366-91c7-00a1a8ba8e3e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Tolerance = -5mm/+15mm if constrained (kerb)
label | 03075162-4647-5889-9d50-fede9ca6781f |  | note | ○ Tolerance = -5mm/+5mm
label | 1c21a97b-a004-5469-84ce-633e1ad4821b |  | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
checkpoint-status |  |  | checkpoint | 16 - Base Course Construction
label | cec63c20-4549-5d4f-8bbc-1b63c4dda40b |  | note | ACTION (Hold, Monitor, Witness) - M
label | 040b5cdd-58bf-5dbd-959d-313cbea001fe |  | note | Detail - Degree of Compaction
label | 7b5759f2-7af8-5067-a1b0-e0c03322ef17 |  | note | Frequency - 5 per Lot
label | e7884e8a-9f00-5674-a572-d7cd3dbb85f8 |  | note | Conformance Criteria - NDM Lab Testing
label | a76c6f17-8964-564e-8c86-6cb6c5616b9b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Avg. >= 98% MDD and Min. >= 95% MDD
label | 982a4a5b-439a-5c9e-9c51-d54ac1845b0b |  | note | Records - Pavement Lab Testing Spreadsheet
checkpoint-status |  |  | checkpoint | 17 - Base Course Construction
label | 1ea92510-317d-5f63-886d-ff0c9c643d14 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f60704b9-0eaa-52b2-aa3a-257a57458d53 |  | note | Detail - Surface shape check
label | a0fe91a2-f6ae-59c4-89e4-90e25e30d59e |  | note | Frequency - Prior to sealing
label | 538d79e2-65ff-565a-b04b-eafa84d07880 |  | note | Conformance Criteria - Measurement
label | 84c8fba6-4d3b-5f76-a463-f2bd99cec00a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | a1183c27-c0aa-5ebc-a348-59fdb1e4be65 |  | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 18 - Base Course Construction
label | 6da2f5bb-54f1-55a5-b356-40af0714de0c |  | note | ACTION (Hold, Monitor, Witness) - H
label | b57dedba-4de5-5f8f-9187-e522ad943702 |  | note | Detail - Surface finish check
label | 22cec296-ffe6-5d1b-bca0-05030a3b11fb |  | note | Frequency - Prior to sealing
label | c9a5a12b-d350-5684-afd9-a3abe3bef8d6 |  | note | Conformance Criteria - Visual inspection by CPS Engineer after site sweeping
label | c25869d4-deab-512e-ab93-ee96550fa02d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | c19dd802-c492-5f18-b092-af259785eeb2 |  | note | Records - Site photos, Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Extension of Culvert
checkpoint-status |  |  | checkpoint | 19 - Foundation Compliance
label | c453b766-4d03-50c1-8ec9-6a643f61a9a6 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e7f73845-0715-5f34-812b-9c73bf74a9cb |  | note | Detail - Test formation level on completion of excavation to check if undercut required
label | 0b181c21-e1f6-53d7-8bee-5c796a6e5f4f |  | note | Frequency - One test per 5 linear metres
label | 65c00509-64a0-55f3-bd01-f33ae0cb4e6e |  | note | Conformance Criteria - Scala Penetrometer
label | 20e4eb8c-866d-5974-8d25-5fc24a68821c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Min 4 Blows/100
label | 6a45421e-c422-55a1-9e05-8617b7bca607 |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 20 - Foundation Compliance
label | e9c3dc9c-3e23-5eb9-8115-70390ab4103c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 09d9d0e3-14ec-5d16-bae0-8a10b2b7a35a |  | note | Detail - Test formation level on completion of excavation to check if undercut required
label | 3c008aaa-15aa-52a4-8e10-088ddd21894f |  | note | Frequency - As stated
label | 1517d179-decd-5e11-97b2-e271111dad47 |  | note | Conformance Criteria - Visual
label | eedb5ddb-d64c-5327-9290-5bc77c19374e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Designer to inspect formation level at outfalls / inlets.
label | 1f8674fd-b5e3-576a-8504-246b97ef8ee3 |  | note | Records - Photos, Visual
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 21 - Materials (Pipes and drainage aggregate)
label | ec11128d-cd5d-53fe-82b6-e3b89da81d68 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3b3a6c12-e43d-54e8-a36f-c1bc9fb69639 |  | note | Detail - Specification Compliance
label | d8704604-0a31-547d-8362-2c5fe78b17b5 |  | note | Frequency - Each delivery to site
label | 2c0e35e2-afc4-59b1-b68c-f61382c510d7 |  | note | Conformance Criteria - Certification
label | 125d29f6-6965-5eca-8218-9575e4fc4377 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Compliance with requirements from Specifications
label | 860b80de-2d70-5e62-b7a0-3a5d054836ba |  | note | Records - Delivery Dockets
checkpoint-group |  |  | section | Sealing
checkpoint-status |  |  | checkpoint | 22 - Seal design
label | 3dcc2ae1-d5ff-5887-b184-46e226460865 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0badc0ac-c767-55da-b9ae-3cd37ff526bd |  | note | Detail - Seal design to be reviewed prior to sealing
label | 636bf2ad-e81b-5cd6-9378-10e6f59dbb87 |  | note | Frequency - Prior to Sealing
label | ac774314-0817-5265-855f-e6c8bcd7eff4 |  | note | Conformance Criteria - Review
label | dac1f1ff-b078-56bc-aa87-208856ccc219 |  | note | Records - Emails/NTE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 23 - Location/Size Confirmation
label | 700e3c0b-2d8d-52d4-8f71-ed664a8e9864 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 92feb180-32ef-534d-b827-cd871865a288 |  | note | Detail - Mark up extent of Chipseal
label | 0da31666-49f6-58d6-b3f1-9b104ed01cf9 |  | note | Frequency - Prior to Sealing
label | 5c8e7de7-14b6-56aa-b2d0-ff290eae92b2 |  | note | Conformance Criteria - Mark out
label | ecc6574d-7880-5bc4-a7ad-247ee11b55cd |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 24 - Surface Cleanliness
label | 25dec5dc-fc39-53bf-8721-c2550e7c48b5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6263d642-6f64-5e46-923c-bf712cf61c8f |  | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
label | 289056ea-2ff4-508b-b4ce-29c72253d563 |  | note | Frequency - Prior to application of binder
label | 5bf7fe40-5966-5c54-aeef-bdf990beb14a |  | note | Conformance Criteria - Visual inspection
label | 7029de6c-7d0c-52fa-88f8-ddd5376e9b99 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 25 - Binder Application
label | 64144a37-8bca-5751-8413-f598d2716e43 |  | note | ACTION (Hold, Monitor, Witness) - W
label | fa2f3664-a20b-5af9-b047-ca668def3389 |  | note | Detail - Ensure the Binder application is according to the seal design
label | e8454c5e-f8ff-5c6c-be90-7b3b7cf28991 |  | note | Frequency - During sealing
label | 41d90711-102d-5bb6-b208-4d953f616a2d |  | note | Conformance Criteria - Measure
label | 6902806c-20ef-5c6b-8216-5d0132563677 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - According to seal design
label | 47b753cf-8684-5c31-97b8-7328a50024b3 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 26 - Chip Application
label | 70dbb959-50eb-5416-aaf4-6298e2124cda |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3b2d0811-30cd-56fc-ac19-bc2770450790 |  | note | Detail - Ensure the Chip application is according to the seal design
label | 07fc4e6b-89ba-5def-bbc6-f033ab1d610a |  | note | Frequency - During sealing
label | 6248b35d-08f2-566a-a403-3e6e1876049a |  | note | Conformance Criteria - Measure
label | c077ff1f-d750-57e4-b299-fa39eea14155 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - According to seal design
label | f172cfad-ff5a-5d41-8e5c-95525052c887 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 27 - Compaction
label | 5ab19bd9-5cae-5bb8-84ee-3cc36c7e4eb3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6bdd99f8-7c3b-5a8d-a67a-3aae8a959cf7 |  | note | Detail - At completion of rolling
label | b1e0e1e8-5e40-5393-b161-6af7df2c7e19 |  | note | Frequency - During sealing
label | fee21524-c683-513a-9ccc-cd2f65260d4f |  | note | Conformance Criteria - Visual
label | 66d4bfd4-54f3-5819-9806-4a4ceff75029 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | fa486582-4a26-5209-8e86-879105da9ffc |  | note | Records - Photos, QA measurement Sheet
checkpoint-status |  |  | checkpoint | 28 - Compaction
label | 6d423816-c634-51f1-91ed-472d6ac69c55 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 868d443f-718d-5b68-9293-f7a922c3ecff |  | note | Detail - Removal of excess chip
label | 0f33d570-007e-55ad-86b3-d291fe5a624a |  | note | Frequency - Within 48 Hours of Sealing
label | c4f9bfbb-cca3-5ecd-880d-994e33faf201 |  | note | Conformance Criteria - Visual
label | e0d324c0-169e-5e98-a0c4-16b9fc8a6596 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | b4a459cf-60c2-50be-83bb-9b1c70f9044d |  | note | Records - Photos, Site logs
checkpoint-status |  |  | checkpoint | 29 - Compaction
label | f5bfb9b5-8a58-52ba-a735-50604325ea94 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a6d7dc60-b72d-5574-9227-ae12ea80c606 |  | note | Detail - Surface finish check
label | 9c6d3ad4-3781-572f-a723-e3e14d5cf8d1 |  | note | Frequency - After sealing
label | b3ebfc1b-95e4-5cf3-bc7f-7a1074ff4e15 |  | note | Conformance Criteria - Visual
label | f71cd3d5-a81a-5d84-8fe7-7ddf90c49de7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Engineers Acceptance
label | 212e1879-0b7e-55b5-8302-f95e4d12db35 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Road Marking
checkpoint-status |  |  | checkpoint | 30 - Road Marking
label | 752281e9-c63d-5d7b-b4c7-8af9826f0f6e |  | note | ACTION (Hold, Monitor, Witness) - H
label | aa86f78e-52ee-581e-b28b-c52ca6b77228 |  | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
label | 1c0b1211-74b7-5c10-bef4-faddb1a05c19 |  | note | Frequency - Prior to the final line marking
label | c34e20a3-a35f-55c9-a783-5c91c58bd079 |  | note | Conformance Criteria - Visual
label | 29cd481a-c3e4-5a61-9e74-7dc9a2919afe |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Engineers Acceptance
label | 112e36cf-1415-5d6a-93b9-8992ce4be647 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Hydroseeding
checkpoint-status |  |  | checkpoint | 31 - Hydroseeding
label | bae93316-f80d-5438-aa05-068c11034ed8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d286a686-7f08-5cbc-b937-f9671be4603a |  | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
label | e5c26cde-ce21-563e-a495-2f96ede4d434 |  | note | Frequency - At the completion of the Lot of work
label | dc1db1c4-3951-55d8-9173-8abba74afeda |  | note | Conformance Criteria - Visual
label | 1b587f00-15d0-5448-adba-9dd64593da91 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Engineers Acceptance
label | b66cf478-8cab-538e-9ac6-9e894ad5ec98 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Final Inspection and Handover
checkpoint-status |  |  | checkpoint | 32 - Quality Assurance deliverables
label | 06aa1799-29d6-5d40-9422-2ddb9361def2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0fd28ea0-2aa1-5ffd-8345-0133ef57db17 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | f0685855-43b8-5d1f-9b64-260e8e5a3190 |  | note | Frequency - At completion of Lot
label | bb541ec9-d059-568c-b8f8-51687c772891 |  | note | Conformance Criteria - Document Review
label | 34269409-2607-5ce1-ab46-5d899b39fb02 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure all QA is uploaded into ConQA / Procore
label | a29efc20-f41e-54d0-8bac-6adb03e4ec88 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 33 - Completion Sign Off From Fields Below
label | 44e830c4-6caa-533d-8fd9-754aed7e4156 |  | note | Records - Signatures
checklist-flat |  |  | checklist | ITP - B1004C White Pine Bush - Subsoil Drainage | itp |  |  |  | Yes | ITP - B1004C White Pine Bush - Subsoil Drainage | 72731249-5c49-48b8-845d-b0c8f1394a97
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 84b01ec0-5ece-51a6-b318-39dcbd1bec4a |  | textbox | CPS Eng.
text | d0afc5ed-7923-5c63-be39-c47108639cb8 |  | textbox | Site Engineer
text | 73647f19-d47f-5921-80b4-e7005452bafe |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 7215b007-1960-5977-bbdb-ce67e9c909ba |  | note | ACTION (Hold, Monitor, Witness) - W
label | c06c5818-555a-57f6-8c77-55fbc5295e34 |  | note | Detail - Set out Edge of Seal to 1m offset. Setout and mark all known services along the line of the Sub-soil Drain.
label | 7781e379-a401-56a8-94e2-6e5d723649df |  | note | Frequency - Prior to commencement
label | 89bccb62-5507-56b5-9194-e030b0c1b1ae |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | b458e502-b6ef-5223-bc37-aff5328034ab |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 014d649c-73a1-52e1-ada2-7335edf66196 |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 2 - Material Compliance
label | 69c4c2bb-1067-5b7d-a875-ad509dcf4584 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 599f95c7-194c-5fa4-9fea-af0ea40b8c9c |  | note | Detail - Ensure Subsoil Drainage pipe is TNZ F2 Grade and 100mm diameter
label | cceefa59-cac0-5318-b26d-34c543244ea2 |  | note | Frequency - Upon delivery to site
label | 343ff28f-950c-59a7-ab66-44c3f6f380db |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | 396f3c03-fc9d-53d0-8cba-9dc0308c7201 |  | note | Conformance Criteria - 100mm diameter Drain flow TNZ F/2 Grade pipe
label | 38f84dd5-29ba-5f4c-a10a-7f4b0cb7b62b |  | note | Records - Delivery docket
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 -
label | 38ffc647-573c-5394-ad13-b3cad077e858 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 31506d5d-5b27-54b1-87ff-543a8f860474 |  | note | Detail - Ensure Material for Bedding, Side support and backfill is 3 to 7 Clean Drainage Chip (Reject Chip)
label | c07cc873-bf62-5f02-b9de-28e6d26e0ab5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 58cda649-181d-595b-89e1-7c1417994a78 |  | note | Conformance Criteria - Ensure clean drainage chip
label | 1520a78f-aacd-58ed-9493-22d8a0c79ae4 |  | note | Records - Delivery docket
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 -
label | 80edbbb6-70bf-5099-bd74-a9b236aed985 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 632bfab8-1c61-5b90-83c9-d805049b545a |  | note | Detail - Ensure the bidim material is A14. A similar material maybe used but it must be approved
label | 54dfd6d7-01d7-56e4-8e28-9fa0bd1f602b |  | note | Frequency - Upon delivery to site
label | c4ab6fc4-eaef-5155-ba30-a7784b6a558b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | b560363c-c56d-5d90-847c-178a7b4e3138 |  | note | Conformance Criteria - Ensure geotextile is approved for use
label | 79cee608-93ff-5717-9be3-aae40a4611c1 |  | note | Records - Delivery docket
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Trenching
label | 95b8734c-2467-5280-b4a9-14e3e3f62412 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ae992298-4fd1-5adb-a2d5-355595f7864d |  | note | Detail - Inspect trench profile and ensure it is 0.300m wide and 1.000m below Edge of Seal level.
label | 34550bed-3a76-5d24-a47a-1b410c1c93eb |  | note | Frequency - 10m intervals
label | eaa27734-a613-52d7-86be-7e8a5df5259e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
label | 62c60d28-cb53-5d36-9a2d-78223567caf1 |  | note | Conformance Criteria - Record levels of base of trench on dip sheet
label | aaf0cd6c-2d05-5059-ae5f-03dd94aec9d7 |  | note | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 -
label | 9fe3f6c4-7fa1-57df-882e-6302c8a16162 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ae03b093-e0dd-57d8-bd5e-9cbcfb6bde8c |  | note | Detail - Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
label | 05cdbee9-f92c-5120-8ecd-c9f25050d81c |  | note | Frequency - 10m intervals
label | f0e5d0ed-bc05-57cc-9835-b74f4d1a27cc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
label | dd0097f3-9bcd-56fd-bca9-157abbcaed96 |  | note | Conformance Criteria - Ensure trench line and levels match the design drawings
label | 57084358-9823-52a0-8b31-1bcde8214126 |  | note | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 -
label | aec8de2d-ca26-5c26-abbd-621816570bac |  | note | ACTION (Hold, Monitor, Witness) - H
label | de409bea-0915-537e-85a5-4fa7594089f0 |  | note | Detail - Design Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
label | 1a28296f-d6ef-587c-bc4e-d8672f61db93 |  | note | Frequency - As required
label | b8284b48-cb12-5688-877c-78bbaae44b1e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 42fea2ce-6e9a-5169-8974-0189e7eef72b |  | note | Conformance Criteria - Design Engineer to instruct action and record on dip sheet and as built drawing
label | 2b8d15b8-ccf8-5b12-b246-8ebbd2cb79ec |  | note | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Bedding, pipe installation and Backfill.
label | a825ac11-005b-5401-935e-505873ba7906 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1018487c-d9d9-54f9-8a99-cb347df15dd8 |  | note | Detail - Upon completion of trenching Bidim 14 or similar approved Geotextile to be placed into the trench and pinned to ensure the geotextile 'wraps' the TNZ F/2 material
label | 679b3b8e-987f-5a3a-ab5e-7f77cf8a6946 |  | note | Frequency - 10m intervals
label | 757fdb49-f1c0-5632-937b-2b894b91c22e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 844a8133-ac15-553f-8233-85f5bfb0bc7f |  | note | Conformance Criteria - Ensure material covers the trench and is pinned in place
label | 8d40e38f-1747-53e5-ab52-0bbba4a3b84e |  | note | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 -
label | d344819b-a948-59a6-9e7c-d7771ddcc1b0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b83fabcd-bacc-5b62-9360-1f1d04194314 |  | note | Detail - Ensure 100mm thick 3 to 7 Clean Drainage chip (Reject Chip) bedding is placed in base of trench.
label | ee9c18d0-4334-5c94-af9c-53669a322e1d |  | note | Frequency - 10m intervals
label | b76fd321-2e24-5daf-9766-1254a51d2d4a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 52671053-0fdf-5c32-b034-fb451abcb35e |  | note | Conformance Criteria - Record levels of top of bedding on dip sheet
label | 43795986-b37e-54ae-a4b8-b7634b825ef0 |  | note | Records - Photo / CS-4001 Subsoil Dipsheet Check Sheet
checkpoint-status |  |  | checkpoint | 10 -
label | 8df46b15-f9b1-5a2d-89f6-5837c2a62272 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5d9d00c8-9b40-5e74-a881-cf02c0457309 |  | note | Detail - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
label | 629b0637-46a9-5775-94ff-357a48c160bf |  | note | Frequency - 10m intervals
label | 2121decc-a387-599b-909f-cad0bef085c0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 1cade1f6-04d0-552f-8891-503e96e97ceb |  | note | Conformance Criteria - Consistency with Subsoil Details
label | b4ae6267-6ec5-566b-bf42-a3a013162972 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 11 -
label | 5c24dfa6-7b30-549c-8a04-2bf9717c36a5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | dee24b3f-94d2-5af4-ba4b-0c1b30b68a00 |  | note | Detail - As built Survey the Pipe before backfill
label | 90c98a2a-21b3-51ff-b727-5f4c476486b7 |  | note | Frequency - 10m intervals
label | 8c58fda0-ec21-5050-947b-ef97c0d24ff8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | ffb216a9-428e-5963-8a4c-c86d3a653704 |  | note | Conformance Criteria - Consistency with Subsoil Details
label | 90bc9bfc-fe52-50ec-bdee-7a0a15a09ead |  | note | Records - As-built receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 -
label | ce31224a-0876-5f6a-a51f-f3a0ab5fa4e6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9020b4ed-29cf-56dc-8649-958f12c8834e |  | note | Detail - Backfill by tipping 3 to 7 Clean Drainage chip (Reject chip) into the trench
label | 42bc53d6-09e6-516d-b01e-3fcb527e3e12 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 5fddcd8d-ed97-56a5-8d6f-9716db10e459 |  | note | Conformance Criteria - Ensure good coverage
label | 20880f36-21db-5a2e-8983-eb3c5cb6dda1 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 13 -
label | 6f1adb94-feab-5a97-a160-a51cc7ea6c47 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d5d2ef24-631e-522f-9055-713f2c52fcbc |  | note | Detail - Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place
label | 712b3111-5670-52e5-b80b-40fe287fad40 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
checkpoint-status |  |  | checkpoint | 14 - As-builts
label | 5b8f5813-24e1-5ea2-a436-18dc0d6e3cf0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 43097f8a-6f28-5805-8f7d-9fe4aab81e98 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 97ed391f-a8fa-508e-8ecb-a98252b3bd1c |  | note | Frequency - At the completion of the Lot of work
label | 34aef70f-0f3b-5d47-9d3d-3c918ec23732 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | c8fc1e81-5ed3-597c-a1e3-bc671e4cccd7 |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - Turitaka Slip Repair - F2601A - Works | itp |  |  |  | Yes | ITP - Turitaka Slip Repair - F2601A - Works | 72a85c26-6540-489f-9a57-5060ee8ac317
checkpoint-group |  |  | section | Section 1: RECEIVING INSPECTIONS
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 0f8957f3-1c53-54a2-af99-301424b6b604 |  | textbox | CPS Eng.
text | 3230aea2-e686-5ea7-a3bc-e4eadd1769f7 |  | textbox | Site Engineer
text | 8fade03e-fb5d-57f6-b176-74cc238804fe |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - 4t Ecogreen/Kyowa bags
label | 5b338e84-8c80-571f-b1e2-7f743d767013 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d21dcba5-e15d-51ab-99f6-9090b8893379 |  | note | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3435.SM(6) SH11
label | 4dd1cf44-e8ee-53a7-adfc-ee6be373deea |  | note | Frequency - Prior to commencement
label | 34dcaeec-b789-582b-9481-75cc0b7d9bb8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 23d80a28-ae35-531a-9846-2dbdba632d33 |  | note | Conformance Criteria - Purchased from Bluemont or similar approved
label | b1291bd3-111c-514e-9b9c-da437697bb50 |  | note | ○ Traceability of all materials delivered to site
label | ccac1cfc-65ca-5a2c-86cd-f89e854a2962 |  | note | Records - Material cert, delivery dockets
checkpoint-status |  |  | checkpoint | 1.2 - Screen river run
label | 7ec5ee1b-8661-5436-b229-d998cd5afd6f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 82e32fab-18f7-5a8a-8f7f-f37c0f67affd |  | note | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3435.SM(6) SH11/SH12
label | aecfd00d-4e7c-5d08-943c-e28abd0de468 |  | note | Frequency - Prior to commencement
label | 63747b1b-d931-5f9c-bad2-d466845ff815 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 5bba963d-22a2-56c8-8102-b17dac2bc7ec |  | note | Conformance Criteria - River run to fill bags 50mm to 175mm screened rock < 2%fines
label | 3d468c93-a7c2-5e24-ad13-72fc1f967e2b |  | note | ○ Provide written evidence of supply source to CPS Engineer prior to delivery
label | d1c59dc4-bc12-5608-a27c-ac0a70d81221 |  | note | Records - Material source test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Class D A39 Geotextile
label | 0c6f2d99-7d9b-5ca5-86e2-f26aae589891 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b6a77b61-7f53-573e-acc9-e7dd716f8af6 |  | note | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3435.SM(6) SH11 TNZ F/7
label | 6b4b10f2-1a6c-5339-9b36-8405fcdce545 |  | note | Frequency - Prior to commencement
label | e45d16d9-295a-5f6b-a4a3-08517046b95f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 3885dd45-2a58-5d07-a5b1-5a5afd7acdb7 |  | note | Conformance Criteria - TNZ F/7 filtration class 1 strength Class D Traceability of all materials delivered to site
label | 222e7c0b-3595-5cf8-805d-daa60a2eb642 |  | note | Records -
checkpoint-status |  |  | checkpoint | 1.4 - Granular fill AP65
label | 0e8f6a61-0033-57dd-b9e7-16cbb8aa4eca |  | note | ACTION (Hold, Monitor, Witness) - W
label | 816775d8-6568-5c68-b13e-806077560844 |  | note | Specification/Drawings Reference - Consistency with Construction Specifications 2-U3435.SM(6) SH11
label | 5204626c-14d4-5d4c-8af8-efff62c5bb59 |  | note | Frequency - Prior to commencement
label | ce0b1fe7-6402-5b62-a8e6-9c5253fe70fb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Suppliers grading certificate
label | 0b759737-e89d-557c-851c-46ce546270bd |  | note | Conformance Criteria - Hard durable well graded free draining material 65mm not more than 5% passing 75 micron screen free from organic fines and vegetive matter.
label | a4657c84-ea14-5c3f-888a-fe04b7c3569c |  | note | ○ Traceability of all materials delivered to site
label | f685051c-7993-5ef7-bada-5756fd013a5d |  | note | Records - Material cert, delivery dockets
checkpoint-group |  |  | section | Section 2: IN PROGRESS INSPECTIONS
checkpoint-status |  |  | checkpoint | 2.1 - Survey Setout
label | ef6e21ac-7167-535b-9b3b-e60d73ebeff0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 85ba12a7-f760-5c96-9c3d-cbfcfbcba1c2 |  | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6)
label | 812470f6-c058-5253-ab74-29495f44d73c |  | note | Frequency - Prior to commencement
label | 83ccad1a-55e6-510f-9afc-1b59fe8bcd68 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | c95fcb1f-a22c-5017-bf58-a57eb2a253e9 |  | note | Conformance Criteria - Set out extents of works and check against design drawings. Check and agree on set-out and number of Ecogreen Rock bags required with CPS Engineer
label | ae5e378b-4215-5566-bf60-b9cbca143311 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Excavation
label | 6c9ff44a-4a67-54ae-9af5-4443db84ca35 |  | note | ACTION (Hold, Monitor, Witness) - H
label | cb53598d-c562-53c9-a389-8039fb95c448 |  | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6), TNZ F/1
label | 95c93a96-b61a-548d-92f5-2cac1bca6593 |  | note | Frequency - During Construction
label | 3fc05a6c-09d4-56c2-966d-84c7e7fef86a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | e4d82910-7562-54c5-8cba-d51027431018 |  | note | Conformance Criteria - Comply with TNZ F/1.
label | eef994df-c389-5023-be5d-6ea97559fb8a |  | note | ○ Remove and clear deleterious material when excavating to formation level. Excavated material to be disposed of off-site. CPS engineer to inspect and approve the foundation level material
label | 2530913a-bc8d-596b-93e7-2e6d6c94e859 |  | note | Records - Photo's, CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Granular Backfill AP65
label | 3f6fa137-1a9a-5dc2-a8cd-45c2a95ba7f6 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0d661a55-dd1a-5345-9c3f-8b8fa9324fa0 |  | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6), TNZ F/1
label | f592547a-0030-5c0b-85f3-7397fb707875 |  | note | Frequency - At 5m intervals max taken at mid point between the rock bags on each 600mm thick layer prior to placing next layer
label | e8d5cd5d-fa91-5fb4-830a-f2632925d99b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg hammer or NDM testing
label | 975c30dc-00de-564e-8302-17574e409825 |  | note | Conformance Criteria - Comply with TNZ F/1.
label | c860b3e9-526f-5bbc-97ab-5f8fc6d9e19c |  | note | ○ Well graded AP65 compacted to Minimum of 95% MDD. Compaction test results submitted to the CPS Engineer for approval prior to placing the next layer
label | c8f71978-cf13-5538-a062-ed0143a1c6a8 |  | note | Records - Test Reports
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Rock Bag installation
label | 5c3d2ff3-2167-55a9-ab8c-6137de7ec63b |  | note | ACTION (Hold, Monitor, Witness) - H
label | f9bba66a-fe7e-5bc9-8a4e-e5d3e92cceb5 |  | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6)
label | 0e4e4f85-cc9d-5676-90a3-670430da6126 |  | note | Frequency - During Construction
label | 0e6cddc5-a864-5dc9-b5d9-75facd090da7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 31a7f9aa-cc9e-5b66-87c3-60edaf2b840e |  | note | Conformance Criteria - Rock bags to be filled and placed in accordance with the manufacturers specification and are to be stacked so that the average angle is no steeper than 2H to 1V.
label | c1690b69-36b0-5f0d-abd8-52ab6f40a9fc |  | note | ○ The final layer will be determined by the CPS Engineer on site
label | 8bd26fff-b2d3-5a71-b18b-4a280b61e6dc |  | note | Records - Photo's, CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Class D (A39) Geotextile
label | 8307755f-f69b-5c89-8566-93e495a2040f |  | note | ACTION (Hold, Monitor, Witness) - W
label | ec56c58c-1b72-5ccc-95c4-19c26bd7483e |  | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6)
label | 0af13aad-756a-5c7e-9189-4ff85a4a0d71 |  | note | Frequency - During Construction
label | 99b894f4-bf5e-5bcd-b068-8f2ac9a43551 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | a5d9bd61-5eb0-5d4a-aedb-6055272e59f4 |  | note | Conformance Criteria - Installation between the AP65 fill and rock filled bags.
label | 61c82b22-8750-50af-8d5f-83616c271b31 |  | note | ○ The fabric shall be laid and overlapped as per manufacturers recommendations
label | 321db55d-125c-506d-9b96-c761ef0be0ec |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.6 - Bulk Fill Placement access roads
label | b3b90f0a-fff2-5687-ae62-f919ed38ed3e |  | note | ACTION (Hold, Monitor, Witness) - M
label | c28fa545-e231-5541-8136-4ff275d606e4 |  | note | Specification/Drawings Reference - Consistency with Construction Drawing 2-U3435.SM(6) SH13, NZS4431:2022, TNZ F/1
label | 0fc9ed06-9e5f-50af-8c53-dc3c00dcee95 |  | note | Frequency - During Construction
label | 64808a28-3f49-500e-abbe-f82014b24e7c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 2e342713-77d6-50cb-95e0-ffc5166a37c8 |  | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade
label | 3dc6f98b-4397-500b-a861-43372398621b |  | note | Records - Bulk Fill Earthworks checksheet (CS-4020), Photo's
checkpoint-status |  |  | checkpoint | 2.7 - As-built Survey
label | cc7118d5-7dc1-53f8-b797-39c125dc7327 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 502050e2-4b45-582c-bb0c-cf53b4348738 |  | note | Frequency - At completion of Lot
label | 02d64319-66da-5520-b291-05b90a9af28e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | e68140ce-71e8-550e-b2d3-c5f18c839e5b |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | cf521bdc-8329-5924-9a56-aa9b26abef49 |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 3: Final Inspection and Handover
checkpoint-status |  |  | checkpoint | 3.1 - Completion
label | 1754d20e-357b-5afc-a2c4-9c9e79373b94 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ce2c452e-9b3d-5029-9dcf-c7d0e68ceca3 |  | note | Specification/Drawings Reference - Consistency with Construction Drawings & specifications 2-U3435.SM(6)
label | cd649d3c-0071-50f1-b96b-2ea2c842c7b1 |  | note | Frequency - At completion of Lot
label | 232f250b-7509-5bda-893a-153408766341 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 3ccd95c4-ef15-58f2-b4ab-133d3cf9e021 |  | note | Conformance Criteria - Upon completion of the works the CPS engineer will be given the opportunity to inspect the works having been done to the required standard and sign it off for completion
label | f4ef162a-b3f3-529b-ba29-39a6cfdcd136 |  | note | Records - CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Quality Assurance deliverables
label | b25b0be9-1821-52d0-980a-d4ba40653593 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b81aea6c-f9a0-5afb-8414-0c7c01d48808 |  | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 0a2b5ce4-065a-55c7-9d87-c0d0f0d1bb63 |  | note | Frequency - At completion of Lot
label | ab2cb3b2-a2d8-51c7-9ca1-7fe71f1bfd60 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 51affa96-3c4b-5647-9f2b-d6ea2e0aed45 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 5892188c-e05f-5e77-8613-84499d3accdf |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 3.3 - Completion Sign Off From Fields Below
label | 6bb45ee2-fc5c-5915-89cb-c8433af2f215 |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | CS-4103 - Water Loss Test |  |  |  |  | Yes | CS-4103 - Water Loss Test | 736c6131-d115-4739-8ce7-944ed76ad586
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | Details
text | 7ded400c-0f07-5cd4-9ac5-25143efa775d |  | textbox | Contract:
text | dd38607d-47f7-58de-86c0-cf803aecc39a |  | textbox | Sub Work Area(s):
text | dbb0a27d-3202-5ebe-860f-109facefc69f |  | textbox | Sublot(s):
text | 2dd69502-b618-5447-9fe8-1be430d80d02 |  | textbox | Work Area(s):
text | 632afdf4-5730-50ac-9352-991284367419 |  | textbox | Lot(s):
date | 751fba3d-6d92-5564-b40d-44aa7d69657d |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Personnel Conducting Test
text | c3b4cec1-565e-5e3f-aeb2-d049b598b03e |  | textbox | Drain Layer:
text | 10bbe19a-3bf0-5533-a4b1-73d381ab8f62 |  | textbox | Site Engineer:
text | 145ffab8-0770-5e7c-a0f3-0b30d40a601c |  | textbox | CPS Engineer:
text | f4910ea0-36b3-5b55-a0a4-b2d3ef3ec28b |  | textbox | Qualification:
checkpoint-group |  |  | section | Pipe Material and Rating
checkpoint-status |  |  | checkpoint | Pipe Material and Rating
text | 7157666f-eeb3-5a70-aa20-0759f5ebe46a |  | textbox | Pipe Internal Diameter (mm) D:
text | 43cdbdc9-c02b-5340-baab-9995c47e5193 |  | textbox | Depth of Pipe Below Water Table:
text | f041d388-724b-5171-a1e7-3a6bab55b6c7 |  | textbox | Ambient Air Temperature: |  |  | °C
text | 266afad6-6778-5072-b08e-e7726af543b2 |  | textbox | Water Temperature: |  |  | °C
checkpoint-group |  |  | section | Water Loss Method
checkpoint-status |  |  | checkpoint | Water Loss Method
label | 39d59fbb-2e36-5e0d-a090-f0b301464968 |  | note | Procedure
label | f15ca8c6-8a25-537f-83cb-0c38790e7505 |  | note | 1. Remove air from pipeline
label | f95b3547-7a52-575b-b612-cc7e4187df8e |  | note | 2. Apply test pressure to pipeline
label | b762be41-675f-5daf-a5da-0939a74bcbc6 |  | note | 3. Allow pressure to settle for 12 hours
label | 6db1223b-dd83-506c-ba30-345a076eaa8f |  | note | 4. Re-apply and maintain test pressure for 5 hours by successively pumping a sufficient amount of water
label | 03ce4e8b-9288-57f0-aa98-995c9a80a3c8 |  | note | 5. Measure water volume required to maintain pressure between Hour 2 and Hour 3 - V1
label | 27c02a64-fc38-5a7f-b712-7ae697800fe7 |  | note | 6. Measure water volume required to maintain pressure between Hour 4 and Hour 5 - V2
label | 2ff3a202-39a1-5a59-9979-f5111d85fbc2 |  | note | 7. Calculate:
label | b40a1f8d-abf6-5303-a0ba-68ec5778a46d |  | note | Where:
label | 976c4b44-b66f-5e37-8aee-f87db98614af |  | note | Q = allowable make up water, (L/hr)
label | e92a123e-42fe-5466-b0fe-16298e6cf1df |  | note | D1 = nominal diameter of pipe size #1, (m)
label | 73ccf97a-adbc-5838-bfc1-c3c38440d3a4 |  | note | L1 = length of pipe size #1, (km)
label | 48e1eebc-391a-5d6e-9c32-c1b62d33e260 |  | note | D2 = nominal diameter of pipe size #2, (m)
label | 07d2c611-431a-5ec8-8c7e-c8688e947141 |  | note | L2 = length of pipe size #2, (km)
label | b7a9b1af-6472-5c35-88d2-5eb6208c5058 |  | note | D3 = nominal diameter of pipe size #3, (m)
label | 5e332500-9ed4-58ca-88fd-b9358fc2d8c0 |  | note | L3 = length of pipe size #3, (km)
label | ea9b6b58-69eb-5b25-99a2-db001c4bdada |  | note | H = average test head of pipeline, (m)
text | 7de69164-9114-5c89-b388-9b6e848cebf3 |  | textbox | Standard Test Pressure: |  |  | kPa
label | 2b2ebb3b-1b12-5999-9be9-fac16f3f0a68 |  | note | – – – – – – – – – – – – – – –
label | 024ae154-3b60-52b7-91b2-5f16f8de421a |  | note | Water Meter Readings
label | 4f15d403-5ae4-5be0-bb16-aef4b5646b6a |  | note | – – – – – – – – – – – – – – –
label | 87a16661-5b8b-56cd-8d04-1e488020cc84 |  | note | Test Time ¦¦ Time of Day ¦¦ Reading (m3)
text | 75d43d88-f140-583c-86c4-688fa9bad5fc |  | textbox | Start ¦¦ 0:00:00 ¦¦
text | 17bf21dd-4137-5b08-af4d-d73d2009b8ae |  | textbox | 2 hr ¦¦ 2:00:00 ¦¦
text | ad992657-e67f-5736-9aea-cee553cfc5cd |  | textbox | 3 hr ¦¦ 3:00:00 ¦¦
text | eb0a97a2-fc2e-518d-b892-f9eb4049508f |  | textbox | 4 hr ¦¦ 4:00:00 ¦¦
text | 976ea41b-a6d1-594b-8c1b-0177054654d4 |  | textbox | 5 hr ¦¦ 5:00:00 ¦¦
label | 62e273a7-5dee-5c2f-8d62-89951d77ce2c |  | note | – – – – – – – – – – – – – – –
label | 92747ef6-5592-5662-9f42-90db22f68d20 |  | note | Water Loss Method Parameters
label | ad82add9-f767-5994-9d6c-2493c56c9a47 |  | note | – – – – – – – – – – – – – – –
text | 3767320a-a131-5bee-9904-7ded46acd89e |  | textbox | L1 (m)
text | 3303f68d-73de-5817-8f86-778ab2fef154 |  | textbox | D1 (mm)
text | 4fc42b42-5910-51ab-80cc-4fbb47e5227e |  | textbox | H (m)
text | ede9534e-5688-506b-a15b-575da7bf3ebb |  | textbox | Q (L/hr)
text | 175cf572-5f14-52e4-96af-addffed8fea1 |  | textbox | V1 (L)
text | 2db92d56-9002-5bbe-a6b8-5be9b8720f0a |  | textbox | V2 (L)
text | 0b18626c-84fa-54d4-a639-b4996b3e26c6 |  | textbox | 0.55 V1 + Q
text | 7820167e-bb72-53bc-ad15-bd402b1417a3 |  | textbox | V2 ≤ 0.55 V1 + Q
checkpoint-status |  |  | checkpoint | Acceptance
label | 369a5207-b839-5449-bc1b-8aa4b7410b10 |  | note | The test length shall be acceptable where:
label | c369cb0b-8b5e-591c-856f-6b2d8ace1bf3 |  | note | 1. No failure of any thrust block, pipe, fitting, joint or any pipeline component
label | a57e6b7c-ae30-5f8a-8494-bc2af7fad64b |  | note | 2. No visible leakage present
label | 356d86e7-ece9-5c66-816c-e4a1fd3674e2 |  | note | 3. 𝑉_2≤0.55𝑉_1+𝑄
checkpoint-no-status |  |  | checkpoint | Comments:
label | b9d94505-8657-5563-a4d8-a38088ebb993 |  | note | Attach Test Section Sketch (show heights, air valves, gauges and filling points)
checkpoint-no-status |  |  | checkpoint | General Methodology Details
text | 7acc7244-7042-5635-b26c-010871c4f4b5 |  | textbox | Process for removal of air
text | 727bdfa0-6f20-5488-90e0-bc6fb6b0bd9b |  | textbox | Details of water meter
text | 03c39c42-61b5-5475-89ad-8d36d6504f6b |  | textbox | Details of pressure gauge
text | 385d4938-6f9d-5647-b262-a8263c0b86d7 |  | textbox | Details of pump
text | 7b79ce00-2e33-5eb6-bfd5-017bbd69684b |  | textbox | Water source
text | fcb492c3-547d-555a-b9cb-b80a1b1cfc56 |  | textbox | Water Disposal
checkpoint-group |  |  | section | Signoff
checkpoint-status |  |  | checkpoint | Checked and Signed by Site Engineer
date | 35749497-3e1c-5598-ab1b-612da7dd6e67 |  | date | Date:
holdpoint |  |  | signoff | SIGNATURE
checkpoint-no-status |  |  | checkpoint | Site Photo Records
checklist-flat |  |  | checklist | ITP - C1503B - Mautaua Under Slip - Geogrids and Geotextiles Placement | itp |  |  |  | Yes | ITP - C1503B - Mautaua Under Slip - Geogrids and Geotextiles Placement | 745f8f0f-997e-4616-9b85-c20e3d9cef3b
checkpoint-status |  |  | checkpoint | Project Site reps.
text | ca4aeeb9-c451-5241-9bb7-14d6ab37912e |  | textbox | CPS Eng.
text | b646ee30-a66f-5564-b993-89a418e95dbc |  | textbox | Site Engineer
text | f11267eb-da48-5bca-aa59-504622ca9d3b |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Prerequisites
label | 48ebec50-d948-537d-ab0d-b63359df5d33 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c7dfb2c6-e570-5709-bac3-73dbed5e2c62 |  | note | Detail - Testing of underlined layer is compliant
label | 920de338-19d4-5318-a228-0b4ff2837b7b |  | note | Frequency - Prior to commencement
label | b03f455d-ed26-50e3-babc-eeb78cf0ad4e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Field Test reports review
label | e18b5d3a-1b48-505e-bae4-90c975adcf0d |  | note | Conformance Criteria - All minimum requirements for each fill unit is detailed in the Earthworks Specification
label | bf8a8412-0365-5896-a773-5d858387445c |  | note | Records - This ITP signed
checkpoint-status |  |  | checkpoint | 2 -
label | d5db54bc-33c3-5182-aca1-bb1d6fa8cb78 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c5e05982-338a-5d3f-b805-8bafb1ff80d6 |  | note | Detail - Proof roll of foundation surface passed
label | f2e8bed9-2cb3-59c9-9b3a-9af1ca617a80 |  | note | Frequency - Prior to commencement
label | 2500bfb0-a452-5629-985c-d090582790e2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3bd22ac5-7fad-5e2d-945b-82f582bfeb0f |  | note | Conformance Criteria - Proof roll completed with a fully loaded load truck with 8 tonnes per axle or equivalent.
label | f2a3470d-b197-5e2a-bdb2-4aa4ad20bcb3 |  | note | Records - COR
checkpoint-status |  |  | checkpoint | 3 - Survey Setout
label | 9c6af25d-0fe2-55c5-92a0-4f43fb4f1e20 |  | note | ACTION (Hold, Monitor, Witness) - H
label | fb680438-3449-58ce-b792-852becaf692d |  | note | Detail - Geogrid or geofabric set out - Set out as per Earthworks and Ground Improvement Layout Plans
label | 4455edbf-c033-5cd8-8ba9-dbf6ed729827 |  | note | Frequency - Prior to commencement
label | ba0adf24-26d7-5766-9b4c-ad6cb5d64df2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - GPS
label | a08ca3e8-9aeb-5703-a200-317e7fb20fc2 |  | note | Conformance Criteria - Site engineer to confirm
label | 1587c618-2778-51eb-8b6d-8c3d36dcf40b |  | note | Records - This ITP signed
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Material Conformance
label | 2194b22a-ca3f-539d-b0f0-2d83b3bffaf4 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 9abb9fe4-6395-59ee-83eb-9ef36e9b25a2 |  | note | Detail - Ensure fill material compliance
label | cdc7aac7-dd4d-59cd-b563-eef0b5ecad9c |  | note | Frequency - Prior to commencement
label | b67a773c-67d0-55b8-954d-0f6fa87512b3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | e742b20c-7eb5-53d2-af04-dada8bb874e4 |  | note | Conformance Criteria - Site engineer to confirm GAP65
label | 903eb7bf-4f5f-5a0d-9835-eff1375406ed |  | note | Records - COR or Photos
checkpoint-status |  |  | checkpoint | 5 -
label | ba41b82e-1763-5515-bd82-2bf0041a4585 |  | note | ACTION (Hold, Monitor, Witness) - M
label | f9a4984c-b326-50ce-a89a-9b44b39941b5 |  | note | Detail - Use of the correct geogrid - Check information on the delivery docket against the requirements indicated on the Drawings.
label | fa331af9-613c-5635-8dc2-52fc6b080657 |  | note | Frequency - Prior to commencement
label | aed36c00-5642-588d-ab6e-65ad021f16bc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 122b30cd-4077-5f19-997e-9f211a8c56db |  | note | Conformance Criteria - Delivery dockets with roll details. Bidim A19 (class B) placed at backand base of cut.
label | 71545b87-f7d6-546f-9126-c464e22e0bde |  | note | Records - Delivery docket
checkpoint-status |  |  | checkpoint | -
label | 5c9d0b9b-2f61-5494-b838-030911e2cc04 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 505bb32b-6759-5458-8bf4-86977ae9097f |  | note | Detail - Use of the correct geogrid - Check information on the delivery docket against the requirements indicated on the Drawings.
label | c50fe64d-0d03-53f6-98fd-e69581bb1698 |  | note | Frequency - Prior to commencement
label | b63e6293-4e6b-5375-a0c8-d05c3ad46e31 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 8b685ad4-89c9-5933-8a19-e7c928fb97cb |  | note | Conformance Criteria - Delivery dockets with roll details. Bidim A49 placed between rock armour and slope face.
label | 5cc75f56-000b-5c05-b702-5df5c01edbb8 |  | note | Records - Delivery docket
checkpoint-status |  |  | checkpoint | 7 - Placement of Geogrid/Geofabric
label | 0690c08f-58bb-55eb-ab36-2226d30ccb55 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9ea1c7c7-0594-5fc5-abde-1e84ddb8a1bf |  | note | Detail - Installation and inspection of geogrids and geofabrics: Grids are cut to the length stated in drawings. Grids are placed in the right direction (high tensile strength perpendicular to face), Grids are overlapped (see manufacturer's spec of the specific grid/fabric), laid flat and undamaged.
label | 187ced89-ce59-52ee-98d8-0b4a0d877c0f |  | note | Frequency - Prior to backfill
label | bd67586a-5aa1-51cf-ac5b-d247f0b7077d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | f58bf21e-9f82-5494-a8bf-87a803f831fb |  | note | Conformance Criteria - Completed and signed Check sheet.
label | 4afeec70-fb73-53ec-bf2b-37e6d3d0a0aa |  | note | Records - No log or checksheet for this, will create and update
checkpoint-status |  |  | checkpoint | 9 - Filling Operation
label | 1854f6b2-cf43-5765-9267-660229d26f06 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 06f8e5d2-e4a5-5836-ade6-9d0dbef5a3c5 |  | note | Detail - Geogrid protection - Minimum 150mm layer placed above geogrid before tracking onto it. Damaged grids need to be replaced
label | ca77a99b-8224-5bee-8637-4781c4fa86c0 |  | note | Frequency - Daily
label | 981fed8f-f98d-52b7-9216-1028b9fd60db |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c5ce028c-2548-514f-810c-34ef0f39867a |  | note | Conformance Criteria - Construction Observation reports and Photos
label | 5d44cd2b-09a6-51b1-aeb7-d7d05077ddcb |  | note | Records - COR or photos
checkpoint-status |  |  | checkpoint | 10 - Lot Number QA File
label | d75dae01-4308-5506-8dfb-0a9ecb98df34 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7ca09bbb-4ed6-5644-9ee2-6dea2cde150d |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 1b399324-8488-5dc4-aa37-c06f3c3a0fe0 |  | note | Frequency - At completion of Lot
label | 6490e87e-8197-5d46-960c-687f82a2f5a8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | ef556b4f-62cc-55f8-9711-4097eec4ac8f |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | fbcc9885-f3e5-5e2a-845d-eeaa6a29abdb |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 11 - As-builts
label | 8fc1329b-4ba9-52c4-87b1-1730aa8cbce7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 599b3750-6a3e-541e-b995-7035a4feb031 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 093b1738-9452-5c00-84aa-153e731e14f8 |  | note | Frequency - At the completion of the Lot of work
label | 3bd2de3b-a4ac-5643-9956-8fa201cfff37 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | bf646638-46be-5576-a6b5-2bfa07b618cd |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - E1401A - Captain's Culvert Inlet Remediation - Subsoil Drainage | itp |  |  |  | Yes | ITP - E1401A - Captain's Culvert Inlet Remediation - Subsoil Drainage | 75e8ab36-4838-4cce-a723-1c1edd15ebc7
checkpoint-status |  |  | checkpoint | Project Site reps.
text | e2237771-6e5c-5960-a3ea-b80b5570a4a0 |  | textbox | CPS Eng.
text | 7e54a6b3-f8ad-5c6e-865c-600bb193bd9c |  | textbox | Site Engineer
text | 55689a6d-df15-5278-ab5e-19db4a45206c |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Setout
label | 4b4cf16d-4273-5473-85d0-52f4d54f8584 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9652d364-67a1-521b-bad7-04857dc17a9e |  | note | Detail - Engineer to confirm the extend of sub soil drain on site
label | 4d1bbb12-1cd6-57f3-9f0d-bfb00a55cf55 |  | note | Frequency - Prior to commencement
label | 1306f084-b451-55ef-a955-b51fbd0a1b1b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Markout
label | b6ccca7d-dda6-5583-b5da-ab77a7f1c461 |  | note | Conformance Criteria - Engineer acceptance
label | 6aa55eed-5116-55d0-9a23-aaa398186939 |  | note | Records - Site Visits, Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Locate existing services by hand digging
label | 34130c19-4624-552b-9e2d-9ce7b8a14e0f |  | note | ACTION (Hold, Monitor, Witness) - W
label | dd77fc3b-88d5-5bae-a755-188ad935d6b0 |  | note | Detail - Ensure all services in conflict with the line of trench are exposed by hand digging
label | 22c69f8a-7bd9-5031-a28c-c7a795f2c7bd |  | note | Frequency - Prior to Installation
label | 72118617-da5d-5df9-ae95-e97df3d97271 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | ee94eebc-e991-5cd8-a719-44fd5935f8c2 |  | note | Conformance Criteria - All conflicts have been located
label | d4c5161a-5bd7-58d6-84ee-c36c3c8f0202 |  | note | Records - Permit To Dig
checkpoint-status |  |  | checkpoint | 3 - Material Compliance
label | 9ec8ac48-5a3b-58b6-9e6a-e45e5added50 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8f8353cd-5fa2-5169-bb44-dd21d0eabb87 |  | note | Detail - Ensure Subsoil Drainage pipe is TNZ F2 Grade and 110 Diameter
label | 2fdae8ca-d188-57fa-bc85-d43cc9bc75a3 |  | note | Frequency - Upon delivery to site
label | 2dd78fc8-5573-5162-bf40-93a4546da1c1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | 29e11b42-ac5f-5343-91b5-db3bc98ce1ce |  | note | Conformance Criteria - 110mm diameter Drain flow TNZ F/2 Grade pipe
label | 839a1023-39b1-58e5-b994-c5e64f79b721 |  | note | Records - Delivery docket
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 -
label | 8cb9190d-9bcc-554e-8694-96c05efdfab5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 59e2c3a4-6d15-5369-9b01-4b08aea57c4e |  | note | Detail - Free draining granular Fill Comply with NZTA F/5 2013
label | b3fdbb0a-e7e3-5b00-8bc3-bbe19d681ddc |  | note | Frequency - Upon delivery to site
label | b0b06983-f822-570a-bc26-c93d074e21bf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | 4e2d2487-995c-56e4-b68d-c7f62ff8d9dd |  | note | Conformance Criteria - Ensure clean drainage chip
label | 121a3349-7f80-5258-aab3-3ac42c45d626 |  | note | Records - Delivery docket
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 -
label | 02a3cf18-499c-5119-99a4-7a86b545b3e0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2b092d3f-0c2e-5d72-a1f2-bd11ff1c5175 |  | note | Detail - Ensure the geotextile filter fabric,strenght Class D in Accordance with TNZ F/7 2003
label | 572a137e-fe50-56da-ba2a-ab75c6355d8a |  | note | Frequency - Upon delivery to site
label | 61a4a971-6176-5fc3-93af-d67496719384 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Ensure delivery docket matches materials delivered
label | 4b7cce6e-c74f-50ee-8d90-fa5e9559c089 |  | note | Conformance Criteria - Strenght Class D in Accordance with TNZ F/7 2003
label | 570cefc8-9e2f-5487-88d3-2f2f60073cb1 |  | note | Records - Delivery docket
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Trenching
label | 30e93838-c58e-5af6-8bbf-c60bf0e954a5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b791da6a-d94b-5dd3-ac0c-06e197b7f124 |  | note | Detail - Inspect trench profile
label | 3ed5f2d9-e270-5eec-b4f9-b0a6bc95f726 |  | note | Frequency - 10m intervals
label | 6859158f-4d6b-5db9-8fbb-d0555c5cbc89 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
label | 78635462-39cf-52c8-920f-456b74ddef36 |  | note | Conformance Criteria - Record levels of base of trench on dip sheet
label | fbec8335-9f8e-5320-81b1-3f4f133c8076 |  | note | Records - Photo & CS-4001 Subsoil Dipsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 -
label | 8f335392-433f-5d31-88f5-c5f52cb41c15 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8661598f-db35-59f8-aaeb-adea1542b119 |  | note | Detail - Ensure the trench is cut in a manner than will ensure that the pipes will be laid true to the depths, grades and lines shown on the drawings.
label | face15c5-e5b8-5ed6-89b8-b97d38593444 |  | note | Frequency - 10m intervals
label | cb60aa28-c2d2-5cfa-85de-270461453164 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and measurement
label | be04c72f-43c1-597c-85c7-676fb9bc6857 |  | note | Conformance Criteria - Ensure trench line and levels match the design drawings
label | e7c91aa7-0671-5d1b-b410-1745bc30387a |  | note | Records - Photo & CS-4001 Subsoil Dipsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 -
label | 75941425-7241-53ae-a226-e0cd8552b461 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5db267a8-fcec-543d-b55c-1ee57f66f761 |  | note | Detail - CPS Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
label | 59b650aa-ff19-5942-8588-d606e842c3f8 |  | note | Frequency - As required
label | 977a9265-7f3e-52ed-bd73-66b9e7f4eeff |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 4b931163-9425-5af9-9936-31a54aec4382 |  | note | Conformance Criteria - CPS Engineer to instruct action and record on dip sheet and as built drawing
label | 2be598b5-d10f-5e99-9c78-553037b5e7f0 |  | note | Records - Photo, Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Bedding, pipe installation and Backfill.
label | c0134d86-f837-585b-9676-b6bd4ec4c3e9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0452a891-3eaa-5f2b-a644-fde02d83d21a |  | note | Detail - Upon completion of trenching Geotextile Filter fabricto be placed into the trench. Accordance with with TNZ F/7 :2003
label | 03c35507-deb5-5c2c-b9d8-7a1f77eb3bd9 |  | note | Frequency - 10m intervals
label | ac6aa259-b428-5886-bdad-c9a7c8566959 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 03112fa8-9f46-5c2d-a151-5d02fa20ade2 |  | note | Conformance Criteria - Ensure material covers the trench and is pinned in place
label | 22765af2-8c71-54c3-a8bd-5f57af652f1d |  | note | Records - Photo & CS-4001 Subsoil Dipsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 -
label | 3ed29aad-e78f-5c8b-badc-74f3f3c6269f |  | note | ACTION (Hold, Monitor, Witness) - W
label | b03fe4c0-d49d-55e5-bb0a-4a28536ca2e0 |  | note | Detail - Ensure 100mm thick Free draining granular Fill bedding is placed in base of trench.
label | 2a865518-c1fd-52f4-a002-5f695a94839f |  | note | Frequency - 10m intervals
label | 28f8df20-497b-56b3-b195-682541955474 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 953705ee-651c-5caa-8dcd-1d56371d8f83 |  | note | Conformance Criteria - Record levels of top of bedding on dip sheet
label | 7210e0f7-ef43-5e7a-9a5e-9263c6321129 |  | note | Records - Photo & CS-4001 Subsoil Dipsheet
checkpoint-status |  |  | checkpoint | 11 -
label | 232713dd-028b-5437-a15e-0b00e33b1af2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 47e37887-ed7c-5d29-828d-6ab6ee7fe7bc |  | note | Detail - Ensure Subsoil Pipe is laid on the Bedding in the centre of the trench
label | 20081d8d-00fa-5318-a442-413dd9435dd7 |  | note | Frequency - 10m intervals
label | b1bbc584-4614-5634-8b05-9eb36af956f1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | d10ed794-e961-511c-8333-e06406d08227 |  | note | Conformance Criteria - Consistency with Subsoil Details
label | 659258e8-0512-5d35-960c-d06614d1bac3 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 12 -
label | 5252882c-f91d-554a-9d10-203dc06d51ea |  | note | ACTION (Hold, Monitor, Witness) - H
label | 42c1f5b0-ab4e-5dcf-bbf2-27d4705b9f62 |  | note | Detail - As built Survey the Pipe before backfill
label | 55c3d484-e45f-52d4-98fc-64c8879f276b |  | note | Frequency - 10m intervals
label | cd0d3da5-7f9d-52c4-82ed-f74aef5b4e1d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 5aa6c5cb-39a4-550a-9991-9ce17c2b291d |  | note | Conformance Criteria - Consistency with Subsoil Details
label | c3a1bb98-2f64-5087-9863-08eba49bb418 |  | note | Records - As-built receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 -
label | b5aaf815-b0c5-590d-a966-74c9c35b5586 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e64a206b-186e-57ba-ae7e-eb725b0a8cc9 |  | note | Detail - Free draining granular Fill into the trench
label | fba9fd8c-0e52-50ef-9266-650b0a348e1d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 67c139c2-eedd-52d4-8dfd-83c1f5a04c58 |  | note | Conformance Criteria - Ensure good coverage
label | bd0b7524-a677-57ff-a74d-2f9ba281b31d |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 14 -
label | f693e248-eede-5f1b-a238-03ba49d7f0f0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0624373d-e7b8-5051-ad8c-c8ba82fff4f9 |  | note | Detail - Cover over the trench so that chip does not get contaminated by other construction activities - this might be with the pavement material or by cloth if other work is going to take place
label | 35fc3472-78b1-528e-90fb-29ce96122255 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
checkpoint-status |  |  | checkpoint | 15 - SubSoil Flushing eye
label | 5f346ec4-4126-542b-aaa8-6f68e9c01e32 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7a24fc91-b09d-5bfd-be1f-68029364fb79 |  | note | Detail - Hynds Round 250mmm Lamphole cover and frame or simislar approved
label | 0065a723-d360-5afa-aa7f-96eee2af2e25 |  | note | Frequency - Upon delivery to site
label | 16a406d4-5c45-5770-b046-ec8209a43c2b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 4b30f687-e514-599f-939b-675b6dab47ea |  | note | Conformance Criteria - Consistency with Subsoil Details
label | 560fc0db-c2cb-529e-8c1a-178bd46fb62a |  | note | Records - Delivery docket
checkpoint-status |  |  | checkpoint | 16 - Final Inspection
label | 563cf71d-2bd2-5ea4-8fd2-8d1151c86fee |  | note | ACTION (Hold, Monitor, Witness) - H
label | 954d484e-e40b-59a5-998b-6353359d4a13 |  | note | Detail - The Engineer needs to inspect the subsoil drain installed
label | 8892f8ba-79e2-5256-80e1-c0a23b5bb53a |  | note | Frequency - After subsoil drain has been installed
label | fdec0952-0152-5f2b-a1f5-04cf105a2f5f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | e56c1e2d-bc32-564b-9e90-0fd0acb1d990 |  | note | Conformance Criteria - Engineer acceptance
label | fcd74e31-7033-50ff-8f49-961b62eea5a1 |  | note | Records - Site visits, emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 17 - As-builts
label | 9cde5b56-c3bf-5b0e-8c86-c12d4b969de1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ad5aca4b-22e8-5a02-902b-dfe365296f07 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 6648132a-3a47-5c97-9988-f137eb73db68 |  | note | Frequency - At the completion of the Lot of work
label | 68d1c488-2bb2-5f33-98fa-c184dcfa9e64 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 7761ee2c-1cba-5ac7-8398-a5d2cd5e499c |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | CS-4044 - Roundabout Kerb Construction Record |  |  |  |  | Yes | CS-4044 - Roundabout Kerb Construction Record | 76b00124-4bca-4938-ae66-13f04f7f7f95
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | 1b48a2cb-2a6b-5487-b356-8ecb0eb359da |  | textbox | Project No:
text | 1e71d37b-b5fc-5bd3-aa70-22835b33566f |  | textbox | Description of Pour:
text | 55f8ff5a-1576-5c06-a01f-c5f2e1427557 |  | textbox | Concrete Qty:
text | 32069efd-e487-5d65-89bc-78d58256a6a7 |  | textbox | Kerb Type & Dimensions:
text | dc235c0b-35ea-58b5-863d-1e1de69f8ae6 |  | textbox | Concrete Grade: |  |  | Mpa
text | 56353951-7f22-5ad5-834a-714235470b66 |  | textbox | Weather conditions:
text | 572a9de3-3d71-559d-a6f3-53c259f77fa2 |  | textbox | Dwg No/Rev:
checkpoint-group |  |  | section | Formwork Mould
checkpoint-status |  |  | checkpoint | 1. Cleaned and oiled
text | f2d1aee0-7ba1-5f2a-a53e-11abd3954764 |  | textbox | Initials:
date | 3c985413-a7e6-51e7-b24a-6c4064160bcb |  | date | Date:
checkpoint-status |  |  | checkpoint | 2. Correct profile/dimensions for Kerb Type
text | df851a82-c259-5a29-acf8-45a431df53d7 |  | textbox | Initials:
date | e14d2d2d-7cbd-5ce8-a5fb-78772c9e409a |  | date | Date:
checkpoint-group |  |  | section | Subgrade
checkpoint-status |  |  | checkpoint | 3. Ensure subgrade construction is complete and suitable for kerb
text | e1a51e7c-05c0-5097-9f74-fdbbf1660b19 |  | textbox | Initials:
date | 1205b86e-d081-556e-8339-8b4096d6e686 |  | date | Date:
checkpoint-status |  |  | checkpoint | 4. Cesspit protection in place
text | 0f4cc689-d6f6-5eb5-83ce-709be2af02f4 |  | textbox | Initials:
date | bfca2294-c7f4-5a94-bcb9-55583cbe2135 |  | date | Date:
checkpoint-group |  |  | section | Survey set out
checkpoint-status |  |  | checkpoint | 5. Check survey set out
text | 42487284-65d0-50b1-ac78-57062ee71bbf |  | textbox | Initials:
date | 77db8168-4db8-5d41-8104-6ab288d0626f |  | date | Date:
checkpoint-status |  |  | checkpoint | 6. Check subcontractors string lines for machine
text | 6771954b-2d8b-52ff-b272-10e8c0c20f3c |  | textbox | Initials:
date | 6e459604-5187-5aea-b938-cab67757b6ea |  | date | Date:
checkpoint-status |  |  | checkpoint | 7. Check crossfall from RAB collar to kerb lip using a tape and level every 5m before kerb is poured
text | cfe3a1a8-9b77-5d77-99d8-01357c5e8b81 |  | textbox | Initials:
date | d148168e-75c6-51e1-bd6e-486b2db52f50 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8. Vertical levels correct to design +/-5mm vertical tolerance
text | 8b8df995-4e36-59b2-a338-35571819b14c |  | textbox | Initials:
date | 47df9b72-0982-5965-a63e-e40aaab4d8ec |  | date | Date:
checkpoint-status |  |  | checkpoint | 9. Horizontal alignment correct to design. +/-30mm profile tolerance but the width between parallel kerbs +/-20mm
text | dc885927-0842-5b92-a8b8-128e824f027e |  | textbox | Initials:
date | 292e526e-ceab-548c-84bc-bd7fd65d3fc5 |  | date | Date:
checkpoint-status |  |  | checkpoint | 10. Crossings / kerb transitions set out
text | c146d451-0912-5df4-9ea8-56c44c87b761 |  | textbox | Initials:
date | bc58bade-f6f2-5e38-a746-763fdb724ccd |  | date | Date:
checkpoint-status |  |  | checkpoint | 11. Engineer to mark kerb types at crossings and kerb transitions
text | 713dd3d2-ef56-5af6-9b4b-c3c9705a3526 |  | textbox | Initials:
date | 0d6af5d9-3765-5080-8362-ce458775a134 |  | date | Date:
checkpoint-status |  |  | checkpoint | 12. Ensure channels fall towards catchpit locations
text | 2d60bd6b-838d-573b-bb31-e7704d5a8a9e |  | textbox | Initials:
date | f7a024c4-5ab6-59ba-a8a1-f4c66e2208e4 |  | date | Date:
checkpoint-group |  |  | section | Miscellaneous
checkpoint-status |  |  | checkpoint | 13. Construction joint roughened & clean
text | cd766fd4-7174-5d46-a123-3eb8f6cdde5c |  | textbox | Initials:
date | 796d4b70-5db5-559e-b7db-d1a0acb52def |  | date | Date:
checkpoint-status |  |  | checkpoint | 14. Correct mix ordered
text | 49dffa7b-208e-5a11-b5be-ff48e01143a2 |  | textbox | Initials:
date | 407e27a8-9a4d-5799-9d28-b2864bdd0bda |  | date | Date:
checkpoint-status |  |  | checkpoint | Pre-pour check – HOLD POINT
text | 66182ba4-7b02-5806-83f4-7f6102dc06f9 |  | textbox | Site Engineer - Name:
date | 149257f5-6978-5525-a577-f2e71e16fe58 |  | date | Site Engineer - Date:
text | 410a5810-68ae-5f94-a3e6-9a869a9337cb |  | textbox | Design Engineer - Name:
date | 56e7e842-e7ec-5301-8137-00c512ec3476 |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | Sign:
checkpoint-group |  |  | section | Concrete Checks
checkpoint-status |  |  | checkpoint | 15. Correct mix delivered?
text | 2d167609-a3e0-5143-b284-acb257269644 |  | textbox | Initials:
date | 0e50bd52-9c9d-51a6-a725-4ed4a2cc4087 |  | date | Date:
checkpoint-status |  |  | checkpoint | 16. Correct slump (within tolerances)?
text | 1150ebcb-f634-520f-a7d1-3341c1cc10bb |  | textbox | Initials:
date | 6fdec9d5-bc73-5927-ba02-24a2006307da |  | date | Date:
checkpoint-status |  |  | checkpoint | 17. Concrete Supply Dockets collected?
text | 0bb04654-ca1b-5594-9ce0-866ec0665271 |  | textbox | Initials:
date | f7743402-8832-5c35-a12e-9c40ddb601df |  | date | Date:
checkpoint-status |  |  | checkpoint | 18. Batching Plant Records received?
text | 69177ee1-92b6-5868-bcb9-c459b6fa639f |  | textbox | Initials:
date | bf76c720-15c0-5b42-820b-cd6d2f8f4a3c |  | date | Date:
checkpoint-status |  |  | checkpoint | 19. Kerb meters completed in m
text | 43dff46e-84c7-5b5b-b1d4-6f364ae7dc45 |  | textbox | Completed: |  |  | m
text | eddd5383-6373-5e2b-90be-c37f48dd32d1 |  | textbox | Initials:
date | 70387762-520f-57d9-afac-848e638c8873 |  | date | Date:
checkpoint-group |  |  | section | DURING CONCRETE POUR INSPECTION
checkpoint-status |  |  | checkpoint | 20. Check height between base prep & kerb lip is consistent with #7 during kerb pouring
text | 8548ff9b-2b30-5d0f-adc3-13ac0aae7d62 |  | textbox | Initials:
date | 3fafc75e-88fe-55ad-bd8f-0802751ea6da |  | date | Date:
checkpoint-status |  |  | checkpoint | 21. Ensure correct kerb type is being installed in the correct location(s)
text | bd26a986-115f-5447-b23c-d490e89444cb |  | textbox | Initials:
date | e0845d63-45a3-5825-b628-f273666fb67e |  | date | Date:
checkpoint-status |  |  | checkpoint | 22. Constantly check levels and line to ensure kerb is within design tolerances
text | 62a26ddc-4869-5387-8b47-0a13f9e09750 |  | textbox | Initials:
date | 2188acda-82b5-557b-89d6-f383a74b8793 |  | date | Date:
checkpoint-status |  |  | checkpoint | 23. Ensure protruded kerb has U4 finish
text | 14182916-6a53-5c6a-bf03-f20fce84b800 |  | textbox | Initials:
date | 7cd86b6d-ec1f-55d1-a450-ad8181bd13cf |  | date | Date:
checkpoint-status |  |  | checkpoint | 24. Ensure Expansion joints are installed
text | b6433b6e-d4ca-508c-b807-3be16482d204 |  | textbox | Initials:
date | 0af7f2b8-b820-5532-87a4-38f4daf8f7f5 |  | date | Date:
checkpoint-group |  |  | section | CONCRETE INFILL ISLANDS
checkpoint-status |  |  | checkpoint | 25. ENSURE F3 FINISH AND THE CONCRETE LEVEL IS NO HIGHER THAN THE TOP OF THE KERB THAT FORMS THE MEDIAN/ISLAND
text | 025cbec2-2d7a-55a7-9639-905668cda469 |  | textbox | Initials:
date | 8b86288d-f3b1-596e-9ed8-97d6352bbdc4 |  | date | Date:
checkpoint-group |  |  | section | TIE INS TO PRE-CAST ELEMENTS
checkpoint-status |  |  | checkpoint | 26. Aprons to be formed around pre-cast elements
text | 64abe454-777a-5d73-8794-4f4d1f16eeef |  | textbox | Initials:
date | ebeebcd7-cc49-5a58-ba15-b28453bdd42b |  | date | Date:
text | 379787ae-3706-530c-a6f8-8dc046d26071 |  | textbox | Pour Start Time:
text | a796caf5-9871-5905-9467-bb5236f48c43 |  | textbox | Pour Complete Time:
text | fe692468-cbc2-5d46-9654-27e059917301 |  | textbox | Volume Placed:
checkpoint-group |  |  | section | PROTECTION
checkpoint-status |  |  | checkpoint | 27. Warning tape to be placed over kerb to prevent any damage
text | b28851c4-7ca1-5b1c-a420-7c070b871949 |  | textbox | Initials:
date | b2ec017c-02cb-57ba-978a-64b329636df1 |  | date | Date:
checkpoint-status |  |  | checkpoint | 28. Backfilling to commence after 72 hours curing time
text | c8b0b072-4e55-5e02-a2c1-e645292400c0 |  | textbox | Initials:
date | b8e57380-210e-555c-a219-27246d3674f9 |  | date | Date:
checkpoint-group |  |  | section | POST CONCRETE INSPECTION
checkpoint-status |  |  | checkpoint | 29. Complete #7 again after pouring using actual kerb lip
text | 97cebb38-e5df-52b3-87ab-ebe225bd24c6 |  | textbox | Initials:
date | fad8e530-f4b2-501a-b6e1-421a353f6052 |  | date | Date:
checkpoint-status |  |  | checkpoint | 30. Surface Finish and levels acceptable
text | f1c8b151-0f93-5a04-b76d-29ee76198f8a |  | textbox | Initials:
date | e7a17dd7-517b-55d5-a5f6-2244ade65ea6 |  | date | Date:
checkpoint-status |  |  | checkpoint | 31. Expansion joints satisfactorily completed
text | 1dd963d8-c8f3-538e-a223-05a049cf2c6b |  | textbox | Initials:
date | e80ab14a-1c15-51bf-a5af-90c83ee8e08b |  | date | Date:
checkpoint-status |  |  | checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
text | 75c4bd58-186d-5cb5-b63f-066fb0b0ce73 |  | textbox | Site Engineer - Name:
date | 57c4edae-68e3-5803-b43f-ba0ab1a5a0ad |  | date | Site Engineer - Date:
text | c905b0e3-d680-562f-9037-17d8a36c30cd |  | textbox | Design Engineer - Name:
date | ba4ddbe8-415e-5e2a-ade6-2eb85f172cda |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | ITP - Tangoio Falls Steep Underslip - B1004F - Stormwater Drainage | itp |  |  |  | Yes | Ω (Deprecated) ITP - Tangoio Falls Steep Underslip - B1004F - Stormwater Drainage (old version) | 770b6e32-6ce5-42cc-a44f-b57055e2d09d
checkpoint-group |  |  | section | Pre-Construction
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 79f83b13-569f-52e5-a9ca-b6fbfd50d7dc |  | textbox | CPS Eng.
text | c3a5e179-0f54-5b1c-ac95-2e9b1c1f0b09 |  | textbox | Site Engineer
text | 04036cc1-181b-5512-acf0-f2381303924d |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Drawings and Specification
label | 0e69d760-b4f5-58ca-b4c9-d97966bba459 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 5306936c-ea3f-55ff-9b7b-8334be494e42 |  | note | Detail - Check drawings and spec are the latest version.
label | b1998854-4929-5cfb-b7a1-63b70933b173 |  | note | Frequency - Prior to commencement
label | bba20ce4-39d7-5e62-9920-697756d76b73 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | a00e56da-431e-55cf-8234-baf98115dbab |  | note | ACTION (Hold, Monitor, Witness) - W
label | cdd4758e-87f3-55d8-b324-87c1a57b8fa9 |  | note | Detail - Set out as per design
label | 803829a9-4d40-50b0-9926-2d7c2c827f84 |  | note | Frequency - Prior to commencement
label | 4ef6441d-1475-5a92-93e0-7388dce1a266 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 26f6795e-45bc-5426-ad6a-6042a1bd8879 |  | note | Conformance Criteria - Check against plans for any discrepancies
label | d9ac2ab7-fbcd-5405-9ea6-d684d4a0bd86 |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 3 - Material Approval
label | 4b137c95-6607-532e-a71f-22aac00978e4 |  | note | ACTION (Hold, Monitor, Witness) - M
label | f9260d02-fc90-5f4c-987f-71e346fedf2f |  | note | Detail - Materials as per design
label | f643a428-6917-5a97-962b-51c3c5224371 |  | note | Frequency - Prior to commencement
label | c2fb43c8-569a-560d-b8ff-2fd690a38a7b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 77a16953-d49f-5899-a9d4-add8886b203c |  | note | Conformance Criteria - Only require approval if proposing an alternative material than that specificed in the drawings
checkpoint-status |  |  | checkpoint | 4 - Location of underground services
label | 0dda9022-e22c-5de0-bddf-c5f9d67a0559 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 117fa14d-8b9c-58cf-b57a-12d6ed900100 |  | note | Detail - Ensure undderground services are positively identified and asbuilt. If the service conflicts with the design confirm resiolution with CPS
label | c30225b8-2ffa-5b4a-89dc-cdad703539a1 |  | note | Frequency - Prior to commencement
label | b3bee91e-afd4-52e9-b74f-fc209ef157fa |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Drainlayer Qualifications
label | 11d0be2a-3d97-5298-899b-08804ebe22d0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ffbfdeae-0dc4-5623-9ec4-19b252b625f7 |  | note | Detail - Drainlayer to be appropriately qualified and skilled to undertake work
label | 941dd3ec-c119-50d9-b8c5-edfbe808442a |  | note | Frequency - Prior to commencement
label | ccfc206d-debd-5180-bfc2-d394a38057e1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 36421d97-414a-58e0-8833-4dac62c66150 |  | note | Conformance Criteria - Drainlayer Certs
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 6 - Trench and excavate for pipeline to design subgrade
label | 6e361085-f9bf-5ea3-ae92-55301d35b78f |  | note | ACTION (Hold, Monitor, Witness) - W
label | f5b3a719-6db2-53fa-bf84-6f02c23cc3d3 |  | note | Detail - Check subgrade with visual inspection and
label | a750e081-3732-5374-81c1-e686a268934d |  | note | Frequency - During Construction
label | 47968c6b-9496-558c-9f99-6a800cba598b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
label | 982d65b1-510a-58c3-a3c2-720cb24629b4 |  | note | Conformance Criteria - Delivery temperature, mat thickness before compaction, mix temperature during compaction
label | ea6acd3e-448e-5213-b1f8-448b72cb486d |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 7 - Surface finish visual inspection
label | 1768b7ec-dda6-5d2b-af77-b1f23fa7bfc2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 97b39c38-5d89-56bb-89e8-891ddb09c2b3 |  | note | Detail - Site walk over
label | a256a169-8fd0-55e1-9d8f-0131d3cdfff9 |  | note | Frequency - Post Construction
label | 5365fcde-752b-5cd7-b5f0-515342428a2a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 4f21f253-1d9c-5bc1-8105-af295a9ef691 |  | note | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
label | 6924bbae-8745-5b99-95c1-dd8fb562799b |  | note | Records - Subcontractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - As-builts
label | 5e019847-5c2c-553f-8837-d785d920a7df |  | note | ACTION (Hold, Monitor, Witness) - H
label | 04cb7e7b-5897-598e-84e6-df89d07c2448 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 5a89915e-0277-5fe0-980f-c754772a6df8 |  | note | Frequency - At the completion of the Lot of work
label | ec83cdbb-a0c4-5b29-90f9-ca9aecafba5f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 4e494b31-4ea7-554e-86e0-1f5384c48844 |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Quality Assurance deliverables
label | 5c20ad53-eab8-5286-b737-2272f0e4e28f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 00cc0a1c-bd4f-56a3-9b66-95247775e505 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | a9c57284-0bc1-5b8a-b37b-72f8a8b4f491 |  | note | Frequency - At completion of Lot
label | a0804abe-4d7d-51ad-9f66-7f032534c814 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 8700cab0-338e-51d8-a4c7-977e5cfcf9cf |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 87b2b2c0-1327-54fb-a1aa-11838e25c84a |  | note | Records - Asbuilts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 10 - Completion Sign Off From Fields Below
label | 9762feb8-90cd-5ba6-883e-5b24b024236c |  | note | Records - Signatures
checklist-flat |  |  | checklist | ITP - E1401A - Captain's Culvert Inlet Remediation - Kerb & Channel | itp |  |  |  | Yes | ITP - E1401A - Captain's Culvert Inlet Remediation - Kerb & Channel | 78d668af-78db-490b-a9f1-3bcf1df2fffb
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 64f134d5-b535-5d93-947e-ecd64ce5cb8e |  | textbox | CPS Eng.
text | 32ee191e-f093-5a74-9d3f-dcda8115363c |  | textbox | Site Engineer
text | 26928e2b-e061-575d-a6a4-76d7b4b6999b |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 0ab5d813-0e49-5b0a-9121-e82bc7a033d0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b975853d-6446-5408-8155-37d8320bec5b |  | note | Detail - Set out kerb line and level at 1m offset to EOS
label | 0ab47cdc-b261-5874-a82f-4825f8a4ff7f |  | note | Frequency - Prior to commencement
label | 00b4238c-b69c-5997-929b-2e6b95414f3c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey, Measurement and Visual inspection
label | 80963869-d6c8-5d22-a7f1-61a6cb885a29 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | faea7cbb-fa89-56a5-9276-4035f8cfc080 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Material Compliance
label | a83101e1-5942-5774-a8a4-b4dcbc3a1349 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 54f00d4a-ca46-5dce-b557-61903f7d6a4e |  | note | Detail - Ensure the Concrete Mix is as per the Kerbing Specification
label | 251b3a08-f206-558f-8f43-3c621f0c921d |  | note | Frequency - 1/600m3, minimum of 1 per source (but make three cylinders)
label | c9868559-725f-515a-ad17-fcdadc26eb9d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Lab Testing
label | cd28ffa7-2f6d-5a8e-9db3-6707da10d896 |  | note | Conformance Criteria - 20MPa at 28 days
label | 6357fade-7e9a-58ec-9594-f76bd5870aef |  | note | Records - Concrete Delivery Dockets and lab test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 -
label | c6b6b98d-aede-5043-a73d-ce8458cbfa50 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4b3ce800-2184-5141-955b-d13bdc6c69e3 |  | note | Detail - Ensure the slip form moulds match the dimensions of the design kerb
label | 3cd1363a-cb11-5db4-89e5-893360aadfa4 |  | note | Frequency - Prior to commencement
label | 4919a36c-054e-5670-b9c3-f771c41758b9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | 80385d36-fcaa-5eb4-a0fa-07e330ecd19e |  | note | Conformance Criteria - Measurements match the design kerb dimensions
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Kerb Foundation
label | 73659c18-3121-54af-bd33-230c59e94716 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 46391509-2607-5424-90d2-8bdeb2c0916e |  | note | Detail - Ensure Sub base construction is completed
label | 9630daba-6a5e-5d80-88c3-4ecd2328c5ac |  | note | Frequency - Prior to commencement
label | 8dbe3ece-a044-5c67-841d-256d8db2768d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 2113d818-c4c0-57ad-95e7-aeb2be42e041 |  | note | Conformance Criteria - Pavement depth and type under the kerb varies depending on location
label | 8c0b8fd9-3c4c-59fe-8e2c-b56558ce20c0 |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Stringing
label | ae9be5cf-b637-5663-9769-bc7582373d13 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 18b62a52-2ff4-59e3-a57b-da50bec80763 |  | note | Detail - Check weather forecast and avoid adverse conditions
label | eeab87dd-0b14-5873-9778-b5a52200663c |  | note | Frequency - Prior to commencement
label | 6b836bad-b3e6-59ad-9c34-f50a5be04f40 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 61fa1116-8203-5b37-af23-2466358a01dc |  | note | Conformance Criteria - No concrete to be placed in adverse weather conditions
label | 5067cecc-12a0-5cbb-b102-9258341700f7 |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 -
label | a3e26f5f-4d49-51b2-aa19-5db08c804f9f |  | note | ACTION (Hold, Monitor, Witness) - W
label | ac8a5276-2f12-5986-bfbe-a4a3da6bb833 |  | note | Detail - Kerbing Subcontractor to set out steel pins and string line to design levels and identify catchpit locations
label | 2c68da22-2e9b-5a4b-b126-768cd223b526 |  | note | Frequency - Prior to commencement
label | a79c64f5-7f18-5e06-a9ca-5c7d0233d69e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | 8259d28a-28ff-5847-b4dd-ae7a48c8f629 |  | note | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
label | a27c6490-05f8-580d-ad3b-0b8a56d6bdf7 |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint-status |  |  | checkpoint | 7 -
label | f77b2f46-ad03-5586-9e1a-bc52a166b222 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 05c71122-3c7e-5efd-a6eb-fb7842ee0a8e |  | note | Detail - Subcontractor String line to be checked by Site Engineer to ensure Horizontal and vertical smooth transition and to ensure the channels flow towards the catchpits.
label | bd8dccbb-dbba-5bc6-819d-c35dc04bce85 |  | note | Frequency - Prior to commencement
label | 685f3c59-c558-5e0f-b9c5-d606538a2feb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | e50eb134-4305-5e83-90ab-fe24501069a3 |  | note | Conformance Criteria - Ensure tolerances are maintained. Vertical +/-5mm, Profile +/-30mm but the width between parallel kerbs shall be +/-20mm of the required width
label | 7423c794-81c0-52e6-852c-b1de83d92d66 |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Slip forming
label | e6181475-22d5-5a0e-9742-5cc64bd91d1b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 561eaf32-5e37-505b-8f34-52f7146b91b4 |  | note | Detail - Check correct Kerb & Channel profile is installed onto kerb Machine
label | dfac2347-5082-5b15-9eaf-0156b8d7672c |  | note | Frequency - Prior to slip forming
label | 3c4637ea-bb75-5bdf-80d4-70c2a83d5aa8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and Measurement
label | 1f46fe61-83f7-598b-8377-7d0fbdbe5a86 |  | note | Conformance Criteria - To ensure the correct kerb types are installed at the correct locations
label | 4d9c34ad-f82f-526c-bff5-8839efb5d832 |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 -
label | e4a5e10e-8c25-5c80-8127-ae7553b12310 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 944d88a0-2209-5a39-bb54-079a4a4ce8ad |  | note | Detail - Kerbing Subcontractor to order concrete as per design Mix and to ensure the concrete is tested
label | f91a4db8-77a8-521f-b142-c34b2978b417 |  | note | Frequency - During Slip forming
label | 85d6f421-4609-5af4-8ffd-c8ce06b23a18 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 80cb0fff-448f-5a20-829d-aa462df56229 |  | note | Conformance Criteria - To ensure the correct concrete mix is delivered
label | e7c5deb4-b5a4-53af-8d72-e75d1cdbf190 |  | note | Records - Concrete Delivery Dockets and lab test results
checkpoint-status |  |  | checkpoint | 12 -
label | f6763fc8-7cdd-5242-8d2d-2c57d054bc86 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 74fdf6c5-1a99-50c8-b4a0-dee39bb3d890 |  | note | Detail - Expansion joints to be formed at 5m centres
label | 3d81d4b3-59d6-5ee9-a71a-ba2d60da90c0 |  | note | Frequency - During Slip forming
label | ca41b970-7c91-598c-ab84-e8153da58e88 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | d05e73f9-6edf-5da6-9aeb-c754f0e17271 |  | note | Conformance Criteria - Kerbing Specification
label | 0f92f39d-492d-54d8-bda2-4b08cd231053 |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
checkpoint-status |  |  | checkpoint | 13 - Tie-in with pre-cast components
label | 7b3fe8c2-c69e-5a37-ad8b-7af1ebc13b9b |  | note | ACTION (Hold, Monitor, Witness) - H
label | fac39dbe-2013-5933-961f-187f53fadfe6 |  | note | Detail - Subcontractor to ensure Slip form Kerb & channel to be cut and tied-in with pre-cast components.
label | 33fe506e-732e-578b-b81b-c513aadad00e |  | note | Frequency - During Slip forming
label | ab64f61c-f365-51af-b980-ac7c84928ea0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 69a1ad86-1290-50b6-9402-87c1e19ee997 |  | note | Conformance Criteria - Consistency with Work Instruction
label | bb21ae84-43bb-5635-b6dd-859e63684ca2 |  | note | Records - CS-4045 Kerb Construction Record Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 17 - Protection
label | 35df2f4b-55dc-510c-867c-4efe80897351 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 162d8a10-cbe2-5e94-aaf8-2472824caa6d |  | note | Detail - Backfilling behind kerbs to commence only after a curing time of 72 hours
label | 61c029f0-c9f8-5e99-af26-e5037c1f0990 |  | note | Frequency - Prior to backfilling
label | ece8ace3-763b-55e0-9454-e94df44a8fd6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | a19140e7-6a9e-5fd4-b09a-18a57dfe56b8 |  | note | Conformance Criteria - Backfilling to commence only after 72 hours
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 20 - As-builts
label | 482d3c34-05ab-5857-bce8-eb644d8e2dc3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | aa0fdad0-aa00-5e1b-a93d-ecc91d97c595 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 6c357053-ee9e-5d51-a71e-5d27cf034f5a |  | note | Frequency - At the completion of the Lot of work
label | 22429908-f6cc-52a8-9d8f-c03d7f3d0830 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | bb057957-8458-5907-93c9-45b348e79906 |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - E1401A - Captain's Culvert Inlet Remediation - Rock Armouring | itp |  |  |  | Yes | ITP - E1401A - Captain's Culvert Inlet Remediation - Rock Armouring | 7a9b9391-1d71-4fe3-b275-b40102e12acb
checkpoint-status |  |  | checkpoint | Project Site reps.
text | b5a74fad-d0c9-5d5f-a435-8cf37bdcdba8 |  | textbox | CPS Eng.
text | 35c3d663-a8c7-5999-99d1-333757bead77 |  | textbox | Site Engineer
text | d15a9e6c-ba17-5bd0-85b2-215e826f0fd5 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 92bcf7c7-280c-58f7-abcc-e74e735216f5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3c71d814-473d-597a-801f-00b14d7f39ec |  | note | Detail - Set out extents and check against design drawings
label | 07bf40fe-54e2-5558-805c-258210a71367 |  | note | Frequency - Prior to commencement
label | 57e36359-792b-558f-94f8-b6407b69cdaa |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | c9aa3d75-fe7a-58c3-9fef-3800c4d3f7aa |  | note | Conformance Criteria - Consistency with Construction Drawing -
label | 6f7209fe-7bb1-5da9-95d3-cc4791796810 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 -
label | 92d0d6b2-71ce-5a3a-b671-8474fa27dc75 |  | note | ACTION (Hold, Monitor, Witness) - H (CPS)
label | feb535b8-0e6b-5055-9a8f-60c69494e571 |  | note | Detail - Engineer to confirm the extend with site conditions - Drawings C03, C04, C10
label | 66a61b74-6925-5524-8866-88c130d6f04f |  | note | Frequency - Prior to commencement
label | 25659552-2e67-513f-b74a-9ee51b7e3f28 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 1dc6a94e-1f55-5c95-b22e-7e325c166626 |  | note | Conformance Criteria - Engineers Acceptance
label | c8f144d6-a601-55db-8024-298f6ed5b5de |  | note | Records - Raise RFI on Procore
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 -
label | 2bd17ebe-7841-5f6a-8b4a-f2e1769b3d87 |  | note | ACTION (Hold, Monitor, Witness) - H (CPS)
label | d5a25bf5-36b3-5325-9013-ae58082bc89b |  | note | Detail - Inspect fill foundation
label | 7298dbf9-bcbb-5f23-b38e-d95ddb5f37b0 |  | note | Frequency - Per area as required
label | 467acd06-0846-58ab-b03c-f2ee38c39a5c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | 88d63909-6ea6-5de3-b854-bfd2db731eeb |  | note | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
label | 2ac273f4-9fec-5d3b-be17-36e51d3ee02a |  | note | Records - CS-4100 Subgrade Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Material Compliance Testing
label | 2d68bbf8-b06e-5090-b92d-f776156f0baf |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0e82d01d-f9ea-5195-9dc5-449414e241b7 |  | note | Detail - Material to meet specifications dependant (D50 of 125mm Class 1)
label | 67fee3b8-6a1e-5634-965a-8dc53f7dcae5 |  | note | Frequency - Each material used
label | 735d1edb-b73c-53ce-8f30-9b11123ba5e0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 -
label | a798f406-274e-5327-a57d-f6ced0af4195 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4bc9b03e-19cc-5fcf-b1f0-6d4edd672acb |  | note | Detail - Rock Construction Material
label | e158cd68-3a50-521d-a116-188e0b1e8d09 |  | note | Frequency - 1 test per Lot
label | 121614f0-4442-5021-94ea-a97fc9f2772e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | d4443e08-6926-5f4d-aa88-e44d6c769968 |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 -
label | fc578f3d-dbf5-53ad-b1dd-1fabcaa6efff |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4c33d978-6a3d-516f-9c8f-64e5684c3321 |  | note | Detail - Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49
label | b48fa8ed-ea56-5755-aebc-1366fa55dfcb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | eae4312c-44d7-586d-b822-3d50c9f41b50 |  | note | Conformance Criteria - Conformance with Specification
label | a77180be-be15-58ec-abd2-17dcc7a72d3f |  | note | Records - Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Construction of Engineered Fill Embankment
label | 01c25a28-1a48-5a76-a367-511672fbe6dd |  | note | ACTION (Hold, Monitor, Witness) - H (CPS)
label | 955b60ba-c6c8-58c1-9be6-d6f2e48843fb |  | note | Detail - Location of bank regrading to be agreed with CPS Engineer - Drawing C10 item 3.2
label | fc027830-f2f6-5ba1-9c5a-b0baed5efb07 |  | note | Frequency - Prior to commencement
label | 634ace84-30b7-5fa5-9450-ab27be907faf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | f18d8949-8463-5419-951c-8c821bc5b586 |  | note | Conformance Criteria - Engineers Acceptance
label | 99727bd0-5816-5f8b-b146-866ba106c28c |  | note | Records - Raise RFI on Procore
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | -
label | d8f76015-8891-5bac-9b23-94159979de30 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d08e1e22-d958-5405-984f-e8e64f437e44 |  | note | Detail - Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap
label | 201ba140-3997-59a7-8d87-62bb463f9758 |  | note | Frequency - Prior to commencement
label | adbf0d80-3398-5de0-8700-9b2a776604cc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 77322fdf-cc5b-5615-beff-5e28a49fce66 |  | note | Conformance Criteria - Intake Earthworks ITP completed
checkpoint-status |  |  | checkpoint | 9 - Geotextile Placement
label | 0ad2a99d-1591-51f5-84cb-709cd9807110 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 26624183-e3c7-54b9-b81e-793f0b1389dd |  | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | 897be73a-bc30-5927-806c-f538e04258b3 |  | note | Frequency - Daily visual check
label | b3d5c525-2d40-59df-b384-5c492542ceb1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | ac22f77a-3d8d-535f-b9c9-dd7b5e145b09 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 10 - Riprap Placement
label | 1b86cd7a-e361-5e1b-8f61-c1413c56410b |  | note | ACTION (Hold, Monitor, Witness) - W (CPS)
label | 213566b9-e237-5efa-b5b7-6d5da23ed82e |  | note | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material
label | 779a5472-f683-51c6-b50e-6a9c6115d359 |  | note | Frequency - Daily visual check
label | a4b6ad98-f276-53f0-9d8a-c4bb1b4eafa6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 379535f9-8154-5f8f-880a-8cf81e526812 |  | note | Conformance Criteria - Specification
label | d746f4c3-6916-5564-9a83-d30ba799c411 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 13 - Survey As Built
label | 0b2c5689-a8eb-57aa-8069-364ca4690be8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ec68d94c-1aef-5994-b16f-bf39891c95a6 |  | note | Detail - Ensure rock slopes comply with design prior to next process taking place
label | e0d261c4-5c86-551e-ac70-468be99517c8 |  | note | Frequency - At completion of Lot
label | bb1f359e-49f3-55f4-8299-10f0e3ed98b7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 170b55ed-c69b-5bd6-b7a9-853534f25a4b |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Lot Number QA File
label | d0290628-a0cf-5632-a891-360bd2a07180 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7130a4b3-92a7-5721-a5b4-1f5aebb45ce8 |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 3680421b-e26e-531a-a038-856e8f034ccd |  | note | Frequency - At completion of Lot
label | a7d9cdde-b66e-5065-bacb-662cfbd714be |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | a9034e78-77df-5eae-980a-6ea86d3fd91e |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 54e7283e-ba15-5f40-9e80-9f1bbe22f755 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 15 - As-builts
label | 45a13bd6-8218-5289-a252-207e23eb7b73 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ad2ad162-dce7-50b0-bfec-b4c3df130a72 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 49b0f0f9-3ca9-5a8e-a162-17523468880d |  | note | Frequency - At the completion of the Lot of work
label | 0eddf604-32b3-5722-9377-3f097b507b0b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 99f844a3-9ff4-5dc0-9ae8-37d050e6d2e2 |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 16 - Quality Assurance deliverables
label | 6e3f782a-c4c2-548d-833a-4467c08b0a48 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a7f40ca9-c724-5368-adb5-e157f74548f9 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | fe1611a8-26bf-5cb1-afe2-8c9a50da76f1 |  | note | Frequency - At completion of Lot
label | 9523d355-656d-5fea-94be-9fbc2855641c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | bafefe6f-6622-5c0c-9e41-512c181157da |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | bf05fe0b-2528-533a-9117-ee40d616326e |  | note | Records - Asbuilts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 18 - Completion Sign Off From Fields Below
label | 9c4cb7da-b88d-5549-97aa-0e2812133b9a |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | CS-4040 - Concrete Inspection Record |  |  |  |  | Yes | CS-4040 - Concrete Inspection Record | 7b254421-66d4-4d15-898d-1eba6529f6ba
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Concrete Inspection Record
text | d5dc53c0-bf3e-51b9-b683-e84adaf04634 |  | textbox | Location / Description of Pour:
text | a78bc1fb-0727-55d3-9d72-0a8347dbbd1d |  | textbox | Drawings & Revision No. used to check off Pre Pour Inspection:
text | 00ab4815-1642-555a-9824-9cc39919987f |  | textbox | Concrete Grade |  |  | MPa
text | fdfbb313-95e5-5214-a095-bac2180ea34d |  | textbox | Concrete Quantity |  |  | M3
text | 2e616ce3-aefa-5832-8768-4a3a3a8ce07a |  | textbox | Pour No.:
checkpoint-group |  |  | section | Formwork
checkpoint-status |  |  | checkpoint | Adequately braced and supported
checkpoint-status |  |  | checkpoint | Grout tight
checkpoint-status |  |  | checkpoint | Correct dimensions
checkpoint-status |  |  | checkpoint | Cleaned and oiled
checkpoint-status |  |  | checkpoint | Formed surfaces straight
checkpoint-status |  |  | checkpoint | Major penetrations located
checkpoint-status |  |  | checkpoint | Embedded items located
checkpoint-status |  |  | checkpoint | Specified surface finish:
checkpoint-status |  |  | checkpoint | Adequate seating Pre Cast units
checkpoint-status |  |  | checkpoint | Permit to Load Obtained
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | Reinforcement Content and size
checkpoint-status |  |  | checkpoint | Grade markings:
checkpoint-status |  |  | checkpoint | Placement, tolerance, clearance
checkpoint-status |  |  | checkpoint | Rigidity and cover
checkpoint-status |  |  | checkpoint | Clean steel
checkpoint-status |  |  | checkpoint | Lap location and lengths
checkpoint-status |  |  | checkpoint | Starters/dowels correctly located
checkpoint-group |  |  | section | Construction Joints
checkpoint-status |  |  | checkpoint | Location
checkpoint-status |  |  | checkpoint | Roughened
checkpoint-status |  |  | checkpoint | Clean
checkpoint-status |  |  | checkpoint | Water bar placed if specified
checkpoint-group |  |  | section | Other
checkpoint-status |  |  | checkpoint | Mix ordered:
text | ccad0b2a-99d8-5644-903f-ec5628f8a0bc |  | textbox | Mix ordered:
checkpoint-status |  |  | checkpoint | Independent Survey – Check off critical survey points
checkpoint-status |  |  | checkpoint | CPS Engineer notified (48)
checkpoint-group |  |  | section | Pre-Pour
checkpoint-status |  |  | checkpoint | Pre-Pour Checked and Accepted – HOLD POINT – Site Engineer
holdpoint |  |  | signoff | Add Signature
checkpoint-group |  |  | section | Wet Concrete Checks
checkpoint-status |  |  | checkpoint | Mix delivered:
text | f6fe92fd-df87-5d91-a560-46d8dfbe3439 |  | textbox | Mix delivered:
checkpoint-status |  |  | checkpoint | Slump/flow Target:
text | e0c71d22-012c-5c4a-92ba-1f8b4f5c388e |  | textbox | Slump/flow Target:
checkpoint-status |  |  | checkpoint | Compliance Cylinders Taken
checkpoint-status |  |  | checkpoint | Site Cured Cylinders Taken
checkpoint-status |  |  | checkpoint | Concrete Vibrated
checkpoint-status |  |  | checkpoint | Mandrels drawn through all ducts to verify no leakage / disconnection
checkpoint-status |  |  | checkpoint | Finished Level: Finished to grout check / angle fillet worked to
checkpoint-status |  |  | checkpoint | Surface to required finish eg U2, U4
text | b9513790-3ccf-52e0-b78e-b521770d9168 |  | textbox | Surface finish achieved:
checkpoint-status |  |  | checkpoint | Retarder applied at end of the pour
checkpoint-status |  |  | checkpoint | Curing applied (specify type)
checkpoint-status |  |  | checkpoint | Concrete Supply Dockets collected
text | 9ac99a60-b892-5257-bb96-dec581533311 |  | textbox | Pour Start Time:
text | d2bec2ec-7fc9-5b41-aede-3675f295e1b8 |  | textbox | Pour Complete Time:
text | 3b5a7af2-eb5c-5a4a-b8ec-ed660b18ab4c |  | textbox | Volume Placed:
checkpoint-no-status |  |  | checkpoint | POUR ISSUES – Add as comments (e.g. formwork failure)
checkpoint-group |  |  | section | Post Concrete Inspection
checkpoint-status |  |  | checkpoint | Curing correctly carried out
text | 0b86dcd1-cf17-5f6d-89bb-69d4dddbf157 |  | textbox | Concrete Strength for Striking:
text | 9d9154f7-7447-5c9d-a3f2-36068eb68e2f |  | textbox | Concrete Strength for backfilling:
checkpoint-status |  |  | checkpoint | Preparation of Construction Joints Completed
checkpoint-status |  |  | checkpoint | Blow holes, tie bar holes filled
checkpoint-status |  |  | checkpoint | Inspection of surface/s & any authorised repairs have been completed
label | 9d792ca5-1faa-5ad4-b676-71ea6a4de4e0 |  | note | CPS Engineer Inspected.
checkpoint-status |  |  | checkpoint | As-Built complete
checkpoint-status |  |  | checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
text | 0a5353d4-6e95-5360-a12e-78db188f1213 |  | textbox | Site Engineer:
holdpoint |  |  | signoff | Add Signature
checklist-flat |  |  | checklist | CS-4105 - Road Lighting & Cable Installation Record |  |  |  |  | Yes | CS-4105 - Road Lighting & Cable Installation Record | 80597afd-0fcc-4eaf-b4d0-246254f1e320
checkpoint-no-status |  |  | checkpoint | Road Lighting Trench & Cable Installation Record
text | 6b6d23de-a193-5585-93ac-1992d5806b40 |  | textbox | Project No.
text | 709da04a-4215-5431-9ba6-50b07486d3ae |  | textbox | Drg No:
text | 50d915c0-9ac0-5290-b947-4256c9400e59 |  | textbox | Rev No:
text | 4d7f6745-e0a9-542a-af82-b10b0f97cf20 |  | textbox | Chainage/Road Light No.:
checkpoint-status |  |  | checkpoint | Road Light Locations set out by Surveyor.
text | b23a6c14-b5fe-5cbd-bb27-40c64728cf50 |  | textbox | Initials:
date | 6e79ddcb-dc73-576d-b730-e045ea39cd3a |  | date | Date:
label | 87af8032-26d4-59d7-b398-11cace4129db |  | note | Comments: Consistency with Construction Drawing, Details and Notes.
checkpoint-status |  |  | checkpoint | Pothole existing services that cross the line of the trench.
text | 1b8dd5d6-2f15-5c0d-8003-261e19905a56 |  | textbox | Initials:
date | e69fb542-102b-5010-9069-b0ba8023f80d |  | date | Date:
checkpoint-status |  |  | checkpoint | Permit to dig obtained and underground services marked out.
text | aa8e2705-a524-5564-aba4-76ba2a039de7 |  | textbox | Initials:
date | 97a18cb9-376b-59d0-ba50-be63f2f64674 |  | date | Date:
checkpoint-status |  |  | checkpoint | Trench location marked out with offset pegs and checked that it clears other services.
text | b8de9298-cefd-5373-8a59-b90df206f447 |  | textbox | Initials:
date | 6ba5e12c-67c5-5693-8816-61b78b60564e |  | date | Date:
checkpoint-status |  |  | checkpoint | Inspect trench and ensure it is required depth below Ground level and free from obstruction.
text | c2901648-0a65-5b91-97a5-9dad592018c9 |  | textbox | Initials:
date | ca672a74-b4db-5e10-82fb-73692b7a5438 |  | date | Date:
label | 7927eefc-703f-54fb-b9cf-63db4fd32cfe |  | note | Comments: 600mm below open areas and under footpaths, 900m under roadways and free from obstruction
checkpoint-status |  |  | checkpoint | Ensure the correct cable is being placed in the trench and check if direct buried or duct required.
text | f2a8af60-8908-50db-aa0d-44656392a691 |  | textbox | Initials:
date | 17b5e319-8324-5ab1-9d28-c71fbff296fd |  | date | Date:
label | d3dbc7d7-00ff-5e93-a894-5f22290c4b8a |  | note | Comments: Ducting is required under roadways, within bridges and when entering concrete foundations
checkpoint-status |  |  | checkpoint | Ensure cable ducts (where required) are clear of obstructions, fitted with Draw Wires and are easily accessible for cable drawing.
text | 44bde1a3-080e-5f3a-b64b-ee62091c8f0b |  | textbox | Initials:
date | 5b08b7fe-95d3-51c4-b88e-75ffa41a8e42 |  | date | Date:
checkpoint-status |  |  | checkpoint | Ensure cables are laid without sharp kinks and loops for connection are provided at Pole locations.
text | ad8c52f4-8d14-5326-bbbe-17f2f5ef486c |  | textbox | Initials:
date | 2d4a6cd2-d4a6-5aa6-9bcf-3d8edd4e3a68 |  | date | Date:
label | d4376497-88eb-5080-b58b-97c4fca0b12f |  | note | Comments: 3m loop on continuous cable, 1.5m loop at cable ends
checkpoint-status |  |  | checkpoint | As built survey Cable in the trench. Ensure the As Built information includes the number and the type of cables and circuit numbers
text | 7878f77e-1fbc-5345-a36c-3eb434834d42 |  | textbox | Initials:
date | 07b229b9-4c66-56b3-b5e3-46dc21cd760b |  | date | Date:
checkpoint-status |  |  | checkpoint | Cables buried directly into the ground shall be enclosed.
text | 9573cb2d-1d50-5b55-9ca9-4caba94c3144 |  | textbox | Initials:
date | dfde0eaa-b503-53c9-94c5-10b61f378d4f |  | date | Date:
label | bfdd5c8a-4ef7-5888-bd5f-b6720c6460a3 |  | note | Comments: Min. 50mm of Sand on all sides of the cables or Soil which passed through sieve no greater than 10mm
checkpoint-status |  |  | checkpoint | Ensure trench is backfilled and compacted by hand ramming for the first two layers, followed by power consolidation.
text | 1d281404-343f-5f2a-8b49-511c1a392a0f |  | textbox | Initials:
date | f72fcf17-10cc-5dac-bd38-56c65d848e26 |  | date | Date:
label | 11ee182c-3ecd-5c43-96cc-6f9892c3c167 |  | note | Comments: Depth of cover:
label | 6065af77-63ca-5150-b938-7fa866dc595d |  | note | ○ Open areas or under footpaths = 600mm Under roadways = 900mm
label | 74a336e7-5d40-57bc-950f-3651438c4a92 |  | note | ○ Check compaction with Clegg hammer every 20m
checkpoint-status |  |  | checkpoint | Ensure 100mm Wide Orange Polythene Warning Tape is installed.
text | b4e0aeac-2b19-59ba-91bf-2f572c77348b |  | textbox | Initials:
date | 8e6a4c78-aad9-5830-9f41-f527434d4e94 |  | date | Date:
label | 15f31217-aefa-549a-b218-dfcf4607f693 |  | note | Comments: 150mm below finished surface of trench.
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | 997a5eec-1a9b-5c86-925a-de455b48888e |  | note | Position: Site Engineer
text | 7fe2a427-7cc2-5338-8f2b-bf82f7a89651 |  | textbox | Site Engineer - Name:
date | 7c30bbdf-2ebf-54a5-b8c2-72f824542e9b |  | date | Site Engineer - Date:
label | d1f6223b-51df-5702-99a7-b106e45daeb8 |  | note | Position: CPS Engineer
text | 5cc07f9e-cbe0-59d5-9ba4-c63265db1d16 |  | textbox | CPS Engineer - Name:
date | 2e7bbc46-cc5d-5552-981a-3e45d222efe1 |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | ITP - G1202A - Waikaretaheke Overslip #3 - Rock Armouring & Bulk Filling | itp |  |  |  | Yes | ITP - G1202A - Waikaretaheke Overslip #3 - Rock Armouring & Bulk Filling | 80b3e6ff-3356-4ff3-89a7-7e36524b8d3e
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 1aaf5e02-b3e5-5804-a831-daadbfa324b0 |  | textbox | CPS Eng.
text | 183729c4-a1d5-5d93-bf91-713a07508cc2 |  | textbox | Site Engineer
text | ab88cf91-d294-53d5-9fd3-5cee5568643a |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | e1f38f48-d12d-5f11-a62d-1ade130b87f9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5f72ff74-57f5-552e-9013-1c0d7b3c3cd5 |  | note | Detail - Set out lateral extents of buttress. Geotech Engineer to confirm extent of works
label | 87b918eb-dc9b-5998-8f3b-373fb9a0a730 |  | note | Frequency - Prior to commencement
label | b5a5d8ea-34aa-5fe5-ae5f-9922c36d5b2b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 614d1c1d-85ba-5669-9c8d-2761e9600490 |  | note | Conformance Criteria - Fault ID 530 - Underslip Recovery Remediation Design Report
label | 2dae98ec-7d44-5de7-9d28-bd844b6a9b48 |  | note | Records - Survey receipt / sketch markup
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | 5b9b2e17-8cc9-5794-8336-b62c1afd0d40 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3bd4f410-2f93-5f9c-858d-90c3c6a6df4a |  | note | Detail - The buttress slope face angle should be 2H:1V. The buttress slope face angle may be steepened to no more than 1.5H:1V if required by site constraints, at Geotechnical Site Engineer's discretion
label | e48e1c45-8c3d-5f4f-8a11-91ee93d28e60 |  | note | Frequency - Prior to commencement
label | 895a6605-6dc3-528e-8687-4781da5ef8b0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 1a5830e5-f57f-563f-94aa-d0d4b4fc8636 |  | note | Conformance Criteria - Fault ID 530 - Underslip Recovery Remediation Design Report
label | 0d8920ea-eaed-577f-9ba6-cd986618ab22 |  | note | Records - Sketch
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Excavate to Sub-Grade
label | 95ffbeb8-cced-5019-8200-ff627322923f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4355d788-40b2-5721-82be-13ce348bb41c |  | note | Detail - Excavation only to start once ESC in place as per ESC ITP. Inspect fill foundation.
label | 4096fb2b-5d20-5155-b486-71dfd434a5f3 |  | note | Frequency - Per area as required
label | d7df1edc-5fd2-53fd-bf6f-0fe278ff1527 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | 9790464a-fadd-5f26-8fd3-7a71f7aa4cce |  | note | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
label | eae83166-6566-52fe-acac-4c45f794c86d |  | note | Records - CS-4100 Subgrade Approval Checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Excavate to Sub-Grade
label | 11743bbc-58e4-5920-9b14-70207ec44141 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f141e38c-a9ab-5199-85b7-19667c4b6af5 |  | note | Detail - Foundation compliance. May be performed by site engineer or CPS as is specifically only for ground strength data for future review.
label | ea9a4b06-3eac-593b-8113-31cdd5b681fb |  | note | Frequency - Per area as required
label | c2389461-c32a-5588-9d7f-fd1fa0716364 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
label | 01961d33-4516-5265-a6da-0446c926244d |  | note | Conformance Criteria - >= 1 test per 10 linear metres, where access is practical and available
label | 058d63da-0d78-5a4b-b184-e2e853e23ca6 |  | note | Records - Engineer or Lab Test Report
checkpoint-status |  |  | checkpoint | 5 - Material Compliance Testing
label | dafb6580-16d3-5389-994b-cdc3d95de44a |  | note | ACTION (Hold, Monitor, Witness) - H
label | da0fd2d9-d67f-5f82-b51c-2710294d266b |  | note | Detail - Material to meet specifications dependant on material type selected
label | 260736a5-7d2a-57ad-9a77-bb9a14358aec |  | note | Frequency - Each material used
label | 314a69c0-be9a-5d63-8ab7-e0460e5957f0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 0255f467-0b6f-5049-b3fe-4308236ce5e0 |  | note | Conformance Criteria - a. GRADATION D85/D15 = 1.9
label | 2cf9de52-99cf-5d33-aab0-65e299d11b8f |  | note | b. D85 690 (MAX) AND 590 (MIN)
label | d379fd8b-41ae-5266-869c-dc011e96eec4 |  | note | c. D15 390 (MAX) AND 275 (MIN)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Material Compliance Testing
label | 8cada2d1-c449-5925-89c0-7001f91b6363 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 419d723f-fb53-5f25-ab28-53a69fce9073 |  | note | Detail - Rock Construction Material
label | f14a50df-dde8-52d6-b4dc-298508248c7a |  | note | Frequency - 1 test per 1 000m3
label | d52778be-a38e-5af9-8ab4-2d50ec13ae0c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 9c8e34e1-534c-5004-9ef1-172c2ff65226 |  | note | Conformance Criteria - D50 OF 450 WITH A MINIMUM SPECIFIC GRAVITY (SG) OF 2,350kg/m3
label | d219826d-6b81-52c7-8d24-7905f6c5f9fa |  | note | Records - Lab Test Report
checkpoint-status |  |  | checkpoint | 7 - Material Compliance Testing
label | 63644ea4-3bfb-5e40-baeb-dc44882fba96 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 20e505f2-fa99-5afa-971c-bb2ce42ccdbd |  | note | Detail - Back Face Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A39 (Class D) or similar
label | 86d0e016-9bc6-5f16-98af-085f989a31c3 |  | note | Frequency - Prior to commencement of placement
label | 9ef19a43-ba9e-5b12-a64d-9660e78f288a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 8fac69fa-e6bf-5ecf-a5d5-859a897a0e37 |  | note | Conformance Criteria - Conformance with Specification
label | e760a788-c035-5561-944a-85ce1f16a96e |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 8 - Material Compliance Testing
label | 1fc3f692-df5c-58ba-b28b-daf307df49cb |  | note | ACTION (Hold, Monitor, Witness) - W
label | 863a2978-07b4-514c-a260-82203134f971 |  | note | Detail - Between Rock Armour and bulk fill Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49 (Class E) or similar
label | acfad55e-6d93-5e18-86c6-a1e65e909991 |  | note | Frequency - Prior to commencement of placement
label | 7b4e40c9-dffb-5010-b656-5a2093eb511e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 0afcb380-96d0-5421-a991-ae207a27c2af |  | note | Conformance Criteria - Conformance with Specification
label | 1f404334-d3cf-589b-8ecd-d0a73155a15e |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 9 - Material Compliance Testing
label | 00462b8f-5fe6-59a2-9315-2988a7370cbc |  | note | ACTION (Hold, Monitor, Witness) - H
label | 63c74947-61c6-5c1f-a6da-65973eab6145 |  | note | Detail - Bulk Construction Material
label | ed65e90c-d88d-5f4b-9070-8b0a8ecb24ca |  | note | Frequency - 1 test SET per 1 000m3
label | f323973c-2ab4-5f2d-9e82-01bf211ef74a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing - OMC Standard Compaction; Grading Curve (wet sieve)
label | b545d3f6-a5b6-5b88-a853-9687d08ae55f |  | note | Conformance Criteria - All bulk fill comprising clean graded granular aggregate with broken faces AP65 (i.e. gravel).
label | 6be51878-f401-5af4-8c2d-02efcae0336e |  | note | Records - Lab Test Reports
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Geotextile Placement - Backface
label | 4e5341e0-1006-52b6-9cae-f78a0f30ca6f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0b4fb4f9-ce15-5a3d-8955-35deaebdedf1 |  | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | 24d7f43f-22b0-571d-835c-23b76a447f5c |  | note | Frequency - Daily visual check
label | 0ecfddcd-5ba8-584c-82b0-85582a73c402 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 72ac4623-1e29-5f68-b39d-7d55515c2a2f |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 11 - Backfilling of Engineered Fill Embankment
label | bf5495e2-1fd5-54e7-b38c-a1099b484206 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5f38aa16-ec19-52a6-9f9d-7390a31d1dea |  | note | Detail - Engineered bulk construction material 250mm lifts with material and regular compaction testing
label | ca561128-7b23-514e-99ef-96d19b8df76a |  | note | Frequency - 1 test per 10m linear length (forming a test set). At least 1 test set every 2m fill height (minimum total of 3 evenly spaced test set intervals over total height of bulk fill).
label | 781ff798-2fb1-5bcb-8ac1-c6343196eed1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing - NDM (required), supplemented with Clegg Hammer tests at discretion of site engineer.
label | fb728b70-2fa0-5051-9020-47afe1a1439a |  | note | Conformance Criteria - 95% of MDD or clegg equivalent
label | dcf3f317-2f9c-5386-b0f9-adf74fbddb5a |  | note | Records - Lab Test Reports
checkpoint-status |  |  | checkpoint | 12 - Construction of Engineered Fill Embankment
label | b8229fb2-01e1-5fbd-a902-2a691af077db |  | note | ACTION (Hold, Monitor, Witness) - H
label | e8a6d18c-8bfd-5a45-b4b5-9f2a94bace4b |  | note | Detail - Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap
label | 21ad2db0-7f41-5b80-bf75-7fa48f24a036 |  | note | Frequency - Prior to commencement
label | 451d4667-1e1f-50b8-baa2-2043147749f4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 8f27dfc5-7f99-57bb-b42e-a783962f4ed0 |  | note | Conformance Criteria - ALL BULK FILL MATERIAL SHOULD COMPRISE CLEAN GRADED GRANULAR AGGREGATE AND HAVE BROKEN FACES AP65 OR SIMILAR MATERIAL.
label | a3bfbc33-d7b6-53e0-9230-f958503205e1 |  | note | Records - Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 - Geotextile Placement - Frontface
label | 76b32109-022e-5be8-883e-f150f8d47df5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4a0f45ec-66cb-5136-9546-d9ad10e67caa |  | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | 389f52fa-a1f0-55d0-aa39-332690c533dd |  | note | Frequency - Daily visual check
label | 9263fcce-ec9e-537c-a97f-f66e7d8a6be5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | e6d506ec-d6c6-5f95-9cbe-5f3b9aecfe9f |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 14 - Riprap Placement
label | 9e1e5865-e114-57a6-a62d-4e377afa96a4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | dd6f7817-f079-54fc-981c-358977c8158e |  | note | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. Design Engineer given notice to visually inspect initial placement of riprap material
label | 2661e7f8-edf2-5b5c-b05b-efcde4d2016c |  | note | Frequency - Daily visual check
label | 5ea0d486-5aff-5a77-932c-ec8a474bd29d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | ac069992-1004-5209-b475-81b0cf869b7c |  | note | Conformance Criteria - Specification
label | 3524a439-6860-52a7-a31e-0d01d78e6860 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 15 - Tie in to existin swales
label | 664a9854-b170-516b-98fd-7957c4f52c07 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 398ae4fe-2bf3-5150-b157-4c77458ed43a |  | note | Detail - Ensure drainage swales are insatlled to tie in with existing swales to esnure drainage flows correctly
label | 39f06ef9-638e-5714-9092-a51116eb3101 |  | note | Frequency - Daily visual check
label | e4ed5720-346f-52d0-a365-f02a2f0afd1a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 575eb873-b13b-5698-8730-609a7f948d17 |  | note | Conformance Criteria - Fault ID 530 - Underslip Recovery Remediation Design Report
label | ffe7d7e0-eb99-5d2d-b5d1-6c78b69a19d3 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 16 - Quality Assurance deliverables
label | 8f3d7360-ea79-5bc5-b122-615d6d505ef7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | fd9da0f7-36a1-5056-be2d-fd88fdf9cce8 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 0d6b272e-d806-576b-ba88-a1120e9fe8ad |  | note | Frequency - At completion of Lot
label | f9f63fcc-7d81-5a1e-b0c1-2e04e9361f7e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review. Red line mark up notes of design plan.
label | abc021f8-80f0-5f5c-8d6f-5d220ca0cce8 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | b62d1345-1f75-56ff-b968-a827d3ef15ea |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 17 - Completion Sign Off From Fields Below
label | c021397a-3e64-50d2-97ca-2e84d8c4dc0c |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | CS-4076 - Asphalt Laying Checklist |  |  |  |  | Yes | CS-4076 - Asphalt Laying Checklist | 833f8bfe-b7ce-40a9-a4fb-496165cf71c1
checkpoint-group |  |  | section | Pre Laying (Tasks 1-7)
checkpoint-status |  |  | checkpoint | Final confirmation job is ready (Site Handover, Job Instruction sheet)
checkpoint-status |  |  | checkpoint | Undertake Emulsion Tack Coat Risk Assessment
label | b9d59b58-0dae-530a-8238-47762fefe612 |  | note | By Who: Foreman
checkpoint-status |  |  | checkpoint | Confirm job matches Laying Plan. If not, confirm and communicate variation with manager/ customer
label | 84b5f67c-2bb5-538e-a206-839215e27c09 |  | note | By Who: Foreman
checkpoint-status |  |  | checkpoint | Visual Inspection of site and stringlines completed as per Site Handover
checkpoint-status |  |  | checkpoint | Daily Pre-Start Meeting/Hazard ID completed
checkpoint-status |  |  | checkpoint | Approved Traffic Management Plan on site (implemented and effective)
checkpoint-status |  |  | checkpoint | Vehicle Movement Plan
checkpoint-status |  |  | checkpoint | Fences, walls, kerbs protected and environmental controls in place
checkpoint-status |  |  | checkpoint | Pre-seal prep including offset of services/ roadmarking and protection of fixtures
checkpoint-status |  |  | checkpoint | Laying Plan and Rolling pattern confirmed
checkpoint-status |  |  | checkpoint | Paver setup. Screed checked at start of the day (level and feed controls functional)
checkpoint-status |  |  | checkpoint | Stringline Tie in points to calculate required asphalt thickness
checkpoint-status |  |  | checkpoint | Starting blocks in place (including compaction allowance)
checkpoint-group |  |  | section | During Laying (Tasks 8-9)
checkpoint-status |  |  | checkpoint | Tack coat applied and cured
checkpoint-status |  |  | checkpoint | Mix visually inspected and the ‘in hopper’ temperature is within tolerances (contract-specific)
checkpoint-status |  |  | checkpoint | Mat depth control (contract-specific)
checkpoint-status |  |  | checkpoint | Stringline Tie in points for correct depth
checkpoint-status |  |  | checkpoint | Rollers working to agreed pattern
checkpoint-status |  |  | checkpoint | Shape and levels achieved as per specification
checkpoint-status |  |  | checkpoint | QA forms completed as per Job Instruction form
checkpoint-group |  |  | section | Post Laying (Tasks 10-11)
checkpoint-status |  |  | checkpoint | Measure and record area, quantities and spread rate
checkpoint-status |  |  | checkpoint | Post-paving subcontractors notified
checkpoint-status |  |  | checkpoint | Collate QA forms and supporting documentation (refer Job Instruction)
checkpoint-status |  |  | checkpoint | Post paving as-builts, coring, survey
checkpoint-status |  |  | checkpoint | Plant de-established and off-hired as appropriate
checkpoint-status |  |  | checkpoint | Roadmarking checked and completed
checkpoint-status |  |  | checkpoint | Traffic loops / counter loops reinstated
checkpoint-status |  |  | checkpoint | Traffic management de-established
checkpoint-status |  |  | checkpoint | Services exposed, raised and painted
checkpoint-status |  |  | checkpoint | (hydrants, valves, manholes)
checkpoint-status |  |  | checkpoint | Job site safe and tidy
checkpoint-status |  |  | checkpoint | Job site tidy. All AC piles picked up. Kerbs chipped and swept. Drains checked for AC. No footprints left in gardens/berms
checkpoint-status |  |  | checkpoint | Transition joins/tie ins are tight and flush (no high/low ridges, no risk of plucking out).
checkpoint-status |  |  | checkpoint | Longitudinal and fresh joins are all tight and flush (no high/low ridges, no risk of plucking out – water running freely across joins).
checkpoint-status |  |  | checkpoint | Kerbs – height/finish requirements met across 100% of job (refer Job Instruction)
checkpoint-status |  |  | checkpoint | Ride Quality – Drive over site - no bumps can be felt
checkpoint-status |  |  | checkpoint | No visible surface defects (roller / stretch marks)
checkpoint-group |  |  | section | General comments
checkpoint-no-status |  |  | checkpoint | General comments:
label | c71dc433-46a6-595a-b314-b4c38b7c6268 |  | note | Score Guideline (record comments/details)
label | 1dd62099-b92a-5c57-8285-4f0a8f376d6d |  | note | 1 - Not Acceptable (remedial/rework required, advise Manager)
label | 8fc511d0-af1c-5966-a0e9-f3cbb5041a24 |  | note | 2 - Acceptable (no obvious problems, can be handed over to client)
label | 0190e2c2-23f5-508e-8b8d-d565e60c3e5d |  | note | 3 - Excellent (entire job above standard)
checkpoint-no-status |  |  | checkpoint | Job quantities/spread rate
text | 7944df6a-601d-53b9-98e6-3305e600f205 |  | textbox | Hand lay (H), Paver lay (P)
text | ae21ea35-8a28-548f-8bbe-4d3b9a1e2535 |  | textbox | Mix Type
text | 6eab55f6-e3e4-57eb-bfa6-925f98d4ff0b |  | textbox | Area (m2)
text | f882b62a-ee25-5c0b-b8e1-d168b82b0373 |  | textbox | Depth as per Job Sheet
text | 3ada4c37-20a8-5000-843c-14ba7da6fa2c |  | textbox | Tonnes Purchased
text | 053717de-d8c1-5138-9f55-153210ce692a |  | textbox | Wastage Tonnes
text | b7bcfb29-d934-55cc-953d-1a9b431d4189 |  | textbox | Tonnes Laid
text | a6998950-b0e2-55e4-b40d-0cca2b5e73ad |  | textbox | Average Depth (mm)
text | 57d0e328-5648-51a8-9f83-695072aa08ac |  | textbox | Emulsion Primer (l)
label | d1bd0e71-36d7-59a1-9fbd-a9d7547b2098 |  | note | Depth = Tonnes ÷ Conversion Factor (Density) ÷ area (m2)
checkpoint-status |  |  | checkpoint | Signoff
text | ecdcc960-3891-5b27-b340-7bc038971657 |  | textbox | Signed by Foreman:
date | e1449790-eea3-550b-87d0-f3951708a4a3 |  | date | Signed by Foreman - Date:
text | 435375bd-548f-5566-be93-e2be1ba1fda4 |  | textbox | Reviewed by Manager:
date | fda81c18-3444-5291-8f40-34ca6776aa22 |  | date | Reviewed by Manager - Date:
holdpoint |  |  | signoff | SIGNATURE
checklist-sectioned |  |  | checklist | CS-4090 - Utilities Check Sheet |  |  |  |  | Yes | CS-4090 - Utilities Check Sheet | 839d9b10-32df-4355-8006-e2f29c064892
checkpoint-group |  |  | section | Pre Construction
checkpoint-status |  |  | checkpoint | Underground services checked
checkpoint-status |  |  | checkpoint | Survey Set Out
checkpoint-status |  |  | checkpoint | Correct materials and sufficient lengths on site
checkpoint-group |  |  | section | Material Approval
checkpoint-status |  |  | checkpoint | Bedding Material approval
checkpoint-status |  |  | checkpoint | Hard fill approval
checkpoint-status |  |  | checkpoint | Draw wired is 10 gauge galvanised mild steel complying with NZS 3471
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | Trench correct depth and width
checkpoint-status |  |  | checkpoint | Subgrade check (scalas), min. 3 % CBR
checkpoint-status |  |  | checkpoint | Bedding laid in trench to correct depth (100mm)
checkpoint-status |  |  | checkpoint | Correct cable and duct sizes laid as per service drawings
checkpoint-status |  |  | checkpoint | Gas provider trench approval
checkpoint-status |  |  | checkpoint | Chorus provider trench approval
checkpoint-status |  |  | checkpoint | Power provider trench approval
checkpoint-status |  |  | checkpoint | Services laid with correct spacing
checkpoint-status |  |  | checkpoint | Irrigation provided to all Rain Gardens and Garden Beds
checkpoint-status |  |  | checkpoint | Lot connections laid 500mm into lot boundary
checkpoint-status |  |  | checkpoint | Street light cables laid to pole locations
checkpoint-status |  |  | checkpoint | As built service locations
checkpoint-status |  |  | checkpoint | Draw wire in all ducts
checkpoint-status |  |  | checkpoint | All ducts end capped
checkpoint-status |  |  | checkpoint | Mag Slab laid
checkpoint-status |  |  | checkpoint | Bedding covering services to correct depth (100mm over Gas, 50mm over all other services)
checkpoint-status |  |  | checkpoint | Approved backfill material placed in 200mm layers
checkpoint-status |  |  | checkpoint | NDM tests every 30m³ of backfill material, 95% of MDD
checkpoint-status |  |  | checkpoint | Warning Tape 400mm below finished surface
checkpoint-status |  |  | checkpoint | Irrigation Pressure Test complete
checkpoint-status |  |  | checkpoint | Gas Pressure Test complete
checkpoint-no-status |  |  | checkpoint | Weather
button | 40059248-0134-56d2-8afa-ffd597981788 |  | button | Weather | Sunny (check plants not left bare root in sun), Raining (ensure soil is not saturated which prevents proper planting), Frost (No planting to be carried out until frost thaws out), Overcast (Good Planting condition)
checkpoint-status |  |  | checkpoint | Sign Off - Site Engineer
label | 89522473-2649-5fd3-bc47-719b750294ca |  | note | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | CS-4052 - Landscaping Planting Checksheet |  |  |  |  | Yes | CS-4052 - Landscaping Planting Checksheet | 85aa2afa-e85f-40d5-ad70-1db65a34c406
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | 4d8b64f8-79e9-581f-911a-3821916a3a10 |  | textbox | Work Area:
text | 16fadadf-1d41-5392-bd20-888fde8ea00a |  | textbox | Sub Work Area:
text | 2d74a6bb-3a34-5313-88ca-31b8c5dd3bbc |  | textbox | Lot:
text | 58d75f32-1666-53a2-8149-ab607ed7d753 |  | textbox | Sub-lot:
date | ad7386ec-1ce2-558e-9a46-4e18698b8bcb |  | date | Document Date:
text | 2202fe5d-2bea-527a-ab36-204e82d52d6e |  | textbox | Created By:
text | b85ab6f1-7ce7-5e29-8e8a-6e49c39dc3d2 |  | textbox | Drawing Number/s & Revision:
label | d77f4e88-43ed-5ba0-a38b-cdb1b57e8067 |  | note | Raingarden (RG), Garden Bed (GB), ), Tree pit (TP), number:
text | 8c758f3a-2072-5f27-85d0-eeef8ca0715d |  | textbox | RG #:
text | 742ec5c0-d75a-5831-838e-80fae1ee5b61 |  | textbox | GB #:
text | 61a58422-f6aa-50b3-8bb6-62156e4d9f8d |  | textbox | TP #:
checkpoint-group |  |  | section | Spec./Site Preparation for Seeding or Planting
checkpoint-status |  |  | checkpoint | 8321/8332/Any other site works that will cause rework to landscaping & planting has been completed.
text | 238b3a4b-d77b-5e8d-8227-5c5d49609a36 |  | textbox | Initials:
date | 595a4f22-f60c-5400-8ad7-6566d6bf7429 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8321/Check for service in the area of this work. Avoid interference or damage to them
text | 55acd7e3-fdd0-597b-b905-99f09a55b86c |  | textbox | Initials:
date | ec198178-9463-57ef-922e-6c5bbdb141fe |  | date | Date:
checkpoint-status |  |  | checkpoint | 8321/ HOLD POINT. Garden bed to be approved by Landscape Architect prior to installation of soil media. Strata Vault installation to align with manufacturers recommendations. Photographs to be provided.
text | 42f58789-a7f1-58a0-b2f4-15f118ce57df |  | textbox | Initials:
date | 09a10aa6-c077-5c41-96f8-f8b7d48ee352 |  | date | Date:
label | e76f0946-79b9-5909-b4f3-6175b6722da0 |  | note | Comments: Date/Signature Landscape Architect
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | HOLD POINT. Raingarden drainage layers to be approved by Landscape Architect. Photographs to be provided.
text | d23cb35c-c282-53b4-9d79-b77e34cef2fc |  | textbox | Initials:
date | 797bd3c2-853c-5044-92d2-2d1e3b9ff656 |  | date | Date:
label | 4077e7da-238e-5b4d-8a05-3b7270e09c2f |  | note | Comments: Date/Signature Landscape Architect
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Raingardens - hydraulic conductivity to be tested to prove this is in line with raingarden material specification.
text | 539afc7a-9d1f-5b31-9db5-9e23e9690eed |  | textbox | Initials:
date | f29fd7a1-6b1d-581d-a6c9-c4e71d3878ea |  | date | Date:
checkpoint-status |  |  | checkpoint | Soil to be adequately compacted in 200-300mm layers to ensure no pockets of air within garden bed / tree pit.
text | 2bfd2ae5-e6f3-5e54-a8d9-d45d7372a1ed |  | textbox | Initials:
date | 1961fea0-6e80-5f5e-adab-b0a9c711e9c5 |  | date | Date:
checkpoint-status |  |  | checkpoint | HOLD POINT. Garden bed profile to be approved by Landscape Architect and Stormwater Engineer post soil media install. Photographs to be provided.
text | 05333f00-827f-54f4-b317-acbe62b9c7e2 |  | textbox | Initials:
date | 83b61db9-33b2-5dc8-a10b-bd1fe8091f63 |  | date | Date:
label | 3b08ab56-b873-54e8-ade6-2722a2db6db2 |  | note | Comments: Date/Signature Landscape Architect
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Should the soil in the garden bed become compromised (by ongoing site works or any other concern) – pH to be tested to prove this is still in line with the soil product specification.
text | f19b7d7e-e540-55fe-94fe-928ce3fcf9f1 |  | textbox | Initials:
date | 4ef07c72-4f25-55fb-9831-377fab30bef4 |  | date | Date:
checkpoint-group |  |  | section | Spec./Planting
checkpoint-status |  |  | checkpoint | Ensure no standing water at base of tree pits – report to Engineer.
text | 3e97e446-8d42-55e9-8109-adde41e8e4a7 |  | textbox | Initials:
date | 99660711-c4b0-5710-8628-f64223e1a688 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8332/Plant material origin checked on delivery for plant material quality and accepted. All plants to be inspected and approved by Landscaping Architect prior to installation.
text | 7fabf680-ce70-5e8c-b607-b3a96330fccf |  | textbox | Initials:
date | 58d90c09-6800-5ec5-8ed3-b6cd277a47f7 |  | date | Date:
label | f9f8bb52-7346-5097-a173-b3f3894e27a3 |  | note | Comments: Date/Signature Landscape Architect
holdpoint |  |  | signoff | SIGNATURE
checkpoint-status |  |  | checkpoint | All trees to be inspected and approved by Landscape Architect prior to delivery on site. 6 monthly photographs to be provided.
text | 9ab02d3b-84af-51f2-995a-714b86c9cd80 |  | textbox | Initials:
date | 9d631b8e-14d3-56e3-a252-2111166c6ca9 |  | date | Date:
label | 28a5d701-15c0-58dd-ba48-02f927ff1553 |  | note | Comments: Date/Signature Landscape Architect
holdpoint |  |  | signoff | SIGNATURE
checkpoint-status |  |  | checkpoint | 8332/Plant material suitability. Roots eased where root bound. Plants not removed from container too far in advance (avoid drying out).Root balls are moist (not dry).
text | 881bdcc5-82b9-5329-bc6b-e275cb2023b6 |  | textbox | Initials:
date | bf003bf3-f9e9-5f8f-a9a0-81575f48da14 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8332/Spacing and set out in accordance with Landscaping plans and consistent & correct to specification and schedule. Tree species according to drawings. Approved by Landscaping Architect. Specific placement and orientation of trees to be confirmed with Landscape Architect on site – including any required pruning.
text | 40ef51ee-924e-5c2a-871f-f4cdb6ae287c |  | textbox | Initials:
date | 32f0b9fc-86cf-5756-9fb1-76df3f928e0a |  | date | Date:
label | df98a13f-79d7-5fa4-95c0-5f06d8bb0454 |  | note | Comments: Date/Signature Landscape Architect
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | 8332/Fertiliser/ Crystal Rain Gel incorporated to manufacturers specification
text | beef0a2b-01fe-570f-afb8-219d671eed95 |  | textbox | Initials:
date | 51a139b1-dba2-5859-9eba-fc8210d5711f |  | date | Date:
checkpoint-status |  |  | checkpoint | 8332/All plants shall be thoroughly watered a few hours prior to planting and again immediately after planting.
text | 7f250f6e-6c45-5bbb-84d1-d7f3cb89c130 |  | textbox | Initials:
date | 93a1fb6b-b47f-5700-9d87-d8a62bd73732 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8332/Mulch clear of plant stem, Soil not left on top or mixed with bark mulch.
text | d17a8be7-689a-52c6-93c1-3c954cc07f82 |  | textbox | Initials:
date | b484af1b-8327-5c6f-9a13-583ba9aa78e1 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8332/Stakes where required to specification, level and with ties fixed securely.
text | 64ae41b3-9337-51d3-ac74-054a9b4db7f2 |  | textbox | Initials:
date | c9444641-077a-5219-bdc0-51605912da86 |  | date | Date:
checkpoint-group |  |  | section | Spec./Turf Laying
checkpoint-status |  |  | checkpoint | 8333/Landscape Architect to inspect area prior to turf laying. If not available on site then photos to be provided.
text | 8b8deec4-56b8-5aad-8cf4-3bdf7544b6ee |  | textbox | Initials:
date | 1af576cf-0354-54af-a85e-35b0a66c3e46 |  | date | Date:
label | 040d0e34-89ee-5c76-9a27-b4504d6655ea |  | note | Comments: Date/Signature Landscape Architect
holdpoint |  |  | signoff | SIGNATURE
checkpoint-status |  |  | checkpoint | Lawn areas to be finished 25mm higher than adjacent hard paving to allow for settlement.
text | 09ed8276-4351-5923-83fa-f0757823fe77 |  | textbox | Initials:
date | 95c05943-1630-560b-ae89-5a8665f777a7 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8333/Landscape Architect to inspect area after completion of turf establishment. If not available on site then photos to be provided.
text | 8223da41-9ccc-5d8c-b80a-6bd8683c20ec |  | textbox | Initials:
date | b338ec7b-a074-503d-afb9-d583ad6b3af6 |  | date | Date:
label | 993a5308-a3a4-5766-89f5-c554ec5c9db9 |  | note | Comments: Date/Signature Landscape Architect
holdpoint |  |  | signoff | SIGNATURE
checkpoint-status |  |  | checkpoint | 8333/Remove weeds, root material, stones, rubble and any other debris exposed during cultivation.
text | 53e851bd-ded3-56ce-a399-2007e426cdc7 |  | textbox | Initials:
date | 2a387cf5-3f2a-56c5-9c9a-79aa71f81587 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8333/ Apply a dressing of fertiliser and work into the top 50mm of soil immediately prior to sowing.
text | 3fb1062f-155f-5d46-9f87-b0a05933c86c |  | textbox | Initials:
date | 184af2ae-0bce-57ab-b5b4-9864ccf0ecd4 |  | date | Date:
checkpoint-status |  |  | checkpoint | Additional areas to be planted/areas missed (mark-up drawings where additional planting may be required)
text | 83c32f05-4379-5108-91c0-7da532409a1b |  | textbox | Initials:
date | b264e4c1-b372-509d-b5ad-44b9efc5cb6d |  | date | Date:
checkpoint-group |  |  | section | Spec./Daily Clean Up
checkpoint-status |  |  | checkpoint | 8332/Surplus plants removed to storage area per specification.
text | 0b9f5641-e0fe-5f5d-9484-223c1373af43 |  | textbox | Initials:
date | d2dfcbe4-1752-578e-bd59-1ca1c14dd25d |  | date | Date:
checkpoint-status |  |  | checkpoint | 8332/8333 Site cleared of rubbish and surplus materials (containers) removed
text | d2ddc42b-cd05-563f-bbc5-bde5f78b220a |  | textbox | Initials:
date | 549509a1-28d6-5517-9251-7898dec21e3b |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Weather
radio | 4eabaa0b-c3c8-52b8-8b77-c3d27b1f2785 |  | radio | (select relevant condition) | Sunny (check plants not left bare root in sun),Raining (ensure soil is not saturated which prevents proper planting),Frost (No planting to be carried out until frost thaws out),Overcast (Good Planting condition)
checkpoint-status |  |  | checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
text | 9e99b015-11be-52cf-a7e1-844c2127b9c5 |  | textbox | Site Engineer - Name:
date | 68e65eb1-897a-5af5-badc-48c28c7d3f18 |  | date | Site Engineer - Date:
text | c422898f-68dc-56fb-874f-56b81fc29aaf |  | textbox | Landscape Architect - Name:
date | 6a61ffa7-0250-5e16-846c-bc99d092bb82 |  | date | Landscape Architect - Date:
holdpoint |  |  | signoff | SIGN
checklist-sectioned |  |  | checklist | ITP - C1603A - Waikare Gorge Descent - Groundbeam & Guardrail | itp |  |  |  | Yes | ITP - C1603A - Waikare Gorge Descent - Groundbeam & Guardrail | 8873c421-178e-4696-a70a-6d584cec4636
checkpoint-group |  |  | section | 1 - Preliminary
checkpoint-status |  |  | checkpoint | Project Site reps.
text | d1329917-ab2d-59ff-91e7-ce3c8ad49bb9 |  | textbox | CPS Eng.
text | 2670618f-526b-5da5-94ae-f3ab577f4289 |  | textbox | Site Engineer
text | c04a7f37-6065-55ff-818e-29a520fe4865 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Alternative Detailed Construction/ Installation Methodology
label | 0556865c-a122-512d-a0ab-56f31b5f415d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 87caa383-9358-5b9a-a85b-e05c95edf470 |  | note | Detail - Documentation from the supplier that proves the safety complies with Section 5 of the project Specification
label | dea3660a-d95a-5001-9c72-f2b3bb799de9 |  | note | Frequency - Prior to commencement
label | 9b09f885-6972-580e-b28e-bd4c6a06b6f8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 4a8670ca-c8fb-5d80-b517-81dfd7de5c51 |  | note | Conformance Criteria - Section 5 of the Project Specification
label | b88c5555-b56e-5eba-baa3-81dfe05fdd63 |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Earthworks and Pavement Works
label | 36a595b8-803b-5998-a86d-8f5ebf6a6e75 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 817ec378-3b06-57c2-b5b9-a750295c2b60 |  | note | Detail - Earthworks and pavement construction shall be completed prior to Ground beam and Barrier installation.
label | 46c27f3c-5156-562c-8abe-b0bdd7a80b8a |  | note | Frequency - Prior to commencement
label | 4334b27a-17ae-5167-b998-3b8cdb5d39a0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 31a83ee3-c034-54b9-8b52-16747d7e1277 |  | note | Conformance Criteria - Previous ITP's approved
label | 6e73de46-4268-5d90-abe5-e32d42e6ee1e |  | note | Records - Previous ITP's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2 - Material Compliance
checkpoint-status |  |  | checkpoint | 2.1 - Reinforcement Steel Compliance
label | 67b71111-e73c-5d04-8df3-894d9d637c23 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b1d73887-9aa1-5eb6-a2cf-e0130b34262e |  | note | Detail - All reinforcing steel to comply with AS/NZS 4671 Grade 500E
label | 63f87062-6b37-5c92-a81f-38a140405b1b |  | note | Frequency - Prior to commencement
label | b7269fe4-1926-54a7-a1d9-cfdce5fe21b8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | df86bad9-75fc-548e-b544-768c8cb2a451 |  | note | Conformance Criteria - DH16, DH12, RH12 reinforcing steel delivered and dockets collected
label | 19bbbc36-6d57-5388-a979-2f3c58b046bc |  | note | Records - Delivery dockets, packing slips, invoices
checkpoint-status |  |  | checkpoint | 2.2 - Concrete Mix Compliance
label | c64d16ac-de84-5563-a76b-44938bb61fdd |  | note | ACTION (Hold, Monitor, Witness) - W
label | e0c997c9-95e4-52a7-92e9-dcb7d49192c2 |  | note | Detail - Concrete mix to meet required strength
label | bf1db101-9820-54ac-9882-d0c64df731a7 |  | note | Frequency - Three weeks prior to placement of concrete
label | fd953b46-711d-5c0b-b63a-5c14c88b4c3d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | c0b5885e-61ae-57cd-b36c-8cfb33222347 |  | note | Conformance Criteria - Minimum concrete compressive strength to be 30 MPa at 28 days
label | 154fa6e0-1027-56c4-9a7a-9c2c6f874718 |  | note | Records - Mix design, delivery dockets
checkpoint-status |  |  | checkpoint | 2.3 - Geogrid Compliance
label | 1f9a9807-72e0-5d38-910c-e3f957473776 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a80489bd-7df2-52cf-b710-daf00b71be35 |  | note | Detail - All rolls bar codes are to be collected and attached to the rest of the QA Documentation
label | 153b607c-87c2-5e2d-bfd7-047a9d825fc4 |  | note | Frequency - Prior to commencement
label | c7fdf94d-664c-5d95-8e9f-6f5e4db8f8f1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 1bb75949-941a-59b3-b860-ce5f289d56cd |  | note | Conformance Criteria - Compliant with Tensar Triax TX160 or equivalent
label | 97fadf55-4ddc-5b35-a13e-9432ac59e1c8 |  | note | Records - Delivery dockets, packing slips, invoices
checkpoint-status |  |  | checkpoint | 2.4 - Safety Barrier Compliance
label | 9be1937f-b06d-5492-8526-16250101bda7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 54ec98e2-8f46-5b51-b19f-d45e18f59f8d |  | note | Detail - Documentation from the supplier that proves the safety complies with Section 5 of the project Specification
label | 13e76bbf-9684-5541-95d7-7cf0b9951f89 |  | note | Frequency - Prior to commencement
label | e31e7012-4b6b-598c-9f91-03a08d55d258 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 393e36b0-0d58-536e-8211-d09130df4b6d |  | note | Conformance Criteria - Section 5 of the Project Specification
label | 3101145c-8d44-5d3a-bb97-a8f5224126be |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Ground Beam Construction
checkpoint-status |  |  | checkpoint | 3.2 - Install Reinforcement Steel
label | 87797773-7e11-5d6d-b132-a25a9468018b |  | note | ACTION (Hold, Monitor, Witness) - H
label | e96b45dc-256d-579b-939c-929a2cd77ba6 |  | note | Detail - Reinforcing steel to have minimum 50mm cover
label | 8f1a7f4d-cff1-5c6d-bae8-7d275c7711d2 |  | note | Frequency - During construction
label | 6dc782f0-1569-5072-96b9-7c39d5b170bf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 977163e1-197b-5fb7-a0d3-2c728e454b0a |  | note | Conformance Criteria - Reinforcing steel placed as per design. No concrete to be poured until formwork and reinforcement approved by CPS Engineer
label | b9c461c6-277e-5fb9-9dcb-94060e5ece0f |  | note | Records - CS-4040 Concrete Inspection Record, Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Concrete Pouring
label | 9d7363ac-7404-5b0e-99a6-ab253471b2a4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b9509732-9e15-5873-a157-481ab183f200 |  | note | Detail - Cast-in bracket as per NZTA B5
label | fb6a2a4f-a308-5fe4-a229-8d8414387aa2 |  | note | Frequency - During construction
label | ed42170e-b7dd-509c-b508-6162502e420c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 75df6793-2a86-5b9c-9add-b4468aa9c28b |  | note | Conformance Criteria - As per design, Concrete dispatch dockets
label | 0f6501d1-ba97-554c-ab3e-4268bce85c76 |  | note | Records - CS-4040. Concrete Inspection Record, Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Concrete Testing
label | d477f10f-d033-5536-9af9-b0cf4ec2bbd9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e7f6f563-d05b-531d-ab25-810d922c2537 |  | note | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores. Concrete slump and spread test reports.
label | 1ffb37c6-b41f-5587-8537-cbb28eee41cf |  | note | Frequency - After Construction
label | e73ced51-e40d-5de2-b1a7-7db264938cf0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | ee857aac-f524-5ec2-bbff-b63fb6ead987 |  | note | Conformance Criteria -
label | 89ff1823-35a4-5519-878a-fa185dce591d |  | note | Records - Test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Geogrid
label | b973aeb9-682e-5b10-80d6-d407ed1f2d1e |  | note | ACTION (Hold, Monitor, Witness) - W
label | 442103e1-5e57-52f9-a72b-38d40409b693 |  | note | Detail - 1.9m wide strip laid evenly across beam and adjacent ground
label | 8e9bb300-c345-5425-b162-fb052f5a48a2 |  | note | Frequency - During construction
label | 88d5c86d-d55b-5566-9a0e-8b759f4ca267 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 51a66eab-3c4d-5d95-b2d9-0b6c853effb3 |  | note | Conformance Criteria - Geogrid at minimum 65mm above top of ground beam
label | 6adc35ec-0d4f-5ba3-be6a-23a6d27fa786 |  | note | Records - Photos
checkpoint-group |  |  | section | 4 - Barrier Construction
checkpoint-status |  |  | checkpoint | 4.1 - Guardrail Installation
label | e10197ea-2b06-5095-add8-bc85ebc7e63b |  | note | ACTION (Hold, Monitor, Witness) - W
label | df60fd46-10d7-532c-954d-5b7e282640cc |  | note | Detail - Install guardrail as per contractors methodology
label | a59a5396-88fd-54d9-9a4f-722566ea7534 |  | note | Frequency - During installation
label | b340d40d-b0a4-5347-aceb-a89ea0e4f583 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 76e28e13-4b50-55b3-ab7e-0d21a5c5ccbe |  | note | Conformance Criteria - Nominally max 3 days, once concrete is hard enough. TBC with the guardrail contractor.
label | b68949ab-c64c-5329-b06c-0c3e290c172d |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 4.2 - RSHDS Inspection
label | 8c8b30d0-a886-5582-872d-f4a78fbd374d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2a5bc6c0-4b85-5dd2-a40a-065f230d8d85 |  | note | Detail - Inspection of constructed safety barrier to confirm compliance with NZTA M23 and the IFC Drawings
label | 426e4140-4bc6-58ca-9132-9d6b8857f62d |  | note | Frequency - At completion of Safety Barrier Installation
label | d1bd57f0-650e-5072-9342-1640a19cbbd8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 87808cfb-b95f-5c41-9ce1-d7edd6ebfb9b |  | note | Conformance Criteria -
label | fcb7aa1d-7bd0-588d-9642-5fa56f1b181d |  | note | Records - RSHDS Audit Form
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5 - Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 5.1 - Final Walkover (Snags)
label | 1ec01b00-f506-5d7b-9a46-6e8106b4749a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1583b1b1-5afc-5be2-be31-342bb4a25f4c |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | ec9d3ee8-adf0-5cf5-8faf-cc055de75af2 |  | note | Frequency - At the completion of the Lot of work
label | acbb8d84-893c-550d-91a1-a5abfdd49e0d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | 8925842e-f0cc-5a3d-ad99-54a8a72ca936 |  | note | Conformance Criteria - Completed report with Snag List
label | 8fce97f2-50d3-5a16-87c7-8fb3a6a7a4d4 |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.2 - Survey As-builts
label | 805417a1-c248-5d7e-bfe9-1d34d5cc49be |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5ddefbe6-b388-5a15-b654-c1b6f656b058 |  | note | Detail - Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided.
label | 8471dba5-9a59-516c-bfa9-d54f95cdd854 |  | note | Frequency - At the completion of the Lot of work
label | 6fb89fe4-7c5e-525b-bd73-426306a69dfc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 9d1f7821-674f-563b-8c07-e3ee1d5a9ec9 |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | 65d9eabe-4f76-58f9-aaee-de534e04fe69 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.3 - Quality Assurance Deliverables
label | cc827e45-5de3-5f90-9358-46b72efc8c99 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 17a266d8-48f4-51e0-94b9-e67bd0cfa444 |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS. All NCRs and RFIs are closed and included with the Handover QA file.
label | 4f5ad46a-f4e9-5e06-b47a-061baef6ecde |  | note | Frequency - At the completion of the Lot of work
label | c0a38b7b-ecd0-5610-961c-a4497f7773f4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 1c8a90ad-da53-50d0-b67e-5b0184bccc9a |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 765d1ab1-b61d-51e2-986f-3e412df62c1c |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 5.4 - Final Approvals
label | 73a122dd-dfd0-56a2-b641-d4deefe9940f |  | note | ACTION (Hold, Monitor, Witness) - H
label | bc858959-1e65-564c-b4d0-786ffe1654d5 |  | note | Detail - Signoffs by Project Manager, Quality Manager, CPS Manager
label | dd9ac091-4419-523a-86b3-f21ef6d2c24e |  | note | Frequency - At the completion of the Lot of work
label | 20128416-f935-56b1-b42f-9a06a929fbff |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 14bf7d46-06c0-5fb5-aa55-b7fa86580df5 |  | note | Conformance Criteria - Ensure all parties have signed and approved ITP
label | 552b9390-306e-5593-ba47-e4082b05059e |  | note | Records - Signatures
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - G1202A - Waikaretaheke Overslip #3 - Network Drainage | itp |  |  |  | Yes | ITP - G1202A - Waikaretaheke Overslip #3 - Network Drainage | 8b5fb8c7-215e-4f94-ab74-7c9c1c9a646a
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 1fda3bc9-409b-537d-88a9-49b339b5c600 |  | textbox | CPS Eng.
text | a4c55642-a82f-5e18-b444-d59bb685fbc8 |  | textbox | Site Engineer
text | 46cdcef9-5ed5-5837-b79f-bf96617a116e |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Locate existing services by hand digging/hydro excavation
label | cd2c6db2-15dc-5eae-b899-b9e19fdc4cfa |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8b95d867-c22b-537e-8593-f5bd83924ef8 |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging/ hydro excavation
label | 5540c231-0984-5a22-a54c-6143e9589927 |  | note | Frequency - Prior to commencement
label | a4aa2c7f-c5f5-5bb8-a2b7-afbead17c450 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | 7af0a82e-6370-5abf-9c40-27fddf11e52f |  | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As-built all services
label | 9623d5d3-772c-5b65-9be3-b7dbbb7f31a7 |  | note | Records - As-built Drawings Doc. Review
checkpoint-status |  |  | checkpoint | 2 - Trenching and Excavation
label | 692260d6-02f6-5190-87fe-88dc43ecbd15 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 787bd98d-b991-5df5-9ffe-ea12f2ccb966 |  | note | Detail - Inspect trench profile and ensure it is correct to minimum drainage standards
label | 4c1162ee-0003-5371-b4b2-c7e80d826ce6 |  | note | Frequency - Daily
label | 78d2d16b-689e-5c08-927e-8ea094b8039c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | a7ee3182-9052-5a7e-a96b-6d8132669962 |  | note | Conformance Criteria - Line and level is correct
label | 5ae01b46-057e-52c3-8470-345a05d0cffa |  | note | Records - CS-4025 Drainage Line Record Check Sheet
checkpoint-status |  |  | checkpoint | 3 - Trenching and Excavation
label | d12d8c9a-bfea-57f8-8df7-e70c130704db |  | note | ACTION (Hold, Monitor, Witness) - W
label | 55f6e185-31b8-592e-bd80-fc8ecfad5146 |  | note | Detail - Ensure trench width is sufficient to provide enough space on either side of the pipe
label | 2d6098be-5621-5f75-9ee5-7c6ca34a9ce5 |  | note | Frequency - Daily
label | de948657-613c-5c17-9e28-077e580ac465 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | f80de7bd-162a-5817-87b6-85cd516802a4 |  | note | Conformance Criteria - D/6 or 150mm whichever is greater on either side of the pipe
label | a813cddd-3dba-5870-8b07-7631f6b1cb11 |  | note | Records - CS-4025 Drainage Line Record Check Sheet
checkpoint-status |  |  | checkpoint | 4 - Foundation Compliance
label | af79596d-3466-5bee-b499-63b0040fef15 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 52320a71-3bb0-5ff5-bbf7-dfa4930fc52f |  | note | Detail - Test formation level on completion of excavation to check if undercut required
label | 3064f3f2-a357-5493-bef8-f6e3805d46da |  | note | Frequency - One test per 20 linear metres
label | 876e493f-e6d3-5d53-8183-70c3d4e221df |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
label | 1a31888e-f5fa-543d-890e-19d54e7363b8 |  | note | Conformance Criteria - If CBR is less than 50kPa , advise Engineer
label | 6073bcfb-a71f-5c96-b129-47b895c052b4 |  | note | Records - Scala Record
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Pipe Bedding Material Compliance
label | 5a1e06ad-8a31-5760-8cda-a8aa6947c289 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0aa17af5-4296-53f5-af73-9a4a3ee4f64d |  | note | Detail - Material to meet specifications dependant on material type selected
label | b5d45428-141b-5c12-95d9-64182e4f57a5 |  | note | Frequency - Each material used
label | 64a29b7c-b8ad-5bb8-ba03-1f078a30da76 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 4c603003-80a1-587f-a513-6e66f2a77092 |  | note | Conformance Criteria - Bedding material
label | e95966a0-cf8e-5821-b497-fed510b1b82b |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Bedding
label | 0923c592-8c9b-5c19-8ace-643c7bbc2e03 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 971b623d-ff52-58bb-877e-a15ea822fc70 |  | note | Detail - Bedding - Ensure correct thickness of bedding is placed and compacted
label | a0d5e98a-8120-5b8c-b47d-cd8d465ea61c |  | note | Frequency - Daily
label | 2bd97e56-1331-5a98-abc1-af10be06afac |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | 23c99cbe-d646-5c5b-81b8-eb37bfb4f231 |  | note | Conformance Criteria - 150 mm thick bedding for all mm dia pipe
label | e4f664f8-cd7a-5bf4-a29c-aa43993c9105 |  | note | Records - CS-4025 Drainage Line Record Check Sheet
checkpoint-status |  |  | checkpoint | 8 - Pipes and Precast Units
label | c8d7b0a8-aed9-5b76-9ab6-c639a0e611ca |  | note | ACTION (Hold, Monitor, Witness) - W
label | 47442f82-6f98-5005-b3cd-618440e9783e |  | note | Detail - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | d56d6a65-2b8e-531e-a128-231f83098c42 |  | note | Frequency - Per pipe
label | 7d3d1e4b-a863-5590-a434-3a6ebd2c7b5d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | 077f1059-b4bc-53ab-9164-c2fb73543168 |  | note | Conformance Criteria - Pipe - Diameter & Class, Wingwalls, Manholes, Cesspits etc.
label | cb8e96f7-5adc-5a44-96b6-806afeee879a |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 9 - Pipe Laying
label | 3330c6a0-1b96-5f7f-9cb2-d583921b9f01 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6b3b8249-8ced-5be9-9277-6ae0c5bcbc3e |  | note | Detail - Pipe Laying - as only replacing section on outlet of existing pipe, grade is to follow existing levels
label | 6ca009cc-e19f-566b-9e6e-f0358b0082c4 |  | note | Frequency - Prior to backfilling
label | c652ace6-ee73-5013-88d1-9f7bc1f62ad3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | f7d9663a-a5a6-5661-8563-3f375fd07b57 |  | note | Conformance Criteria - Invert level following pre-existing grade
label | 2eda8e12-7885-54e1-a506-01b0f888d74a |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 10 - Pipe Laying
label | a60fb744-3c14-544c-be60-e56b1754ceab |  | note | ACTION (Hold, Monitor, Witness) - H
label | b04b9d2b-aa0f-5eb1-917a-0418f0453bdd |  | note | Detail - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | e790ebcf-36ab-56cc-8a39-4dd55a4c8472 |  | note | Frequency - Prior to backfilling
label | b65eee45-d2dd-5987-bb67-263582ad3410 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | 123f5ff3-fd23-546a-8492-9397c5305041 |  | note | Conformance Criteria - No defects/ gaps / pipes are aligned correctly
label | 2991f685-ce14-5b64-bda5-e77b55d6bdb5 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Pipe Backfill Compliance
label | 2686a1a2-7d72-5a81-bb00-12d0dcfc184a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 34f14952-eb58-57f1-a668-86d57cc3703f |  | note | Detail - Material to meet specifications dependant on material type selected
label | 8b54f006-9921-5fe3-8a21-e7df1503230a |  | note | Frequency - Each material used
label | b05cf48e-feb7-59d8-8286-d2b2aee46c1c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | bb23f186-77b2-58ff-b30c-4c2447f70943 |  | note | Conformance Criteria - Compliance with requirements from Specifications
label | 634e2ddd-13c7-5ec7-9e59-b53431a598cd |  | note | Records - CS-4025 Drainage Line Record Check Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Pipe Backfill Compliance
label | d18fc675-2e61-5c68-9700-72cddc9e1dd0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5f72e963-f721-5e6c-972d-ba61bd451a4c |  | note | Detail - Backfill Construction Material
label | 74221a0f-4255-5faa-85f1-67cb2a043d2f |  | note | Frequency - 1 test per 50m
label | 85c48d26-8d69-5f8f-b58d-2623cf581b80 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 19cba11c-57b5-520f-8fe2-79023e92f412 |  | note | Conformance Criteria - CLEAN GRADED GRANULAR AGGREGATE AND HAVE BROKEN FACES AP65
label | e12bfbcc-f9f6-5768-97a7-7f70c2fcd43a |  | note | Records - Lab Test Report
checkpoint-status |  |  | checkpoint | 13 - Backfilling
label | 2b48186c-3bd6-55f3-9296-d9e9b4b53ff0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c5bc1d40-fef6-5eb9-87ff-ed860cebb652 |  | note | Detail - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms. Remainder of backfill to be done with excavated material.
label | 87bfd999-ca7a-5527-8130-2a913ee0fa9a |  | note | Frequency - 1 test per 20 m length of trench per 300mm lift
label | 8884610c-ccae-5374-949a-15ebb1e8cbdc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | d6c2f02b-9fd2-5c18-916e-4fa2c1e4ef47 |  | note | Conformance Criteria - 97% (under carriageway) or 95% (under berm) of MDD or Clegg equivalent
label | 98e3c371-25c1-58e3-be0d-f0c6016857ae |  | note | Records - Clegg or NDM Test Results
checkpoint-status |  |  | checkpoint | 14 - Quality Assurance deliverables
label | e867cee8-9be4-5e17-b347-8ffba9f87fbb |  | note | ACTION (Hold, Monitor, Witness) - W
label | ce0634ee-4c05-51c5-a2fb-80dc8ea80a78 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 8bb73d9c-9fe2-5d74-b086-a7f1110438b4 |  | note | Frequency - At completion of Lot
label | 076100cb-fff6-53b2-bbe3-f82f5c44f1f2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 1aa5aff7-319e-5f24-a6c7-d888c8c7fb65 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | ff026c5e-0ce2-5b01-bf53-ddd4ae239f73 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 15 - Completion Sign Off From Fields Below
label | d3f3075f-c66b-59a7-a44d-8b44645547f0 |  | note | Records - Signatures
checklist-flat |  |  | checklist | CS-4000 - 1M Scala Worksheet |  |  |  |  | Yes | CS-4000 - 1M Scala Worksheet | 8b6868d5-75af-44a5-967a-4701141bb533
checkpoint-no-status |  |  | checkpoint | 1M Scala Worksheet
text | 65b4726a-e597-50e6-a2bb-0fde9f35683b |  | textbox | CH & Offset:
text | 91c51beb-949a-5a18-abc5-e5a2fe1f7160 |  | textbox | Date:
text | 3d0be7b0-7869-5fbb-a5ea-5c9344e2ad7b |  | textbox | Start Depth (mm):
checkpoint-status |  |  | checkpoint | Depth [mm] - 0-100
text | 96468306-f9c9-5fac-930c-a32d1b9a459b |  | textbox | No. of Blows
text | 14b6b6fe-e8e7-5a16-8e34-5d6d920fef57 |  | textbox | mm / blow
text | 324dbcaf-9518-5e72-97ef-27b8feb4c601 |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 100-200
text | 36fa8622-a5d8-5e8f-891a-41fe82bfa9a9 |  | textbox | No. of Blows
text | 974b3642-4e7c-5a19-abe0-d10b6ca2e88a |  | textbox | mm / blow
text | 36fe9db2-4e57-5716-a651-eda533ceb0ce |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 200-300
text | af1735f7-d667-5758-b624-77a576139a34 |  | textbox | No. of Blows
text | 53fe5e73-73e3-5df0-bfcd-1c0fba1b93fb |  | textbox | mm / blow
text | dbd066f0-1be0-507c-a670-d205a3c31c58 |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 300-400
text | ec014790-cabd-5494-90d6-207f7681edd1 |  | textbox | No. of Blows
text | 0eea0f61-7705-5b07-962d-d08100a21b2e |  | textbox | mm / blow
text | dac1cfe0-72f1-59a3-ae95-c4ca2572441b |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 400-500
text | a1f3293f-6e0d-56ff-96de-8b193a40e733 |  | textbox | No. of Blows
text | ca3752be-90c2-5e62-927a-5aaa263414be |  | textbox | mm / blow
text | 8baf975b-edf4-5905-ab45-8b7451a41f5b |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 500-600
text | 7e76c82d-f021-52b8-8e83-96e901a35a99 |  | textbox | No. of Blows
text | 63e0a230-dc72-58cd-bd60-6270bbcc0cd9 |  | textbox | mm / blow
text | a6d0cbf7-d1ec-5f13-b1e9-82b5e3e78073 |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 600-700
text | 6ea485af-139a-5864-b253-fa78f0cfdc3e |  | textbox | No. of Blows
text | 721cfca9-c8ea-544e-ba6b-996154681473 |  | textbox | mm / blow
text | 9708fe6c-7a7b-5a3c-998b-5595950f90de |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 700-800
text | a4d83d97-46c1-5b84-96ae-009c7052d906 |  | textbox | No. of Blows
text | 9db6258a-d3a6-580d-bb27-66a77cb80d04 |  | textbox | mm / blow
text | edecd32d-5f55-5cca-8368-cc8b50bb1989 |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 800-900
text | c33d1d69-e051-5f4e-8588-9fe5035b375f |  | textbox | No. of Blows
text | acfcbd32-09ae-52e0-a634-90bba1d5f7f9 |  | textbox | mm / blow
text | 08c44241-b040-5d75-97d6-33d256b21b42 |  | textbox | CBR
checkpoint-status |  |  | checkpoint | Depth [mm] - 900-1000
text | 33d1a1bd-492a-5984-b178-14d956b08bb7 |  | textbox | No. of Blows
text | 386711de-5fbf-5c52-aaa3-c4d85e7c1156 |  | textbox | mm / blow
text | 573d6ea1-fbf2-5f6a-a72f-9550cd1fcec2 |  | textbox | CBR
checkpoint-no-status |  |  | checkpoint | Tested by:
text | 010d7737-72ac-5535-bf46-63fd73757ee2 |  | textbox | Tested by:
checkpoint-no-status |  |  | checkpoint | Checked by:
text | f011b290-333e-5500-846b-b4a545fc59f6 |  | textbox | Checked by:
checklist-flat |  |  | checklist | ITP - Mangahuini Sheet Pile Wall - F3002G - Rock Armouring | itp |  |  |  | Yes | ITP - Mangahuini Sheet Pile Wall - F3002G - Rock Armouring | 8df91791-bce1-4754-87d3-02e9ead54bc7
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 4bef4597-7959-591f-8908-acef648caf0a |  | textbox | CPS Eng.
text | b4c5798e-1d4e-5313-be62-365318144750 |  | textbox | Site Engineer
text | 6b073cb6-7cf8-5333-9f35-237e567de475 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 453387c9-be0d-5f93-8652-0103d677f030 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1912eac5-97b3-578d-913c-7ed88814bb6b |  | note | Detail - Set out extents and check against design drawings
label | cdfb859c-4c04-5300-ad90-ad799e6252d8 |  | note | Frequency - Prior to commencement
label | 0668ccf3-6712-5ff7-8b7b-1f0bef549313 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 7b9145e4-59b8-5cfc-a46d-fa9381aba409 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | aace3aad-a4da-51bb-83f5-02e65a7eddbb |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Geotextile material
label | 2c925392-a7e2-5f82-99b7-1d3ceb0d855c |  | note | ACTION (Hold, Monitor, Witness) - W
label | c85a242b-d81d-5c5b-8c65-048517d60a7c |  | note | Detail - Geotextile filter fabric to be compliant with Bidim A49 or similar approved
label | 1ec1d88f-e134-597d-bb67-253be488cfa7 |  | note | Frequency - Prior to commencement of placement
label | de453872-89c9-507a-8a84-f469968af6c4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 71f56043-c40a-57c7-876e-843c190ac8c4 |  | note | Conformance Criteria - The material shall be non-woven geotextile and comply with TNZ F/7: 2003 meeting filtration class 1, strength class E requirements.
label | 80eda5e2-bfa9-551f-bbef-1235115167c5 |  | note | Records - Material certificate(s), Photo's
checkpoint-status |  |  | checkpoint | 3 - Rip Rap Grading
label | 47ab396f-99bf-5c6f-9610-774c13e693d7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 203dc1e5-b8d9-5e6b-b72c-4a3cc36d440b |  | note | Detail - Rock Armouring Construction Material compliant with Rock Rip Rap Grading tableas per Typical Sections Views sheet S03 Rev 1
label | 7ecfae93-1a27-5cc4-864a-983d287fe000 |  | note | Frequency - 1 test per 75m3
label | 48644135-abd0-5a37-894c-91960a8f37b8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing, Visual inspection
label | 325ddbbe-c3ae-5491-9dbc-202c04471551 |  | note | Conformance Criteria - 100% smaller than 2400Kg, 20% greater than 1000Kgs,50% greater than 600kgs 80% greater than 175Kgs. Stone shape shall be as close as possible to cubical. Long, thin, slabby shapes are unacceptable.
label | 843c1e74-a3ab-5568-a54f-b21fb9cc1a45 |  | note | Records - Lab Test Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Geotextile Filter fabric installation (1)
label | 68d4745b-0e75-5608-b622-df12be94a0a4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 40a06619-9311-50a6-a8bd-4e652ccec76c |  | note | Detail - Filter fabric shall be placed under rock and against the end faces of the excavation as per design/drawings
label | 8b500198-fe37-5b32-8d46-bf7bfe2bcba3 |  | note | Frequency - Prior to placing rock fill
label | bbf91ec3-a66d-5f44-b274-6626fbebb8a7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | d971a8a0-84c1-532b-9e5b-4ee3a55fa1ed |  | note | Conformance Criteria - Placement of fabric shall be as per design shown on Typical Sections Views sheet S03 Rev 1 and be laid/overlapped as per manufacturers recommendations
label | 903f6017-d532-5203-9e3a-8e509aeb74b5 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4 - Geotextile Filter fabric installation (2)
label | 6482a52b-f06e-5a78-9395-3219e7e50ef5 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 0b42fe91-7f74-5d1b-b65d-72252c42075a |  | note | Detail - The Contractor shall take care not to damage the fabric during installation. Any tears shall be repaired at the Contractors expense by placing additional fabric over the damaged area
label | 4a4a9f05-b98c-51e9-bd12-127ea70da7af |  | note | Frequency - Pre/ During install
label | b0f34020-e966-5dbe-84b7-f36fb8bbacfd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 6d625eb9-dc2c-5eba-903b-467e88facb95 |  | note | Conformance Criteria - tears shall be repaired by contractor
label | b8de44ce-f607-5d4a-9c8c-b39a1c2783ed |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 5 - Armour/Riprap Placement
label | 47788299-6c60-58c3-890e-213c48844cac |  | note | ACTION (Hold, Monitor, Witness) - H
label | bfa23fae-95c9-5e69-a11a-49ebf31051a2 |  | note | Detail - Ensure that rock material is placed in such a manner to minimise segregation. Rock is not to be end dumped or allowed to fall from an appreciable height. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material
label | 340efce0-892c-5035-a2fa-d612c6989c8a |  | note | Frequency - Daily visual check
label | e90bff94-06cd-530d-8a52-a7f551449df2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | adc8b13b-8380-5047-b811-9d9ed2cae573 |  | note | Conformance Criteria - As per design/drawings. Rock toe construction to be sighted and approved by CPS Engineer
label | 9f40ce74-5d2f-5791-98af-1c323bd499ca |  | note | Records - Photo's, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - As-built Survey
label | 72a1ac89-f12d-56e9-8f1f-895cd507a1f3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0138de6a-0035-5822-b6d1-5ac12a37453f |  | note | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
label | d61373af-5602-58b1-85a8-f52e8c0cdee0 |  | note | Frequency - Prior to placing topsoil/pavement/ finished surfaces
label | 626b657e-5a90-5787-a728-bd5b76e6463a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | e432ef22-b811-5c52-aa62-55c9a0873ce3 |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | 0af3194f-4691-558f-88e8-d35d643bcf6e |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Quality Assurance deliverables
label | 0b7a2d63-5dce-5151-926f-86229e23e230 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b8180eec-a38f-5653-a96a-0c4cb0e8b6a3 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 2ae03511-18e2-537c-890f-d4c90dfa7dfc |  | note | Frequency - At completion of Lot
label | 4e7f8844-5a62-5432-b3bf-c2a9b867b80a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | cadaa7dc-e720-5ce2-8438-da690c074409 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 8997f693-a76c-5087-82d2-23cd839f9b5f |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 10 - Completion Sign Off From Fields Below
label | f64bc4b6-f807-502f-88ae-28b23cda1132 |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | CS-4106 - Traffic Sign Foundation Record |  |  |  |  | Yes | CS-4106 - Traffic Sign Foundation Record | 8f398791-a007-4c46-87a1-4ffa361df1cc
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | cc0ae279-5d41-57eb-a608-cd38bc5d2ce1 |  | textbox | Project No.
text | dd6a7260-9243-5e8c-a9a5-687e26da94f0 |  | textbox | Drawing No:
text | 4f95c3ed-380d-56a3-b97d-0f6ea5f20423 |  | textbox | Sign No:
checkpoint-group |  |  | section | Sign(s) Location
checkpoint-status |  |  | checkpoint | Check sight distances
text | 89eec98d-bac6-5296-a602-e6b483ca9853 |  | textbox | Initials:
date | b8d13f16-d539-5788-9416-d4cfdf2ea3a1 |  | date | Date:
label | a7444925-93d7-5856-977c-287f4bd656d0 |  | note | Comments: Ensure the sign will be in a location where drivers can see it clearly without blocking views from driveways, other roads etc.
checkpoint-status |  |  | checkpoint | Check Lateral Distance
text | 21f06716-dce1-5806-95e6-be33d28272b3 |  | textbox | Initials:
date | afefb919-4194-5faa-be9b-09a0b31c6c95 |  | date | Date:
label | 02e8a1e0-6ec1-5b51-931d-4af9f4907c8b |  | note | Comments: Ground mounted signs shall be located at least 600mm clear of the outer edge of shoulder, line of edge marker posts or face of road safety barrier; and be between 2-5m clear of the nearest traffic lane edge line
label | 5f8a0004-afde-52f7-8e1f-2d35d6c4a190 |  | note | ○ Large ground mounted signs shall be located a minimum of 1m clear of the outer edge of a motorway or expressway shoulder, or 4m from the nearest traffic lane edge line, whichever is the greater, or 1m behind the face of a road safety barrier, or 1m behind the face of a kerb, or 1m clear of the outer edge of a ramp shoulder
checkpoint-status |  |  | checkpoint | Check location of existing services, if there is a clash with the new sign location seek approval from CPS Engineer to move the sign to a new location
text | af9378ca-2830-522a-abee-af1d982c4957 |  | textbox | Initials:
date | 45dd9a51-347b-5e9b-a0b9-d63981f7408d |  | date | Date:
text | fd7341e7-eefe-524b-b383-f14546e6bbcf |  | textbox | Comments: OFI # |  |  | (if needed)
checkpoint-group |  |  | section | Sign(s) Foundation
checkpoint-status |  |  | checkpoint | Expose any existing services by potholing
text | f8a3373e-2b0a-55d9-bf0e-016dcd8012c8 |  | textbox | Initials:
date | 08fd0230-9866-5bd5-af2d-9b18f24695ad |  | date | Date:
checkpoint-status |  |  | checkpoint | Confirm Type of Foundation(s) i.e. Ground sockets, Breaksafe etc.
text | d7b675b3-8a1c-5713-875c-92368a332829 |  | textbox | Initials:
date | 2304407a-e8db-5b0f-bf1a-77bb740da3e3 |  | date | Date:
text | 72597bd8-cc68-537d-a175-ac2341d7cb23 |  | textbox | Comments: Type(s) =
checkpoint-status |  |  | checkpoint | Confirm depth and diameter required for augering
text | b38dcd77-e3e1-52dc-ac80-0fd90cf38266 |  | textbox | Initials:
date | 553b1c11-e70e-5a3f-817f-14f696e02195 |  | date | Date:
label | 1f1ddd1b-ec5e-57d5-89ec-847037bb5b48 |  | note | Comments:
text | e98577a7-bec8-5172-98a1-84a2d48149ba |  | textbox | ○ Depth(s) =
text | 5888ce61-e092-5a1f-a570-1a9e33e1aee6 |  | textbox | ○ Diameter(s) =
checkpoint-status |  |  | checkpoint | Mark out post(s) location(s) remembering lateral distance (above) and sign orientation
text | 1ca1af2e-3775-5e09-8101-e753c8f6e301 |  | textbox | Initials:
date | 745cc154-a0ca-5d97-9098-e4a82ded676a |  | date | Date:
label | 998cc01c-0cb9-5505-a13d-b73d8740f7ad |  | note | Comments: Sign orientation should be turned about 5 degrees away from the approaching drivers line of sight, this varies depending on the location on site. This is to help reduce possible specular reflection from reflectorised sign surfaces. If there is still specular reflection on a straight when the sign is turned about 5 degrees away from the drivers’ line of sight, then it shall be increased to a maximum of 10 degrees.
checkpoint-group |  |  | section | Installing Foundation(s)
checkpoint-status |  |  | checkpoint | Install the foundation(s), Check the correct type and sized foundation is being installed
text | 377ae775-d362-5174-b37d-c302f5109fa6 |  | textbox | Initials:
date | 7d3e8fdc-de5f-5b1e-9213-cdef77f7c48a |  | date | Date:
label | 5eb5c657-a283-5d8a-85ba-722def0b6a9b |  | note | Comments: E.g. Ground socket diameter and length etc.
checkpoint-status |  |  | checkpoint | Check the location, level and plumbness of foundation(s) prior to pouring concrete
text | 4acd469b-512d-5cdf-8d28-0e60bea6ccbb |  | textbox | Initials:
date | 9a3c929b-d5b6-5e99-99b5-b565d3b5508a |  | date | Date:
checkpoint-status |  |  | checkpoint | Check the correct distance between foundations (for 2 post signs)
text | b21fcbf3-c948-55e0-b090-57a9f2fc669f |  | textbox | Initials:
date | c8ef3345-acdc-542c-937b-1e0d4c117350 |  | date | Date:
checkpoint-status |  |  | checkpoint | Check the height from final ground level (FGL) to top of foundation(s)
text | d503a838-2653-5bd0-bc3d-9c7891c8b617 |  | textbox | Initials:
date | e239e9b6-b058-51a6-9f75-7a23f0ed438f |  | date | Date:
checkpoint-status |  |  | checkpoint | Check there is equal cover around the foundation(s) prior to pouring concrete
text | 2d9586ea-5217-598c-95ef-33c37be273ef |  | textbox | Initials:
date | 2a5fd66a-06ab-5b5e-a455-1a30ed95d071 |  | date | Date:
checkpoint-status |  |  | checkpoint | Order concrete, ensure correct mix delivered, correct slump, concrete vibrated, dockets collected and concrete cylinders taken (1 test per group/lot of Signage posts)
text | c87002aa-6247-5856-a98b-d863678edb4d |  | textbox | Initials:
date | 12420f7d-1e50-58c7-973d-c9b1bbb75861 |  | date | Date:
text | 09ed4ca8-8b30-546e-bce9-e6d113c59522 |  | textbox | Comments: Concrete strength ordered = |  |  | MPa
checkpoint-status |  |  | checkpoint | Pour concrete to top of final ground level and wash off any concrete splashed onto the foundation(s)
text | 83b83e02-bf5e-5580-8817-f9a0b5077c24 |  | textbox | Initials:
date | f8233ca6-1ef4-59ac-8593-f93483c1c7a5 |  | date | Date:
checkpoint-status |  |  | checkpoint | At the completion of the concrete pour check the foundation location, level, plumbness and height from FGL as this may have moved during the concrete pour
text | aee237fa-fb62-590a-a493-cf0a556bb13c |  | textbox | Initials:
date | 0bb9a6ed-bd14-508b-83a5-916dd40e0780 |  | date | Date:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | dea22028-bd37-5839-be8e-d763bb6a353c |  | note | Position: Site Engineer
text | 9cd68d30-9339-5824-b03d-3a6d94c72884 |  | textbox | Site Engineer - Name:
date | 97deca2f-8acd-5e14-ba1d-4e0abdfcc558 |  | date | Site Engineer - Date:
label | 44592d9d-4e6e-5fcc-a7cd-0214b0c98076 |  | note | Position: CPS Engineer
text | 22cf4bbe-15fd-569d-9a67-159a276352f7 |  | textbox | CPS Engineer - Name:
date | 2a186948-2021-5223-90eb-ebb2452c1ccc |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | CS-4098 - Bottom Driven Pile Card |  |  |  |  | Yes | CS-4098 - Bottom Driven Pile Card | 8f838a6d-fbe3-4e57-a7d9-850a9fefe2ba
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | e01a57ff-eab0-5667-b97a-ed734896820c |  | textbox | Project No.
text | 2c078e06-7953-5893-ba70-95407917f3eb |  | textbox | Pile Type:
text | 5c1381d0-7d4a-5bd0-b859-5a95edb408d0 |  | textbox | Yield Stress: |  |  | MPa
text | d4993cf8-83e3-543e-afe9-8b0c303c6ed0 |  | textbox | Capacity kN (calculated):
text | fe8347d8-24f0-5eab-8a6c-7540a7648f4e |  | textbox | Capacity kN (required):
text | 151916f8-74c6-5f72-a3e5-f3d3c6b00bac |  | textbox | Temporary Compression (C): |  |  | Mm measured
text | a5489048-6092-58b8-9715-657d9c23c878 |  | textbox | Set mm (measured):
text | 679010aa-ab28-5147-9c10-0e5e8771876d |  | textbox | Set mm (required):
text | c1a7e5d5-3e79-594d-9f72-88eaf294628a |  | textbox | Hammer (mass): |  |  | tonnes
text | 6e4bd1e4-a4c3-5e15-8a5f-e24d447dacf9 |  | textbox | Hammer (drop): |  |  | metres
text | 87347fd3-136f-5d63-bd09-88df9b3b910b |  | textbox | Hammer (Efficiency): |  |  | %
text | 7ce6655a-d6c5-56bf-ad8b-4e9c8014b9ed |  | textbox | RL top of Pile (1): |  |  | m
text | 40d694e9-a57a-5c34-99e9-d7fd3778b568 |  | textbox | RL top of Pile (2): |  |  | m
text | 0a3cfbc7-35fd-564e-b749-89098f37ae92 |  | textbox | Pile Length: |  |  | m
checkpoint-group |  |  | section | Pile Construction
checkpoint-status |  |  | checkpoint | Pre-Drive / Bore / Jet
date | f65542f4-e07d-5a51-bded-115dc831d38b |  | date | Date:
text | 09869ea4-c799-586a-b895-a783579121d8 |  | textbox | Start Time:
text | 4a504f87-c5d3-558c-a86e-70e43c073899 |  | textbox | Finish Time:
text | b2d51fb9-c232-5ed5-b1f2-65a43f61d116 |  | textbox | Hrs:
text | a900bffc-a1dd-5581-b5a6-5d72c263de07 |  | textbox | Conditions:
checkpoint-status |  |  | checkpoint | Drive No. 1
date | 88925610-8ef9-5431-bf04-278af2186f9d |  | date | Date:
text | 15a5f7e8-e6fe-5893-b55e-3f7e79026e03 |  | textbox | Start Time:
text | 89c12725-6625-5b4d-8a1a-aff864ca129f |  | textbox | Finish Time:
text | f8ac20f1-cbd7-515a-a9a3-eba301714c68 |  | textbox | Hrs:
text | 756e64a6-6ab7-5252-b447-043d48fd6b59 |  | textbox | Conditions:
checkpoint-status |  |  | checkpoint | Drive No. 2
date | eb79dff2-e399-5f46-bd84-cce25e45062c |  | date | Date:
text | 05671c8d-e1ec-5ae4-872f-a5b3989efd62 |  | textbox | Start Time:
text | d2851446-badb-5133-b2e3-680a38f2ef24 |  | textbox | Finish Time:
text | 7ed6451a-44b8-5600-a357-53199801910a |  | textbox | Hrs:
text | c6911dc3-229a-524b-880f-cbaf79f0411d |  | textbox | Conditions:
checkpoint-status |  |  | checkpoint | Drive No. 3
date | 87182d17-03b2-5c05-8a76-cacbe70b406b |  | date | Date:
text | 5d0ac2ac-705f-57e1-a1e6-7cdfb1a5114c |  | textbox | Start Time:
text | fa2fdb16-cc3c-57c8-a089-70c8e63045ed |  | textbox | Finish Time:
text | 8a427e5a-40cd-5ac2-a54f-c8e0d2f913b4 |  | textbox | Hrs:
text | 7b0614bf-308f-5dd3-9ada-209ff4dda76e |  | textbox | Conditions:
checkpoint-status |  |  | checkpoint | Re Drive:
date | f1489191-56e6-5867-8945-54dc3265b76b |  | date | Date:
text | f9d3bc3e-d09f-5bdd-9ee8-60c6dffddc8d |  | textbox | Start Time:
text | f72cdacf-dae0-5ef0-bbc1-2efdf07ac92b |  | textbox | Finish Time:
text | dc2fd469-aebe-50fd-aa09-9b178fa04161 |  | textbox | Hrs:
text | 9639eacb-1c8c-514b-a880-dbfbc377ba03 |  | textbox | Conditions:
checkpoint-group |  |  | section | Obstructions Encountered
checkpoint-status |  |  | checkpoint | Obstructions Encountered:
text | 814e9c50-2435-5010-9b84-e6fda9dfd945 |  | textbox | Type:
text | 09904912-a4a3-57df-8af2-2708cdd48def |  | textbox | Depth:
text | f42ca91d-0481-52f5-8e8b-44fc00d7cc8a |  | textbox | Action Taken:
checkpoint-group |  |  | section | Penetration
checkpoint-status |  |  | checkpoint | Penetration (1 m):
date | 4830d7c9-b26b-5068-932e-496e5e1cdd0b |  | date | Date:
text | c6bc0454-83af-5113-96fb-5f06ba4b60eb |  | textbox | Time:
text | aa9581e6-e299-5a82-aa50-102eb0b542e2 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (2 m):
date | db20bccd-1562-508a-94a9-39643e5ac8db |  | date | Date:
text | d796fb4a-58c6-555a-8ad9-01b2374cdda5 |  | textbox | Time:
text | 8ec8af45-1492-5b88-9db5-d42fd094acd9 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (3 m):
date | be658c40-9200-5fb4-8172-a6af27ca1d0f |  | date | Date:
text | 333db92d-4827-59d4-b71a-742cee74e869 |  | textbox | Time:
text | 9c723f7c-c9de-5d5b-a57e-bfe8a41c7f44 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (4 m):
date | 42b86a35-a173-555f-89e9-ce5bc79131f2 |  | date | Date:
text | d369f014-45ef-542f-86bc-617232a6dbbd |  | textbox | Time:
text | 4e2be4f8-3b0f-57bb-a32d-2ecbec5f97dc |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (5 m):
date | 41d1ff6d-4470-5957-a5ef-f2ecacfb87ee |  | date | Date:
text | 3d8cbf6c-0ce7-5735-84a1-3ba1d9dce9a2 |  | textbox | Time:
text | 41a7587a-84e5-55b4-9e2f-f5e2aa7c7f36 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (6 m):
date | 2f1f642c-ca79-5070-8a15-763bbfa77b05 |  | date | Date:
text | f7a9340e-ac88-555b-a4f3-70f4ef47076b |  | textbox | Time:
text | 85aa8259-7688-5c6f-b6ea-a486c7e39889 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (7 m):
date | c28aa738-dcf7-5a89-928e-25c436d0446f |  | date | Date:
text | f664a549-5dcf-51e8-b139-a2e9e1bb18e1 |  | textbox | Time:
text | 464ee841-69b7-53a2-80b5-e4ee1e71cf22 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (8 m):
date | 61bea284-204e-527a-91cd-710dd8580225 |  | date | Date:
text | 1b8bbec8-5d5a-5cdc-8339-b0d63a2f2ea5 |  | textbox | Time:
text | 716742d4-1d4a-5c31-b58a-65a305d147db |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (9 m):
date | 063d9560-a665-521c-8bd9-24a8481ab951 |  | date | Date:
text | 539c9498-912e-5516-b1a5-5df45da954ef |  | textbox | Time:
text | 708b5dba-485a-5df0-8dbe-2c934a771cf1 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (10 m):
date | 35f73df7-d740-5009-9bdc-bebdc2df586b |  | date | Date:
text | 47bcb7d2-75f8-5de7-ae5f-3cd9e5d6a808 |  | textbox | Time:
text | 2290302f-fa08-59d4-a8a7-436bceae26d1 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (11 m):
date | 4395781c-dfe1-5202-9b41-0660fb9ffdd2 |  | date | Date:
text | f71541ad-6cc9-585a-971c-f27139b7d9a6 |  | textbox | Time:
text | 429f1cf9-0da7-5773-8e25-6cf56616d948 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (12 m):
date | da0526f4-db37-5fbf-9ace-0c1c67ab3f6a |  | date | Date:
text | d7eac5ae-0922-5136-a7a3-ff8c854474c6 |  | textbox | Time:
text | c3e8901c-2cd9-5ff5-ac77-f3b863ffa094 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (13 m):
date | b9102896-a016-557b-b0f4-7fce3b41f43c |  | date | Date:
text | 2fbde354-bc86-56b5-a243-5780267d7c49 |  | textbox | Time:
text | 08f4d001-920a-5e2f-8e78-2d43a7910839 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (14 m):
date | b40be10a-6bed-54c6-af69-5d062795010c |  | date | Date:
text | 4e7932b6-e957-515d-90c7-e18424bac1f2 |  | textbox | Time:
text | a492adf0-c810-5bae-a45b-4160e216721b |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (15 m):
date | 4315f217-bddb-58d9-a211-75b9396a8d44 |  | date | Date:
text | 2fc7ea93-2084-5252-ba2e-3c667ec453e7 |  | textbox | Time:
text | b75e8344-3ddd-5f65-8ac2-2a583210150f |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (15.5 m):
date | be8ac0be-4302-58e1-83c6-6c27c0a70e45 |  | date | Date:
text | 368f631a-8836-5ca8-aad1-d8a55b0ee1a0 |  | textbox | Time:
text | 5bd90873-1c82-51ee-96e9-eeff3041ed8b |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (16 m):
date | d0e62d79-8808-5175-8768-da63e7fd154c |  | date | Date:
text | d1c0d8f1-7cc3-54a9-8c9a-a56c5b93cc3d |  | textbox | Time:
text | 7461ba30-e950-54d7-af52-5f2f70eeacf6 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (16.5 m):
date | e1333211-4d4d-58a6-863d-f031b09aca68 |  | date | Date:
text | 1d88c3be-0790-570f-935b-dba8d77d2e67 |  | textbox | Time:
text | 2d1bc558-e1aa-50ba-bff8-91f3a09a554e |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (17 m):
date | 0ca48846-d2aa-5e92-8c81-7380415d0aa3 |  | date | Date:
text | d0f332af-4819-51a1-a928-e4555501028e |  | textbox | Time:
text | 33cbfc17-db6d-5738-ab61-71ce9163fbc3 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (17.5 m):
date | d68b1057-3e62-5ba2-b43c-33077e3aa357 |  | date | Date:
text | 4f320acc-fddc-5bc2-82a0-3569956e0b14 |  | textbox | Time:
text | bd69c5e5-6c54-595e-9391-da45241008e8 |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | Penetration (18 m):
date | c23b89db-2a3b-5a6e-8b30-969a4e51d0a3 |  | date | Date:
text | 8084af44-b487-596c-ba69-4c77fcf82489 |  | textbox | Time:
text | d428830c-a81f-5a39-9aeb-a5c85079ce8d |  | textbox | No. Of Blows:
checkpoint-status |  |  | checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
text | cd85fc33-7c25-5759-a0de-9dd24b03a7b3 |  | textbox | Name: Site Engineer
date | 5f01391e-8186-5aaa-a7db-779ef8bde6a7 |  | date | Site Engineer - Date:
text | d85cdc55-fd98-5c6e-bf65-ac3da4169bfe |  | textbox | Name: CPS Engineer – Geotechnical
date | b01aa0fa-bea5-5b11-b72b-fb74adf88de8 |  | date | CPS Engineer – Geotechnical - Date:
text | b5223f51-0e3d-5e96-bce5-59ba5368b40e |  | textbox | Name: CPS Engineer - Structural
date | fb6ef722-bb34-55a8-b474-46c4970d52d1 |  | date | CPS Engineer - Structural - Date:
holdpoint |  |  | signoff | Sign:
checklist-flat |  |  | checklist | CS-4074B - Low Pressure Air Test Record for Concrete Pipes |  |  |  |  | Yes | CS-4074B - Low Pressure Air Test Record for Concrete Pipes | 8fda284b-34e7-47ec-bd44-3d12b23846d7
checkpoint-no-status |  |  | checkpoint | Details
text | 40012e63-5061-59b4-8bce-22b3119f2dc2 |  | textbox | Work Area(s):
text | 589e7100-058c-556b-a156-f8fdbe7c7593 |  | textbox | Sub Work Area(s):
text | d0ecd944-e64d-5aad-b5b2-f6163ccdaace |  | textbox | Lot(s):
text | 670bdbda-350e-51ba-ae96-4f43b288505f |  | textbox | Sublot(s):
text | 6d7081b7-11d1-5402-88fb-87d38ec6fed8 |  | textbox | Document Date:
text | ced9f228-e11a-5483-b36b-787df0cbb981 |  | textbox | Updated By:
text | 97124c04-bf20-5632-8fc3-40dd10b3915c |  | textbox | Area:
radio | 2bf7ca71-d2ec-5d69-ace7-bec3b52f3da4 |  | radio | Weather: | Fine,Overcast,Showers,Rain
text | f3b4a924-f5e7-553d-a435-97c166711ffb |  | textbox | Location:
date | db5326a2-3b22-5ddb-8a68-8f77576cfdfa |  | date | Date:
label | 7f7d6155-8206-5630-a79f-a043297330a2 |  | note | Personnel Conducting:
text | 4da9fc61-5909-579e-8c30-195be8ae64b1 |  | textbox | Drain Layer:
label | 24fc7929-d47a-5ef7-b5fe-8e27bf59860e |  | note | Witnesses Requiring Notice of Test:
text | bba48e6e-fb50-5faa-baaa-351cdcc4688b |  | textbox | QLDC Rep:
text | 624eb0bb-8965-5890-8f9f-fc53e583039e |  | textbox | CPS Engineer:
text | 2f6792e3-59b2-56c0-af4a-96140be920ac |  | textbox | Site Engineer:
checkpoint-no-status |  |  | checkpoint | Pipeline
text | bd453cf9-a1d8-5b99-9403-6f53396669a4 |  | textbox | Pipeline:
text | 7c5d6ed4-e0ba-523a-8785-2b09af69259e |  | textbox | US MH Number:
text | 8332cd9e-4abf-5aaf-8559-c06195d75b79 |  | textbox | DS MH Number:
text | 20b4b335-fc54-57e2-a0ae-3c9ab3f72d57 |  | textbox | Drainage Plugs used: Rubber & Aluminium Plugs, Rubber Blow up plugs
radio | 70ba72b9-45ff-5e47-865c-6391feca6ff1 |  | radio | Plugs Braced? | Yes,No
checkpoint-no-status |  |  | checkpoint | Pipeline Material (concrete):
text | ba65afce-ae74-5893-b04e-70465a274ebd |  | textbox | Pipeline DN (mm):
text | 8b3585c8-87fc-559a-aeba-582ee376d6d7 |  | textbox | Pipeline Length (m):
text | 8c916b61-6354-56ce-b570-fbad1e20ac73 |  | textbox | Test Time as per Table B1:
checkpoint-no-status |  |  | checkpoint | Prelim Checks:
radio | 375f9613-bbd2-5a72-9cdd-d2b39c707c84 |  | radio | Stabilisation period (at 10 kPa) for minimum of 15 minutes. Soap solution used to check plugs/fittings. | Y,N
radio | 66b99bfc-a4b8-519d-84e4-481946d6ccbe |  | radio | Line water soaked for 24 hours | Y,N
radio | 58285822-e5eb-5516-96e3-3a2119563ef5 |  | radio | No Leaks Detected? | Y,N
checkpoint-no-status |  |  | checkpoint | Start Pressure
text | f2b3563a-c8bd-5ead-a43a-7e1e037b4563 |  | textbox | kPa:
text | 1b7c3f13-42b0-5fe7-9f7f-659ec1c21397 |  | textbox | Time: |  |  | am/pm
checkpoint-no-status |  |  | checkpoint | End Pressure
text | 823269eb-1d17-5493-a417-70561690f441 |  | textbox | kPa:
text | f6ad0113-a685-5c1c-8394-6c52ca275a26 |  | textbox | Time: |  |  | am/pm
checkpoint-no-status |  |  | checkpoint | Pressure Drop:
text | 5706ba86-9c10-5e18-afa4-b3257e6cd575 |  | textbox | kPa:
text | 09a2501d-0f20-5429-b848-1b55ea8f4bd7 |  | textbox | Duration of Test: |  |  | Mins
checkpoint-status |  |  | checkpoint | Test Result
label | ee492be7-5ca8-5733-b14f-5351b57595f1 |  | note | Acceptance where the gauged pressure has dropped less than 2 kPa for the time interval shown in table B1 after the shut-off of the air supply.
label | 762ce970-b719-5baf-afe3-65afd831f687 |  | note | ○ The test length shall be acceptable where the gauged pressure exceeds 8 kPa (or not more than 2 kPa less than the pressure at the start of the test) for the time interval shown in table B1 after the shut-off of the air supply.
label | 072702b5-53c7-583b-8f18-ec04c9fc003f |  | note | ○ Table B1 is based on an average air test pressure of 9 kPa. Start pressure is 10 kPA.
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions for the purpose of this test
text | 75580610-9e9d-5c79-bb8d-0b1f6ccf1961 |  | textbox | Name:
label | 3227c8a1-c9da-587d-bd39-f1b29062b9b8 |  | note | Position: Site Engineer
date | 1a66836a-0e23-506c-b0a8-21b98176aaaa |  | date | Date:
holdpoint |  |  | signoff | SIGN
checklist-sectioned |  |  | checklist | ITP - C1503B - Mautaua Under Slip - Master ITP | itp |  |  |  | Yes | ITP - C1503B - Mautaua Under Slip - Master ITP | 93595409-952c-49ef-8efe-670682e8335e
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 08c14d68-237d-5677-8fb5-9e9c90cedd25 |  | textbox | CPS Eng.
text | 45c74036-bf5d-5c59-b582-6d4dd5ad90f9 |  | textbox | Site Engineer
text | 19ce8c05-7451-5dff-a71f-71396b0b4a09 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Confirm Solution is Appropriate for the Site
label | 6c6a6f1d-756b-5e12-bf84-803a9786e0fc |  | note | ACTION (Hold, Monitor, Witness) - H
label | 77f73635-b550-5cde-a994-5d0e965fe1f7 |  | note | Detail - Confirm the applicability of the solution for the site
label | 8329c7ad-96d5-5324-b4c7-e16fd5189004 |  | note | Frequency - Prior to commencement of construction
label | da1b64f3-69da-5509-8ddd-0501fb81b130 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | f7baebdd-4e88-5aaa-92cb-6b52fa0db148 |  | note | Conformance Criteria - To be confirmed by the CPS Engineer/Geotechnical Engineer
label | e9a020c1-b856-5afa-880a-a4b2f1c42bf2 |  | note | Records - Photos, COR
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Topsoil Strip
label | c48a9414-2a49-5578-947c-761e181afd97 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ee188a7c-4b61-52bf-ab00-eb820020f7cf |  | note | Detail - Once all ESC controls have been installed & the Tree Felling & Vegetation Clearance has been carried out
label | 3f886a48-b0e5-5c3a-9592-e0b371b78c85 |  | note | Frequency - Prior to commencement
label | a2c04c7a-8b57-5891-be16-2da55ec7c077 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 9639ebb4-01ff-5a42-a25b-19925b44c2e4 |  | note | Records - Photos, log
checkpoint-status |  |  | checkpoint | 3 - Topsoil Strip
label | e46fc4e1-7b4d-5e46-aa41-f1bab7e8593a |  | note | ACTION (Hold, Monitor, Witness) - H
label | b68bbcd5-33f5-5d59-8ce1-4e5f3aaf1ac5 |  | note | Detail - Confirm buttress extents and rock armouring toe extents
label | df92cd3d-6fc7-56df-81c5-f67f5f7f5695 |  | note | Frequency - At completion of topsoil strip, before Toe construction
label | 8ef1c077-e702-5d3e-961c-9bc9374e30e8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | fa7f480c-4204-596c-a9f1-d6a24e3c6b97 |  | note | Conformance Criteria - Buttress dimensions to be confirmed by CPS Engineer, including toe dimensions and placement.
label | 761fee7d-010a-5692-a9b0-96107a962c31 |  | note | Records - Photos, log/sketch, COR
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Topsoil Strip
label | 04de48c2-f700-5259-8c40-ce5957efbf6c |  | note | ACTION (Hold, Monitor, Witness) - H
label | c8cdcf4a-dc0c-5775-8243-91345b558f6f |  | note | Detail - Confirm Buttress foundation to be on suitable natural ground
label | e4db3c86-d098-573e-8459-1e9e4bee495d |  | note | Frequency - At completion of site clearing and foundation excavation
label | 0109c46a-835a-5ca2-b2c9-8baa4769d823 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the CPS Engineer
label | 1a69641e-808e-5e67-9c95-26dfb9d33804 |  | note | Conformance Criteria - Foundation to be suitable natural ground
label | b57876e4-298e-5bf7-b099-4edf7a387341 |  | note | Records - Photo's, Scala, COR
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Topsoil Strip
label | 7586caae-c537-5d7b-8865-b5e95b4312f2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 82e96f6e-2c3c-58b6-8bdf-0a85cb4e1b04 |  | note | Detail - Confirm Slope face is 2H:1V if its required to be as steep as 1.5H:1V CPS Engineer approval is required
label | d91f1bdd-9717-5c89-8a2d-273a2d4322fe |  | note | Frequency - At completion of clearing and foundation excavation
label | 2bfd5fab-5698-5c61-b378-743c12be818d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the CPS Engineer
label | 91e5045d-679f-5fd1-8d8f-df25140cb93d |  | note | Conformance Criteria - Slope 2H:1V - proceed
label | 8328cc5c-44be-584b-985d-9a1fe5b684cb |  | note | ○ Slope >2H:1V CPS Engineer Approval required
label | 92b8fcaf-eb98-5132-8b47-04bf79689e75 |  | note | Records - Photo's and COR
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Materials
label | 345aed39-d5a6-587a-88b0-4efd00e4bb02 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d1e69ce8-0425-5a45-88ca-ea0c8ce13a25 |  | note | Detail - Bulk fill to be approved by the Engineer
label | 6006c287-a161-5372-8db2-ff7395fae410 |  | note | Frequency - Prior to commencement
label | e48318ed-627a-5283-a497-83e2796ba205 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 815b1ddb-077a-5bd3-ac1e-6a3e15a77e79 |  | note | Conformance Criteria - Rock of GAP65, 100, or 150 grading. Broken faces.
label | bef7fe3a-dcaf-598e-9d37-8867cf2bb632 |  | note | Records - CS-4020 Bulk Fill Earthworks Record Check Sheet, material receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Materials
label | b225e137-75db-5af6-a856-7da3a38157b9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8a942d22-9c9d-5569-94ae-e3e9f85a7d39 |  | note | Detail - Rock Armour to be approved by the Engineer
label | 6ef673e8-99b9-5da0-83c8-7631b9ecf8e8 |  | note | Frequency - Prior to commencement
label | 0cb82983-3e07-5575-bc33-d8695ed7af7d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | fc36c396-063f-58cb-b10f-b35a8a0eb53c |  | note | Conformance Criteria - Rock armour shall be hard, durable, crushed, quarried or natural stone free from dust, clay, organic matter and other deleterious material. the stone shall be free from laminations and cleavages and shall not disintegrate on exposure to weathering.
label | 780cbdd7-ca5a-5fe2-9dcc-cefbb991f056 |  | note | ○ Rock to be SG 2,350kg with a D50 of 450mm
label | 889d2698-e963-5e05-8532-fb18f734c446 |  | note | Rock size to be:
label | 8022ba40-d7f5-56bf-a89d-6a65d90e125d |  | note | A. Gradation D85/15 = 1.9
label | d36ad47d-6931-5f02-8e2f-1574a8d0b7b1 |  | note | B. D85 max 690 (max) and 590 (min)
label | 24fddc87-3b6b-57a8-b970-781158c9000f |  | note | C. D15 390 (max) and 275 (min)
label | f031ff95-78a1-584a-9d64-0b9fd81910be |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Mega Flow Strip Drain or Drainage Blanket
label | d29f96c0-38ee-52f9-84e5-1d65547af78c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5475843e-601d-51fa-ae27-8313bfb9995d |  | note | Detail - If seepage is present in the slip scarp mega flow strip drain or a drainage blanket is required.
label | 65e2c1b7-1b12-5c51-a3f6-9df148d67c79 |  | note | Frequency - Prior to commencement
label | 21a26e5e-cabb-5a9a-921c-4d37d4e65136 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | a0f23d40-c42c-5d14-a1e2-8d758275ce01 |  | note | Conformance Criteria - Ensure Bidim complies with specification
label | 8a35b490-f483-536c-90eb-ea7ee17358b3 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 9 - Geofabric
label | 8236c5e9-0148-5771-a904-32d2b8d89dca |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7d5a6874-2a43-5b70-bb34-25f63b156373 |  | note | Detail - Lay Bidim A39 geofabric over the slip between the existing ground and the bulk fill. Lay Bidim A49 between the bulk fill and the rock armouring.
label | dc0483dc-4ae4-5007-86dd-4cbeb93f2479 |  | note | Frequency - Prior to commencement
label | 28e4f73a-726f-5a82-a0fc-300851eb30cf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 058554c0-cfd9-5d89-8a06-a5e129ab9769 |  | note | Conformance Criteria - Ensure Bidim complies with specification
label | 47f26b63-a44a-5899-b2c7-bb651156474a |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 10 - Geofabric
label | 7712da06-31e7-50e3-861b-1b6196c79200 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 3eba0a87-681e-5fe3-8dc6-2130051983c4 |  | note | Detail - Check that the geofabric have been installed in accordance with the manufacturers specification - overlaps and pin centres
label | 3df4df01-fa69-5b8b-a7bc-c62be008382f |  | note | Frequency - On completion of geofabric installation before fill is placed
label | 60070e13-402a-5d60-a502-c00fa8d6bdbc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | d711d07f-2292-5264-a342-0c7c65850fdc |  | note | Conformance Criteria - Manufacturers specification
label | 054df029-edec-5718-b02c-60db9703aeb4 |  | note | Records - Photo's and Site Diary
checkpoint-status |  |  | checkpoint | 11 - Geofabric
label | 7bca3424-95f2-563a-b1ee-75ee1674ab94 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 27647efb-c9b1-5840-a043-5919cfbab810 |  | note | Detail - Use of the correct geotextile at back and base of cut - Check information on the delivery docket against the requirements indicated on the Drawings.
label | 066649bf-14d1-58c8-92ce-b7c187497c57 |  | note | Frequency - Prior to commencement
label | f694858b-5349-556b-9db3-ebb275845495 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | d36530ab-52c5-582d-80e6-6d29a7d55c03 |  | note | Conformance Criteria - Delivery dockets with roll details. Class D placed at back and base of cut.
label | 713a7601-1156-5029-9407-58e7229f50aa |  | note | Records - Delivery docket
checkpoint-status |  |  | checkpoint | 12 - Filling Operation
label | 1b1b74c0-82a5-5eb4-8e5d-7950fe1acddd |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1eecc0fc-78fd-5f14-96ae-6ab53f385a11 |  | note | Detail - Filling carried out in fully drained conditions with no free water on the working surfaces. Any erosion to be repaired immediately
label | 3b3a0e63-498b-50bb-a3aa-d1d146c1ac6e |  | note | Frequency - Daily
label | a73a625f-114f-5bd3-bb7f-977ebed5e176 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 43797d6b-e25f-5715-927f-152c712af518 |  | note | Conformance Criteria - Fully drained conditions
label | 85b6a2d2-641e-57fa-9eaa-78dcdffd5686 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 13 - Filling Operation
label | d2d034ce-48c5-5ab5-8b48-d58ee01f57c4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6d4acec0-91ff-54e9-92ff-494247400eef |  | note | Detail - Site Engineer to check embankment slopes for location, line and level as the fill progresses ensuring that batter faces are overfilled and trimmed back so that so that the fill is well compacted to the edge
label | f1c39e48-551a-5102-81ef-abb8137b001d |  | note | Frequency - Daily visual survey check
label | c4ad24d1-e7be-546c-8855-b33636014362 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | bc7a4b7c-60a2-56b9-af57-a4f8d70e84ed |  | note | Conformance Criteria - Line and level to be worked through with CPS throughout layer installation
label | 29b0ca06-9f83-5a0c-9ffb-962c445e2d4f |  | note | Records - Photos, Site log
checkpoint-status |  |  | checkpoint | 14 - Filling Testing Requirements
label | 6e56eebf-74f7-5166-a881-a20c93ca84f5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 671ca6ba-29e0-55cb-a625-0f8805a9c1ef |  | note | Detail - Fill placed in horizontal layers no greater than 300mm and compacted. Site Engineer to instruct lab when and where to carry out testing
label | 824093b7-cddf-590c-81e7-f9efaf258821 |  | note | Frequency - testing low middle and top of buttress
label | 1c483823-59c5-5940-a1a4-bc10897d8595 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection and NDM Testing
label | a5808135-5ebc-5b67-8b3c-70d8be12f07b |  | note | Conformance Criteria - Fill shall be compacted in accordance with NZ4431: 2022
label | 4bdd6194-2841-5ea9-a797-0ccd25692490 |  | note | Records - NDM testing report
checkpoint-status |  |  | checkpoint | 15 - Filling Testing Requirements
label | f4675b19-152f-5810-8c44-0b15ebdc214a |  | note | ACTION (Hold, Monitor, Witness) - M
label | 0229f8ea-18c5-519a-859d-97d2c460478d |  | note | Detail - Use of the correct geotextile at back and base of cut - Check information on the delivery docket against the requirements indicated on the Drawings.
label | be7c2a64-f497-5fbe-92fe-9744c43a0cbb |  | note | Frequency - Prior to commencement
label | 3be34958-f877-5ea1-b601-337e0f4771ba |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 44e628c7-4294-55c4-8aa9-b483efc9398f |  | note | Conformance Criteria - Delivery dockets with roll details. Class D placed at back and base of cut.
label | ba305d18-ffcb-54a3-b872-d0615ef47aa7 |  | note | Records - Delivery docket
checkpoint-status |  |  | checkpoint | 16 - Filling Testing Requirements
label | 315c4be4-6336-5c3c-83fe-c1d21b51fe9a |  | note | ACTION (Hold, Monitor, Witness) - M
label | 2baa5cfa-6ec5-575d-ab8e-d7502430a549 |  | note | Detail - Check that the geofabric have been installed in accordance with the manufacturers specification - overlaps and pin centres
label | aa953b3e-554f-5bf9-836c-f2a0b134b760 |  | note | Frequency - On completion of geofabric installation before fill is placed
label | 74891f9b-503b-5f8a-ad80-8b1486866b1f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | d670c441-024a-5467-b2ea-c01c21bc1251 |  | note | Conformance Criteria - Manufacturers specification
label | 8b41881c-4ca3-55a2-bf57-4e0be0dd9266 |  | note | Records - Photo's and Site Diary
checkpoint-status |  |  | checkpoint | 17 - Filling Testing Requirements
label | fc567c33-ddd3-55dd-b1fb-fa90fd5982b8 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 2439427a-f450-573b-a620-5f23fe117f02 |  | note | Detail - Use of the correct geogrid between slope face and rock armour- Check information on the delivery docket against the requirements indicated on the Drawings.
label | 85d66cf0-b7a8-54c8-94b3-534bf4ec452b |  | note | Frequency - Prior to commencement
label | 6df61c83-e139-5dd5-9c8a-c3844b481028 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 68b626e9-5f4d-5903-a43f-bfd5412be65b |  | note | Conformance Criteria - Delivery dockets with roll details. Bidim A49 placed between rock armour and slope face.
label | ff3e9842-c708-5b87-ade7-deaa2e1d2200 |  | note | Records - Delivery docket
checkpoint-status |  |  | checkpoint | 18 - Riprap Placement
label | cc091761-df42-504f-942e-bdcf057c243d |  | note | ACTION (Hold, Monitor, Witness) - W
label | bfa700e5-96eb-55f2-8bfe-bdc000474e43 |  | note | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material
label | 82ecbdfc-82d2-5203-ae69-b969794fcc92 |  | note | Frequency - Daily visual check
label | 37edc961-1956-57c2-97c3-efb5bf7e616d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | e4cd16b7-2cd8-5c5b-9cc0-41fe228b3ec8 |  | note | Conformance Criteria - Specification
label | 5c9d6437-7f8f-5604-8858-e3e32274094c |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 19 - Trenching
label | e85518dc-712b-5f48-9147-c0599f51f4b4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3095a933-a9e7-5e89-bbc6-cace234fd425 |  | note | Detail - CPS Engineer to be informed of unsuitable ground or seepage in Trench and instruct testing and remedial works.
label | 431a476f-ff45-52c5-a352-79880b03c65c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 086d0454-5ac0-5214-aadc-f52557edb09c |  | note | Conformance Criteria - CPS Engineer to instruct action
label | 410f3702-8519-559b-9784-4d35b3652006 |  | note | Records - RFI
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 20 - Trenching
label | 81bd8c95-272c-58cb-a877-d79d794aa286 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2ba54ef9-ea28-5c97-a383-d33ce4ee27cd |  | note | Detail - Location to be determined by CPS Engineer
label | b880c47b-cd1a-5579-a28e-25bfb7e83fd4 |  | note | Frequency - Prior to install
label | 40135429-b334-567c-bf27-2dd8c1dd4143 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 05210e2f-3cec-551c-9ef4-1252aaa6fd49 |  | note | Conformance Criteria - Trenching location and direction to be confirmed by CPS Engineer
label | 20f6f45f-384a-5345-a0bf-050af22db31c |  | note | Records - Photos, Log TBD
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 21 - Drainage
label | 2384ddb2-5634-54c6-869a-5c5341684bc1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 00ce6ee9-aabb-5a4d-91a8-79ed35f73856 |  | note | Detail - Ensure drainage outlet from pavement connects to buttress fill if required
label | 0d6f9b52-2987-5816-aad7-cd2f77b8621d |  | note | Frequency - Prior to pavement commencement
label | 9e076c6c-66c5-570f-85b9-3989165bd464 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 368b2ce6-ab76-5d25-a586-75e96032f1b9 |  | note | Conformance Criteria - Confirm drainage connection if required
label | 8db3efbd-9535-5568-ae75-c1744b22ff8c |  | note | Records - Photos, Log TBD
checkpoint-status |  |  | checkpoint | 22 - Road reinstatement
label | 554faf58-cdf6-5667-8b3d-ae6766a23e3d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6af42992-5470-535b-8e8c-02c17fd6ff97 |  | note | Detail - Refer to Pavement and Surfacing ITP's
label | e59e75a9-6d17-52cf-9c64-5dbcec707c88 |  | note | Records - Pavement and Surfacing ITP
checkpoint-status |  |  | checkpoint | 23 - Survey As Built
label | 5cab7663-4b4a-5078-9b1c-aa8592d1f466 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 635a3861-e8c6-5913-9a50-2221f5be3145 |  | note | Detail - Ensure all subsoil drainage lines comply with design prior to carrying on with next construction process
label | 3e706729-4be0-50c0-a1b2-d6caad5b2d64 |  | note | Frequency - At completion of sub soil drainage line
label | 0f26a82b-42e4-5d1e-a7c1-0e8aef2505f6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 546d8075-6744-5ab8-932d-c4f6a340dc78 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 24 - Lot Number QA File
label | b65cac74-0b93-5965-bddd-eab65eff199e |  | note | ACTION (Hold, Monitor, Witness) - W
label | e457ab5b-f70d-5e01-8f00-d1fce23bffbe |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 463be53b-578c-527a-8f18-28cfd7cc1f08 |  | note | Frequency - At completion of Lot
label | 0388a153-c860-5ac0-8627-d53b1169fa45 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 968a7d38-2203-5ef8-8aea-2204ef5c45d6 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 8d2e211b-d02f-53e2-a25b-26f85c70a585 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 25 - As-builts
label | ba792bee-c866-5c69-a1a2-846099870dc9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7bdaddea-0811-5221-9525-deb6e6703709 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | cb616503-0378-5b0c-b1ce-12d0fe413751 |  | note | Frequency - At the completion of the Lot of work
label | e3a3e096-0e25-5861-827f-32e5fea5c398 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 7afcc781-8c09-5e10-84df-c92793e102ea |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - Tangoio Falls Steep Underslip - B1004F - Reinforced Slope (Rock Bolts, Soil Nails) | itp |  |  |  | Yes | Ω (Deprecated) ITP - Tangoio Falls Steep Underslip - B1004F - Reinforced Slope (Rock Bolts, Soil Nails) (old version) | 94259252-c925-4900-855f-1a4e517fa531
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 2e08fbd2-a3b6-5d62-b0f9-a0ada44c7a37 |  | textbox | CPS Eng.
text | 54611865-1909-590a-9a58-5307fac3e2ee |  | textbox | Site Engineer
text | f52a4f33-a0b2-56a6-8161-21ff78fd0212 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Erosion and Sediment Control Plan
label | 9c4923b9-26fb-5282-aa40-54bb2ea3f2db |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6f087281-1ae9-5781-b797-6fc0160e9bb4 |  | note | Detail - Need ESCP before construction begins
label | 87d943c6-33f2-5779-984f-eba7f4616c40 |  | note | Frequency - Prior to commencement
label | 8668f1f6-76e5-5e50-bdea-669bdda4c3c9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 41c753fe-56e2-5a23-831d-ad7e9f187873 |  | note | Conformance Criteria - Erosion and Sediment Control Plan must be submitted to the design team
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 -
label | b37b7eab-1daa-5df1-a8b9-5c3586ddf343 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b30b8259-014d-54d2-bd15-5e378228fb82 |  | note | Detail - Implement ESCP approved by environmental team
label | 40c09d8e-65c6-5de3-9778-02ddbe572cdb |  | note | Frequency - Prior to commencement
label | fdc5d510-f84b-553f-9689-b459ef3b2fad |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Road Safety Barriers (1)
label | f94407f6-4848-5fd5-87b1-196ecaa64f75 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 37660f0f-ccd0-558f-86cb-ad824d686127 |  | note | Detail - Proprietary barrier system type and installation methodology
label | 78a5d5bd-46c4-5c85-9647-bbaa5209dc18 |  | note | Frequency - Prior to commencement
label | 193f83c4-110f-5354-bddb-a66aade4f46a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | c9091017-556c-5a3a-b5e1-2b57e0e43d00 |  | note | Conformance Criteria - Approval from Design Engineer
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Road Safety Barriers (2)
label | 77d2929a-19db-531a-a3ef-2319769c19bb |  | note | ACTION (Hold, Monitor, Witness) - W
label | cc7728de-2884-5ea3-996c-648d6282b8b5 |  | note | Detail - Propritary barrier system compliance records
label | 4764b12e-959d-5f2f-8a57-246dfb9164b9 |  | note | Frequency - Daily
label | cc3a4fa8-ceda-5872-982f-f2396fd713dd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 6606412f-8816-5874-950d-f845e8aec77e |  | note | Conformance Criteria - Daily checks to ensure the safety barriers are instyalled correctly and that no damage has been sustained
checkpoint-status |  |  | checkpoint | 3 - Clearing & Earthworks
label | 4281375b-b432-5196-bcdf-7f9fbae85b1c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 12aaeaec-450c-5e32-8507-7f7a4aa4c70d |  | note | Detail - Before setout of the reinforced slope method all vegetation and debris clearance within the limits of the site is to be completed
label | 463321d3-8425-5738-92e6-65c2465fe3b1 |  | note | Frequency - Prior to commencement
label | 758402c3-e96b-577c-99c8-e13f4c48b912 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 11f96e6a-98f7-5190-991f-49809136af49 |  | note | Conformance Criteria - In accordance with TNZ F/1
label | 472762a8-38ff-50b6-be65-9bbb37062f1d |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 -
label | cd9254a7-36ea-561b-9860-907a9fefcb42 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2bd05ba1-e814-53f2-bf2f-23b6078ec335 |  | note | Detail - Any excavation and filling required is to be carried out. Excavation should be kept to a minimum
label | 3c8404ec-0f36-5f9c-bb40-912fc9b64f12 |  | note | Frequency - Prior to commencement
label | 5019dac6-4bff-5295-bc90-b1efb136095a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 14bdf43a-5958-59ea-b09e-913e8f4396a1 |  | note | Conformance Criteria - In accordance with TNZ F/1.
label | af911c5e-396b-5e8a-ad8c-ff5fed141144 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Survey Setout
label | ae1cf51d-518a-597d-9a19-72e9150cee06 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e01d78e4-a035-5fc1-bf6e-974afaedbde6 |  | note | Detail - Arrange for a set out survey to be carried out & check against design drawings
label | 8dedc862-2ab3-5aa7-8178-c7c4cc4269cd |  | note | Frequency - Prior to commencement
label | 600f1aa2-be0d-5eba-8cc3-2e39cce9a3d5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 9fa88142-0560-5af0-a89a-6e02237f0238 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | ef7fd4bb-c2d3-5306-880e-267b88f14730 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Material Compliance and Methodology Approval (1)
label | 7924f54c-55be-5e73-9d8f-ea3aa0a2128f |  | note | ACTION (Hold, Monitor, Witness) - H
label | c785dfa6-809d-505e-8c2a-e5b3e726765d |  | note | Detail - Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings
label | a72c1159-69b0-5ec6-aac0-19bc89bdf12d |  | note | Frequency - Prior to commencement
label | 12bf91e7-781e-5da9-9ee1-1385398660e9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | f334f386-37e0-5705-a522-53c520e80491 |  | note | Conformance Criteria - Grade 500E soil nail
label | 9e96c3fc-3a02-59f5-8642-d0b5e436a32d |  | note | ○ Class II corrosion protection
label | a5a5d80f-85f8-5a0d-9cbd-35df09c12f79 |  | note | ○ Lengths and diameters shown on drawings are the minimum required
label | 6180addc-c69e-509f-845e-e78fafa02b63 |  | note | Records - Delivery Docket
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Material Compliance and Methodology Approval (2)
label | 0bebe6dd-6a7b-5648-90b1-3e097b3a7e5f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 32b22426-2b02-54d7-86a0-1b30a8f2df9a |  | note | Detail - Concrete quality plan
label | 7e56dce0-4256-5d90-9c08-2d7a804bc232 |  | note | Frequency - Prior to commencement
label | 518ccda1-e334-56ca-a104-9afb67c1f711 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | a3b303d2-4aab-51f4-8afc-2b4f3e45bb72 |  | note | Conformance Criteria - Including:
label | ee761071-342a-5d06-bdec-e6a460537b29 |  | note | – Name, qualification and expoerience of concrete works inspector
label | 642e355e-af4a-5e90-b55f-2383b894e9ed |  | note | – Form and content of concrete placement card
label | af257b23-aa95-517e-ae96-5dfc5de47b73 |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Material Compliance and Methodology Approval (3)
label | f7e03c44-5a87-5789-ac43-86d0fa49d817 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9ddf62f1-fd3b-51ed-bc56-21d9e725754a |  | note | Detail - Details of concrete supply plant, copy od certificate of audit for plant
label | 779d825b-217d-5348-b473-1376eeb0471a |  | note | Frequency - Three weeks prior to pouring concrete
label | da91a3cc-9dce-5f24-a434-6794cc29d3d4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 4afbce4f-9d99-5c00-b7c6-3fcde734c63f |  | note | Conformance Criteria - Including:
label | 77a84885-2a90-5cc4-aa82-201a93fbddfb |  | note | – Plant test Results
label | 4b90e87b-da89-5e0d-b3f6-6b0de9cc6cd6 |  | note | – ASR Compliance Records
label | cf6513a1-9eae-5cc3-b6c4-2c8a3bcef0e6 |  | note | Records - Email
checkpoint-status |  |  | checkpoint | 6 - Material Compliance and Methodology Approval (4)
label | 28af4e27-67a4-5019-8172-7cfaacce26be |  | note | Detail - Concrete work plan
label | b7d611e9-d81d-509f-89cf-531dc8e42344 |  | note | Frequency - At least 10 days before commencing works oinsite
label | 340cffae-6883-5d87-9979-85ae0b335355 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 5aea05ce-7dee-5d52-8fc0-07b938fd1bd3 |  | note | Records - Email
checkpoint-status |  |  | checkpoint | 6 - Material Compliance and Methodology Approval (5)
label | 238bd1ca-ab0f-58b5-86cc-48dd079e82cd |  | note | ACTION (Hold, Monitor, Witness) - W
label | def2d018-bed9-5f35-afc4-97b182e18e09 |  | note | Detail - Reinforcing steel manufactureers test reports and certificates
label | 14cf4d8e-222d-58ca-a22b-d3b24de161c2 |  | note | Frequency - Prior to undertaking works
label | d14ccb4f-73c5-5813-a8ff-8dd98b259e3c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | fc3cedda-658b-5f89-8763-59bd316fe249 |  | note | Conformance Criteria - Including despatch records
label | 8d121cde-6829-5eaf-acf6-b7d269fe0390 |  | note | Records - Email
checkpoint-status |  |  | checkpoint | 8 -
label | cc948d8e-fc09-5038-bd7f-1a0b303891de |  | note | ACTION (Hold, Monitor, Witness) - W
label | 86f39136-e6b9-569c-9016-f465278644bd |  | note | Detail - Submit all concrete mix designs, trial mixes and compliance records
label | 38f82903-3ee1-5b04-afb3-fa2d08158490 |  | note | Frequency - Three weeks prior to pouring concrete
label | fcd32786-381e-5d97-9b0b-bd5b85874215 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | ce6061f1-1982-5cab-b0de-4cd30052f480 |  | note | Conformance Criteria - Mix Design to be approved by CPS Engineer before commencing construction
label | 015f5c0c-b3bd-5d27-bf6c-40acc0cdafa3 |  | note | Records - Email
checkpoint-status |  |  | checkpoint | 9 -
label | 8a8134f1-284b-5dde-b04d-6c3252e9ede5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 65c08e5e-6ceb-5e5a-a8d6-4f89b3f20d63 |  | note | Detail - Test to be carried out on Grout mix before it is ordered for construction
label | 3b7a6d00-ff27-5879-9ca5-a4c34e6a16f4 |  | note | Frequency - Prior to commencement
label | 09a23709-f1f6-5baf-aed8-3b9ac57b84b6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | f1fcc6be-9b0f-5ea9-8e98-3deaac4bb841 |  | note | Conformance Criteria - Mix design to be approved by CPS Engineer before commencing construction
label | b2af9b3d-f2e3-5745-8700-0d1fb4f63a83 |  | note | Records - Test results to CONQA Procore
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 -
label | 5853eb55-dfb2-5145-8ff2-05106696c74d |  | note | ACTION (Hold, Monitor, Witness) - W
label | b65c8cfb-ef28-571d-9079-79bbda5ea456 |  | note | Detail - Grout checked if its free from lumps & segregation
label | a674fe0e-6954-5319-b3fc-8eecd07eb6df |  | note | Frequency - Prior to commencement
label | a3f9beb4-9e72-57a1-98d6-58957d645c67 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint-status |  |  | checkpoint | 11 -
label | 35b6c3a3-c568-5e9b-b4e3-46f9de823b12 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c0cf27d6-11ce-5691-87c8-4b58c71c1604 |  | note | Detail - Request for use of alternative Drilling Fluid (Section 7.5.2)
label | 4892e9e4-4b78-53fc-ade4-8092c1b42858 |  | note | Frequency - Prior to Commencement
label | 375bd94f-8a51-5ece-8d40-2a067026b31b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 4b1be4db-032b-546b-a978-cdd90d2cb3bb |  | note | Conformance Criteria - If required
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 -
label | 7b40de65-84c3-5055-bcde-1e7bd6e30ebd |  | note | ACTION (Hold, Monitor, Witness) - H
label | 69c5bf4f-bf11-501f-b0e4-aa2f90ccbc18 |  | note | Detail - Soil Nail construction methodology plan must be submitted two weeks prior to works starting
label | abcad524-d823-58c5-bd19-5d2d3e19f0b2 |  | note | Frequency - Prior to commencement
label | d430108a-28ee-57e2-ba20-5e73efb87277 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | c0ec667e-7c91-5101-bf63-c1275ec0e623 |  | note | Conformance Criteria - Include sprayed concrete, grouting and tremie concrete in methodology
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Sacrificial Testing has been Completed and the Results are in the Design Report
checkpoint-status |  |  | checkpoint | 13 - Working Bench
label | d05ec5a1-da9b-5eec-850d-0782ab8ed225 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7d8ccc5e-1e91-532f-a264-4f1a8b021570 |  | note | Detail - The construction team shall stage the excavation of the retained face such that the excavation proceeds no more than 1m below the current level of soil nails being installed or vertical spacing of the soil nails plus the required reinforcing lap or the short term stand up height of the ground, whichever is less.
label | 3be47c70-9eae-5cfb-b45b-ddd0bb6e3e3d |  | note | ○ The construction team shall protect the face of the excavation from damage at all times.
label | 958e9c02-6712-5d9c-b605-d8c4692cc380 |  | note | Frequency - Prior to commencement
label | 0991d622-6e2d-53cd-8c5b-7ae9e4a17c35 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 1accea89-427a-5dc8-a526-59782d1ec236 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 21 -
label | 7a29f3f3-c580-5d36-a879-a74d84f092ad |  | note | ACTION (Hold, Monitor, Witness) - H
label | d69779ea-2fe7-5333-b3b9-f50a10987b74 |  | note | Detail - Location of all Test Nails to be agree on site (Section 7.8.1)
label | 2147da13-2ac3-5e29-9253-7f2eafd28b62 |  | note | Frequency - Prior to Trial
label | f48bece2-d2f1-5368-a5bd-2324a04f94f7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 3b23ec92-7fb4-5aba-ad50-86c6eac6a81b |  | note | Records - Photos, Site Diary
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 17 - (1)
label | 9f8d3823-513e-5209-9e9c-137af1450fa8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6ffed7d6-3e21-507a-9b96-a685cc43db85 |  | note | Detail - Insert micropile bar (ReidBar RB32) to full required length
label | e314c402-28f2-5fe0-ad8c-257f3a6bddb8 |  | note | Frequency - During Construction
label | 2d508046-64c2-5eb6-8dff-59250abe8d87 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 04d3d86b-138c-54b3-8c0d-7dfb909737c8 |  | note | Conformance Criteria - Embedded length of micropile 3.0m into ground
label | 494e90db-6153-5756-a72b-20a672c4a7ab |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 17 - (2)
label | 8ed618f7-2498-54b3-ac5a-2dd8b865cd6c |  | note | Detail - Drill hole
label | d570e94e-2bfe-5ab3-904c-c91e35bf70a6 |  | note | Frequency - During construction
label | 25184bba-5b1e-5ed5-9735-662b1ca00e62 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | e2d0f7bd-dfda-5a66-b9e8-b5c5de3bfb4d |  | note | Conformance Criteria - Drill log to be submitted to CPS Engineer including the depth at which water was encountered if there was any.
label | 0dfc5cef-17d9-5758-9886-447dd648970d |  | note | ○ Submit all installation records for each soil nail and pile.
checkpoint-status |  |  | checkpoint | 29 -
label | 061b1afb-356a-5705-949f-dfa51a91e4e4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ae61c3ab-1250-53cf-aa41-4f0f5c280d5e |  | note | Detail - Flush all soil nail holes with water and air after drilling to remove smear and drilling debris
label | aecc33ec-43ac-5554-ae54-8f73399d7790 |  | note | Frequency - During Construction
label | dc5eae4f-88fc-50d6-b701-fc726b772534 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 31 -
label | 865d3ff4-20d4-5c38-a014-c52ab95580b3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 83da2bf5-586b-52c3-a619-6e89ee0f383b |  | note | Detail - Insert soil nails as specified
label | f76f8fdd-80cb-5fea-a4b4-355937c68967 |  | note | Frequency - During Construction
label | 60335836-dce2-5aaa-befe-087f0b5a49bc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | de0fcc36-c47e-5dc6-8bf4-0f03c982377f |  | note | Conformance Criteria - Soil nails must be inserted into the drill hole to the required length without difficulty to prevert damage
label | 5c735cdd-f329-5cba-bfbd-e24c31503136 |  | note | Records - Subcontractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 32 -
label | e18c8d52-22c2-5d1e-8224-0631d890cc04 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3f306aa4-7a59-50bd-a505-7be978d6e2e7 |  | note | Detail - A record is to be maintained showing the type and installation date for each soil nail
label | 1d3aae72-3fb2-5c57-b9ed-3de32e2041bd |  | note | Frequency - During Construction
label | e5d82ec9-6570-55c3-bbe0-f9636760354a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 9be4e0b3-23a9-5ca2-a1c4-dde0b4ea335a |  | note | Conformance Criteria - Installation records shall include:
label | b5d45de4-f3a3-5fe5-8eb2-b37ff25b0bc2 |  | note | – Length of bar
label | ed148775-d2fb-52df-b8a1-93f70710edb9 |  | note | – Depth of drill hole
label | cc043f9a-ca59-589f-b764-b9961466e3ff |  | note | – Inclination/Verticality achieved
label | 5c4c2083-9cab-5b7d-9a1e-9c42fca9e4b2 |  | note | – Level of grout placed
label | eb50d99d-3fbd-512d-8129-1638ffca87b3 |  | note | – Batch numbers associated with grout placed in each hole
label | 1ec141b4-6f4e-5f0e-93b0-ef83c3b77347 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 18 -
label | 1337721c-5957-560b-bb27-3b4ad8d85d02 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 47d3a89e-acea-59ed-9bd4-3f770e847f44 |  | note | Detail - Install Grout
label | db81b36b-dc4f-53a3-a7e1-b86413ee5f87 |  | note | Frequency - During Construction
label | d476496b-4277-5f13-9c41-c7d38a9b490d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 530473d2-4a5c-51ad-9dd5-7d35de72a55e |  | note | Conformance Criteria - Including :
label | ea775a6a-c04f-5ff2-90bc-46e5a0182f79 |  | note | – Concrete despatch records
label | 6feee161-2388-504e-b824-e8d7adb2ba0f |  | note | – Compression test results
label | 89e6ee14-ed27-5906-971a-5e99504a2e2a |  | note | ○ Must notify CPS for any failed result and cease works until resolved
label | 9360a16c-235b-5769-ae62-e1d697aea97e |  | note | Records - Subcontractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 33 -
label | f5638925-bda7-5a8f-9852-325f74b991d2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7d8495b8-05cd-57b9-8085-52611c43edb6 |  | note | Detail - Install Grout on the same day of drilling unless otherwise approved by designer
label | f1dc0494-8138-5e7a-ba2d-37f124137dc5 |  | note | Frequency - During Construction
label | f30750c9-76ee-52c2-b49d-bec1ba0adbb3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3db3e17d-24b9-5bb1-9502-1d51e0570be0 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 34 -
label | 7d85c194-ea63-58e7-9fa9-92b5fc54b828 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 48eae4eb-52f0-5799-9b9c-0e5b4d3d3ec8 |  | note | Detail - Grout samples shall be taken from each batch and tested by an approved laboratory. Flow cone tests shall be undertaken for each batch
label | 7ad16412-46d1-59eb-afee-ea2640fa4490 |  | note | Frequency - During Construction
label | 79680c5e-cb37-5ca0-be8e-9a7ff2ee34be |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 48d09ecf-3e2c-526a-ae8f-7da459e30060 |  | note | Conformance Criteria - Must reach specified minimum 7-day and 28-day compressive strengths
label | c65839f7-28da-563b-aecc-78c3e2c07baf |  | note | Records - CONQA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 35 -
label | d4491a30-eb7a-5d20-b58c-924012ec43b8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | da03c785-6efd-55d5-9d73-9c42268c55e4 |  | note | Detail - Loss of grout shall be monitored and recorded for each hole during and immediately after grouting
label | a8c10b7a-341f-5942-80bd-3f2953ef617e |  | note | Frequency - During Construction
label | 5f20c536-106a-51b3-bb27-62a51085ddf9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 4bf97c30-aeef-5759-97ac-92c59d35da0a |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 36 -
label | 4a32e18c-99d4-5c43-b757-d786aeba77fd |  | note | ACTION (Hold, Monitor, Witness) - H
label | b463f295-f826-5e3a-b7a9-95ce8e67ebc5 |  | note | Detail - Install Bolts/Nails washers & nuts
label | 64bed8dd-c015-533b-be02-65c3b4230307 |  | note | Frequency - During Construction
label | 1b701791-6a15-5882-839f-0eaea1c9c275 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | bcb861f1-6ce6-5bdf-b463-7c7a68915431 |  | note | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
label | 64b7fb8d-9a30-5fb7-8471-6d939c2270ff |  | note | Records - Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 37 - Testing of Soil Nails
label | f6e444cd-90ca-58ba-90b3-e5dc76a0f3af |  | note | ACTION (Hold, Monitor, Witness) - H
label | a0b94712-f11b-5e61-88be-88a6ce0f2f56 |  | note | Detail - All testing equipment must have been calibrated by an IANZ registered laboratory (or approved equivalent) within the last three months and shall be certified
label | c325c938-e2e7-5976-92cb-c7a39a3a24ac |  | note | Frequency - After Construction
label | 72afb0a6-3920-5eb7-bf2c-096e1f09f411 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | b26985e6-87e0-54c3-ae3b-5914e39c98df |  | note | Conformance Criteria - Certifications of all testing equipment within the last 3 months
label | 3fb64ab3-2a3b-5518-9fc3-c46c3082fec2 |  | note | Records - Certifications
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 38 -
label | f1d9f2b7-9029-56ff-98a5-a270527a556d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9171556b-f9e0-563b-a79f-4546327082b4 |  | note | Detail - Leave nails in an undisturbed condition until the specified 7-day grout strengths have been achieved
label | 1618ae3f-cc1d-5a48-a848-8fc68e6e5de7 |  | note | Frequency - After Construction
label | 54fd5915-6c04-5eca-8d55-4c0799f84f36 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 39 -
label | 69f7a75b-04f1-5702-b4c4-ef0d1a495a59 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6589b5ab-faf7-5687-a780-8ce513ad7368 |  | note | Detail - Test soil nails in accordance to design specs (Section 7.6.1 and 7.6.2)
label | b395ad4f-9edb-5ffb-828b-cf4d2dd1e578 |  | note | Frequency - After Construction
label | b2637abb-4ae7-57f3-9796-c2d9aa4d45a5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | b45b3c9d-ccf0-5998-a118-0b1b3768b56c |  | note | Conformance Criteria - Load testing 10% of working soil nails - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | 2955c343-7592-5443-a32b-764ce5dcd8de |  | note | Records - Test results to CONQA Procore
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 40 -
label | 0b537d9f-77cd-552a-8c33-4a93114073d3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6389a486-de36-5b57-99e6-a6e8bc53ac43 |  | note | Detail - Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails
label | 5212ceee-d31e-54c7-ba7e-1bf340bc61c5 |  | note | Frequency - After Construction
label | 4f3df9d2-ead0-5600-881d-4efbbdf5ae7b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 7fa025be-86cd-5f34-a268-3ada64c26c03 |  | note | Conformance Criteria - CPS Engineer to give approval via a NTC
label | 3b34cf71-463b-5343-9e73-b9f989facbda |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 41 - Shotcreting
label | e4154589-58ac-54f7-888a-26170a7f80ed |  | note | ACTION (Hold, Monitor, Witness) - H
label | a40a4dcc-44bf-5774-813e-ee77ecb5a310 |  | note | Detail - Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened
label | 1cab9b94-f783-5973-b861-8b05614643f7 |  | note | Frequency - During Construction
label | dda277ac-2127-539f-be53-86c350dc2ded |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3b6a9d14-ff99-561f-9993-039b4831bf10 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 42 -
label | 1f4c1218-eb10-5f98-9e96-dbe776e51cb5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e4315cbd-239c-5b34-823f-a732a5db353e |  | note | Detail - Apply shotcrete - 200mm Nominal thick (Vertical)
label | 5d16ec90-b722-54d6-9d7e-dd39f69a83dd |  | note | Frequency - During construction
label | 50f9d0e7-86e4-5cc6-b750-20e77a7da38b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3175f56a-8397-5641-b6ac-3b2d8ff5ed62 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 43 -
label | 61454bf7-5f0b-5274-a651-57bf64d75d2f |  | note | ACTION (Hold, Monitor, Witness) - W
label | c22eddac-60f5-52c6-a37f-7f2d6f623d34 |  | note | Detail - Apply shotcrete - minimum 150mm thick and nominal 175mm (Horizontal)
label | f420409a-d8e3-5139-a098-a37088b7291c |  | note | Frequency - During Construction
label | 7174d3a5-f81a-50b7-8062-aeed5f6bd220 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3ab633b8-0e62-5fab-9cab-ade69fe271ae |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 44 -
label | 08b30fa7-f611-5af2-bcc3-aaae13d215e9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1190faf1-c170-55b5-9f0c-fd7d7612fb96 |  | note | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores
label | 252c24fb-5b11-5b4c-acbd-828217ec25b1 |  | note | Frequency - After Construction
label | c256687d-e467-5628-90a3-b92090932c17 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 20cbdd3b-74bc-5926-8dce-e0ee29b08c15 |  | note | Records - Test results to CONQA Procore
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 45 -
label | 2d127220-0560-58e6-a733-eec5aeb5accc |  | note | ACTION (Hold, Monitor, Witness) - H
label | 724598e5-e2d1-5075-ab3b-ba85522208ef |  | note | Detail - Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m
label | 014e80a0-f162-5403-99a6-33237bfed7eb |  | note | Frequency - After Construction
label | cd26d7bd-886d-50ae-a17b-b025db24b4e0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 4167d080-eec7-5ba3-bca5-bd8329d503a0 |  | note | Conformance Criteria - Surface Inspected by CPS Engineer & Approval given to carry on with works
label | 26e4607f-34f7-5f21-ba5b-a5452fd44e66 |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 46 - Post Construction Survey
label | 6bee2354-423b-53f4-b6e6-923291f08ac2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1154b71e-8116-5446-b9cc-93893ccc4a9e |  | note | Detail - Survey final position of bolts for as-built purposes
label | 8032a508-14e8-5a98-9eb4-da7d1188d7f4 |  | note | Frequency - At completion of Lot
label | b6912d89-32ba-5e24-9fd6-98be3ad02134 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b6d790b6-9c95-5b22-ab79-08bd512ea0c9 |  | note | Conformance Criteria - Survey report complete and conforms to specification
label | d405e6f8-9e45-5f53-bd2f-2d80a93286db |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 47 - Lot Number QA File
label | bf90cd8f-eef5-56b7-87f5-7cc60cceea87 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ba5fca82-2437-5527-8bfc-43bc48b0adab |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | dfb01f9f-07e2-5a94-a005-1e149578c4a6 |  | note | Frequency - At completion of Lot
label | 38c61592-223a-5e17-a4f6-8d5491773085 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 0e361d37-2b15-52cc-8ec4-dd9858d845d3 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 9561ca11-5d2a-5faf-82bc-12623a7674c1 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 48 -
label | c06cce51-93c8-5346-bde4-ff6d7533d838 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5acdee03-8adf-5209-9099-94e0d8dd466d |  | note | Detail - All subcontractor documentation to be included in QA file
label | 63ff7980-238e-5b46-a7c5-09cce94944fc |  | note | Frequency - At completion of Lot
label | 09b3a1b5-f4ee-5818-89c3-cab8321722af |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 7ab619be-78c1-5bf0-b3cf-cfaa79208795 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 49 - As-built
label | 1c6f8078-c481-55dc-ac87-07240043c399 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ddde80ac-7209-503c-a476-dd9d0bc77d8f |  | note | Detail - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file
label | 77e1d642-efd3-506d-a962-6f8ecf9796fc |  | note | Frequency - During and at completion of work.
label | 91e43805-8cca-595b-bcdb-826e7fbc0f8f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | c7e62184-7943-596a-aabe-bf399c11b37b |  | note | Records - Survey receipts, As-built plans
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 50 - Quality Assurance deliverables
label | 44c48998-6a4b-53b8-8b3f-f65af6ee4723 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 127de175-ba10-5b4b-80be-61a993be103f |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | bdf86c6d-5c63-579b-972a-f8a9374f0011 |  | note | Frequency - At completion of Lot
label | f66e3a1e-e9d5-570b-80b7-1a50d7ecf890 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 7f5fa922-e07d-5f13-9271-e0fe9c9d47c1 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | bf5a3195-1d2e-5a15-ac51-41d382687398 |  | note | Records - Asbuilts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 51 - Completion Sign Off From Fields Below
label | 2ca9959d-2d15-502c-afab-a25fa184aeb7 |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | CS-4006 - Manhole Catchpit Record |  |  |  |  | Yes | CS-4006 - Manhole Catchpit Record | 978c3e27-52a6-427f-96c6-aaec8ddfe0c5
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | 39f52d11-476f-5b69-90b0-c7fddfd05d0a |  | textbox | Drawing No:
text | 2089f17a-4b74-58c7-9057-11a05800d98b |  | textbox | Rev No:
text | e5269b3b-5f1a-5dc4-a524-953a309b7901 |  | textbox | Manhole/Catchpit:
checkpoint-group |  |  | section | Inspection Stage
checkpoint-status |  |  | checkpoint | 1 - Setout
text | 8c7823fe-ecbd-57d7-8c4b-11ce065cb89c |  | textbox | Initials:
date | 3abb2434-d5c6-5a01-b437-bc37219c8caf |  | date | Date:
checkpoint-status |  |  | checkpoint | 2 - Excavation
text | 19d6887b-e659-58f2-9b5f-a080385fb33a |  | textbox | Initials:
date | 6bbdcd35-4a98-51e3-aa10-211461ac254d |  | date | Date:
checkpoint-status |  |  | checkpoint | 3 - Prepare & Level Base Bedding – Testing req?
text | 45cbaa9d-405b-5f3f-a2bc-85ff638fee2e |  | textbox | Initials:
date | 4ac1df3a-dfbd-5cfa-a005-3dd0f60ec5ba |  | date | Date:
checkpoint-status |  |  | checkpoint | 4 - Confined Space Permit required?
text | bcd16cc1-a174-56fd-a180-41f851a2b48a |  | textbox | Initials:
date | 965f5850-21a3-5c51-9789-70c543744261 |  | date | Date:
checkpoint-status |  |  | checkpoint | 5 - Installation of Precast Base Unit on Bedding
text | 950e08e9-f8d3-5e27-b3b6-db0b99112ac6 |  | textbox | Initials:
date | 644b3515-afb3-51d9-add7-6890bea70b16 |  | date | Date:
checkpoint-status |  |  | checkpoint | 6 - Installation of Precast Risers to Lid Level
text | cfcc38ed-479e-5c82-aefb-4158e88f33bc |  | textbox | Initials:
date | f31d8cd6-3ebc-53d6-a05d-1934b2573921 |  | date | Date:
checkpoint-status |  |  | checkpoint | 7 - Installation of Manhole/Catchpit Furniture, Steps / clamps
text | 51cc18e6-5b03-56ab-a480-0a601d4f8801 |  | textbox | Initials:
date | 392256fd-aa19-506d-b76c-6359df4720c3 |  | date | Date:
checkpoint-status |  |  | checkpoint | 8 - Haunching / Make Good Base. Joints sealed
text | 5866bb86-0970-5a41-8b3a-8bea2f32454e |  | textbox | Initials:
date | 73af349c-0e6d-5709-b5c9-fb189b0b8952 |  | date | Date:
checkpoint-status |  |  | checkpoint | 9 - Installation of Precast Lid
text | 3f0663cc-466b-5d40-adcf-13ae22a1855c |  | textbox | Initials:
date | 810843b8-970f-512a-8ca9-b6e6b86295c9 |  | date | Date:
checkpoint-status |  |  | checkpoint | 10 - Backfill Around Manhole/Catchpit – Tested
text | b9b14bb7-0d4e-5d4f-9a2a-14c2b5fb9c79 |  | textbox | Initials:
date | 7ebcbdb0-c79c-5687-89b6-f8bd37a559a4 |  | date | Date:
checkpoint-status |  |  | checkpoint | 11 - Installation of Cast Iron Frame A Cover Lid Level – set with contour
text | 767e8c28-69a1-57c3-bbec-e85f8d729a8c |  | textbox | Initials:
date | 0b806df0-c35f-525e-855a-3397dded02f3 |  | date | Date:
checkpoint-status |  |  | checkpoint | 12 - Final Inspection
text | 7b280592-5b70-57b9-82ae-5339e2ab4652 |  | textbox | Initials:
date | 0dacebaf-d571-5fb6-ac98-4a966c50f04a |  | date | Date:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
text | 4698a137-7311-5075-ac7f-8543985b8385 |  | textbox | Name:
text | 6c59abe9-500a-5a92-9189-767d8fab1295 |  | textbox | Position:
date | 6116e931-316f-5d68-87ae-63da8e8b873c |  | date | Date:
holdpoint |  |  | signoff | Signed by
checkpoint-no-status |  |  | checkpoint | Location/Chainage
text | fb11e52c-c9bf-5bce-9b1f-321da5808886 |  | textbox | Location/Chainage:
text | 2f2fcc29-2138-55f1-9e7f-b8ecfcd8c956 |  | textbox | Size:
text | 03348ecd-4a82-565c-a1ec-89bbe339f93e |  | textbox | Class:
text | 0b4c6899-ee87-5fae-a2c5-c517ca541e1f |  | textbox | Concrete manhole lid opening diameter: |  |  | mm
checklist-sectioned |  |  | checklist | ITP - B1004F - Tangoio Falls Steep Underslip - Asphalt Surfacing | itp |  |  |  | Yes | ITP - B1004F - Tangoio Falls Steep Underslip - Asphalt Surfacing V2 | 9d617e70-f1e5-4686-9238-4584fd472829
checkpoint-group |  |  | section | Asphalt - Surfacing (AC 14)
checkpoint-status |  |  | checkpoint | Project Site reps.
text | ee190d90-3d86-58f6-a6c6-d9bffa466a82 |  | textbox | CPS Eng.
text | 11fa5f4e-7937-5386-ab8e-5631764c3726 |  | textbox | Site Engineer
text | 6304bdb9-c9ac-5eab-8992-52619b2b0229 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | cd6e042a-4654-581a-bbae-7870489bd0c0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | acafc2a4-3ab0-5503-ba93-84cb0788694c |  | note | Detail - Set out pegs installed every 20m if required
label | bbd28be3-dd78-5143-ba76-a2119384fe2f |  | note | Frequency - Prior to commencement
label | cd7b564f-3a6f-5b36-87de-089a02b7d1c4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 43ad8b17-7634-51f8-b76f-38554af6269d |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | da18a30f-5f48-5d39-9cd6-c689d9680bfa |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8ddb7e90-e8ec-5c89-9f49-dc7d743f5d4e |  | note | Detail - Determine paving run start/stop locations
label | ebbd04d5-1e88-5012-9186-e2bd60323442 |  | note | Frequency - Prior to commencement
label | 1faa64af-a80f-5f57-be77-013e03db32f6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | d15a5786-1ae7-56c6-a85c-9b51f4a37275 |  | note | Conformance Criteria - Mark out on site
label | daeb8406-a8ed-5fe9-9c1c-e1ed3095f520 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 3 - Material Compliance
label | 3601c097-194b-579e-9d23-b41c1c7f4800 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d3777e2f-aee4-58f0-ab08-ceecac174122 |  | note | Detail - Mix Design approved including peer review
label | cb478996-6698-5129-baee-485997dde801 |  | note | Frequency - Prior to commencement
label | 7da723e8-f8f5-5edd-bcaa-b40ed39de493 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 42268bfa-235e-518b-acea-0502356cb59f |  | note | Conformance Criteria - Material is approved by a Notice to Supplier being issued
label | 11828e6d-65cf-5cb8-ba19-b5b43e40f553 |  | note | Records - Mix Design
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Material Compliance
label | 0dca4c6a-5a26-5c22-9bc8-c2cb6178d48a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 782d0af5-6615-501a-9be1-768cc1f1211b |  | note | Detail - Asphalt Material Quality Testing
label | 6c999260-3af4-5abf-80d6-8441f7c9953d |  | note | Frequency - Prior to commencement
label | fb095ab4-66ce-50ce-a47a-75083f28e8ab |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 5b9c29f7-705f-53f0-a438-b5f3ac281a32 |  | note | Conformance Criteria - Fine and Coarse aggregate Weathering, Crushing, Sand Equivalent, Broken faces, PSD, PSV. Bitumen testing, Penetration @ 25 degrees Celsius, Dynamic Viscosity at 60 degrees Celsius
label | 2cf8c556-4dc2-55f6-9277-20e36daca62c |  | note | Records - Asphalt Plant Results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Asphalt Production Testing
label | 9e136aa4-d12c-5a33-af6f-f37602860b39 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 27c014de-4015-5639-ad06-3d3fcc86bf5c |  | note | Detail - Full volumetric and air voids test 1 test - 1 test per day
label | cc537174-d76b-5389-a90f-a5cd634631d5 |  | note | ○ Binder content and grading 1 test per 100t.
label | d7461b3d-e731-5f23-a8fd-f5d9d34fc77b |  | note | Frequency - Prior to commencement
label | ed98e696-bc9d-5a4f-8ab3-d9ebf3386fb4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing and measurements
label | a1f8ff2d-7a05-53e3-9d4c-44ff6e77133c |  | note | Conformance Criteria - Binder content, PSD, Mix Volumetric, Mix performance related properties resilient Modulus and wheel tracking, mix production temperature and load out temperature
label | 929ab1af-da33-5caf-b528-f2decda2b4e4 |  | note | Records - Asphalt Plant Results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Tack Coat
label | 6e114c51-e434-50a3-9298-07fda70cc838 |  | note | ACTION (Hold, Monitor, Witness) - M
label | d5ff4330-b770-577c-b62a-0e3ac9338694 |  | note | Detail - A Spray sheet for every day
label | e8359d2e-60ba-5795-81f1-1b71e826f188 |  | note | Frequency - Prior to placing Surfacing AC
label | 0ba6d3cf-2418-54e2-9baf-711844020070 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 834052af-6e0f-5d1a-b1d6-fb11ae40b4d4 |  | note | Conformance Criteria - Showing the required spray rate 0.2 L/m2 with a tolerance of +or- 0.1 L/m2
label | 5071ce36-91cc-51f7-9aed-0c57781542c9 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 7 - Construction of Surfacing Asphaltic Concrete
label | 3df799e3-092a-5967-b442-16652946e42a |  | note | ACTION (Hold, Monitor, Witness) - H
label | e4d8d781-d512-5989-8fa1-0990aa255fd1 |  | note | Detail - Site team QA Checks
label | 062ef966-0e39-52e5-b9b7-61f49ebf2204 |  | note | Frequency - During Construction
label | 7235b7c6-4ac5-5db9-b465-c08472fc7c5c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
label | 76378479-46e1-5aaf-ae1d-784fd19e1aa3 |  | note | Conformance Criteria - Delivery temperature, mat thickness before compaction, mix temperature during compaction
label | 98530902-5dce-52e4-910a-8cdaed3f2066 |  | note | Records - Subcontractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Surface finish visual inspection
label | b6795b9f-e2cf-56e8-8ca8-2b72d15f9ad2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 11e75f24-6ab0-5585-91c5-e0cae34603ec |  | note | Detail - Site walk over
label | 32ec15b0-dbc1-5b3e-8973-3738c931094a |  | note | Frequency - Post Construction
label | a53e2b2d-d986-5139-8d3d-2f754ef8032f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b6d36f74-cfbe-5ed7-ac7b-669188ac2671 |  | note | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
label | a394fe70-cfed-5337-8044-c7d6781c1ebf |  | note | Records - Subcontractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Asphalt - Surfacing (AC 14)
checkpoint-status |  |  | checkpoint | 9 - Final Walkover (Snags)
label | 9daf2657-595d-5b75-b5a4-deb17da58295 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b19d482e-9302-50d0-8177-f1e0434d5008 |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | 6a8b72df-e116-5c95-8bc7-4d51a6345011 |  | note | Frequency - At the completion of the Lot of work
label | 903b3b33-7039-53b3-bef9-584877607ae5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | dc8ddcdb-ca9f-5bd8-b539-643a15a16c78 |  | note | Conformance Criteria - Completed report
label | e7fa0f43-274a-51da-835c-e6ee32837502 |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Survey As-builts
label | b179254e-202a-5ffa-9069-d906ff85606a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3d2c4c38-f97f-5aca-9a3d-86473779101f |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | 28b421fd-a702-5a3a-a897-a2a8f3a0d9e9 |  | note | ○ A survey as-built of completed work must be provided
label | eb5a94e7-3b7b-5d12-8cc7-1b643dfc2022 |  | note | Frequency - At the completion of the CWP of work
label | be5865d3-f4a4-537f-8ee4-ef7e169bfda2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 12cd6fd1-ca8a-5be8-9382-843578b4c8c9 |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | 3ee47fc1-797e-56c3-afcc-b4f5f674eda6 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Quality Assurance Deliverables
label | bf44627a-4336-509a-b7fd-b0a9406da1f9 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 65a2d5a8-c4c5-54c4-a172-384eedca78b1 |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | f39f4558-28a4-5117-8e5f-166e50eacef2 |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | 789f0a49-eef0-5649-acfb-05efe69ec35c |  | note | Frequency - At the completion of the CWP
label | 24d611a1-91d9-56dd-925b-9a07cb3b4dd3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 2ed824ab-3cf3-505f-8053-9d66eb41b5de |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | c3921459-0a0d-5cfb-ae15-25815f756569 |  | note | Records - As-builts, NCR's and RFI's
checklist-sectioned |  |  | checklist | ITP - E3001A - SH05 SIP Site 1 - Guardrail & Wire Rope Barriers | itp |  |  |  | Yes | ITP - E3001A - SH05 SIP Site 1 - Guardrail & Wire Rope Barriers | 9f633b7a-3c5c-4843-94a3-aa84728eea43
checkpoint-group |  |  | section | Guardrail & Wire Rope Barriers
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 758eb6ad-2873-5e7b-b204-28da6b6bfbb8 |  | textbox | CPS Eng.
text | bc09aa80-d789-5b2e-9ada-1385248cfba4 |  | textbox | Site Engineer
text | 21cc7cc8-edc4-5855-93b2-8ad8815b53da |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Design Check
label | 1828de01-e90f-5ff8-907c-23774ae62ff0 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 032db625-53ee-506a-9191-82c441d61a1f |  | note | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | d0d9b12f-4fe7-5443-a69c-8e14cdec1434 |  | note | Frequency - Prior to commencement
label | 03579d6e-9b73-58cb-bfad-aa270a5b2021 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 99d5de9d-6452-530a-9b29-822df37a1628 |  | note | Conformance Criteria - National Standard for Traffic Signal
label | 6f0c5e2a-519f-531d-a0a3-96c003eef7e4 |  | note | Records - OFI or NTD/NTC
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | 7144c113-46d7-596b-9d54-9b10611bd483 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 504afca7-5d28-5476-8605-4d039317ea25 |  | note | Detail - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
label | a730970f-7705-5c63-84a3-a6dd45b36a98 |  | note | Frequency - Prior to commencement
label | 28f47454-07de-592c-b726-58f3528c4e6d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | a9535095-c4e2-5219-9f30-97c383244cc6 |  | note | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | 95910492-aa8e-5704-84aa-34a53d57689f |  | note | Records - Approved Construction Drawing.
checkpoint-status |  |  | checkpoint | 3 - Material Compliance
label | 1de6bc03-a39f-5e40-a98c-7c07d46156b8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | dc5ea69d-64a3-5798-8883-777a9672ac91 |  | note | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
label | 7c41ca5d-b7fd-5d01-9890-1f620ca890b0 |  | note | Frequency - Prior to commencement
label | 7400d344-5a39-5d82-8e22-93f7e7cb1009 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | e1f1f435-bca8-5ba5-b12b-a1ee4e0af043 |  | note | Conformance Criteria - TNZ M/23:2009
label | 4c5d73f8-4012-5cfc-a61f-8592efebb882 |  | note | Records - Manufacturing certificates and delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Material Compliance
label | 187d790b-47cb-596d-a198-927bba673fc2 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 06613769-514b-5562-9576-e997de19fc62 |  | note | Detail - All materials to be sourced from registered suppliers
label | 1451a7f4-197a-55f9-8a4b-0f19b25e8798 |  | note | Frequency - Prior to commencement
label | 89a0a243-45ea-576b-85a6-f1ddd6aa80de |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 6e4e0bcc-354d-53b1-897a-37172532e8db |  | note | Conformance Criteria - Registered suppliers
label | 50dd5561-ed78-5e5c-b35c-f61928050176 |  | note | Records - Materials register
checkpoint-status |  |  | checkpoint | 5 - Material Compliance
label | 5dbe622d-7071-5dbd-a7fb-e06535b0105b |  | note | ACTION (Hold, Monitor, Witness) - H
label | d5622037-b6f3-5e86-8d06-60503c8bd0e2 |  | note | Detail - Proposed galvanising repair methodology to be approved by Engineer
label | 7cd29671-4771-58e0-a342-5f4ca2b5fe6a |  | note | Frequency - Prior to commencement
label | 2f3785c8-5b5b-5944-ba4b-ec65a2eeb978 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 895b6383-1974-5552-adef-c8e534cc9245 |  | note | Conformance Criteria - Best practice
label | 48387041-fc19-5901-82a0-f60fe2b42344 |  | note | Records - Approved / Signature
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Guardrail Installation
label | 81bca486-28c0-5488-93c0-71e8559955cc |  | note | ACTION (Hold, Monitor, Witness) - M
label | d3f7622c-50c6-526b-8634-e60ce45e8a0d |  | note | Detail - Certified Competent Installer. All roadside barrier work shall be undertaken by certified installers
label | 2354c452-fac9-5e02-a655-5d4364dd4811 |  | note | Frequency - On Procurement of installer
label | dd2dab29-a83c-519d-85ad-602dac92a1a9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Written confirmation
label | 64c1e163-318f-54d6-aca5-b3135734ba4d |  | note | Conformance Criteria - ASHTAS operative and installer course
label | ad32f265-36ea-5a32-878b-5372b6a0aa24 |  | note | Records - Attendance Certificate
checkpoint-status |  |  | checkpoint | 7 - Guardrail Installation
label | d7748823-3fb3-5d76-b290-18d3496ccdb1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a4636cb8-d0d9-5d3d-b11d-697bee5ddbce |  | note | Detail - Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | 563b2e60-9713-5475-97f4-b32a029f0add |  | note | Frequency - During installation and on completion
label | b8e5a8f6-f9be-55a7-97fd-40429ab03259 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | 5548a4ee-1f7b-5d7f-bed4-d08893a9c104 |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | 82cb35af-2f7c-5824-be58-98a071fec757 |  | note | Records - CS-4117 Guardrail Installation Checksheet
checkpoint-status |  |  | checkpoint | 8 - Guardrail Installation
label | d58c5529-e050-5cd0-8b62-daedbc5a2913 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 3f5b6f11-7096-5c56-beed-0ff73897d113 |  | note | Detail - W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | ba1501f6-67d0-520c-8ac8-5a5b83fc1ace |  | note | Frequency - During installation and on completion
label | 1b550293-e414-5bfb-a39f-6d27fc6a9e26 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | efdf288b-53bc-56a4-9ba1-d6b9df8237b3 |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | accc7b8e-d26c-5871-9206-ec81465d9961 |  | note | Records - Installation Checklist
checkpoint-status |  |  | checkpoint | 9 - Guardrail Installation
label | e3847334-0311-59f8-aee2-a1b98704956f |  | note | ACTION (Hold, Monitor, Witness) - W
label | d4193ee1-9da5-5344-bc84-da08dff87eb5 |  | note | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | 95ec324e-2a29-5287-a41d-782a30ad05df |  | note | Frequency - During installation and on completion
label | 50ba4034-ed93-5670-810c-2fccac864637 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | 081051d0-aed3-53ff-b27a-00c5f581fa0a |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | e7d8a766-36ce-5ea9-b2ff-4c0adfa8e529 |  | note | Records - Installation Checklist
checkpoint-status |  |  | checkpoint | 10 - Fit for purpose Inspection
label | 4b2dba2b-1e04-5918-b73f-3c291a4f8032 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e5b6e777-3067-5a57-b43a-6a3dfaed1384 |  | note | Detail - Barrier to undergo fit for purpose inspection by competent person. System checklists to be completed and co signed by contractor and CPS. All faults to be rectified before acceptance into network maintenance and RAMM.
label | fab7481e-e2fa-5c85-9a45-8bf66e7b72a2 |  | note | Frequency - Prior to trafficking,
label | 81ae9a3d-f56c-58c1-9037-2d275e25c4d8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 824fdb24-8ff0-57d1-9778-762e0981da75 |  | note | Conformance Criteria - Pass inspection
label | bcb8d528-3209-5489-a274-6e0ee6ade9d0 |  | note | Records - Confirmation from inspector
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Final Inspection and Handover
checkpoint-status |  |  | checkpoint | 11 - Quality Assurance deliverables
label | 19fa0a23-d736-55db-a23c-7014f38121ec |  | note | ACTION (Hold, Monitor, Witness) - W
label | 36648b68-29f7-566e-b53a-44423610372f |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 926c0adc-9a24-50c4-a4d2-c4c43ee66be3 |  | note | Frequency - At completion of Lot
label | 3ba9d05c-4cb2-53ca-b9d5-17b1a4b38cb1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 237c8c65-8236-51b2-b2d5-927643e35a2c |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 1f1dd3b5-c5c0-5ce3-9883-ed9f11904e0b |  | note | Records - As-builts, CPS COR Report, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 12 - Completion Sign Off From Fields Below
label | 781d06b1-13d8-5cd3-b2f7-8de786d574d6 |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | ITP - F3202B - Earthworks Mangatuna River Buttress | itp |  |  |  | Yes | ITP - F3202B - Earthworks Mangatuna River Buttress | a186a86a-03fd-426f-90c4-e10ceef55c74
checkpoint-group |  |  | section | Section 1: RECEIVING INSPECTIONS
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 3d7c1d9f-5c85-55ef-a48a-2d9580d45035 |  | textbox | CPS Eng.
text | 5c1b453e-4b8f-5e9c-a8bc-c8df3ae99bcd |  | textbox | Site Engineer
text | b97fca2a-d94d-57ab-8ecb-3837af0ee861 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Rock Armour (D50=450)
label | b00f8af2-f079-5b7f-ab9e-6310bdaa85c2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8befd2ba-2da4-5530-a680-22d1f8947345 |  | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
label | 27c29eca-e287-5231-ad62-d5e1ba349b9e |  | note | Frequency - Prior to commencement
label | 0f20889c-51b7-5f67-a84b-c22aa052027c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | c7a1bbb1-dfc3-526a-a1a7-c35084577642 |  | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 of 450 with a minimum specific Gravity SG of 2350kg/m3.
label | 136e042a-f0f7-5a48-84c0-051e96d153b7 |  | note | Records - Material source test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Bulk Fill (GAP65/GAP100) or similar
label | 680257d4-0e81-55cf-a714-3072c550a966 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b9992734-21be-51e3-b722-8e316082be78 |  | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
label | 2152777b-98b5-5769-b7ba-867f4e1c0317 |  | note | Frequency - Prior to commencement
label | 7da5b836-ea72-5151-8941-67379f1c254a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 9fcec33e-52d9-5851-ab1d-a8be944053df |  | note | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
label | b4f02d22-66c7-522a-8409-464b56a6b5d9 |  | note | ○ Material source testing
label | fbbbd757-c4df-5b35-9eee-f7fe2783e505 |  | note | Records - Material source test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Class D A39 Geotextile
label | 7ce55843-bce5-5f48-b0b9-1a3079e364ec |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2a681a28-74d1-53a2-ac03-88e0939f9604 |  | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001, NZTA F/7 compliant
label | dbbb33da-12b5-587f-8a8c-a0e532388a49 |  | note | Frequency - Prior to commencement
label | 05203b0d-81f9-5713-b109-c24486951430 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 813dc71e-5d49-5952-a36e-2168d9f99b7f |  | note | Conformance Criteria - NZTA F/7 compliant before placing foundation material and engineered hardfill
label | ce1cd929-bf90-5161-bb5f-47d29975d37f |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.4 - Class E A49 Geotextile
label | 0767e3ab-c632-5e49-bd98-67c699caa77a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6a482b2e-5935-5d5f-8e54-17f4747a9585 |  | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001, NZTA F/7 compliant
label | dc145734-9009-550d-a343-84f5c3f0806d |  | note | Frequency - Prior to commencement
label | 6460516a-3c76-527e-8a6e-9ff2912d3acf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 6f78b780-df08-5b0f-971a-73b2ef4f83e3 |  | note | Conformance Criteria - NZTA F/7 compliant before placing foundation material and engineered hardfill
label | 43f8edb8-5902-5e28-9a0b-82cd67c4384a |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.5 - Megaflow strip drain or drainage blanket for seepage if encountered
label | 07f36520-c2ee-5128-af71-6b3d74bb539b |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9973be82-d622-5270-88e9-565a40f39b1d |  | note | Specification/Drawings Reference - Buttress typical details and F3202B-DS-GT-RP-0001
label | 21c6d585-d824-506f-b140-4dacea588efe |  | note | Frequency - Prior to commencement
label | 2cf5a38e-9322-501c-bf81-8895cf9e2d84 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 20310bcd-6455-560d-9990-3dbfb65cbb75 |  | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
label | 8bf89a32-8214-5c57-8c22-5e7e96fda505 |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.6 - AP40 (Basecourse)
label | 3f3ee13f-1f28-5611-a3c5-31e243f64609 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7af918f9-ea37-51a8-a71a-67c9308eba41 |  | note | Specification/Drawings Reference - TNZ M/4
label | 0519996c-e15a-57c2-9755-b007c4f4b1c6 |  | note | Frequency - Prior to commencement
label | b77a741f-2fae-5bdc-804e-0f4d1e2b00ec |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Testing
label | 38052fc3-5cf1-5193-bcf2-12848615d78f |  | note | Conformance Criteria - Comply with TNZ M/4 specification
label | 7d76500e-05e0-50dd-bf3f-bb3a6ea38247 |  | note | ○ Source property testing
label | 461c865f-4852-5ad3-876c-276a44afe553 |  | note | ○ Traceability of all materials delivered to site
label | f9028564-8aa8-5dc5-89f6-d97ada6b1200 |  | note | Records - Lab test reports, Delivery Dockets
checkpoint-status |  |  | checkpoint | 1.7 - AP65 (Sub-base)
label | c204980c-2ac8-5007-bb8d-6c4f8c3c4c6f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6d9fa096-e2d8-57e5-a2d3-0e84c084d0fe |  | note | Frequency - Prior to commencement
label | a8c52fda-c8c7-5e0c-b704-70263e3fa920 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 7cd40b0e-6936-5daa-b853-2bba1150dea7 |  | note | Conformance Criteria - Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak)
label | 14b83719-42c2-5b70-96c0-c64ef0be9235 |  | note | Records - Lab test reports
checkpoint-status |  |  | checkpoint | 1.8 - Grade 3/5 Chip
label | f52df208-4a2d-5e67-ae7b-43d8ac9c704d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 50a8b36b-360b-5535-962b-a43cbd9b9d02 |  | note | Specification/Drawings Reference - NZTA M/6
label | f58bcf40-2052-5f8e-9b4e-da1b66a5331b |  | note | Frequency - Prior to commencement
label | 08b5465c-7f7c-5608-8f4f-aaf730b86ded |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission, Testing
label | dc5d071c-fccd-5f97-a169-2f05fbb46e23 |  | note | Conformance Criteria - Comply with NZTA M/6 specification
label | f0629f67-5ccd-5006-9891-1fa9e93eb42a |  | note | ○ Source property testing
label | 656a3022-1e15-562e-b5c2-2986f961a8a6 |  | note | ○ Traceability of all materials delivered to site
label | 5d9a672b-d6f7-584a-bf0c-3fef2702d28c |  | note | Records - Lab test reports, Delivery Dockets
checkpoint-status |  |  | checkpoint | 1.9 - Cement Material cert
label | ca75a6b3-f237-5210-b085-7cd3a1ee4d86 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7dd82d59-98b2-5d2a-bbeb-c1562e869be2 |  | note | Frequency - Prior to commencement
label | 96ac36b4-121c-5b36-8909-e595482d26a6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 0bb48d40-3935-5d64-bcd0-005a492e834b |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.10 - Bitumen
label | 698c226c-404e-54cf-a040-8779ce4736cc |  | note | ACTION (Hold, Monitor, Witness) - W
label | 677dd4d0-2678-590b-b9b3-d890aa1fb45c |  | note | Specification/Drawings Reference - TNZ M/1
label | 29befbed-4754-5fc8-9269-621b215bfde4 |  | note | Frequency - Prior to commencement
label | c3254eaf-6b4d-5c1b-b59e-fac4f151ef9f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 4970f541-c2e3-5cfe-8a16-3a139e62f2ff |  | note | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
label | aa577a09-1202-536c-b628-ead433a040a3 |  | note | Records - E2 Certificate
checkpoint-group |  |  | section | Section 2: IN PROGRESS INSPECTIONS
checkpoint-status |  |  | checkpoint | 2.1 - Survey Setout
label | 542f2082-647c-5236-b608-ef31d1e4a2e8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 84636dde-d7bd-5c39-b076-9f9c43d7c2e2 |  | note | Specification/Drawings Reference - Consistency with Construction Drawing
label | b8c466f6-a0eb-5216-b46f-732a3a666d7c |  | note | Frequency - Prior to commencement
label | 0c54ce75-bc03-5bce-a46d-117ba2764462 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 6a8e6dde-26e0-5285-86c9-ee44ea6d915e |  | note | Conformance Criteria - Set out extents of fill and check against design drawings
label | d955f81a-8c4e-5136-97cc-f7a9441f416f |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | 76c3e1b1-5136-555b-b030-f20052bdf3de |  | note | ACTION (Hold, Monitor, Witness) - W
label | bb53824c-b923-5d23-a63b-065d03f06fa7 |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | 7469758a-a608-513f-82db-219261b54d0a |  | note | Frequency - Prior to commencement
label | 88c8594a-3741-5630-8870-8cb5b217baa8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 0813a297-e691-5992-bf95-00bfefa5c3e6 |  | note | Conformance Criteria - Remove and clear the vegetation
label | e12c85e2-93f3-5228-a998-74db516e0a29 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.3 - Subgrade Excavation
label | bb6aba83-3f04-562f-9df4-62b2fa513b66 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f70d0d8b-9600-5f36-88ac-6be2af596b59 |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | 27dca832-2785-54ef-9131-88adb93688fd |  | note | Frequency - During Construction
label | 1aabf870-6dd6-509f-b016-62a13c127795 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection During Construction
label | 1fa691a7-ed17-5068-8593-f9c2c8057a23 |  | note | Conformance Criteria - Engineer to assess foundation material suitability
label | 6a4af242-6d59-5ced-a5cb-d7fac7799483 |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Subgrade Inspection
label | 648f509b-f386-5834-8772-ec6a014c2509 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6aef5cb7-bb2e-5a9d-84b7-2d8ee34ad9d7 |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | cb744bee-8930-5bd5-a389-b2c36a993826 |  | note | Frequency - Per area as required
label | 78e490b5-659f-5844-a93e-3ad899756c12 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | 3d173007-afae-5e31-bc08-c84874b1f7b4 |  | note | Conformance Criteria - Inspect fill foundation.
label | f1cda49b-4f22-5482-a138-02564a48c337 |  | note | ○ Fill foundation must be approved, in writing, before filling commences
label | eadb1661-dd59-5ab5-9f2d-daceb9c89f22 |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Ground Improvements
label | 82da808d-a6e9-509c-b1ef-c44e62862daf |  | note | ACTION (Hold, Monitor, Witness) - H
label | e16d32f6-8f9b-597f-a35a-338941673659 |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | 6acc7daa-206c-5c84-b7ae-1ed6b0154be7 |  | note | Frequency - Prior to commencement
label | 640d38b7-26f8-53ad-aa15-162bd7b59e10 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | aa4eee53-d14b-57cd-8474-49516914cdd5 |  | note | Conformance Criteria - Any area that requires Ground Improvements must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence
label | 8ab4b7da-203c-5d3e-9878-5ddd6f67cc54 |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Class D (A39) Geotextile installation on the excavated face
label | 7a70d917-86a8-5b25-90ac-6347a80c696d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5ec8eb08-d906-57a5-a02b-00d1cb74cb86 |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | 683006d6-f046-5508-9d2c-f347f588ba1b |  | note | Frequency - During Construction
label | 5cfa5334-e7e3-58cf-9554-617b6560ed4e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3f8a5e9c-3990-5695-abcf-7c52062156b2 |  | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill.
label | 4c70292e-2cfe-5fd0-b01f-dc62b08b2670 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.7 - Megaflow strip or drainage blanket installation for seepage if Encountered
label | 1ce34d9c-889a-5559-b5de-1c057578050e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7f7d8e7f-6f58-5ed0-813b-fd56d8261f64 |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | 9edadbc9-b6dd-5b09-bfb2-57ae82d66900 |  | note | Frequency - During Construction
label | eeb80f6b-c46e-5201-aca1-a07667b95fcd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 23d2a3d7-1ded-57c0-a124-72928072442d |  | note | Conformance Criteria - Engineer to assess suitable drainage location.
label | b78ad7f9-49d5-5800-b43a-83a1135688d6 |  | note | ○ Drainage positions to be confirmed on site by the Engineer. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required.
label | 9c85a504-eadb-54a5-a08c-ff5271a5bd1f |  | note | Records - Photo's, Drainage Line record check sheet (CS-4025)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Bulk Fill placement
label | 55859e77-ad8f-56a6-9568-78bc91a7459a |  | note | ACTION (Hold, Monitor, Witness) - M
label | 09388e0c-ba09-5f55-a263-a01af0cdcaae |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | 825d3590-ff3d-5753-8cb6-8927ef74ec96 |  | note | Frequency - During Construction
label | 130c02da-1530-5544-ac76-3abac2533208 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 6e8b59b2-9f17-56a4-b804-50c2aad9290d |  | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control.
label | 5f60c18b-8990-5199-9fb1-8988bb79c697 |  | note | ○ Fill should be placed on dry subgrade.
label | 62efdfb3-e662-5fab-8e8b-a5262a9eba00 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.9 - Bulk Fill Compaction
label | a1bb71b0-6d6c-5974-b797-31646af81fc5 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1c0ce3d3-fe73-544b-81dc-fa760fe4c5d5 |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | 726461c1-10e8-5561-9033-fecf183728f9 |  | note | Frequency - During Construction
label | 6fd17e7d-8670-5aa4-826f-e1a099313f7b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 9f8ab8f2-12a3-564d-a661-ac73a9b6f97f |  | note | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
label | 33c3a105-8533-566e-9522-c24021fdd28a |  | note | Records - Compaction test reports
checkpoint-status |  |  | checkpoint | 2.10 - Form and cut fill batter as per design 2H:1V
label | c1447588-bcb1-5138-8c2e-5acb45348eef |  | note | ACTION (Hold, Monitor, Witness) - H
label | b2852862-03f6-592b-bc89-6485e050994e |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | 9abab4f5-92b3-53c9-9b09-3ab6adaee9d9 |  | note | Frequency - During Construction
label | ee9db302-4d8a-560a-86b4-c09b6f0eb93a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 46083da9-b8b9-598f-a6e1-2919719d344c |  | note | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
label | 45ada656-c772-5e8d-8511-50bdc4a9d9c9 |  | note | ○ Slope angle of buttress is to not exceed 2H:1V
label | f8e46bc7-537e-55c1-b39b-3abd12758fd1 |  | note | Records - Survey as builts
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11 - ClassE (A49) Geotextile placement along the face of fill batter
label | 33a098a7-f7fa-5c48-8484-df5ddaf79e19 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f1c04c40-b704-5772-98e6-9b6458d79198 |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | b6e4ab50-e4e8-5e72-ada2-84ec3c4c81e5 |  | note | Frequency - During Construction
label | f55d5f83-f183-57a9-80db-1f91607bd4a9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 5cd3c0c3-ddf4-5075-b6c8-bced2a03d6ef |  | note | Conformance Criteria - Class E geotextile to be placed between the rock armour and bulk fill
label | 9ca5f7e3-444a-5233-b14f-be8ea28e2bfb |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.12 - Rock Armour placement along the face of fill embankment
label | c0bad696-8b13-5779-9c9d-8943af8d1fe5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | af348cff-e741-5f40-b59b-3dac75926440 |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | a7cacb3d-5b00-572e-b33d-5862ce6fe59d |  | note | Frequency - During Construction
label | 6b9290a1-c439-5271-bb6e-9f5916d9f88e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | 15c4a07d-7edb-544e-8acf-ff8be93be4d7 |  | note | Conformance Criteria - 2 x Layers of Rock riprap (D50=450mm diameter)
label | fdc58580-1827-5f14-8ad6-d1919a214dff |  | note | Records - Photo's, Survey as builts
checkpoint-status |  |  | checkpoint | 2.13 - Rock Armour key into ground
label | d7647abc-d16e-5735-a101-09ab95d62cde |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6c69ad48-3728-5f00-9d79-a0bdc844a3e3 |  | note | Specification/Drawings Reference - Buttress typical details C and F3202B-DS-GT-RP-0001
label | 5fcdbeb7-2e12-5eb7-8cb5-fc487539391a |  | note | Frequency - During Construction
label | e5718869-eb2d-5bc5-89ae-cf871f5aa24e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | 5a4c0d3c-26b7-55f6-8983-2a4fbf1dbb3a |  | note | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 1m to 2m wide.
label | 5ce8fbfb-38d7-5539-b1e7-e55fbe2a1178 |  | note | Records - CPS COR report and survey as built
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 3: IN PROGRESS INSPECTIONS (Pavement)
checkpoint-status |  |  | checkpoint | 3.1 - Saw cut existing pavement
label | ec26ab9c-f6eb-5f36-b29b-685aec8879fa |  | note | ACTION (Hold, Monitor, Witness) - W
label | 88d315e5-41be-5a64-8c80-494ea869b685 |  | note | Frequency - Prior to pavement construction
label | da79f036-9eb4-5cdc-a08a-68c9d2003f29 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | bb5b1dda-0fd2-5859-89b0-561010fd51dc |  | note | Conformance Criteria - Smooth and straight saw cut
label | ea1fd34c-cbd9-5059-8e60-43945f389adc |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 3.2 - Subgrade construction
label | 59c5d923-a8e6-5cd2-8c41-5e7cf7be6141 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f947924e-7b5e-512f-8d92-3415d70f999d |  | note | Specification/Drawings Reference - TNZ B2
label | ed4c1fb5-61df-50b8-81a8-9722afe0612b |  | note | Frequency - Every 20m
label | bb66882a-f8ae-5990-a305-e3dd93ed1ca3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | a212ea49-90f4-5d80-bd89-8fceaa319bbc |  | note | Conformance Criteria - 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92%
label | 31f13429-a713-5eea-a23e-1f0e112345de |  | note | Records - Test reports
checkpoint-status |  |  | checkpoint | 3.3 - Subgrade Cement Application rate
label | e577e1cc-aa18-5a72-9094-2c78569fbc22 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 167a3b3e-602b-5a95-acfc-f426130a0964 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
label | b6925712-2da2-5dc2-ac66-5ea4c24c808e |  | note | Conformance Criteria - 2% cement stabilisation at 250mm deep subgrade
label | 6f479d70-8c21-5b8f-994e-a5321da1be26 |  | note | Records - Bag test records
checkpoint-status |  |  | checkpoint | 3.4 - Sub-base construction
label | ba15115a-e11b-5bc5-b4d0-bf70fefb6b20 |  | note | ACTION (Hold, Monitor, Witness) - W
label | edb9bc33-7068-5834-99c3-e7394ab7a04d |  | note | Specification/Drawings Reference - TNZ B2
label | 92f4ae29-af5d-59df-a759-2e92dd9763e5 |  | note | Frequency - Every 20m
label | 0a13e1f6-d5cf-5cdf-96d2-d5049e0e88e1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | c3b77605-7677-5d19-9d88-391c5e30fefc |  | note | Conformance Criteria - 200mm thick AP65 sub-base compacted to a minimum dry density of 95%
label | 542e96ad-2928-55a2-922f-6d707724c8ae |  | note | ○ Average 95% of MDD with nothing less than 92%
label | 44a0171c-b1c7-546e-a655-d72c16982039 |  | note | Records - Test reports
checkpoint-status |  |  | checkpoint | 3.5 - Sub-base construction
label | 33035d97-49bc-5e9c-b4df-70ae6cc415a3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 22fea1ee-404d-5b6d-8dd8-24544ba62b39 |  | note | Specification/Drawings Reference - TNZ B2
label | ddce049e-ec81-5288-ae64-a482c545153f |  | note | Frequency - Every 20m
label | 54bfb7ce-c633-50fa-8959-d7af9cb1fb28 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | 935c7ef6-b31b-50c5-a363-366199973242 |  | note | Conformance Criteria - CIV>=25
label | 8ef13e17-8de3-5b3f-a904-db7323709cd3 |  | note | Records - Test reports
checkpoint-status |  |  | checkpoint | 3.6 - Sub-base construction
label | 224fa1a8-9a43-5793-8264-4c6bbdf307f2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 98931da3-83d1-542d-b92a-02cc441ed142 |  | note | Specification/Drawings Reference - TNZ B2
label | 56aa2af6-125e-537c-9ccb-173340490250 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey as-builts
label | 0438a408-0410-52be-96a6-6e743de45d38 |  | note | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
label | 84b6b003-4157-58a5-a5b7-a9572de8e18e |  | note | Records - Survey as builts
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Basecourse construction
label | 27833f22-b022-56c1-be48-4251b3cbf8b4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 42c1b2b1-0797-5253-83b0-13bf261e42b5 |  | note | Specification/Drawings Reference - TNZ B2
label | 34928bc4-a8a0-542b-9372-0e0da6ff5610 |  | note | Frequency - Every 20m
label | 3e320a1c-a791-5dff-943e-cbad4fa0db0c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | 2f4a381f-a4ff-5771-a4b7-991ae5fa873d |  | note | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%
label | 40b30b88-a2b9-5afb-b071-e9b423048012 |  | note | ○ Average 98% of MDD with nothing less than 95%
label | 8761add4-8b3f-5062-a24f-1304349040a2 |  | note | Records - Test reports, Photo's
checkpoint-status |  |  | checkpoint | 3.8 - Basecourse Cement application rate
label | 1fa8ae3d-718a-5150-a3cc-da6c24ec991f |  | note | ACTION (Hold, Monitor, Witness) - W
label | bb3d312d-0628-5808-a2e1-88557cefc52d |  | note | Specification/Drawings Reference - TNZ B/5
label | 0e071a12-de0c-5b7c-9209-217bd5953e56 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 4373e81c-929a-55b8-b90b-4dfe50fea19b |  | note | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
label | d003697d-f7bd-5e72-9499-8c4352170753 |  | note | Records - Material specs, Photo's
checkpoint-status |  |  | checkpoint | 3.9 - Basecourse construction
label | b8890d7a-3841-543d-9446-e9d7109bf58a |  | note | ACTION (Hold, Monitor, Witness) - W
label | d56c1b13-6537-5914-8b15-7ee7965ce103 |  | note | Specification/Drawings Reference - TNZ B2
label | a3cd02cb-e8a5-5299-afff-9fbda0e80bd2 |  | note | Frequency - Every 20m
label | a70b5b19-a388-56e5-adb0-e3af6df4a5e7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 52370be1-8e29-5738-a5b3-f535ad85f216 |  | note | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
label | 7713d8af-334e-573d-a9a5-f8f478a41259 |  | note | Records - Survey as builts
checkpoint-status |  |  | checkpoint | 3.10 - Basecourse construction
label | ee4f6a9d-922d-55c4-899c-aea300a00385 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b343250a-186b-521f-ba10-ae42fd5309ca |  | note | Specification/Drawings Reference - TNZ B2
label | c208e9b8-f0f5-5e3a-991c-46155cb970b8 |  | note | Frequency - Every 20m
label | 898df548-2eea-53dd-972a-8cf848c0292a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | 7ddf0d1e-b5d6-50e1-8913-67048251a3ff |  | note | Conformance Criteria - CIV>=25
label | 12d4e996-ea15-516c-afc5-a8514aa1e730 |  | note | Records - Test reports, Photo's
checkpoint-status |  |  | checkpoint | 3.11 - Basecourse construction
label | 355d14ba-d90e-57cd-a82c-e45ce559983e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5ab01e68-8180-508a-9fe5-024aea400c2e |  | note | Specification/Drawings Reference - TNZ B2
label | cae5a6fd-1c0f-5097-900f-60e036a4b2ca |  | note | Frequency - Before sealing
label | 0739e501-cf0d-5c88-926f-5109c4869a5f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | 615793be-f992-566e-9f8d-3392a0f7160e |  | note | Conformance Criteria - Mosaic surface
label | fb804712-9a83-5d71-a72f-04dd2c9a4020 |  | note | Records - Photo's, Pre-seal checksheet (CS-4060)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.12 - Applying Bitumen
label | 14b04779-8899-5f3c-8dd5-c2f94a6c43b9 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c8ad93ec-8b13-511c-a91e-056715c9baca |  | note | Specification/Drawings Reference - NZTA M/6
label | bc8f4b1c-2f1a-557e-b850-0ec20e4eae16 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | e46f6a88-c3f9-51ff-9a07-dac7ef9cba7e |  | note | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
label | 8b97e749-8551-55cd-9f5f-7249b9f66106 |  | note | Records - Photo's, Pre-seal checksheet (CS-4060)
checkpoint-status |  |  | checkpoint | 3.13 - Degree of saturation
label | 9eb30f4d-9c42-52e4-a481-3023c92b54ee |  | note | ACTION (Hold, Monitor, Witness) - W
label | 30542b94-b336-5c5c-b3c0-9b311be92f17 |  | note | Frequency - Before sealing
label | a076e980-9d73-57f6-af04-8b78b87e809e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | f3debbbd-a937-5f75-9df6-dea338fae89b |  | note | Conformance Criteria - Degree of saturation should not exceed 80%
label | 343d839e-0a81-5eb7-8377-bd87504ea81a |  | note | Records - Pre-seal checksheet (CS-4060)
checkpoint-status |  |  | checkpoint | 3.14 - Chip seal laying
label | 36a0cdc8-39ad-5630-b175-0b6ca085fddb |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8a8f7375-559a-5799-8c7f-1d36bbede43c |  | note | Specification/Drawings Reference - NZTA M/6
label | 01f6c1aa-51ec-5f01-87ac-8652e0023a88 |  | note | Frequency - During Construction
label | 65dbce93-d542-5c49-8f87-bb38c8d3134d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | c02f9e9e-ee7b-5ddd-8880-0a2d1d020ef1 |  | note | Conformance Criteria - Grade 3 and 5 chip seal
label | 45531bcd-71ac-5fe9-8e90-ffa5460c973f |  | note | Records - Material certificate(s), Photo's
checkpoint-status |  |  | checkpoint | 3.15 - As-built Survey
label | 50804e25-fddd-5a4a-9491-d5b420eaf227 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f70e1beb-b5d1-5262-8c99-f6d355a931b8 |  | note | Frequency - At completion of Lot
label | 09f3d00e-b94b-5c9a-bc7a-998586c9a62f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | 88ce1934-31d3-5685-b5b3-bc4479ce21e0 |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | 072b3f7a-d820-5e48-a889-f574a91a250e |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 4: Final Inspection and Handover
checkpoint-status |  |  | checkpoint | 4.1 - Quality Assurance deliverables
label | 81176b79-9ef0-5143-98dd-5530f59a372a |  | note | ACTION (Hold, Monitor, Witness) - W
label | dc35f08e-1abb-548f-870b-c75856ce7ca4 |  | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 1094fc3c-2de7-5e2c-b8ab-4a4265a05c99 |  | note | Frequency - At completion of Lot
label | 06301faf-674b-51b0-95e4-fed016502ea9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 2618d148-cea5-5564-af6b-381c5f8d1e64 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | ef2afa73-b1df-5b6d-b891-373b76d35837 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 4.2 - Completion Sign Off From Fields Below
label | 7277d007-af50-5af1-88bf-9209083f0d19 |  | note | Records - Signatures
checklist-flat |  |  | checklist | ITP - G1202A - Waikaretaheke Riverbend Recovery - Network Drainage | itp |  |  |  | Yes | ITP - G1202A - Waikaretaheke Riverbend Recovery - Network Drainage | a237353b-2194-49c6-b9aa-762b2474f4bb
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 7fbddc50-e153-537c-b301-3aefd19c37b4 |  | textbox | CPS Eng.
text | b89050fd-c618-5fff-9847-038b72e20eea |  | textbox | Site Engineer
text | 64b83f64-e765-5ac6-b2bd-f5a5bc8ef4ec |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 2e57edb8-9554-5d89-b2d4-e135d311d621 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 67d7e0eb-3927-5068-9b49-86fea18c8b0c |  | note | Detail - Setout inlet & outlet points with inverts as required by Contractor to construct to design
label | e909b721-0b58-5beb-9edc-fe87de61d607 |  | note | Frequency - Prior to commencement
label | e9f8aaa1-8df2-500f-ad78-553217978fe7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 57f6de6f-09c8-5dd3-b90e-b0517be7f089 |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 2 - Locate existing services by hand digging/hydro excavation
label | 00e93fb7-4f8f-5020-808a-d389ad869983 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 71739925-c04c-5b65-bffa-475a35c3cb8f |  | note | Detail - Ensure all services conflicting with the line of trench has been exposed by hand digging/ hydro excavation
label | ded29cd8-df38-5728-8e6c-8d99bb830421 |  | note | Frequency - Prior to commencement
label | 6b1ca492-8faa-5b93-99f2-bec14275bde2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Potholing
label | c005ee1d-e81e-5b91-9098-a83204413e86 |  | note | Conformance Criteria - All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. As-built all services
label | ff27047a-17e2-5296-86aa-6a7a24792304 |  | note | Records - As-built Drawings Doc. Review
checkpoint-status |  |  | checkpoint | 3 - Trenching and Excavation
label | 01c1baff-6244-539c-a2c8-c453e5df57f1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 84be7284-861c-54f8-a854-46f0e5be9470 |  | note | Detail - Inspect trench profile and ensure it is correct to minimum drainage standards
label | 0c975529-3411-52b2-90f4-6b408ff56c17 |  | note | Frequency - Daily
label | 697b7ba8-9aa5-5eba-aa85-4ab801ca8e79 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | 40c2e924-07eb-53ae-a072-fcc784eb7efd |  | note | Conformance Criteria - Line and level is correct
label | 10fd0aef-25ba-5aad-8db0-5db58a8f1624 |  | note | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint-status |  |  | checkpoint | 4 - Trenching and Excavation
label | 4f54e8f8-4522-5a4c-b600-c65c4614a9e5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | dc9a9e5a-2018-5803-9838-c1a56de5cef1 |  | note | Detail - Ensure trench width is sufficient to provide enough space on either side of the pipe
label | 434a48c3-101f-564e-8b74-76d558524aa7 |  | note | Frequency - Daily
label | 06d2fa9c-2eef-5e41-afe6-78aaac36e186 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | c7147289-a3a7-5661-927e-945b4373f524 |  | note | Conformance Criteria - D/6 or 150mm whichever is greater on either side of the pipe
label | 157f966a-1aac-5419-9165-912860d594f8 |  | note | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint-status |  |  | checkpoint | 5 - Foundation Compliance
label | 7c5404f6-c18c-5f90-be33-d4ef39d7e7cf |  | note | ACTION (Hold, Monitor, Witness) - H
label | 44c6b0f4-553d-5564-af85-437d9528592c |  | note | Detail - Test formation level on completion of excavation to check if undercut required
label | d15c4f64-3419-5d57-8136-738022579b13 |  | note | Frequency - One test per 20 linear metres
label | 468c2bb8-6d36-5038-8995-70de93f229b8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
label | 34680943-5851-5855-a20a-25f158c4e333 |  | note | Conformance Criteria - If CBR is less than 50kPa , advise Engineer
label | f3be3a46-787c-5d0d-859c-0ee33cef8358 |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Pipe Bedding Material Compliance
label | a0297ffc-d5b4-5448-a980-df5b3588abc1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 223b949c-f401-5295-bdaa-f01640bcbdc4 |  | note | Detail - Material to meet specifications dependant on material type selected
label | 1f2e95b6-de68-5128-9dbe-474f42c4415e |  | note | Frequency - Each material used
label | eddf6694-03fd-524f-b8ac-05a152d35b95 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 6398ce0c-f496-504a-8b72-14ceabb11d8f |  | note | Conformance Criteria - Reject chip 10-20mm
label | 03038752-fe37-5361-945b-1035fcc56b5b |  | note | Records - Supplier Documentation / Lab Test Report
checkpoint-status |  |  | checkpoint | 7 - Bedding
label | 7cb6fb8e-5f40-54a4-99a6-52725d9eefb1 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d8a0b1a5-ee4d-5da8-8cd1-37097d7fee45 |  | note | Detail - Bedding - Ensure correct thickness of bedding is placed and compacted
label | 791c1f4f-8d38-5894-8819-5fc368bfe388 |  | note | Frequency - Daily
label | dbdd8854-4faf-5dc2-8839-49c493292675 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | a17a73bb-233a-5322-9492-756a88f084cf |  | note | Conformance Criteria - 100 mm thick bedding for all mm dia pipe
label | b52f4a88-73e7-50b0-9689-4f36cf9a9e9e |  | note | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint-status |  |  | checkpoint | 8 - Pipes and Precast Units
label | d59db7be-1758-56f2-b997-40be14b371f0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c07132bd-22de-5eda-8f66-bcf29f4bcef3 |  | note | Detail - Confirm pipes diameter, class & jointing type as shown on the drawings, and that the pipes are correct and in good condition.
label | 20c57cd5-4855-5913-a869-75b183314a06 |  | note | Frequency - Each delivery to site
label | bbc3d58c-70d5-57af-bdb1-a0b19755a341 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
label | 0a49ea97-22ce-58d7-a53e-d66f504c7c23 |  | note | Conformance Criteria - Pipe - Diameter & Class, Wingwalls, Manholes, Cesspits etc.
label | 250d41ae-1418-54c5-b6b9-32497f33bdc1 |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 9 - Pipe Laying
label | 4400a3b5-2530-581c-ad21-fcf7c902ec1b |  | note | ACTION (Hold, Monitor, Witness) - W
label | cd6fb686-cc99-5fb8-827d-1617ad9524eb |  | note | Detail - Pipe Laying -Variation between design invert level to as-laid invert level must be less than 5mm. Variation of grade of one pipe to the next shall be less than 3mm
label | f26d4beb-12a2-542c-b8e6-3d4e19451be5 |  | note | Frequency - Daily
label | e3b9dbc3-b95d-5af3-8261-ca846a3a01de |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | ffe8f492-0d46-5eb0-9ddb-233c691a9cdd |  | note | Conformance Criteria - Invert level <= 5mm and grade <= 3mm from design levels
label | 71b56eec-c0a0-5559-9194-100322d0fb8e |  | note | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint-status |  |  | checkpoint | 10 - Pipe Laying
label | e5512f07-b9cd-5861-95db-dad2c1eccc61 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ca632798-0337-582b-b470-d65030707d54 |  | note | Detail - Inspect pipes prior to backfilling to ensure they have been installed correctly and the joints are in place. Check for gaps and/or defects and check pipe alignment for straightness
label | e0c8e9d5-b329-5bc4-90a9-040f3e1fe97f |  | note | Frequency - Prior to backfilling
label | 29f3f393-e23f-5c70-bed9-c8fc4adc1f59 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | 6cf098c6-bab0-5bb1-b483-70d11ee27a98 |  | note | Conformance Criteria - No defects/ gaps / pipes are aligned correctly
label | 413c0741-a844-5745-9444-facfa24029ca |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 11 - Pipe Laying
label | a7c896ad-9fb1-5293-920d-6405126b08c3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 634a6ba0-f705-50cf-af46-8e9caf759ede |  | note | Detail - As-built survey of pipes installed
label | c47378e5-576c-5cba-9c66-29962c122a99 |  | note | Frequency - Once line is completed between 2 structures
label | f498b9c0-4ea3-563e-a3a9-6d21fe06d3f0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 831f86e7-0fdd-5d61-9a11-45e52b8f0448 |  | note | Conformance Criteria - Invert level <= 5mm and grade <= 3mm from design levels
label | 55ebd781-9730-5a30-90d8-5184e3578835 |  | note | Records - Survey Receipt
checkpoint-status |  |  | checkpoint | 12 - CPS Engineer Pre backfill Inspection
label | d3ece75b-2896-57da-addc-7628fc683272 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1051376c-235b-559d-87e7-46ab0573abf6 |  | note | Detail - Inspection of pipes prior to backfilling to ensure they have been installed correctly and that the joints are sealed. Check for any gaps.
label | 87b72960-801c-58ff-88a7-c4f23bd0888c |  | note | Frequency - Daily
label | 666bd3af-9c07-5c82-877c-7a67e37f22b6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c3841fcf-900e-527e-9523-a61d69f351e8 |  | note | Conformance Criteria - Compliance with the Specification
label | 976c8ff9-6f8e-5f6f-906b-7ab1199efcb3 |  | note | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 13 - CPS Engineer Pre backfill Inspection
label | ababf02f-356d-5ce5-93eb-d20fe73bbea5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f11fa872-8cf4-57dc-9f73-3779d10cda9a |  | note | Detail - The pipes shall be laid with the variation between the specified invert level and invert level laid shall not exceed 5mm
label | e2af7a5f-043b-5452-998b-f4844ca8b6d9 |  | note | Frequency - Prior to backfilling
label | 2b6cf55e-7865-56ed-8288-da7e736dd78b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | c27cf77f-a47e-5d63-ae84-c1d8dd504dff |  | note | Conformance Criteria - Vertical tolerance +/- 5mm
label | 1179710e-2219-55bc-8a98-a86e22e13252 |  | note | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint-status |  |  | checkpoint | 14 - CPS Engineer Pre backfill Inspection
label | 3055770b-c1e7-5d69-bf2f-f45aa53564ce |  | note | ACTION (Hold, Monitor, Witness) - W
label | b553426e-720f-571f-a31f-a7bfe021bf86 |  | note | Detail - Pipe invert checks shall be carried out at least once per day with a maximum of 20m between checks.
label | 0657d488-3f57-5247-83af-f9b7ecbda2a2 |  | note | Frequency - Prior to backfilling
label | bdf1b684-546a-54ba-aaa0-97ba368f86fa |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 9997fe47-7d5b-5a11-8480-017926690b8f |  | note | Conformance Criteria - Vertical tolerance +/- 5mm
label | aa1bd214-7038-52b6-9f57-87681c1cd104 |  | note | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
checkpoint-status |  |  | checkpoint | 15 - Pipe Backfill Compliance
label | 5105f763-5abb-5a61-9eb7-e773c6a633c1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 53270cea-1e1b-5130-a706-645d28a841f6 |  | note | Detail - Material to meet specifications dependant on material type selected
label | 615ea508-0fdd-53d4-86b3-3556c6c9fad5 |  | note | Frequency - Each material used
label | 0e913085-842a-5bbf-bdf5-861cbbca3ff8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 3e27ab7d-04f4-5ade-a42f-9df87fc0f781 |  | note | Conformance Criteria - Compliance with requirements from Specifications
label | f2f1d136-d3ce-5faf-a365-e37eb0beb0c3 |  | note | Records - CS-4025 Drainage Line Record Check Sheet (or equivalent)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 16 - Pipe Backfill Compliance
label | 35e794a9-d920-5c5c-b6fe-a1a9a2f1dc48 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 869af08e-f726-512c-bf71-bffb782b9592 |  | note | Detail - Backfill Construction Material
label | 36f5ea41-6f6c-546d-a949-84cda196e452 |  | note | Frequency - 1 test per 50m, or per 500m3 of source.
label | 5b2e7cd3-25cb-5574-9017-2ae41202656a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing - OMC Standard Compaction Curve; Grading Curve (wet or dry sieve)
label | 27b1afb9-13af-5e4d-8d51-832295f35c0c |  | note | Conformance Criteria - CLEAN GRADED GRANULAR AGGREGATE AND HAVE BROKEN FACES AP65
label | 5f445352-26c9-5ef8-92f1-502b1c9c63f1 |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 17 - Backfilling
label | 99419b45-6d78-575e-af0c-30400c7d5cdc |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8903c538-bba7-54a6-9ff8-e39e278229b5 |  | note | Detail - Backfill 150mm lifts with (material) and test every 300mm lift to underside of Subgrade alternatively, to 300mm above crown of pipe in berms. Remainder of backfill to be done with excavated material.
label | 83ea7ac1-aafa-5829-9cd0-269d7eba35c2 |  | note | Frequency - 1 test per 20 m length of trench per 300mm lift
label | af647640-f0d5-50aa-83df-e9a92e97c128 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 696ae9a6-4dcf-508b-b23f-3a0fb2ad54b7 |  | note | Conformance Criteria - 97% (under carriageway) or 95% (under berm) of MDD or Clegg equivalent
label | 4908f73e-6574-59b5-83e4-1da2a88b0dda |  | note | Records - Lab test results
checkpoint-status |  |  | checkpoint | 18 - Structure installation (Manhole, Catchpit, Wingwall)
label | 1ce4607f-9a33-568f-aae0-dbfee8e6d853 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9245ef83-c1a9-5d58-b440-9590eceef0b1 |  | note | Detail - Structures to be installed to the design survey location and level
label | 291e3823-303f-5e2c-821a-fa76103f4c9e |  | note | Frequency - During structure construction
label | 6b8ab263-0384-565c-95cb-26086ba3dc9c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | dd478f29-5e8e-5d07-acad-71ea3a9ff994 |  | note | Conformance Criteria - As Built Survey
label | 368b8f66-d41f-5d83-b8c7-27720e11d439 |  | note | Records - ACE-CS-4006 Manhole Catchpit Board Check Sheet and Survey receipt (or equivalent)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 19 - Structure installation (Manhole, Catchpit, Wingwall)
label | 85ea0e5d-ad8b-5c91-8cb3-45032039a7d5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b9e22f53-c70a-58be-a2bd-9d7af8041226 |  | note | Detail - All joints are to be sealed including rungs and lids
label | d4444d61-bab4-5780-b239-48f5fc9afebf |  | note | Frequency - During structure construction
label | 79220d6a-1058-5699-9f99-7e735d42ccf5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual/Inspection
label | 8be09cdb-ca94-5fee-a655-32b89e7510dc |  | note | Conformance Criteria - Pipe joint to structure shall be encased in 200mm (min.) thick 20MPa concrete
label | b64b187c-8721-5850-b63e-75e4762a2bbc |  | note | Records - CS-4006 Manhole Catchpit Board Check Sheet (or equivalent)
checkpoint-status |  |  | checkpoint | 20 - Structure installation (Manhole, Catchpit, Wingwall)
label | 22639be1-f2f9-5ae5-8c09-b805737a0a3e |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8da4f9f6-1bd6-5db4-aa1a-9681f21ecf8d |  | note | Detail - Arrange as-built survey of the structure and all invert levels
label | 18711f92-0e4e-5c75-8bdd-82881747464f |  | note | Frequency - Once installed
label | 1e055832-3ebc-5f26-b9da-e2439e0a4d6b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 2415fd7d-a718-5aa5-9836-49f35e0a421d |  | note | Conformance Criteria - As Built Survey
label | 346dce77-b1f6-548a-88d3-af649a2e1624 |  | note | Records - Survey Receipt
checkpoint-status |  |  | checkpoint | 21 - Survey As Built
label | 9cbf6ff6-1a4c-5b6d-99fb-1bd134f21770 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b10fb010-36f8-5788-a774-e8421c24e3c5 |  | note | Detail - Ensure all drainage lines comply with design prior to carrying on with next construction process
label | 5a069e0d-4663-5247-8016-7279e0c585f0 |  | note | Frequency - At completion of drainage line
label | fed9e068-0ce6-58f3-8feb-ae06dca97f9f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | eddbf916-3aa2-5408-8bce-b414a4f9c8dc |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 22 - Lot Number QA File
label | 06812f70-c3f0-5a0c-a61d-2b7fb2920305 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e8d76b5b-474a-5fed-b77e-466e1e9d9eef |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 66a65d87-4ebe-5e70-94a8-9ce06a4941c7 |  | note | Frequency - At completion of Lot
label | f60f1878-fb55-5a28-b92b-5193250cda9b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 6cfd0fea-22ed-53af-8169-380f93bda0bd |  | note | Conformance Criteria - 65
label | 2e01aa85-e483-5e1e-976f-8244dceb95be |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 23 - As-builts
label | 05e3385a-7370-50e8-8d58-5bc13840778a |  | note | ACTION (Hold, Monitor, Witness) - H
label | ac31e0f7-d1c9-5ca0-bde2-a50796f737ab |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 7ea5b51d-2dee-547f-acff-89679381c5e7 |  | note | Frequency - At the completion of the Lot of work
label | 2ae9beb8-e6ab-5194-bca9-be5c155e8829 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 3d7b6c9d-c6f7-5bb0-8fdd-5b4e94027cd2 |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 24 - Quality Assurance deliverables
label | 5ee83a3e-4b7e-5d5f-9f22-2f1a3db045bf |  | note | ACTION (Hold, Monitor, Witness) - W
label | ff1cf9e5-5dbc-5fbe-86fa-ba8eb24b5ca7 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. Red line mark up drawings to be included in QA file
label | b37f0cce-f721-5b65-a798-23868c26c466 |  | note | Frequency - At completion of Lot
label | 904d7869-e7c1-5716-984a-7c7bf2fb1fe5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 0a1bf5f1-0e21-5c3f-bb43-e56f6f68cd0d |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | b2bd1fa1-089c-5230-8ca0-f2b238a3b345 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 25 - Completion Sign Off From Fields Below
label | 4a344c3b-31c7-587b-9cd4-c910667a49fd |  | note | Records - Signatures
checklist-flat |  |  | checklist | CS-4009 - Socket Foundation Install Checklist |  |  |  |  | Yes | CS-4009 - Socket Foundation Install Checklist | a2c244e7-44d1-479b-b55f-7efb100549cb
checkpoint-no-status |  |  | checkpoint | Details
text | 2962b428-cb7d-5cad-8443-b3142b2b8b44 |  | textbox | Date of Pour:
text | 060b85bf-6456-54bc-a875-1179f55ee318 |  | textbox | Light Pole Number:
text | b30b7ce8-6fd9-5295-97b7-6dc132867a31 |  | textbox | Pole Type:
radio | 482e0d7e-1cc8-590b-80ad-2cb4dbc17d3f |  | radio | Retention Socket Type: | RS168 x 750DF,RS168 Shallow,Rse273 x 900
radio | c38c4078-7075-55db-97a7-d085215df651 |  | radio | Installation: | Street Installation,Rain Garden Installation
radio | 02f716e1-fec0-51cd-ac0b-29d4876fcd19 |  | radio | Services Present: | Yes,No
text | aa2401d5-0517-5252-ba46-35aefbb6b32b |  | textbox | Services Maximum Depth:
text | 5c946d6d-4195-5a63-abb6-e140b538696c |  | textbox | Lateral Measurement – Foundation to Services:
text | e4815990-2afa-5be9-816b-c5136ef9ff56 |  | textbox | Maximum Foundation Depth:
radio | 916a86f5-62d0-51eb-b0a8-95bf6c4d4e72 |  | radio | Finished Ground Level Confirmed and Rebar Cage in correct location: | Yes,No
checkpoint-status |  |  | checkpoint | Has minimum cover to rebar of 75mm been achieved?
radio | ae910e4f-a25a-5170-b70f-6d884755e7e3 |  | radio | Foundation layout as per approved drawings: | Yes,No
label | c5d26410-94c6-5050-a224-12dde4449dfd |  | note | (If NO what approved action is taken?)
text | 80c06562-8c42-5434-84ae-4ce965ea2ff7 |  | textbox | Action:
radio | 8f62968d-2835-5e9e-8c59-ad9d56144207 |  | radio | Photos of pre pour foundation taken: | Yes,No
checkpoint-status |  |  | checkpoint | RS168 Foundations Stub Pole in place and checked level. (1)
checkpoint-status |  |  | checkpoint | RSe273 Foundations – Correct pre chamber allowed. (1)
checkpoint-no-status |  |  | checkpoint | Water present in base of foundation to be removed:
text | e083c247-1294-51f7-94f5-d94fe4ce5253 |  | textbox | Maximum allowable water in base is:
checkpoint-status |  |  | checkpoint | All fixing locations secure pre concrete pour.
text | 2f6de784-3485-5d59-abc5-d0972e16bcf0 |  | textbox | Concrete Batch Number:
radio | fe65a720-1ffc-5bb4-beb7-55ec7af02023 |  | radio | Pour Correctly Vibrated: | Yes,No
checkpoint-status |  |  | checkpoint | RS168 Foundations Stub Pole in place and checked level. (2)
checkpoint-status |  |  | checkpoint | RSe273 Foundations – Correct pre chamber allowed. (2)
checkpoint-status |  |  | checkpoint | Stub pole should in centre of foundation.
checkpoint-status |  |  | checkpoint | Ensure top of pile is roughed up
checkpoint-status |  |  | checkpoint | All rebar starters are installed
checkpoint-no-status |  |  | checkpoint | Supervisor
text | ea1a86eb-fd12-52d5-8127-b30f0fdcb22c |  | textbox | Supervisor Name:
checkpoint-no-status |  |  | checkpoint | Levels to be recorded
text | a9ee1562-99af-5dce-aa78-28cd167609ae |  | textbox | Ground Level:
text | de677dca-d558-55ce-96ab-e0b96a50e1f8 |  | textbox | Base of Foundation:
text | f5488bf0-e79e-5dae-a942-9b0a471f6f5e |  | textbox | If Plug used base of Plug:
checklist-flat |  |  | checklist | ITP - C1503B - Mautaua Under Slip - Rock Armouring | itp |  |  |  | Yes | ITP - C1503B - Mautaua Under Slip - Rock Armouring | a50cb28c-1f87-4b06-8391-ffc4e21a6c87
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 61468ce6-4c44-5ebd-9dac-7e238c15384d |  | textbox | CPS Eng.
text | 1740bafa-2d94-5ccf-ab77-09aa8f74fc43 |  | textbox | Site Engineer
text | 2f7d1ac9-0d40-5246-a8da-91540c5338ff |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Foundation Inspection
label | 39415dc7-880b-524c-b613-6540c7be0b94 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d6db8628-fc48-5b1d-a17b-d8a616ac26b0 |  | note | Detail - Inspect fill foundation
label | 572345d2-590c-5eab-a844-da37a2e370dd |  | note | Frequency - Per area as required
label | 5509d1f8-e47c-5bcb-8b13-8ae76a17c373 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager
label | c9bd2484-f8cf-5c5f-bf68-e13e94070404 |  | note | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
label | 5fc5c201-c4be-5d07-b817-db2446884bac |  | note | Records - CS-4100 Subgrade Approval Checksheet
checkpoint-status |  |  | checkpoint | 2 - Material Compliance Testing
label | f9e0c859-7068-5e40-91a1-423b00ca489c |  | note | ACTION (Hold, Monitor, Witness) - W
label | ae0d972c-d654-5bea-b598-15036956369d |  | note | Detail - Material to meet specifications dependant on material type selected
label | b40a210f-4813-501a-a2d0-55d38e0049f8 |  | note | Frequency - Each material used
label | 02357632-3c07-5e41-a522-be55fa50b360 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | d4897cae-c3fc-5cb8-8308-ff84c2b53abb |  | note | Conformance Criteria - ROCK ARMOUR SHALL HAVE A D50 OF 450 WITH A MINIMUM SPECIFIC GRAVITY (SG) OF 2,350kg/m3
label | a702920b-ba03-5809-88ce-2315660239b8 |  | note | Records - Lab Test Report, delivery docket
checkpoint-status |  |  | checkpoint | 3 -
label | 9745ce43-07d4-5013-968b-ef3df36ffcac |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7f6b1a3e-0905-50ed-888a-16b0d2945fa0 |  | note | Detail - Rock Construction Material
label | 23aa24dc-744c-540e-b4c6-7b0fbde39c7a |  | note | Frequency - 1 test per batch purchase
label | 1ed3a967-bdf6-5a74-acb8-6d683a8c9098 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | c0937a14-91c5-550e-8373-ab5be234010c |  | note | Conformance Criteria - ROCK ARMOUR SHALL BE HARD, DURABLE, CRUSHED, QUARRIED OR NATURAL STONE FREE FROM DUST, CLAY, ORGANIC MATTER AND OTHER DELETERIOUS MATERIAL. THE STONE SHALL BE FREE FROM LAMINATIONS AND CLEAVAGES AND SHALL NOT DISINTEGRATE ON EXPOSURE TO WEATHERING
label | 31b6985c-4591-52fa-98c1-ebd0714a470a |  | note | Records - Lab Test Report
checkpoint-status |  |  | checkpoint | 4 -
label | 9f71d66e-3a6a-5cf7-9a73-fb98a9295769 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6f391fcc-54f9-5bdb-8c1c-c07f3c99e3ec |  | note | Detail - Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49 and Tencate PES 1000/Tencate PES 2000
label | 02ce2f53-0913-5d14-9ae8-fcf8add05083 |  | note | Frequency - Prior to commencement of placement
label | 1a011959-6acb-5792-92cd-ecfc7b0bfd70 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | bf895ec4-c4e7-5955-b9cd-092e28c4cffe |  | note | Conformance Criteria - Conformance with Specification
label | 3df19563-818c-5147-862a-ebd484dc429a |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 5 - Construction of Engineered Fill Embankment
label | 4ed914af-d11c-5e9e-a6ec-9aa0774e8000 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a17ee469-b647-55ee-ae7a-9a5d7c613e5e |  | note | Detail - Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap
label | 536b35bb-f5e0-5435-a134-3bfb6e4ad4c6 |  | note | Frequency - Prior to commencement
label | f543687b-0b25-599b-8652-85058c441b63 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | bb386fc3-3cd7-53c8-904b-23e3b1576bc3 |  | note | Conformance Criteria - Intake Earthworks ITP completed
label | bdd51e3f-d87f-55e7-96e3-9d4ee6630995 |  | note | Records - Backfill ITP
checkpoint-status |  |  | checkpoint | 6 - Geotextile Placement
label | 46041add-393a-5ef6-a4ad-0224f377450f |  | note | ACTION (Hold, Monitor, Witness) - H
label | aae3a285-3f7c-50e7-810c-4367dccd8b70 |  | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | cce0c0f6-9eb7-5acf-a595-96561d97c695 |  | note | Frequency - Daily visual check
label | b3b0c80b-fe55-5056-8ef6-5c0fc8afd7a4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 270a93b7-46d6-5b1c-8b05-3ac69dc7c80f |  | note | Conformance Criteria - Installed in 0.5m trench laid back, as outlined in drawing
label | e54c9c50-bb19-5b0a-bc0a-c20942afa398 |  | note | Records - Photo's, insepction log
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Riprap Placement
label | 7f1d3f90-a066-5111-a849-b57702305a3c |  | note | ACTION (Hold, Monitor, Witness) - W
label | ebb2699c-c34b-5f2a-86e2-5d23562b9250 |  | note | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. Design Engineer given notice to visually inspect initial placement of riprap material
label | 7d9542c5-448e-5733-a292-b35072a8ece1 |  | note | Frequency - Daily visual check
label | a8a0b1e7-fb2c-549e-b853-d2b0082ad5d9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | db5f232c-5824-5117-a1b5-719a4f6a0a87 |  | note | Conformance Criteria - Specification
label | c9bf1525-736a-5153-8082-ce28e4e2e403 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 8 - Survey As Built
label | 9f6d5382-bd89-5157-8b53-193b7f9c7af0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8ff0233b-0f76-5474-8908-a42f2cd6bfd8 |  | note | Detail - Ensure rock slopes comply with design prior to next process taking place
label | 7900975b-d635-5533-9a0e-b56f6a36857c |  | note | Frequency - At completion of Lot
label | 6d51d184-e406-57e1-bcc0-33a7b54cda4b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 84a63fa4-0b11-5817-abf4-c0a2ea219b0f |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 9 - Lot Number QA File
label | 705717ce-e384-5ea5-a74d-aec32b93e073 |  | note | ACTION (Hold, Monitor, Witness) - W
label | bcd6d59e-2e58-5e2d-880f-7dcec90244b9 |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | d4aecc9b-a74b-5312-9050-ab20d1f4f7f6 |  | note | Frequency - At completion of Lot
label | db9bc96a-d501-524c-abb1-8515fd7777af |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 21d8a015-8aa4-5973-b012-6aa99c01df6d |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | dabc297a-ef6c-5627-8be8-34e8e68256d9 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 10 - As-builts
label | 669a768f-e9d7-53a3-afca-83984504f6e4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f9b87baa-375d-553f-8816-7c11e778a734 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 4701edb3-c6e7-5915-906c-0c6240cad0be |  | note | Frequency - At the completion of the Lot of work
label | ae96f9a4-b653-5734-9367-ab079286a6d0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | fb9a593f-4419-5715-ace8-18e63c82248c |  | note | Records - As-built Drawing
checklist-sectioned |  |  | checklist | ITP - F5001A - Hicks Bay Slip Repair - Guardrail | itp |  |  |  | Yes | ITP - F5001A - Hicks Bay Slip Repair - Guardrail | a7b98b4a-fa4b-4bd8-ae67-7d152c96fbf4
checkpoint-group |  |  | section | Guard Railing
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 4b70e3c0-cfa8-59bc-80d9-9e291f6f6e15 |  | textbox | CPS Eng.
text | e5bf1f80-bb44-5291-b9c5-5914eed2727c |  | textbox | Site Engineer
text | f24d9f01-de9d-55ef-9f30-a411c6ab4067 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Guardrail Posts Installation
label | a942fc10-2d03-5a38-91a1-34afea684d79 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1f3f6076-7834-588e-a156-b067e4ae0970 |  | note | Specifications/Drawing Reference - Design check locations of posts and check for any clashes with underground services or similar.
label | 3da9985a-c2c5-5c8b-adb4-185f8c839540 |  | note | Frequency - Prior to commencement
label | 28639fa7-b187-5b99-b205-bf698ca0be56 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 63c9e628-f4bc-57d3-be79-56a14f074bd1 |  | note | Conformance Criteria - Contractor to confirm that installation of posts avoids culvert clash
label | adef905a-97f2-530a-82b0-5862eae7a562 |  | note | Records - Site pics, NTE/NTC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | a243c6a6-df95-5fac-b7c6-4a4e324b0c87 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3618c143-2cff-5c10-b73a-2db9a9b48130 |  | note | Specifications/Drawing Reference - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
label | f290a01d-a475-5af2-bb0f-f6d738a54a93 |  | note | Frequency - Prior to commencement
label | 927ca9a4-40cf-50e7-9ca7-8c98282e6e65 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | ba97c57b-40f9-5439-a220-64ccafdee70c |  | note | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | b1e0bad6-54be-5f32-9ae6-2f3b261ed5c8 |  | note | Records - Approved Construction Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Material Compliance
label | 80751b05-1d77-5095-bb36-4172197e78fd |  | note | ACTION (Hold, Monitor, Witness) - W
label | ffa797bc-1f61-580f-b757-d444dbe2f13d |  | note | Specifications/Drawing Reference - All roadside barriers shall comply with NZTA M/23:2023. Only MASH TL3 approved systems to be installed as specified in the specification & guidelines for road safety hardware and devices, Appendix A: permanent road safety hardware.
label | c04d5b10-6e05-56db-ab22-1cab1a9aa69c |  | note | Frequency - Prior to commencement
label | 485d9cb2-e51d-5da6-beca-21bf1b85b429 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | 175a022b-0171-5cf8-997f-e740e364aec4 |  | note | Conformance Criteria - Comply with NZTA M/23:2023. MASH TL3 approved systems only
label | 788478a5-7b4b-53d2-b6c1-ad8f610aafd4 |  | note | Records - Manufacturing certificates, delivery dockets, Photo's
checkpoint-status |  |  | checkpoint | 4 - Guardrail Installation
label | 79cc6213-8f38-5234-bda0-eb296117b96b |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6ae8e769-9b87-597c-8f5d-86746957f9be |  | note | Specifications/Drawing Reference - Guard railing shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications. All Guardrail laps are to be lapped in the traffic direction
label | e9c9f644-c1b4-51b8-9de7-7a081e00fc8c |  | note | Frequency - During installation and on completion
label | c1afa3eb-f35d-55cd-85ae-703132d2bbed |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | f1f1c3c0-aa95-5bf2-91b4-c6ae464db8d7 |  | note | Conformance Criteria - Each section inspected to comply with manufacturers specifications
label | cd5cd24a-dbcf-5970-a338-e9bc4da7d6df |  | note | Records - Guardrail Installation Record (CS-4117), Photo's
checkpoint-status |  |  | checkpoint | 5 -
label | 9040ad6f-9925-5015-b624-2272029b476e |  | note | ACTION (Hold, Monitor, Witness) - W
label | 50bd3935-2270-50ad-bfc9-32ca99174c79 |  | note | Specifications/Drawing Reference - Hazard markers to be installed on all terminal ends. Edge markers posts to be secure to the guard rail face. Face of Guardrail to be a minimum of 1.2m from edge line. Engineer to confirm min of 1m support width behind the barrier at a desirable grade of 10:1
label | 4086cd3d-0f3b-5102-a826-21fe7fb42a21 |  | note | Frequency - During installation and on completion
label | 89357190-1c3a-5816-9d04-8a438dbccaac |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | ceec723a-2d0d-59c0-a227-79f11f3588ae |  | note | Conformance Criteria - Each section inspected to comply with manufacturers specifications
label | 4bb2b504-033b-5133-bf83-560bdc767903 |  | note | Records - Guardrail Installation Record (CS-4117), Photo's
checkpoint-status |  |  | checkpoint | 5 -
label | 1fed0805-c529-5919-9778-f791172b53e8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5e50f481-5873-5ee0-8ceb-54f7ab9b1a84 |  | note | Specifications/Drawing Reference - Terminal anchor points ground conditions assessed and confirmed as being adequate based on barrier manufacturer requirements.
label | 5b8a87f9-9d46-52cc-a083-aee5097babd0 |  | note | Frequency - During installation and on completion
label | 15bc4814-2566-5ad9-b261-21ea83d2769d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | 38175823-83e8-591f-ad53-0623f128d5f4 |  | note | Conformance Criteria - As per manufacturers specifications
label | 3bdbb742-ce84-5325-95cd-197bcad4e4a6 |  | note | Records - GHD COR, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 -
label | 2b383ddd-217c-5228-9948-1b589a1dfd02 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 202e328f-dcff-5e5f-9d79-16f2f04f158a |  | note | Specifications/Drawing Reference - Hazard markers to be installed at terminal ends. Edge markers posts to be secure to the guard rail face. Face of guardrail to be a minimum of 1.2m from edge line. Engineer to confirm min of 1m support width behind the barrier at a desirable grade of 10:1
label | 50e0a133-cfc2-5eda-be97-aef347ed444b |  | note | Frequency - During installation and on completion
label | f214deb7-e485-507e-9347-6fc25a257b4d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | 8d28ce60-7f31-5ed0-85f5-211c135c9fb5 |  | note | Conformance Criteria - Each section inspected to comply with manufacturers specifications
label | e0115a5b-b30d-5e36-b05c-adcff1fdb11c |  | note | Records - Guardrail Installation Record (CS-4117), Photo's
checkpoint-status |  |  | checkpoint | 7 -
label | e780e90f-764c-5121-891d-71fe79c50c36 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f6fc848b-452f-52ba-b6b0-9bd464138455 |  | note | Specifications/Drawing Reference - Barrier face is to be a maximum clearance of 200mm from the kerb face in the location where there is kerbing. Design speed 100Km/hr AADT <1000 V/D run out length 64m. Existing single post signs are to be repositioned behind the barrier. Offset of fence is to be confirmed to ensure that there is sufficient room for barrier installation
label | f6b9f9db-a8d9-54cf-900b-de3a86f31ef8 |  | note | Frequency - During installation and on completion
label | ad4d8d39-a277-58ae-8443-691250f59627 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | cd02edea-9e07-51e9-b741-00ebf45ff0e1 |  | note | Conformance Criteria - Each section inspected to comply with manufacturers specifications
label | ca6396c3-0ff4-5e40-8f8b-d0421120b7ca |  | note | Records - Guardrail Installation Record (CS-4117), Photo's
checkpoint-status |  |  | checkpoint | 8 - Fit for purpose Inspection
label | 28da455d-f2b2-51f3-9789-a783c9373e2d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 26ad1898-f942-553a-ae7c-9d21e8030be6 |  | note | Specifications/Drawing Reference - Barrier to undergo fit for purpose inspection by competent person
label | aaa97180-9c9d-5ee9-99d1-4efdd2777df6 |  | note | ○ System checklists to be completed and co signed by contractor and CPS.
label | 29bda815-aac4-5e7f-8df5-c018c9839c9c |  | note | ○ All faults to be rectified before acceptance into network maintenance and RAMM by contractor
label | 018627ca-5cf0-5692-9f7c-5dd8c76fa9be |  | note | Frequency - Prior to trafficking,
label | dfac64ea-54b8-5a20-990b-b3c11536633f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 5c763779-6ac7-5468-885f-9c2931aeb8d2 |  | note | Conformance Criteria - Pass inspection
label | 81ee6aaf-9941-5c80-bc3a-db5c3609109a |  | note | Records - Written Confirmation from NZTA IMI qualified inspector
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - As-built Survey
label | 52c9ef1d-06b4-538a-bed7-c3f418d9671c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8159c396-228c-50b1-ad72-ec48ed9029ff |  | note | Specifications/Drawing Reference -
label | ab6594a6-b83f-5868-bbcc-b30a9ab3a80c |  | note | Frequency - At completion of Lot
label | 2fcf2074-cb0a-5e45-afff-f3f2a8b8843b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | 346ed996-0dd7-5bed-b8d6-c55c4160af6a |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | 812c4f4b-b39b-5470-b2fc-4e09f8081821 |  | note | Records - As-builts, GHD COR
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 4 : Final Inspection and Handover
checkpoint-status |  |  | checkpoint | 11 - Quality Assurance deliverables
label | 5e786bba-a2e3-5098-9cd3-af60c0c0df85 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0b950c01-cabf-5bab-9eb8-959ea1f4ea55 |  | note | Specifications/Drawing Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 4b1f0cd7-ba5a-5941-97fa-878b0d368a45 |  | note | Frequency - At completion of Lot
label | 2faa3775-d0cd-599c-9480-7e207864a0a3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 835a8b56-8d85-5278-bc88-7a1893428af3 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | be56291e-153e-5cc2-937d-57b0739d3da2 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 12 - Completion Sign Off From Fields Below
label | df9c28b4-2060-5e96-a325-6b2d04e0b0b5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d95dddf8-7031-5b5e-9fc1-dfd2eac04621 |  | note | Records - Signatures
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | CS-4011 - Bored Pile Record (to be used in conjunction with WTPA-CS-4083) |  |  |  |  | Yes | CS-4011 - Bored Pile Record (to be used in conjunction with WTPA-CS-4083) | a80de8cd-6781-433c-a1f3-ce2c52cd4f62
checkpoint-group |  |  | section | Details
checkpoint-no-status |  |  | checkpoint | Details
text | 737871c5-6677-5df0-b239-8fbadc7dd3fe |  | textbox | Work Area(s):
text | 8916eca6-5a10-5774-bebe-94be09a98a04 |  | textbox | Sub Work Area(s):
text | 19fed7e6-d8d9-5531-8065-70204f190262 |  | textbox | Lot(s):
text | 54fea670-2ec1-5dc8-a10d-3c20d13a1569 |  | textbox | Sublot(s):
date | fbcdf3c1-d833-545c-aecf-bc5c0df6a721 |  | date | Document Date:
text | 84cf52c8-2c93-57a9-965c-4a0c0291f79d |  | textbox | Created By:
text | d1875c84-420e-5e88-b880-23a5ffd5539a |  | textbox | Drawing No:
text | a83b2936-a166-586d-bce7-11efd7d70b15 |  | textbox | Concrete Grade: |  |  | Mpa
text | b591e8a0-9386-535e-b927-10c6509a764b |  | textbox | Pile No:
text | d7372937-1d9d-55f9-9a09-6a42cd11d197 |  | textbox | Diameter: |  |  | mm
checkpoint-group |  |  | section | Set Up
checkpoint-status |  |  | checkpoint | Piling Platform Compacted & Level
text | db71bec6-a8aa-5d39-8526-a68cd1cec4e3 |  | textbox | Initials:
date | 7f516cd5-e1d0-5976-80f2-ba903b592bb2 |  | date | Date:
checkpoint-status |  |  | checkpoint | Permit to Dig Obtained
text | 4534cb44-053d-57ce-bd88-afab291b0966 |  | textbox | Initials:
date | 0a65cb2d-c359-5341-97d6-f36aaed6842b |  | date | Date:
checkpoint-status |  |  | checkpoint | Pile Set Out & Checked
text | 5e76b8c6-1aed-5c7a-9a4f-02eaf6ad1c48 |  | textbox | Initials:
date | 5b355ff4-7949-5ac0-979f-05cb82bd1471 |  | date | Date:
checkpoint-status |  |  | checkpoint | Erosion & Sediment Controls in place
text | 5101f0ad-5987-5a0e-889c-7cc1b3a4a3a5 |  | textbox | Initials:
date | 944ecf49-b6f3-56b4-b7ad-f4499804a714 |  | date | Date:
checkpoint-group |  |  | section | Drilling
checkpoint-status |  |  | checkpoint | Design Engineer Notified
text | 58e0723a-604c-515b-923c-1cd8ba448ccb |  | textbox | Initials:
date | 1aad6b6a-e4d9-5525-b71f-693d7b9a2f92 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pile Casing Installed to Rockhead
text | dac68e9b-9979-5c36-a228-07a4160cbda4 |  | textbox | Initials:
date | 672d30cb-038d-56c9-ad6a-97970c1eeab4 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pile Bore Logged
text | a642634b-a9bb-58f1-b876-0bab9a174809 |  | textbox | Initials:
date | 41578f3d-6353-5b8d-b111-dd53bc94f6b9 |  | date | Date:
label | a53c0e24-f25d-5b0b-bf52-e362276fe260 |  | note | Comments: CS-4083
checkpoint-status |  |  | checkpoint | Pile Drilled to Required Toe Level
text | ae6b1d89-35ff-557c-8b8f-85c4edf9051a |  | textbox | Initials:
date | 7660d418-940e-58ed-8c2a-17cfca58df48 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pile Sides Grooved
text | 9026ede0-80bd-5882-b93c-c7bd92dc8f25 |  | textbox | Initials:
date | 234d68a8-205f-517f-83e8-c5e52ed307fc |  | date | Date:
checkpoint-status |  |  | checkpoint | Design Engineer Inspection of Bore
text | 2b6b31ff-2147-51a5-aa9b-8fd92f0774bc |  | textbox | Initials:
date | 51fbdb09-a221-5434-9d8b-3aa2cfa78eec |  | date | Date:
checkpoint-status |  |  | checkpoint | Pile Toe Cleaned
text | 084d26dd-6f89-565c-b17d-e933d3c850f7 |  | textbox | Initials:
date | 9782738b-00ef-5c44-b825-268a292d84e9 |  | date | Date:
checkpoint-status |  |  | checkpoint | Pile Pumped Dry
text | b8083541-ba4d-5719-b914-cab2eae2df9c |  | textbox | Initials:
date | 17a0ec6b-4225-5b4d-89d7-b2534492e5fc |  | date | Date:
checkpoint-group |  |  | section | Reinforcement
checkpoint-status |  |  | checkpoint | Reinforcement Content, Grade and size
text | 6ce5af14-b087-5185-9c6a-6e638aed6b30 |  | textbox | Initials:
date | 20534527-9b22-56d1-b43b-986c99d64206 |  | date | Date:
checkpoint-status |  |  | checkpoint | Placement, tolerance, clearance
text | d10118f8-b3ee-5d46-a671-3293eb543d8c |  | textbox | Initials:
date | d3b2d216-e0d1-5ecb-8e0f-c6376f5a4bd1 |  | date | Date:
checkpoint-status |  |  | checkpoint | Rigidity and cover spacers fitted
text | 4c10ddaf-714b-5c78-929f-5d54c93649d9 |  | textbox | Initials:
date | 974d383d-7b45-5093-bd76-40f258ff0f3f |  | date | Date:
checkpoint-status |  |  | checkpoint | Clean steel
text | c5972ca9-0023-51f9-b29d-c49b89cda808 |  | textbox | Initials:
date | 11d6d151-e12c-5b77-ac6e-1801a24b5bf1 |  | date | Date:
checkpoint-status |  |  | checkpoint | Lap location and lengths
text | ecfae8bc-e23a-5e02-b5c6-0c942f00ef9e |  | textbox | Initials:
date | f78e61d9-2e61-5b8b-9da4-071645dc0dce |  | date | Date:
checkpoint-status |  |  | checkpoint | Foam liners fixed to Starter bars
text | 75b43746-4133-5b20-9a85-9f99ac31315e |  | textbox | Initials:
date | 387deebf-600b-5b4d-80e0-a28fd71736e1 |  | date | Date:
checkpoint-group |  |  | section | Other
checkpoint-status |  |  | checkpoint | Correct mix ordered
text | aaa7bc73-bf5f-5cb0-94a0-44e9d06b6a1b |  | textbox | Initials:
date | 77d6cfa2-3618-52a1-8bf0-454dfb39613c |  | date | Date:
checkpoint-status |  |  | checkpoint | Design Engineer Notified
text | 9509b38f-280c-512c-8e7d-af498a1e3ecc |  | textbox | Initials:
date | a058d932-02fc-503e-9ce2-3b5d86d9cf08 |  | date | Date:
checklist-sectioned |  |  | checklist | CS-4047 - Traffic Sign Installation Record |  |  |  |  | Yes | CS-4047 - Traffic Sign Installation Record | ab881ad6-f2f5-4385-8820-0594bb300c74
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | 5ca24cff-1050-531c-8681-cc6619af9776 |  | textbox | Project No.
text | 8f869db5-3998-579a-b448-288c34d5133e |  | textbox | Drawing No:
text | 6f712278-524d-528d-b5a3-df8e29af51f6 |  | textbox | Sign No:
checkpoint-group |  |  | section | Installing Sign(s)
checkpoint-status |  |  | checkpoint | Ensure the posts are the correct length to ensure the sign will be installed at the correct height
text | 5e4bbc68-5c07-5c3e-b0d3-8e5a8134994e |  | textbox | Initials:
date | 2706ad7b-c082-58d8-9e9a-7231866dd716 |  | date | Date:
label | 7e098fb2-7e75-5911-a164-67ce288fb119 |  | note | Comments: Minimum mounting height 2m from the underside of the sign(s) and the adjacent road pavement, trafficable shoulder or top of kerb whichever the critical dimension shall be. The exception is for exit signs where the minimum mounting height is 1.2m.
checkpoint-status |  |  | checkpoint | Ensure posts are connected to foundations with correct fixing bolts/brackets and are fixed securely to ensure the posts are firmly installed in the vertical position
text | 115c508d-3103-5d0e-81b2-c492ee5a7e92 |  | textbox | Initials:
date | b4622b50-2240-51c2-82ba-cbbeeb031cb6 |  | date | Date:
checkpoint-status |  |  | checkpoint | Once posts have been installed check they are plumb and to the correct spacing apart at the location of the sign
text | ed7428af-c195-5c08-a903-eb27a0cabd03 |  | textbox | Initials:
date | 54a956ad-9959-53dc-9726-f7a212e65f70 |  | date | Date:
checkpoint-status |  |  | checkpoint | Check the sign before installation and ensure the sign is exactly as per the shop drawing
text | d7c07bbe-132d-5605-a135-d8b9f309e74b |  | textbox | Initials:
date | 9e8baf1d-afcd-5178-9bb8-5a26f3723943 |  | date | Date:
checkpoint-status |  |  | checkpoint | Inspect the sign and make a note of any damage
text | f04ab461-92f8-5e55-8b09-ea0e3b9efc16 |  | textbox | Initials:
date | 15948e62-9370-5299-bfde-c37cf79309cb |  | date | Date:
text | 48e1016d-7ba0-5f17-aed0-ce7f012418a2 |  | textbox | Comments: Record any damage:
checkpoint-status |  |  | checkpoint | Ensure graffiti guard or dew guard is present on the sign
text | 9e08f656-7b1f-501c-ba26-c86e9a283d13 |  | textbox | Initials:
date | bb283ca3-6a89-5284-a182-16d010ae9087 |  | date | Date:
label | d4fcd8f6-c166-5d1d-b21a-7285b549243e |  | note | Comments: Graffiti Guard on Sign, Dew Guard on Sign
checkpoint-status |  |  | checkpoint | Clean the sign (if required) as directed by the manufacturer
text | ad3d9964-fb60-5ccb-a136-e8cdd7356b3f |  | textbox | Initials:
date | b19ee5dc-81bd-5ebf-b6ab-bed81b853f10 |  | date | Date:
label | 2d0769cc-20d1-5521-a496-8af697f19fe6 |  | note | Comments: Signs shall be cleaned in a manner and frequency that maintains visibility of the sign at all times
checkpoint-status |  |  | checkpoint | Ensure signs are connected to posts with correct fixing bolts/brackets and are fixed securely to ensure the sign is firmly installed in the vertical position
text | 41c473f3-5faf-5642-bc21-c7f721457855 |  | textbox | Initials:
date | 78e54dbf-3a17-5903-8418-0b163b970df3 |  | date | Date:
label | 19be6b4d-5dad-5e68-825e-4474c6926c74 |  | note | Comments: Do not fix signs to posts by bolting through the sign unless approved otherwise by the CPS Engineer
checkpoint-status |  |  | checkpoint | Overhead mounted signs - Ensure horizontal and vertical axis are checked
text | d77fa154-1af9-57ec-90de-f201147ee66f |  | textbox | Initials:
date | c379fd1b-19cc-5847-af5f-a70079f95b4d |  | date | Date:
label | 2a693807-1558-58ba-ab45-545a12777fb6 |  | note | Comments: Where the road gradient approaching the sign is =2.0% or greater, position the sign so the vertical axis is parallel to a plumb line and the horizontal axis is at right angles to the road.
label | 554b3343-efc8-5d70-b430-dbfcd45ceb15 |  | note | ○ Where the road gradient approaching the sign is =2.0% or less the sign shall be positioned so its horizontal axis is at right angles to the road, and the vertical axis of the sign is inclined to face upward at a rate of 3mm per 300mm of vertical sign surface for each 1% the road gradient differs from +2%.
checkpoint-status |  |  | checkpoint | For sign installation follow the Work Instruction and ensure Lifting and Working at Height permits are in place
text | bcec1d66-d053-56a3-922a-eef772c73980 |  | textbox | Initials:
date | d1dc5844-1cc9-5b33-93e6-35c6e38fb69d |  | date | Date:
checkpoint-status |  |  | checkpoint | Measure the mounting height after the sign is installed to ensure it complies with MOTSAM Part 3, Section 1.18.2c) for Ground mounted signs or Section 1.18.3c) for overhead signs
text | 53a2be80-f75e-5df5-aac8-c8dbb044694d |  | textbox | Initials:
date | 241e2d81-78f3-5b1e-87d7-0c9e5ce430c8 |  | date | Date:
text | 3ca629a5-ef64-57c1-be2a-fee573e9a711 |  | textbox | Comments: Mounting Height =
checkpoint-status |  |  | checkpoint | Ensure the sign is installed above the hinge where hinges are required (Breakaway signs)
text | c59c64f8-136e-55a7-88c9-8946aefd1850 |  | textbox | Initials:
date | 6e5a3e05-398f-581a-973c-e48affd0fe81 |  | date | Date:
checkpoint-status |  |  | checkpoint | Undertake a ‘drive by’ with CPS Engineer and ensure the sign(s) are orientated correctly and sign off below
text | 4bb0a786-a3c9-5296-a9c9-d348329223c7 |  | textbox | Initials:
date | c6ef2c25-61fb-5ab2-ad32-2d6281e77cfe |  | date | Date:
label | 69d0f5c2-86da-5667-927c-dd232ffd580f |  | note | Comments: Ensure signs are directing traffic the right way and are visible.
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | b73ec8d2-7e59-5f0a-b67d-379f606b4cca |  | note | Position: Site Engineer
text | 0ed9a9c8-aa76-5c56-97a7-7b2d9b7a5741 |  | textbox | Site Engineer - Name:
date | a3d69635-1f43-5a0a-87bc-dc51a262ab9f |  | date | Site Engineer - Date:
label | 6ea7f95f-6909-5966-a79f-561aad4b7173 |  | note | Position: CPS Engineer
text | ff4e9641-df59-5a62-89c0-9c8094a431b9 |  | textbox | CPS Engineer - Name:
date | 70a7e1f5-861a-54ea-ae42-97a1ff244703 |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-flat |  |  | checklist | ITP - G1202A - Waikaretaheke Riverbend Recovery - Compliance and Environmental | itp |  |  |  | Yes | ITP - G1202A - Waikaretaheke Riverbend Recovery - Compliance and Environmental | b01d59ef-d668-43e1-a1e5-39144e7bc786
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 88e2a397-a2a8-57ce-bb59-f25c5eb450b4 |  | textbox | CPS Eng.
text | a7152f1a-2dff-5955-b3d5-720e372c19a9 |  | textbox | Site Engineer
text | ed542aa1-c975-52c9-b11d-9c4abcae4db4 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Approved Consents
label | 574850ff-6c80-5782-804c-a179caeeb9e3 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 8c6e7f5e-311f-5fef-88e4-7184f9533639 |  | note | Detail - Is a copy of approved consent(s) available on site
label | 13b50fc9-8d46-501c-a0d9-f4ec2e0bb229 |  | note | Conformance Criteria - Check latest consents and SSESCP's are at each site office
label | a6330879-2007-5787-85b5-f0e821d04bd7 |  | note | Records - Copy of Consent
checkpoint-status |  |  | checkpoint | 2 - Internal ESC Pre-Construction
label | 42f4efc9-3d7c-50f6-987b-99581fc10757 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e368b1f4-cf3e-5a60-9c4c-81b0ca97332f |  | note | Detail - Internal pre-construction meeting held with Environment Team
label | a42e9670-b074-55f2-ab33-69fc33a98514 |  | note | Conformance Criteria - Environmental Advisor to organise
label | b45716fe-cf10-5a2b-b0b5-7ed1a54463d7 |  | note | Records - Meeting minutes or similar record
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Type and Location of Erosion & Sedimentation Control
label | 059da8b9-d7bf-5085-afdf-f1c5d7825926 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 061b668b-b7e2-5610-8897-fb12c2f564c9 |  | note | Detail - Confirm type and location of erosion and sedimentation control, based on relevant drawing/s
label | 47957109-37e4-520c-a156-311ad2c66ffe |  | note | Conformance Criteria - Relevant ESCP drawing
label | 3b4222b7-de06-5df0-9dc8-73b7b807f54b |  | note | Records - Relevant ESCP drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Channel Bund (if required)
label | d8f9d0a0-7f53-59b6-b415-0a8d9a0e527d |  | note | ACTION (Hold, Monitor, Witness) - M
label | f8032a87-a737-5ab2-ae81-a1ce00295193 |  | note | Detail - Bund is constructed in correct location; to agreed / specified dimensions and levels; and is firmly compacted.
label | 8684bed6-66df-59d3-bbfa-ace3967d7a42 |  | note | Conformance Criteria - Work Instruction, Drawings and Checklist
label | 03a9bd65-d80d-53ea-8faa-a1b8ee3834d1 |  | note | Records - Photos and Checklist
checkpoint-status |  |  | checkpoint | 5 - Silt Fence (SF) (if required)
label | 63491a1a-cd90-58dc-98c8-8f9ff4c64ab5 |  | note | ACTION (Hold, Monitor, Witness) - M
label | e3eb192f-ee19-503f-bedc-ee07c161619a |  | note | Detail - Silt Fence or Super Silt Fence is constructed in correct location; to correct dimensions, and geotextile secured and waratahs located as shown on the WI and drawings
label | d50b1efc-d80a-5c01-a930-43546deadb98 |  | note | Conformance Criteria - Work Instruction, Drawings and Checklist
label | 432cffbb-ace7-5281-83dd-025e4bcb062a |  | note | Records - Photos and Checklist
checkpoint-status |  |  | checkpoint | 7 - Maintenance Inspections
label | af1b48e1-e251-5044-9ee8-ae83fa6948ab |  | note | ACTION (Hold, Monitor, Witness) - W
label | 370af2d4-2bc1-5ad7-ac21-26e21b1e8406 |  | note | Detail - Undertake weekly inspections of all erosion and sedimentation controls and after > 5mm rain to identify required maintenance
label | b19140e3-a89c-5874-9009-95dea27f8301 |  | note | Conformance Criteria - Approved ESC Plan. Complete weekly and upload to ConQA / Procore
label | 14debedd-6790-58b6-9e57-3e3eb364f28b |  | note | Records - Inspection Record
checkpoint-status |  |  | checkpoint | 8 - Decommissioning of Erosion Sediment Controls
label | 4be35db9-c330-56b8-a6d6-9543e0d6e029 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b9fef797-6845-5fe6-8ee7-bfa7c318e0e8 |  | note | Detail - Decommissioning Plan submitted to HBRC for Approval
label | 728afc50-3fd7-51f0-bd79-9ceccdcd5d49 |  | note | Records - Decommissioning Plan and Email record
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Decommissioning of Erosion Sediment Controls
label | 1a9e2774-7245-5bb2-9330-458268c0d2b2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2a4d7d2f-641a-55d7-8396-a72feae8c3e3 |  | note | Detail - HBRC to issue an approval document so that Decommissioning works can commence
label | c458b923-57aa-5cee-a0eb-4c08cad5e0c8 |  | note | Conformance Criteria - Approval for Decommissioning
label | f7b29347-56bf-5b07-b25e-d5791c8b4316 |  | note | Records - HBRC approval Doc
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Completion Sign Off From Fields Below
label | b6ebb761-d585-5493-97a5-9760ce7b4cf3 |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | ITP - C1603A - Waikare Gorge Descent - Chip Sealing Reinstatement of Carriageway | itp |  |  |  | Yes | ITP - C1603A - Waikare Gorge Descent - Chip Sealing Reinstatement of Carriageway | b2a4f3ca-28dc-473a-93ab-0a0e4511bb8c
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Project Site reps.
text | cc9e2a19-dfbe-5067-8541-babcabc9b119 |  | textbox | CPS Eng.
text | c6adeb89-a90c-51cb-aefe-f016a511a92e |  | textbox | Site Engineer
text | 178ac339-3abc-599c-82e3-24dea4c618f2 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Seal Design
label | 5913534d-9c8c-5d11-9386-0bfc4a5699a8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0f0f11dc-d672-587c-9022-6a5a2156b091 |  | note | Detail - Seal Design to be submitted by Contractor for review and approval by CPS
label | d5f8bb21-87f5-5b1e-8c71-3d31c899de28 |  | note | Frequency - Prior to commencement
label | 6415f021-0073-5cc9-a9f0-59417c8f7e5f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | c2ba6fb2-0529-563f-94a0-73ad356aea42 |  | note | Conformance Criteria - Approval by CPS Engineer prior to activities commencing on site
label | 68e58b5d-a64f-5cdf-aee1-b65a26a3f484 |  | note | Records - Seal Design
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Previous Lots Completed
label | ec357bce-55d5-55c2-8eba-263fd6e420f0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 94431e3d-14b9-5661-bdad-549663634ad3 |  | note | Detail - All previous Lot ITPs - Basecourse Construction and/or Modified Basecourse completed & signed off before Chip sealing laying commences
label | c8bdb10a-45fd-50b0-9ef8-ddfaf21596af |  | note | Frequency - Prior to commencement
label | 2815540d-5407-5f7a-8d50-8ad0923bc7b6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 156911de-a0a5-558f-9b05-b298eb9402e4 |  | note | Conformance Criteria - Previous ITP completed
label | 4f5eaed1-05ed-5d93-a09b-05abca92ed53 |  | note | Records - ITPs - Basecourse Construction and/or Modified Basecourse
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Survey Setout
label | ba04b947-73ab-53cd-99a8-66a538ddb53e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2f70dd47-d228-5a31-931e-0b95253b3014 |  | note | Detail - Mark out the extent of the seal if not working to a kerb line. Square off edges to tie-in to existing pavement if encroachment is into wheel path.
label | 3499b3c1-4a88-5bf3-9527-82411b24a468 |  | note | Frequency - Prior to commencement
label | 30d18d5e-3b2e-5399-b4d9-e072811a6602 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 44c46191-1a90-5a57-aae3-421e9f899dcd |  | note | Conformance Criteria - Spray paint edge of seal lines
label | cf8899c4-2242-5f9f-8d66-37e6f791de2c |  | note | Records - Sketch / Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Survey Setout - spray runs
label | 51d3f590-b61f-5441-8811-c810b8a2ac17 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 307b3828-b275-5164-b61e-9deaba28d4e5 |  | note | Detail - Determine spraying runs start/stop locations
label | 81f7c621-c4c3-538c-9093-cc565a9c6329 |  | note | Frequency - Prior to commencement
label | e976479d-ca42-5c2b-927e-d5b943b2d061 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 2e4ecbb5-0943-5879-ad37-1d867687a60b |  | note | Conformance Criteria - Mark out on site
label | d97ccd4d-8d1f-5142-a5a6-135c5ee67131 |  | note | Records - Sketch / Photo's
checkpoint-status |  |  | checkpoint | 5 - Material Compliance Bitumen
label | c9a66b8a-d178-553d-849a-25b7a8343078 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1a8ab85d-3bce-5c6e-8a9a-95e6661cd011 |  | note | Detail - 1st or 2nd Coat Chip seal - Bitumen (Design dependent on season)
label | dd40fb1d-9186-56b5-81e7-892fd8d7183c |  | note | Frequency - 1 test per bulk shipment or grade
label | 89719395-371d-5593-8163-ef175129a7da |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - IANZ Lab Testing
label | 80251b1e-2a0f-544f-9f0c-54b82abd6830 |  | note | Conformance Criteria - NZTA M01:2020
label | c1c4766a-58fb-5eb5-85ed-8966e3984627 |  | note | Records - Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Material Compliance Sealing Chip
label | feeed439-0b53-5586-bef6-2fdb05c0f66f |  | note | ACTION (Hold, Monitor, Witness) - H
label | f52e5415-c1fa-5550-ba36-81b4f67b8cce |  | note | Detail - Sealing Chip Source Properties as per seal design
label | a0d3d9ca-79d8-5d89-9765-2b27a455ab04 |  | note | Frequency - Prior to Delivery
label | 28df58b5-ad94-5c40-9faf-0830623c5d75 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - IANZ Lab testing NZTA M/6
label | 724a0e44-4f95-5fea-8879-cf6e6c99d7af |  | note | Conformance Criteria - NZTA M/6:2019
label | 5028ce68-cacf-5166-9859-d2180dbb0cc3 |  | note | Records - Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Chip seal - pre-seal Inspection
label | bc0a46a8-ab25-5061-af1b-f2561ab4b770 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 517375eb-64c0-523c-92e3-f5cff79554bc |  | note | Detail - Pre-seal inspection
label | ee64957c-4b3f-577a-aa00-40669438984f |  | note | Frequency - Each site
label | d0bbc522-35fb-5e01-9239-1aa85b7c7aa6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
label | 9b4bd75a-cdfa-5f64-9ae4-3afa624b9e24 |  | note | Conformance Criteria - Walk over site
label | 27f38d67-a29f-541b-b7f3-f465211a8675 |  | note | Records - CS-4060 Pre-Seal Checksheet, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - Chip seal - bitumen temp
label | 7a84c697-6029-5ab2-9d3d-a05f4c39d194 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5dc077d7-f377-5864-b9b4-ab61d7b26221 |  | note | Detail - Record Bitumen temperature at time of spraying
label | b6fc4e9d-760d-5c16-9476-86dbf1e19d0b |  | note | Frequency - Each sprayer load
label | 55015d0a-5b71-5bd8-9cfe-6d25311d2abb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Temperature of load using sprayer calibrated temperature probe.
label | ecae2803-af46-5c7c-929d-7adad3f7e7dd |  | note | Conformance Criteria - Temp. appropriate to base emulsion and +/-5 degrees. IANZ calibrated probe
label | 760fac91-7439-5085-8141-0dcb7e01ea52 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 9 - Chip seal - bitume app rate
label | 97c48499-a800-5f6b-8080-5b297a09b476 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f37c6213-1790-57f8-a6cc-462d5a3659c4 |  | note | Detail - Bitumen application rate each spray run to be determined on the day dependent on conditions by sealing supervisor
label | c260bee0-1745-5ee7-b8d0-4821292456f7 |  | note | Frequency - Each spray run
label | 6db5224c-441d-5ef3-9e3b-5ac12c9d464a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure by calibrated dipstick reading
label | f408065e-f816-54ad-aa03-0688865e9765 |  | note | Conformance Criteria - Current E/2 Certificate, +/- 4% per Spray Run
label | 74f8df16-d943-50bf-80ff-8dfe9621b13c |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 10 - Trafficking/Rolling
label | ce11ba9b-8332-5334-bb5c-f29734257564 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 48fb630d-5e86-55b5-9e6f-5b21c78a75f7 |  | note | Detail - Details of roller type, etc please
label | 45e77a81-016e-5cb2-b5f6-d586d55a0164 |  | note | Frequency - After completion of sealing, rolling. 24 hour trafficking post rolling
label | b7b4191a-323a-5032-967c-4953f7507adc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 5373891e-fffb-5b57-b7cc-f3fce6e275a1 |  | note | Conformance Criteria - Walk over site
label | 1686f1b2-065d-51c9-bffe-63f251b61bff |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 11 - Post sealing inspection
label | b3513e3d-4e8a-5e5e-838a-10f20f452fdf |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1e1a982e-9562-55af-b666-f13a520fb28f |  | note | Detail - CPS Engineer to carry out inspection and check the bitumen is completely bonded to the sealing chips. (No stripping)
label | 74924378-34aa-5e9d-9d58-1dace024be67 |  | note | Frequency - At Completion of Chip sealing, for each site
label | 10ee90ca-5230-5913-91eb-16147cfda61b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 6ba4b40b-2d84-5f0f-8858-a325dd424cd8 |  | note | Conformance Criteria - Walk over site
label | 7be59156-b51a-583c-a201-99cd162fcfbb |  | note | Records - Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Lot Number QA File
label | a4fe7684-37b7-5cf1-a9a4-5913a368ee07 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e2d46813-74c2-5f9c-90c9-f6d9a26b8f45 |  | note | Detail - Ensure all NCRs are closed and included within QA file, Lab Testing Test Reports to be included in QA File
label | 4d15ec21-4b7a-5bf4-bc9f-1dc5e2ed5c07 |  | note | Frequency - At completion of Lot
label | 01976745-f850-59c5-80f3-bf4b9ff739cd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 1cfe620c-17d1-521b-865e-1ec6fab25884 |  | note | Conformance Criteria - Ensure all QA is uploaded into CONQA/Procore
label | 37ed715f-a61d-53e0-90b0-dfa7534863ab |  | note | Records - Test Reports, Lab Tests
checkpoint-status |  |  | checkpoint | 13 -
label | f48bd43b-49ed-5047-834f-76b70d434615 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a07f26c2-60d1-5a53-9e6e-ea6fee3ffa12 |  | note | Detail - A complete set of subcontractors QA to be included in QA file
label | b8c1f7f9-328b-5fbe-8651-d8d3647a20b5 |  | note | Frequency - At completion of Lot
label | 68c63f70-6349-5b91-8bec-aea7d5eaebd9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | d736d731-131b-579b-8a66-dfb649982bce |  | note | Conformance Criteria - Check all subcontractor QA records
label | d56efbb4-c4a6-5b5d-a52e-1f187c7acb45 |  | note | Records - Subcontractor QA Records
checklist-sectioned |  |  | checklist | ITP - E1401A - Captain's Culvert Inlet Remediation - Parking bay Construction | itp |  |  |  | Yes | ITP - E1401A - Captain's Culvert Inlet Remediation - Parking bay Construction | b91c12cd-11d6-4fc8-b33c-5bcb92aab5bf
checkpoint-group |  |  | section | Setout
checkpoint-status |  |  | checkpoint | Project Site reps.
text | ceb1c1e9-1856-51a6-9b6d-418c1684447a |  | textbox | CPS Eng.
text | a60cba7c-2e1e-5d16-a9f4-2a7b95d02c7e |  | textbox | Site Engineer
text | ebda585a-0903-5687-a04b-5ba5c83e22bb |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 212763a5-0c5f-5fae-928f-a1e4f35454ac |  | note | ACTION (Hold, Monitor, Witness) - H
label | 45a57b27-f2d0-5066-a330-e9fdd2d0b902 |  | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
label | 93273dfb-94cb-53f4-9697-ce374561d75a |  | note | Frequency - Prior to commencement
label | 09c5fc60-ec88-58be-92ca-47114db252b9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 31783811-7f32-5057-933f-4a0cc199dca6 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Proof Roll of subgrade
label | 2ed52153-b982-59e5-a8c3-f31ae8e21ef5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c203fb28-b7fb-58e1-8cb9-13fb0bdc7a2b |  | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
label | cfae26cf-75b9-5c15-ba78-771ad1cf15ce |  | note | Frequency - Prior to Sub Base Construction
label | 60b862ef-62ef-5c5a-8ec8-1392d7ff52ba |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c9ac3c63-ad9b-5ef3-ad2f-a073523112a2 |  | note | Conformance Criteria - Engineers Acceptance
label | 2348cdbc-1362-5f4f-bd2d-c295b9f8d558 |  | note | Records - Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Sub base
checkpoint-status |  |  | checkpoint | 3 - Material Compliance
label | 8087f501-0214-56b3-8b65-8f830a854f3a |  | note | ACTION (Hold, Monitor, Witness) - H
label | e5cdd21c-f7de-58f1-a5da-283c3de1bf7b |  | note | Detail - Aggregate material compliance for Subbase stockpiles
label | c8b99a80-d15a-5d43-b1d4-64c7c477fd5b |  | note | Frequency - Prior to commencement
label | 31bfa694-f21d-5648-b460-170733696e58 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 2245adc3-dcdf-51ee-8d08-e3cf9826e82e |  | note | Conformance Criteria - Crushed AP65 with 30% Crushed face. Lab test for MDD at OWC
label | 28cce37b-42e4-58f6-b682-7875f9e77211 |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 -
label | e9f8e870-9ddb-5bea-88c7-6a0e12204b81 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4a51e39c-24f4-57c8-8700-60c563ea4eb3 |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | fb205668-e000-5d78-9397-d9206ac7b78e |  | note | Frequency - During construction
label | a4e0a07d-c830-5892-8b80-c32e208ac177 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | 7b9aba9c-60c1-5f11-b590-74faa0c726b3 |  | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials deliveresd to site
label | 4bbd5f70-332c-5021-bec1-857a4fbb60d4 |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Sub Base Construction
label | 233ca137-22db-5fb8-81f4-669e086721d5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1dc4985d-17e7-5997-b784-91869c3b730a |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | adac4c1d-15a1-59ea-aa33-b3f9fafcd404 |  | note | Frequency - During construction
label | 8c0b4743-7710-5434-85bc-dad070c906cd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | bf6c4ed9-631e-5929-a3ed-979f5b261c55 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 6 -
label | 9694fe49-bf19-5cbc-b268-7fa3ed010325 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6acf8cef-859c-591a-aac2-cd5b4f82cd2c |  | note | Detail - Carry out a Level Check on the trimmed Basecourse
label | 6f6be30e-49fa-55fb-bc2a-0f232becd24e |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | f1514366-323a-5de0-a0b1-66480376e69e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | b3ef84e5-dc26-57f8-aa4d-cdac88eb48fd |  | note | Conformance Criteria - Tolerance = -5mm/+15mm
label | c086a417-7078-58f9-b0bf-744014e95f92 |  | note | Records - QA measurement Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 -
label | d4ef6132-f8ce-50af-a26a-e60a3f98b7ac |  | note | ACTION (Hold, Monitor, Witness) - H
label | 74d8d24f-a126-51b9-9346-ffeab15498b2 |  | note | Detail - Degree of Compaction
label | d2f6d690-19c5-575d-a1db-d7e37fdf58c5 |  | note | Frequency - 5 per Lot
label | 598df6bc-12ea-5e0b-9290-c5c919920d8a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | fdf0c47b-be49-5e67-aaca-d489f4d2dd75 |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | cee8562d-2f3c-58c3-b396-21e74944cfe7 |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 -
label | f5c0a594-3734-5369-adaf-3b0b39e2e224 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9ff3ffb0-c117-5265-8f0a-2918f3aaad18 |  | note | Detail - Surface shape check
label | aa71dc6c-be3e-5ffe-9611-077d05d8e69f |  | note | Frequency - Prior to base course Construction
label | e822b3ac-5eac-5b04-b86a-53d4031b5378 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 17392b6c-ee71-5708-99aa-b6bf45a1babc |  | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | ce183eab-6664-57e2-8448-92ffd416ee1a |  | note | Records - QA measurement Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Base Course Construction
checkpoint-status |  |  | checkpoint | 9 - Material Compliance
label | e055c6c1-1b3c-5215-b488-a6b3218d0040 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6f65e327-c81e-54cd-b090-5c68dad172c5 |  | note | Detail - Aggregate material compliance for base Course stockpiles
label | 14a38f51-dda3-55e8-bae8-4dd8d5030cc5 |  | note | Frequency - Prior to commencement
label | 58cad80f-8f29-5abe-af6c-8b6a981f4987 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | a279cfee-b023-510b-acb3-76b50c20cc80 |  | note | Conformance Criteria - Aggreate shall comply with TNZ M/4
label | b0e75ff2-7f22-5df3-8ee6-74572ab5550f |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 -
label | 1e2416dc-58c1-55e4-821d-e1e04ca3a27a |  | note | ACTION (Hold, Monitor, Witness) - H
label | bec6f2d5-6540-5aa6-ae83-167d92da04bf |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | 78b97c41-5ef8-51fc-9a70-bb6a56225203 |  | note | Frequency - During construction
label | da1a8f4f-f094-5ae8-b0f4-92c660573281 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | fcfe2d2c-c224-5f5d-8367-25b410c92a55 |  | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials deliveresd to site
label | 1fc76703-e212-5ea0-aab5-381e6ba6f58f |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Base Course Construction
label | 9eb0f2e5-cbb3-5e19-888d-d2208ae8b0cf |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8a94034e-7f81-59b5-9bbb-a3d1647056ee |  | note | Detail - Mat sampling of Basecourse Material
label | 07e68a9a-e8f0-55cc-a2e6-c82692da8320 |  | note | Frequency - 1 mat sample for the job. Pavement CPS Engineer for further instruction
label | a953f07f-97d2-5d3d-a9a9-306fbc52b72e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab testing
label | 6c0c080b-4187-5321-be22-f8c0803175ab |  | note | Conformance Criteria - Grading to comply with specification
label | 84a059f0-a434-5743-aae1-6eea68119956 |  | note | Records - Mat sample lab test result
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 -
label | 66a4b2d6-ad70-5382-a00c-3fc0cc8c337d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9f9668f6-f09f-5cc0-8407-005218022ffb |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 78e1af79-193e-543c-878a-2eab3f4d1d31 |  | note | Frequency - During construction
label | 70fe6f5a-a66d-592d-8ca9-653d6277605c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 8210bdad-d62e-5a93-9983-089f81d8143b |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 9 -
label | 230d28bd-dae7-520c-8737-8e53b0fdc9d3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | afa39e0a-828b-5167-95e1-76ee0235bfa8 |  | note | Detail - Carry out a Level Check on the trimmed Basecourse
label | f35b1c5c-fda7-51b5-a3d5-5c499b3b181b |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | 3d7dfd3e-1803-5216-8828-f05b627dcf3f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 441a1e2e-91a7-53f5-b484-763f322fbbf5 |  | note | Conformance Criteria - Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm
label | 20ac5e2c-f7a9-5dde-9e65-52c5f8c7413a |  | note | Records - QA measurement Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 -
label | 6152c7b6-57d1-5012-b68d-9c57ee56cbe4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2d124f8f-e608-516f-aa8a-dda751c85ecd |  | note | Detail - Degree of Compaction
label | a620f6ed-5677-58c4-9b46-bddbbe852e14 |  | note | Frequency - 5 per Lot
label | 381aad5f-7daf-511f-b7b1-5d1fe47b9124 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | e8a4d1c0-2ada-5f1f-8d15-2a3dfb7b7f54 |  | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | 2df809c9-1b32-5e87-aeaf-274c68f62345 |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 -
label | 608fce49-f222-5850-98ab-8fc1d292c7d8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 802c8387-88f9-5a58-98fc-9d69c5c7af91 |  | note | Detail - Surface shape check
label | a8bdf62f-1bbc-528a-b437-10c0aaa2c267 |  | note | Frequency - Prior to sealing
label | 7ba5b0b4-ae70-5c43-ab6f-eb496fb05ba4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 508ac4c9-a92b-5d61-90d4-204bdebb8bdb |  | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | b2b306a8-3dc1-55bd-8d9b-06af36a65008 |  | note | Records - QA measurement Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 -
label | 09863528-ec79-57b1-8cad-a8fb2926b26e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1e4d11af-dd9c-5b1f-9f19-ffa25f1e8034 |  | note | Detail - Surface finish check
label | dbc60e43-9104-5cb4-bbfa-1c3e440f163d |  | note | Frequency - Prior to sealing
label | 96d52e5f-e26f-53bb-96d8-c402c2108391 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | 71030b1a-91d3-504e-838f-de20cf6d37c9 |  | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | 373a8be4-036e-5bed-89f4-89da5862b370 |  | note | Records - Site photos, Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Sealing
checkpoint-status |  |  | checkpoint | 13 - Seal design
label | ad39c149-3ca6-547b-8400-0717408b539b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8115f3f7-6365-5737-9038-317f044d8c35 |  | note | Detail - Seal design to be reviewed prior to sealing
label | 5ddf09c2-6339-52ae-ad9e-bbc21678c92c |  | note | Frequency - Prior to Sealing
label | e9df74b1-a029-5985-88a8-52ba1f59b38d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 432bd01b-34a2-5a27-8f30-aa589bd6caba |  | note | Records - Emails/NTE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Location/Size Confirmation
label | b359946d-224f-5d5c-9bd2-0bb7633e073f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 485661b6-3aff-5fba-8015-8045b180727a |  | note | Detail - Mark up extent of chipseal
label | 3ee77a7b-11e4-5e4d-9bfb-53ac6175796b |  | note | Frequency - Prior to Sealing
label | 02280ee2-9674-5f9d-848f-2c6d26490ebd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Markout
label | 6a154bd2-fecd-556a-81be-f0c13d699ad9 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 15 - Surface Cleanliness
label | 38a8cffa-5c64-5d08-b700-59016737a967 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 23c48578-b4df-5d1e-bc0b-d1f594228825 |  | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
label | 26fb3d07-3a30-5eea-b057-f8d169bf839e |  | note | Frequency - Prior to application of binder
label | 2874f116-084b-510e-b7a3-4048f62cfbae |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 2931bdc8-f659-5284-9646-4cd7a68e1da9 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 16 - Binder Application
label | 636fcd3a-937d-59d8-a051-558dbb1405de |  | note | ACTION (Hold, Monitor, Witness) - W
label | 27330b5e-79e9-585f-bd89-e4896001851e |  | note | Detail - Ensure the Binder application is according to the seal design
label | 4c71d3d6-079d-546e-a1a3-af957bb51db1 |  | note | Frequency - During sealing
label | f74e14e4-9b62-5dd8-9a27-e6acd9686249 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 02dff363-c013-5cbf-9424-95a68c60387d |  | note | Conformance Criteria - According to seal design
label | 071019b2-1840-5752-826c-d83983d4b9bd |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 17 - Chip Application
label | 6060fbc4-701c-501d-bab4-4836d52e3590 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6e323dd8-4bd9-5470-be25-bd7a92c3b354 |  | note | Detail - Ensure the Chip application is according to the seal design
label | 866675df-e7d4-5d95-8d32-36f0db1fc2d8 |  | note | Frequency - During sealing
label | 9a043b31-a570-5900-9e62-b524acb6246d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 6e5a5804-1f2b-52d8-b130-9bb94704792e |  | note | Conformance Criteria - According to seal design
label | 7ee75279-30f8-55e9-a60f-26b455ea13ed |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 18 - Compaction
label | 102000db-2e2a-590e-8d0a-ae4e02373726 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7563fff2-3234-5d59-a25a-8f42892a4b5b |  | note | Detail - At completion of rolling
label | 32f85830-575d-5432-9211-a5ed90b0e0a0 |  | note | Frequency - During sealing
label | eb6de82e-acdd-5ee4-812e-a0d6bc9dcad5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 0e15bc6d-2713-58d3-b8be-192da04592b8 |  | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | 30e11b46-8e94-5d6b-89fc-7012f66b922b |  | note | Records - Photos,QA measurement Sheet
checkpoint-status |  |  | checkpoint | 19 -
label | 7da55e0f-30c5-55e0-80af-dee71565413a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2e9a508f-e39b-5641-b4a0-c91f55514f5e |  | note | Detail - Removal of excess chip
label | a85f0e80-df11-586a-a8a4-d51bb5a7f920 |  | note | Frequency - Within 48 Hours of Sealing
label | 9687a92b-a03a-5998-887c-03550625dc70 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | cd8c7c76-9775-53f1-9aa8-0b34340cc4bd |  | note | Conformance Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | 79ce4688-a624-52cd-a066-0994e25b19dc |  | note | Records - Photos, Site logs
checkpoint-status |  |  | checkpoint | 20 -
label | 1d512069-6da0-5eae-a91d-6328352f312e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 69819213-f331-5c17-9007-e5a2ae7cf179 |  | note | Detail - Surface finish check
label | 455df514-f7ab-5405-94a5-174486db4165 |  | note | Frequency - After sealing
label | a26ae8cf-1dd7-591f-b9ed-5540123d0a2a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 84602eb7-57ac-5daf-9eb3-e2dc7f9eafb1 |  | note | Conformance Criteria - Engineers Acceptance
label | d7b2acfc-4ce5-5cf6-9a5d-5eaf901d091a |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 21 - As-builts
label | a203f543-ae86-5b9d-a67f-29c48cffab8e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3fe5c3c8-b236-5617-a7e8-41b8c3f23992 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | b0f60817-c727-596f-8d35-932c18c0f281 |  | note | Frequency - At the completion of the Lot of work
label | f5cadd40-8ded-550c-9155-34744cb09d25 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 0bd74447-db38-5c1a-9265-07beea54a51d |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - B1004F - Tangoio Falls Steep Underslip - Asphalt - Surfacing (AC 14) | itp |  |  |  | Yes | Ω (Deprecated) ITP - B1004F - Tangoio Falls Steep Underslip - Asphalt - Surfacing (AC 14) (old version) | bc91395c-3574-4df1-817b-1c6ed833c600
checkpoint-status |  |  | checkpoint | Project Site reps.
text | dd97d2f3-04f3-5375-946e-99945aa9c3ad |  | textbox | CPS Eng.
text | 88de46ff-3f8c-5f16-8eaa-9a46471fcdca |  | textbox | Site Engineer
text | 88ec92cf-f25e-5055-8cfe-ac9595f40975 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Installation of Erosion and Sediment Controls
label | ec3706ea-3787-505a-81c9-56f74b80688c |  | note | ACTION (Hold, Monitor, Witness) - M
label | 5cf6ba6b-7d9d-5988-9c81-a36b50cf1180 |  | note | Detail - Monitor effectiveness of the ESCP Controls throughout the construction process
label | f885ce89-7ae8-5944-a5ab-028cb75328ae |  | note | Frequency - Prior to commencement
label | 07ba551a-83cc-5d80-867a-b877fbc391cd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | e2c303ef-e489-5dcd-95af-2df7c1385e5b |  | note | Conformance Criteria - Visual Inspection
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | 45c22153-d3c7-5732-a6e1-76d70a5c46d2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3fb8d337-2268-59c2-9fbd-401a98e1e80c |  | note | Detail - Set out pegs installed every 20m if required
label | e1a024cd-8830-56d8-b74c-463694515b6b |  | note | Frequency - Prior to commencement
label | 7d63004f-9404-5478-9d68-cc5ac765a900 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | b38ec1c0-1250-5999-9e8e-60d80bc20c32 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 -
label | cf030fc0-539e-57c2-9058-a4570f913722 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 97bc7611-ea62-550f-9910-07db8268f789 |  | note | Detail - Determine paving run start/stop locations
label | 6eb93131-fcfd-53e0-a9fe-f546539dae20 |  | note | Frequency - Prior to commencement
label | 03adaaeb-584a-5700-afa7-17b64425ef18 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 39fc1a1a-7f18-56ef-8958-74cbcd7faa67 |  | note | Conformance Criteria - Mark out on site
label | 6556e340-1572-5382-bf54-e46c350660b2 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 4 - Material Compliance
label | 8a69f5d4-32ee-53c0-8e78-4ea493b4c891 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 12bdfbf8-34b8-51bb-9abc-7c44d85698cd |  | note | Detail - Mix Design approved including peer review
label | 46f0a0d3-62c5-503a-8b53-70af4cc9ca11 |  | note | Frequency - Prior to commencement
label | 268e3e13-7ec3-52bd-b3ff-ed87bc31e4a5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 98db704d-158f-5d88-a4b0-fe2bfd2bc007 |  | note | Conformance Criteria - Material is approved by a Notice to Supplier being issued
label | d5911bc1-7335-5137-86ef-be96f604713c |  | note | Records - Mix Design
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 -
label | 0969cc3b-1bf0-5226-861f-2f27f0242e1b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9f37d8cc-a167-5175-94a8-953bfe64c55a |  | note | Detail - Asphalt Material Quality Testing
label | 81779b37-9045-55ae-b0e6-2580d0ea7112 |  | note | Frequency - Prior to commencement
label | 17a7528b-d063-527f-8d77-de93257c6266 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 23b1ddf3-4a4c-5022-8214-978679553f46 |  | note | Conformance Criteria - Fine and Coarse aggregate Weathering, Crushing, Sand Equivalent, Broken faces, PSD, PSV. Bitumen testing, Penetration @ 25 degrees Celsius, Dynamic Viscosity at 60 degrees Celsius
label | fbad5d01-45cb-5b9f-abf6-e651f76b0a9e |  | note | Records - Asphalt Plant Results
checkpoint-status |  |  | checkpoint | 6 - Asphalt Production Testing
label | 7439643c-f313-57e1-abb0-eabedd485eda |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1d60bc71-57d9-5755-b668-684eb227b852 |  | note | Detail - Full volumetric and air voids test 1 test - 1 test per day. Binder content and grading 1 test per 100t.
label | 42eb7b11-0a11-5f30-8ee1-a70b6fde0df5 |  | note | Frequency - Prior to commencement
label | e64519ed-9ae0-54b3-98ac-53c883d2f9bf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing and measurements
label | b86df6e9-cbf9-51a2-b451-80a83d184840 |  | note | Conformance Criteria - Binder content, PSD, Mix Volumetric, Mix performance related properties resilient Modulus and wheel tracking, mix production temperature and load out temperature
label | 87c7804c-471f-5cdc-8556-59cbaa5ac865 |  | note | Records - Asphalt Plant Results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Tack Coat
label | 0406553e-4558-5ac6-a7a1-fe8a1d2c95f6 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 483546b9-cd63-5e7d-ba7c-f86e99720e22 |  | note | Detail - A Spray sheet for every day
label | b03d475d-157a-5596-9cc2-f21875c343ba |  | note | Frequency - Prior to placing Surfacing AC
label | 6ec5941f-2cda-5dc2-9a81-05f720674371 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 64940ddb-098c-54bf-ad0b-2f26483b99ec |  | note | Conformance Criteria - Showing the required spray rate 0.2 L/m2 with a tolerance of +or- 0.1 L/m2
label | 5d255db8-42c2-571e-a7c4-111fcafe9bb9 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 8 - Construction of Surfacing Asphaltic Concrete
label | 3f1925e3-2eeb-5781-8bc4-172c00e78e03 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d5f70935-e6d0-584c-ae3c-c3f37ca07cec |  | note | Detail - Site team QA Checks
label | 18d69fc3-8056-5324-845c-67ad586bc498 |  | note | Frequency - During Construction
label | e0c1bcb4-8b69-58ea-bbf3-2385d29bdd50 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Measurements
label | 96974d6a-4194-58d4-afa4-b8c18e66a1db |  | note | Conformance Criteria - Delivery temperature, mat thickness before compaction, mix temperature during compaction
label | 790f8d4f-2590-5e15-a034-ab893f39fbb6 |  | note | Records - Subcontractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Surface finish visual inspection
label | 794fd98a-5589-584f-b141-224664c0a537 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2de6cb83-df27-54ff-b0ce-b302fd806f3b |  | note | Detail - Site walk over
label | 29dd2d38-0484-5df3-9ea7-cc01065af781 |  | note | Frequency - Post Construction
label | ea4c6dd0-0300-5b82-9e2e-03165aabb15d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 58e6a9a3-72b9-5fcc-88c6-8c7658de501b |  | note | Conformance Criteria - No visible cracks, No obvious defect related to poorly constructed joins, No areas where water can pool; No part of all pavement surfaces deviate more than 5mm from a 2m straight edge lying under its own weight on the road surface parallel to or perpendicular to the road centreline.
label | ecd82465-a0cb-5caf-b9bf-2359bb888bf2 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 10 - As-builts
label | bc71e17d-d0ff-5080-8dfd-4e9b6a642d39 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2721306e-1a0b-5f12-bcd4-792ebf10d6fd |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 47d8243c-57cd-536d-8916-188e9691113c |  | note | Frequency - At the completion of the Lot of work
label | d522578f-81cb-5827-9186-24e1f012acbf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 19f28616-a1d2-5580-b442-07f90c313ccf |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Quality Assurance deliverables
label | f56a7804-4f46-5c48-84c0-4c1bc5f8db33 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 36678925-3bc1-57d0-8d5d-3a37bb9ce273 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 499a7f78-8f05-5973-834c-20b2820f4305 |  | note | Frequency - At completion of Lot
label | d725802e-8896-5317-9388-2d253a24f7f0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 4dfe398e-0173-5eed-ad61-2a45d3fa1712 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | cdc7d351-8d14-5ace-958a-d14244cc37b4 |  | note | Records - Asbuilts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 12 - Completion Sign Off From Fields Below
label | 502affd4-8d82-5843-871d-ec7f9d9f4fbb |  | note | Records - Signatures
checklist-flat |  |  | checklist | ITP - Tangoio Falls Steep Underslip - B1004F - Guardrail Installation | itp |  |  |  | Yes | Ω (Deprecated) ITP - Tangoio Falls Steep Underslip - B1004F - Guardrail Installation (old version) | c13fcb74-c6bb-4ccf-af26-adfa7f821e68
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 29030db5-c00a-5b76-8e85-eb4404a9a888 |  | textbox | CPS Eng.
text | b1819594-5ef7-580d-b4ab-2d32a8e7bbeb |  | textbox | Site Engineer
text | 01af451b-070b-54a3-af99-fd72751c6a1f |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 -
label | 6dea88ec-f58b-501d-93d7-ebe9321acfad |  | note | ACTION (Hold, Monitor, Witness) - H
label | e2b7f8d1-f743-5c3d-b96d-ddeec4662f68 |  | note | Detail - Earthworks and pavement construction shall be completed prior to barrier installation.
label | 3d1b7539-b5a4-5fb0-96a4-7a711a9a67d5 |  | note | Frequency - Prior to commencement
label | f7f07292-9d4a-5fe9-bd99-544ff0e59e66 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 -
label | b4d1b46c-d3cf-5dce-8af9-9b2118e5b1c1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | fd791560-24a0-5cba-89b2-5614beb3ff29 |  | note | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | 45bb7fb4-fa52-5425-9cee-20e73b2cdc4e |  | note | Frequency - Prior to commencement
label | da9da46b-3e10-5b2c-a0c4-46c90b193eca |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 8cf02767-536a-5b90-93ba-0fb1a6a07af8 |  | note | Conformance Criteria - National Standard for Traffic Signal
label | e1a6c097-4c60-5fd5-992e-458a89670ed9 |  | note | Records - OFI or NTD/NTC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Survey Setout
label | cc7b4c94-fcc6-5d9b-b31e-c4c3b73a0444 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 74046930-de13-54a9-97bd-75341a09cc5f |  | note | Detail - Surveyor to mark 20M Chainages on the bridge from which Start and End Point of Barriers will be referred.
label | eecd08ac-cfc5-558e-8fc2-29e426462a0e |  | note | Frequency - Prior to commencement
label | 9179c29a-c84e-5494-b4d1-e5af0211fbf0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | ed185c4e-f0e5-5d57-a2de-4d45da1890d4 |  | note | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | 58cc6129-b50b-54bb-99f3-272f57897a2e |  | note | Records - Approved Construction Drawing.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Material Compliance
label | 233b4d6d-2bb1-5890-a1a7-9d78ae99e9a0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ab460161-921d-51a5-88d5-129389fdcdc7 |  | note | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
label | 5432a543-85de-50a3-ac6e-93a1495fe1f3 |  | note | Frequency - Prior to commencement
label | 129c1afb-386f-5c1c-bea0-4f202db11fe0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | 3c1bcf6a-5c66-58af-b5cf-d955a2b528ad |  | note | Conformance Criteria - TNZ M/23:2009
label | 5a71919f-4867-5c44-b0d4-c8fb1222b41e |  | note | Records - Manufacturing certificates and delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Guardrail Installation
label | 635c447b-241f-562a-a41a-e64794178222 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 535dd2ef-9199-5ec6-ae4a-eaeba9eee84a |  | note | Detail - Ezy-Guard shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | fa3ee647-49fd-5f03-b55a-d00991d50621 |  | note | Frequency - During installation and on completion
label | 48aa63b9-dccb-50c0-af1e-1f9548ba3a66 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | ddd40a3e-864f-5ed9-bed5-1b156d454036 |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | f20f2faf-8ae1-5e13-b2f3-05d312ee7ed4 |  | note | Records - CS-4117
checkpoint-status |  |  | checkpoint | 6 -
label | bd31f059-a6ae-58f5-a3d1-0f696684cea5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | fc916c8a-8f72-59ff-b542-a84c12b3b363 |  | note | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | 3b14b24f-290a-5901-8e36-881d6e834327 |  | note | Frequency - During installation and on completion
label | 2e01dd05-689a-5aae-aa45-8fa7d0d6c2a1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | b473369e-cec7-57a9-9841-1fee3b11c242 |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | 383552a4-6603-5ef4-a69c-09d1a17fe519 |  | note | Records - CS-4117
checkpoint-status |  |  | checkpoint | 7 -
label | c4779109-59af-5f99-b511-8b2d4b38941e |  | note | ACTION (Hold, Monitor, Witness) - W
label | b42d7b6c-a6da-5bc4-a39b-0b853b6e25b6 |  | note | Detail - Thriebeam shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | 730916ea-5aaa-5269-8362-6450c76557d9 |  | note | Frequency - During installation and on completion
label | f2793c75-5064-51b2-b568-c5ed5f5c9e44 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | 8fc72101-7539-5344-9387-ee862663bddf |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | fdb25ff3-fa19-5687-b44e-9fdd6bfd0b10 |  | note | Records - CS-4117
checkpoint-status |  |  | checkpoint | 8 - Lot Number QA File
label | 6a94fcf7-bf73-5fb0-85cd-bc85e8b1aea6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9faec207-dc75-5bc7-beb0-899cf0eb72d0 |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | cf38c6b2-2650-5b7e-a488-41a027fdfd23 |  | note | Frequency - At completion of Lot
label | 8404a664-fc35-5666-89c0-37f8b6713dd5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | e114dbe6-7bbd-5767-9f8a-ae0cb7cfacad |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 8f12b964-f263-5df6-94fb-6ad076e6ff68 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 9 - As-builts
label | f873b643-3c92-5754-a495-8f8e9fcfc7ba |  | note | ACTION (Hold, Monitor, Witness) - H
label | baaa1cf1-66b9-5b21-97d8-5ea87ed9f116 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 677c987d-f423-5afe-8ae3-e23dee0e244b |  | note | Frequency - At the completion of the Lot of work
label | 46f55ef4-025d-5ae3-98d1-7284c2f83ef8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | b4a953d2-9324-5f84-b162-c5d61b856abf |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Quality Assurance deliverables
label | 488bfea8-12ee-5683-a6bb-e585b6e494e5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7bd1409e-5c51-574a-94ea-5d1a577d0ab7 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | afdb8cde-14df-593c-9b6d-cf1b34638285 |  | note | Frequency - At completion of Lot
label | 7d7ce66b-c1e6-5c98-b8ad-041593cf4433 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | ff76fa94-d064-5be4-bdbf-4cf71d915da8 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 77b45e4c-4079-5210-b526-133a44e1be5f |  | note | Records - Asbuilts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 11 - Completion Sign Off From Fields Below
label | 466662aa-c337-5563-97ac-633f107d1786 |  | note | Records - Signatures
checklist-flat |  |  | checklist | ITP - Mangahuini Sheet Pile Wall - F3002G - Precast Dolosse Installation | itp |  |  |  | Yes | ITP - Mangahuini Sheet Pile Wall - F3002G - Precast Dolosse Installation | c14bda9b-0f1c-4b37-b664-054c087e0a17
checkpoint-status |  |  | checkpoint | Project Site reps.
text | b361f670-2dba-51ff-aab5-f5cf9699b5c2 |  | textbox | CPS Eng.
text | b0b5cd6d-eb61-5be4-bc3e-07d859425b14 |  | textbox | Site Engineer
text | 96a52802-96d6-5dab-bb8b-7500140a7c5e |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 6fcd7122-16c2-5a42-9217-3aeffd5089fd |  | note | ACTION (Hold, Monitor, Witness) - H
label | c4201754-69a8-5739-9728-f159d2aa8631 |  | note | Detail - Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | acc1f260-9890-5f36-9013-9d65348c31fc |  | note | Frequency - Prior to commencement
label | 2f0d38a7-72c6-58ee-a73c-16e5b9ab714e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 3438655d-7ea4-5aa7-b9cc-8d33ad73a432 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | acc1d686-ec4b-5188-a20e-fecaaf22abc0 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Precast Installation
label | 710f06c9-044a-541b-8f53-fd97e082087e |  | note | ACTION (Hold, Monitor, Witness) - W
label | d142d536-a34a-5a89-900a-c6cec0caf839 |  | note | Detail - Delivery Dockets are collected and signed before precast materials are removed from the truck
label | e7e58567-c46b-59b7-b12e-ebedaf82ae01 |  | note | Frequency - Prior to commencement
label | 512d5a3b-9945-5c3d-a430-90b982bacd3d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | f71bc4f5-aa8d-5e3f-b911-f28e08998869 |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 3 -
label | cfe9cb73-635e-5102-ae4b-677302351e20 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0aa0bfbf-d943-5ac2-9d10-e9401b306736 |  | note | Detail - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
label | 0cac6042-734c-5be0-a6c3-9b83b65d830b |  | note | Frequency - Prior to unloading
label | 497c3cab-27c0-5303-b12f-a69cc5ef5499 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | a2e2dd6b-8c5a-55a2-b662-04363a8def84 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4 -
label | 51f59ae6-5f93-5151-8502-0ae8e8c2a8ed |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6f7c6874-6c4e-5041-825a-90047c6da07c |  | note | Detail - All Steel brackets, bolts/nuts & steel wire ropes must be inspected on delivery. Any damaged items shall be isolated, repaired or replaced
label | 867ce4bd-065a-51af-8cd9-fef44a3d6e5f |  | note | Frequency - Prior to commencement
label | 27cabd83-5c5d-57b6-9792-ce988b4b9867 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, Document review
label | e76414d0-2ed7-5b1a-b48b-6d4073b4b1a4 |  | note | Conformance Criteria - Comply with AS/NZS 5131. Brackets will be manufactured from 16mm thick 300 grade steel plate. Steel wire ropes shall be 20mm in diametre. Any welding required to be approved in writing by CPS Engineer
label | 825ebf85-e701-5839-8b14-9479a2c86eba |  | note | Records - Photo's, CPS COR Report, Manufacturer Test Certificates, Welding tickets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 -
label | ca1eb944-aad6-52c7-9df1-58bf7e8fb0ab |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1e89c40b-fb9e-5871-bcd3-9c40028ac5d9 |  | note | Detail - Approved methodology for the lift is followed by all site crews and any variation from the original plan is documented at the pre-start/OFI
label | c8bcdc95-7263-5f15-b0bd-0c47643b0285 |  | note | Frequency - Prior to commencement
label | 28c4a49b-5185-585e-8fa0-515c44d41e94 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review, Visual inspection
label | eefb803e-3080-5eeb-8da3-924bc2e45a57 |  | note | Records - OFI, Photo's
checkpoint-status |  |  | checkpoint | 6 -
label | 528e4ea3-a1e1-5a12-8bdb-445fe765c2ac |  | note | ACTION (Hold, Monitor, Witness) - H
label | 93279b0d-fb8f-5dbb-9375-968c76d32f87 |  | note | Detail - Precast Components are to be installed in accordance with the design/drawing. Each unit is to be butted tightly against the adjacent unit to present a coherent mass
label | aaafdde0-7b37-5f5e-b5a7-b19cdff292b1 |  | note | Frequency - Prior to commencement
label | 2fca2821-352d-5cf6-bcb4-e94089df17a6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | eae7edc8-94d5-54be-a420-ef80fee5dd9f |  | note | Conformance Criteria - The position of the dolos groynes will be set out and agreed to with the CPS Engineer
label | e754b700-f686-53b4-aae6-589facf50ef9 |  | note | Records - Photo's, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 -
label | 2a42c47e-4dc6-5775-96be-76729bca4cf7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c952c7fe-eef6-523e-8614-bfd133f28c84 |  | note | Detail - Dolosse’s will be secured in position using 20mm diameter steel wire ropes passed through the lifting eyes of the Dolosse’s and secured to brackets welded onto the existing sheet pile wall.
label | 530afb9a-c65c-5cf2-a630-7b674416fed6 |  | note | Frequency - Prior to commencement
label | 8d807c06-2580-544e-855f-5287502c9ca1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 78bbd848-3279-53a0-9bde-8bd250c4201b |  | note | Conformance Criteria - As per design/drawings. Welding to be inspected and be approved in writing by CPS Engineer
label | a909d8de-9bd1-59e7-b7e1-b77aa26abc64 |  | note | Records - Photo's, CPS COR Report, Welding tickets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - As-built Survey
label | 4aaff410-aaff-53fe-8a03-3bbaa1045954 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2b073b31-5fba-504a-9198-288199bb8a77 |  | note | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
label | cab7c53a-0278-5ac6-97ec-73bf56fc38ed |  | note | Frequency - Prior to placing topsoil/pavement/ finished surfaces
label | 73b0908c-2361-5cf1-8248-69ac2fd3d608 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | 0f5b2c0a-709c-5908-bb25-29283e177875 |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | 76feba2c-877a-5a5e-bf9e-d17e9d53db51 |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Quality Assurance deliverables
label | 8ea93cba-65d5-5478-8fa7-c6d0af5f7c5d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9b72ccbf-e087-52de-83fe-29b7b47d29b1 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 799e8dba-7f79-55bb-aa83-e6039effc78e |  | note | Frequency - At completion of Lot
label | bb12e4da-08d8-54b9-a823-a2ef485f0c66 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | f019f10c-1706-53f2-8b95-f1727901e8c2 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 6486f58f-ebcd-5bd3-bfca-c7d09713eb5b |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 10 - Completion Sign Off From Fields Below
label | 3db71024-9154-54d5-9335-73285f4ffab8 |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | ITP - F3002D - Mangahuini Long Drop Site - ITP for works | itp |  |  |  | Yes | Ω (Deprecated) ITP - F3002D - Mangahuini Long Drop Site - ITP for works (old version) | c26c115f-33e7-4ae6-9c0c-177c7ec0243e
checkpoint-group |  |  | section | Section 1: RECEIVING INSPECTIONS
checkpoint-status |  |  | checkpoint | Project Site reps.
text | a9ef3422-cf18-5e07-95f5-b983861f6c25 |  | textbox | CPS Eng.
text | 1c7f6ca3-0c79-50a4-90a0-39e9bf8e661b |  | textbox | Site Engineer
text | c670454a-08e0-5e75-b4dd-7317d3e654d7 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Buttress Rock Armour (D50=800mm)
label | c03a65c0-ea92-5fbf-889d-e3593fc3ba9d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 82ede738-003a-51d3-a1c8-7928fa284a46 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 7a862530-a12a-56b7-9f9b-93281c2f1b85 |  | note | Frequency - Prior to commencement
label | fa82e688-0b3f-5323-92ad-99411b5d52f5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 3754b16b-d255-5fca-acd7-6a94747d8ef3 |  | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 to 800mm with a minimum specific Gravity SG of 2350kg/m3.
label | 3cc65163-0bd9-5a91-b119-ad8c8ae64f57 |  | note | Records - Material source test results, Delivery dockets, Photo's
checkpoint-status |  |  | checkpoint | 1.2 - Culvert Rip rap rock (D50 = 500mm)
label | 6f11bac8-5ff4-5f1e-b357-b3b3470c1cb8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ff483354-72a4-5a50-9667-b0680b7be3d2 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 293475d9-e6d5-5c52-b990-87078c3e00f0 |  | note | Frequency - Prior to commencement
label | 7ce9b540-2c6f-5f09-9c7c-64dac7573ba9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 2d07d77a-881c-5883-a0aa-d56214b0bc65 |  | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 to 500mm with a minimum specific Gravity SG of 2350kg/m
label | cbbafe0e-7d89-5fde-937e-569318fea65d |  | note | Records - Material source test results, Delivery dockets, Photo's
checkpoint-status |  |  | checkpoint | 1.3 - Drainage material
label | d2d7b4c5-c4ae-5da7-a934-c6ffacd87e78 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1c6684d0-6e9a-5c6e-a94b-f54acadc2eb7 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, TNZ F/2
label | 514e4d67-e043-5a9e-accb-ad613dd2fe56 |  | note | Frequency - Prior to commencement
label | 9f40bc43-58e0-5455-845e-ccf6d8e9c810 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 8b8c52a4-0b0a-5819-a8f5-9c3e63debe66 |  | note | Conformance Criteria - Comply with TNZ F/2 or approved equivalent.
label | 0795f3c0-a764-5049-b1fd-4c40d19ea30a |  | note | Records - Material source test results, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.4 - AP65 Granular fill
label | 0d08838e-b18f-5cb8-9522-9b75fc949598 |  | note | ACTION (Hold, Monitor, Witness) - W
label | edcbf013-294e-563c-974a-73fcf9feb66e |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 7b675523-017f-5cb0-9e96-d4618489228b |  | note | Frequency - Prior to commencement
label | a4d0f02a-796c-53cd-9925-9019d2db8d97 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Particle size distribution test
label | 0ae45cfb-9d2a-5aca-8610-be2559169ab1 |  | note | Conformance Criteria - Test results from a representative general fill sample tested in an independent accredited laboratory
label | 09fb2d97-a197-5c2f-b0cb-7cb7a54df5a6 |  | note | Records - Material compliance cert, delivery dockets
checkpoint-status |  |  | checkpoint | 1.5 - Class D A49 Geotextile
label | 3618705d-f5e7-539c-99e0-c70f42443444 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ce140532-f616-5fb1-8cb8-befc888e41be |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZTA F/7
label | dc3276e0-eca2-5304-b0e9-51d37c17e0bb |  | note | Frequency - Prior to commencement
label | 313a8183-b64e-5525-80dc-905b0f76f8a6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 5e9076cb-28dc-5769-8383-aba37c52b016 |  | note | Conformance Criteria - Non-woven & NZTA F/7 compliant, On dry bed below fill
label | ff33550d-4c2c-5803-a479-480db728b5da |  | note | Records - Material compliance cert, photo's, delivery dockets
checkpoint-status |  |  | checkpoint | 1.6 - Perforated lateral drains
label | 5f247443-504f-5e3c-8a29-98975bf6f1bb |  | note | ACTION (Hold, Monitor, Witness) - W
label | d7f57fd1-78fc-5363-a524-155d2bcfcff6 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 7d6aff42-ebfe-52b3-8927-104d962bd4ad |  | note | Frequency - Prior to commencement
label | b2dbce8b-b3b6-58c0-b9eb-1b1400c3bc47 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 826c43ab-a1d4-5703-81cb-4cf318bbc629 |  | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter perforated lateral subsoil drain, or similar approved.
label | e8bba67d-4edf-5b7d-96a7-b179e9154209 |  | note | Records - Material compliance cert, photo's, delivery dockets
checkpoint-status |  |  | checkpoint | 1.7 - Precast concrete box culverts
label | 92c9288e-f734-578b-b2dd-4768e8ca156d |  | note | ACTION (Hold, Monitor, Witness) - W
label | a29391f5-ab9a-5f22-98c7-27c1b7cd3281 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 4fa3117c-9a1f-5709-a93f-a86aca799f4a |  | note | Frequency - Prior to commencement
label | afc84df0-d27e-5e19-ae0e-713c9ff28a0a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | cce606a5-a5c3-506f-9dea-3f6d723a99b6 |  | note | Conformance Criteria - Delivery Dockets are collected and signed before precast wing walls are removed from the truck.
label | 46ec0856-0784-5260-a2ee-66db83489272 |  | note | Records - Material compliance cert, photo's, delivery dockets
checkpoint-status |  |  | checkpoint | 1.8 - Precast concrete wing walls
label | bb243049-2fad-5f77-83a7-78a57720b393 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d03c9aec-6f89-511a-9f5f-310157e6a26b |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 6256cdea-fb71-5c66-8697-9e1c4d5ce587 |  | note | Frequency - Prior to commencement
label | 17cf72d9-0182-5f1c-ba3e-f4c19face22c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 3c6c3f17-f531-560d-9697-1cc334f13486 |  | note | Conformance Criteria - Delivery Dockets are collected and signed before precast wing walls are removed from the truck.
label | 52027a57-bcae-5416-a287-27dfc8cdc637 |  | note | Records - Material compliance cert, photo's, delivery dockets
checkpoint-status |  |  | checkpoint | 1.9 - Precast materials
label | 317be5b5-ef9f-543c-af0c-57895778e6b1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2b64fc08-8a27-5674-a95e-1b063c1879dd |  | note | Frequency - Prior to unloading
label | cff43614-6a9b-51c6-8ff4-5701fd607107 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 3274bec8-283c-5334-9735-1d8e01b85ca6 |  | note | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
label | ab513b4c-8e89-57c0-adcf-203636eac19b |  | note | Records - Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.10 - AP40 (Basecourse)
label | c344cab7-8b40-5201-a1cf-c43d9eba008b |  | note | ACTION (Hold, Monitor, Witness) - W
label | b3c54fac-938d-57c4-919f-b08d29da6853 |  | note | Specification/Drawings Reference - TNZ M/4
label | 1bce9c57-1b10-5399-99a0-48b28755599f |  | note | Frequency - Prior to commencement
label | a5d88b4f-6f5f-55f0-afa5-92061b268e0b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 633c0d81-624e-5243-8c83-a9bd21081390 |  | note | Conformance Criteria - Source property testing, Traceability of all materials delivered to site
label | f40fa169-dc4b-57c0-8f7c-1163c10ae89e |  | note | Records - Lab test reports, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.11 - AP65 (Sub-base)
label | 123f072b-f90e-5c76-ad02-ebeb9ec55b2d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 44811f22-3ce9-5cd3-85cf-a4bb97df66cc |  | note | Frequency - Prior to commencement
label | 05ec2c5a-1ef3-54ae-8944-fae2fe010709 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 0aae071a-0fad-5e4b-8243-baffcb6e6630 |  | note | Conformance Criteria - Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak)
label | 829278be-5376-505e-a49e-b6828b7e7cd5 |  | note | Records - Lab test report, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.12 - Grade 2/4 Chip
label | 66111881-6678-56bf-8ceb-861332e5faf5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6cd91063-75db-5649-9c35-69d26df3efff |  | note | Specification/Drawings Reference - NZTA M/6
label | 3d1203ea-7e0d-5b61-93b9-4db4ed0715ac |  | note | Frequency - Prior to commencement
label | d6c9cb2c-3a50-5193-943e-2ed56b6e7ae4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | cb59b10a-e502-5c77-963b-c5d1b4ad64f1 |  | note | Conformance Criteria - Source property testing, Traceability of all materials delivered to site
label | 31cb2573-9eba-50c9-b1da-f2307a755fe8 |  | note | Records - Lab test reports, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.13 - Cement Material cert
label | 7030eb22-2303-5aac-9ac0-5885baa93f48 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 44b930b8-62b4-5543-90db-5333cae2eb1b |  | note | Frequency - Prior to commencement
label | 60e0de73-92a6-56b7-8144-7ca5cbeabebd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | fcaeaeb7-f6dd-5ecd-a260-258edf2e6327 |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.14 - Bitumen
label | a97225ed-df3e-53a9-a91a-0b8d8c969c94 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5b25d497-83c6-54b1-9279-2259cc8ddf3c |  | note | Specification/Drawings Reference - TNZ M/1
label | 0b27f2f0-b54f-5e04-a1c9-37365c978cc5 |  | note | Frequency - Prior to commencement
label | 6163deec-f423-57e0-9240-00d7c6898204 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | d3e4a8db-35f8-5a99-acf2-4597177739a1 |  | note | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
label | 36664ebf-055a-5156-961f-bdd4f337ae7f |  | note | Records - E2 Certificate
checkpoint-group |  |  | section | Section 2: REVETMENT & BACKFILL INSPECTIONS
checkpoint-status |  |  | checkpoint | 2.1 - Survey Setout
label | 7da3f0b9-5d65-5fcb-854e-674e50295a1d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 406c77ee-3c05-5b14-a8ab-d200feaef8b7 |  | note | Specification/Drawings Reference - Consistency with Construction Drawing
label | 851a5c60-4afd-5d45-8fb6-707895e5a909 |  | note | Frequency - Prior to commencement
label | a12cb09e-5272-5f84-b14a-a0e37373f1b5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 2b4794da-6bec-5a4a-ba64-0db681f2da3b |  | note | Conformance Criteria - Set out extents of fill and check against design drawings
label | ea7acb07-35c5-5452-bd55-cf94b6f9c961 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Unsuitable loose material and vegetation
label | be6c13ae-5810-5260-8a29-f60420352b9a |  | note | ACTION (Hold, Monitor, Witness) - W
label | eab67c33-1009-506c-8d0b-e6bb762e281d |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | b50f8387-5ba5-545c-ac75-e57b3e65d0cf |  | note | Frequency - During Construction
label | 25227ef3-73c8-541c-809d-04b36e5d29b1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 7341260e-cd6a-5d68-acf2-94cc7b2adbe4 |  | note | Conformance Criteria - Remove and clear any vegetation, trees and unsuitable material
label | 6dcc4955-9a38-5c2d-b216-ec81d7d2a607 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.3 - Subgrade Inspection
label | 5d788543-4e87-5231-acb3-18c83e897db2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f67ba027-9fd0-5a4c-9fb6-019253125e60 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | dd222ce0-241a-5ee5-848a-2b0c50c07a1c |  | note | Frequency - Per area as required
label | 65e0541a-8439-52c2-9ab7-07480fc681eb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | d1adaa3d-cb22-58a1-843d-e94af84e89b3 |  | note | Conformance Criteria - Inspect fill foundation, Fill foundation must be approved, in writing, before filling commences
label | 056a8437-8ede-539d-b0ae-79c1e9659724 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Class D (A49) Geotextile placement
label | 11f108fa-d610-5559-aec7-4be3a3cc1589 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 21b4c435-67e4-5104-97ab-f33a314aebc5 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 7cad53fc-f208-5a75-9431-e95f0e804b94 |  | note | Frequency - During Construction
label | 2722b31b-d429-5f11-8830-24ceceff4b8c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 8d266f1c-6eb6-5242-8e8c-7ca9a57e849e |  | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A49 or similar approved before placing granular fill. Bidim layer required between granular fill and rock armour.
label | 84424e6b-8dc8-520d-96ce-3b1230dfb76b |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.5 - Sub soil drainage
label | 85f372ac-6535-50da-91c9-0db286c825bd |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1b37ae33-80de-5348-9c06-b59a32c7f152 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, TNZ F/2
label | d174de45-6679-512a-9e06-c271dc0d3414 |  | note | Frequency - At lower bench level and mid bench prior to placing granular fill.
label | 11167a2b-9335-5ed5-965f-9675cc1a91f0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 89a1ced0-5b37-5bd6-ae70-a75cfdc8727a |  | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter perforated lateral subsoil drain, or similar approved. To be inspected and approved by CPS Engineer prior to install.
label | 3dfec212-b757-5523-884b-87555d8cbdc9 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Imported Granular Fill Placement
label | 71aa9db8-621d-5246-a7d1-eb5ed2aba815 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0049cd55-5b9d-5e5c-9321-980bd817500c |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZS4431:2022
label | 2f95ce24-7300-549e-a30f-f88fd59da3a0 |  | note | Frequency - During Construction
label | d81ae3b5-a6f2-5caa-8d2e-3cabbf05431b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | eb34cb0c-7e1e-5424-adc5-acca7f8cefcd |  | note | Conformance Criteria - Granular fill to be placed in layers of maximum 150mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade.
label | 8bb8503f-e988-57a6-b700-6f2073f55cbb |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Imported Granular Fill Compaction
label | 32884c5b-0bb7-5a32-9733-cf01894f9c47 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8c49d56b-8070-5aa9-b735-f2e32dac9ebd |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZS 4402:1986, Test 4.1.3
label | 4cfc5b80-de1a-586e-9390-f6dfd11736a9 |  | note | Frequency - During Construction
label | 2a7f51a2-a2b1-5bab-ab41-2c9437313081 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM & Clegg hammer testing
label | 4134df0c-dede-584f-b5ce-4b646900a06d |  | note | Conformance Criteria - A target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3. Testing done as per Site Instruction by CPS Engineer.
label | cce5123c-e95b-58e9-a247-a71783506d54 |  | note | Records - Test results, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Form and cut fill batter as per design 1.5H:1V
label | 91f09654-8b72-510b-a91d-a0fe01f86273 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 563f42f3-d666-50f4-9de2-198a45767fd2 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | b37562c8-6604-598a-8d55-2be008c5bd4e |  | note | Frequency - During Construction
label | bd14e94b-1017-5c59-aaca-8f4bd6bc3b23 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 151eae9e-3134-53fb-be16-01ce47d20ed9 |  | note | Conformance Criteria - Benches to be cut and profiled to suit slope profile
label | a8bd0aa3-8d3f-5eee-b780-82a277808c05 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Rock Armour (50-800dia) to form revetment
label | 8085f2d1-c815-53b1-b13b-9947d1af01b9 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 16c087b0-93ed-5d8e-9bb4-092601834c06 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 53e57817-b2bf-55a9-82eb-0a50b8ecae1e |  | note | Frequency - During Construction
label | 225a6808-e2ad-50de-945c-9a2b689364ea |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c4d5107e-d130-508d-8854-2fb70db0ce8f |  | note | Conformance Criteria - The buttress is to be keyed in to ground directly behind existing displaced reno mattresses and existing railway line timber panel retaining wall
label | b0b5120f-ddec-525d-8288-f2b932b2ee27 |  | note | Records - Photo's
checkpoint-group |  |  | section | Section 3: CULVERT EXTENSION INSPECTIONS
checkpoint-status |  |  | checkpoint | 3.1 - Clear, reshape & apply rip rap to culvert inlet
label | d076819e-d147-5f8b-b13b-b82052361596 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b3824a2f-dab4-5bd8-902d-952bfb54ca3f |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 8a36cd12-f137-56b6-a9b0-e4e3fa5d240d |  | note | Frequency - During Construction
label | d30b5756-8050-520d-9ece-540a3ec6bc41 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | ee12a33c-e0f1-56ab-b763-05470255b842 |  | note | Conformance Criteria - As agreed on site with CPS Engineer
label | 6fa166ed-35e7-5786-a4d9-990d0923908f |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Form foundation for culvert extension
label | 55109c44-b41a-5a69-8287-2c866e852561 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 897afe54-2359-5396-bb69-4b8c8e76486c |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 16103866-10a5-5e72-938f-e457e7f94b1a |  | note | Frequency - During Construction
label | 8c55a817-780c-529e-a249-ed4e91344501 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 7e6894a3-a38c-526e-8633-7ed13a8f3f1e |  | note | Conformance Criteria - Granular fill to be placed in layers of maximum 150mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade
label | a6ff5ec6-f6a0-5a96-b4ce-cc5216af97dd |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Expose the end of the existing concrete culvert
label | 248cb304-17bd-5670-9872-d793128b59c2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 490a5c4c-900d-52c8-8cf9-ba7dd4bca2d3 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | cd86a046-e785-5e59-805f-66728e2ce44f |  | note | Frequency - During Construction
label | 0e3ddb8a-7d17-5470-8acc-97b72b538c36 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b57f29b6-e007-5268-b3c0-f4b0a89ae262 |  | note | Conformance Criteria - Once exposed, CPS Engineer is required to carry out a Structural Integrity inspection on the culvert
label | a7c424ff-844c-54c0-8e63-549e364a19bd |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Install precast concrete culvert units & headwalls
label | 8dd15534-cfab-585c-a2b6-106512eddfbc |  | note | ACTION (Hold, Monitor, Witness) - H
label | 28b3079e-410a-577c-aa7c-1629aded0c02 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 24986c80-7e50-598b-987b-fdbc9f09f0e0 |  | note | Frequency - During Construction
label | 4f502ccc-f9ab-5d27-bac6-6554601d23e8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 8f111287-daf3-5886-aa82-6774da78c23b |  | note | Conformance Criteria - Precast materials will be placed in accordance with the manufacturers recommendations & as per design
label | a71cec3a-7632-58c2-9ce3-405672b542e2 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Rock Rip rap (50-500dia) placed at culvert outlet
label | b9a2c042-179d-546d-a640-2840d0014d93 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3664566f-14fe-57ed-8ebb-a8d0df65db48 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 72ea57fc-fb40-5867-a5aa-6501c3bba42d |  | note | Frequency - During Construction
label | 4372c090-d4cf-5666-b644-40b83304bfa6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 25815389-a9bf-526e-bb10-e78c920d5600 |  | note | Conformance Criteria - Riprap rock to be placed around culvert outlets. Bidim A49 to be placed at base
label | a1744f78-5477-58e0-aa2a-8d3eaee9aea1 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 4: PAVEMENT INSPECTIONS
checkpoint-status |  |  | checkpoint | 4.1 - Saw cut existing pavement
label | 710edcfa-fd40-592d-98fe-90ec40eb5306 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 00ff4a36-0d4c-59db-ab3e-65615492515f |  | note | Frequency - Prior to pavement construction
label | cdaeb63b-7066-5b3c-9669-ab2202e7ac13 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | ba4dd4da-cae6-5350-a07d-e0b019e440ce |  | note | Conformance Criteria - Smooth and straight saw cut
label | e5a7754f-d963-55eb-a3a6-a1c0e2cbacd8 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.2 - Subgrade construction
label | 4cc7e69b-2f46-52ad-a050-e84e2d951b16 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 57d20c28-4e32-583c-83b6-f846c7843962 |  | note | Specification/Drawings Reference - TNZ B2
label | 51c6cc3f-1e65-5948-b65e-1ecce0798e45 |  | note | Frequency - Every 20m and/or at random
label | d58338ad-5ff5-599c-a151-8e74aff58532 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | c222b690-0528-52e2-8a3b-51ba28253c36 |  | note | Conformance Criteria - 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92%
label | 229c3c51-c399-5442-9bfa-1fb74d6c8db3 |  | note | Records - Subgrade Approval Check sheet, Test (CS-4100) reports
checkpoint-status |  |  | checkpoint | 4.3 - Subgrade Cement Application rate
label | dd661f3e-2a5d-5b8b-9525-cddb305f475f |  | note | ACTION (Hold, Monitor, Witness) - W
label | bfccb06c-34ae-54ad-bfb3-55a551c3d73b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
label | 629eb42e-55b8-53b1-b9c4-8220c5e7d642 |  | note | Conformance Criteria - 2% cement stabilisation at 250mm deep subgrade
label | 0374ff82-d082-5930-9bb1-bd78dd092537 |  | note | Records - Bag test records
checkpoint-status |  |  | checkpoint | 4.4 - Pavement construction: Sub base and base course
label | cb80c122-1cf9-5e63-b603-e0b2ba9e671c |  | note | ACTION (Hold, Monitor, Witness) - M
label | 55745685-ca12-56cf-ad55-0558d6bcfb76 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | dcd43ec6-7d4a-5a90-9ce0-6af7b1f556f7 |  | note | Frequency - During Construction
label | fb172aef-b24c-536e-aa97-2b168ed22b4f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 54af69e1-77c0-5605-923e-3ea746ea0a89 |  | note | Conformance Criteria - Sub base and base course to be placed in accordance with TNZ B2. Compaction required in accordance with NZS 4407:2015. Cement supplied to NZS3122 and stabilised in accordance with TNZ B/5.
label | 6f540409-c418-5191-8a59-2b71a2166ca8 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.5 - Sub-base construction
label | 817110a1-3da4-5632-855b-edcd072f715a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6742271d-37bb-56a6-a23b-2dd19fd866f6 |  | note | Specification/Drawings Reference - TNZ B2
label | 792c1fb2-28af-5b8a-8646-9f5fb3210a4a |  | note | Frequency - Every 20m and/or at random
label | 5ac77008-8fa0-527f-bd4c-c385e891ce21 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | 5181a94f-9752-5b57-acba-acfdde25ceb4 |  | note | Conformance Criteria - 200mm thick AP65 sub-base compacted to a minimum dry density of 95%, Average 95% of MDD with nothing less than 92%
label | 8cbb7d97-87c6-579d-9ff6-523dff586dc8 |  | note | Records - Test reports
checkpoint-status |  |  | checkpoint | 4.6 - Sub-base construction
label | 52b24b3a-83d9-5540-99d7-5a43b44b0b83 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 51be4e72-aef6-5fc8-965a-c9a400a6164e |  | note | Specification/Drawings Reference - TNZ B2
label | 3a8c312e-f53e-5748-bd0d-9771f2eebf7a |  | note | Frequency - Every 20m and/or at random
label | dab84777-e98d-5bbd-a022-31e2376b24ee |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | 2a256567-5f53-531c-9de2-c8a52fe79673 |  | note | Conformance Criteria - CIV>=25
label | fb660500-8100-5640-aa05-4a733de3888a |  | note | Records - Clegg Hammer Checksheet (CS-4037c), Test reports, Photo's
checkpoint-status |  |  | checkpoint | 4.7 - Sub-base construction
label | 4671bc3d-22bd-5d06-8d41-14a1c51b0d1d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6af96b19-be96-5160-a9ae-8b21c57f93b6 |  | note | Specification/Drawings Reference - TNZ B2
label | fe22fd06-761f-5e39-9d78-adb55e46dcd3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | cd87e44e-9a52-51a0-812d-f4d83fdb6597 |  | note | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
label | b00ac2c4-2afe-5d99-bce0-8c5893d0fba9 |  | note | Records - Survey as-builts
checkpoint-status |  |  | checkpoint | 4.8 - Basecourse construction
label | 59565f1f-e742-587f-aac4-4ed220f0be55 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ecf1921e-9394-50c1-8bcd-0516b9bb7744 |  | note | Specification/Drawings Reference - TNZ B2
label | 09f7e13c-fdd1-593c-aba4-248e82160d04 |  | note | Frequency - Every 20m and/or at random
label | ce8387cc-0b25-5f08-ba97-0902000bbf77 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | bb425576-355f-5cac-9073-242eca1b7cef |  | note | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%, Average 98% of MDD with nothing less than 95%
label | 4915793c-a33d-528f-ba01-adf98b6378f3 |  | note | Records - Test reports, Photo's
checkpoint-status |  |  | checkpoint | 4.9 - Basecourse Cement application rate
label | eefc9803-168f-5b45-b6ff-f8cf0543bd31 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2cc6bf52-a046-5f24-b0e1-86d2c94a2680 |  | note | Specification/Drawings Reference - TNZ B/5
label | 1979dccd-90da-5c76-ad40-b82cb21ee0b2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 24a7dcc8-074a-5f28-8655-5e77d5dc0ecd |  | note | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
label | 948a1fbf-b2bc-5270-937b-326f839cdde8 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.10 - Basecourse construction
label | b2809508-80ad-5f07-803f-5c5009989323 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 65b3eeef-96ba-51b3-ae1d-b7cfcd00353a |  | note | Specification/Drawings Reference - TNZ B2
label | 431ebb1e-3f9c-533a-b80a-b87c1a9455b6 |  | note | Frequency - Every 20m
label | 1b4a8ecf-d0aa-5f22-b896-1f59b8f1d9b6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 67d56403-499e-5046-941d-2935d4b911b7 |  | note | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
label | a5848cb4-00fe-59d9-b4a5-58bb16510bcb |  | note | Records - Survey as-builts
checkpoint-status |  |  | checkpoint | 4.11 - Basecourse construction
label | d694245c-8b3a-50fd-9f7c-90b7344bb526 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b8e04bdd-330b-5cff-8933-206d29e964b1 |  | note | Specification/Drawings Reference - TNZ B2
label | e78397cc-e89c-5d25-ab92-f49ed69c045a |  | note | Frequency - Every 20m and/or at random
label | d448cb1c-a25d-5a9b-bb2b-1f2534f5786a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | 8590ea8e-dfa4-54b2-8b86-f03f18beb37a |  | note | Conformance Criteria - CIV>=25
label | f6e63303-1408-58b6-8c71-e3a010d125e4 |  | note | Records - Clegg Hammer Checksheet (CS-4037c), Test reports, Photo's
checkpoint-status |  |  | checkpoint | 4.12 - Basecourse construction
label | c7a01409-f9c0-50b9-be07-5d40f127846f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 246d0095-ca47-5939-9378-bbd594aee71c |  | note | Specification/Drawings Reference - TNZ B2
label | 85edb96b-d490-5a7f-b948-3103778f4377 |  | note | Frequency - Before sealing
label | c5b76d4a-5044-5f2f-a71b-6916972fa106 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | aa7e6455-c163-57ec-8a21-86b5001cb67d |  | note | Conformance Criteria - Mosaic surface
label | cf8eae15-4e4a-536d-ad6c-8bff749f270d |  | note | Records - Photo's, Pre-seal checksheet (CS-4060)
checkpoint-status |  |  | checkpoint | 4.13 - Applying Bitumen
label | 1b208aa0-3550-58cd-a74b-9f82bb50a2f0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d88ad228-04bf-5377-9322-c4c716c88ec0 |  | note | Specification/Drawings Reference - NZTA M/6
label | dd3f81f5-b3d7-56b2-aaff-2af00861916c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | ff31b8e1-27ac-5ddb-a5e0-218003e2c4d9 |  | note | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
label | 28154d3b-b2ff-555c-88d6-4a05f80248dc |  | note | Records - Photo's, Pre-seal checksheet (CS-4060)
checkpoint-status |  |  | checkpoint | 4.14 - Degree of saturation
label | e7a00282-380c-52d9-b50c-7f371f511469 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5cf1640b-1cea-5c2d-afba-d6dc9ac59dc6 |  | note | Frequency - Before sealing
label | 7b1906a8-d1ea-59b4-b0ca-6550aa70b6de |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | bbeb4d1a-304d-5c9d-b66c-193eff011470 |  | note | Conformance Criteria - Degree of saturation should not exceed 80%
label | b7f0bfe3-311b-57e5-aa5d-61db4ab3c915 |  | note | Records - Pre-seal checksheet (CS-4060)
checkpoint-status |  |  | checkpoint | 4.15 - Chip seal laying
label | b67a40c5-eed7-50eb-b190-543e0df9f894 |  | note | ACTION (Hold, Monitor, Witness) - M
label | ac79861d-73be-56ca-8ea8-d2b8fc85bb86 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZTA M/6
label | c9d705cc-90c0-5b14-92c2-afd808f4fb88 |  | note | Frequency - During Construction
label | 96d4120c-94a7-55f6-b12a-bdecddc9cc96 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 30260e0b-7633-5153-8ff0-202640bbb00e |  | note | Conformance Criteria - Chip seal will match existing seal. The seal will be placed and compacted in accordance with NZTA P/17. The seal will be rolled in accordance with NZTA P/3
label | 772f1aa1-d52b-583f-89ab-3557e71798a6 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.16 - Verge
label | 032f2c41-230e-5533-83d9-fbe4563ebd12 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 15ef146a-6d2e-5481-b9f6-163295a9eaf3 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | d45e62e2-874f-5489-85a5-eabc13a62400 |  | note | Frequency - During Construction
label | 62ab50de-2177-5691-bd40-f1f919e2bb44 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | bc40de31-e6dc-54bc-ad09-c839a6dd9593 |  | note | Conformance Criteria - Verge reinstatement to match existing
label | 6a56a8a7-a3f3-51e0-8526-1f3b4869c1c2 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.17 - Sweep & Line mark new chip seal road
label | cc54946e-c3e2-540e-b988-60e6da65b593 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0d9b2772-1076-53de-9747-eddce6d37773 |  | note | Specification/Drawings Reference - TNZ P/12:2000
label | ea8d196c-f304-5ab8-aa7b-2ff59eab259e |  | note | Frequency - During Construction
label | fa11f26d-acbd-5368-a8f9-daa98c750616 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 059c4f85-aa1d-5ee2-96f9-d1982e581a5d |  | note | Conformance Criteria - As per TNZ P/12:2000
label | 0d95f362-ecdd-5221-9f40-0ce430396284 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.18 - Install Traffic services
label | b8ed0110-4dd5-5a5d-a815-40bfa102045e |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6c5fe011-6c15-5e40-852a-e9095b61ed90 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 59f1eb50-79c1-5bf0-b580-1b24068b3835 |  | note | Frequency - During Construction
label | 3212adb4-eb93-51dc-b749-21f98e3922b0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 406d6ee5-69f2-583d-aa65-35a26916f1ae |  | note | Conformance Criteria - Traffic services including signs and edge marker posts to be supplied and placed in accordance with TNZ C/20
label | 1984da92-b7cb-5e21-81bf-895e69a54f12 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.19 - As-built Survey
label | dac24ce2-cad6-56b1-9afc-62341879af1e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2dd4c9ed-1dda-54a2-a74f-4951f9366c46 |  | note | Frequency - At completion of Lot
label | 28fccd8f-48eb-5cf7-b934-6f020c98d0c6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | 2739aa90-9602-56a4-8975-389b397aa1e8 |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | 635f52ae-34bc-522e-86f2-37964043babf |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 5: Final Inspection and Handover
checkpoint-status |  |  | checkpoint | 5.1 - Quality Assurance deliverables
label | 3a188a2e-7b4e-5ae2-a2a6-e7988254e9d2 |  | note | ACTION (Hold, Monitor, Witness) - W
label | fcfb7b96-8418-5abb-a4ba-ea2846757d0d |  | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | e4acff03-2b8d-58cf-8d27-2cd1d84fa02e |  | note | Frequency - At completion of Lot
label | bd6c3791-b80a-5328-a88f-b8f7f13a20e4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | b5ff29d7-cca9-553a-8275-b58a66a25fba |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 380f38a8-c5f3-5acc-bfce-711b99f09e9a |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 5.2 - Completion Sign Off From Fields Below
label | 14de49a7-97cf-593c-b022-6bc3a00e4c5e |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | ITP - F3002D - Mangahuini Long Drop Site - ITP for works | itp |  |  |  | Yes | ITP - F3002D - Mangahuini Long Drop Site - ITP for works REV 1 | c5f2bb34-e766-4f47-a09e-75e6088ceda2
checkpoint-group |  |  | section | Section 1: RECEIVING INSPECTIONS
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 69ba1670-d957-5bf0-aab6-a05b34916406 |  | textbox | CPS Eng.
text | 8c1f7a61-58b7-54cc-985b-9d091d0caa12 |  | textbox | Site Engineer
text | 77331545-1f61-5d64-86b1-70c1c05c6353 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Buttress Rock Armour (D50=800mm)
label | 77a1b739-aa7d-52af-873f-8fea8d11d5f0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c00b327c-0b7d-55f3-8a4e-94cd541a9503 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 38104185-906c-5367-bb72-f1624cd0c436 |  | note | Frequency - Prior to commencement
label | 0345be39-11ca-56cb-a012-bd64752adead |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 37043cb7-64ff-53c9-a037-eff6e5916412 |  | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 to 800mm with a minimum specific Gravity SG of 2350kg/m3.
label | 63e617f4-6f33-584a-8c0f-23e714aa66dd |  | note | Records - Material source test results, Delivery dockets, Photo's
checkpoint-status |  |  | checkpoint | 1.2 - Culvert Rip rap rock (D50 = 500mm)
label | cbb5e7b4-aee7-54a5-9db8-f2133086a8d3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a5d0924d-c932-5dec-9668-c2ab2dc2c891 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 147b2162-95d4-59bd-aa36-caa7c047e1b3 |  | note | Frequency - Prior to commencement
label | 4d1cde87-9a24-5ee6-891a-fe000445b504 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | e86ac567-be0a-57ff-8535-eadfe4166e36 |  | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 to 500mm with a minimum specific Gravity SG of 2350kg/m
label | cbd6ea1e-10bd-5ddc-b1a7-a1b0ebcd524a |  | note | Records - Material source test results, Delivery dockets, Photo's
checkpoint-status |  |  | checkpoint | 1.3 - Drainage material
label | aca1b633-ca8c-5e14-a0a3-91b599b2cf37 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0b226452-4dd7-52ae-9c5a-3cc6e5bee58e |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, TNZ F/2
label | 12864a85-e69f-5cb8-bc9a-0fa19845ccd2 |  | note | Frequency - Prior to commencement
label | a3b42221-b1c2-50d1-a6bc-06f01c20a0c7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 06f86aa8-369a-5c49-9c4f-ec4c106d0de2 |  | note | Conformance Criteria - Comply with TNZ F/2 or approved equivalent.
label | 86a71b0d-58b8-585c-9914-f3579c766ce0 |  | note | Records - Material source test results, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.4 - AP65 Granular fill
label | 81656688-a056-5b33-bcea-1f01a771a750 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4bdae82d-30d9-58a3-8361-04931f16a23a |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 979eea29-ffbc-573b-a8a5-780d1813811e |  | note | Frequency - Prior to commencement
label | 2b3e77d0-9b52-5237-ab18-263603d9d2b0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Particle size distribution test
label | 75bdec89-211c-508b-b6c9-d5d14e57ecda |  | note | Conformance Criteria - Test results from a representative general fill sample tested in an independent accredited laboratory
label | d55bd3b5-a234-5c65-a02b-8762d25d8b55 |  | note | Records - Material compliance cert, delivery dockets
checkpoint-status |  |  | checkpoint | 1.5 - Geogrid: Miragrid 80/20 Biaxial Grid or Similar Approved
label | 91bb69ac-64d5-52b1-a6da-7340bf460ccd |  | note | ACTION (Hold, Monitor, Witness) - W
label | 307e4e13-bea8-5f07-bb23-742da2ab9dbc |  | note | Specification/Drawings Reference - Mangahauini Long Drop Site NTC F3002D SH35RS225RP7.8 final
label | 6b4056aa-a48e-5642-926e-c73d49bce54b |  | note | Frequency - Prior to installation
label | e3345105-59eb-5e15-9c12-0f21546c8b10 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 3fdd3c05-1843-5866-93b3-8889d1237307 |  | note | Conformance Criteria - Delivery dockets with roll details. Check information on the delivery docket against the requirements indicated on the Drawings.
label | b3a20d44-55b7-588e-9dc4-d43f2539ab8f |  | note | Records - Material compliance cert, delivery dockets
checkpoint-status |  |  | checkpoint | 1.6 - Class D A49 Geotextile
label | 3e88f360-590e-566c-b998-430c6c1e2296 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0721bf09-a894-5c53-9878-3215d6accd88 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZTA F/7
label | f8ed2091-ed7b-5511-9b3d-190772d28f39 |  | note | Frequency - Prior to commencement
label | 93f77f79-9d09-5bac-a2f4-f5c3f34d2a8f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 007fd651-2825-5d3d-9224-6ad73a0eed39 |  | note | Conformance Criteria - Non-woven & NZTA F/7 compliant On dry bed below fill
label | 61602227-dab1-57e2-829d-06fcbb4f9853 |  | note | Records - Material compliance cert, photo's, delivery dockets
checkpoint-status |  |  | checkpoint | 1.7 - Perforated lateral drains
label | b61e6e97-3878-5994-bc6f-8219890ecdf7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ac6bd562-86fe-56fc-958b-a5ab06b05628 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 22373b6a-52c9-5722-bce0-343bbedcab13 |  | note | Frequency - Prior to commencement
label | 5a2cfc61-174d-5810-9f4a-6458a6a3a0d7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 3bbaa945-929b-5765-8731-993eac9c9a77 |  | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter perforated lateral subsoil drain, or similar approved.
label | 4ff021b4-a716-5d7d-9a3e-2854f222e565 |  | note | Records - Material compliance cert, photo's, delivery dockets
checkpoint-status |  |  | checkpoint | 1.11 - AP40 (Basecourse)
label | cf0b8a31-c159-5e3e-8093-337c41592bfb |  | note | ACTION (Hold, Monitor, Witness) - W
label | 215115cd-2af9-58e6-93ba-8eb51d9731db |  | note | Specification/Drawings Reference - TNZ M/4
label | 9b7574c2-5927-527d-9f54-cefa95d853e5 |  | note | Frequency - Prior to commencement
label | 1e984488-a525-54ec-98c6-521b044cad1f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 1f0438b5-ec5d-5177-9bd6-dabbc262042e |  | note | Conformance Criteria - Source property testing
label | c057982e-e6f8-5883-8091-e712b47b3d41 |  | note | Records - Lab test reports, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.12 - AP65 (Sub-base)
label | 19bad9ec-6394-5b2f-8bc3-ff8f93dfa23a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7b0fa3cd-7cbe-5425-bcc1-af691c1c4b2b |  | note | Frequency - Prior to commencement
label | 58d3418d-3265-5a7e-9f8c-54978e7d2c51 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | a4fc5c80-af03-57e3-82d5-b91bc42a8f95 |  | note | Conformance Criteria - Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak)
label | 52456a5a-6278-583c-a8ff-90b515c1d9cc |  | note | Records - Lab test report, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.13 - Grade 2/4 Chip
label | 713ae944-f691-501f-b2b3-aa37889a90c6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 81f2c5cd-6d1c-5947-b7e6-33f5d32b2bb1 |  | note | Specification/Drawings Reference - NZTA M/6
label | baacf0dc-3a17-52a4-93e0-fa642ba86f26 |  | note | Frequency - Prior to commencement
label | edd2a852-1b29-5250-a868-661a5a84154a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 13b6c27e-af8c-5629-833a-a6c23777fbcb |  | note | Conformance Criteria - Source property testing
label | fe4e9545-21fa-564e-822b-621ecda0f051 |  | note | Records - Lab test reports, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.14 - Cement Material cert
label | 187b79f7-a78e-584e-8ecd-e31951799b00 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 01f01242-bdc2-55a7-bd4c-180ee1d34136 |  | note | Frequency - Prior to commencement
label | abb65add-a615-5900-8b02-475699c7c0ed |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 870d7da7-872c-5f0b-9316-62752b762745 |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.15 - Bitumen
label | e774e17d-5d65-5475-a031-b8c571c34639 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a7687c65-8b09-5572-b7ca-cb2ec4e61d22 |  | note | Specification/Drawings Reference - TNZ M/1
label | 30934812-4a16-57b8-830a-25658fb405d1 |  | note | Frequency - Prior to commencement
label | 5e896a46-fe5e-5bca-8da9-3625898c8ab1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 851b358b-f1b1-559d-8f03-fbe7dee87474 |  | note | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
label | 07254412-94a2-58dd-b1be-6bb4b52f1f5f |  | note | Records - E2 Certificate
checkpoint-group |  |  | section | Section 2: REVETMENT & BACKFILL INSPECTIONS
checkpoint-status |  |  | checkpoint | 2.1 - Survey Setout
label | 77243461-0405-5401-b865-7c94cc5422ce |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5462632e-00fb-5c00-8aa1-6133221795d6 |  | note | Specification/Drawings Reference - Consistency with Construction Drawing
label | 77c11763-b412-598f-9074-76f7bd4ea803 |  | note | Frequency - Prior to commencement
label | 68448adb-6031-5c27-a369-ca09ea462244 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | b9931fc1-f327-53c8-a357-5edd7aaa0492 |  | note | Conformance Criteria - Set out extents of fill and check against design drawings
label | 9519d962-d180-50a2-9da2-13654bcda9e8 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Unsuitable loose material and vegetation
label | e17bbec4-b120-5755-91e8-041e3a842e4f |  | note | ACTION (Hold, Monitor, Witness) - W
label | d73b5d0e-f59c-5a56-8595-2da4f162e89d |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 1f764354-1045-50f3-a5ef-5af7767258a3 |  | note | Frequency - During Construction
label | a40660a0-0c17-5d04-8777-439a001d6cb7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b37b6f9b-46d2-525d-beff-2446d3fac350 |  | note | Conformance Criteria - Remove and clear any vegetation, trees and unsuitable material
label | 662e07a7-deb1-5865-8663-a864df0f2880 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.3 - Subgrade Inspection
label | 1b73dbf1-4e95-5edd-bfe7-20812ba5f68a |  | note | ACTION (Hold, Monitor, Witness) - H
label | ed5216f2-91e3-5fb6-8004-c6ceeef73475 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 4095da97-1525-5c47-a84f-6b90b7ca096f |  | note | Frequency - Per area as required
label | b16f65aa-22fa-5e62-b78d-09afdbae9592 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 5522a425-5a6d-5692-ba9e-b8330d9a85a1 |  | note | Conformance Criteria - Inspect fill foundation. Fill foundation must be approved, in writing, before filling commences.
label | 65db3e2d-382a-5a49-8da8-5805d36eb4b0 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Class D (A49) Geotextile placement
label | 366c7b76-67c4-594d-8c94-24ac9cc27afe |  | note | ACTION (Hold, Monitor, Witness) - M
label | a6c3967f-ca4e-54a7-bc58-453a1d18e291 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 58de8393-4019-5c37-b418-6833605779b8 |  | note | Frequency - During Construction
label | 51cbc4a5-2cfd-5a1e-ac57-4c1074b475c2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | f4ce3702-28a7-5023-ade6-34b0d123ec40 |  | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A49 or similar approved before placing granular fill. Bidim layer required between granular fill and rock armour.
label | 9ef26a1f-daea-5171-8e03-17e9afa40833 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.5 - Sub soil drainage
label | bf12397b-2030-5353-84da-4965698066e3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | de08250f-01c0-5e3f-85ca-787fc2e1909e |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, TNZ F/2
label | 0ebcebef-8d19-54d3-8c4f-355aa1b026a5 |  | note | Frequency - At lower bench level and mid bench prior to placing granular fill.
label | 90ee9db3-26e2-562d-aa44-588375753c5d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 9f927b06-fa36-5846-86d8-1dee158aa795 |  | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter perforated lateral subsoil drain, or similar approved. To be inspected and approved by CPS Engineer prior to install.
label | 531837d0-3b74-55d3-948a-fbee43382917 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Imported Granular Fill Placement
label | 732b3b5f-e0d1-53f4-8e48-a9bf00296c6f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6436c7d9-837b-5d54-aa8b-b0a1caf8e548 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZS4431:2022
label | 6b02f525-f74f-5e9e-a978-81f2b996c94a |  | note | Frequency - During Construction
label | b544d24e-3511-5dbb-a33a-2023ae38bb56 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 1624f3d2-4ed1-53ec-b06d-20f90f4dbc5b |  | note | Conformance Criteria - Granular fill to be placed in layers of maximum 150mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on a dry subgrade
label | c6502f86-fd87-5379-9582-98d134354f6e |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Imported Granular Fill Compaction
label | 6d14a2ea-9b2c-5f9f-92ae-ca122ab0b323 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 03661876-f6ed-5c8f-beab-78cac80c4719 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZS 4402:1986, Test 4.1.3
label | 7dfa6c83-1fc1-55ab-a11d-065dce8e550a |  | note | Frequency - During Construction
label | cf0a0ed0-f9d7-5e82-b47c-58b66054572b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM & Clegg hammer testing
label | ab9b46bf-bd68-579e-b02d-c36213cb9256 |  | note | Conformance Criteria - A target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3. Testing done as per Site Instruction by CPS Engineer.
label | 10597727-27f6-54d0-b91e-5601fed515f1 |  | note | Records - Test results, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Geogrid Placement
label | 71a9322d-065d-5203-aba6-2673b1a221eb |  | note | ACTION (Hold, Monitor, Witness) - H
label | d958f2e6-ab7c-511e-a2cb-7bf786661d28 |  | note | Specification/Drawings Reference - Mangahauini Long Drop Site NTC F3002D SH35RS225RP7.8 final
label | d6ddd0c0-6107-5153-bb2c-5be25ccdf127 |  | note | Frequency - During Construction
label | 884e212d-fd3f-56cc-a38d-b063e4f71172 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | eb956fbd-9b5a-5f67-a96d-7caaa20d5d0e |  | note | Conformance Criteria - Geogrid to be placed in engineered fill 300mm thick between geogrid layers. Geogrid to be wrapped with a minimum overlap of 2.0m. Panel overlap on geogrid layers to be minimum 0.5m or manufacturers minimum.
label | 1f9a3541-9511-503d-ae6b-b36dd5e8af33 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Form and cut fill batter as per design 1.5H:1V
label | 61252a02-4800-5d33-b00c-c7d4ba723fc3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a5770630-99c6-54e8-bbcd-d61657489c80 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 8d5591c7-1ea7-553f-b832-cf39d8a8c8f8 |  | note | Frequency - During Construction
label | a8ba870b-c554-5783-90b3-f56cfe32d638 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | da3fdaa7-8770-5515-b4ff-2d250a603179 |  | note | Conformance Criteria - Benches to be cut and profiled to suit slope profile
label | a3706d50-7949-573f-bf52-ea0957c273df |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Rock Armour (50-800dia) to form revetment
label | 5bf79f7e-dcda-59bb-94c3-1f19f1979fdb |  | note | ACTION (Hold, Monitor, Witness) - M
label | 880d5199-68b6-5f7a-8dfe-c0a9b205523e |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 1c85ac03-a6c6-5ddc-8e97-eb900bfae1b2 |  | note | Frequency - During Construction
label | 4972af42-8c66-5246-802c-179c1883cea6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 544f5f91-b24e-5240-974e-8ab8608bd848 |  | note | Conformance Criteria - The buttress is to be keyed in to ground directly behind existing displaced reno mattresses and existing railway line timber panel retaining wall
label | 22e0777b-ef4b-5a57-9bf3-1398f12f387a |  | note | Records - Photo's
checkpoint-group |  |  | section | Section 3: FISH PASSAGE INSPECTIONS
checkpoint-status |  |  | checkpoint | 3.1 - Survey Setout
label | 5d084ca1-c657-5a90-8342-72273b53dbcf |  | note | ACTION (Hold, Monitor, Witness) - H
label | 07c391a5-109c-5fd1-b33c-83730d13a857 |  | note | Specification/Drawings Reference - NTC F3002 D
label | 63710ad7-547b-52a7-a4b0-c173d8131809 |  | note | Frequency - During Construction
label | 3cf3b01e-2436-5c8a-92f8-44c1642fbedc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 94b71ae2-1a24-5f45-a62e-247a56006e82 |  | note | Conformance Criteria - Set out extents of fill and check against design drawings
label | 6b19af11-661c-5833-9e98-eb843a5b46ee |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Void Fillings
label | 61c9f388-b059-548e-919b-0a0c4a20cb76 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ab3eea29-6be5-5d41-83ed-6f10f6fe8492 |  | note | Specification/Drawings Reference - NTC F3002 D
label | f0b77a74-192c-51d4-afd3-7e78d8bece84 |  | note | Frequency - During Construction
label | 5f84243d-6781-5f16-9640-214a829a36d6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 9ce95f60-291d-5ce4-a467-966a4d488148 |  | note | Conformance Criteria - Measurements of Materials
label | 088e556e-739e-53a7-8c7b-1909cf4fca16 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Gradient of the fish passage
label | 27faf134-ee3f-5d9d-bc90-484c7144689f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6955f498-b90e-5f8b-8bd1-e4579049095a |  | note | Specification/Drawings Reference - NTC F3002 D
label | c661b9ea-bd52-558a-beef-da89998ebbea |  | note | Frequency - During Construction
label | 6574d70d-96f8-542e-b0bd-1405da94d0ec |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | f5abfa32-1bed-596b-9c47-bd0c1334cbf5 |  | note | Conformance Criteria - Set out extents of fill and check against design drawings
label | f2419f99-43ea-5ae5-ae31-fb607d04e078 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Clear, reshape & apply rip rap to culvert inlet
label | ca073347-b1aa-5580-9e8b-27e587454f24 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 566ab8fc-34d7-52ee-b3a6-1e2114ccc74d |  | note | Frequency - During Construction
label | d1044034-9e45-529f-ae75-f06a619993b5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 984648b4-15be-59d2-ae5b-c6a66651b2a8 |  | note | Conformance Criteria - As agreed on site with CPS Engineer
label | 27d636a1-7246-5f91-a136-156c813d798a |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 4: PAVEMENT INSPECTIONS
checkpoint-status |  |  | checkpoint | 4.1 - Saw cut existing pavement
label | e3ae9fe2-d9d7-5b3c-8e87-6c33a5594485 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 69f866f3-5564-5809-9830-64869c8d22b2 |  | note | Frequency - Prior to pavement construction
label | d8b4bbf7-6894-5014-80d5-fceb9816f462 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 8fddf259-83e2-5239-ab1a-507660d5f143 |  | note | Conformance Criteria - Smooth and straight saw cut
label | ec85849f-19ec-5b41-9167-3db26ced296d |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.2 - Subgrade construction
label | 8a78d471-4505-5de9-9d75-5b3d9dca3871 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c659d7fd-1148-514b-b560-41aea63bdf53 |  | note | Specification/Drawings Reference - TNZ B2
label | 6ee9f9da-bbe9-5134-a21d-8c4b98c7b2b7 |  | note | Frequency - Every 20m and/or at random
label | 6f721878-33aa-5093-b58b-0165bf708462 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | 17496a70-f1d1-522f-aff8-00ff70ff25e8 |  | note | Conformance Criteria - 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92%
label | 09fefa71-1164-5a2a-91dc-66ae39e81cb3 |  | note | Records - Subgrade Approval Check sheet, Test (CS-4100) reports
checkpoint-status |  |  | checkpoint | 4.3 - Subgrade Cement Application rate
label | 73b3f88d-d1cf-5570-9923-ce47bc149d0d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 36e174b4-6f93-55ea-8068-0ec45de986d1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
label | f2bc55d7-74a4-5d11-a37e-888744e0e95c |  | note | Conformance Criteria - 2% cement stabilisation at 250mm deep subgrade
label | d1da49ae-186a-56ff-b180-999619d3b293 |  | note | Records - Bag test records
checkpoint-status |  |  | checkpoint | 4.4 - Pavement construction: Sub base and base course
label | 7fcf9c73-9ac2-5ec7-87d6-aad027db7a4d |  | note | ACTION (Hold, Monitor, Witness) - M
label | caf1d79d-9fb4-545a-985d-16b9a8339133 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 14ba1bc4-e16f-5671-8317-ff422c97caca |  | note | Frequency - During Construction
label | 710c2693-2418-5438-9ef1-1674e46df538 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 03ec83f2-73ed-530b-b079-5c4e2aff29fb |  | note | Conformance Criteria - Sub base and base course to be placed in accordance with TNZ B2. Compaction required in accordance with NZS 4407:2015. Cement supplied to NZS3122 and stabilised in accordance with TNZ B/5.
label | 57d2a0d9-7303-51ae-b926-0b79349b88ab |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.5 - Sub-base construction
label | a922f33f-5424-5091-90b3-e476b86d8983 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 28e9b5e2-65cc-5967-bb9d-887adcd93b10 |  | note | Specification/Drawings Reference - TNZ B2
label | fc27ada3-350c-5358-9314-0eac7b0aa95e |  | note | Frequency - Every 20m and/or at random
label | f4475cc5-3870-5581-8aad-a2fd217f52ce |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | 873f65af-5b16-5ac4-a75c-065812de0155 |  | note | Conformance Criteria - 200mm thick AP65 sub-base compacted to a minimum dry density of 95%. Average 95% of MDD with nothing less than 92%.
label | d5255fc9-41ae-5d3c-9d81-7b56b8c80e51 |  | note | Records - Test reports
checkpoint-status |  |  | checkpoint | 4.6 - Sub-base construction
label | 94210b9c-2b05-56f0-ac19-991fa81ebab3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ace5074a-1705-5ca4-95fe-de98e9761845 |  | note | Specification/Drawings Reference - TNZ B2
label | d5e69c2c-6ab1-5397-a858-277275b218f0 |  | note | Frequency - Every 20m and/or at random
label | d983ea52-b33e-5e67-9702-513fc54e3597 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | cbd37141-8c2e-5dad-acc4-828f44a3960d |  | note | Conformance Criteria - CIV>=25
label | 53fbd93f-8de9-56e5-9450-5cfbed7c11f8 |  | note | Records - Clegg Hammer Checksheet (CS-4037c), Test reports, Photo's
checkpoint-status |  |  | checkpoint | 4.7 - Sub-base construction
label | 73ca106a-8345-5539-8b01-bd9d554a4201 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5e5377f3-d0e6-5421-8250-cb15db8b47db |  | note | Specification/Drawings Reference - TNZ B2
label | 598d6281-ca43-5eb2-b503-6dbc13c14b56 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 69d41c07-e05c-50d3-9c0f-8fdd6754a999 |  | note | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
label | 8d3c3826-1225-59cd-9faa-f5c882927bda |  | note | Records - Survey as-builts
checkpoint-status |  |  | checkpoint | 4.8 - Basecourse construction
label | 1babbece-6e2d-5b6b-9995-d18a660f29f0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3c05a4a1-e58f-5e12-a674-a70beace4fcc |  | note | Specification/Drawings Reference - TNZ B2
label | d7be59e4-8cb4-52cd-b8ef-7689cd1300a2 |  | note | Frequency - Every 20m and/or at random
label | 54ba58bf-5af0-5007-9f4c-906154cf3e08 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | c13516f4-c684-526f-b0ad-b90992a4fdab |  | note | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%. Average 98% of MDD with nothing less than 95%.
label | cc84b23a-7814-5d99-b7eb-4a5f9a6c248f |  | note | Records - Test reports, Photo's
checkpoint-status |  |  | checkpoint | 4.9 - Basecourse Cement application rate
label | 8cc691fe-6701-5bec-b1e3-33f0414ce5de |  | note | ACTION (Hold, Monitor, Witness) - W
label | 456bb4b5-2e36-5cc6-b679-31a375a52c1d |  | note | Specification/Drawings Reference - TNZ B/5
label | c3423cb9-8d48-574b-97fa-48687d0a35ce |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 03940fb6-1936-5c84-8a58-843fab5ba2f4 |  | note | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
label | a3fa84e9-6cf0-5694-8a76-9a824686655a |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.10 - Basecourse construction
label | 6ff3dd56-ac1d-5f23-8088-092372b9d5a3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5abe17a8-ee53-52f0-9939-18a6dd34002f |  | note | Specification/Drawings Reference - TNZ B2
label | 5a0ea1e0-47aa-5039-ac88-c0e0ab356f48 |  | note | Frequency - Every 20m
label | 35d67124-04ef-52f3-8866-ad8900187bac |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 6405343b-bdf9-5a65-8cf9-f8c0dcff6e74 |  | note | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
label | 71473fc3-30c9-5590-bef3-f9fd80eba79c |  | note | Records - Survey as-builts
checkpoint-status |  |  | checkpoint | 4.11 - Basecourse construction
label | 2913bcb9-a245-5945-913e-089c5debc8a3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ac7cda92-e8e5-5898-95c4-b49a90b66755 |  | note | Specification/Drawings Reference - TNZ B2
label | f5d7089a-9846-57b7-8679-474b7f240099 |  | note | Frequency - Every 20m and/or at random
label | aa313e2c-d2fb-514e-ac0a-4999f46b8e43 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | 65f3b842-4d8a-53a5-8aed-888e602fcd7e |  | note | Conformance Criteria - CIV>=25
label | a2d2d79c-f5b7-5013-8af8-814b4a1f3e37 |  | note | Records - Clegg Hammer Checksheet (CS-4037c), Test reports, Photo's
checkpoint-status |  |  | checkpoint | 4.12 - Basecourse construction
label | f843ddba-0355-5072-ab3e-8271b35a7ae3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1815ae73-b8ca-540a-8ef3-0dcdb1ebac4d |  | note | Specification/Drawings Reference - TNZ B2
label | f606d52c-63f3-5484-bebd-74872d11e5d1 |  | note | Frequency - Before sealing
label | c1818244-e088-50e9-bff5-614479e20b79 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | 8197e20c-1192-5c84-9f3b-2bfe92a97281 |  | note | Conformance Criteria - Mosaic surface
label | 72d1e3dd-8881-5065-9d48-ac6bd252741e |  | note | Records - Photo's, Pre-seal checksheet (CS-4060)
checkpoint-status |  |  | checkpoint | 4.13 - Applying Bitumen
label | 32f8ab63-a791-54a0-8b3a-b7674cd2fef9 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b8cd8ca5-8aac-5112-a313-4e13922acab8 |  | note | Specification/Drawings Reference - NZTA M/6
label | 5244362d-05eb-5e37-ac16-e7af59156ddc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | f871c2c9-444a-5a18-96b2-7521996de80b |  | note | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
label | 191aca1e-0629-5ce1-b488-0b5a8c188f1b |  | note | Records - Photo's, Pre-seal checksheet (CS-4060)
checkpoint-status |  |  | checkpoint | 4.14 - Degree of saturation
label | 9f484139-7754-5d2f-9f64-8f6a9d75501f |  | note | ACTION (Hold, Monitor, Witness) - W
label | e9b475d5-531d-5cba-a1f1-75c64497e7e3 |  | note | Frequency - Before sealing
label | 8c2c0399-b533-5a54-aaeb-c8bed1be3abb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | 899338fd-bd25-5daf-90f8-53d293bab74e |  | note | Conformance Criteria - Degree of saturation should not exceed 80%
label | 08537d5f-4a0c-573a-a3c1-d39f09e519c3 |  | note | Records - Pre-seal checksheet (CS-4060)
checkpoint-status |  |  | checkpoint | 4.15 - Chip seal laying
label | d8fb7d51-db7f-59ac-8eb4-72d89aea975a |  | note | ACTION (Hold, Monitor, Witness) - M
label | 4eda1095-4a39-5e97-9396-dc14660e75b1 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM, NZTA M/6
label | 756d26d9-b79b-565a-b282-396208cc5b49 |  | note | Frequency - During Construction
label | 0051120d-4222-590a-b9a5-c9b671e0f618 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | a0d2c8c2-86a0-5a7e-af94-7ba01bf0fe45 |  | note | Conformance Criteria - Chip seal will match existing seal. The seal will be placed and compacted in accordance with NZTA P/17. The seal will be rolled in accordance with NZTA P/3
label | a228eca9-bb26-5144-92a7-241f48e01d72 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.16 - Verge
label | f17a5978-f022-5980-aefd-a21fe408f485 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 831a439a-f6d3-5880-bd53-2ca39bbc3142 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 178ce6d7-0b4d-5033-b2ce-deddf9904c1a |  | note | Frequency - During Construction
label | 1c1d93c0-b2a9-5d94-8eae-f88e4e909016 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 171f9219-b694-5de1-9eba-b4baff33d4a1 |  | note | Conformance Criteria - Verge reinstatement to match existing
label | bab5eba6-b22b-57d3-896c-c21f10141478 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.17 - Sweep & Line mark new chip seal road
label | d7ec98cf-1d78-533f-9658-fb694cdfd56a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 70362e1f-b03d-5c3b-9ac0-2fec1751085b |  | note | Specification/Drawings Reference - TNZ P/12:2000
label | d6ac6e36-b352-5525-9104-a4a62a49cfe1 |  | note | Frequency - During Construction
label | 1dd2d797-4310-59a2-b5fc-8af5b460ae47 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 615e77f3-90fe-5221-a653-04ba4a2ee7e3 |  | note | Conformance Criteria - As per TNZ P/12:2000
label | b9ea0ed8-6d8a-561a-8079-8da3ee899d55 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.18 - Install Traffic services
label | a5515068-2261-5479-b4f0-3cb3b7182bf9 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c6fcb241-e371-5f18-9dad-2376c68dc9c5 |  | note | Specification/Drawings Reference - F3002D 2-U3436.BM
label | 7bbd97b3-4f5a-583c-b99f-d3b24e4c8102 |  | note | Frequency - During Construction
label | d5a6f097-efa5-5774-965b-52f1f379737f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c05f1cad-f858-5fac-89de-bbd2771f85c7 |  | note | Conformance Criteria - Traffic services including signs and edge marker posts to be supplied and placed in accordance with TNZ C/20
label | bc41fc26-2540-5ded-8b67-612583f44bee |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 4.19 - As-built Survey
label | fa744596-59ef-5f9c-8e91-e92a908c91f9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 26261f5f-7784-5943-9e0c-502c678934bf |  | note | Frequency - At completion of Lot
label | bf1072e0-d007-52af-b1e7-313347889819 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | 966f64d8-5bfa-550c-9258-25c8bd5cfad0 |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | bfa7950b-a82e-5e8e-9c24-b9198fa22823 |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 5: FINAL INSPECTION AND HANDOVER
checkpoint-status |  |  | checkpoint | 5.1 - Quality Assurance deliverables
label | 85680821-106c-5ad5-b2f1-c0dfabac1e00 |  | note | ACTION (Hold, Monitor, Witness) - W
label | bcc20ede-d4bb-5724-afa1-da6d53ffd737 |  | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 1a6c4c76-f022-57ea-b64d-961adac549bc |  | note | Frequency - At completion of Lot
label | fc90df9e-2dfa-5850-ad45-4e516892bd5c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 034f5d3b-3de3-56ed-9d17-38d29c4a2620 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 1112bc04-6f45-5d1c-a430-f29279f287a4 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 5.2 - Completion Sign Off From Fields Below
label | 6dff8cb4-a725-545c-b9a9-aff3fe9787fb |  | note | Records - Signatures
checklist-flat |  |  | checklist | ITP - G1202A - Waikaretaheke Riverbend Recovery - Swales & Overland Drainage | itp |  |  |  | Yes | ITP - G1202A - Waikaretaheke Riverbend Recovery - Swales & Overland Drainage | c831da04-a99c-4a80-8b82-3903692b5503
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 9e35585a-2bf6-55d9-8a8d-c7b0ece18bcd |  | textbox | CPS Eng.
text | e462aca7-6062-5a76-89e6-cf76e6ae7462 |  | textbox | Site Engineer
text | 73f99775-8a79-5a39-92c9-073d3486030f |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey As Built
label | a0793920-b5c0-535f-9a93-f8fac3b6c128 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c696e729-63a2-5bee-b91a-313e831530c9 |  | note | Detail - Ensure cut/fill slopes comply with design prior to swale drain or over land drain construction
label | d3eb4eb3-b1f9-5585-af7c-5a943e7e950d |  | note | Frequency - Prior to commencement
label | bf675016-1051-5b3c-879d-04a8768da13a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 89045eb3-a6f1-52af-a576-5e641659f41d |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Previous Lots
label | 64dd18eb-fc67-5b3e-baf5-87ddabde5090 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5daf409e-9580-56cd-bed6-b0d0d33f97c8 |  | note | Detail - Are all previous Earthworks & Topsoil Respread ITP's are completed and signed off
label | 64bd46ce-e93a-5de9-89aa-e1c42fe9783f |  | note | Frequency - Prior to commencement
label | 65ca1878-c20e-5ad1-b3b9-b538ad39e23f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 9335feaa-f76d-511f-8060-cf2eed8ccedb |  | note | Records - Earthworks & Topsoil Respread ITP's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Previous Lots
label | 54bef59d-6251-5d28-b635-647dbdab1819 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 32692ff9-3f40-5a99-94f8-babcb24da6f7 |  | note | Detail - ANY OTHER SITE WORKS THAT WILL CAUSE REWORK TO SWALES HAS BEEN COMPLETED
label | 2f9b3215-6021-57c4-9382-45a2d359b48f |  | note | Frequency - Prior to commencement
label | f9265c26-3e81-5412-bc0c-c3ffaa796592 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 3a2c04b4-870a-5b9b-b6bd-031be53e4d7f |  | note | Records - Snag Lists for previous Lots
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Excavation of Swale Drain
label | 7bae49be-50f3-5e04-9c5a-9dfd54762887 |  | note | ACTION (Hold, Monitor, Witness) - H
label | cfcea117-caee-5d53-9d08-15cc44d51c0c |  | note | Detail - Swale drains shall be excavated, shaped and constructed to the dimensions and the types on the For Construction Drawings/ existing swales
label | 92801c93-5fa7-53f0-9f9f-c1a932e8e6b2 |  | note | Frequency - During Construction
label | f2cba139-d8bd-5184-ab98-4b7fdc6909af |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | da4e8e17-2f78-5fff-a52f-ec121b5924ae |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Profiling of Swales
label | da3b95e3-9c5b-5bd5-b917-58bbc5afa29d |  | note | ACTION (Hold, Monitor, Witness) - W
label | cdbe21f1-a1ea-500b-8236-9a00e90da762 |  | note | Detail - Level check prior to topsoiling
label | 0dd8cea9-180d-5fd6-a557-85fe7ed7dddf |  | note | Frequency - During Construction
label | e64fcd91-ec99-5d7f-98de-727c95ed5043 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and Visual Inspection
label | e669ddcb-834a-5033-8ca6-c79b3cb948be |  | note | Records - Photos, measurement sheet
checkpoint-status |  |  | checkpoint | 6 - Profiling of Swales
label | 53d2920f-f05d-5e14-bb39-37930f86a3dc |  | note | ACTION (Hold, Monitor, Witness) - W
label | e152f914-3104-5c14-9284-23cbc9b20385 |  | note | Detail - Level shape upon completion of topsoiling by As Built survey
label | fbee2dcb-9ce2-5972-b0e3-75793eb34072 |  | note | Frequency - During Construction
label | a28e7f3c-e7b3-59f3-bf82-6d48f872aa2f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and Visual Inspection
label | aad95d6b-9621-5a57-86c2-5920e20bba3e |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 7 - Lot Number QA File
label | 46dc9919-3cf4-50eb-9351-1503fff08492 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b5422c95-4082-51b7-9a3e-c1fca8e769e5 |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | eb4af9df-93e5-52f8-9be1-f7e746db25d3 |  | note | Frequency - At completion of Lot
label | 24b4f3c8-8db7-56f5-b7c8-5be18d463e34 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | b8620c47-fd82-5137-b7d2-5020f04a5eae |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | aebc79a6-c88b-5f84-ac23-578ba0c2ddde |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 8 - As-builts
label | 18bea5c4-9dd4-56fe-a168-46928c1e9956 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9d034dc6-6068-5d7a-91b0-35561f2a5770 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | eb818c67-ec9a-5f17-a6ce-703b81f3e1c9 |  | note | Frequency - At the completion of the Lot of work
label | e42804f2-799a-52df-b2ea-b02711a834f7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 84fbe299-fa50-59ed-8920-bb367caeda0f |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Quality Assurance deliverables
label | a81ec121-503c-56e5-8757-a5b844538c2e |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6d7af1fb-8243-5d8a-92bd-2d23aa5b75e5 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. Red line mark up drawings to be included in QA file
label | 0f61cf24-33e0-5d8e-8c6b-91a1939758a3 |  | note | Frequency - At completion of Lot
label | 82c336ea-7af1-5b90-a385-e5a0a63f0814 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | edf5adad-3463-5b96-b584-3d5851d1d845 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 76192795-528e-5e93-afca-6dc43e7ea2d8 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 10 - Completion Sign Off From Fields Below
label | 9d1bdc22-7a6f-5f15-83b6-fa132042a4a3 |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | CS-4046 - Barrier Concrete Inspection Record |  |  |  |  | Yes | CS-4046 - Barrier Concrete Inspection Record | c84b1644-fb9f-4467-92e7-f547577a1ce4
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | b5144b99-70c5-5873-811e-d9bf67ae147b |  | textbox | Project No.
text | fd0d2af9-4fa7-55d4-bc8b-76b3fd32ccf4 |  | textbox | Location / Description of Pour:
text | 5263e3cf-e973-5d92-8241-c6b59726f4d2 |  | textbox | Concrete Grade |  |  | Mpa
text | 9caf3e0d-1925-52cb-96f3-48bcacb59388 |  | textbox | Drawings & Revision No. used to check off Pre Pour Inspection:
text | a5795527-8b8f-5207-b443-945633428235 |  | textbox | Pour No.
checkpoint-group |  |  | section | Formwork Mould
checkpoint-status |  |  | checkpoint | Cleaned and oiled
text | 93306f34-f21c-5a85-bbc2-5fbecab60332 |  | textbox | Initials:
date | 8f4078a5-95aa-522d-bbce-f96721a5df54 |  | date | Date:
checkpoint-status |  |  | checkpoint | Correct profile/ dimensions for Barrier
text | 939a39a0-b8aa-59ea-8e42-37b94179756a |  | textbox | Initials:
date | a2ad9ad9-8c2b-552d-a6ca-5ae60cbb0b61 |  | date | Date:
checkpoint-status |  |  | checkpoint | Check set out – 350mm from face of Barrier
text | 65d5be14-698e-5478-875a-9518f0a1431b |  | textbox | Initials:
date | 8b3e3b4d-22ce-511e-bd99-bfa9614e4d11 |  | date | Date:
checkpoint-status |  |  | checkpoint | Embedded items in correct location
text | 89714c2e-3fe4-5cd2-83b2-fa1b9f2ef77b |  | textbox | Initials:
date | bfe2880b-1826-5e65-af34-c0f68a7fb159 |  | date | Date:
checkpoint-status |  |  | checkpoint | Horizontal and vertical alignment correct to design
text | 4df07d1b-847d-5c8c-8c4d-542bd02b18ce |  | textbox | Initials:
date | fd4ff0ef-3b65-5ac7-9487-ab05ae20ac70 |  | date | Date:
checkpoint-status |  |  | checkpoint | Stop-end coated with Rugasol MH Extra, installed and braced
text | e2cd3cc8-ee5a-5c38-b456-d52c9db58388 |  | textbox | Initials:
date | 90c08d1b-2f8b-5a5e-95e1-fcc63bd7d9ec |  | date | Date:
checkpoint-status |  |  | checkpoint | Grout tight
text | f532aec3-24f6-554e-9205-5c60eec0fd72 |  | textbox | Initials:
date | fb70467f-5803-505d-b08c-80efda6ea9ef |  | date | Date:
checkpoint-status |  |  | checkpoint | Voids set out
text | 398ff702-ae78-5ed5-8a87-b2b97c9e5730 |  | textbox | Initials:
date | b511a7d9-0bda-56b7-a757-721c1bae585d |  | date | Date:
checkpoint-group |  |  | section | Reinforcement/ Strains
checkpoint-status |  |  | checkpoint | Strains/ reinforcement content correct
text | 6efb4c32-890b-51af-a6e2-d5afcbf9f79b |  | textbox | Initials:
date | 85997b12-93d3-503d-8668-1290ab3d440d |  | date | Date:
checkpoint-status |  |  | checkpoint | Correct grade markings
text | f02c307b-c8f1-5f2a-bad5-8a3d9b8a54d0 |  | textbox | Initials:
date | 68283238-2b3c-5da6-bd6a-67fd3e7b4158 |  | date | Date:
checkpoint-status |  |  | checkpoint | Correct cover
text | 0397bfac-faac-5c5c-9117-b37cdc53634b |  | textbox | Initials:
date | 1cf8d819-8888-5da4-a38b-9aa04720a288 |  | date | Date:
checkpoint-status |  |  | checkpoint | Lap location and lengths
text | ee4ef100-597e-5f7d-9e5c-05b264166db9 |  | textbox | Initials:
date | 00fe70a0-f7b1-5b30-8cfb-7d994d72ea22 |  | date | Date:
checkpoint-status |  |  | checkpoint | Strains placed in correct location
text | 4d5ba5f8-ce71-5fb4-a6a4-509ebad073bd |  | textbox | Initials:
date | 266834ff-7e6f-5ce8-af21-55fea8580252 |  | date | Date:
checkpoint-group |  |  | section | Subbase/Basecourse
checkpoint-status |  |  | checkpoint | Suitable for Barrier
text | e721dffc-43ef-53c5-886f-09e08430fbc5 |  | textbox | Initials:
date | 8dcd4a95-f3c5-5602-8642-f59bd8503d15 |  | date | Date:
checkpoint-status |  |  | checkpoint | Cesspit protection in place
text | bc0cff06-c0f0-5782-b9e9-d162ab57f772 |  | textbox | Initials:
date | 5db6e3cf-512b-5c1a-a459-f25266d6adc2 |  | date | Date:
checkpoint-group |  |  | section | Other
checkpoint-status |  |  | checkpoint | Correct mix ordered
text | 266a6093-99e6-5e22-8649-3c0390afba31 |  | textbox | Initials:
date | 44d94349-0d42-5739-91ab-ab0c11ce2680 |  | date | Date:
checkpoint-status |  |  | checkpoint | Construction joint roughened & clean
text | 11560753-f850-5dc5-891b-4ea825f33d1d |  | textbox | Initials:
date | 88eecfed-fca8-5283-807b-8c237d4df379 |  | date | Date:
checkpoint-status |  |  | checkpoint | Road Light/ BG 800 openings secured
text | 0afbb9d5-c316-527b-936a-0acfaa4f6237 |  | textbox | Initials:
date | 028e4219-86e0-5d84-af31-9e5ac07280b0 |  | date | Date:
checkpoint-status |  |  | checkpoint | Independent Survey – Check off critical survey points
text | 17a09c41-fad4-5abb-8bd5-0e6535d4c441 |  | textbox | Initials:
date | 78e17eb8-01f1-58de-a856-1a52fd2a2d87 |  | date | Date:
checkpoint-status |  |  | checkpoint | CPS Engineer Notified
text | 62293849-1cc0-5c5e-bd32-7dcc34f64667 |  | textbox | Initials:
date | 10e8aef9-f2c5-5bfa-9a12-c763193dc27e |  | date | Date:
checkpoint-status |  |  | checkpoint | Pre-Pour Checked and Accepted – HOLD POINT – Site Engineer & Engineer’s Rep to sign
text | e251572f-8954-5226-97ad-25b4fd90d587 |  | textbox | Site Engineer - Name:
date | efb3a4f2-2f62-56ee-b1b4-00bbe5533527 |  | date | Site Engineer - Date:
text | 710ad721-38d6-54f5-bafe-881054a6d922 |  | textbox | CPS Engineer - Name:
date | d85a0a97-3697-5b93-a144-873ca1611d93 |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checkpoint-group |  |  | section | Wet Concrete Checks
checkpoint-status |  |  | checkpoint | Correct mix delivered
text | bed209ad-d6c6-52ff-b2ad-1e59b869c797 |  | textbox | Initials:
date | 1b9caa66-cfb2-5f56-949f-b8319a267b8a |  | date | Date:
checkpoint-status |  |  | checkpoint | Slump/flow Target
text | bd050dc4-9e72-582d-8c61-821ab4f0df35 |  | textbox | Initials:
date | 3bb46878-8d9d-53ff-bcd7-e706f270faa9 |  | date | Date:
checkpoint-status |  |  | checkpoint | Compliance Cylinders Taken
text | 91005d1a-e354-5c6a-ab75-18401d054fd1 |  | textbox | Initials:
date | 7478dd9f-e3c3-5e85-9973-56a8b7ef332f |  | date | Date:
checkpoint-status |  |  | checkpoint | Site Cured Cylinders Taken
text | f3eb417b-87fb-5e9e-aa57-2c58ddc28f7e |  | textbox | Initials:
date | ce5d602f-38d2-5759-b0d6-d2cf87e1ab50 |  | date | Date:
checkpoint-status |  |  | checkpoint | Concrete Vibrated
text | 81caf226-0ec8-5129-96cf-ade6e04e7467 |  | textbox | Initials:
date | 6c6c7846-841a-52bd-a0b1-5ff7509b3cb6 |  | date | Date:
checkpoint-status |  |  | checkpoint | Finished Level: Finished to grout check / angle fillet worked to
text | 2e424e6d-0430-5534-8914-758618d01527 |  | textbox | Initials:
date | ffb73446-a6e9-5231-8877-cdffdd7db0d0 |  | date | Date:
checkpoint-status |  |  | checkpoint | Surface to required finish
text | f28916de-160f-59cd-a169-2e1d0a1120d7 |  | textbox | Initials:
date | 39bbd1d5-e5ab-5c5d-a780-c8635329876d |  | date | Date:
checkpoint-status |  |  | checkpoint | Curing applied (specify type)
text | d9257b2a-d3e4-5751-8613-10ec37a4f3a4 |  | textbox | Initials:
date | 112bc82d-4fb6-5d4b-bf4f-3f32dec93a9a |  | date | Date:
checkpoint-status |  |  | checkpoint | Concrete Supply Dockets collected
text | 44803ed2-811b-5388-851f-cfeb7cf84c85 |  | textbox | Initials:
date | 0d22ee87-f117-5dc6-89a1-9a4aa501e0ad |  | date | Date:
text | 2238694b-93c3-54ba-9576-f36391e66f48 |  | textbox | Pour Start Time:
text | df82e48d-0912-5541-88f8-1cf41f310a98 |  | textbox | Pour Complete Time:
text | 4b3d0dae-1bc5-54eb-8cbd-a577e4307d4e |  | textbox | Volume Placed:
checkpoint-group |  |  | section | Post Concrete Inspection
checkpoint-status |  |  | checkpoint | Surface Finish F4 or F3
radio | 86411ae9-9eb6-5800-b4d1-044340a70b5e |  | radio | (select one) | F4,F3
text | 813a2c67-8ffd-54d7-ae37-9611a7fe3b71 |  | textbox | Initials:
date | 7286244f-3f9d-54ad-9b50-f3593f588688 |  | date | Date:
checkpoint-status |  |  | checkpoint | Curing correctly carried out following application of water
text | db1a1f81-8f8c-5740-81b8-a8171a958bda |  | textbox | Initials:
date | 8b625a44-1af6-5819-9476-56792c665e8c |  | date | Date:
checkpoint-status |  |  | checkpoint | Barrier saw cut within 24h
text | 92fc6765-d856-5f5c-b1e1-2adef7276981 |  | textbox | Initials:
date | 12512729-6b2a-5c9d-9c59-f6c9ddf1cb1f |  | date | Date:
checkpoint-status |  |  | checkpoint | Preparation of Construction Joints Completed
text | ff965517-2e59-5633-8339-526dc7a73827 |  | textbox | Initials:
date | 22eda5bd-7bf3-5dac-b428-59554933bfc1 |  | date | Date:
checkpoint-status |  |  | checkpoint | Blow holes, tie bar holes filled
text | 1fedffe5-0bb6-5154-915a-4d5ac4318ff6 |  | textbox | Initials:
date | 9182bcf2-5c45-53e6-b516-c05f544038ca |  | date | Date:
checkpoint-status |  |  | checkpoint | Inspection of surface/s & any authorised repairs have been completed
label | abe751de-e45d-529b-966e-1eed3c21f692 |  | note | CPS Engineer Inspected.
text | 27175136-f559-5e2a-ac06-9a934331d92e |  | textbox | Initials:
date | 4cbe8874-de15-5c9f-af1a-f131f8e7eff0 |  | date | Date:
checkpoint-status |  |  | checkpoint | As-Built complete
text | f80bf983-3313-5f68-8f8c-eccaa28b59a1 |  | textbox | Initials:
date | ebadd7b4-808a-549a-95ed-5914f105d2bc |  | date | Date:
checkpoint-status |  |  | checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
text | e7ae042a-64ad-569c-bc34-76b65dedf1f7 |  | textbox | Site Engineer - Name:
date | 32add1aa-42ff-5090-8020-eab2a38a1877 |  | date | Site Engineer - Date:
text | 10fb224c-3501-5f1b-b0a8-441ccd7a4a43 |  | textbox | CPS Engineer - Name:
date | f6dd27f0-2dea-500f-8c82-b2c34a5a41ee |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | CS-4048 - ITS Duct Installation |  |  |  |  | Yes | CS-4048 - ITS Duct Installation | cab7b78a-82ce-4de1-9ee9-ba32f7970bc9
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | cd6e4441-b839-5df4-8649-dea0af337dd4 |  | textbox | Project No.
text | 0bb1b82b-f225-5ad3-984d-f488b069000a |  | textbox | Drawing No (& Rev No):
text | 09c32336-53c2-5394-b462-65fa30a21d78 |  | textbox | CH Start:
text | 360de2c3-e86a-552e-8b51-c8828670c025 |  | textbox | CH Finish:
checkpoint-group |  |  | section | Inspection
checkpoint-status |  |  | checkpoint | Pull Pit/ intermediate line points set out by surveyor
text | 63a0ddb3-66b0-5715-9375-4bf746e01019 |  | textbox | Initials:
date | 05ed1ca9-61c1-599b-9c21-68e0b5834586 |  | date | Date:
label | 9f2ca632-e438-5bd7-ad22-d1e1680a544d |  | note | Comments: Survey Receipt
checkpoint-status |  |  | checkpoint | All existing services exposed and identified before trenching
text | abe8ac65-0d58-54ba-9efe-d42ea60c29ca |  | textbox | Initials:
date | a3906b11-d0a1-5461-9cb7-e61908bb322e |  | date | Date:
checkpoint-status |  |  | checkpoint | Trench must be made safe before any person may enter the trench
text | 1711b517-498c-58bf-851f-e474f851122c |  | textbox | Initials:
date | 9ac900dc-6da0-53ff-ad09-5a491ffa7114 |  | date | Date:
label | 7c4c22e2-5d58-5653-a544-f1f566b68f1b |  | note | Comments: Trench depth > 1.5m must be shored or battered.
checkpoint-status |  |  | checkpoint | Base of trench is clean and inspected by engineer
text | c7658b40-4450-5dcf-8308-13547550b8c3 |  | textbox | Initials:
date | a7e768f2-2c73-507d-a766-6f6390df58a1 |  | date | Date:
label | e40a13a6-3d6f-5850-ae99-4a8a1b96abe7 |  | note | Comments: Base to be as flat as possible
checkpoint-status |  |  | checkpoint | Bedding material to be placed in layers 100mm thick
text | f831b90f-522b-5f5c-b0ea-39cc982fe43a |  | textbox | Initials:
date | ed0dfa67-1bb0-556e-a76d-abafdbd07ea1 |  | date | Date:
label | 7b6227af-b916-583d-8f53-c50e6aebcc7e |  | note | Comments: Lab test 85% of MDD (CIV=8) or 95% of MDD under carriageway, Frequency 1/20m
checkpoint-status |  |  | checkpoint | Glue ducts together and lower carefully into trench.
text | b4fd6f4b-b270-5e49-bee5-46baaaa90d55 |  | textbox | Initials:
date | 078db0f4-89ae-51f3-aafa-d863db70e8e8 |  | date | Date:
label | 6baddb75-6a7a-587f-9445-f02506119b6d |  | note | Comments: All open ends shall be taped up to prevent material entering
checkpoint-status |  |  | checkpoint | Guide wire installed in ducts before lowered into the trench
text | 1a023787-56da-5e8e-85ef-deb4122c4e1d |  | textbox | Initials:
date | 99b23a06-31ac-5347-ab5d-5f031f66ea90 |  | date | Date:
checkpoint-status |  |  | checkpoint | As built survey every 20m
text | 2527bacb-dc51-58c5-8238-1f3bb156aaba |  | textbox | Initials:
date | 49453e77-ea87-587e-9c9c-a7a7a8338ca1 |  | date | Date:
label | f2f23299-6837-54ec-9be7-50b520e29efb |  | note | Comments: Must pick up all changes in direction
checkpoint-status |  |  | checkpoint | Ensure 50mm gap between ducts sitting in the base of trench
text | 2a1d78d7-fc35-5eed-a779-eb9ea606b081 |  | textbox | Initials:
date | 550b1391-4723-5b4b-97e7-b89eb836c1e7 |  | date | Date:
label | f9849275-12fd-5594-b8a0-bcfcc532459d |  | note | Comments: Check gaps before backfilling
checkpoint-status |  |  | checkpoint | Ensure backfill material is suitable and un-contaminated. Compacted and tested in 200mm lifts
text | fc70f256-0834-54d2-8233-a20a5ab0d4a4 |  | textbox | Initials:
date | 0be3701d-eaa8-548f-97ac-4aa41fb55ca3 |  | date | Date:
label | 73c65f2f-1f81-5031-b403-835d4a9726c6 |  | note | Comments: Footpath/Berm - Backfill with excavated material. CIV 8 required.
label | ca2e21b7-06ad-5a28-ae93-15d8d9de5531 |  | note | ○ Carriageway – Hardfill (GAP65) 95% of MDD
checkpoint-status |  |  | checkpoint | Warning Tape to be installed 200mm above the top ducts
text | cc82e8ee-ac2d-5219-9c25-80d5d542e7ac |  | textbox | Initials:
date | c732dbeb-6666-5f10-b9f5-7e8406eb1301 |  | date | Date:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
text | 8f82e7e2-7e90-50c6-9bae-d9a23eb0544b |  | textbox | Name:
text | fb609ef2-fa08-5c2b-b890-8ccf80db00f2 |  | textbox | Position:
date | f2c0c731-b3e7-5faa-969f-453b55fe8d31 |  | date | Date:
holdpoint |  |  | signoff | Sign:
checkpoint-no-status |  |  | checkpoint | Trench Cross Section
text | 60eeb5c7-c647-5891-a747-32353c0fa858 |  | textbox | H |  |  | (m)
text | 1a38f294-ad22-5fe9-8aa0-b18e1642c73b |  | textbox | L |  |  | (m)
text | fa245ff9-8bff-53ff-817a-559e4d9d7a93 |  | textbox | Backfill: Warning Tape 200mm above top of duct
text | 112f7d48-9f7f-508a-a987-fb64f125662b |  | textbox | Backfill Material Type & Source
text | 2f3d22cd-3ecf-5050-875c-d21aeb679dd8 |  | textbox | Bedding layer Material Type & Source
checklist-sectioned |  |  | checklist | CS-4102 - Pressure Rebound Test |  |  |  |  | Yes | CS-4102 - Pressure Rebound Test | cb8296f5-9035-4a28-acbc-4ec912d424f0
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | Details
text | e724d01d-ea69-5e5e-ac58-c10a63f49e73 |  | textbox | Contract:
text | 9d6a5538-0d9f-5a94-a1d7-2516c8be0ae5 |  | textbox | Sub Work Area(s):
text | cd7cf66a-d066-5f25-9611-b0c020a70449 |  | textbox | Sublot(s):
text | 2d3cd535-9ae0-5429-b9a6-3fc0c0d3a611 |  | textbox | Work Area(s):
text | 5f7b59f5-14b8-5cbb-a2ea-0ec713ebe216 |  | textbox | Lot(s):
date | 5be53653-f00d-5f59-b172-ac47c286458e |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Personnel Conducting Test
text | 9c48c970-6874-5f8e-975b-dbe7fb91f62a |  | textbox | Drain Layer:
text | d1cd1b64-3919-5c62-8cfe-f7a6cce7e432 |  | textbox | Site Engineer:
text | 37fb57ea-655e-55d9-92b7-eeca59e284d3 |  | textbox | CPS Engineer
checkpoint-group |  |  | section | Pressure Testing Record Sheet For Pressure Pipelines
checkpoint-status |  |  | checkpoint | Pressure Testing Record Sheet For Pressure Pipelines
text | a609aa52-016a-53f3-8ca2-6a10f60fa8d2 |  | textbox | Pipe Material and Rating:
text | e03464a3-eb05-5e36-8680-7391b5d97d7f |  | textbox | Test Length (m) L:
text | 1f41c936-3b84-581d-9c2e-98378d61c821 |  | textbox | Pipe Internal Diameter (mm) D:
text | f09b0f99-cf2d-52ea-9cce-2b0a318c1b5d |  | textbox | Depth of Pipe Below Water Table:
label | 63ece3fe-1a1b-592e-adb6-0624a5040196 |  | note | Attach Test Section Sketch (show heights, air valves, gauges and filling points)
text | 5bfa9ebd-ab9e-5c70-8730-36fff4f435f4 |  | textbox | Ambient Air Temperature: |  |  | °C
text | 99c0a19d-b1f0-5671-91e1-e600f1c90356 |  | textbox | Water Temperature: |  |  | °C
checkpoint-group |  |  | section | Pressure Rebound Method
checkpoint-status |  |  | checkpoint | Standard Test Pressure
text | 2c2ab003-41f0-532b-a4ee-d7269513444d |  | textbox | Pressure Applied: |  |  | kPa
checkpoint-status |  |  | checkpoint | Preliminary Phase
label | 5e33e545-ba42-5062-a391-a25bea340d1b |  | note | P60 > 70% STP
text | 6033571a-0043-56a5-af5a-90803287732c |  | textbox | Acceptance:
checkpoint-status |  |  | checkpoint | Air Volume Assessment
label | b2de1d37-f13e-5b38-9f26-2060c312cf77 |  | note | 1. Reduce pressure by 10%-15% STP (ΔP)
label | 56e220c1-d744-5723-87ad-df764cfd620a |  | note | 2. Measure water volume bled out (ΔV)
label | a618c612-f586-578a-8642-a18fc1fb4589 |  | note | 3. Calculate ΔV max allowable
label | fe836d62-375b-5947-b2ab-03d5c672890a |  | note | Where: 〖∆𝑉〗_max⁡𝑎𝑙𝑙𝑜𝑤𝑎𝑏𝑙𝑒 =1.2𝑉∆𝑃(1/𝐸_(𝑤 ) +𝐷/(𝑒𝐸_𝑅 ))
label | 37e28497-dced-5f30-b35e-2d60d87f11b5 |  | note | Acceptance: ΔV < ΔVmax allowable
label | ea3db8e7-b556-5c14-afd9-b748f458e973 |  | note | – – – – – – – – – – – – – – – – – –
label | 3c66bd2a-a0a8-5e22-823f-03c1f7c52192 |  | note | Air Volume Assessment Parameters
label | a400edaa-c929-5b88-9122-1592ce8f9e3d |  | note | – – – – – – – – – – – – – – – – – –
text | 094127d2-88c5-550f-9835-1a4c1971098b |  | textbox | Nominal Size (mm):
text | b5e1dd7d-12ae-5f22-bd1b-edf72bc8bf2f |  | textbox | Mean Bore (mm):
text | e25b2208-0ef7-5499-b3a1-c534736059e0 |  | textbox | Tested Length (m):
text | d3676f5e-4b40-5df9-9612-3638970f5659 |  | textbox | V (m3):
text | db7ef8d7-eefb-55c8-ab2e-b3c1e947ed70 |  | textbox | e (mm):
text | 77c89574-b76f-5f93-b3d8-8850d0c594c8 |  | textbox | Ew (kPax103):
text | 121fb1c3-9264-58d9-b6dd-8ef823bfad59 |  | textbox | Er (kPax103):
text | 3ea3bb46-ad1c-50aa-83e4-20d058c92c2b |  | textbox | ΔP (kPa):
text | 2b06502f-cec1-587a-9c20-54e4142aa622 |  | textbox | ΔVmax allowable (L):
text | aa39badb-5e3b-5f42-98c6-47cd90016e0a |  | textbox | ΔV (L):
text | 6bf70bb4-5fc6-5f7f-80cf-ced1aca5a953 |  | textbox | Acceptance:
checkpoint-status |  |  | checkpoint | Main Test Phase
label | 740e61d1-efd8-536c-a2ea-d42b5d091b50 |  | note | Observe and record pressure for 0.5 - 1.5hrs
label | acddcd48-bcf3-54ef-8c90-15c5979773b4 |  | note | Acceptance:
label | 13bda726-0c51-5ef0-9ca2-7aae78e9a759 |  | note | 1. No failure of any thrust block, pipe, fitting, joint or other pipeline component present
label | 1b47f015-7729-559b-a676-3b97dd0e3e3a |  | note | 2. No visible leakage present
label | b2437a90-5694-5a36-a034-a191ad26020d |  | note | 3. Pressure rises or remains static for 30min period
label | 7ed30a72-b384-5b22-988a-b110769387ed |  | note | 4. If doubt exists extend pressure recovery to 90min where pressure drop is to be < 20kPa
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-no-status |  |  | checkpoint | General Methodology Details
text | d9c5f9ec-5f22-5167-94d8-cd43d1a87435 |  | textbox | Process for removal of air
text | 5bd7cc87-f117-51b7-b40e-3b5c10bead69 |  | textbox | Details of water meter
text | 24a48635-e059-5cd6-b40d-1731307e4550 |  | textbox | Details of pressure gauge
text | db4a29b0-5999-5dcf-9095-001da783ff98 |  | textbox | Details of pump
text | e62a05be-df00-54ad-891a-3e7931a50073 |  | textbox | Water source
text | 86b2f820-6593-591d-a22f-0c60a9ad4506 |  | textbox | Water Disposal
checkpoint-group |  |  | section | Signoff
checkpoint-status |  |  | checkpoint | Checked and Signed by Site Engineer
date | d252c2c2-daee-5390-b19b-72b20c21156a |  | date | Date:
holdpoint |  |  | signoff | Signature
checkpoint-no-status |  |  | checkpoint | Site Photo Records
checklist-flat |  |  | checklist | CS-4100b - Basecourse Approval Checksheet |  |  |  |  | Yes | CS-4100b - Basecourse Approval Checksheet | cdf100e4-dfe1-4a6d-a203-b3e35ae5030c
checkpoint-status |  |  | checkpoint | Material production testing (1/source and at least 1/3 months):
label | 3d2b1110-9503-5044-b16a-817a67a781f6 |  | note | – PSD: NZTA M/4 Section 4.2.3 Table 2and 3;
label | 41eb930c-5b6c-595a-9dbd-14d48c5ec73f |  | note | – Sand equivalent: >=40;
label | c70649f1-485f-5170-8ab7-b3ad11e21bad |  | note | – Clay Index (material passing 75µm): <=3;
label | 85549dc1-8abb-52b5-aefa-5a7565d5cbcd |  | note | ○ Plasticity Index (material passing 425µm) :<=5
label | 51d64e70-6f56-57c0-9ec6-83dbb3fb97b6 |  | note | ○ Aggregate material compliance for Basecourse stockpiles – CPS Hold Point
text | a7071819-48ca-59ca-8381-ddfd0c96f434 |  | textbox | Initials: CPS / Design Engineer
date | bb9374a7-08f1-5331-ad16-01ef00b999e6 |  | date | Date:
label | f9d4093b-d9be-5077-95f6-6a62b87dc9c2 |  | note | Comments: Material Test Report – Aggregate shall comply with TNZM/4
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Visual inspection for any defects on the subbase – CPS Hold Point
text | ccb6e976-4360-51e7-88ad-61a72d77debd |  | textbox | Initials: CPS / Design Engineer
date | 03e1d47f-c7db-51b4-9d53-efc4cde7073d |  | date | Date:
label | 5893a188-8d18-5f94-b809-085c596c6ed2 |  | note | Comments: Visual Inspection
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Basecourse Compaction: - NDM tested (Mean>=98% of MDD; Minimum>= 95% of MDD) – CPS Hold Point
label | 773cccd1-cb9b-573b-abab-a73315e5d6a0 |  | note | ○ Note 1: To test every 30m of road per lane, staggered at 15m
text | 9dbe9343-d47b-5adf-b975-1ec2fa9ada6b |  | textbox | Initials: CPS / Design Engineer
date | 5eb2ac4d-9d2a-5b6b-9f20-4dfb36315a95 |  | date | Date:
label | dcd55c0b-a5f9-52a3-b53e-6c1402cd39d2 |  | note | Comments: IANZ Test Report
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Basecourse Benkelman Beam Test (only when specified on IFC drawings):
label | 9db5bc1b-2861-5c6e-8ddf-7593258d565d |  | note | ○ No more than 5% of the deflections exceed 1.4; No single deflection exceeds 1.5mm -- check moisture content if high deflections are obtained.
label | 45aaa502-2b81-5cee-bef7-35e9ecf8be85 |  | note | ○ Note 1: At 10m interval in each traffic lane- staggered
text | 3441342b-ee9a-5e6a-937d-3547810528d4 |  | textbox | Initials: Site Engineer
date | c1203ef6-6fec-5b46-b63d-3515415c1383 |  | date | Date:
label | 36696e61-fda6-5807-9e7a-e92233cbfb60 |  | note | Comments: Benkelman Beam Deflection Test Record – only if required
checkpoint-status |  |  | checkpoint | Basecourse FWD: Testing to only be performed post Benkelman Beam deflection testing based on results. Not required for chip seal roads – CPS Hold Point
label | f999e157-1831-5455-8a00-bfd26507e695 |  | note | ○ Note 1: At 20m staggered intervals in each traffic lane
text | eae522c7-3865-595a-bbd4-fdc6046b60fe |  | textbox | Initials: Site Engineer
date | ec2951c0-9992-5d16-aca6-19616c45e8f7 |  | date | Date:
label | 1bf548ee-53ae-5025-a910-70705478d298 |  | note | Comments: Only if required
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Basecourse surface shape - stringing line checked and within tolerances:
label | 1dd1f34c-b412-5c04-8fc4-050fa9eb9b5a |  | note | (a) Level: with concrete channel and at or close to the lip of channel –5 mm +5 mm; other locations -5mm +15mm (Survey Report attached);
label | f6c186c1-2b76-55ba-99ab-c83db96c61ff |  | note | (b) Crossfall: no depart from the design crossfall by more than 0.5%;
label | db8fdeb0-41e3-5892-99ee-0d4daa560ab7 |  | note | (c) Manhole lids must be in line with the crossfall.
label | 5feaccc8-72e3-5435-86eb-1000ebbe596d |  | note | ○ Note 1: 1/10m intervals and across manhole lids – CPS Hold Point
text | 3102205e-65ee-593d-8dfb-3e036fe128df |  | textbox | Initials: CPS / Design Engineer
date | e4d8eb81-6d5e-5ae9-bae4-a5c2a1d9c1cd |  | date | Date:
label | 0044e013-3432-5c9d-a453-3f6d8090b082 |  | note | Comments: Survey Record Sheet & Stringing record sheet – no point of the surface shall vary more than 10mm over a 3m long straight edge
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Final Inspection - Prior to chip sealing or asphalt surfacing – CPS Hold Point
text | 47999f3b-62c1-54ed-9bf3-57a36bbb8145 |  | textbox | Initials: CPS / Design Engineer
date | c3dc1aba-e28b-5071-9f2c-d3ab593f0c34 |  | date | Date:
label | 4d2caf99-07a7-5b27-9f13-48de07b58a40 |  | note | Comments: Visual Inspection – the large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
holdpoint |  |  | signoff | HOLD POINT
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | b7cb5b67-82e6-5b44-ac2a-9dde019c82b0 |  | note | Position: Site Engineer
text | 78301d2a-d67b-578c-87ef-78abde26eeef |  | textbox | Site Engineer - Name:
date | 6f3d706e-8cf7-5638-b979-3464e131b0ba |  | date | Site Engineer - Date:
label | f359b41c-5326-5581-a752-8205a3d0fd8a |  | note | Position: CPS / Design Engineer
text | ce6580cd-d5bb-5182-802e-c1e768e0e950 |  | textbox | CPS / Design Engineer - Name:
date | 5572acbc-4aed-58a2-95c6-61d6c6cc0e8d |  | date | CPS / Design Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | CS-4060 - Pre-Seal Checksheet |  |  |  |  | Yes | CS-4060 - Pre-Seal Checksheet | d013f395-d983-4e71-9e42-8ebccaf17868
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | e680f4b0-25f7-5da1-bf72-0f08519aa019 |  | textbox | Project No.:
checkpoint-group |  |  | section | Surface Shape Check
checkpoint-status |  |  | checkpoint | Surface Shape Check:
label | 82ed9eff-ac83-5cc3-9c79-b5f05c2a0739 |  | note | No point of the surface shall vary more than 10mm when checked with a 3m straight edge (Measurements to be undertaken at a frequency of 1 every 100m)
label | 0c7fdb6c-40aa-528e-b416-69998cfd03ca |  | note | Note: Left and Right when facing increasing chainage.
checkpoint-no-status |  |  | checkpoint | Chainage (1)
text | e92e7ab6-f4c6-5aed-adff-48f5e2091ca5 |  | textbox
label | 5f329be3-0d18-5d51-95b6-ceed0ef4ab2b |  | note | Measurement taken from straight edge to surface level
text | a5b46890-b942-56cf-b9a0-5d286d8747cf |  | textbox | Bound Left
text | 618ab3fc-797f-53ba-8399-219b50c9ffdc |  | textbox | Bound Left - Left:
text | c06c9b8c-aff1-57dc-8a91-65692e6b0419 |  | textbox | Bound Left - Right:
label | 3c6bb777-8701-5d99-9d1c-686d22f224ef |  | note | ––––––––––
text | 3829c982-1bf5-5b70-92b1-5792eb978bcf |  | textbox | Bound Right
text | 41c6bbca-9542-5eb2-be6e-8f78d4925ea2 |  | textbox | Bound Right - Left:
text | 1d525690-61d3-55b7-854d-0d0630bf7319 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (2)
text | 7e89886c-a6ea-5346-baef-14a9f10f20fb |  | textbox
label | c3de1249-30db-5fb8-ac72-8438fed5b48c |  | note | Measurement taken from straight edge to surface level
text | 545aa83f-2b4b-5c07-bd26-9b3bccbd440e |  | textbox | Bound Left
text | aeec7564-3a6a-5fdb-8a74-4a5e0c8934f8 |  | textbox | Bound Left - Left:
text | e42629e5-87c5-5878-827c-2aac2aba5d37 |  | textbox | Bound Left - Right:
label | 2ebb30a3-1858-565b-a6df-d26d9236c4d5 |  | note | ––––––––––
text | 0acf8cc4-d935-5d44-a2c1-a0988f12308a |  | textbox | Bound Right
text | 90e15747-3538-5043-891b-aafb22712202 |  | textbox | Bound Right - Left:
text | d6a5ed88-43aa-56ce-9fff-91b1378dd103 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (3)
text | 88b91cf3-2df0-5586-a9f0-a1eaef78d40e |  | textbox
label | 8796ef06-29fb-5714-a048-3308b30595a5 |  | note | Measurement taken from straight edge to surface level
text | 7598e928-9fd3-5508-8b41-ffdd79ab9cb8 |  | textbox | Bound Left
text | fb49f2d8-58f9-55c4-894d-ad00dd1dff90 |  | textbox | Bound Left - Left:
text | 18d8a580-d415-51a0-82ec-2d3c70c053b4 |  | textbox | Bound Left - Right:
label | 7b00d527-4c7d-59f4-8090-4674b573f466 |  | note | ––––––––––
text | 6bf67b05-929a-5cad-9abb-ab0f83539087 |  | textbox | Bound Right
text | 2c5c95d4-a862-5e29-b567-a6c0145efbe4 |  | textbox | Bound Right - Left:
text | 285f212b-b246-5c5e-8ded-d95ea51d3cc9 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (4)
text | 89554460-494d-5628-9ee6-75e510640a60 |  | textbox
label | b75c67b6-83e4-58a2-8369-d1f1ea0bfd9c |  | note | Measurement taken from straight edge to surface level
text | 341ba656-eb6b-5c2f-bc55-2f01362f6044 |  | textbox | Bound Left
text | a1e09f22-6491-5c3c-9a6e-f71546757b23 |  | textbox | Bound Left - Left:
text | 04ae6e54-04f4-5a1f-8fea-8de757612684 |  | textbox | Bound Left - Right:
label | f0938f92-b95a-5871-ab72-b8a096df6b67 |  | note | ––––––––––
text | c548068e-fc72-510e-b082-f4ba615dbdfd |  | textbox | Bound Right
text | accf95fb-b20a-5aac-aaa8-ec2a524265a3 |  | textbox | Bound Right - Left:
text | 096dfb33-535b-5743-b030-5f7c00a804cf |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (5)
text | 313b03e3-d6a6-5d80-83fe-055c655254f9 |  | textbox
label | c7d91e7d-8789-5785-8376-70f55dc6cc3f |  | note | Measurement taken from straight edge to surface level
text | b2e147cf-74da-5aba-90ca-643c620d0501 |  | textbox | Bound Left
text | ba32a4c2-b74e-5a0e-94cc-ae4fcf00aede |  | textbox | Bound Left - Left:
text | 5d467305-7f07-510a-8292-b7d87b99c9fd |  | textbox | Bound Left - Right:
label | 0c52e9ba-0fee-51bd-b833-2beddcc1a038 |  | note | ––––––––––
text | 22a3f6f9-f0fb-5425-a5cd-b651f96eb6e7 |  | textbox | Bound Right
text | c24a594b-d30c-5a84-baf3-73fb22c3abc7 |  | textbox | Bound Right - Left:
text | 6199480a-3767-57da-8b85-ff8ad933da93 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (6)
text | 82e1aa96-b86b-5358-895c-68442f026031 |  | textbox
label | c9a155f1-fc0e-5b01-ad76-b1552e6c05a1 |  | note | Measurement taken from straight edge to surface level
text | f9629db2-9cc3-5396-8578-d33aa3a5adaa |  | textbox | Bound Left
text | c359a22d-b3b8-5928-b595-d736ae5647db |  | textbox | Bound Left - Left:
text | 04fa1c72-bd96-5cab-877b-b1382b6813a0 |  | textbox | Bound Left - Right:
label | a325e96d-ad4e-5f6a-bb78-8f6c61fb7664 |  | note | ––––––––––
text | 746fb513-cb62-58ec-9382-b63c5c830e46 |  | textbox | Bound Right
text | ac24b8eb-cbf4-590f-8551-9c55d18daf9d |  | textbox | Bound Right - Left:
text | 35153a16-fb70-52d1-ac07-611af63f5d2a |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (7)
text | 4a5b7137-2a3d-5602-81e5-917bd3212b9e |  | textbox
label | 8299ac5a-c4a1-53f1-8e48-b06864e89bf8 |  | note | Measurement taken from straight edge to surface level
text | 7cec3a04-2582-5029-8d1f-5e2a6a063a56 |  | textbox | Bound Left
text | 1dc0beae-8a47-5b53-850b-6e05c31f9257 |  | textbox | Bound Left - Left:
text | d085fdb9-f4c9-504a-b1e4-c82f7c4e3009 |  | textbox | Bound Left - Right:
label | 31d60c69-5721-5843-b972-ea2a5c335552 |  | note | ––––––––––
text | 69a84a54-e7eb-556c-b822-522ce100d304 |  | textbox | Bound Right
text | b66d79e7-573d-5cfa-b184-c7248096b718 |  | textbox | Bound Right - Left:
text | 684e0ab1-e33e-56ae-9bb7-29e0987abc47 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (8)
text | ca1e2fa4-d589-50de-9404-d6de78707351 |  | textbox
label | 2f3f5fc9-63e5-5432-b821-3614c5e72e2f |  | note | Measurement taken from straight edge to surface level
text | cf154829-5061-5deb-985c-e5cb7d81ce06 |  | textbox | Bound Left
text | 4c7c9cff-e904-52cc-aa95-b6f9c27bc587 |  | textbox | Bound Left - Left:
text | 7e0e1cfe-a4cf-5800-9fe3-bb5f8b578e91 |  | textbox | Bound Left - Right:
label | 4046e219-2503-5371-9231-bd140b2617b1 |  | note | ––––––––––
text | 78c2dcc7-6ee0-50cd-84c9-e9eb0ffc124b |  | textbox | Bound Right
text | cd41cc5e-d12d-50ed-ac58-63dba25032a5 |  | textbox | Bound Right - Left:
text | 870d9d52-7e0d-5454-8ba1-2045e4929b79 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (9)
text | d2f29e9d-4f89-541c-aca3-4bddf3c0f022 |  | textbox
label | f25c0e24-0819-56db-8c28-1b2d1cd1d0b9 |  | note | Measurement taken from straight edge to surface level
text | 0b073558-02fa-5901-a754-be78f0c3d184 |  | textbox | Bound Left
text | 67548459-1277-57b9-8e1e-50e8e60e0fff |  | textbox | Bound Left - Left:
text | 6cc7f07e-e409-5c00-bf15-8892631fe245 |  | textbox | Bound Left - Right:
label | a8e063dc-5fa7-5afa-a507-02e54417ba27 |  | note | ––––––––––
text | 102317b9-0157-5b5f-9480-27fe3d0269cf |  | textbox | Bound Right
text | 4e73d8b6-5dcb-5aee-81c4-1c338ee79641 |  | textbox | Bound Right - Left:
text | 8ff216bf-faba-51aa-9bc9-4e2978009860 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (10)
text | 79616cd4-3496-59a3-9438-929a92f384dc |  | textbox
label | 994b769f-dfed-5830-ad01-10ad9e53a8a5 |  | note | Measurement taken from straight edge to surface level
text | b4bb3a88-8036-5db5-9386-2a3063b8165a |  | textbox | Bound Left
text | cee68034-fb59-5975-a410-b5abcee51824 |  | textbox | Bound Left - Left:
text | 526df30f-e038-5e93-a520-4b805358ff3a |  | textbox | Bound Left - Right:
label | 5438d4f9-accb-5482-9dba-52ce1deb88b8 |  | note | ––––––––––
text | db88c26c-6469-5b2b-b4b2-1e91bf6914f5 |  | textbox | Bound Right
text | fd09b895-b377-5a2d-ab2e-69f13c04d318 |  | textbox | Bound Right - Left:
text | fa495bf8-bbff-5374-ae7d-a14c98bdfeb0 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (11)
text | f44c3d79-fa8f-525c-9e6c-3a2bc743ade6 |  | textbox
label | dfc07bdd-6332-5e1a-a71a-02b5be60893e |  | note | Measurement taken from straight edge to surface level
text | fdfb65de-d817-56e0-bdb8-687cfbfad2e5 |  | textbox | Bound Left
text | d4ae5468-e751-525d-9f87-9e50c597b2b2 |  | textbox | Bound Left - Left:
text | 1c62eb48-c8e5-51c6-8fa6-c355c0ad43b3 |  | textbox | Bound Left - Right:
label | 6d9582ff-3f31-511c-a8fa-5e951bac37f7 |  | note | ––––––––––
text | f19bbdaf-a346-59e5-9717-3ff5ffc6c8df |  | textbox | Bound Right
text | 5fff06f0-7a7c-5f18-a011-fdab5144ee4f |  | textbox | Bound Right - Left:
text | d7d12a91-b030-583c-92b8-d373abe881c3 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (12)
text | 72d79e4b-3703-5d50-aa8f-19d4b28d979e |  | textbox
label | cfc0ba80-24c8-548b-a38d-dadee168fefc |  | note | Measurement taken from straight edge to surface level
text | 842458b8-10d2-573f-820e-312ed9582597 |  | textbox | Bound Left
text | f39c78df-da0d-5d9c-a9cf-488da3159e2b |  | textbox | Bound Left - Left:
text | e61d2840-9670-513e-94f3-3373af72f8bd |  | textbox | Bound Left - Right:
label | 4ee5b69b-d373-5c41-868a-07bb602b9e9d |  | note | ––––––––––
text | e089c57d-d6d1-5bd8-8ece-6258bd4db66c |  | textbox | Bound Right
text | 8c7d1125-a4a2-5b94-8f99-7af600314f22 |  | textbox | Bound Right - Left:
text | d607653a-1efe-53e6-a548-3f89e3f8e370 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (13)
text | 3ebd7162-a1ce-540f-a53f-5c6f39c89d79 |  | textbox
label | 377942d7-9e7d-5475-a706-217c51d03762 |  | note | Measurement taken from straight edge to surface level
text | 42cbbf92-843d-57d7-b831-e01dac9cf77b |  | textbox | Bound Left
text | c245a071-0db1-5c8b-805f-30009cf87fca |  | textbox | Bound Left - Left:
text | 19436b31-23bb-5229-b21e-472244036e15 |  | textbox | Bound Left - Right:
label | 32a19ad0-11c7-5c92-bc18-eb39dd436157 |  | note | ––––––––––
text | 26ba308d-9e3b-5272-af74-71845a8ddd35 |  | textbox | Bound Right
text | 14b9c5c5-4892-5b75-89d0-913542cd7f0c |  | textbox | Bound Right - Left:
text | b3bd42d1-9263-5a51-8d1e-2fc057570c24 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (14)
text | 7d5c42c0-42f6-52df-a084-5b557c03d407 |  | textbox
label | 9876efe3-8f39-5080-8d58-a72d39dee379 |  | note | Measurement taken from straight edge to surface level
text | 3d7b2c55-075f-5012-88dc-078ca1cdf7e2 |  | textbox | Bound Left
text | 8fa4f6cb-c7ca-5be8-85b4-fb9e497acb13 |  | textbox | Bound Left - Left:
text | ca383e9c-31bc-56ef-8b4d-98a3133dbfaf |  | textbox | Bound Left - Right:
label | 776dcd15-95a6-5d56-89f7-cd730fe951d6 |  | note | ––––––––––
text | 4bb26dce-b40b-5fbc-8068-73c34d1dcd2a |  | textbox | Bound Right
text | 924a39a4-883e-5a79-81c9-208b6921f29a |  | textbox | Bound Right - Left:
text | c79f2a04-e57e-5668-8024-63225887d9b3 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (15)
text | c3dd139b-4ed4-59ea-9251-b9132442c32a |  | textbox
label | ac915276-5488-59cc-9c94-824316d5b1ed |  | note | Measurement taken from straight edge to surface level
text | e63598ca-013b-5297-aafc-1a137aa1fa17 |  | textbox | Bound Left
text | ef23ca0e-45df-5dcb-97c9-986cadd49a9c |  | textbox | Bound Left - Left:
text | fbbc1a15-ddc8-5283-a1a6-167737567a96 |  | textbox | Bound Left - Right:
label | 6e365bdf-11c3-5ddb-89d6-61af2aa81a7d |  | note | ––––––––––
text | 9ac4cbc4-2a07-5ac4-9116-f9dc0a5a10de |  | textbox | Bound Right
text | b8044a39-a780-525e-b159-8c9dec7463e7 |  | textbox | Bound Right - Left:
text | 47ea4cfa-24fa-54f5-8964-ed3f865db6b1 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (16)
text | 6912e009-c12d-5336-b5c3-b6e53b54110d |  | textbox
label | ad9e2636-553f-5a74-9dae-0a031eeddfd2 |  | note | Measurement taken from straight edge to surface level
text | b87a78b8-911e-5bd2-88a7-7c51242be915 |  | textbox | Bound Left
text | 55d59cde-9f40-541f-8c86-57a0b75b2890 |  | textbox | Bound Left - Left:
text | 3d236a31-54c2-5908-a901-b8f2c92e2c12 |  | textbox | Bound Left - Right:
label | 8d07dab6-c759-5cab-8281-1349221f6612 |  | note | ––––––––––
text | fa38038a-138f-5e68-92a6-508ab4485e66 |  | textbox | Bound Right
text | 8e625185-cc8f-5b5b-8aee-e66c61b44245 |  | textbox | Bound Right - Left:
text | 54a8c159-4335-5648-b76a-99ecf539d5a7 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (17)
text | c865175c-4d36-5564-b5f6-878b02be916f |  | textbox
label | ffbc19c8-5491-5fd3-9351-99a61c76f0f7 |  | note | Measurement taken from straight edge to surface level
text | ed5fd678-e8f9-5535-ae20-5ad7d01756a8 |  | textbox | Bound Left
text | 82e4893d-268f-512f-9a48-32eb380dfdd8 |  | textbox | Bound Left - Left:
text | f4190b71-4067-5972-9df4-045a36c5a537 |  | textbox | Bound Left - Right:
label | eb5298d1-01cd-505e-a814-ef519f99d723 |  | note | ––––––––––
text | fccad95f-78ba-5569-b33c-7f30290eb958 |  | textbox | Bound Right
text | dff5edeb-682a-5eee-a281-c8d97f42fa19 |  | textbox | Bound Right - Left:
text | 627e08f0-83ca-503b-aea5-a91e97fd001f |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (18)
text | c3b82a09-91d6-56ee-ad0b-6fc8e586f48f |  | textbox
label | 63d9c208-26c4-5486-98e2-8c9a3fd80c81 |  | note | Measurement taken from straight edge to surface level
text | 2c03c718-dcc8-512e-b790-1694695b9eb0 |  | textbox | Bound Left
text | 4d23b0c8-44bf-5890-9bff-c4d867fc0636 |  | textbox | Bound Left - Left:
text | a650d640-c7a0-512a-b443-f48aee6d51cc |  | textbox | Bound Left - Right:
label | fa79ca04-8536-5a0a-b44e-bd8c59500dcf |  | note | ––––––––––
text | 89997ddb-4eb0-5e91-9e91-f789d71b2d65 |  | textbox | Bound Right
text | 7018c26c-a1dc-5386-971e-9a15db2e3a02 |  | textbox | Bound Right - Left:
text | 7dd261de-a271-56f2-9b8d-b0aac7daaea1 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (19)
text | 16c6a6e6-7fd4-524e-96e8-2d0cd5c92687 |  | textbox
label | fef418f1-1b62-5bcd-be91-7c153a2c1d0c |  | note | Measurement taken from straight edge to surface level
text | 5b90e01c-dbd0-5fec-b450-c34152d04763 |  | textbox | Bound Left
text | 1e956c38-a1e2-57a5-98c6-031c6698fd38 |  | textbox | Bound Left - Left:
text | c084ab8d-b648-5265-a906-1eddd6dae989 |  | textbox | Bound Left - Right:
label | e6b99129-d32e-5875-9282-e9b1a5ee7372 |  | note | ––––––––––
text | a44c1576-3d17-5809-99f7-b4b852ea30b6 |  | textbox | Bound Right
text | f2ed8dd3-b57e-539e-8018-91d0a8daf2fc |  | textbox | Bound Right - Left:
text | 853fc421-8cee-5dfe-aa63-0d9fd78c678f |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (20)
text | 2673b637-f07f-5969-a3fa-613880c7d53b |  | textbox
label | 99b495b2-9b5b-59c5-b679-3232a6d71a53 |  | note | Measurement taken from straight edge to surface level
text | 89e01413-66a1-54f5-b78b-c82ee146eada |  | textbox | Bound Left
text | 53bdb546-14c7-5132-99b6-72ffdc847dc7 |  | textbox | Bound Left - Left:
text | 0768300a-dad8-5402-926c-f1bf3703cfc4 |  | textbox | Bound Left - Right:
label | 5006e100-a11f-53cc-a86f-0b5e66740d4c |  | note | ––––––––––
text | f71cf138-69e9-54ff-ad00-f8c3d9c4604f |  | textbox | Bound Right
text | 8f57dc20-af6b-5ff3-a59e-77485314085e |  | textbox | Bound Right - Left:
text | 6a342f2b-9367-5acc-a4ec-1cb20a82ae7d |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (21)
text | 0500afae-0b81-5e2a-8dc8-7684c1927cb1 |  | textbox
label | e216d8f1-ee16-54c0-b6ff-259c57e3dfa5 |  | note | Measurement taken from straight edge to surface level
text | 67e95544-3620-5d45-b307-37edfb217835 |  | textbox | Bound Left
text | 732c2a93-5778-5dc5-9103-769978755eb8 |  | textbox | Bound Left - Left:
text | 0d91a9fd-1794-5698-a87a-2357b9069196 |  | textbox | Bound Left - Right:
label | a91e0c79-a3e0-52b2-b45b-9f8ed0bdaf5f |  | note | ––––––––––
text | 030b1e65-a634-5726-bc07-1d56e68efb38 |  | textbox | Bound Right
text | 7627886e-78ba-50ce-85ae-ae366c4ff33e |  | textbox | Bound Right - Left:
text | 42892d95-62c1-5863-aaff-57abab2d4bf6 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (22)
text | cf362460-5af7-580d-91af-5143372f04bd |  | textbox
label | e8904f2a-4186-5eb1-bd01-fe9a61c12dfc |  | note | Measurement taken from straight edge to surface level
text | 485b6a96-31f3-5fd0-86a9-bc514c0fb548 |  | textbox | Bound Left
text | 7522863d-49ad-5b3c-a825-e2b5449448ea |  | textbox | Bound Left - Left:
text | af07cec1-3514-5936-b870-9f56e776d855 |  | textbox | Bound Left - Right:
label | eb8c86fa-88bd-57d8-a3d7-a644e97c4287 |  | note | ––––––––––
text | 4659965d-0474-5817-b5bc-2a9e99246086 |  | textbox | Bound Right
text | eea40594-e0e1-53f7-9f60-00bcc3941e6c |  | textbox | Bound Right - Left:
text | 5fb522b5-a581-579e-a68b-f33e783b9a87 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (23)
text | 50464358-b393-5952-9612-0fe6138f0027 |  | textbox
label | cb80555d-5edd-554d-a250-ba966faaca06 |  | note | Measurement taken from straight edge to surface level
text | bc10ab7f-5052-5549-b787-bee7f2c95910 |  | textbox | Bound Left
text | 2e4d1a1a-f73b-5149-8161-bbad8eafb3b3 |  | textbox | Bound Left - Left:
text | bd3c98ff-03a6-5283-b541-9a68f0336cb3 |  | textbox | Bound Left - Right:
label | 8201d1f4-b6f0-5f94-b731-d22922f889bf |  | note | ––––––––––
text | 34826fcb-fbd5-5d4a-bae1-4257ed7b4799 |  | textbox | Bound Right
text | 1d6e5be1-ed00-5372-96e9-8b0593beaedd |  | textbox | Bound Right - Left:
text | 660ed061-bffb-5939-a8eb-ac912f202f69 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (24)
text | 03106092-3040-5073-9d0e-3203a8ff5691 |  | textbox
label | 2b73f6ac-080a-53a9-8821-97d0b92927e9 |  | note | Measurement taken from straight edge to surface level
text | f08f5875-7724-511f-91de-06e80b8c1cd8 |  | textbox | Bound Left
text | ee83aad4-57ae-5364-a9dc-cd9809bf9fae |  | textbox | Bound Left - Left:
text | f4f29359-440b-57c4-80fd-cc9a997bd750 |  | textbox | Bound Left - Right:
label | 66c3c302-4f7f-5f24-adfc-e53dd7e40c11 |  | note | ––––––––––
text | ad91f351-d923-55da-ad7d-8f31bfcf8c12 |  | textbox | Bound Right
text | 1d7e708d-6a1b-5d9a-baf7-b49aae719428 |  | textbox | Bound Right - Left:
text | 4cbfe470-fa6f-5804-add1-6fac674f99ac |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (25)
text | 08e8a697-89ac-5550-8ce4-91875b60c48c |  | textbox
label | 9501a61e-3df4-5f18-9c8b-c52eb60b0444 |  | note | Measurement taken from straight edge to surface level
text | 08742e4e-52c4-5b5a-9abf-8f624454e114 |  | textbox | Bound Left
text | d61e72b1-cfad-5065-8956-86936914aedb |  | textbox | Bound Left - Left:
text | 2f32e35a-1e6a-5d0a-b801-aa812e806a3d |  | textbox | Bound Left - Right:
label | 01f1993c-8a91-5ff3-8d44-760e475eee58 |  | note | ––––––––––
text | 01971b74-87df-52ff-8396-7f7d1726b27f |  | textbox | Bound Right
text | 101e5b87-d82a-5e7e-b553-86bb7996bce6 |  | textbox | Bound Right - Left:
text | f0f59bbe-b3e9-57f2-b659-98a546224756 |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (26)
text | fb1e97ef-9141-522a-b821-02b24c310322 |  | textbox
label | c2dea588-3055-53f1-a306-c9653d83d1c8 |  | note | Measurement taken from straight edge to surface level
text | 5358f613-f710-5f78-a2d7-29ac9d4837cc |  | textbox | Bound Left
text | 492f09ab-421a-5666-9d2f-76f7b9e61be8 |  | textbox | Bound Left - Left:
text | 6c402ef1-be84-54fc-9fa5-d8b778a6dea9 |  | textbox | Bound Left - Right:
label | 3408056b-3f68-5ee1-b919-47e8978df5c9 |  | note | ––––––––––
text | 281e1eba-0a78-5f96-8340-07e9d5bd075e |  | textbox | Bound Right
text | 0ecfa564-5501-5ced-9f26-d19443c114c5 |  | textbox | Bound Right - Left:
text | e5201837-8aad-59f6-8d70-ec3000bb6cab |  | textbox | Bound Right - Right:
checkpoint-no-status |  |  | checkpoint | Chainage (27)
text | c18adb20-ebc6-5636-a15e-401091151199 |  | textbox
label | bdbbc1d7-a7f0-572e-9c38-6f48c4af50ac |  | note | Measurement taken from straight edge to surface level
text | f0ae7e6d-892a-59b6-8fe4-cfddae09934a |  | textbox | Bound Left
text | 9bd9361d-d582-5a6d-b08d-f61767644ea7 |  | textbox | Bound Left - Left:
text | e554141e-da0e-540f-9944-17b404283f43 |  | textbox | Bound Left - Right:
label | 68ed063a-c5a8-5b24-8f94-97e6ea8a95f9 |  | note | ––––––––––
text | 94ab1d7e-b9b6-5dee-93c8-473a6b67436f |  | textbox | Bound Right
text | e8ef4c10-35b0-564c-984f-7f8ff7b87a27 |  | textbox | Bound Right - Left:
text | bfa54055-ed97-5f9e-87ff-2a0b79328e30 |  | textbox | Bound Right - Right:
checkpoint-group |  |  | section | Cross Fall Check
checkpoint-status |  |  | checkpoint | Cross Fall Check:
label | d8e4964c-656a-5fc9-a2c1-d36dde5a7630 |  | note | The cross fall between 2 points more than 2m apart, traverse to the centre line shall not depart from the design cross fall by more than 0.5% (Measurements to be undertaken at a frequency of 1 every 100m)
label | 022797cd-2b3a-512d-818d-42653aa4998a |  | note | Note: Left and Right when facing increasing chainage.
checkpoint-status |  |  | checkpoint | Chainage
text | 272e6e65-8f89-566f-b2b2-12f859c64043 |  | textbox | Bound
radio | 0c5a0392-50dc-5fc6-a255-838d7f639922 |  | radio | Left Lane / Right Lane (Select one) | Left Lane,Right Lane
checkpoint-no-status |  |  | checkpoint | Chainage (1)
text | 08088820-52f3-5640-bfb5-ee15e01cca8d |  | textbox
text | 75c3476b-4415-5e99-8ea7-2b3ba7a20f46 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 52076ac4-3a7a-5bf3-85de-7e83b8fb5ef9 |  | note | Cross Fall tolerance <= 0.5%
text | eaccadd6-9630-5661-9f72-fa8b88bd49cd |  | textbox | Calculated Cross fall
text | ccb96cc9-b46e-565d-9e80-13e73f0779ac |  | textbox | Design Cross fall
button | a3d98d62-9f19-51b2-9fde-92dff8179edb |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (2)
text | 29889a57-502a-5b56-a6c9-972a65440a7e |  | textbox
text | fbaac1cd-a18f-5846-ab21-7dfc9ef7df79 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 4ed4a240-2121-55f1-9984-42f808895478 |  | note | Cross Fall tolerance <= 0.5%
text | 2e27e20e-a432-5f25-a6fe-f3067e317fec |  | textbox | Calculated Cross fall
text | f90bfd05-59ce-5e3d-8923-6341597b6398 |  | textbox | Design Cross fall
button | 7bfb4fa1-eb93-5473-afd0-a66d14edd50d |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (3)
text | aa64c409-ca75-5fc5-b875-ec438ddc24bc |  | textbox
text | 8f8b798b-949c-54f4-a31d-755245b68d5c |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 8af1bc10-98e5-53b1-bb08-3775522e5021 |  | note | Cross Fall tolerance <= 0.5%
text | 2dca969e-62ae-5836-8af2-a1af7308e6c0 |  | textbox | Calculated Cross fall
text | d372cf17-04b5-53c9-a627-a27892ca448e |  | textbox | Design Cross fall
button | 01f3990d-85f0-52c4-b321-c3e5233a54d5 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (4)
text | 98c85f49-8c42-54e2-b317-5de5e4f2e099 |  | textbox
text | 6e1ce8f8-1dd0-507c-a54d-295472552e71 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | e5808b0c-f9cd-5a70-af4b-28521fcf9ed5 |  | note | Cross Fall tolerance <= 0.5%
text | bed26441-3abd-58b5-a41c-bd53c9d1acd5 |  | textbox | Calculated Cross fall
text | a1f27b75-190d-5bab-b560-9adc4750f0be |  | textbox | Design Cross fall
button | a1b6ca09-848b-5855-8372-5b54cb7d8a68 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (5)
text | 68e3933d-625e-5b24-8f16-f27dbd4d0cb7 |  | textbox
text | 3c53eafb-547a-54c7-b1bf-beec90257a57 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 72822049-02f8-5959-853f-cc041681b192 |  | note | Cross Fall tolerance <= 0.5%
text | ee8f9add-89bd-5140-a4e2-ff70e5141914 |  | textbox | Calculated Cross fall
text | c37cb6e7-a60d-5008-a667-a91acc35b73c |  | textbox | Design Cross fall
button | 54c3b9b3-75f8-59b3-ad31-2aa52119c698 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (6)
text | e3b69d90-5928-5252-9af1-796489438288 |  | textbox
text | 15125779-8e12-5dd8-bb64-b5f75094ddf7 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 43020a21-c2b9-5569-88bb-284e12b3d30b |  | note | Cross Fall tolerance <= 0.5%
text | 1487b080-9541-53b7-b2a3-bd04c8db945f |  | textbox | Calculated Cross fall
text | fd7b1a25-c660-51f0-8d0a-36178ac8510f |  | textbox | Design Cross fall
button | efbb42c8-92d7-50c6-b1f6-9aab9de3aaea |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (7)
text | e087cae5-3473-542f-b161-d84308f182d4 |  | textbox
text | 99fe54ac-e3a0-5bce-a47c-e1f83e1dd113 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | e77d71df-f77a-50b6-a39f-bacf86484b97 |  | note | Cross Fall tolerance <= 0.5%
text | baedd67f-7f26-5136-8f2e-07cfc0e122be |  | textbox | Calculated Cross fall
text | db22bdf9-5633-5a28-b308-7be849c3baba |  | textbox | Design Cross fall
button | 1674cd11-d265-55e2-8ec0-904a8a0dc2f8 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (8)
text | 6ec10509-3a3a-5a52-a282-67de7026f387 |  | textbox
text | 3df7e334-b88f-54a7-9e0f-0dbbaacc3f38 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 0f97ddaa-3797-5d78-bdc1-5d1d8219d7fe |  | note | Cross Fall tolerance <= 0.5%
text | d6dd241b-b024-5e32-8628-9ec4fad946fa |  | textbox | Calculated Cross fall
text | c089b570-d8f2-54c6-a590-38537697f3f9 |  | textbox | Design Cross fall
button | e2006905-9c13-5787-a843-004a54dbdc2c |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (9)
text | 64378021-9c30-5c7a-9467-25c856b2809e |  | textbox
text | f8043bbf-75ec-5b57-ab05-3909dc2ca256 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 620d7dbf-b36d-5a7e-be41-869c0bc02c0b |  | note | Cross Fall tolerance <= 0.5%
text | 3c139048-9a4e-57d7-8816-547479ecebec |  | textbox | Calculated Cross fall
text | 606d002e-137c-59e6-9903-b8d8654c3e01 |  | textbox | Design Cross fall
button | 83c7086a-6f9f-544f-9a51-c0252562d8d7 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (10)
text | 2d20333c-d1b3-5a95-88e5-9a9d9409c4e1 |  | textbox
text | ba568527-5657-59c9-973b-cf1997d7bfe3 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 7833c52a-434e-5664-8c59-1907afdc6100 |  | note | Cross Fall tolerance <= 0.5%
text | 2478ea78-9524-5e47-a2fa-5553a460aeeb |  | textbox | Calculated Cross fall
text | 71c02d3d-eb7f-5e82-8d0d-534b088795e9 |  | textbox | Design Cross fall
button | 1e982541-2320-501a-80a6-e54fa9055d6e |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (11)
text | 98fff139-0781-5db9-a14f-87cf3c5b5458 |  | textbox
text | 3111335c-bc84-502d-b878-b8553527c468 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | cf9a5d6a-60cf-538b-90c4-1d71bcf1cdcc |  | note | Cross Fall tolerance <= 0.5%
text | d8dd660b-d41b-5008-898a-2769894286ce |  | textbox | Calculated Cross fall
text | 62dd94b3-78a4-5400-8d02-f53ee463a6bb |  | textbox | Design Cross fall
button | 331777c1-df43-5d0c-9700-8b5686ec64c9 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (12)
text | 3607d62b-03ea-5c4a-9a01-54f7c573755e |  | textbox
text | 93fdf856-e1c8-5090-b376-4d7cafc46539 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | ff33bedc-4e19-59f5-88d2-8c0ac44b2e99 |  | note | Cross Fall tolerance <= 0.5%
text | 3d3437b5-e742-5abb-9f1f-127d18dd66b6 |  | textbox | Calculated Cross fall
text | 9b59aac5-afde-532f-b398-fc78fa6da182 |  | textbox | Design Cross fall
button | 5b124413-6b31-5d10-b7ce-0e0dcbf2b25e |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (13)
text | e5306d4c-95bb-5b2d-a860-fa47547bb3fc |  | textbox
text | 257c54e4-eabf-5b69-bb66-cc4fe6e00dff |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 74f38645-9112-5cce-8a49-50efce7869b8 |  | note | Cross Fall tolerance <= 0.5%
text | 6055a3f7-1f65-5de0-a5ca-d129cd374d13 |  | textbox | Calculated Cross fall
text | 569f77e2-4fe3-5886-a19a-f6b78281a515 |  | textbox | Design Cross fall
button | a45a5de3-45fa-53db-a76b-38178f9cc5f5 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (14)
text | 8d4d7b40-d9ed-56db-a106-d31ceb107651 |  | textbox
text | 38a1fc29-5a04-5a91-9d8c-d09a72c453d3 |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 1f5aff5c-6a78-59f0-8ba6-3d2125ca45bf |  | note | Cross Fall tolerance <= 0.5%
text | ce324c1f-bfc3-52bf-8e00-128706084422 |  | textbox | Calculated Cross fall
text | a3824bae-7f5f-531e-ba19-9b547f7200dc |  | textbox | Design Cross fall
button | aa5647c7-4030-5b1a-8060-81f9f535016d |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (15)
text | 12c18a7d-1154-55c5-b9f8-082d92f87758 |  | textbox
text | 706311a5-0c84-539c-884f-47a6021cd1bf |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | ccf7cd91-0ff3-5cff-a1c5-606fb829c3fd |  | note | Cross Fall tolerance <= 0.5%
text | 5dc8bc9c-a3a4-5f26-a22d-479c6738f7c1 |  | textbox | Calculated Cross fall
text | 0a784fc9-015c-5ee8-b59e-4196704eb028 |  | textbox | Design Cross fall
button | db305a12-c563-516a-92a6-e30d220ee801 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-no-status |  |  | checkpoint | Chainage (16)
text | 98608919-ac25-548e-a8d8-2057848fc2f7 |  | textbox
text | 23bd8a86-f501-5538-88bb-bdaae1e908bf |  | textbox | Measurement taken from straight edge to surface level at 2m from known point
label | 524c5fd6-bc62-5cb1-b5ca-a176505fd459 |  | note | Cross Fall tolerance <= 0.5%
text | 2ed1c7e7-ca12-55b8-a63a-ebdd00028ae6 |  | textbox | Calculated Cross fall
text | 4cecf759-f8b0-586c-9739-3cdaf18a0849 |  | textbox | Design Cross fall
button | de20930b-9e66-5b94-8449-d6e141e78978 |  | button | Within Tolerance (Y/N) | Yes,No
checkpoint-status |  |  | checkpoint | Pavement Construction Test Results Spreadsheet – Tests Completed, Checked & Signed
checkpoint-status |  |  | checkpoint | Surface Finish Check
label | cfca92f6-929e-505c-9a20-456caa94e3eb |  | note | Site visual Inspection carried out by CPS Engineer & Construction Manager after sweeping and prior to sealing taking place.
label | 56e6f8bd-2fc6-5c3d-a415-9ff7f9ae49cb |  | note | Checking that the large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping.
checkpoint-group |  |  | section | HOLD POINT – Final Surface Sign Off & Approval given to Seal Area
checkpoint-status |  |  | checkpoint | Final Surface Sign Off & Approval given to Seal Area
text | 82d33fad-3cdb-5220-8943-bb413135d78d |  | textbox | Name: Site Engineer
date | 68defed2-0ff4-5fa0-b90f-cbb08bee0b39 |  | date | Site Engineer - Date:
text | 66a06c34-4e97-549f-8466-d1f98d1daf47 |  | textbox | Name: Construction Manager
date | 6c41a01a-f42a-58dc-a8e1-b9b2192a44d7 |  | date | Construction Manager - Date:
text | 495caa10-fc3c-5a6e-903e-a36a71334a45 |  | textbox | Name: CPS Engineer
date | b639b622-cd6e-5381-9443-5d23c8b91089 |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | ITP - F3001B - Te Puia Dropout | itp |  |  |  | Yes | ITP - F3001B - Te Puia Dropout V2 | d6eca4ab-a250-43f8-b33d-7c027e0b5123
checkpoint-group |  |  | section | Section 1: RECEIVING INSPECTIONS
checkpoint-status |  |  | checkpoint | Project Site reps.
text | d5886eb3-a0de-5c61-921b-d30af2fbf729 |  | textbox | CPS Eng.
text | bae783f7-d269-5d23-999c-b42af6f08699 |  | textbox | Site Engineer
text | 7ca7109d-b0ca-5f9e-b2e6-fd77ddc4d7ff |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Rock Armour (D50=450)
label | 2efad191-92e2-5f3a-a888-fe001effe14f |  | note | ACTION (Hold, Monitor, Witness) - W
label | a93e5f66-7e0d-52d5-971a-0822c653d1c0 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | 65236aa0-90e6-5f1f-9c88-dcbb1f2b88a1 |  | note | Frequency - Prior to commencement
label | b072a4ad-2c07-548a-9499-b644f49b6ecb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 706525fc-135b-5755-89fe-535780952c20 |  | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious materail. Shall have a D50 of 450 with a minimum specific Gravity SG of 2350kg/m3.
label | 9f9414e7-179e-50c9-89b9-cfafea24efe7 |  | note | ○ Traceability of materials is required
label | 8735c40e-d22e-5a8c-a712-559b9c81298b |  | note | Records - Material source test results, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.2 - BulkFill AP65 or GAP65/GAP100
label | 4831e455-3774-531c-9c51-7e18c56eeec1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 94c285c2-727e-5b2f-8fad-06be49e5c555 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | 2c6406b0-8b8d-515c-afa3-ded7b052d44f |  | note | Frequency - Prior to commencement
label | a57aae86-37a1-551d-9d97-38dacf1d0f74 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 31b99d8f-4b28-5650-a06b-f069550175f9 |  | note | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
label | 654f126e-4009-5869-82e7-0639a4c005cc |  | note | ○ Material source testing
label | e8da746e-fca7-57a0-b041-592acf263bdf |  | note | ○ Traceability of materials is required
label | ce03e7b2-888f-537d-85a9-dfe8f262ecc3 |  | note | Records - Material source test results, Delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Class D A39 Geotextile
label | eb3c85d5-c7cd-51cc-93c6-9780893699a5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 32293d84-98aa-5f8e-9b4a-5a415ed2c725 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | 41279df7-1183-575c-9791-c38fb7460287 |  | note | Frequency - Prior to commencement
label | 075c13cb-d0a8-516a-bbc5-4d898c6ef833 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 1edfa198-df8f-55e5-9d3f-746e9ce35216 |  | note | Conformance Criteria - On dry bed below fill
label | e77e60a7-4a5d-51fe-8474-336ffa92a226 |  | note | ○ Comply with NZTA F/7
label | 702d1850-5ec5-52c0-935e-57cbdb07b409 |  | note | Records - Material certificate(s), Delivery dockets
checkpoint-status |  |  | checkpoint | 1.4 - TNZ F/2 drainage material
label | 2b3b2145-ccef-5ef0-87cb-197976fd1cfc |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6460b965-ab28-5b06-a43c-143553b14fda |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001, TNZ F/2
label | a48b02be-73fc-5b30-88c8-9d47a9b9d41d |  | note | Frequency - Prior to commencement
label | 77b7796a-640b-5aae-80df-60d2c0abd7e5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | f2c36c2e-b630-5d08-b702-133405225cd7 |  | note | Conformance Criteria - Comply with TNZ F/2
label | 6e2cb734-6e63-5fab-aac6-4a271d08cb2c |  | note | ○ Traceability of materials is required
label | 631dd9f5-cd29-54fd-b325-030f2100f413 |  | note | Records - Material source test results, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.5 - Megaflow strip drain or drainage blanket for seepage if encountered
label | 24043b29-1917-5891-9cb0-ee2dc9bd1d8c |  | note | ACTION (Hold, Monitor, Witness) - W
label | a5c320ff-ce1a-5d03-9f13-0e662a8fc012 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | 8d3d2cbd-ed40-5c36-a9a2-f479ea3bf373 |  | note | Frequency - Prior to commencement
label | 189e2faf-74c6-5ca8-ae7b-de70bc0dd7e9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 5e8385b9-49e4-58ba-ae6d-eb68c2cb5c52 |  | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
label | 74fa60f2-83d5-5f74-a5f0-4c8e6140caa8 |  | note | Records - Material certificate(s), Delivery dockets
checkpoint-status |  |  | checkpoint | 1.6 - 110mm Novaflo drainage pipe
label | fb978551-3cea-5a47-baa0-37a7969f6304 |  | note | ACTION (Hold, Monitor, Witness) - W
label | bd71725a-1d6e-54ba-abe0-916860cca927 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | 85819755-63f1-5a4f-9cd5-b03ca8f11403 |  | note | Frequency - Prior to commencement
label | 79400abf-ebbf-5468-bbdc-e18f3b6e8de5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 85744991-173d-5f9c-be99-0e1ef7746d02 |  | note | Conformance Criteria - Comply with TNZ F/2
label | d8a4f37f-faed-5968-8f79-21e2aab3cc76 |  | note | Records - Material certificate, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.7 - Biocore erosion control matting
label | 040045b0-3555-5cb8-bee8-929356def80e |  | note | ACTION (Hold, Monitor, Witness) - W
label | f5597053-1948-535f-bb09-69cfc6ed04b1 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | c35dd2fc-6ae9-5bc1-bc8a-ee736cba8beb |  | note | Frequency - Prior to commencement
label | 959e8c3d-75fc-5981-b574-a4992a8f1d3e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 86c98595-dc53-5d6b-b75c-3c38537766bb |  | note | Conformance Criteria - NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders
label | 5d593ebe-0950-58d7-b9f1-132628f737de |  | note | Records - Material certificate(s), Delivery dockets
checkpoint-status |  |  | checkpoint | 1.8 - Enkamat 7018
label | ce9c48a5-f190-561e-93b8-4d8fddbaa380 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b49111c6-049e-5580-be46-14d8ef5ca081 |  | note | Specification/Drawings Reference - Buttress typical details and F3001B-DS-GT-RP-001
label | b30aa0f8-92d5-54a4-b866-123efde2a14e |  | note | Frequency - Prior to commencement
label | 5cc3c0ef-ce25-583a-9412-fb94494f0aa6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 5923c629-5560-5cdd-9bcc-f572c2b98a76 |  | note | Conformance Criteria - NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders
label | 0c1be551-040c-5285-a5d9-e3c4bb88cf19 |  | note | Records - Material certificate(s), Delivery dockets
checkpoint-group |  |  | section | Section 2: IN PROGRESS INSPECTIONS
checkpoint-status |  |  | checkpoint | 2.1 - Survey Setout
label | 2c6af61c-4d7c-5922-84d9-fc97da36b0a4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a44540ac-8d79-58b2-b082-2dfb9ee70b16 |  | note | Specification/Drawings Reference - Consistency with Construction Drawing
label | 245f2761-65e2-5c6e-9ebb-21bfbc36818b |  | note | Frequency - Prior to commencement
label | 0834b667-0b05-55d6-a8b3-71b3f4e134ec |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | ee72cd15-fbe1-5c15-9c36-6c0a716cdfe2 |  | note | Conformance Criteria - Set out extents of fill and check against design drawings
label | dba849cd-216c-5f96-96c7-e1c3c0dd7d59 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | d00fdfb6-9470-511d-93fe-39a5ecb142d6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 154733fc-f4c4-5789-8c09-3c6975db5845 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | eeaf5627-81de-5dd1-a8c2-812e497665f1 |  | note | Frequency - During Construction
label | 00f602ae-01dc-543f-b8ae-6495b87a3379 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 7925ccb3-df6c-5cd9-96fd-da53d14f930a |  | note | Conformance Criteria - Remove and clear the vegetation
label | ce65565f-9801-5688-8401-48398d39d8e2 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.3 - Subgrade Inspection
label | 3f34c1a7-c4df-5732-a75a-fdf70427b9be |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1d798224-c504-56cf-81bb-f1fad579d0a9 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 4b1df22b-5ff4-5af6-ae72-7eb4c7175274 |  | note | Frequency - Per area as required
label | 886aab3e-c0b3-5594-bf1d-7ebd2ce80550 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Geotechnical Design Manager or representative
label | cbc261ef-2982-5449-a38b-67daa049bc7d |  | note | Conformance Criteria - Inspect fill foundation.
label | 834627b1-ad12-5926-ac77-33db0059bbfb |  | note | ○ Fill foundation must be approved, in writing, before filling commences
label | 2afa4c7d-76fb-52ce-8f53-f0aaa9102eb7 |  | note | ○ CPS Engineer - to determine any testing requirements here
label | decbc955-c5ff-5e7b-bef5-b6f6b4d66938 |  | note | Records - 1M Scala checksheet, CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Ground Improvements
label | 6feb87ae-c63a-5727-bb51-c66d3c25b74e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 86300ed6-823d-57bb-a36d-b1cd271134d7 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 2145d0c3-0e3b-5ddf-b72a-cc1d9613cb19 |  | note | Frequency - During Construction
label | 7581ced4-6d66-59d5-ad4b-e796d7ff7bfe |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | d15431b8-2fd9-536e-b35b-c9f72f58bb79 |  | note | Conformance Criteria - Any area that requires Ground Improvements must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence
label | 1346da4e-c4cf-54fa-86e4-57b9095bf8d0 |  | note | Records - Photo's, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Class D (A39) Geotextile installation on the excavated face
label | b8486f92-3009-5058-acb7-a876885d2465 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8b50b391-8ed2-5679-8ca8-9eea19b66010 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 83a3b3d7-ece8-5088-bd61-18b7ab017617 |  | note | Frequency - During Construction
label | c5c2a0fd-fc43-52de-9d48-9fb7e9da15cd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 11c55e9c-31a1-5cb6-a699-3c42919f412b |  | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill.
label | 26b1cb0b-d88c-5440-b1b0-377f9ac001ac |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.6 - Sub soil drainage
label | 615e52b0-3922-511c-9d54-1e733d4c2b0c |  | note | ACTION (Hold, Monitor, Witness) - H
label | d3ec1b92-8253-596b-852f-6cc562b69a1b |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0002, TNZ F/2 or approved equivalent. CPS requested a 110mm diameter nova flow drain around the perimeter of the works
label | 0e37120b-6d1c-5e53-aeb0-6fdc6bf2eacc |  | note | Frequency - As works progress in agreement with the CPS Engineer
label | f45807c4-7a1b-5e05-8f4c-824f65b047c1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 81f9706f-ebfb-526d-97b0-9f4ee8d77af1 |  | note | Conformance Criteria - Engineer to assess suitable drainage location and confirm drainage positions on site.
label | 69edf05d-78db-5be7-b05a-9d4f490e7481 |  | note | Records - Photo's, Drainage Line Record check sheet (CS-4025)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Megaflow strip or drainage blanket installation for seepage if Encountered
label | 95cd155a-340f-5289-8ed1-5e003d53145d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7051c6bf-6253-5d2d-bb8a-573a7f5d23f6 |  | note | Specification/Drawings Reference - Buttress typical details A and F3001B-DS-GT-RP-0001
label | 15fbf63b-0dcd-5146-bf02-941bedf24121 |  | note | Frequency - During Construction
label | 3d2d5f62-85e3-58ff-a110-0cd7ccd9df15 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 498dca08-2c80-55ef-8875-b1bb70730803 |  | note | Conformance Criteria - Installed in accordance with manufacturers recommendations
label | 2d9df7f3-ed6b-58be-a86f-86e717266224 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.8 - Bulk Fill Placement
label | 85dee485-46b8-5991-a1f5-53a9488e65d0 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 95e787ff-46fb-5a2e-abe1-3d4e743b273c |  | note | Specification/Drawings Reference - Buttress typical details A and F3001B-DS-GT-RP-0001
label | 1e9ad25f-d1a4-51ff-a869-c143a9f61c3e |  | note | Frequency - During Construction
label | 05bb11a1-4e92-5b25-8bb7-8d7ae16d3e01 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b8df0f9a-cf1c-5d82-8282-0b067f607b70 |  | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control. Fill must be placed on dry subgrade
label | 647cad54-1dd3-53d7-8d56-e4b8b7a184c1 |  | note | Records - Photo's, Bulk Fill Earthworks Check Sheet (CS-4020)
checkpoint-status |  |  | checkpoint | 2.9 - Bulk Fill Compaction
label | e457a3c1-23c6-51f6-be4a-499e86d85de2 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 294b20c1-fefa-5294-8f74-696dc4619651 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | dd254345-2283-5c8a-8ab3-c79b3b2a9e81 |  | note | Frequency - During Construction
label | 8b13bce4-ab62-5ea8-b0c1-756a9c07673b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | 05240f67-5347-55e2-8605-1e1fa296115b |  | note | Conformance Criteria - A target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3 CPS Engineer to confirm number of tests / lifts to be completed
label | 5336a973-78cd-5d12-8d58-4f0741eb977f |  | note | Records - NDM test report
checkpoint-status |  |  | checkpoint | -
label | 0c068ee2-a4dc-5daa-bee5-15fa1fb845a3 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1178116a-e1d0-5574-a6b4-7132a6b93781 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | c49587a8-aab8-5a68-8655-9b3f44b74339 |  | note | Frequency - Every lift/layer
label | 5e72fab6-53b0-5b6b-9101-df39325e5212 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | 5dc78e36-9e65-5e50-b8ed-204f404a21f8 |  | note | Conformance Criteria - CIV>=25
label | ec942465-645a-506e-9748-b98f054956e7 |  | note | ○ Shall be carried out for each lift/layer and recorded
label | 842ffe63-6ae8-5a0c-98d4-da0476004c90 |  | note | Records - Clegg Record test sheet (CS-4037c), Clegg calibration certificate, Photos
checkpoint-status |  |  | checkpoint | 2.1 - Form and cut fill batter as per design 2H:1V
label | e3b6bcb3-e47c-58a4-bb67-9cbb98f71c5a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 13adac06-f0e2-5b3a-9cb8-4dfcffddd604 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 3a1555a9-80e6-54ee-a1a4-855b985dd024 |  | note | Frequency - During Construction
label | 27a2186b-9bd0-597e-ab46-b8ca46d3e300 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b509a875-62a4-5e5a-b17f-14d437dd914e |  | note | Conformance Criteria - Erosion control matting to be placed and pinned on the face of the fill in accordance with the manufacturers recommendations
label | 2f986d59-913c-5cf8-8c22-81062e7e4257 |  | note | Records - Site inspection on completion, Survey as builts
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11 - Rock Armour (50-450dia) placed on the toe of the slope
label | 56f83237-cb9d-5aff-8c37-de868fdb41db |  | note | ACTION (Hold, Monitor, Witness) - W
label | e6e173cf-b4d4-5314-8fa1-b6ff7ab0dc8a |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 024d45d0-84a8-505d-8034-ea5259813bf9 |  | note | Frequency - During Construction
label | 52090ee9-1a05-5e30-a027-af6c505f3700 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 932aef3a-6a2b-51d9-b2fa-4cc43a8dbdbb |  | note | Conformance Criteria - The buttress to be keyed in to natural ground as required and agreed with the CPS Engineer. Rock armour to be added to the toe as required
label | 1d6f2f26-d1af-55d1-8858-1df7cc567b5d |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.12 - Verge & Fence Reinstatement
label | c0704f72-b43a-586f-8d8b-6ead4fc33fd7 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 9d7ce1a4-d9bf-51e5-b2ed-354b3deb27e0 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 542efebe-36cc-511e-9f0d-67c1ce42fb09 |  | note | Frequency - During Construction
label | e2392eea-d2c3-518c-a10b-8e6f4396cf0c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | f2ebe251-a82f-5b9f-af93-751d7289968a |  | note | Conformance Criteria - Verge reinstatement as per site instruction by Engineer
label | 1c602820-e49e-5789-88f1-f4b1867f523c |  | note | ○ Fence reinstalled to match existing
label | bfff5779-5d2e-54e6-80fa-d566e1b638d9 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.13 - As-built Survey
label | defd746c-a0d4-5b34-8d91-d9e0a19ba431 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 67256af9-139d-5610-b747-cacc1e585581 |  | note | Frequency - At completion of Lot
label | 62ca4e0c-31b7-599f-a367-41e2ebfbbbc3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | 535da349-2897-5f6f-8f59-ca4c8c334842 |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | c5585b2f-58e4-58a6-9986-aaba2fcaa541 |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 3 : Final Inspection and Handover
checkpoint-status |  |  | checkpoint | 3.1 - Final Walkover (Snags)
label | 3133cf79-6721-5e85-a47b-81b912a70b7c |  | note | ACTION (Hold, Monitor, Witness) - H
label | ad7f4a42-bb8c-555b-9bed-cf4000415f9c |  | note | Specification/Drawings Reference - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | 507f2a2a-24da-53dd-8ca1-b122a6147ed5 |  | note | Frequency - At the completion of the Lot of work
label | 06f98d94-449d-5978-a3bc-6acbae604c2b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover/Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | a9463427-7da7-5a1b-8093-d2d596a6aa35 |  | note | Conformance Criteria - Completed report
label | ddfc20e8-8aa1-5a00-a6a9-7850a8cf227a |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Quality Assurance deliverables
label | 1ccc7a01-cf9c-52a7-ab7e-ac2839d347b6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a2830549-4943-5fd2-b4f7-d3f43438f7ec |  | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 75148702-9349-5372-813b-dd525415c2ac |  | note | Frequency - At completion of Lot
label | 5d910072-3ca1-534a-9289-0c76f705dcc8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | cfc21ccb-55e1-5bfb-9dcd-4b65b2c0f2dc |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | a956c156-6659-5642-9bc5-112ecb6e77f7 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 3.3 - Completion Sign Off From Fields Below
label | 730f35aa-6dd0-5e99-b0c8-2865c67758e2 |  | note | Records - Signatures
checklist-flat |  |  | checklist | CS-4001 - Subsoil Dipsheet |  |  |  |  | Yes | CS-4001 - Subsoil Dipsheet | d7d76c5f-9404-4514-9ffb-e3fea966f153
checkpoint-no-status |  |  | checkpoint | Details
text | 0c0efcbb-afd5-562c-866d-5d94c74bc4d6 |  | textbox | Work Area:
text | 1b7a8e16-3cda-5a3d-a4e0-0f4b2a79d736 |  | textbox | Sub Work Area:
text | aa272f94-396b-5f4d-8f52-228f4fbabe7d |  | textbox | Lot:
text | c82f3c89-f911-5fd2-8b02-ee801ee5f1a6 |  | textbox | Sublot:
date | 6642070c-8ade-56b7-87d2-d190d481b3c9 |  | date | Document Date:
text | 9cb4987e-a720-5601-bb96-d849af4b82f5 |  | textbox | Created By:
checkpoint-no-status |  |  | checkpoint | Note that depth is to be checked every 10m as a minimum.
text | 2ead78d3-82b6-5818-8436-683a72cbc404 |  | textbox | Drawing No:
text | 6ce22861-4b15-564e-ae2b-cc4622fb076e |  | textbox | Rev No:
checkpoint-status |  |  | checkpoint | Chainage - 1
text | 73d9722d-ed8c-5937-ba7f-d3d1d768fd99 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 2
text | 787a8fb6-02b5-5c23-94bd-01173947523b |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 3
text | c53818cd-48ae-54c4-a603-bc04a96f0774 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 4
text | d6e6ec68-2d34-5e2b-9ac0-833a8944fb6d |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 5
text | ee02fa8c-f1bc-5d83-9805-eb99ccedefb6 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 6
text | 9a01c157-3d97-5edd-a994-405677213799 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 7
text | 552177af-5f5d-5838-a237-e4ca68eb79c9 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 8
text | 3cb2c94f-c4a2-54ed-bebf-17060dd2e985 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 9
text | 5bbd3af3-2a06-55e6-af49-078edb41c5d0 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 10
text | 725ac940-6d3b-556f-8c06-2fe134bc2872 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 11
text | 6600d8a7-fd9f-5ea7-914b-e4a2638da4d1 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 12
text | 57eaa85d-76df-5e35-800c-3cc8a73dff2b |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 13
text | 304791c4-5f14-5679-8042-5a2aaa032b19 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 14
text | e36f44ab-d765-5b14-80aa-e6c3f37b4a34 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 15
text | d6455214-8c09-582c-822a-9785f88aed60 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 16
text | f0758c0f-b0f4-50cb-94b6-37f963df86a3 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 17
text | 362c20a7-5ad5-5adc-bf97-a74bb181045b |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 18
text | 3a4b6c30-e5eb-5fd1-b9a8-55034940d9f6 |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 19
text | 41f5cba1-8613-524a-95c1-0230d12a783d |  | textbox | Depth:
checkpoint-status |  |  | checkpoint | Chainage - 20
text | 08e14eef-ae71-584d-a651-1911bfe06b69 |  | textbox | Depth:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions.
text | 54ed57db-1286-5115-89ee-e1bf24326444 |  | textbox | Name:
text | 914db0d2-94ea-5ec4-998c-3510304c9eae |  | textbox | Position:
date | aa6eb554-aca2-5145-8d18-a725dc74f2ca |  | date | Date:
holdpoint |  |  | signoff | Signature
checklist-flat |  |  | checklist | CS-4065 - Blast Record |  |  |  |  | Yes | CS-4065 - Blast Record | d959ae74-b927-4060-b5e9-9170f08b3948
checkpoint-no-status |  |  | checkpoint | Blast Record
text | 9be0b40d-7617-55de-9f06-7f507951d866 |  | textbox | Project No.
date | c0bd5fd4-319b-5c51-9177-617b95b1cf51 |  | date | Date:
text | b73150dd-bc8c-5af8-804e-7551da47a899 |  | textbox | Blast No:
text | 9090af04-56d7-5629-9294-81cd3dab262d |  | textbox | Location:
text | dc0ec74e-fbc4-5a82-bc1f-be26a0aaee42 |  | textbox | Shot Firer:
checkpoint-status |  |  | checkpoint | Design Powder Factor
text | 604cf7bd-d5fc-53e4-8209-a9a61cf5dba4 |  | textbox | Initials:
date | 009e8467-767b-5993-a665-276817c22419 |  | date | Date:
checkpoint-status |  |  | checkpoint | Diam. Hole
text | 9ca6ebbd-b711-5320-a5d6-060340784a7e |  | textbox | Initials:
date | 2224e7ab-3c0b-5901-9a50-c96fcb6789e1 |  | date | Date:
text | b607f0b0-b123-56b0-b68f-6a233828fee6 |  | textbox | Comments: Diam. Hole |  |  | mm
checkpoint-status |  |  | checkpoint | Shot plan attached
text | aefaa3c0-b0cf-5475-996a-52044d55938a |  | textbox | Initials:
date | 8da5e91c-3edb-5f7c-be23-50aa315f1ab8 |  | date | Date:
checkpoint-status |  |  | checkpoint | Monitor 1 vibration & overpressure report attached
text | d87b9fc4-a475-5fb0-b05f-c67eacd272fb |  | textbox | Initials:
date | a57103a6-7ad4-5dc8-bf5e-5e5f4d7eb257 |  | date | Date:
checkpoint-status |  |  | checkpoint | Monitor 2 vibration & overpressure report attached
text | 998a3566-6f5f-51c6-bea1-c97b342e3a4e |  | textbox | Initials:
date | 8aa03136-9962-5bc5-9585-92ee005425fa |  | date | Date:
checkpoint-status |  |  | checkpoint | Vibration & overpressure beneath consented limits (PPV 10mm/sec (5mm/sec 95% of time) 128 dB) if not OFI
text | 8e33e895-853c-51f8-8474-946a60cf2fd6 |  | textbox | Initials:
date | 04cb9123-8dc5-5680-888c-2944e8be5bca |  | date | Date:
checkpoint-status |  |  | checkpoint | Shot Firer’s Blast Evaluation attached
text | 27d5b263-14a0-545f-9a05-f72a61cb6c43 |  | textbox | Initials:
date | c07afe1b-5c06-5de0-9077-4a7fc3a07440 |  | date | Date:
checkpoint-status |  |  | checkpoint | Coordinate (GPS) plan attached on (Contract Name) grid reference
text | 33f93715-278a-5f1c-b7d6-0b736c3d274c |  | textbox | Initials:
date | 8af70be4-1edd-5335-841b-2c5c5a14a455 |  | date | Date:
checkpoint-status |  |  | checkpoint | Actual powder factor
text | f2f10767-d805-5d33-8ad4-2608b7562cb9 |  | textbox | Initials:
date | 1d084493-4b91-5538-834c-e7b12be4bff9 |  | date | Date:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | 88674369-e522-5388-a1be-28b3860e45f2 |  | note | Position: Site Engineer/Supervisor
text | 68c09df6-a125-5059-a18f-94abe250100a |  | textbox | Site Engineer/Supervisor - Name:
date | 19d93321-6146-52d8-a44e-4cdc61775db7 |  | date | Site Engineer/Supervisor - Date:
label | 5550b798-32d4-5909-9108-4ea6d934627d |  | note | Position: Shot Firer
text | 3085af56-ce4c-5325-926b-b64134a2611e |  | textbox | Shot Firer - Name:
date | 47070bc7-0338-52d6-acf7-53cf2a7ad1ae |  | date | Shot Firer - Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | ITP - B1004F - Tangoio Falls Steep Underslip - Reinforced Slope (Rock Bolts, Soils Nails) | itp |  |  |  | Yes | ITP - B1004F - Tangoio Falls Steep Underslip - Reinforced Slope (Rock Bolts, Soils Nails) V2 | dc159693-1a67-4606-aacf-3e9ab154c94b
checkpoint-group |  |  | section | Preliminary & Setout
checkpoint-status |  |  | checkpoint | Project Site reps.
text | c597509f-a0d6-5925-8bbe-8f7d9cd5d283 |  | textbox | CPS Eng.
text | f1b41ed8-a41a-594d-a548-827a32b04661 |  | textbox | Site Engineer
text | d4b5b0cd-6be6-5275-a324-d7327441f494 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Vegetation Clearance
label | 92794bef-88c9-5bcc-9e5e-4d382d552801 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6dbc1eab-402b-5e41-a82a-953b6076fe62 |  | note | Detail - Before setout of the reinforced slope method all vegetation and debris clearance within the limits of the site is to be completed
label | c9304622-c35f-5da6-b3a4-40440e87b0a9 |  | note | Frequency - Prior to commencement
label | fd65e04c-1444-548c-92ed-f1ff720f5e22 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 0bea21ed-27e9-5849-9f98-ca3344ea294d |  | note | Conformance Criteria - In accordance with TNZ F/1
label | c4cb0c52-7e85-5629-a39f-39a9b592a0da |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Excavation Clearance
label | 4ec20830-a207-5513-995f-20b3a35783a5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4c9b120a-f6a1-511c-9ef1-8145f43f9f13 |  | note | Detail - Any excavation and filling required is to be carried out. Excavation should be kept to a minimum
label | 7e5ca8e0-22cd-5c6e-9a4f-afd6b8a4f927 |  | note | Frequency - Prior to commencement
label | d6cbab65-4df9-5e3a-b7ea-9f8e161cb503 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 96ecd08c-9404-501a-92a1-94136ab8dc74 |  | note | Conformance Criteria - In accordance with TNZ F/1.
label | ee4a2a36-a260-56fa-a4c7-0b6d40363788 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Survey Setout
label | ae00cd3a-4d2b-5222-870c-968a57dedc56 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 79187153-a368-5d72-b72b-a8e6970c8edd |  | note | Detail - Arrange for a set out survey to be carried out & check against design drawings
label | efde8262-726c-5ffb-a00d-9d1aaf0db3e8 |  | note | Frequency - Prior to commencement
label | bd9e8712-915e-581c-a477-dea41edce1ee |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 9112c6de-91d1-5211-a5ab-3e2df0da749c |  | note | Conformance Criteria - Consistency with Construction Drawing
label | f5efd13c-4ad1-5bd7-97b4-29f116b31132 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Material Compliance
checkpoint-status |  |  | checkpoint | 4 - Material Compliance - Rock Bolt & Soil Nail
label | c9a7282c-2a78-5ba7-90c4-3fca28a62eb8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 91fff0f9-fca7-5948-a926-905fe77794f9 |  | note | Detail - Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings
label | 7a71d360-6b29-557b-86bc-c2bb4083406e |  | note | Frequency - Prior to commencement
label | 9c4c906e-4d12-5e69-a7d8-8fa5f8ad4828 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 8dc8edcb-6cf9-5748-b6d4-96e9a0f41026 |  | note | Conformance Criteria - Grade 500E soil nail
label | 303e96a0-5a4e-5c5f-8ccc-111059a80148 |  | note | ○ Class II corrosion protection
label | e0a18e25-a967-5995-a42e-52f34affe939 |  | note | ○ Lengths and diameters shown on drawings are the minimum required
label | 25f4ba8d-2713-5b37-856b-1b72a62631d9 |  | note | Records - Delivery Docket
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Material Compliance - reinforcing steel
label | 98fcb961-4786-5a73-8de4-69eb74cfcdbe |  | note | ACTION (Hold, Monitor, Witness) - W
label | 703cf1ee-a272-55d8-8942-0f32ba7ad5d7 |  | note | Detail - Reinforcing steel manufacturer's test reports and certificates
label | a103564b-0409-5a21-940c-490509c42af2 |  | note | Frequency - Prior to undertaking works
label | 9c233152-98ac-53a2-8ec5-48bd631fabea |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 74cd483e-ea70-5b5f-b968-65f775c295d6 |  | note | Conformance Criteria - Including despatch records
label | 7ec918cc-c199-5d66-8afe-91d06fca1e5d |  | note | Records - Email
checkpoint-status |  |  | checkpoint | 6 - Concrete quality plan
label | 782f2a5a-e0ce-589b-b6fb-2419767c85a5 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f7cda1d5-2690-578e-81b8-5d5406fd2763 |  | note | Detail - Concrete quality plan to be produced and approved before work starts
label | 86dfa2d6-175e-5beb-b681-d001d56766bd |  | note | Frequency - Prior to commencement
label | e2369fbf-137b-59a9-b07f-257b33b1885c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 935ffd4a-4c77-5160-b2b2-ada04611901b |  | note | Conformance Criteria - Including:
label | 230ef11e-d99b-5186-b650-1f798df0680b |  | note | ○ Name, qualificationand expoerience of concrete works inspector
label | 66eb45c5-49a4-5c78-ba89-1341ff061a14 |  | note | ○ Form and content of concrete placement card
label | af693f71-eb8c-539e-9216-998a609d151f |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Concrete plant compliance cert
label | e84f5e66-c2a6-5a7d-801f-2e36dbad02fe |  | note | ACTION (Hold, Monitor, Witness) - W
label | f6d6060d-4a83-5c17-889c-2c2213b8beab |  | note | Detail - Details of concrete supply plant, copy of certificate of audit for plant
label | 6a2a58bf-d5d2-5ff3-8d5f-7cdbd7f47d50 |  | note | Frequency - Three weeks prior to pouring concrete
label | 2cb0f2fe-3edc-535f-b25a-eb733f60b4f0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 3da03a8b-668c-50bc-968e-955b679cddc1 |  | note | Conformance Criteria - Including:
label | 67182d49-4c88-53cf-8e80-4395010768c7 |  | note | ○ Plant test Results
label | 7534d6b3-3db6-52bf-819b-5be0af77e6c4 |  | note | ○ ASR Compliance Records
label | a1c99cfa-b766-52e2-b5d1-9725765eaace |  | note | Records - Email
checkpoint-status |  |  | checkpoint | 8 - Concrete mix designs
label | 144ed046-16d5-5db1-9b37-ffac5dfa8b35 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a502f3da-7f60-59a9-9fb9-0a878f003b92 |  | note | Detail - Submit all concrete mix designs, trial mixes and compliance records
label | 4b267ddb-a853-5a0c-b6ff-820ee9ebb3bf |  | note | Frequency - Three weeks prior to pouring concrete
label | c30e1a7a-397c-5b4b-975e-782e47062636 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | b2637857-b4fa-5382-97fa-3acf07b43485 |  | note | Conformance Criteria - Mix Design to be approved by CPS Engineer before commencing construction
label | 9a823e33-19a3-5803-a788-e5647bb53a8a |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Grout Mix
label | 91555d57-6e85-5b50-a627-0192afd90e8f |  | note | ACTION (Hold, Monitor, Witness) - H
label | ef095c7a-e4f4-5a58-ac4b-677f84108f7c |  | note | Detail - Test to be carried out on Grout mix before it is ordered for construction
label | 0f1718c2-cf71-50c2-be5e-58af8abd1840 |  | note | Frequency - Prior to commencement
label | 5da17bb4-03b4-5d37-a4fb-017aa16ec1c2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | c007b909-13b4-5455-9144-56cb300f0f80 |  | note | Conformance Criteria - Mix design to be approved by CPS Engineer before commencing construction
label | 9d76be13-976a-5e5b-9a31-4f195f7082d4 |  | note | Records - Test results to CONQA Procore
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10 - Grout Checks
label | a3ad5ee8-63ec-596f-9d94-a99edbf4b60b |  | note | ACTION (Hold, Monitor, Witness) - W
label | d90bafd2-6791-5a8c-8a50-a2918e2ae8f1 |  | note | Detail - Grout checked if its free from lumps & segregation
label | 19fc3b3c-fb6e-5962-9cea-ee9138808230 |  | note | Frequency - Prior to commencement
label | 9c463533-6c21-5807-8c5e-804f1b0b597c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint-status |  |  | checkpoint | 11 - Request for use of alternative Drilling Fluid
label | 17bea228-b675-5592-98be-7408985cb1b3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 33087294-5f76-5c10-9eec-6a710d171ed8 |  | note | Detail - Request for use of alternative Drilling Fluid (Section 7.5.2)
label | a00edb68-d87e-538a-b61e-7ee1bc62d5ed |  | note | Frequency - Prior to Commencement
label | d0b48531-bdcc-5d95-9439-2cf31ff3547c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | ee1b0e4d-6c39-5371-9936-df31cf0998d2 |  | note | Conformance Criteria - If required
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Soil Nail construction methodology
label | 97f745c7-055b-5727-b758-584dde58df74 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f77610c4-fbcd-5a8a-a0c6-03d49c9889c6 |  | note | Detail - Soil Nail construction methodology plan must be submitted two weeks prior to works starting
label | 7fdcd5de-f183-5a3c-9122-0e3d2ebe4eb9 |  | note | Frequency - Prior to commencement
label | ccfdd90a-8e9a-5ffe-a5cd-ea400eafab0f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | afc7badc-8c7f-54d8-8f81-3d20eff19608 |  | note | Conformance Criteria - Include sprayed concrete, grouting and tremie concrete in methodology
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Sacrificial Testing has been Completed and the Results are in the Design Report
checkpoint-group |  |  | section | Construction
checkpoint-status |  |  | checkpoint | 13 - Working Bench
label | 6197bd08-cc04-5394-83f1-73c229accc82 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d408ea98-8a50-50d5-83cd-17888494bf20 |  | note | Detail - The construction team shall stage the excavation of the retained face such that the excavation proceeds no more than 1m below the current level of soil nails being installed or vertical spacing of the soil nails plus the required reinforcing lap or the short term stand up height of the ground, whichever is less. The construction team shall protect the face of the excavation from damage at all times.
label | b5f98dce-11b7-5f3e-9321-9ec54e1d8c8f |  | note | Frequency - Prior to commencement
label | c8220563-aee4-5a13-ac14-3a87fec9b275 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | d44fbe0e-0a63-546a-89c9-9e246dfb4922 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 14 - Test Nail Locations
label | b76dbd7b-7bc6-5604-a66e-d30813174489 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0ae5424d-f67e-52b8-9abf-4658b7a24881 |  | note | Detail - Location of all Test Nails to be agree on site (Section 7.8.1)
label | 72a60394-5f9f-5d1d-b4d6-461c1ed7197d |  | note | Frequency - Prior to Trial
label | 845e43d1-4953-534b-976a-cc61a9971c76 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 7d45b2ce-3bb2-573f-a7fd-493f67b9ee73 |  | note | Records - Photos, Site Diary
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 15 - Insert micropile bar
label | c0342f8e-1d95-5b6d-aefc-91940d30cc2f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6e6e6742-ed2e-5c15-80ab-d908e0e36b32 |  | note | Detail - Insert micropile bar (ReidBar RB32) to full required length
label | d70551df-255d-5534-bbae-9d18588dd3a2 |  | note | Frequency - During Construction
label | d6e3594d-9c9a-5941-b3da-36e297009206 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 6e046df4-f623-5bfe-83e9-6dc12557b56b |  | note | Conformance Criteria - Embedded length of micropile 3.0m into ground
label | 5068e1b4-172f-5a82-b52f-a364fc6ede5c |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 16 - Drill Holes
label | 047d52f7-5465-5e15-a656-b6ae72d9ef1b |  | note | ACTION (Hold, Monitor, Witness) - H
label | a9bcade7-229b-5118-b9e4-1708e23dac3c |  | note | Detail - Drill hole
label | f5113170-80ac-521c-b0b7-1bff4c0302e9 |  | note | Frequency - During construction
label | 81b1db31-4f21-54b3-aae5-91512e678d66 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | ba97d82e-d6d0-574b-b9b6-bc753e7cfb4a |  | note | Conformance Criteria - Drill log to be submitted to CPS Engineer including the depth at which water was encountered if there was any.
label | 88492e18-7334-5586-a0fb-9f894393c9ce |  | note | ○ Submit all installation records for each soil nail and pile.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 17 - Flush holes
label | ac57f2e5-5dc5-5383-8983-fd9a26937b1c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2c1aaead-e5c0-581c-81a1-c35d731942b6 |  | note | Detail - Flush all soil nail holes with water and air after drilling to remove smear and drilling debris
label | e911033b-7bc7-5016-a046-a69d4b99e03b |  | note | Frequency - During Construction
label | 7d4131cd-ef2c-55d0-b503-330eeeb6ec4c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 18 - Insert soil nails
label | 80d853c0-6321-5575-af0a-a7d2b72712a2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | edc3bf28-4063-5e0f-ade3-47e18ebc8ea5 |  | note | Detail - Insert soil nails as specified
label | 88967146-12d7-5c25-933d-8cbb58b16292 |  | note | Frequency - During Construction
label | 061fcf95-6bde-5a92-90d8-a8e9df29a9bc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 775d6676-62ac-58e0-bc5d-2dcaed27b243 |  | note | Conformance Criteria - Soil nails must be inserted into the drill hole to the required length without difficulty to prevert damage
label | db8d0566-5278-5c04-9521-4398c8e6ea7f |  | note | Records - Subcontractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 19 - Installation Records
label | 15137362-950d-5d5f-b3bd-5a624ca03f56 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 468f8286-7f38-50a9-9625-80ccf7f0eb0a |  | note | Detail - A record is to be maintained showing the type and installation date for each soil nail
label | be584b8f-9a67-5130-b1c3-2d5627ec4f5d |  | note | Frequency - During Construction
label | c8ab16f7-d88e-54d6-998f-5c645f2735db |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | b7d69505-ba18-57c9-8e9c-2cacaa51fa19 |  | note | Conformance Criteria - Installation records shall include:
label | 04c49ce7-e443-5acf-81e5-b69c03cc6779 |  | note | ○ Length of bar
label | e34e81b6-b6ff-52c2-8779-c4c9d90647b5 |  | note | ○ Depth of drill hole
label | 4a6216f2-054e-5177-863c-6be3852d4f23 |  | note | ○ Inclination/Verticality achieved
label | a1a8d5a1-95b7-5f57-9c22-773db7132096 |  | note | ○ Level of grout placed
label | bc381ab5-7957-53fa-9277-386a47106268 |  | note | ○ Batch numbers associated with grout placed in each hole
label | 8656ce83-ecc4-5259-87cb-5942c664c361 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 20 - Install Grout
label | 88c393cf-2ab2-5db4-8b88-c41808a29a47 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0df75351-a6b2-5abd-9861-28ab7f8faf98 |  | note | Detail - Install Grout on the same day of drilling unless otherwise approved by designer
label | 846bc6ba-902b-50fa-83af-ae46b560847c |  | note | Frequency - During Construction
label | 69f6d250-6942-5f6a-94d8-edc8864010d1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c9a6d5ce-70ea-5306-954e-529517d66046 |  | note | Conformance Criteria - Including:
label | 87fb3884-0c0a-5f16-9269-89053dccf5f5 |  | note | ○ Concrete despatch records
label | f89fb700-1bf5-5637-aefe-9e1cc58a6360 |  | note | ○ Compression test results
label | 506aa84b-cb14-583e-8001-cb6c4f9965a2 |  | note | – Must notify CPS for any failed result and cease works until resolved
label | 2bb957c2-383b-5143-816b-9f478c27c0c0 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 21 - Grout Sample Testing
label | 181d725a-12e2-5416-858b-f31faeb05a51 |  | note | ACTION (Hold, Monitor, Witness) - H
label | bdaa09f6-15bc-565d-8234-0d879842f753 |  | note | Detail - Grout samples shall be taken from each batch and tested by an approved laboratory. Flow cone tests shall be undertaken for each batch
label | 6077ce32-d765-56d7-9e3e-42f3a1b8e631 |  | note | Frequency - During Construction
label | 6ec55729-17e3-5000-8eb6-94a5156fa3ca |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 5b8dad5a-eea1-554d-85b4-dc5779496630 |  | note | Conformance Criteria - Must reach specified minimum 7-day and 28-day compressive strengths
label | a473c828-cf33-54e4-9038-473e41a188dc |  | note | Records - CONQA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 22 - Monitoring of grout loss
label | 822374f8-7cbd-519e-af21-ba00bbd4c79c |  | note | ACTION (Hold, Monitor, Witness) - W
label | b7baccdf-fa61-584a-9399-128b486e6147 |  | note | Detail - Loss of grout shall be monitored and recorded for each hole during and immediately after grouting
label | 787617a1-e07f-5014-aae7-53ba091d8417 |  | note | Frequency - During Construction
label | 51414012-5de3-5ed5-801b-e8f5ed0b5c69 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 4b0137b8-684c-513c-a4f3-89d6ec03d4c9 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 23 - Install Bolts/Nails washers & nuts
label | dbfcf1bf-837d-576a-a7da-85821541b817 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b931ce4a-1ddb-5208-9fd8-81060f172aea |  | note | Detail - Install Bolts/Nails washers & nuts
label | 897dcde2-38b5-51bf-9615-66b13e347354 |  | note | Frequency - During Construction
label | 284f8d3f-4636-5c60-a159-7ed7bed57e8e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 3d9d295d-584a-5462-a203-a21b0439cb48 |  | note | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
label | cc8d7a1a-1f88-57e7-b7b0-1f3b47e045fe |  | note | Records - Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 24 - Testing of Soil Nails
label | 47c6bea9-4053-5477-b2cb-01c74585b7d2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ff36b338-6dee-5dbe-8189-5b5e45617c24 |  | note | Detail - All testing equipment must have been calibrated by an IANZ registered laboratory (or approved equivalent) within the last three months and shall be certified
label | 8158d5dd-5157-5f51-be87-2f10a20d655e |  | note | Frequency - After Construction
label | e5c44c2e-af75-55d7-95d6-fd6b46bb3823 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | da0641e0-6d92-59db-b5e2-a6f73dc71190 |  | note | Conformance Criteria - Certifications of all testing equipment within the last 3 months
label | d61ac91e-64ff-5b04-8cfb-fc4d907d0cbb |  | note | Records - Certifications
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 25 - Testing of Soil Nails
label | dc207b1d-7de7-55ee-b3e9-7eeeb5b0cb1c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4137ec2b-3f74-5051-b751-af7d6dc2a057 |  | note | Detail - Leave nails in an undisturbed condition until the specified 7-day grout strengths have been achieved
label | f02b6ef5-66f5-5b6e-8e75-315016c673fd |  | note | Frequency - After Construction
label | 011ec301-5529-500f-b71b-799635f2e560 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 1465fb60-cc80-5fd2-9960-13c32056bdc1 |  | note | Conformance Criteria -
checkpoint-status |  |  | checkpoint | 26 - Testing of Soil Nails
label | ba2ea797-126f-5a45-a408-a877022b2e5a |  | note | ACTION (Hold, Monitor, Witness) - H
label | f01c5263-03da-58da-9c1c-44136bdb9d4a |  | note | Detail - Test soil nails in accordance to design specs (Section 7.6.1 and 7.6.2)
label | 480e6246-d1e2-5478-9b0a-4513fcdc1d5f |  | note | Frequency - After Construction
label | 63a68129-5873-5627-bfc0-95ae19f1881b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | dd8fa0fa-58ce-590f-9fd3-6a7965a3885f |  | note | Conformance Criteria - Load testing 10% of working soil nails - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | bc1f6335-0e33-538a-be34-977fc47019c3 |  | note | Records - Test results to CONQA Procore
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 27 - Soil Nail Final Inspection
label | 61c45d6f-486e-56c9-8231-d44a0a2cc1e2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a9b5bcc6-b602-5076-a59a-9f04aa9f9750 |  | note | Detail - Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails
label | 4dddc209-39f5-5d20-a155-0437c2842d7c |  | note | Frequency - After Construction
label | d3af11d0-b942-52ee-baf0-3428ebd3a284 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 77547439-1f73-5305-b1f3-84a809239b5d |  | note | Conformance Criteria - CPS Engineer to give approval via a NTC
label | c91694d6-3121-5851-81f8-40c07dd66818 |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 28 - Shotcreting- prepare surface
label | 626210ac-4e8f-57c6-92a9-f5bc5f00fa85 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1e7b2e30-cf35-5ba2-9073-b57d41442484 |  | note | Detail - Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened
label | 41b7cc92-897a-5754-94ef-125769ce5be3 |  | note | Frequency - During Construction
label | 3a98218c-ebc3-5212-8ce7-40e30d0e45a0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 358e1c4d-f551-584a-8d16-64c00211a8c5 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 29 - Shotcreting- apply vertical
label | 78f95401-83f3-5ecf-9ac8-0250256fac72 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0b4ddb97-e833-5e3a-bed1-13248906e0de |  | note | Detail - Apply shotcrete - 200mm Nominal thick (Vertical)
label | 092b04f4-77cc-5f86-8e9c-e2b31186f22c |  | note | Frequency - During construction
label | 7ab7aee1-7ed9-50e8-a352-471b4dc4f748 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 05780c4b-adda-58d0-b6a2-d176a0c62c84 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 30 - Shotcreting- apply horizointal
label | 78dac9d9-3e0d-557e-a0a1-ac0b5565746b |  | note | ACTION (Hold, Monitor, Witness) - W
label | e23a6f5e-2b4d-5139-9b5c-f947fc26568f |  | note | Detail - Apply shotcrete - minimum 150mm thick and nominal 175mm (Horizontal)
label | 27cb846a-e9e3-53c4-9340-4189f027d337 |  | note | Frequency - During Construction
label | 9a532789-21a2-5971-bb86-1d299237f214 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 93c15a71-6dce-5f79-ac38-5a845f29f289 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 31 - Shotcreting- compression testing
label | dcbe3aca-7490-59c7-980f-e8416e4f082a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 62347d3b-e868-546d-979b-1e82798a1c69 |  | note | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores
label | d12fd928-f04b-535a-88d8-e8da556d87ce |  | note | Frequency - After Construction
label | d0fae98b-92ab-50e6-8831-825df4308f74 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 0fcd638f-7948-5ff0-b696-2bf9d950ffe9 |  | note | Records - Test results to CONQA Procore
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 32 - Shotcreting- surface inspection
label | c2597081-27a2-5695-837b-2ed1122a293b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 412af196-695c-5444-94dd-7806a3521815 |  | note | Detail - Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m
label | 2222f226-0cfa-5cb4-960c-4e47f451682c |  | note | Frequency - After Construction
label | 51f7f8b6-ce97-5907-85bb-1402fdbf8644 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | bf680958-ad8f-5fde-a02d-5134301c2118 |  | note | Conformance Criteria - Surface Inspected by CPS Engineer & Approval given to carry on with works
label | 63b288ce-eda6-5563-b46c-cbfaad124dc1 |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Post-Construction
checkpoint-status |  |  | checkpoint | 33 - Final Walkover (Snags)
label | d09194e4-32a7-5623-a4f9-b276065effba |  | note | ACTION (Hold, Monitor, Witness) - H
label | a58889d7-80d9-5bb4-b5a9-6c7ad7a5c645 |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | 6a192b10-e9fe-525d-86b9-f16053050ebf |  | note | Frequency - At the completion of the Lot of work
label | ca3d7870-84ef-5aa7-a276-2c9432e14afb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | 17aab5b6-0bb5-5cc1-b2e0-a49e1dc671f2 |  | note | Conformance Criteria - Completed report
label | 46aeeed9-0c9c-58b4-8ade-d9e158578049 |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 34 - Survey As-builts
label | 9e538293-317d-56e1-a24e-c5cd4c0742eb |  | note | ACTION (Hold, Monitor, Witness) - H
label | eadbdcc5-4ab7-595a-a0bc-bee0fe393d09 |  | note | Detail - Red pen mark-up drawings are to be included in the QA file. A survey as-built of completed work must be provided
label | 153a928e-2d9b-5729-a19d-b2221077a255 |  | note | Frequency - At the completion of the CWP of work
label | 412f7365-6f16-555c-ae07-3580d3807b98 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 80f62c3b-2e5e-5a01-a3e0-2f0ee98a79f3 |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated
label | 7533c7c7-ebf1-5e61-90fb-99c12c0a5350 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 35 - Quality Assurance Deliverables
label | 7c2f208b-87ee-5fe7-84bf-cf58fcb9e46a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6febf0a5-0b8d-59c6-b112-05711e6494c6 |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | f36e118f-30bf-5cbd-b971-ea0e7f7c8765 |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | d9029c43-a925-50d7-b304-27c96969a01d |  | note | Frequency - At the completion of the CWP
label | 9fdfea99-1a38-5c96-bac4-f66fc2e82efe |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 4ba0ea1b-2990-518e-8215-71c27d7e2318 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 4bc73f4e-f7cb-5233-a0e8-b134adeb9091 |  | note | Records - As-builts, NCR's and RFI's
checklist-flat |  |  | checklist | ITP - Waikare Gorge Descent - C1603A - Bored Pile | itp |  |  |  | Yes | ITP - Waikare Gorge Descent - C1603A - Bored Pile | dfd895ab-e858-4f4a-96ce-1a1e1215b4e4
checkpoint-status |  |  | checkpoint | Project Site reps.
text | c0f8c7c2-0f92-5ff4-a561-2fcf05075edb |  | textbox | CPS Eng.
text | cd831d9e-37d6-5ff8-8377-4d3f4c25ff1e |  | textbox | Site Engineer
text | a8b66195-d44a-5c8d-9f5e-8eb6430eb451 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | be193455-e28b-5cd3-96ef-ba0e185c9166 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 20d99eff-930e-5f29-871c-cc2bb7bef108 |  | note | Detail - Contractor to set out grid lines as per contract drawings and specification.
label | 07f2bd98-80b9-580f-8b33-eb73d54c5891 |  | note | Frequency - Prior to commencement
label | 42b55cf5-da05-5b27-87bd-0c340943e35a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | b2320059-c7f1-5971-8fe3-f95f08299cee |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 24c570fa-d276-542d-b811-bce2547a2984 |  | note | Records - Design Engineer Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 -
label | 5c46e044-c976-53f2-bca4-5e205278667a |  | note | ACTION (Hold, Monitor, Witness) - M
label | 6507584b-e308-585c-a209-82d6436dabc5 |  | note | Detail - Any services in the area are to be clearly marked before any work commence.
label | 5446ad2c-272b-5ec6-9d23-5d3e3a1d58f0 |  | note | Frequency - Prior to commencement
label | 1a1a532b-3cbc-58b0-921d-884f3f16b930 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 283cc7ab-5733-52a6-bf5a-1d88e874f134 |  | note | Conformance Criteria - Service location conducted by asset owner, marked out with dazzle on site.
label | 8f1d8d1c-c5aa-58a8-a86e-0a236ef016e1 |  | note | Records - Photos, log, site inspection
checkpoint-status |  |  | checkpoint | 3 -
label | a546c0dd-120f-59bc-9bd8-e825e9f4460c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1f130842-1de6-54b6-91ef-b6208ddf0a17 |  | note | Detail - On completion of the set out of the wall, the Contractor shall immediately advise the Engineer for the purposes of checking the set out. No other works shall be carried out until this has been checked and approved by the Engineer
label | ffe6b519-90d1-5960-804e-8338cb72b514 |  | note | Frequency - Prior to commencement
label | 5ca02a7e-721a-5319-b8c8-13407694ec98 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 5b4579d1-e92c-5f02-b019-97f671a963de |  | note | Conformance Criteria - If the set out is found to be incorrect, the works shall again be set out by the Contractor and re- checked by the Engineer.
label | 268d0caa-a838-58de-8688-c62c7446bd6d |  | note | Records - Design Engineer Approval (RFI), ConQA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 -
label | c511fbaa-acf5-5e65-9746-51c3f9ebc28b |  | note | ACTION (Hold, Monitor, Witness) - M
label | 63fa3c53-4122-5bff-b136-00f5a663f594 |  | note | Detail - Timber post spacing and clearance to be in line with the drawing specifications. Set out should allow for clearance, angle and spacing of centres
label | 61858a11-3a64-5a81-b9c1-ddd6448536af |  | note | Frequency - Prior to commencement
label | 8a189b64-db83-553d-a83b-c4e05b908422 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 5801b3d2-78b5-560c-ba7c-b248e6fb8762 |  | note | Conformance Criteria - MAX 1.10m centres
label | 530d6d38-35bf-5851-8a3e-d17b52fd4f32 |  | note | ○ set at 4 degrees from vertical
label | 25215b6e-be33-51ad-bd3f-18568cc2724f |  | note | ○ 100mm of clearance on all sides of pile
label | 057ba9fd-e0fb-524c-b192-814575d041aa |  | note | ○ 100mm minimum cover of concrete at base.
label | 5c21b524-ffb8-5b31-950a-2e8368d46d51 |  | note | Records - Photos, log, site inspection
checkpoint-status |  |  | checkpoint | 5 -
label | ea73bac1-8b72-5d57-b59a-0965ff9108f8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 767cdcfe-7508-52ff-8075-dfe55d4a2d83 |  | note | Detail - Minimum Pole embedment to be as outlined in specifications
label | 0e62367e-bd40-5045-87ee-e975a504d5ac |  | note | Frequency - Prior to commencement
label | bca3e34b-f082-596a-89f5-37576a9d9882 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 2109dbbe-bc16-5cfb-b4e3-ade00a168755 |  | note | Conformance Criteria - Pole minimum embedment to be be 3.25m, unless otherwise stated in the pole schedule on drawing C013
label | c4084f5a-9ecb-549b-a83e-e5ad28518864 |  | note | Records - Photos, log, site inspection, ConQA
checkpoint-status |  |  | checkpoint | 6 - Pile Material Compliance - Timber Poles
label | 41cbd10e-15c3-5e33-8ae8-69d1c7274b42 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e1716da8-5749-596f-a36e-9e16f0f1b947 |  | note | Detail - The timber poles are to be radiata pine, high density selected in accordance with and complying with NZS 3605:2001 for cross-section, length, straightness, strength and branding. All materials used in the works shall be new unless otherwise specified.
label | 86d19c38-b21b-5791-a76d-f2dc676ba3ba |  | note | Frequency - Prior to commencement
label | 87eff655-c3ae-54ba-a5b2-f621f40aad89 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 732bce53-d396-532c-a090-d92053947447 |  | note | Conformance Criteria - The Engineer shall be provided with a certificate of compliance
label | aaf073f2-3d9a-5960-ab0e-54a766c4afe9 |  | note | Records - Document/ConQA
checkpoint-status |  |  | checkpoint | 7 -
label | 63e0df30-78cc-535c-a64d-8160e52d3abc |  | note | ACTION (Hold, Monitor, Witness) - M
label | e9b6c533-81fb-5ef9-89e8-0c1a6cef8d27 |  | note | Detail - The poles must be H5 treated in accordance with NZS 3640, H5.
label | ebb6f15c-31ec-54c9-b2aa-e54a54afc929 |  | note | Frequency - Prior to commencement
label | 4a2b578f-e0bd-5be4-b713-4dc826cdc85e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | f391808d-f3e7-5d61-8128-c8024e438007 |  | note | Conformance Criteria - The Engineer shall be provided with a certificate of compliance that the poles have all been treated to NZS 3640, H5.
label | ac54c80f-f01b-5f1f-b879-1f40d327b53d |  | note | Records - Document/ ConQA
checkpoint-status |  |  | checkpoint | 8 -
label | 9df0690b-b75a-5db3-9b73-94fb7a8e5c8c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 77e6bde5-96e1-5b72-bd85-ac76ef5c4c05 |  | note | Detail - Poles are to be peeled and not machine shaved and not steam treated. All cut ends, notches or drill holes shall be treated with a liberal brush coat of copper naphthenate or equivalent wood preservative before sealing with a bituminous sealer. Cut ends shall not be in contact with soil.
label | ce999cd9-cac4-57f2-b905-b0281997da75 |  | note | Frequency - Prior to commencement
label | f6f947c8-37a2-5b83-a2a6-3498ba9f30fb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 5ad89d19-c448-54d2-9c2f-9b207ad4f105 |  | note | Conformance Criteria - Engineer to inspect as accordance with specifications
label | 6fb43252-2d3b-576a-8005-148bfd9b6e21 |  | note | Records - Photos, log
checkpoint-status |  |  | checkpoint | 9 - Pile Material Compliance - Concrete
label | 7b32a45b-05a4-512b-a9af-998803986d6b |  | note | ACTION (Hold, Monitor, Witness) - W
label | 200da0c0-5684-52cd-8424-54860224acff |  | note | Detail - Concrete mix design(s) shall be submitted to the Engineer in writing prior to placing concrete and approved before placing concrete.
label | 17ea213c-2184-52e8-82c3-576ebceb51ca |  | note | Frequency - Prior to commencement
label | d66fdf8e-3f1a-50e9-9599-b2da5e567896 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | b001da80-a4bc-5982-8155-4e18d0822202 |  | note | Conformance Criteria - Engineer to approve design prior to commencement
label | c69d2744-d2e8-522e-a2e2-430c1b144cd9 |  | note | Records - Design Engineer Approval
checkpoint-status |  |  | checkpoint | 10 -
label | 08860cd6-81d1-5696-b3f3-7af7bd59e6da |  | note | ACTION (Hold, Monitor, Witness) - M
label | f6568834-3ffe-5a16-a2d0-c2c751aeafe1 |  | note | Detail - All concrete delivered to site shall be produced strictly in accordance with the approved mix design
label | 4a8a2990-c4f6-5754-aa56-d9f86d3a0c20 |  | note | Frequency - Prior to pouring concrete
label | 6bfc8592-42ca-5818-94cb-37998a299329 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Concrete Delivery Dockets
label | 34bb0b2a-c3b5-5dcb-b8d9-fcda944dceef |  | note | Conformance Criteria - Site engineer to inspect delivery dockets
label | 74dd2563-6e78-50ef-bb8f-50330b98d534 |  | note | Records - Concrete Delivery Dockets
checkpoint-status |  |  | checkpoint | 11 -
label | b88c95d6-e00c-5d2f-84a8-9b51e0d4144f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 31f1af45-5eca-5792-b004-8efcbc7c9136 |  | note | Detail - The concrete used to backfill around the timber poles must have a minimum 28-day compressive strength of 20MPa. Concrete batch crush test supplied by concrete supplier for 28 days.
label | 7a9e74b6-043b-5f78-acab-1ee25ba5e5a3 |  | note | Frequency - Each batch
label | 81cfb03b-c060-5dba-a200-8540e0b5d117 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 2dbfe536-5d33-5b17-8439-93f5224ab976 |  | note | Conformance Criteria - 28 day strength of 20MPa
label | 93fa166b-f24e-5dec-a4f2-6c1fe352026d |  | note | Records - Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 12 - Pile Line
label | 23ff5523-b1e2-52b3-b006-1efdca492241 |  | note | ACTION (Hold, Monitor, Witness) - M
label | eeb9fb3d-1961-5256-9c82-d68a7772b7f4 |  | note | Detail - Check if the bench the has been excavated/filled can accommodate the entire pile line
label | 00087894-e7ea-5d19-bb5c-e97b844d2d10 |  | note | Frequency - Prior to Commencement
label | 6117e6d8-518e-50e9-a912-df519b588398 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 6b7c1303-1f54-53dd-ab9b-feb105157d82 |  | note | Conformance Criteria - Site engineer to inspect against relevant drawings
label | 7c8e93e9-506e-5717-86a4-66720e8bec18 |  | note | Records - CS-4011
checkpoint-status |  |  | checkpoint | 13 -
label | 82865199-8e1f-502b-b258-4ab485a03643 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7c19f46b-fd2b-5a23-8e24-1037576ed295 |  | note | Detail - Drilling is to be carried out for every second pole, and poles shall be placed and concreted for at least 24 hours before any drilling for intermediate holes
label | 1f81406e-0a71-5d78-b413-c6cce0c616bb |  | note | Frequency - Each Pile
label | c7095c7e-0872-595a-adef-348a88fd793f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | d5a7dfe5-47f4-596e-a871-2e3a61f77dd6 |  | note | Conformance Criteria - CPS engineer to inspect
label | 6ed8e71a-0d8d-50ba-a337-032821608a91 |  | note | Records - Photos, log
checkpoint-status |  |  | checkpoint | 14 - Drill Rig Set Up
label | 458cc103-0f33-5a7b-825a-ac2b9b12aa86 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 89880d59-bae6-54c4-a414-569c0c65cd8e |  | note | Detail - Check drilling performance, verticality and position using equipment of sufficient capacity for the ground conditions.
label | 309d183f-9e9f-5349-befc-9955d0f5fbc3 |  | note | Frequency - Each Pile
label | 808c6b97-9711-5440-9733-28b34b122cbf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | e05770aa-42b5-509a-aa25-1f1eea175b58 |  | note | Conformance Criteria - Site supervisor to inspect
label | 18f4ad27-33e2-5bca-be44-ab4d22de82a4 |  | note | Records - CS-4011 & CS-4083
checkpoint-status |  |  | checkpoint | 15 -
label | 100bed62-e56b-5a59-86eb-3717fd8f4618 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a2b63a9c-75fa-5a89-ab82-46b730c93a66 |  | note | Detail - Timber poles are installed in pre-drilled holes to the dimensions and at the locations and batters shown on the drawings,
label | d8e6653c-7c2a-5cbe-8853-977e35949f31 |  | note | Frequency - Each Pile
label | bc77a84c-67ed-54c8-85e1-c2a11b1e654e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 8d35eddd-d811-5e8e-9ad2-c55febcdd093 |  | note | Conformance Criteria - CPS engineer to inspect, inspect as accordance with specifications
label | aa923a38-0c76-5059-a041-9b144295041b |  | note | Records - Photos, log, site inspection
checkpoint-status |  |  | checkpoint | 16 - Pile Bore Condition & Logs
label | ae67d3b3-ae21-573f-9e63-140528aab307 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8021aa59-91d7-5995-a4bd-aec79a10a213 |  | note | Detail - Inspect pile bore condition, pile depth, rock socket length and toe level
label | adaca05a-17e2-5b17-a0e5-bdfa3b2e6c32 |  | note | Frequency - Each Pile
label | 30f4febe-7691-5ed3-b7ca-7c6250ec0033 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | aeb31c5c-c146-5669-84a8-4ea763b71d51 |  | note | Conformance Criteria - CPS engineer to inspect, inspect as accordance with specifications
label | a0f637be-9ee6-5814-a40d-9cf78a1c8460 |  | note | Records - CS-4011 & CS-4083
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 17 -
label | e2ddfda9-25c7-5f28-a7f2-39735c11ea49 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 362584b8-7dd7-5990-ba35-60b14ea0a031 |  | note | Detail - The Contractor shall maintain a log describing the type of soil and rock, the ground water level and the general ground conditions encountered in each hole excavation; hole location, reference number, and total depth of hole below ground level.
label | a08b49e6-4e0e-53a1-938f-9c0911e6138e |  | note | Frequency - Each Pile
label | b1a2a91e-11d0-5452-bb39-3785ef4a2f1e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, visual inspection
label | 0ef29b59-6f56-584e-b9e1-a480bdd47101 |  | note | Conformance Criteria - Information shall be provided to the Engineer at the end of each day's work.
label | ef598990-adcd-5ff9-bff0-83cc0a75a7b0 |  | note | Records - Document
checkpoint-status |  |  | checkpoint | 18 -
label | 580092b6-0633-5235-aead-7cd94f4c637f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 23ca0757-3432-56b2-a25c-441887259475 |  | note | Detail - The chosen method of excavation shall minimise overbreak and prevent collapse of ground outside the hole excavation. All loose material is to be removed from the base of the hole before post installation and concreting
label | f97a8dc3-0a74-50f0-b670-13bd5773c57d |  | note | Frequency - Each Pile
label | f0168f8b-cf99-5bee-b1d9-1bd90dc9c82d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - visual inspection
label | f7e31311-1c55-51e5-9985-36655bfaa698 |  | note | Conformance Criteria - Areas of overbreak are to be reinstated in an approved manner
label | aa66ec7b-0360-5e47-904e-12890e3bfb40 |  | note | Records - Monitor, inspect
checkpoint-status |  |  | checkpoint | 19 -
label | bc145fe6-ca34-5bd8-b080-a9e4b8d310d1 |  | note | ACTION (Hold, Monitor, Witness) - M
label | f50ace83-29cb-5634-9419-80491fc41284 |  | note | Detail - The contactor must minimise the impact that the drilling has on the environment.All material collected from the drilling process will need to be removed from the site.
label | 3d3d91e0-741f-5cd3-ae7a-b5c9f7dbe307 |  | note | Frequency - Each Pile
label | 762f4d8a-0335-5b34-9ac1-fa57a4db7f3b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 0973d4fe-90b8-5d56-9a43-44542f3b7e33 |  | note | Conformance Criteria - All drilling must be in line with the EMP and other environmental protection documents
label | 299118da-fc49-5d99-9a83-4a42dd56493b |  | note | Records - Monitor, review document with Environmental team
checkpoint-status |  |  | checkpoint | 20 -
label | d7264ecf-b6ed-527b-aca6-05a3d36e7ed3 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 46070096-7058-58d7-8583-79a4742ea727 |  | note | Detail - Check that holes are not to be left open overnight.
label | bf63a037-3488-51fa-8425-808fd4020f4b |  | note | Frequency - Close of works each day
label | 12acfe02-3b37-5910-afd2-e73c73f1043f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - visual inspection
label | 66903b44-8ad0-5209-afce-0cfc5e87069c |  | note | Conformance Criteria - Site supervisor to check at close of works each day
label | 57edfcd7-90d7-51c8-abde-0c931bf802c6 |  | note | Records - Visual check
checkpoint-status |  |  | checkpoint | 21 - Pile Bore tolerances
label | 6707aec3-f4b7-5c62-8e69-621098d0c89c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8fa464c2-e4be-571c-8a0c-a79b4a4ef78f |  | note | Detail - The Contractor shall inform the Engineer for an inspection of the excavation by a suitably qualified geotechnical professional
label | 94d6083a-cce9-51c6-8828-c170fdb42eac |  | note | Frequency - Completion of stage or bore drilling
label | 60d6fa38-1a9a-5198-b69b-6d026f5284fd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 0cc1f5c4-606d-5e14-a98c-80d1b53d4d96 |  | note | Conformance Criteria - Contractor to notify engineer, Geotechnical Engineer to attend and approve excavation
label | 77de0e13-1253-59a8-accb-e712cd5b51f8 |  | note | Records - Geotechnical Engineer Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 22 -
label | 2020aaa2-3f74-5818-b9c9-2ae37391e865 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 61339f11-5d5e-575a-b8b8-130e2cc4d7b7 |  | note | Detail - The hole must be excavated to the tolerances outlined in the specifications
label | 473ec2c1-3429-5f9c-8aa2-893f1072ddd5 |  | note | Frequency - Each Pile
label | 70d0203d-f399-5d8a-9ece-f2304d595197 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 0292e4dc-0e7a-54cf-946f-2dd0e25efaf3 |  | note | Conformance Criteria - Pole hole diameter +50mm / -0mm
label | 8aadc27a-b3af-51a9-9693-204ff88d8018 |  | note | ○ Hole plan position at all depths +/- 20mm
label | 636d6b9b-0f76-5c8f-aa35-92ec44b13c52 |  | note | ○ The pole shall not vary any more than 2 degrees from 20 degrees
label | f9eed877-3790-5aba-b7ff-ac3aefc66fe4 |  | note | Records - Geotechnical Engineer Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 23 - Timber Pile tolerances
label | 9409dc89-ef39-5302-a668-6060c7eb1bc9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 24075fe3-f938-5a00-a0b1-b55d3499e874 |  | note | Detail - Timber poles shall then be set into the holes, complying with the tolerances outlined in the specifications
label | 9123d3d8-bc3f-591b-b9e3-2285be540e18 |  | note | Frequency - Each Pile
label | ce48f5d4-9580-523b-ab4a-15014e838a80 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 69f4194e-5308-53fb-9dbd-5af30673efd4 |  | note | Conformance Criteria - Deviation of pole centre from line in plan +/- 10mm
label | 4f2093bd-8e35-54d7-a481-a5d375478530 |  | note | ○ Pole top reduced level +/- 10mm
label | 98bbd0d3-5a34-5e64-9ac0-b028dd5a98cd |  | note | ○ Pole base reduced level +/-50mm
label | 1e1cdab8-8851-53fc-a835-ea555f14fe06 |  | note | Records - Geotechnical Engineer Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 24 - Concrete Pumping Operations
label | 65c0f45f-feb5-5e72-aa09-99a4bbac44db |  | note | ACTION (Hold, Monitor, Witness) - M
label | d3f4776f-4c7e-5082-8494-ecff2456a336 |  | note | Detail - Ensure the Permit to Concrete Pump & Pump Operator Checksheet has been completed before concrete pumping commences
label | 5519172b-2ab4-5744-8e86-441f24167fe5 |  | note | Frequency - Prior to commencement
label | 4227f32b-55a5-5f04-bfb8-d42958973a46 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | fdb44cc3-f2fe-5650-b067-1f92368e2f68 |  | note | Conformance Criteria - Site Engineer to compete CP and PO checksheets
label | 7789f216-cda0-5e0d-b0ee-9c5015b6c6de |  | note | Records - CS-4029 & CS-4002
checkpoint-status |  |  | checkpoint | 25 - Concreting
label | b2c1139b-48bd-5988-9ac3-763e9b37fa90 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 946451ba-7f1f-53c4-8e9b-8c6b2e336554 |  | note | Detail - Concrete pre pour inspection
label | 8888825a-a5a8-5bbd-95a0-c9681ce22a0f |  | note | Frequency - Prior to concrete pour
label | 9fb2fa5b-9f25-54db-abe0-b2281663adf8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | d7c05663-0391-57d0-9aa0-60d406d66257 |  | note | Conformance Criteria - A pre pour inspection checksheet to be completed outlining:
label | 94fc241b-08cb-512c-bf0f-91d5fdb52c2d |  | note | – Pre pour inspection checksheet to be completed
label | 5ec7cb45-fa0c-5740-a694-9fa30874c9c2 |  | note | Records - CS-4011/ TBD
checkpoint-status |  |  | checkpoint | 26 -
label | 41d8b3fa-9ef3-51ce-8b02-fc12bf9f1504 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 8abd268c-3f8b-578c-965b-ffacb4e95edd |  | note | Detail - Concrete dockets checked for correct mix and concrete site testing undertaken. Dockets to the Engineer and keep a record of the volume of concrete placed.
label | 44eeefa4-f4f9-5213-b2aa-eb27c01f08e4 |  | note | Frequency - Prior to concrete pour
label | 6958a507-f390-5d44-b15c-b6078ee76b85 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Test Results
label | 3cef2173-e38d-5dcb-ac48-6a0d3f5e7016 |  | note | Conformance Criteria - NZS 3104 Concrete dockets match design
label | a0528c79-1abf-5d65-b2df-5bf91146f656 |  | note | Records - CS-4090
checkpoint-status |  |  | checkpoint | 27 -
label | 603356dd-f642-5f72-8cf5-92688bfeb308 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 7269f070-aa20-50af-a1a7-4b069df3f098 |  | note | Detail - The concrete in each hole shall be completed as one continuous operation
label | b7112cad-2c64-516b-add7-145917a046fe |  | note | Frequency - Each Pile
label | b9fd7a6d-f650-5325-b754-71969cdd2a42 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 79ddcb59-11de-52c3-a263-69e5c00190e1 |  | note | Conformance Criteria - Concrete Inspection Record
label | f647d7c8-6d33-5abe-8e57-5d8fea6916b7 |  | note | Records - Photos, log, site inspection, Document
checkpoint-status |  |  | checkpoint | 28 -
label | 9ea10b46-f5bc-54ee-ae8c-a92e70875f89 |  | note | ACTION (Hold, Monitor, Witness) - M
label | a4a01dcb-c215-53aa-be4b-884a10ca0b66 |  | note | Detail - Securing of poles in position, then the approved concrete mix shall be poured around the timber pole with concrete being tremmied if required
label | fe77ace9-752c-547d-af5e-a0c561cb1818 |  | note | Frequency - Each Pile
label | 3b66de67-0ebf-5295-8278-59e944e1b8e1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 2fa6e6e5-17b6-544d-a02f-74ace7928cee |  | note | Conformance Criteria - Concrete Inspection Record
label | ca2c3e62-a5e1-58a3-95f2-c1516a9a8024 |  | note | Records - Photos, log, site inspection, Document
checkpoint-status |  |  | checkpoint | 29 -
label | c380e777-1ef7-50c5-b894-eb98cccc5021 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 119c3d92-3d7e-54d4-bdf5-cba839709db6 |  | note | Detail - Check concrete placement method and finish
label | f3e8666b-6ba5-5ba5-bd7f-5e79ae30f902 |  | note | Frequency - At completion of pour
label | bbb5f6b9-0ec8-5c7c-b411-973532253a54 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document Review
label | 99922070-ba2b-5920-934a-795c18b84d29 |  | note | Conformance Criteria - Concrete Inspection Record
label | e8760f80-6b1e-5308-a4d3-f541deb39482 |  | note | Records - CS-4011
checkpoint-status |  |  | checkpoint | 30 - Survey As Built
label | fce2bc97-1068-56e0-bf9d-d6888841d75f |  | note | ACTION (Hold, Monitor, Witness) - M
label | d4947f35-a84d-5361-a62a-de30edc3e5e4 |  | note | Detail - Survey final position and R.L. of each pile, produce As-Built drawings
label | 2081d59c-9e89-58af-ae44-36aca89e2318 |  | note | Frequency - Each Pile
label | 8ccc5d34-eb9e-59cf-8eee-b9ef94268fc6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement / Survey
label | 2a51e531-7779-5d1b-a926-28a86c2c578e |  | note | Conformance Criteria - As-Built Drawing
label | 26523812-96bc-5a2f-9bed-e9f2d6c6d697 |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 31 - Lot Number QA File
label | 03b92a6e-5576-5638-bc14-fc0ec883132a |  | note | ACTION (Hold, Monitor, Witness) - M
label | a0a9fed7-a577-561a-a4ff-a28d811727ba |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 8a01c41f-06c2-5630-a963-f5a95d2b112a |  | note | Frequency - At completion of Lot
label | c999b3a7-7777-54e9-845b-c9522a33c62b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 3f566e6f-5adf-542b-bee3-e3211c677995 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | fc523927-ac25-5585-9593-63e90e89f7f6 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 32 -
label | 59c4c592-b0a7-5223-a9dc-5416044cb72c |  | note | ACTION (Hold, Monitor, Witness) - M
label | bf2c2042-a7dd-5230-b058-0eb12ee0a2d9 |  | note | Detail - Check all piling records are completed and signed by the relevant signatory.
label | 4745cb1e-278d-5469-9ce2-5eb87197c471 |  | note | Frequency - At completion of Lot
label | 7117c316-9c1d-5852-8908-d0876a5ec150 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 11f3d9f0-a03c-51f4-b4a6-eaa75bbe2249 |  | note | Records - All relevant documents
checkpoint-status |  |  | checkpoint | 33 - As-builts
label | d8651c18-89ed-5754-9739-3c4e6474d829 |  | note | ACTION (Hold, Monitor, Witness) - M
label | d0424fc1-eb99-5e28-bc90-a86eb219d30d |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 68219caf-3fb6-5eb8-a4d7-ec0ac338cae8 |  | note | Frequency - At the completion of the Lot of work
label | 9dc031ec-9953-542c-a768-15c2b749967a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | 0f0a3b1c-7cd1-5bfc-b665-d84cdd3b4c08 |  | note | Records - Asbuilt Drawing
checklist-flat |  |  | checklist | ITP - Waikare Gorge Descent - C1603A - Retaining Wall & Backfill | itp |  |  |  | Yes | ITP - Waikare Gorge Descent - C1603A - Retaining Wall & Backfill | e4173bd3-2a17-4f67-a764-abb84968d108
checkpoint-status |  |  | checkpoint | Project Site reps.
text | b05bfea2-e0b7-5f61-8c49-5d042c7c60e3 |  | textbox | CPS Eng.
text | 2a96be31-b54e-5467-ab2a-acc26ff09fb8 |  | textbox | Site Engineer
text | 9523ca51-cedf-51f6-b92b-a3000d53ae21 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 4329d3f1-4b6a-5892-9547-9a0f90d2a381 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c21a4a29-a1b4-5e39-b963-a7b3c84f0af2 |  | note | Detail - Contractor to set out grid lines as per contract drawings and specification.
label | d58a3b52-34a9-58d7-a9f4-ee2ede24f51c |  | note | Frequency - Prior to commencement
label | 94bdf949-1ed0-56cd-9cfb-75b2850f63f0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 96aa777d-2a26-5a0b-806f-642e623a6159 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 347d4a71-ea6a-5ffb-be0a-6c783b67fce9 |  | note | Records - CPS Engineer Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Timber Lagging Material Compliance
label | 99f774ff-b79b-537e-a6f6-d519ac5d6b22 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3c299ef5-2e78-57c3-b5d9-2613ceac7dd2 |  | note | Detail - The lagging must be radiata pine planks of normal density, All.
label | 1b3fa55d-b042-5189-b930-719eef1b0f6a |  | note | Frequency - Prior to commencement
label | 2f99d6e6-8e19-5156-851d-d86a7b3e25e2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | f5ce0e92-067c-5d91-b5f9-99e8f30e5bd0 |  | note | Conformance Criteria - The Engineer shall be provided with a certificate of compliance:
label | 8b0a0c81-56c8-56de-9b64-abebe3525eb0 |  | note | ○ H4 treated in accordance with NZS 3640, H4
label | 46770623-7dd9-55cb-ba55-0ecb428a2f6d |  | note | ○ Cut ends or notches shall be treated with a liberal brush coat of copper naphthenate or equivalent wood preservative
label | 2e35b755-49ca-5060-9a13-eb9326c0c6a1 |  | note | Records - Material receipt
checkpoint-status |  |  | checkpoint | 3 -
label | 0ddf14af-6f5a-5b5c-a939-ef4b99798bc7 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 74a967be-0a93-54a3-86ed-9fd2fdb6bc1f |  | note | Detail - Each section of lagging shall span a minimum of three poles.
label | f66c9a7c-658b-503f-ac4d-dd64eaf6791c |  | note | Frequency - Prior to commencement
label | b9ccd96f-5734-5aa3-819b-004e58e205f7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 32b940f8-8ad0-53db-b891-43af5148d2e5 |  | note | Conformance Criteria - Inspect and document span of lagging
label | 9c06dd49-6bac-549d-870d-8f66691c8224 |  | note | Records - Photos, site inspection
checkpoint-status |  |  | checkpoint | 4 - Backfill Material Compliance
label | 23053c83-4c80-5e82-9862-a0a3cdbe72b8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d6ed38bc-b61c-55e0-8123-0a756136f2c9 |  | note | Detail - The granular aggregates for use behind the wall shall be open course graded clean washed durable aggregate
label | e4fd072f-9332-577a-b541-c9746f17b857 |  | note | Frequency - Prior to commencement
label | ad5eb9f2-1ab1-5817-b844-016668c91027 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 5aef291a-5655-58aa-ae3e-583ded8fea9f |  | note | Conformance Criteria - Crushing resistance of not less than 100kN when tested in accordance with NZS 4407:1991
label | 24d1d6d6-b0bb-5b50-bc61-d73d28fe48d4 |  | note | ○ Be crushed aggregate with a min. 50% broken faces (NZS 4407 Test 3.14);
label | 1b01c5b9-3738-5b8e-b3e8-a2f7e7837b9c |  | note | ○ Free of organic and other deleterious material; and
label | 3ec77809-f86a-5308-a70a-d80525bf011d |  | note | ○ Meet the particle size grading envelope outlined in the specifications table in drawing C200
label | a3443625-de32-5127-8b35-ed1a8923fedb |  | note | Records - Materials receipt, test results
checkpoint-status |  |  | checkpoint | 5 -
label | 9cf87e2b-8ed0-5292-a5c8-3f13d65c9c26 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 155ece68-d31e-51ca-9a64-c33726bbb039 |  | note | Detail - The Contractor shall test a representative sample of the proposed granular aggregate to be used to determine the maximum dry density and optimum moisture content, standard compaction and the particle size distribution
label | 386e1c5d-cd6b-5949-a229-cea7f27bf273 |  | note | Frequency - Prior to commencement
label | f63686f6-5b95-5ab3-92f0-7a103a092397 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 945b033a-1387-503b-81ef-c41cfb22d131 |  | note | Conformance Criteria - NZS 4402: 1986 Test 4.1.1, NZS 4402: 1986 Test 2.8 .2
label | 31790dc4-39c0-5b67-bb7e-ac2113c36520 |  | note | Records - Materials receipt, test results
checkpoint-status |  |  | checkpoint | 6 -
label | 0c1e874b-9c14-5a5e-8fa4-12783569fd50 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d572b8a7-1c8a-503a-b9f9-c3d9f7408fe0 |  | note | Detail - The test results shall be no older than 3 months so that they represent the actual proposed materials.
label | edfe4dcc-4982-5dd6-bb56-bdb5ecfc913c |  | note | Frequency - Prior to commencement
label | 5d9982a6-9322-5856-b40b-2acb1ddebdfe |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | fb1d7ff8-9267-548e-8772-c5e1aceeb341 |  | note | Conformance Criteria - Check testing results are less than 3 months old
label | 2427b484-4b7f-5e72-869b-52a2ce9215fa |  | note | Records - Materials receipt, test results
checkpoint-status |  |  | checkpoint | 7 -
label | 936002f7-7ec5-56cc-9c99-20d9ced3c6a0 |  | note | ACTION (Hold, Monitor, Witness) - M
label | e5407c15-61c0-5592-ab4a-56f30e6b0dda |  | note | Detail - All material sampling and testing shall be completed by a suitably qualified laboratory and laboratory personnel
label | 0b5648c0-8252-57cc-b36f-1d06255b68a7 |  | note | Frequency - Prior to commencement
label | ca460067-51d7-5f21-980b-60b8e36b4169 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 152845bf-694f-5823-9ad5-f7539bcb8193 |  | note | Conformance Criteria - IANZ registered laboratory, laboratory certified to ISO 9001 or 9002
label | 773c0a4d-190b-56b9-ab56-7f4350ced8b7 |  | note | Records - Certification
checkpoint-status |  |  | checkpoint | 8 - Geotextile Material Compliance
label | c1985ada-a9d8-510a-bedd-fbacc49414c4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c3a6cacb-3758-5b4b-9c5e-c09354bf0653 |  | note | Detail - The geotextile filter fabric lining the excavation and wall, Examples of acceptable materials are 'Duraforce AS410' and 'Bidim A29' or similar approved equivalent.
label | 27ac0d5d-6938-56d8-a42d-a43252f70acb |  | note | Frequency - Prior to commencement
label | bc3d112c-d1b9-5a26-9f39-5f79d87c9878 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 8debf3f3-59a2-5ad3-971f-0c4e757f0868 |  | note | Conformance Criteria - non-woven geotextile and meet the requirements of TNZ F/7:2003 for strength Class C and filtration Class 1
label | 53858759-a35b-5dd2-80f3-f107a68827e1 |  | note | Records - Material receipt
checkpoint-status |  |  | checkpoint | 9 -
label | 87be8b32-3956-517b-b7dd-2bb94b2512ca |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1ce60f18-6c5f-5b19-b242-69d28a1ff722 |  | note | Detail - The geotextile's properties, testing, storage and installation shall comply with the requirements of Transit NZ
label | ec4bfe89-a947-5b2d-85cf-0f4536dd2ad9 |  | note | Frequency - Prior to commencement
label | d69eec38-ab1a-51a5-a474-55dd678455a4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 5ab17b54-faff-570a-b4e0-5edd8aba0999 |  | note | Conformance Criteria - TNZ F/7:2000
label | 89586a6d-81f7-5d79-a461-d170221d1446 |  | note | Records - Material receipt
checkpoint-status |  |  | checkpoint | 10 - Subsoil drainage Material Compliance
label | 98f825df-5442-56e6-adc9-6a3881ef930d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 6310b2ec-61d2-52d8-9398-7d5977d25be9 |  | note | Detail - The subsoil drainage pipe shall be smooth bored, perforated 110mm dia. HDPE or PE complying with NZS 7604:1981 and TNZ F/2:2000. The perforations shall be circular 6.5 mm (+1.5 mm) in diameter, arranged as shown in the Appendix 1 of TNZ F/2:2000, “Pipe Subsoil Drain Construction”.
label | 6e532b45-080c-52f0-b1a6-7284b2082b9e |  | note | Frequency - Prior to commencement
label | a422761f-1118-5020-9c35-ad288e4b383b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 71408f06-e6bb-5e40-8ab5-3a81f518859b |  | note | Conformance Criteria - complying with:
label | 07c6ae30-b833-582c-98a1-fb3bfae112b1 |  | note | ○ NZS 7604:1981
label | 7941c2af-c3f3-532a-b427-fbfc4cc571e1 |  | note | ○ TNZ F/2:2000
label | 04ef69ca-f686-54a1-aa34-5bd7e6e45f24 |  | note | Records - Material receipt
checkpoint-status |  |  | checkpoint | 11 -
label | 425308fa-d004-50c0-bdee-289e1de85a8d |  | note | ACTION (Hold, Monitor, Witness) - M
label | d020f1bf-e6e1-5dd7-b0c5-11ee4656a1c5 |  | note | Detail - Outlet and connecting pipes shall be unperforated.
label | 89301b0d-2b01-53d1-9788-7e3d3a143023 |  | note | Frequency - Prior to commencement
label | 782b02b3-647d-5fcb-9891-c103bce845a0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Visual Inspection
label | cdd21bdf-985c-5c7d-871c-eb957f6a100b |  | note | Conformance Criteria - complying with:
label | 428e18d5-93dd-5a24-b98d-fce5facd5339 |  | note | ○ NZS 7604:1981
label | 4ee6774d-7c2a-51ab-a54c-8a9615a8c36f |  | note | ○ TNZ F/2:2000
label | 74152d46-a8e8-53dc-ae8f-54075201fc1c |  | note | Records - Material receipt, site inspection
checkpoint-status |  |  | checkpoint | 12 -
label | 9e1999fb-fb8e-56bd-a1f9-a66c8723e89c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0d5f8085-0a2d-5c8c-9167-561aaf565239 |  | note | Detail - The drainage pipe shall be wrapped in a drainage blanket geo-composite, such as 'Filter sleeve' or equivalent approved.
label | 4e990a0c-a7a7-5055-bffc-b15493b846d6 |  | note | Frequency - Prior to commencement
label | cd165d5c-bb17-572a-be96-dd09181ea6b4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Visual Inspection
label | fad49e43-0c8d-56dd-ba5a-80f5359d9100 |  | note | Conformance Criteria - Confirm drainage blanket before install
label | 0f2d605f-e2e9-5586-9168-b1835238ffd5 |  | note | Records - Material receipt, site inspection
checkpoint-status |  |  | checkpoint | 13 - Timber Lagging Installation
label | a635a422-c016-5076-8694-6a6b74affb26 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 0a59807b-740e-5e8e-be58-747cf855959f |  | note | Detail - The timber lagging shall be placed against the back of the poles so that they fit closely to the poles and to the lagging board below. Only lightweight compaction to be used within 0.5 m of lagging with care to avoid lagging deformation.
label | db68d73b-1622-5dca-afd6-9da1b201491a |  | note | ○ All lagging joints shall be located against a pole. Lagging joints shall be staggered so that there is a continuous lagging board above and below each joint.
label | f76fa834-f0e8-56aa-bdfe-e0bbdee97b0f |  | note | Frequency - Pre/ During install
label | 0b5e4d3d-2e71-579c-ab4c-94f86c9805f9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | eeee478b-e909-59b0-87ae-2b1806f95a21 |  | note | Conformance Criteria - Confirm lagging is placed correctly, and no heavy compaction conducted within 0.5m
label | ad15b6b9-7d06-522d-a31c-a864b081a615 |  | note | Records - site inspection, Photos, log
checkpoint-status |  |  | checkpoint | 14 -
label | cc9695be-0b06-5c3a-a311-1d712921f8d6 |  | note | ACTION (Hold, Monitor, Witness) - M
label | ca6dda3d-1aea-5efe-b704-6ea460ea8a4e |  | note | Detail - The lagging shall be held in place using screws. No boards with obvious defects shall be used e.g. severe warping, knots etc.
label | 694dba47-dbfc-5132-8698-a9b9a46ce969 |  | note | Frequency - Pre/ During install
label | 654701fb-66b7-57d7-966e-672cd9aac491 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 53820310-ee37-5364-a092-33b461ef6f2b |  | note | Conformance Criteria - Confirm and document screw installation is correct and lagging timber is appropriate
label | 73ca901b-1876-5f27-bdf0-2f2761b4645f |  | note | Records - site inspection, Photos, log
checkpoint-status |  |  | checkpoint | 15 - Geotextile Filter fabric installation
label | 5075f4ec-0ae6-5f15-bd80-b3882c580a66 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 9d061467-9ed1-5a5e-aae1-2a3a3e984933 |  | note | Detail - Geotextile filter fabric shall be placed in the locations shown on the drawings. At joins the fabric shall be overlapped by a minimum of 200mm.
label | 9b9a7aa7-ab0b-5ac3-9a5b-171648cb1a10 |  | note | Frequency - Pre/ During install
label | bc28438b-1578-5726-97b3-2ce0a2d3dffc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 90c45369-f62a-5965-8f50-1ab5cf5065d7 |  | note | Conformance Criteria - At joins overlapped by a minimum of 200mm
label | 690d8337-9de8-5ed3-871a-63093074b164 |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 16 -
label | 3c55b368-725c-5aaf-86b2-c360c1f8ec5f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 9dcc0ac7-1354-5e84-8341-a3fed103d55d |  | note | Detail - The Contractor shall take care not to damage the fabric during installation. Any tears shall be repaired at the Contractors expense by placing additional fabric over the damaged area, with a 200mm overlap on all sides
label | 0c57c9d2-f624-5807-b96c-1d5217f2b0d1 |  | note | Frequency - Pre/ During install
label | 5c628d35-a8cd-568a-9839-41f69bdf3c48 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | fb9229c8-a2f3-576c-b5da-05a7de54588a |  | note | Conformance Criteria - tears shall be repaired by contractor, overlapped by a minimum of 200mm
label | b615a9c4-7287-5011-80dd-96d748a8ea43 |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 17 - Subsoil Drainage
label | 2b436e13-f6d4-5b56-b741-e05eb0562cc8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b89d01d8-1eb6-5b4c-8785-7abd4d06570e |  | note | Detail - The subsoil shall be placed as shown on the drawings. Outlets from the subsoil shall be constructed to discharge water clear of the site, onto stable ground, with sufficient fall across the length of the subsoil pipe to prevent silting.
label | a1b40941-d41d-5ee0-b984-a8f56341f93d |  | note | Frequency - Pre/ During install
label | 7c3af5ce-9b67-5bf7-bc5d-2a14cf3d8687 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 7f7616a2-f76b-56fa-98de-09d59730aa51 |  | note | Conformance Criteria - Outlets from the subsoil shall be constructed to discharge water clear of the site
label | 16e67474-8c45-55ad-8d25-b9082066aa37 |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 18 -
label | a589d508-f4c5-518e-b9b3-b9df08cf53fe |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0f274aa9-746f-55d3-a628-a7e571a2d542 |  | note | Detail - The location of the outlets shall be determined in conjunction with the Engineer on site
label | 1d6369d8-d627-5516-9af5-9fa2a1d8e27c |  | note | Frequency - Pre install
label | eb87262a-f602-56f3-887b-2c06187a55b7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, Document review
label | 9f9a94a1-4ce6-558a-a9e2-e3a42557e624 |  | note | Conformance Criteria - HOLD POINT: CPS engineer to review and approve location of outlets
label | 65b9d6a3-258d-5998-bc26-d48fc7dbe62e |  | note | Records - CPS Engineer Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 19 - Retaining Wall Backfill
label | 86509298-765d-55c7-b502-036dad0e36d7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3ba880b4-369f-51e7-acba-a89d3f81eac5 |  | note | Detail - The Contractor shall ensure that the method of placement and compaction permits safe labour about the excavation.
label | 52675688-027e-56b7-8f50-3752a92af42d |  | note | Frequency - Prior to commencement
label | 97dc0b60-6f2e-5703-9aee-4f3963c71de8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review, Visual Inspection
label | f2c26d0f-55c3-5691-993e-70c581e5c25b |  | note | Conformance Criteria - Temp works confirmation for excavation area, for placement and compaction
label | 731e0261-8ba3-570b-b337-178aac7176c6 |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 20 -
label | cb343e8f-29c7-54a5-bba9-779308cf3652 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 314e56dc-c805-572a-8b75-5f73fd6fd58a |  | note | Detail - Lightweight compaction shall be undertaken within 1 m of the wall face, to prevent damaging wall components.
label | 5647a9f0-6bc9-5307-8eca-29ec342a2831 |  | note | Frequency - Pre/ During install
label | aa9a3dae-1bdc-5c10-976c-e493f8e4fcfc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | c1078d49-f3d1-5fee-8589-549b69d85c0f |  | note | Conformance Criteria - Not heavy compaction works within 1m
label | 58b9ae4f-3fa9-5679-9c98-85ce6f06415c |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 21 -
label | e71d75f6-db7e-59f6-a42a-d9957620ca2c |  | note | ACTION (Hold, Monitor, Witness) - M
label | c746a2e7-2b49-5596-96b9-a6b941b42a24 |  | note | Detail - The backfill material shall be placed and compacted in layers of no more than 200mm loose depth. Each layer shall be compacted by hand operated mechanical plate compactors, heavy compaction may be used from 1 m behind the wall to aid compaction.
label | 8731b274-466a-5971-b504-7e2a7086163c |  | note | ○ Care shall be taken to avoid striking or damaging the wall components with compaction equipment.
label | 4c7f24db-06ce-5e16-9ea5-959d69d3c414 |  | note | Frequency - Pre/ During install
label | 4d1fd0f3-2dc9-51bb-82a7-a7cf6f87e2e8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | afb098b9-f4f7-5016-ba03-9e1388df5b3a |  | note | Conformance Criteria - Compaction shall be no less than 95% of the Maximum Dry Density, heavy compaction may be used
label | 50f90d85-cc5d-5656-bbef-c02f4dddcc7c |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 22 -
label | f49bf372-aa4f-5413-a427-bf06584b18ef |  | note | ACTION (Hold, Monitor, Witness) - M
label | 793b562b-0201-5fe3-b38a-7c6d922a3c5b |  | note | Detail - 1m behind the wall compaction requirements vary from within 1m. But Care shall be taken to avoid striking or damaging the wall components with compaction equipment.
label | d0d3250b-271e-5f1c-bbc7-ede58b4d3dec |  | note | Frequency - Pre/ During install
label | ee1deeb6-a60b-533f-9943-3f4ee4866c13 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 417a8204-4ad4-51ca-9cea-963ab023e9d3 |  | note | Conformance Criteria - Compaction shall be no less than 95% of the Maximum Dry Density, heavy compaction may be used
label | 446d5e87-c759-559e-b25f-8d09d07c8a35 |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 23 -
label | fedba573-c4bb-51f6-b10d-53cf12018278 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 73eab55f-f099-504e-93a7-7c7f78cc0536 |  | note | Detail - At least 3 sets of at least 5 NDM tests shall be carried out, Back-fill shall be compacted in layers no greater than 200 mm loose 'lifts'. Clegg Hammer tests shall be conducted every second lift along the length of the wall.
label | 4dc9278f-96d2-54a2-b233-61d458646b1b |  | note | Frequency - During install
label | 2f328b11-170b-54b5-a9cc-b65892b94857 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 51467152-ba2a-5325-ae6f-e36a90a37708 |  | note | Conformance Criteria - l 3 sets of at least 5 NDM tests
label | 658f2408-24cd-5cf2-9c66-1beaf70a83c8 |  | note | ○ Carried out at approx. 1/3, 2/3 and finish level.
label | 37f43e8e-1ccf-56d6-bf42-f979fc9ad229 |  | note | ○ Results shall be forwarded to the Engineer within 24 hours of the tests being carried out
label | dfe1bc85-05f7-5745-99f1-320d69ef597e |  | note | Records - site inspection, Photos, test results
checkpoint-status |  |  | checkpoint | 24 - Subsurface drainage
label | 05e2d470-b159-58e5-b65e-70beb3e3c710 |  | note | ACTION (Hold, Monitor, Witness) - M
label | fb709d71-9b06-5f60-9cfb-4ecda70b4f75 |  | note | Detail - All the surface water should be diverted away from the proposed retaining wall.
label | 7a60a9ba-9256-5359-8b68-61b00eb8661c |  | note | Frequency - Pre/ During install
label | 91b520ee-e5c8-5f1d-be6f-6891b4ca48af |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | a7127de8-4e21-5dca-a89b-d6bc613d713f |  | note | Conformance Criteria - Subsurface designed on site in a way to ensure surface water is diverted away from the retaining wall.
label | da2106af-2c82-54a7-8534-6041685bf2b1 |  | note | Records - site inspection, Photos
checkpoint-status |  |  | checkpoint | 25 - Survey As Built
label | 2055fb05-7dd8-50d8-a9b2-9f8e8a83325a |  | note | ACTION (Hold, Monitor, Witness) - M
label | 66f2b5e1-95cd-5f03-a256-72a7558bfe06 |  | note | Detail - Ensure all works comply with design prior to carrying on with next construction process
label | 9007b607-ea8f-514f-98e7-6a1122dffb8a |  | note | Frequency - At completion of sub soil drainage line
label | 59bd4bcd-4a76-5d9b-8677-359550ddbb79 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | a8a86f5d-9ec2-524e-b115-fac809a4154e |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 26 - Lot Number QA File
label | 6a8f9592-6196-5512-800a-bf2b76954b7f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 75c03242-6f66-5f36-82b3-88029f4bf65f |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 1873fe6c-886a-5247-a522-3575abd4c444 |  | note | Frequency - At completion of Lot
label | b743ee8e-48e0-58ae-a41b-241c1c5b36a0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 1266a891-6783-5a8e-80dd-1720b3479860 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 3b403cf2-21a8-5800-ac79-c1fdd684725a |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 27 - As-builts
label | 0efbfb4f-4a08-520a-a507-bb4f060cf59b |  | note | Detail - Red pen mark up drawings to be included in QA file
label | 09730124-cc66-5576-b4cc-600d0ac85f98 |  | note | Frequency - At the completion of the Lot of work
label | 74271c37-7ade-54a3-90b0-e0ac0b2580f1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | b996e380-26be-5920-a949-63d25944c0b4 |  | note | Records - As-built Drawing
checklist-sectioned |  |  | checklist | CS-4117 - Guardrail Installation Record |  |  |  |  | Yes | CS-4117 - Guardrail Installation Record | e5c687f4-47c1-4fef-a1a1-07713208fa4a
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | Details
text | 762995b5-7add-55d5-b62f-5bb6eae04957 |  | textbox | Work Area:
text | bb19bd0b-fe7c-5758-87e6-dd93aaa50a46 |  | textbox | Sub Work Area:
text | 4352b99c-37e9-52b0-b2ad-903de552c8e1 |  | textbox | Lot:
text | 0db56f97-32be-55a1-8abd-44885e495cba |  | textbox | Sublot:
label | 2e81df1d-4ab5-58d3-b936-009bd45557a5 |  | note | Document Date: 27/11/2019
label | d540d46d-1cdf-57c0-8b06-e14996777a8b |  | note | Created By: Kirsty George
text | 16ab1770-4e2b-5db6-8f62-83501414098e |  | textbox | Drawing No:
text | e1f91275-78d3-5bc7-a2a7-e68fc9e645ac |  | textbox | Rev No:
text | 2512424c-e948-587a-a6a9-0bf644e7bcac |  | textbox | Chainage:
checkpoint-group |  |  | section | Guardrail Installation
checkpoint-status |  |  | checkpoint | When driving post, use a driving cap with timber or plastic insert to avoid damage to the post
text | 5d5b4abf-232b-5725-8eab-7beb902aae18 |  | textbox | Initials:
date | dc0ae872-e8a4-5854-b999-d531dc9db4e4 |  | date | Date:
checkpoint-status |  |  | checkpoint | Height to centre of rail is 635mm
text | f700a609-20af-57a3-9a7e-5dd10c031862 |  | textbox | Initials:
date | fdc3dfa5-bb92-5722-be4b-d93cc2335277 |  | date | Date:
checkpoint-status |  |  | checkpoint | Top of post should be a minimum of 20mm above top of guardrail
text | 7e1312cc-a92f-5cd3-9b70-81abee65e354 |  | textbox | Initials:
date | d6a72b2e-db4e-511a-b7fb-903c1126f083 |  | date | Date:
checkpoint-status |  |  | checkpoint | Post is aligned with flanges rail for road side applications and alignment is alternating for median applications
text | c9ba258f-6621-5081-8d96-5e055ff1ac30 |  | textbox | Initials:
date | ca7c0337-303a-5dcc-9906-6306d183905b |  | date | Date:
checkpoint-status |  |  | checkpoint | There is a 90mm dia. Washer between rail and post.
text | 276338da-704a-523f-8c74-396fd4feecba |  | textbox | Initials:
date | f5c7abc2-efc2-5d8a-b7c0-ce86d5ec7288 |  | date | Date:
checkpoint-status |  |  | checkpoint | Rail is lapped in the direction of traffic
text | 7740af7e-fc30-569c-9021-32626b6d17cf |  | textbox | Initials:
date | d5807dc4-e8d7-5b02-8a58-67523cbb1eef |  | date | Date:
checkpoint-status |  |  | checkpoint | All bolts are fully tightened
text | 9407cdd0-de00-5863-a421-756106e00037 |  | textbox | Initials:
date | 6185fad5-1c64-5c68-9691-c5608523711e |  | date | Date:
checkpoint-status |  |  | checkpoint | Nut on backside of post is a splice nut
text | 6491e48d-def6-52bb-a680-873dbe1aa09d |  | textbox | Initials:
date | b05b42bd-8e05-55c4-8109-82349fd585f7 |  | date | Date:
checkpoint-status |  |  | checkpoint | If a median installation-excessive bolt length is cut off on backside
text | 9551fc6b-1e9a-571c-afa9-1e36d93c2042 |  | textbox | Initials:
date | e7830b87-8db5-5841-8f0c-a81e3d79d903 |  | date | Date:
checkpoint-status |  |  | checkpoint | That transition details to existing guardrail or terminations are correct
text | 9d03d1a5-a8d8-5e64-b007-11734e27f86d |  | textbox | Initials:
date | 5525a21a-b888-5770-90e6-c23c6d2f524f |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | 48c407a6-2e44-5b46-a0ef-2e24e148aed4 |  | note | Position: Site Engineer
text | 04e48ccc-45fa-57f2-91ab-335e60f0e3d2 |  | textbox | Site Engineer - Name:
date | db4c1d0e-38e7-5ece-ad51-f618c3efbfb3 |  | date | Site Engineer - Date:
label | f1efec51-86fb-581c-9f8e-8b8c0bcccd13 |  | note | Position: Design Engineer
text | a3b16058-6aab-5206-95ba-b8a2d8c5aaa1 |  | textbox | Design Engineer - Name:
date | 55f5aa34-62d7-52c6-ac41-c6626b46e35a |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | SIGN
checkpoint-group |  |  | section | Thriebeam Installation
checkpoint-status |  |  | checkpoint | Panels are pre-bent to suite curves.
text | 4d502998-b501-5552-85f4-2229da23d4cb |  | textbox | Initials:
date | f20a4d75-7173-5bb6-8001-dde1312ee5d0 |  | date | Date:
checkpoint-status |  |  | checkpoint | The rail height is in accordance with the plans and specification.
text | 6c95fda2-3ba3-5cf3-ae93-cde2fc8e7ba1 |  | textbox | Initials:
date | 90eb94fb-5c54-5e86-8ff8-24cfc27e91dd |  | date | Date:
checkpoint-status |  |  | checkpoint | Correct lapping of rail away from the direction of Traffic.
text | 8b14e66e-8525-540d-bd22-bb3e68300465 |  | textbox | Initials:
date | ea1b0527-3e19-5ae2-9c9e-df9b1d31de1e |  | date | Date:
checkpoint-status |  |  | checkpoint | Timber block outs secured to the post.
text | 3e08086a-91ee-53bd-a269-02d81dadc207 |  | textbox | Initials:
date | 1d6e51fe-e569-5002-9ec8-536a3fba72eb |  | date | Date:
checkpoint-status |  |  | checkpoint | Rail is aligned and level.
text | b794102a-71fb-5238-a5b3-647d38056360 |  | textbox | Initials:
date | 14d373a8-e011-5727-851d-584f713401a5 |  | date | Date:
checkpoint-status |  |  | checkpoint | Posts align, at correct spacing and backfilled compacted.
text | 10ba481b-abba-5c45-94cd-fdfe4a4fff42 |  | textbox | Initials:
date | 223fa954-12e9-5811-9bb1-e32278abc32d |  | date | Date:
checkpoint-status |  |  | checkpoint | Post bolts are tight and washer is fitted at the back of post.
text | 23735155-9320-5789-9da9-39ec949cd442 |  | textbox | Initials:
date | d74eb590-0d64-5653-8fe0-b373d0d88687 |  | date | Date:
checkpoint-status |  |  | checkpoint | Backing pieces are fitted at the intermediate post only.
text | a983f808-79e6-545f-a20a-7d82a70b3629 |  | textbox | Initials:
date | 6873306b-0d99-5ca0-8c58-4af8d2bb1dd7 |  | date | Date:
checkpoint-status |  |  | checkpoint | With flange based post the necked bolts are installed with washer.
text | a4ea5f67-5fe4-56da-aa2e-1238b06ea677 |  | textbox | Initials:
date | df1804a6-ec13-5f88-9be0-e948216fb80f |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | 12e8b40e-cf33-5ab5-a850-0f4700194a4f |  | note | Position: Site Engineer
text | e7ee4af6-69ca-5ff0-b8da-a5faa8d165da |  | textbox | Site Engineer - Name:
date | 5ce474b2-2385-5783-925a-302e99521b87 |  | date | Site Engineer - Date:
label | 3572089d-3d9a-5629-92be-cb0a89436f26 |  | note | Position: Design Engineer
text | e18e1c45-8b85-51e7-96bf-29da47c0ce96 |  | textbox | Design Engineer - Name:
date | 45097ad1-a46f-5a05-82a7-acf9778ac485 |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | SIGN
checklist-flat |  |  | checklist | CS-4120 - Wire Rope Installation Record |  |  |  |  | Yes | CS-4120 - Wire Rope Installation Record | e8461a3a-9f61-4d15-b758-5ddc189c2b0b
checkpoint-no-status |  |  | checkpoint | Details
text | bd89f5ec-530f-5a17-97b8-ed0e275aa818 |  | textbox | Work Area:
text | f9a69b0b-e222-5da9-a300-b38478453d27 |  | textbox | Sub Work Area:
text | 5c9ed7a8-b00f-5691-90d4-6eafcfa2c721 |  | textbox | Lot:
text | 99a194b0-23b3-5406-885b-2897615753a5 |  | textbox | Sublot:
label | 9240f3f7-406c-5786-ade4-1eb95345047f |  | note | Document Date: 27/11/2019
label | cd02a07d-a685-5edf-8111-40b3d441998f |  | note | Created By: Kirsty George
text | 6079db1b-2513-5783-b0ae-9fc76a513021 |  | textbox | Drawing No:
text | f9d58335-bb05-5247-bc34-06e4eb7fbd84 |  | textbox | Rev No:
text | c405b6cc-7c85-5934-bc80-0c930aa44a7e |  | textbox | Chainage:
checkpoint-status |  |  | checkpoint | Drilled holes spacing does not exceed 3M and are 300mm diameter and 750mm deep.
text | 3ad278a2-6266-5f6d-8845-6955e60dbed4 |  | textbox | Initials:
date | 3dfc7c5d-3bf2-5b5a-bd54-8720097cd6b4 |  | date | Date:
label | 2e331c0a-cd54-596d-b7c3-277ab8a57189 |  | note | Comments: Consistency with Construction Drawing, Details and Notes.
checkpoint-status |  |  | checkpoint | Concrete is 25Mpa.
text | 17808ae9-666e-58f2-87ba-34b1a5347887 |  | textbox | Initials:
date | 2a74f5c1-68d7-5a5d-82fb-95b0680e9488 |  | date | Date:
checkpoint-status |  |  | checkpoint | Concrete Dockets Collected
text | f8ffba2e-6b1b-54f3-bd03-894e0cb66ef5 |  | textbox | Initials:
date | 8ac9bf2a-b9ea-5613-a7fd-76d9a2d93f12 |  | date | Date:
checkpoint-status |  |  | checkpoint | The plastic Socket is correctly positioned and a rebar ring is placed 100mm down from top.
text | a7819c9b-3463-58f5-b190-afba77241acf |  | textbox | Initials:
date | 5b607d29-63bc-58a2-85c4-e04f80b11a0b |  | date | Date:
checkpoint-status |  |  | checkpoint | Post are installed with slot orientation consistent for the entire length of the barrier.
text | 11fed7f7-ad62-5469-afeb-94150d06d714 |  | textbox | Initials:
date | 8fceaefb-5918-5db3-97ce-362698688337 |  | date | Date:
checkpoint-status |  |  | checkpoint | Top 2 Cables are positioned in the Top slot while the bottom 2 cables sit at the bottom of the slots on either post
text | 14ba0108-9ac2-5904-a9a6-d6100629e346 |  | textbox | Initials:
date | 27d462c3-e460-5bee-9551-719b9d43ac8f |  | date | Date:
label | dedf9864-3766-5ce8-a2fd-68d3cd6f190f |  | note | Comments: Cable Heights 530, 650, 770 and 790mm (+ or – 30mm)
checkpoint-status |  |  | checkpoint | Ensure no corrosion to the internal collars at swage connection
text | 3f96a15b-59db-5e6d-b617-7d2154782c4c |  | textbox | Initials:
date | 46eb642d-3baf-50cf-a521-9cd0c3aa2c27 |  | date | Date:
label | e8da1347-21e7-5517-a4e0-0ac8574fe2b4 |  | note | Comments: Also check swage seat & collar thread connection. Should be tight and should not be able to undo once in place.
checkpoint-status |  |  | checkpoint | All posts have a plastic cap inserted in the Top and pushed hard home.
text | 9e4b3009-5137-5614-b5b6-222190f79be6 |  | textbox | Initials:
date | 3160ed1d-fdaf-5a7a-a314-1adefc52c905 |  | date | Date:
checkpoint-no-status |  |  | checkpoint | Comments:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | 6e738399-ff08-52ec-954a-2eed5214a172 |  | note | Position: Site Engineer
text | 80b62557-72d8-5787-ab63-396a87c0da3b |  | textbox | Site Engineer - Name:
date | 4d35e144-3807-5bbb-81e8-8e30564763e4 |  | date | Site Engineer - Date:
label | c58add1e-a3ed-53cc-8422-a0bbce57eb4e |  | note | Position: Design Engineer
text | 116ab345-e079-5d1a-ae99-1b0655171ad0 |  | textbox | Design Engineer - Name:
date | 9970b52d-881c-524b-a836-b13f7361285b |  | date | Design Engineer - Date:
holdpoint |  |  | signoff | SIGN
checklist-flat |  |  | checklist | ITP - Mangahuini Sheet Pile Wall - F3002G - Earthworks - Bulk Cut | itp |  |  |  | Yes | ITP - Mangahuini Sheet Pile Wall - F3002G - Earthworks - Bulk Cut | e960010f-82d1-4b8e-b659-ffb1fcc3dbc4
checkpoint-status |  |  | checkpoint | Project Site reps.
text | f7eb4be8-0141-5220-a9bd-b6dc1240d70b |  | textbox | CPS Eng.
text | 5f1e35c7-a05b-5bca-96a2-36e336cfb902 |  | textbox | Site Engineer
text | 106042a6-bd71-5857-b6ae-53d4ef2f908e |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | 54e656aa-b6e4-57c5-b6a3-2280c6d19067 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d490be53-6bac-509b-b04d-d04ade180eb1 |  | note | Detail - Set out extents of fill and check against design drawings
label | 5caa6f5d-0259-5132-9946-a9a185488a78 |  | note | Frequency - Prior to commencement
label | 76c748ae-8ffc-51d4-9f7b-a82d9b652aec |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 3adb0d78-c4cd-5b94-8c8d-ceb02c730d91 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | bd5693a5-6693-5ca5-8e58-ff4f4abf1638 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Excavation (1)
label | 620b8bec-88d6-542d-8095-eef0c61d5bb4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 38818efb-c17b-5d40-9b3b-562eb2f14c5e |  | note | Detail - Ensure that all top of batters are rolled over preventing erosion & slips during/after constructions
label | bd77c310-c4d3-55f6-b6af-67564ac5c05d |  | note | Frequency - During construction
label | 1de98e51-1ded-52ef-b0fb-01d2f3e21e7a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3bcb9200-d7a7-5dc5-a82e-b31bd80b0936 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 6d16b584-890d-581b-9695-bd378a76a709 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2 - Excavation (2)
label | 77aa6537-6194-5382-99cd-fe58ad53e2f1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ddfaefb6-53ea-5615-adf9-cb9b68f08b35 |  | note | Detail - Existing ground/bank & foundation for rock toe to be excavated/trimmed to remove any deleterious and loose material
label | 70255cc2-0852-5231-a3ae-d573ad36bb0d |  | note | Frequency - During construction
label | dd5a9a59-0039-5dfe-9e0d-677033320e89 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 89f34932-d1b8-54f3-96c0-64f9b7454d5d |  | note | Conformance Criteria - CPS Engineer to inspect and approve trimmed surface & founding level material before proceeding further.
label | 848fbb3f-f9ef-5f45-8dda-66010f8d21c6 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 - Geotechnical Inspection
label | 39618f64-ead8-5905-9511-11baaa6bf042 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 03fb03ba-bc1f-5ed0-bbbb-18ac46909d3c |  | note | Detail - Any areas of concern with the face at any time, ensure the Geotechnical Engineer is involved and any changes that are required are documented
label | cf1720b0-1282-5ddb-bb24-ba53fbe6a119 |  | note | Frequency - During construction
label | 259b541e-f4a4-5edc-81bb-57e6911ac0fc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | e973c19f-a5e6-551f-94e3-2415067b4961 |  | note | Conformance Criteria - NTC/NFD
label | 6f59361b-3e11-5d1b-b9f2-1ee0b19882f8 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 -
label | e4261c2b-640d-5848-9af8-4b6ae5b2b03d |  | note | ACTION (Hold, Monitor, Witness) - H
label | ae0dc4e4-efdb-5691-b026-b1ca3c2ccc7c |  | note | Detail - Any changes to the design (soil nails, rock bolts, shotcrete etc.) are to documented individually
label | 5ed9949b-8a42-58c3-ae8f-25a70881c4e0 |  | note | Frequency - During construction
label | 79f97b6e-38bd-5a8b-aba4-5facd09d9228 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 426310f3-f03b-50ef-abf2-9df9547f8422 |  | note | Conformance Criteria - NTC/NFD
label | 2cca6452-dd9d-5dcc-8230-241aa59aa246 |  | note | Records - CPS COR Report, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Formation
label | ddd8ef40-563e-5d1e-957c-948031c85b62 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6d89dd5d-d29e-5c1a-9688-8723aed46b8e |  | note | Detail - Once cut is down to Formation level complete Scala check sheet
label | 78a3350a-6e62-517c-b6d7-b3255d94b255 |  | note | Frequency - At completion of section
label | c2994f46-c4f2-5b7e-9bc0-779eafddfb91 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 7c9c1aae-a3ef-5f9e-a7bf-e34a04f471ae |  | note | Conformance Criteria - As per design/drawings
label | dabba7bd-1843-583a-87d8-6450027dfe45 |  | note | Records - CS-4000 1M Scala check sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 8 - As-built Survey
label | 766b3879-e3c0-5646-88b6-22f900b40ad0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c60e1edb-b1a6-56ee-800f-3928023f881a |  | note | Detail - Ensure cut/fill slopes comply with design prior to next process taking place
label | 8b0ec46e-7ccf-5afc-95ec-f66fdac9243f |  | note | Frequency - Prior to placing topsoil/pavement/ finished surfaces
label | 672060c6-444e-505a-ac45-cf14c4757a36 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | dd9b1392-6182-5906-ba0e-1e7387b97d59 |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | b0c7b74d-0ec2-5e46-b5fe-e9de94b3e94a |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Quality Assurance deliverables
label | fe445447-aeb7-5059-b06f-08596ca7df9b |  | note | ACTION (Hold, Monitor, Witness) - W
label | d09e44e8-d5e1-5151-8c31-28c04ae21732 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | c754de72-6f21-5d5d-a3e8-e0f6143af8e8 |  | note | Frequency - At completion of Lot
label | c1d25cf8-ec42-591f-b621-87336127da6a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | efbde662-39a2-5542-b1d1-761213540c59 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | f4129db3-4a0b-5f31-b5db-3f93d2cc0e5e |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 10 - Completion Sign Off From Fields Below
label | 84cb292b-57ff-5318-84f7-45a293187a2e |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | ITP - E3001 - SH05 SIP Generic - Pavement Construction incl Culvert Extn | itp |  |  |  | Yes | Ω (Deprecated) ITP - E3001 - SH05 SIP Generic - Pavement Construction incl Culvert Extn (old version) | e9b02e05-4a8b-4ec3-8f68-9fc7efbfc9ce
checkpoint-group |  |  | section | 1. Setout & Saw Cutting
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 9ce1f35e-76a7-5b3c-aa9a-fc1df0c0f5d6 |  | textbox | CPS Eng.
text | 2c8a9808-6c01-57c1-86e2-47990d510f5f |  | textbox | Site Engineer
text | bf9f9142-454e-5d51-b1e7-820f48a4f833 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Survey Setout
label | 7ae96138-2bde-5db0-98e9-86903f764f7e |  | note | ACTION (Hold, Monitor, Witness) - M
label | 3149dec2-142e-5574-9558-ebd0d2054dfc |  | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
label | 0929aa0b-4ffa-501d-876f-ebfa101dbce9 |  | note | Frequency - Prior to commencement
label | 54b47c6f-6bdb-5122-8b07-1cbafe785304 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 273d53ec-98b5-5fcd-bac1-58b80ab1ba08 |  | note | Records - Survey receipt
checkpoint-status |  |  | checkpoint | 1.2 - Saw cutting
label | 1a3e5c4a-15c8-53cb-9e41-8933c41c25a1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 018fdcee-a87f-5b3f-9834-2c40339f1918 |  | note | Detail - Proposed Sawcut line to be inspected by the engineer
label | dbc2cf99-fecd-5a12-8958-503e3394de6f |  | note | Frequency - During construction
label | 463bdaa6-f8e7-5263-894b-c40166c6d949 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 558e0bbf-7f12-510a-a6cb-d95cabb7127f |  | note | Conformance Criteria - Project Specification 6.6
label | c97ac814-ee34-55c2-8d0a-04ec024669f8 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2. Material Compliance
checkpoint-status |  |  | checkpoint | 2.1 - Sub Base Material Compliance
label | 7ac2b99f-54f4-5d43-8f20-118c413297b0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5a0ce795-39d5-588e-b14b-66cb3284d482 |  | note | Detail - Aggregate material compliance for Sub Base stockpiles
label | 00a8935a-729a-5bab-9d82-a2e4439c4457 |  | note | Frequency - Prior to commencement
label | e65cac31-644a-51fb-94b3-f9d2b39a24bf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 7c08b8da-d6be-57a0-b52a-0aae34ee3178 |  | note | Conformance Criteria - Comply with TNZ M/3 Specification.
label | 2ade152a-4211-5591-bdc4-e2203e08a656 |  | note | ○ NZTA B/2 Specification Lab test for MDD at OWC.
label | 1443824a-5374-5d59-b9ab-cb8178316a5d |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Base Course Material Compliance
label | 6c5c5a07-4d3f-5547-bfd9-6ce0fbaa7897 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5ddf5f74-7c1f-5e71-a926-80b877f370b2 |  | note | Detail - Aggregate material compliance for Base Course stockpiles
label | 3b560496-63bc-5fbe-bdf9-040cba51c859 |  | note | Frequency - Prior to commencement
label | 47dd98e9-3514-5dc5-8995-47f58f792b24 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | a0671090-cede-55d6-89b1-816d9dcbe83a |  | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
label | 0acd8990-8b54-5a75-9b93-f1a2ec1c84db |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.3 - Base Course Mat Sample Testing
label | 2fbc43ab-1bb9-5883-a701-83325110de10 |  | note | ACTION (Hold, Monitor, Witness) - H
label | bef1127a-c8a4-5ddc-a0d5-f1d0d327e68a |  | note | Detail - Mat sampling of Basecourse Material
label | 4c731d45-cb3a-52d2-b51f-6b07e8723cd4 |  | note | Frequency - 1 mat sample for the job. Pavement CPS Engineer for further instruction
label | d6de8b2c-bea9-5edb-9d2c-cecb7ff2e5b7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab testing
label | daea67b6-d86c-5aab-ab18-923513e05a5e |  | note | Conformance Criteria - Grading to comply with specification
label | f7439385-b22b-578f-a741-4fc74921e776 |  | note | Records - Mat sample lab test result
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Concrete Pipes
label | 87314527-dbd1-509d-915e-9b569e7cb185 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e7a27303-17ca-53d1-81e9-6290b952a968 |  | note | Detail - Specification Compliance
label | 20687415-62aa-5be4-aa46-665cb1131b4b |  | note | Frequency - Each delivery to site
label | e6e586fb-d9a3-5822-a73c-ff33cf38f5b4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
label | fd3bcc6d-0db6-5678-9970-dd5943bc7e61 |  | note | Conformance Criteria - All concrete pipes shall comply with the requirements of NZS 3107 "Precast Concrete Drainage and Pressure Pipes".
label | 76c1a483-b959-5144-b95b-5af03d72e2bc |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 2.5 - Pipe Bedding Material Compliance
label | 4d8f8f37-8fab-59f1-8b9f-f618ec0f9f2b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 440b398b-5de6-5a4d-bce8-de50a5cf67ed |  | note | Detail - Material to meet specifications dependant on material type selected
label | ba3e5641-445e-5ea5-adca-92b125824f7b |  | note | Frequency - Each material used
label | 8a2bbef4-da7a-563d-8aa2-f1180cbbcd5a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 48af8dff-b831-5610-a47d-d2a363082cfd |  | note | Conformance Criteria - Compliance with requirements from Specifications
label | f0c2eaff-b884-5e78-8844-c56c7b27731d |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Pipe Backfill Compliance
label | 762d2c41-f39b-5c7e-8496-2071e341d1c9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4961cd62-56ef-5a6f-8fa1-93d94c1c7276 |  | note | Detail - Material to meet specifications dependant on material type selected
label | 659e0b65-f1b8-56b1-95a7-18d7f885022a |  | note | Frequency - Each material used
label | 4722293d-6139-5345-8313-6eb4f3090d9e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | a932c686-c766-5ab7-a363-80889c364842 |  | note | Conformance Criteria - Comply with grading specification
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Chip Seal design
label | cfe837e3-5f4d-5555-bc8b-ce44ac847e57 |  | note | ACTION (Hold, Monitor, Witness) - H
label | abc3a8d4-b7b2-54db-a8c0-6af326661e9f |  | note | Detail - Seal design to be reviewed prior to sealing.
label | 63ffc584-6c48-5010-813b-47091e3e5932 |  | note | ○ Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer.
label | ea27dac5-e63e-5da0-9853-58263ea709d7 |  | note | Frequency - Prior to Sealing
label | 703382c7-24f9-5f6e-84eb-89ffd5486cd3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 8df544c3-a3e8-556e-aef6-7053cd09631f |  | note | Conformance Criteria - The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995.
label | d24acce0-8bf9-5b66-a9ff-e5a0d15b6ee4 |  | note | Records - Emails/NTE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Sub Grade Construction
checkpoint-status |  |  | checkpoint | 3.1 - Sub Grade Strength
label | a863b3d0-161b-5434-a9fc-31038b113ab1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b4cd07f6-b8d8-5a27-9503-27af5853c622 |  | note | Detail - Determine Bearing strength of Sub Grade
label | 816cbf19-00c0-50f1-98e4-8f9577685ee9 |  | note | Frequency - After Dig out, every 5m
label | a252a2d1-a13c-5e97-869e-592547972c9c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | fbbb8b09-b4bd-56f3-8f34-727633cc0695 |  | note | Conformance Criteria - Min. 2 blows /100mm, 2 blows = 4 CBR
label | fea47037-19a5-56da-aef8-049ca4f77f34 |  | note | Records - QA measurement Sheet, CS-4000 1m Scala
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Proof Roll of subgrade
label | cebf5dc1-3f52-51a3-9cb9-c691bd285146 |  | note | ACTION (Hold, Monitor, Witness) - H
label | fdf3506f-1119-5453-9b12-41d3444b941f |  | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
label | e0724539-3029-564b-82dc-183caf047a3c |  | note | Frequency - Prior to Sub Base Construction
label | 255594cf-14be-55d6-8f31-d6eed92106a2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | efa8800f-47ac-5e7a-bc55-6476280e937f |  | note | Conformance Criteria - Engineers Acceptance
label | 7f785f2a-9e27-5740-a8ae-bf3a40d457d8 |  | note | Records - Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. Sub Base Construction
checkpoint-status |  |  | checkpoint | 4.1 - Sub Base Aggregate Delivery Checks
label | b4364af1-0076-5bb9-8477-e6cdf8367d53 |  | note | ACTION (Hold, Monitor, Witness) - M
label | d2b2edcf-94cb-50c8-8c67-a7a4ae0d5f3e |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | 2e29359d-1e74-5b60-8e22-4409361d4ed0 |  | note | Frequency - During construction
label | b57e3707-d9bb-5004-aa66-6acb13586e20 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | f9a0b613-4da9-5a93-a402-ed6b8c89465a |  | note | Conformance Criteria - Comply with TNZ M/3 Specification.
label | 34ce98f0-d165-53a4-8445-034f5ba6b130 |  | note | ○ NZTA B/2 Specification.
label | ec3e09a5-3df4-5d67-98e4-00565e19cb38 |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 4.2 - Sub Base Material Contamination Checks
label | 2b3ef890-d249-5a26-b5b9-41020ebb90cf |  | note | ACTION (Hold, Monitor, Witness) - M
label | 20b90db6-b628-5075-827c-a533b08b7771 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 810beec6-525f-5cc2-bce2-e7c2cd34ab43 |  | note | Frequency - During construction
label | c7ebec40-40c6-5f43-baa1-13dfcd43eab0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 9f99e5d3-06ea-501a-a300-c60229241bfb |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 4.3 - Sub Base Trimmed Level Checks
label | 55298ce3-3d8a-5ea8-8f30-c70907cbccf2 |  | note | ACTION (Hold, Monitor, Witness) - M
label | fb1f9f6d-5f7e-5b7b-a14e-158ffa13d2b2 |  | note | Detail - Carry out a Level Check on the trimmed Sub base
label | a8b3b83e-422f-5111-855d-1fd9ad5d693e |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | 1b9de626-57ab-52df-818f-6ea43bd55f4a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 61f12aaa-4659-5ce0-b3ff-15876d44a660 |  | note | Conformance Criteria - TNZ B/2
label | 765304c5-b343-5c54-aff0-b61374f1a180 |  | note | ○ Tolerance = -25mm/+5mm
label | 043cbbe0-a382-5be3-8e0a-709c40708100 |  | note | Records - QA measurement Sheet, CS-4100a Subbase Approval
checkpoint-status |  |  | checkpoint | 4.4 - Sub Base Compaction Lower
label | 9240d5e8-058d-58df-8e41-56d5753b414f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 51a429e5-812a-5dc9-a09d-d20a069a127d |  | note | Detail - Degree of Compaction.
label | 7cfd3ac8-b279-5735-a571-ea3573829e8a |  | note | ○ The subbase shall be constructed in two layers.
label | 863ff24f-da28-50f4-9e42-0b59864fe73a |  | note | ○ Lower subbase results must be approved before construction of upper layer.
label | 1b38f1d9-01b0-559e-ae65-04ae3937b5f6 |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | a61430f9-7862-5868-a6b4-6b89bc0a6562 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | 5dac9e67-70dc-51a4-b36c-53e8241c6bf9 |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | 869295c9-93d4-5b81-bf01-7ad2ab2d73fd |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Sub Base Compaction Upper
label | dfb65156-7da8-580a-a0fb-3212d845895c |  | note | ACTION (Hold, Monitor, Witness) - H
label | e4f42a23-2779-5483-9492-bfbcbb01fa7a |  | note | Detail - Degree of Compaction.
label | d826c4b7-02b7-55c0-94ba-d8512d70ab9b |  | note | ○ The subbase shall be constructed in two layers.
label | 00d72ab9-d80a-547a-b9dc-512d21118e60 |  | note | ○ Upper subbase results must be approved before construction of basecourse.
label | c67894f7-3671-575e-a5ce-98b94fbb1fda |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | c4895cfe-eb9c-5810-93da-003197349279 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | a02d2c91-e8c3-5de5-951c-49ebd7c43a22 |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | 77891d4c-2c21-5992-b3ea-ae84aa78446b |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5. Base Course Construction
checkpoint-status |  |  | checkpoint | 5.1 - Base Course Aggregate Delivery Checks
label | d4c78109-34a3-5b73-a7b2-0f93f34fa78c |  | note | ACTION (Hold, Monitor, Witness) - M
label | 0a112c96-a607-571a-9497-06d4fca3dc5d |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | 29efe8de-6493-5c47-af74-3a8ff5baa834 |  | note | Frequency - During construction
label | 8cb6be14-829f-5f4a-8865-e64a7dd1abae |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | 61afba88-1b1a-5769-bc3d-cf099b62c59c |  | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
label | 477f6cb3-84a6-511f-87c8-5cae4ba2bd5f |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 5.2 - Base Course Material Contamination Checks
label | b03b4fd4-693e-5d31-98d1-5c4a5e0d65ba |  | note | ACTION (Hold, Monitor, Witness) - M
label | 61da3a9b-7e56-5b37-ab77-38256c0a1518 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 625932cd-2942-541e-988c-d4a36709f87e |  | note | Frequency - During construction
label | c787a0d5-993a-5165-8d18-5096bf99c2ff |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3dc89d11-e3ee-5097-9c73-037e4e9d7e9d |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 5.3 - Base Course Trimmed Level Checks
label | cd2584b1-504c-582a-8b34-5352fc333c63 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 41abc580-20c0-5c1a-adec-e7b5b3c7b51b |  | note | Detail - Carry out a Level Check on the trimmed Basecourse
label | d71a8625-551b-5ec6-821c-d8b909c7b0d7 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | d8668638-7d69-5437-b232-9369941442a0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 99149bf0-b529-5ce4-bfad-46626380f421 |  | note | Conformance Criteria - Tolerance = -5mm/+15mm
label | 4c685373-b6ac-585d-88cf-b4d01b51633c |  | note | ○ if constrained (kerb) Tolerance = -5mm/+5mm
label | 504ccab6-21c5-520b-99c6-313e4450b5db |  | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
checkpoint-status |  |  | checkpoint | 5.4 - Base Course Compaction
label | 8c4b8e61-9c58-5142-833d-2a383d998e77 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f46a1184-0d38-5fb4-8a93-0efc79b6be71 |  | note | Detail - Degree of Compaction
label | e4c6919f-5621-5e43-94bf-ae5cc8a8292e |  | note | Frequency - 5 per Lot
label | 1aae71af-5d32-5633-a6fb-f240cad7e9e7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | 831df6a8-3210-59d0-b483-ac0eeb3edb6a |  | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | e01e0f79-7dee-5736-b2c4-436777b91786 |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Base Course Surface shape check
label | 91c53700-df46-5077-9683-57750b487068 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a99319c9-723a-5920-a501-2cb5365f7f69 |  | note | Detail - Surface shape check
label | 62716a5f-12f8-5a62-ba65-331ae54d086a |  | note | Frequency - Prior to sealing
label | 60097ab6-6f2f-5d79-b89b-e1cc8ca71e01 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 9ca60351-2997-5d5c-adbb-7b0783edb75b |  | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | 1564206e-39f9-59ae-b3c5-8d1625f84755 |  | note | Records - QA measurement Sheet, CS-4100b Basecourse Approval
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Base Course Surface finish check
label | ab0793cf-9c5a-59ef-8a69-69e91a182787 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f43da890-92bd-5018-b4b2-9725a7a281c5 |  | note | Detail - Surface finish check
label | 1422edc3-96af-56ea-9512-0d5c8fc9a48e |  | note | Frequency - Prior to sealing
label | 60d94cde-8839-510c-8b4d-0bc40f734006 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | f28573d7-41bb-5f80-8f8d-3e09c026b1bd |  | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | 263f1acb-a5ba-5056-b144-1c0c9e690eb4 |  | note | Records - Site photos, Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6. Extension of Culvert
checkpoint-status |  |  | checkpoint | 6.1 - Foundation Compliance
label | 1b3f5216-3428-5662-a510-32239bb67f92 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7c0714ff-1227-52e7-909f-a859b10653fa |  | note | Detail - Test formation level on completion of excavation to check if undercut required
label | ab13df29-0a3f-5316-8897-29d3be2ce1c2 |  | note | Frequency - One test per 5 linear metres
label | 02d56bea-8350-5799-85e4-a21032538c78 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
label | 372212f1-c350-5835-8a32-9f70fe99bf27 |  | note | Conformance Criteria - Min. 2 blows /100mm
label | 9d285fca-d44b-5568-b6f7-3871de00b547 |  | note | ○ 2 blows = 4 CBR
label | 0108a17d-ea92-573b-a725-d676d4f5fc03 |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 - Levels Compliance
label | 45c3e8f7-d899-557e-bf10-23ca4f5b2a88 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 27778dfe-fef7-54a1-bf7d-9b4b060e32e7 |  | note | Detail - Test formation level on completion of excavation to check if undercut required
label | 642edcad-c648-516a-8f3d-1fd6f39a0774 |  | note | Frequency - As stated
label | 54890746-774a-55bd-a528-fc578379fb9e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | a8cd8454-22c4-5813-8137-461ee98cbe11 |  | note | Conformance Criteria - Designer to inspect formation level at outfalls / inlets.
label | 33e9021e-8b77-53d0-a689-720143bf11c9 |  | note | Records - Photos, Visual
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7. Sealing
checkpoint-status |  |  | checkpoint | 7.1 - Location/Size Confirmation
label | 0b3abbbe-61c2-5deb-9410-3239b458ce3d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 889a6e99-7292-5a03-baf8-c4e8205232f6 |  | note | Detail - Mark up extent of Chipseal
label | 5a1b5bf3-736e-5c18-9ad5-3605efb07b40 |  | note | Frequency - Prior to Sealing
label | 1d228bfa-7520-50ee-84b3-ad5b6920b822 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
label | dd2b1ee3-9645-5503-ba98-4ecd17714dec |  | note | Conformance Criteria -
label | 250138ae-4472-576e-a097-d1b669b7d464 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 7.2 - Surface Cleanliness
label | 6fd44084-ca2a-50ea-9ae8-c9cde660bdbe |  | note | ACTION (Hold, Monitor, Witness) - W
label | 69367b26-3272-5c25-bf9e-769822ac1959 |  | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
label | 8f7916b6-4a2b-5b48-9f1d-4eb492dddae5 |  | note | Frequency - Prior to application of binder
label | 3e339253-537e-5a8e-9141-9e157f02cbf6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 24a023a8-5f74-51e4-b2ae-88574f27b0b3 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 7.3 - Binder Application
label | 890ca594-f9ea-5616-9a25-deb604ea5e43 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b2687fbf-ad33-582a-a613-fe32e21798a8 |  | note | Detail - Ensure the Binder application is according to the seal design
label | 4c0a9797-43bc-5994-9bd0-8d6681f094ea |  | note | Frequency - During sealing
label | e17d31ef-dd19-5c75-b7ab-e012ce07694a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 1b2d9547-3a45-55e4-a46a-efab039af768 |  | note | Conformance Criteria - According to seal design
label | af43d413-bd2a-5f0b-8aed-36c37b5ecb63 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 7.4 - Chip Application
label | 5a2ebc7e-1fed-54bd-bad5-b81208e4dcd0 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a2bf96b2-7f02-502b-b82a-3ae3e5d71c40 |  | note | Detail - Ensure the Chip application is according to the seal design
label | f6dc59dd-348d-5862-a9c6-c62ab75d65fc |  | note | Frequency - During sealing
label | c5252c26-5cec-5141-989f-ba419b8595b8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | d45e4c50-cdf1-5b89-96a3-b6b7248ae5d3 |  | note | Conformance Criteria - According to seal design
label | a6f825e1-6cf7-5663-99aa-83477e0391b5 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 7.5 - Compaction
label | 9dd05e4f-ad2a-5794-8771-32f5c9470d84 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 18832216-c261-5271-acae-a4227d7532bf |  | note | Detail - At completion of rolling
label | efc81bde-e9c9-5c64-91ef-42638232d46f |  | note | Frequency - During sealing
label | d799f111-d74a-5f7c-afa4-766ddc20dbe3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | ea6650da-5d6d-5b40-9076-ca20c98f12a8 |  | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | d7b24350-f433-57bd-b97d-3d0a6b613567 |  | note | Records - Photos, QA measurement Sheet
checkpoint-status |  |  | checkpoint | 7.6 - Removal of excess chip
label | 13005bc4-804c-53ed-a1ed-6d289fcb2224 |  | note | ACTION (Hold, Monitor, Witness) - M
label | dbeb6b00-35dd-57de-9141-992ec1033593 |  | note | Detail - Removal of excess chip
label | e78207ec-60be-503a-9d27-a995f5670a67 |  | note | Frequency - Within 48 Hours of Sealing
label | 007dcf16-629b-5d68-a13c-8115d1b7f4a9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | fcbd0f76-3a5b-59a3-81ba-9f0c2eddc9d2 |  | note | Conformance Criteria - Ensure all excess chip removed from site.
label | 79473162-10d4-5de4-8bf8-092d903115ac |  | note | ○ No chip windrows left on site in Shoulders.
label | a10b2fc2-4cd8-5028-bfa9-9f92062505a8 |  | note | Records - Photos, Site logs
checkpoint-status |  |  | checkpoint | 7.7 - Surface finish check
label | 0d8add72-8214-51b9-8944-3dec0f2c3b7c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1c0d802e-8633-5fa7-9eae-53fa77d937bc |  | note | Detail - Surface finish check
label | a1ea5924-f7e8-5499-b586-d65f631962ca |  | note | Frequency - After sealing
label | d186cc22-6f94-5ebc-a7af-596c3449e0b9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 8e8b4d46-3cbd-5014-8cef-ed7d31b1e23a |  | note | Conformance Criteria - Engineers Acceptance
label | 9c77c6a8-de48-509f-912b-6a9cd891bab1 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 8. Road Marking
checkpoint-status |  |  | checkpoint | 8.1 - Road Marking
label | 85189b8a-220c-5649-bb53-5fd852cd7067 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8c1238ba-7c3c-5601-bd79-8b96449fbae3 |  | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
label | 81f6d7b7-548b-54d8-9d63-97beeafd7084 |  | note | Frequency - Prior to the final line marking
label | bec53a2c-92e1-527d-bcea-a1b089fd9c35 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 97d210df-4dfd-599f-b7f1-1dc4a2956715 |  | note | Conformance Criteria - Engineers Acceptance
label | b5a23775-828d-563f-9151-c9bcf26792ee |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 9. Hydroseeding
checkpoint-status |  |  | checkpoint | 9.1 - Hydroseeding
label | 24d16e96-c7a1-5341-8799-5cbfccd931a3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 283e78f0-a8ee-52d5-85ae-18912a42a915 |  | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
label | caed83b7-df0b-53a6-a057-4feca423fe0c |  | note | Frequency - At the completion of the Lot of work
label | 6c07c63a-a10a-5004-abdd-5fbed3538814 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | e602bb73-fb78-5635-a4ad-70fe46f3b7c8 |  | note | Conformance Criteria - Engineers Acceptance
label | 5490f4f7-7e5d-5c41-914f-f16aa20e9f89 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 10. Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 10.1 - Final Walkover (Snags)
label | 263515ad-4454-5eb1-96fe-65456f96d0d2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8cd81723-329e-5d40-a9e9-96d91a72abdf |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | bf751700-4f4e-57ad-bb13-9f4e7a7afb1f |  | note | Frequency - At the completion of the Lot of work
label | de116035-741d-5f0e-a69c-6bb35db60a51 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | b972551d-4d0b-56a6-968f-4c3533cb629f |  | note | Conformance Criteria - Completed report
label | d10daeaf-8ec9-53d0-905f-ba857372075c |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.2 - Survey As-builts
label | afb36436-7fa4-5891-add7-be4534a7a400 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f2601dbc-319e-517f-9d8e-507835da97d5 |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | ce2daadf-4d83-5492-bd71-0a7f0d636ca0 |  | note | ○ A survey as-built of completed work must be provided
label | ccda0400-3db7-5547-8971-f44ac254256c |  | note | Frequency - At the completion of the CWP of work
label | 641eebb3-a697-5ebd-a38d-335e35d45cc8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 4ad4db0d-b4cf-56e6-bbe1-9471fac6e8c3 |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | 6ba3039d-7126-571c-9b67-e9786f11aef8 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.3 - Quality Assurance Deliverables
label | 0de96a70-f838-58e1-b37f-1ac078da2344 |  | note | ACTION (Hold, Monitor, Witness) - W
label | fb6d43f0-a347-5ed6-b420-1582b68833d0 |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | cd2a1882-6eaf-58bc-8e3c-27e4554ea43e |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | ec63282f-fe5c-5a90-8b1f-e55d9d935535 |  | note | Frequency - At the completion of the CWP
label | 7d37fd43-f24f-5546-9467-102be1b8d659 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 14632523-b5d6-5b8a-826b-06ad5c17f0e3 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | b08e92bd-15f0-5f78-89f3-911152dbe7d8 |  | note | Records - As-builts, NCR's and RFI's
checklist-sectioned |  |  | checklist | ITP - F2501A-ID460 - D9 Gully Underslip | itp |  |  |  | Yes | ITP - F2501A-ID460 - D9 Gully Underslip | ea7851d6-da70-4bfc-9305-881dc286549d
checkpoint-group |  |  | section | Section 1: RECEIVING INSPECTIONS
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 79593a82-6448-5d46-b205-71bd59a3579c |  | textbox | CPS Eng.
text | 01e04ef5-326a-5945-a46e-cb58253be3ec |  | textbox | Site Engineer
text | ac7b8a5e-e585-5aec-81d7-92c42fcf1c0b |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Bulk Fill (GAP65/GAP100) or similar
label | bcb67f85-629b-520a-be24-f6f1058685cf |  | note | ACTION (Hold, Monitor, Witness) - H
label | fe9e16ee-170e-5359-84f9-4c26c67c261a |  | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | c539ee73-fdea-58a6-91f7-53d5f03cd825 |  | note | Frequency - Prior to commencement
label | 6fcd712e-aed7-5aa4-9890-19c4b56012f0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 0f4c5072-770c-5f4c-8c88-23715d455047 |  | note | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
label | f579305d-05ac-5694-bc38-a38be4091561 |  | note | ○ Material source testing
label | 7d7e07b9-cc4e-5ab0-9113-dba528a805d9 |  | note | Records - Material source test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Class C A29 Geotextile
label | 4c500886-5616-5b29-976a-d3aacbddb01e |  | note | ACTION (Hold, Monitor, Witness) - W
label | e0c315de-bc5d-5543-8e18-a15fc27ab028 |  | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | 43642500-6938-5f58-a160-4b3a0cafde76 |  | note | Frequency - Prior to commencement
label | a9f5922c-67b7-5ee5-a214-397cd805eb16 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 14bac9b2-4c87-51d1-a779-01552fdef079 |  | note | Conformance Criteria - before placing foundation material and engineered hardfill
label | d014664b-0401-5ecc-8dac-922b3ad09325 |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.3 - Drainage blanket (AP65 or approved material)
label | ae50977b-48b5-53e6-bea4-34594cbee6f3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1b15d9d5-6728-5e3a-82af-3d1934918afb |  | note | Specification/Drawings Reference - F2501A-DS-RP-GT-0003, F2501A-DS-SK-GT-0048-A
label | 5ea96361-ecc0-511c-bef2-0a9537e633de |  | note | Frequency - Prior to commencement
label | 4421785c-aff0-59d1-84ab-e4cceaa94348 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 6b65e326-76b2-5f94-9519-e05c5023bd1b |  | note | Conformance Criteria - Material source testing
label | 8bbf3199-c1a9-55fa-bb08-04e5b67b8652 |  | note | Records - Material source test results
checkpoint-status |  |  | checkpoint | 1.4 - AP40 (Basecourse)
label | db955d16-530f-5033-bb73-3ba5d7d9ec87 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d67c5092-8886-5b43-bce2-0a762b2ab1cc |  | note | Specification/Drawings Reference - TNZ M/4
label | 6516e45a-47e3-50f2-a473-3d0d6dabf48e |  | note | Frequency - Prior to commencement
label | 38db5660-763b-50e2-9150-5243df5ec6b4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | edc5f169-9d2a-540c-ab69-a46856913203 |  | note | Conformance Criteria - Source property testing
label | 5ddeefa7-c627-57b7-aea4-0338ff90370f |  | note | ○ Traceability of all materials delivered to site
label | 7d6bfcff-92f0-55c4-b320-370313f60779 |  | note | Records - Lab test reports, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.5 - Geogrid/Geotextile
label | 5087926f-22fa-5886-9af8-158002c0b4d5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2bee1034-712b-5ab8-a60a-8eab9830f192 |  | note | Specification/Drawings Reference - F2501A-DS-RP-GT-0003, F2501A-DS-SK-GT-0048-A
label | 331c4260-a241-5438-96f3-2da77be6a2e8 |  | note | Frequency - Prior to commencement
label | 270dd5c2-5d7d-5deb-96c8-ffdc7881f80f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 22bbd409-6751-5b54-be4f-cfde360aa6d7 |  | note | Conformance Criteria - Delivery dockets with roll details. Check information on the delivery docket against the requirements indicated on the Drawings.
label | 8f32d773-4854-5412-8e27-a1b0dca57d5f |  | note | Records - Delivery docket
checkpoint-status |  |  | checkpoint | 1.6 - AP65 (Sub-base)
label | 227972cb-05a4-51c9-9132-3d87759fd795 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 39febf7b-c108-594c-a7a1-517ee9f5cac1 |  | note | Frequency - Prior to commencement
label | d58843af-8ce8-52fc-b1a0-868f1dfd2b75 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 967bcda7-1cae-520e-9cf7-3175b92323e7 |  | note | Conformance Criteria - Particle Size Distribution Maximum Dry Density Plasticity Index CBR (4/Soak)
label | f2656b2f-95ff-5446-a54f-da75a24f5e48 |  | note | Records - Lab test reports
checkpoint-status |  |  | checkpoint | 1.7 - Grade 3/5 Chip
label | 8bce78bc-f43f-53a8-8b4b-8a0671dac7e7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 59003c17-3df4-5a68-a855-d1a09e0ef497 |  | note | Specification/Drawings Reference - NZTA M/6
label | f9695cb1-cd9f-5964-9b39-e559087f0019 |  | note | Frequency - Prior to commencement
label | d56ad5d0-0b14-54e8-a439-d1891be9a568 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | f84a7e55-5aaf-5b19-b7d5-b311115ad8f5 |  | note | Conformance Criteria - Source property testing
label | 9d0d42f4-9fc8-57a9-9e6a-ae5fafcf58a5 |  | note | ○ Traceability of all materials delivered to site
label | b0bcf333-65b9-5300-9072-355e6b018a47 |  | note | Records - Lab test reports, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.8 - Cement Material cert
label | b760c934-7c79-59c7-a0ba-80421ca47a27 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8ca3e3fb-1151-5f5a-9632-28c9805f1eed |  | note | Frequency - Prior to commencement
label | 1eec91ba-4606-531c-94dc-9af3cca4e507 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 17825815-1b52-5bde-9814-63d545f42e3b |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.9 - Enkamat 7018 (or similar approved)
label | 3b904bdf-eb85-535b-8bd1-3400ebecefc5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 47481378-eed6-5923-b02b-6d4445be0a7b |  | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | 1be117b7-47fa-5c8d-80bd-978e8022b6be |  | note | Frequency - Prior to commencement
label | b8ba4485-948b-525c-83f9-679b8da73fe0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 42159eca-19cc-5372-847d-eaa229f3dbde |  | note | Conformance Criteria - NZTA Erosion and Sediment Control Guidelines for State Highway Infrastructure - Section 8.12 Geotextiles, plastic covers, erosion control blankets and geo binders
label | 8056458e-7321-5f77-93a2-dd6b27f832c6 |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.10 - Bitumen
label | bb6c50a2-8c6d-5a17-86f5-b64b308f3baa |  | note | ACTION (Hold, Monitor, Witness) - W
label | 02c58db7-20e9-5b2a-8dfd-6c121f6b55a9 |  | note | Specification/Drawings Reference - TNZ M/1
label | fb8a00c4-c65a-547a-8a73-b89697719028 |  | note | Frequency - Prior to commencement
label | d4a10c1b-465c-51c5-8f1b-6a9e35867c1f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 4537019d-9d09-5e63-98c6-82fb74670b97 |  | note | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
label | 3a2080b0-1a48-5a98-8b0d-2f15053cc0db |  | note | Records - E2 Certificate
checkpoint-group |  |  | section | Section 2: IN PROGRESS INSPECTIONS
checkpoint-status |  |  | checkpoint | 2.1 - Survey Setout
label | fed335ca-2fb2-57f5-9ba3-05258d726d33 |  | note | ACTION (Hold, Monitor, Witness) - H
label | fec84958-d488-59d4-a621-29c9a1adadfe |  | note | Specification/Drawings Reference - Consistency with Construction Drawing
label | 135751a0-9515-5ab1-9035-50d5f5d044f8 |  | note | Frequency - Prior to commencement
label | 4ee333a7-6172-5abd-b9a2-b54c05d61e38 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 4d0fb0e6-e8f4-54fa-9f97-858f0ca82c48 |  | note | Conformance Criteria - Set out extents of fill and check against design drawings. Subcontractor to arrange survey
label | 235115d2-6cc9-506e-bc89-0c5c29fe601a |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Vegetation Clearance and removal of fence & loose debris
label | 12622f30-4f31-5ed1-b993-f7884c69f31b |  | note | ACTION (Hold, Monitor, Witness) - W
label | 925f365f-affb-530a-ada0-0d5c398125fa |  | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | aec5c7a4-bda9-5dd7-9907-d82fc8a1be6b |  | note | Frequency - Prior to commencement
label | eacb7928-830a-5ac5-a020-fd3b88d0ff0b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 61a105e9-4953-550f-b2a2-eafab87e1e36 |  | note | Conformance Criteria - Remove and clear the vegetation & fence
label | 37cfa2b6-8ac8-555c-9b1c-edfdd7c929be |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.3 - Subgrade Inspection
label | d2441fb0-dc63-529a-886f-312c76ab514c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7757c630-0b06-5668-9e79-a598f796ef50 |  | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | 8e22e228-7461-5d3a-8d2c-2eede1a5f655 |  | note | Frequency - Per area as required
label | dd79439d-0887-5e8e-9bf4-298b38e9ce78 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | edf6ad55-4e22-59ce-af55-fd879a4a37e3 |  | note | Conformance Criteria - Inspect fill foundation.
label | 1b8caa08-a737-5c44-8963-5584239d1bf9 |  | note | ○ Fill foundation must be approved, in writing, before filling commences
label | 69877691-9f0e-5786-81ac-cf8ba35bc7d6 |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Ground Improvements
label | fa04603d-f016-5057-9ec4-c780ad9ec62f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4a912f19-7b87-52a6-ae60-470cc5212802 |  | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | 5f3ba6cd-41c5-50e5-920e-1639285dc9d4 |  | note | Frequency - Prior to commencement
label | ed2be660-d149-55b8-8c52-77ef3f4bfed6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | d6630ae5-be22-59a2-be41-0b1db21f8b2c |  | note | Conformance Criteria - Any area that requires Ground Improvements (i.e undercut) must be completed as per CPS Engineer requirements and be signed off and closed before bulk earthwork operations commence
label | 78de86dc-1dbf-57aa-adf5-8cd0be83a5ad |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Class C (A29) Geotextile installation on the excavated face
label | 1651861b-4001-5b06-b460-372bd498c97f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5b302b67-3052-5212-8c18-97dcb1709a5a |  | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | 0674e93a-1649-5495-8096-085548e4b314 |  | note | Frequency - During Construction
label | 0d97242b-2ebc-56a2-8b84-77ed08830f06 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 988141c7-4924-5e22-a6d5-46234b8a8b4a |  | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A29 or similar approved before placing drainage gravel material & and engineered fill.
label | 117fa03e-21af-5c4e-836a-478a69abf908 |  | note | Records - Photo's, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Drainage blanket/material installation (AP65 or approved material)
label | bfc8d66c-dbc9-560d-b9a3-8fbfd9413b92 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3ef5a68c-c334-5ebb-895c-b5038ae6b828 |  | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | 535676e3-f95b-568d-af47-4ea28b980296 |  | note | Frequency - During Construction
label | e0a30c31-9648-5655-b56d-3f037177d807 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 842b2411-9e44-5870-8a9a-63970c0c246b |  | note | Conformance Criteria - CPS Engineer to assess suitable drainage location & extent.
label | ff9a4beb-f08c-5a09-b1ae-5db6bbeefced |  | note | Records - Photo's, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.7 - Bulk Fill placement
label | 95d86604-376b-54cf-a089-95c165cdcbd4 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1fbbc4c1-bda7-5b05-8437-f32f459931c6 |  | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003, NZS4431:2022, NZS 4402:1986
label | 63df2b6c-6b19-58a0-a115-784432abe101 |  | note | Frequency - During Construction
label | e668654d-10f4-5040-ace3-18a350956ca3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b4a611ed-f6ac-5598-b0c7-f5b63109663d |  | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022.
label | de6517cb-f789-591d-8937-1a927fdf03c0 |  | note | ○ Fill should be placed on dry subgrade.
label | 2e8e4eac-8c06-5ffa-9e3f-c2fbfdd82ea5 |  | note | Records - Bulk Fill Earthworks checksheet (CS-4100), Photo's
checkpoint-status |  |  | checkpoint | 2.8 - Placement of Geogrid/Geofabric
label | 04114585-6c9e-5dfb-b713-d70916c25663 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3592ddb2-7c38-5de7-b170-1880020b8045 |  | note | Specification/Drawings Reference - F2501A-DS-RP-GT-0003, F2501A-DS-SK-GT-0048-A
label | 03f7d541-056d-5b7a-b9a3-a14bde184424 |  | note | Frequency - Prior to backfill
label | cbff8ebb-b055-56dc-b723-0f6370431c99 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 17123964-02ce-5126-993d-858c8c2574de |  | note | Conformance Criteria - Placement to be sighted & approved by CPS Engineer
label | 801eabec-74a9-5a74-97cc-23ff51d36892 |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Cutting of Geogrid/Geotextile
label | 05d72e18-f01a-5ee6-a623-5e07a1aefa48 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 90b5a91b-f859-574c-bba6-396cb3387d2a |  | note | Specification/Drawings Reference - Cuts shall be limited to 0.5m and only made along the weak axis.
label | 243d461c-f49d-5ad9-9967-1650d29c8840 |  | note | Frequency - Prior to backfill
label | f121fd78-3d25-5cb0-8d3b-f2e3a48b6247 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 3b66f0f7-7ebf-5ab3-bdf2-b311658564e0 |  | note | Conformance Criteria - Geotextile/Geogrid cuts shall be undertaken if pre-approved and inspected by Engineer as per photographic evidence
label | 33c8c425-b18a-595e-9dad-8fae4ad50ce1 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.10 - Bulk Fill Compaction
label | ead58b58-f430-5654-8b50-f6beb00c975c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5a97d800-e7ed-513f-b466-55018741c01f |  | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | 9def9c38-a0c8-5dc9-b054-40752c035ee3 |  | note | Frequency - During Construction
label | 915cbc55-5f00-583f-9234-7b44754adb89 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 9a80b594-7d73-58c1-b36e-0b643cf85b2e |  | note | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3.
label | cd412b59-bf03-58e6-90b2-a97923c79625 |  | note | ○ Completed and signed COR per 1000m2 with a minimum of 3 checksheets for area covered. Scala results to determine CBR and required lap widths.
label | 631d2ae5-0768-5588-8ff5-7ca009071252 |  | note | Records - Compaction test reports, 1M Scala check sheet (CS-4000)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11 - Form and cut fill batter as per design 2H:1V
label | 48f61314-2d14-555d-b731-2f50cf672017 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f9d0de3e-f8ef-5c7e-bf02-aa84dfe3b61a |  | note | Specification/Drawings Reference - Buttress typical details and F2501A-DS-RP-GT-0003
label | f22a816f-62ee-5e2b-8b64-cffb8a87c7b7 |  | note | Frequency - During Construction
label | 3ad72981-69a4-584a-b437-ca37c46d31de |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 6d9b05a9-c19f-55ea-9def-0ab10f15af45 |  | note | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
label | 27757f25-8903-58ea-8bd0-c44a27d02143 |  | note | ○ Slope angle of buttress is to not exceed 2H:1V
label | 41950e0c-a575-5761-8378-48ead053fe82 |  | note | Records - Survey as builts
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 3: IN PROGRESS INSPECTIONS (Pavement)
checkpoint-status |  |  | checkpoint | 3.1 - Saw cut existing pavement
label | 6db4c396-b249-5d16-ab08-10a89d828133 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 25c3e3e4-6184-5aa4-ac7f-cae00deed48b |  | note | Frequency - Prior to pavement construction
label | 46ab9f68-4326-5489-9331-ad18af2570fb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 1d673398-6eee-5c92-97ec-c24677ad0e0e |  | note | Conformance Criteria - Smooth and straight saw cut
label | 6485a148-e986-55e1-9fae-53ee0be7d9c3 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 3.2 - Subgrade construction
label | 56e4574e-bbef-5e30-8ce7-d08184401867 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 436c6663-04c7-56e3-9747-c19bfca875ea |  | note | Specification/Drawings Reference - TNZ B2
label | 8b4eebce-ae02-5923-ab98-0eca2a615a7b |  | note | Frequency - Every 20m
label | ac9027de-0253-5400-a073-92f54e48de77 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | 76332d06-b763-5ea4-8e9a-dc83857817eb |  | note | Conformance Criteria - 250mm thick cement stabilised subgrade (AP65) with 2% cement compacted to minimum dry density of 92%
label | 1d2cefc9-8218-5800-ba6e-a220e126870a |  | note | Records - Test reports
checkpoint-status |  |  | checkpoint | 3.3 - Subgrade Cement Application rate
label | a5173348-18bd-5b35-abd8-beda3d7c1477 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 869e0d7f-fbd1-5971-ac55-bbe1b68feb4b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Bag test
label | 6a876534-c63e-50ce-a744-d9c2c6b95990 |  | note | Conformance Criteria - 2% cement stabilisation at 250mm deep subgrade
label | 4303f717-6eb6-5135-846a-9cc287020a9a |  | note | Records - Bag test records
checkpoint-status |  |  | checkpoint | 3.4 - Sub-base construction
label | 19ebaf4d-f805-5bcd-9f1a-05f822e7964d |  | note | ACTION (Hold, Monitor, Witness) - W
label | ba9072dc-3ec3-5132-b6c1-1d2bde7690d2 |  | note | Specification/Drawings Reference - TNZ B2
label | 1f3d5e69-cedb-5aad-9b9c-a43d42b2d2ba |  | note | Frequency - Every 20m
label | 02d7a108-8b3a-5f8c-a577-53542755fd84 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | da506688-dda7-5faf-9a79-f8d8941deb23 |  | note | Conformance Criteria - 200mm thick AP65 sub-base compacted to a minimum dry density of 95%
label | 8ccc9012-65b2-5e62-adf5-32bba0970cfd |  | note | ○ Average 95% of MDD with nothing less than 92%
label | 3b9966b8-8218-5a82-9f47-b012bd4b2693 |  | note | Records - Test reports
checkpoint-status |  |  | checkpoint | 3.5 - Sub-base construction
label | bcbcc9bd-ba42-59ef-b1cd-544d94de33fb |  | note | ACTION (Hold, Monitor, Witness) - W
label | dcad67dd-4f6b-5466-9b30-8fc5ca480f49 |  | note | Specification/Drawings Reference - TNZ B2
label | 98afa033-dc89-5320-9535-d460d723f3c2 |  | note | Frequency - Every 20m
label | 3baedc51-cf81-58a8-980c-43f54163b9b1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | bcaba973-e0f1-5197-9766-4822fdd99f19 |  | note | Conformance Criteria - CIV>=25
label | bc46b977-4057-5d91-b78e-b0d5627804a8 |  | note | Records - Test reports
checkpoint-status |  |  | checkpoint | 3.6 - Sub-base construction
label | b8c5019d-4c74-5866-8073-45ff6a5ae170 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f47988b7-06f9-5721-9fc4-8dddd09b102d |  | note | Specification/Drawings Reference - TNZ B2
label | ec5367fc-26f7-58b0-b294-9a6acc398141 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 377ce7ee-e391-5e33-9cbf-b5177a49f122 |  | note | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
label | f2961e80-ea7a-505d-8bd6-34f34e1d1910 |  | note | Records - Survey as builts
checkpoint-status |  |  | checkpoint | 3.7 - Basecourse construction
label | e721120e-e529-53fd-96df-c67ea95f2a99 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 613d8e40-aa0d-5981-a596-b99322485945 |  | note | Specification/Drawings Reference - TNZ B2
label | b89e7222-1da9-5d94-86d8-67125acec2e6 |  | note | Frequency - Every 20m
label | d1f6e00c-b37e-5a09-81c4-3f25715149ac |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | 8c587a75-4b8e-5eab-8fd4-2b7537d1235a |  | note | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%
label | f032ca4c-331f-5d5a-ae8f-cf20f046660d |  | note | ○ Average 98% of MDD with nothing less than 95%
label | 0f8c0272-8c5e-5f04-8a50-dedd81dca62d |  | note | Records - Test reports, Photo's
checkpoint-status |  |  | checkpoint | 3.8 - Basecourse Cement application rate
label | 2e92a789-3fe6-5763-abd9-74b37ac9a91c |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1c0a35d6-e2ac-5082-a398-3d6441798e18 |  | note | Specification/Drawings Reference - TNZ B/5
label | 5e10de9d-3551-5e38-bda3-36ae1f87ab68 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 0a1884de-f1e6-5232-a4f4-c8a48a3a7fd6 |  | note | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
label | f06a96ff-6010-5f76-8357-87110201102b |  | note | Records - Material specs, Photo's
checkpoint-status |  |  | checkpoint | 3.9 - Basecourse construction
label | a45b4a71-3b21-5d7a-8cff-22e837bfd867 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5370112d-5a2f-5ccc-ac41-c2460194d835 |  | note | Specification/Drawings Reference - TNZ B2
label | 91007fec-2e58-5c4e-8b4a-391decc81a91 |  | note | Frequency - Every 20m
label | 9a7f04c8-c4ef-5ec3-a5a4-53f5a3e6b78e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | efa7ac4b-9cf7-5621-a90e-2de9e9e3a716 |  | note | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
label | d9714f52-c982-5480-aeab-31c8f352af3d |  | note | Records - Survey as builts
checkpoint-status |  |  | checkpoint | 3.10 - Basecourse construction
label | a8c490b9-66dc-5d05-a50e-1b6b1b0b6b60 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4ea2263e-2593-516b-ba4d-ada616c33163 |  | note | Specification/Drawings Reference - TNZ B2
label | 3e3409e0-1dbd-55c7-9ead-34e16c0c5383 |  | note | Frequency - Every 20m
label | 03227d5c-d804-5bfb-ba56-ec425cb26151 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | 86f9698f-83ff-5d59-9579-07ff53373224 |  | note | Conformance Criteria - CIV>=25
label | f823ce89-108e-59e4-a3e6-14e39bcc7bdb |  | note | Records - Test reports, Photo's
checkpoint-status |  |  | checkpoint | 3.11 - Basecourse construction
label | 27e97157-0ec5-5a8d-89e0-ea167ed829a4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1bcaf79c-9c11-5c7e-9f41-2cfe24624e3c |  | note | Specification/Drawings Reference - TNZ B2
label | c64fb4e9-6c51-5eba-873f-e2652fe69160 |  | note | Frequency - Before sealing
label | 1d9c6734-1069-5670-971d-3b8eeed9db1f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | 3179474f-cae7-55b3-b9d9-a0b2d4c28681 |  | note | Conformance Criteria - Mosaic surface
label | 4dbe1879-f74e-5847-a5d5-64362a406aaa |  | note | Records - Photo's, Pre-seal checksheet (CS-4060)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.12 - Applying Bitumen
label | 9ccff7a5-af5e-5a12-8a17-67c87ae26a71 |  | note | ACTION (Hold, Monitor, Witness) - W
label | cadf0e62-5791-5026-a453-26e1d85c08b0 |  | note | Specification/Drawings Reference - NZTA M/6
label | 0a148a6a-0d1a-5151-bffe-cf398badfb49 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 7e26ede5-5018-546f-aebd-128f1cc6eec2 |  | note | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
label | 368a9a67-145f-5d89-b7c3-c2efba7ffbe9 |  | note | Records - Photo's, Pre-seal checksheet (CS-4060)
checkpoint-status |  |  | checkpoint | 3.13 - Degree of saturation
label | 53fed0c5-13e3-54a9-a4b2-fee745b308e9 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 61f422ac-79fd-54d9-94ab-dffacf9ad989 |  | note | Frequency - Before sealing
label | 8a1d91e3-c0f5-50d2-9a99-7da5925dde8d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | 8d936735-d644-5076-ae80-3f01fd90baf8 |  | note | Conformance Criteria - Degree of saturation should not exceed 80%
label | 6f276759-bfe7-594d-b5c5-f0b65dcaf861 |  | note | Records - Pre-seal checksheet (CS-4060)
checkpoint-status |  |  | checkpoint | 3.14 - Chip seal laying
label | 108d5f81-b8fa-54d2-b9f3-e3028cb2c370 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3d6d5284-042d-5624-9efc-6323b0fe063c |  | note | Specification/Drawings Reference - NZTA M/6
label | 4683ab54-98dd-5674-850d-502eadd90f2f |  | note | Frequency - During Construction
label | 5e31aaa5-9c4d-56e4-b192-8b3a707df70a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 235d39e5-42ac-548a-be56-7962b303cb9c |  | note | Conformance Criteria - grade 3 and 5 chip seal
label | 7e9b9caf-85d6-5db5-a5f1-2e235873d112 |  | note | Records - Material certificate(s), Photo's
checkpoint-status |  |  | checkpoint | 3.15 - Sweep & Line mark new chip seal road
label | f653e592-308c-5635-90bc-97b9d98ffb06 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 62d7dca9-38bc-59a1-8973-a1281cac654a |  | note | Specification/Drawings Reference - TNZ P/12:2000
label | 8c92ca16-d369-5afe-8e3d-0233c730327a |  | note | Frequency - During Construction
label | e899b782-cd3e-5568-be15-f43e690bfdd9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | df09c25a-6b6b-5e5e-91b0-a8058a4f87ed |  | note | Conformance Criteria - As per TNZ P/12:2000
label | 88ddd69b-48b3-5c60-b3e6-a7c8b70bbc61 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 3.16 - As-built Survey
label | 5b8ca600-77aa-54a1-bc6b-0d6d4009a169 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 85f42fc8-0a93-57b4-b21d-fe9c72d14b6c |  | note | Frequency - At completion of Lot
label | b2aeeeaa-d8d7-56ff-b6dc-67763838b43a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | dfd17e65-ebb5-5a20-b41e-3f250e47a947 |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | f16cacc7-c7de-5aaa-aecd-c9c93cf592df |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 4: Final Inspection and Handover
checkpoint-status |  |  | checkpoint | 4.1 - Quality Assurance deliverables
label | 8a0eb5ba-f9e8-51bd-bc59-62fc16898792 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ba8197df-b613-54b0-87f3-1fcb6f8d4c8d |  | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 5459a453-144c-53ba-8544-eee4bb42a29a |  | note | Frequency - At completion of Lot
label | 236bb8b4-8297-5014-ada2-540911848bfd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 35623637-b9c8-5329-8bb5-e570e0fff161 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 4f73cfaa-f970-5e51-a4f8-a4349c5c3a00 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 4.2 - Completion Sign Off From Fields Below
label | 4ab39cd5-0c79-5f72-882c-ee376fb24c57 |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | CS-4002 - Concrete Pump Operator |  |  |  |  | Yes | CS-4002 - Concrete Pump Operator | eda62232-3d8f-4ff6-9c50-29437ae6b228
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | Details:
text | 4d6fdc48-3dd6-54d4-a55c-3b8439c32153 |  | textbox | Project No.:
date | 9d66a844-4978-5bc4-b520-094910046cff |  | date | Date:
text | 7d488fee-830e-5de1-8eea-0cd2b92d15ca |  | textbox | Name:
text | c5ee79e1-a5ec-5936-9a99-b799551ef73b |  | textbox | Area:
text | 8ca685e0-ac2e-5fb8-91de-3bcfeabca29e |  | textbox | Location:
text | 2d91851f-cd26-5f14-b6cc-96bb3b0e2a3a |  | textbox | Fleet No.:
text | c9868f55-71d5-5148-b8c9-6cad627a9699 |  | textbox | Make/Model:
text | decc9998-0f63-5014-822d-9d53b6a81b8b |  | textbox | Hour Meter: Start:
text | fbe84f25-b1ba-5317-a850-d28daa5d968c |  | textbox | Hour Meter: Finish:
checkpoint-group |  |  | section | CHECK BEFORE STARTING
checkpoint-status |  |  | checkpoint | Grease Points
label | afd7e609-3931-518b-afd7-68d922070709 |  | note | PASS = OK
label | 5ecaf92d-fcac-5442-9459-16a2745020d0 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Oil / Water Leaks
label | 6ba8aa8c-5644-595e-8af8-8a06dd066899 |  | note | PASS = OK
label | 336103a5-7bf5-5e71-8399-ba7239ef19a0 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Radiator & Fuel Tank Level
label | dabe8f71-cdba-57b0-99fb-5980d0b50589 |  | note | PASS = OK
label | 4f1bab09-3c0a-5a8f-a40f-265ba75bba2c |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Engine Oil Level
label | 4cc92694-2702-588c-944b-7c57fde8d808 |  | note | PASS = OK
label | 2b1a3c7b-240d-5e67-b8d2-3deb47a55e1c |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Hydraulic Oil Level
label | 0c378f70-a72a-5374-9ac1-af6df63622e1 |  | note | PASS = OK
label | 87de07db-1ac7-58b9-9899-ec38bdbedef0 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Fire Extinguisher & First Aid Kit
label | b0ef466b-3c33-52e6-9a3f-1248a606821b |  | note | PASS = OK
label | e330dcd7-a63e-594a-a60e-1aa715cc65e3 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Pump set up level & secure
label | ef2a5220-4c81-5b41-bf72-22f66d41c55f |  | note | PASS = OK
label | 04af0138-aa36-5d3b-89be-b89b0c6ea354 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Water Box Full
label | 72c8e385-880e-50f0-9b5d-db16a89abe38 |  | note | PASS = OK
label | 9ece22e2-c745-56c9-b297-2ea5b0fbb2a6 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Guards and Covers in Place
label | b83e9227-e104-50a5-9fc5-0e8a45dccb9f |  | note | PASS = OK
label | c860d745-db1a-5f31-8fe3-780f4a369c51 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Delivery Pipes condition & cleanliness
label | f1e1b7ca-25ff-5ba2-8af2-d7f37802a6da |  | note | PASS = OK
label | bf88d323-be15-513e-b0bd-ca4fae09b268 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Delivery Pipe Connections correct & Locking Pins Fitted
label | 93bd1e6d-c2bc-59e4-acf7-78a2520928b9 |  | note | PASS = OK
label | ff5f647f-4469-5c02-a913-9517181181c9 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Delivery Line Adequately Supported
label | 04057f2a-8227-51c3-a804-fb6ceeffdc96 |  | note | PASS = OK
label | 378728d6-c053-5d0c-afee-03e8df296f67 |  | note | FAIL = Defect
checkpoint-group |  |  | section | CHECK AFTER START-UP
checkpoint-status |  |  | checkpoint | Oil Pressure
label | e9393ee5-ced6-5194-bc39-6d2ecfa2191f |  | note | PASS = OK
label | 9f7a1b1e-928e-56c6-99ea-6fea78ca49d2 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Water Temperature
label | 3c1f6a18-3983-5ca7-940b-d65907f0d7a8 |  | note | PASS = OK
label | f2b93b0a-7d48-5962-a6b7-5e8fda38d269 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Emergency Stop Button
label | af5a70b4-eaa5-5867-a2d3-12ece36391ff |  | note | PASS = OK
label | cb03ae7b-32b2-591f-9b9e-5b8d1ef39282 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Remote Control Functioning
label | ad091776-780c-5d36-ae6c-7236414339da |  | note | PASS = OK
label | cd711624-702a-58bd-bc17-a9f9569746be |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Hydraulic Oil Pressure
label | 502978cb-6cc2-580f-8baa-169dd20b504a |  | note | PASS = OK
label | bca8e067-8a6e-5b5f-bcf3-267778ca0a30 |  | note | FAIL = Defect
checkpoint-group |  |  | section | DEFECTS
checkpoint-status |  |  | checkpoint | DEFECTS:
radio | 4963446a-2916-574a-8170-78fbd022a990 |  | radio | (Select One) | No Defects Found, Unsatisfactory Condition Found
label | 36dc4118-fc9c-5339-bdfa-6874d9505774 |  | note | Defects Corrected By:
text | 4970dff2-62f3-5953-b886-452df32f2038 |  | textbox | Name: |  |  | (print)
date | 37edabc4-d235-57fb-9c99-99d8b833d113 |  | date | Date:
checkpoint-group |  |  | section | CHECK DURING OPERATION
checkpoint-status |  |  | checkpoint | Deliver Lines Grouted
label | 52f61c32-a4ed-5eb1-bf3a-78e424906411 |  | note | PASS = OK
label | a31a17d0-0bb5-53a3-a046-5f295eed4616 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Concrete Slump
label | 27498e5a-56ac-5084-baab-fdfebc409a49 |  | note | PASS = OK
label | b2e44601-ee9b-5b50-878f-450fa318f483 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Hydraulic Pressure during Pumping Max 160 Bar
label | 29d7b0ec-53d9-5b45-a197-9424889621f6 |  | note | PASS = OK
label | 6994b09e-e9b7-5038-b541-7a33c92f2768 |  | note | FAIL = Defect
checkpoint-group |  |  | section | CHECK DURING CLEANING
checkpoint-status |  |  | checkpoint | Direction of Cleaning
label | eca1ce58-0e9f-59b6-a5f4-db4ac24f336c |  | note | PASS = OK
label | c3160cd8-1ea1-55d3-9581-ecc2ce457bcf |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Reducer & Rubber Hose removed
label | 214d9dfc-2efe-51d1-9612-5df22bdd2aff |  | note | PASS = OK
label | 0a338f44-a564-52e7-824d-ba39f5df93ea |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Air manifold and Catch Basket Fitted
label | c12a73dd-1919-52d3-a3ed-d50cbd9ba292 |  | note | PASS = OK
label | c98d1fa3-b20a-5f6d-9d25-0c2f79a50407 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Personnel Clear of Discharge End
label | 3ba526a3-827c-5fb7-81f9-8b2d03d21e64 |  | note | PASS = OK
label | 19f39336-c14a-53c0-a87b-ab859e21bf61 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Air Pressure Max 40 Bar
label | e88012e0-4ffa-58aa-b7a0-6f145d6698ac |  | note | PASS = OK
label | 62cd997a-ef1c-527d-908d-66fe2b042433 |  | note | FAIL = Defect
checkpoint-status |  |  | checkpoint | Equipment Clean
label | 92303094-1091-51f2-a42f-968429289940 |  | note | PASS = OK
label | 18aebd28-d572-5f16-a19a-8b98f95a5982 |  | note | FAIL = Defect
checkpoint-group |  |  | section | COMMENTS
checkpoint-no-status |  |  | checkpoint | COMMENTS:
label | 7c5ac4ce-e32f-52b0-bd2b-3679d8a1f033 |  | note | This report MUST be handed into your supervisor at the end of each pumping operation
checklist-sectioned |  |  | checklist | ITP - D1603B - ID587B - Otoko Flats Underslip | itp |  |  |  | Yes | ITP - D1603B - ID587B - Otoko Flats Underslip | f08233bc-12f7-4efc-8321-92d9e17a472f
checkpoint-group |  |  | section | Section 1: RECEIVING INSPECTIONS
checkpoint-status |  |  | checkpoint | Project Site reps.
text | d0a4b0c4-2d59-53d6-b82c-1c3a502cc6e8 |  | textbox | CPS Eng.
text | 640c2b6a-3389-5421-ba2e-c43315181886 |  | textbox | Site Engineer
text | e5591bdd-dbd4-567d-8fec-0c8b4288d644 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Rock Armour (D50=600)
label | 07cf68c7-8e9c-5192-8cc9-266b04f1ad3f |  | note | ACTION (Hold, Monitor, Witness) - H
label | bb64b39a-9bc1-56eb-a043-fd9c43faac04 |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | b38ddd73-2f1e-5cbe-8a63-d9007646b6fd |  | note | Frequency - Prior to commencement
label | 2e3c6909-4b64-50b8-a1ba-d8311ff1d3eb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 629ba05e-6f1e-5e9b-9849-45c77c06fb73 |  | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D50 of 600 with a minimum specific Gravity SG of 2350kg/m3.
label | f7bad2c9-7509-5955-b25b-87ed4e032f4a |  | note | Records - Material source test results, Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Bulk Fill (GAP65/GAP100) or similar
label | 0ead98b4-a138-5c97-a61e-dc24252cfeb1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 31708954-544d-5db7-93a7-eb017325ced0 |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | c707215a-1a6c-53a7-bb19-fd2d2c8c930a |  | note | Frequency - Prior to commencement
label | 5c590bd7-dbda-5d0b-bcda-e1cc5d8adbb5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 5c513e90-0c9e-564b-a2b4-c305389d939a |  | note | Conformance Criteria - Should comprise clean granular aggregate and have broken faces.
label | 3b895cf1-b122-57ec-ac62-c795f1bfd979 |  | note | ○ Material source testing
label | 48603bf2-c0ff-513f-9601-94d009240ac0 |  | note | Records - Material source test results, Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Class D A39 Geotextile
label | 76be5439-fc7b-5a49-9a5d-6bc042fc5804 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 58bf3d70-0564-5e1a-939a-0cb0315401e4 |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001, NZTA F/7
label | aaa64b86-e044-5759-abd1-31b0163df075 |  | note | Frequency - Prior to commencement
label | 13cfe51a-4956-5a9c-bcaf-e05b7642f03c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 3e820097-2ecc-549d-bf95-eab17434ef38 |  | note | Conformance Criteria - NZTA F/7 compliant before placing foundation material and engineered hardfill
label | 3a728f12-220d-547a-b160-a0b01e08032e |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.4 - Class E A49 Geotextile
label | 0ddd966a-8134-53f6-bd78-12b2dc037fae |  | note | ACTION (Hold, Monitor, Witness) - W
label | c50c61aa-aef5-5244-a28c-8f84fd2da8cf |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001, NZTA F/7
label | e6b644ac-e675-5426-82c4-6c501e031ef0 |  | note | Frequency - Prior to commencement
label | 2f6e83cc-aa8c-5bfd-9c4b-a9710ef0ca6a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 6a47b1c4-a243-5041-9393-85df3f76e53b |  | note | Conformance Criteria - NZTA F/7 compliant before placing foundation material and engineered hardfill
label | 11471221-ec42-52cb-8a09-e02c77b4b57e |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.5 - Megaflow strip drain or drainage blanket for seepage if encountered
label | 342c0437-c034-5ca4-9362-85a094706f7d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9c3dcdc1-cec6-576b-8c59-107abc05308f |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | a04c400a-e989-514a-aa88-e9e97d5c61ce |  | note | Frequency - Prior to commencement
label | 51257ea8-4bdb-5a72-9c8e-b028467e3151 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | e2ed87ef-a2da-5303-9b7c-8d6630c4eb6e |  | note | Conformance Criteria - Subsoil drain shall be in accordance with TNZ F/2 or approved equivalent. 110mm diameter Novaflo subsoil drain, or similar approved.
label | 961373b9-792b-58a6-92ca-61c4ba55aff0 |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.6 - Top Buttress and surface water drain rock D50=150mm
label | c008f964-9753-5263-ab25-2343ac995e46 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f8a26446-8af4-5604-a8cf-4cce31f307b0 |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | 9cede806-8546-5248-a764-dc654fadc989 |  | note | Frequency - Prior to commencement
label | 993825ac-1735-5357-9b7e-90a0e1b4d9ef |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Source test reports
label | ed9529d6-301d-511b-913f-88ffdc211c9a |  | note | Conformance Criteria - D50=150mm rock with minimum specific gravity (SG) of2350kg/m3
label | 6cd3e68a-a5f5-5ba3-aef1-85b567074b99 |  | note | Records - Material source test results, Delivery Dockets
checkpoint-group |  |  | section | Section 2: IN PROGRESS INSPECTIONS (Buttress)
checkpoint-status |  |  | checkpoint | 2.1 - Survey Setout
label | a73e536d-02c3-5f72-8a3d-24a1c7e5abcf |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5d9e0dff-beed-5418-999d-31cadb400d45 |  | note | Specification/Drawings Reference - Consistency with Construction Drawing
label | 42106f1d-de1e-5bdc-9458-4a39d0bef5f6 |  | note | Frequency - Prior to commencement
label | d1934c9f-7846-5da8-8e1a-812980ff2423 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | f926665d-7019-52cc-82f0-9171146ef564 |  | note | Conformance Criteria - Set out extents of fill and check against design drawings
label | 0341067f-fef8-568c-8b59-bbc667bd73dd |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | 59ad444a-cf31-544f-8bf7-a55128caca6b |  | note | ACTION (Hold, Monitor, Witness) - W
label | ee437ed9-4520-5d74-bfc3-e9bac0bc4d1a |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | e54bc3d7-19fb-524b-ae78-5a27a283a14a |  | note | Frequency - Prior to commencement
label | c65df24d-7345-5dc7-b4ae-37d78d06f1a3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 7b8acf47-e836-55f2-9c70-5b11ac62f7e5 |  | note | Conformance Criteria - Remove and clear the vegetation
label | 0fafd3a9-edc5-5582-88c2-ca409684edd2 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.3 - Subgrade Excavation
label | 8699af9e-0797-582a-801c-9a1baca64cf1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ba89d294-9c3d-571b-8339-d376d604d0e2 |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | be33e8ff-bc0a-5057-b296-5e1ccaaed6f3 |  | note | Frequency - During Construction
label | 2949ae17-4f3c-5a6b-81f8-ce4c12db44d3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 99d0e3ef-ac33-5d38-ad47-c71a20e71936 |  | note | Conformance Criteria - Engineer to assess foundation material suitability
label | 247572b3-bae4-59ee-913c-ca54934132bf |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Subgrade Inspection
label | b90769ce-9bad-50d8-ad76-b7506d1a42e7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7103cdd3-e2df-54ec-887f-f5a8768b7ae5 |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | a9c72c03-104d-5df3-91cb-dfbc709a1b3a |  | note | Frequency - Per area as required
label | bb0891b0-74d3-51e0-82ad-327407f7156e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 3fcd46a8-c969-561e-abb2-7bcb055e98f4 |  | note | Conformance Criteria - Inspect fill foundation.
label | dc03fa11-a6e6-5691-8f0e-3bc999e52458 |  | note | ○ Fill foundation must be approved, in writing, before filling commences
label | 4129c859-842b-5a88-a096-05bf0656c79c |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Ground Improvements
label | c128f040-136c-5adc-97c9-9feb36e63c62 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1ceef1f4-037f-56c6-b097-14d83c1adb5e |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | 7ce4b197-fec8-52eb-bc5d-30bc7ef9e0ad |  | note | Frequency - Prior to commencement
label | d98953fa-1838-5d2c-9671-697d2faf5d73 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | d405f476-fbbe-5416-b14f-999d0971d7c9 |  | note | Conformance Criteria - Any area that requires Ground Improvements must be completed as per Engineer requirements and be signed off and closed before bulk earthwork operations commence
label | e33d33bc-6fbb-520f-a5f3-60f5112afe4b |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Class D (A39) Geotextile installation on the excavated face
label | 2a90ff42-0964-57bd-93e1-d8228f64bcd8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 31c99359-7046-5f18-9bae-48562c68631e |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | 10f1f4c3-3efd-5f7f-b85d-f0f3ddb7822d |  | note | Frequency - During Construction
label | 8924e778-ecea-58bc-b5d0-a393bd11799b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 4bd04732-1567-5ad8-93e0-10508958c798 |  | note | Conformance Criteria - Excavation undercut to be underlain with Bidim A39 or similar approved before placing foundation material and engineered fill
label | db2e6580-a64e-50b7-b70d-585dff1aa0ee |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.7 - Megaflow strip or drainage blanket installation or 110mm Novaflow in 300x300mm trench for seepage if Encountered
label | 388e9175-f4cf-510a-a01c-1820709c4bf3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b3d1d38f-a638-5ef0-af84-a036f26e344d |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | ed505663-86cf-59ae-afc3-4b37be449267 |  | note | Frequency - During Construction
label | 6f8d936a-5f42-54f9-9e2c-ee659475450f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 8c891a36-396b-55b1-8ca0-6f800122cbf0 |  | note | Conformance Criteria - Engineer to assess suitable drainage location.
label | b29c5a33-1899-59e7-9fee-0d0b4bbd1840 |  | note | ○ Drainage positions to be confirmed on site by the Engineer. If water is seen to flow through existing fill or natural soil, additional undercutting or subsoil drainage may be required.
label | 472e6966-31b9-5b1c-bed3-7ac1dc3a1f5f |  | note | Records - Photo's, Drainage Line record check sheet (CS-4025)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Bulk Fill placement
label | ecc1f6cd-7dec-53da-9fb6-d309d76db644 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 3ad16f9b-03a0-58e5-9777-a05e0c1714eb |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001, NZS4431:2022
label | 235c74d9-bd9f-5337-bbd8-41327a6a9949 |  | note | Frequency - During Construction
label | 167ff4e8-592b-5ebe-ac3c-ca08807a79d7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 06eceeb0-83c4-52ab-890f-bdbc66e13c59 |  | note | Conformance Criteria - Engineered fill to be placed in layers of maximum 300mm and compacted in accordance with NZS4431:2022 with appropriate on-site quality control.
label | 7abd16a8-69db-596f-bdd4-95aaae524efc |  | note | ○ Fill should be placed on dry subgrade.
label | 664f3078-c8ce-5cd3-abb2-690ae786f2a9 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.9 - Bulk Fill Compaction
label | eceff239-be61-59f4-ae39-b886ed8a712d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 057ffa41-9701-5735-b624-68bd38421f09 |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | a64a9020-0c3c-5e70-bad3-dbd4d6f88ef8 |  | note | Frequency - During Construction
label | 49ade9f1-88a6-5771-a455-8b16e10a6a41 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | 6e28ab32-8355-5af3-abc1-f3029bc52514 |  | note | Conformance Criteria - A Target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
label | 29e68b04-2b8d-565e-97b1-8120349e6ded |  | note | ○ Nuclear densometer testing (NDM), by an IANZ accredited laboratory, will be required to confirm the engineered fill has achieved the required level of compaction
label | 81cd3bb9-6c6c-5220-868c-c2695812721a |  | note | Records - Compaction test reports, Photo's
checkpoint-status |  |  | checkpoint | 2.10 - Form and cut fill batter as per design 2.5H:1V
label | e2c85e42-e213-5f74-9520-91676ba8c5c8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a471ffa7-f369-5285-a522-07f12711ccc7 |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | d3183490-1108-5175-9e72-0e4bdce1572a |  | note | Frequency - During Construction
label | df8dde18-6825-59c9-a5a4-a499742d585e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 9dfc6c5c-5d76-5697-9dfd-61b1dbe3654d |  | note | Conformance Criteria - Engineer to assess the completed slopes suitability to the design guidance.
label | 6094a647-0d16-5e09-bfd2-fd04fbed97d2 |  | note | ○ Slope angle of buttress is to not exceed 2.5H:1V
label | f2eecfff-4d45-592f-b65a-41e532fc040b |  | note | Records - Survey as builts
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11 - Class E (A49) Geotextile placement along the face of fill batter
label | 6dcf9a01-f460-59a8-b252-9f494d01388b |  | note | ACTION (Hold, Monitor, Witness) - W
label | 9414b357-948b-5227-a05f-dbfc9e24964e |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | affd7acc-e11c-5dc2-818f-dea1267a162b |  | note | Frequency - During Construction
label | c010fe47-4c02-5004-b0f0-2936309d5cbe |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 92e0caef-4576-524a-a5b1-252050548e33 |  | note | Conformance Criteria - Class E (A49) geotextile to be placed between the rock armour and bulk fill
label | fc1ff568-cba2-5fbf-b7af-dedcaf0a347b |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.12 - Rock Armour placement along the face of fill embankment
label | 4a962155-0cfd-5a83-beaf-7895085480cf |  | note | ACTION (Hold, Monitor, Witness) - W
label | b950dbc0-b457-573c-8686-086f8f5315c1 |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | 57bdba66-7bc2-57c0-8e50-6aef56811fd0 |  | note | Frequency - During Construction
label | 59fc2f18-a662-5814-ac23-91e36a65b351 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | c29a9f09-b701-516f-8280-883420eb2737 |  | note | Conformance Criteria - 2 x Layers of Rock riprap D50=600mm diameter)
label | 9678b4da-c415-5206-95c2-13a0f138e44b |  | note | Records - Photo's, Survey As builts
checkpoint-status |  |  | checkpoint | 2.13 - Rock Armour key into ground
label | 32e43943-bdfc-512d-844c-7dd21d95ace6 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 946970ba-7b6b-5f61-ab68-3ede9aff20ff |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | 025042a9-59c3-5d35-8546-e1faab176bf8 |  | note | Frequency - During Construction
label | a4ce3254-afed-55ed-a44a-e1e35c9e6e27 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | 5b41b1c8-806f-579f-8efe-e3adc6c433ff |  | note | Conformance Criteria - Rock armour to be keyed into natural ground in front of the bulk fill buttress, Dimensions to be confirmed by Engineer. Typically 0.5m to 1m deep and 3m wide as per notes on drawing.
label | aeb7660e-be25-5664-973a-b97429a7bc8f |  | note | Records - CPS COR report and survey as built
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.14 - Buttress Crest
label | 972b1364-7920-54bf-937e-2231c5d281fa |  | note | ACTION (Hold, Monitor, Witness) - H
label | d954c1dd-c3e4-5f94-90bc-8d00445b7ae9 |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | afef67ba-d73a-56b1-adb0-6280f5c063dc |  | note | Frequency - During Construction
label | bc4047cb-3c5b-5d07-916e-df92508c4888 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection, survey
label | f7ee2cac-4e76-5605-882c-0472f44e0f8c |  | note | Conformance Criteria - The crest of the buttress slope shall extend to a width of 2m beyond the current fence line alignment. The drain and top of the buttress and secondary flow path shall be lined with rock (approx. d50 = 150mm diameter)
label | a717bcf8-a364-5da2-9150-ac0818271f8d |  | note | Records - CPS COR report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.15 - As-built Survey
label | 60711ec1-f055-5df9-8422-240114db505c |  | note | ACTION (Hold, Monitor, Witness) - H
label | c255d6c6-77fd-5f55-9172-5df326cc31cb |  | note | Frequency - At completion of Lot
label | 96331e58-404f-5dcb-bb12-8438b36ce81e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | bf8434ed-3086-5dea-a0c2-17ffa3f2ec3b |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by CPS Engineer
label | d1f7da35-8906-5c83-8cfa-1d5097a8fb53 |  | note | Records - As-builts, CPS COR Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.16 - Fence installation
label | a2c751d8-7e67-5f4f-a717-c668877862ba |  | note | ACTION (Hold, Monitor, Witness) - W
label | 609d0d88-fe7a-5a85-b6ad-c41b237618f9 |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | c034d96b-26c6-5139-b7c0-e4f2754ed15a |  | note | Frequency - During Construction
label | 5070eb9a-84d6-5cae-a555-4d90775e87e8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b3836fa1-f4cb-55f1-a2eb-37352b19e1af |  | note | Conformance Criteria - Fence line to be reinstated shall be "like for like" and positioned along similar alignment to the existing fence line
label | 31c92313-2c83-5af5-a4cb-b40ac244e2c7 |  | note | Records - Photos
checkpoint-group |  |  | section | Section 3: Final Inspection and Handover
checkpoint-status |  |  | checkpoint | 3.1 - Quality Assurance deliverables
label | 385d4ac6-ed80-50d1-a2bc-e46a85147969 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 03614316-af17-55bf-9ac8-c5de922058a1 |  | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 0647edae-469f-54e0-a827-b9794191d844 |  | note | Frequency - At completion of Lot
label | 1f1828b1-5e8d-5084-9764-de39f7e94974 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 0a278d4b-5c47-52df-a6c0-a4d56323dc57 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 06122f0e-8ece-51f6-afa8-ba167231a91c |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 3.2 - Completion Sign Off From Fields Below
label | 5fd8387a-d79d-55ae-b855-4f68619bc226 |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | ITP - F5001A - Hicks Bay Slip Repair - ITP for works | itp |  |  |  | Yes | ITP - F5001A - Hicks Bay Slip Repair - ITP for works | f1ac2565-6c2b-4a96-baa6-00b453de60ff
checkpoint-group |  |  | section | Section 1: Materials Compliance - RECEIVING INSPECTIONS
checkpoint-status |  |  | checkpoint | Project Site reps.
text | ba7e57d0-75c3-5132-9109-e7f7f4217e61 |  | textbox | GHD Eng.
text | 25aafb23-dbf1-587a-9d78-ae062011aec0 |  | textbox | Site Engineer
text | ed4a5ebe-47e2-54de-b0f4-dc803832b1b9 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Rock Armour, 2 tonne rock class (D0.7m to 1.5m)
label | 786f645d-1e3e-5f38-8e5e-c8f72c10be86 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 77e16301-8dc4-53f0-91ec-dc894d000dc8 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-1253342-Q002
label | f1473d90-41c0-5b31-8549-18795847cd01 |  | note | Frequency - Prior to commencement
label | 1afd8d2a-25ff-5d97-b6ad-e6773f1db683 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | ab17d09d-58d4-5de3-b9cc-7db8712b3706 |  | note | Conformance Criteria - Rock armour shall be hard, durable, quarried or natural stone free from dust, clay, organic matter and other deleterious material. Shall have a D700 to 1500 with a minimum specific Gravity SG of 2350kg/m3.
label | 079e806d-be9c-511d-8b29-32f50e560c79 |  | note | Records - Material source test results, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.2 - Granular Backfill - AP65 (1)
label | 1073a260-844b-5be0-945e-d034293ba329 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 81f9fa33-3f63-56bd-9350-ea1410b1fcca |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | bcb515b2-92ed-5a38-99c7-a3b49cc991a7 |  | note | Frequency - Prior to commencement
label | 8eb52025-b62c-5adc-9f6d-0eca6b1bc8eb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | d21a73e3-6484-5acb-bb75-456c1a15b5fe |  | note | Conformance Criteria - Shall be free draining, hard, durable, well graded, crushed granular material such as AP65 with a fines content <5% with more than 2 broken faces. It shall be free from organic and vegetative material and compacted to achieve 90%MDD. Compaction maybe checked by clegg hammer.
label | 39aedeec-f922-5f14-a210-5f297434705f |  | note | Records - Material source test results, Delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Granular Backfill - AP65 (2)
label | a9342567-ef5a-565a-a755-3abf7c8af8a3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5127c2b3-46a3-5297-b54b-ea62a2975fb2 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | 5abd01ac-0dd1-543c-8b92-f784eeb262e6 |  | note | Frequency - Prior to commencement
label | 770e95bb-ab15-5cce-b733-2547f812d642 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Laboratory Test Results
label | 19db35eb-9f16-59ce-bb2b-7c8807eb184e |  | note | Conformance Criteria - Address of the source quarry. The geological description of the parent material. Particle Size Distribution (PSD) Test, Compaction Test and Broken Face Percentage Test Results from a Representative, General Fill Sample Tested in an independent and accredited Laboratory
label | 59d83fe0-eb41-558a-8c1b-d786a206c173 |  | note | Records - Laboratory Test Results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Granular Backfill - AP65 (3)
label | 0ca72c48-6a4e-570e-bf2d-9c8f86e10157 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 450528b5-d01c-505a-891d-89ce3f4491d4 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | f210f35c-6ed5-5467-b728-38721ca26039 |  | note | Frequency - Prior to commencement
label | a5ce139f-4a52-5e6c-ab7c-6ee61de8fd36 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Laboratory Test Results
label | 29fcff46-66fd-5f44-b811-a900cc2bae14 |  | note | Conformance Criteria - Results of Compaction Tests as Specified in NZS 4402:1988 - Test 4.1.1 or Test 4.1.3 are to be carried out on the proposed backfill and the results presented to the engineer for agreement prior to construction. These are to clearly show the Optimum Moisture Content and Maximum Dry Density Achieved
label | 8d9240fa-3d5a-5900-85c2-ab5038925311 |  | note | Records - Laboratory Test Results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.3 - Geotextile Filter Fabric Bidim A64 (or under Rock Rip-Rap on Culvert Outlet Scour protection
label | 0ed90c4b-86f9-5e72-b227-fbeb34a1e8f5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a504e602-dd7f-59d9-8528-fd80ffd09e44 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | 5a440ab3-7fb2-5402-a0c3-2ca62c6b6365 |  | note | Frequency - Prior to commencement
label | 8980ddc9-e196-5d20-a7ca-c768c4729352 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | 86d7d972-2fa4-5c78-b5e5-fdd1883f054a |  | note | Conformance Criteria - NZTA Strength Class C. Filtration Class 1 - Bidim A64 Geotextile or an approved equivalent - compliant placed under Rock Rip-Rap
label | 4801fee7-5e78-5049-8790-cc4735a4b3b8 |  | note | Records - Material compliance cert, Photo's
checkpoint-status |  |  | checkpoint | 1.4 - Deep Rock Rip-Rap (300mm-500mm dia.)
label | bfe3922f-e352-5458-89e2-b954a8e94dac |  | note | ACTION (Hold, Monitor, Witness) - W
label | d66555f3-a4ea-5950-b05c-ed72273eaeff |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | bcaf8729-73ff-5c2e-96fa-acf7453150b6 |  | note | Frequency - Prior to commencement
label | 87ff15dc-cb6f-58ca-af46-1777d5db6f8c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier material test certificate
label | 674996d0-0349-506a-8ef4-825b49cb369c |  | note | Conformance Criteria - Apron for Scour Protection at Culvert Outlet
label | 9a8304fa-0d02-56aa-ab78-2ad88987e808 |  | note | Records - Material source test results, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.5 - Guard railing
label | 48bfd126-b35b-59bc-b002-b61ae8334b2c |  | note | ACTION (Hold, Monitor, Witness) - W
label | c8a435a6-c6f4-580d-9880-4c81fd152854 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C004
label | 4d3bb00c-0283-5041-8184-80eb5112036d |  | note | Frequency - Prior to commencement
label | fe3bd8de-d849-51da-86a8-10644b986d15 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Manufacturers certificate
label | df1d45e9-9c0c-5383-a899-415b90e9b67f |  | note | Conformance Criteria - Guard railing system to be installed to manufacturers specification. see ITP for Guard Rail
label | 2b52e970-74a4-5089-95f3-4589cd7e9281 |  | note | Records - Manufacturers spec, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.6 - Precast RCRRJ 525 dia. Pipe
label | d128f6d1-56bf-5415-9154-2a1af6c37806 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d9887691-4f1f-5d23-a2ed-71eb9b632a72 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | 90633ec5-e87c-576b-b9d7-78c487afb459 |  | note | Frequency - Prior to commencement
label | 153a783f-6783-51c6-a2eb-e41f9148c5e9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | cf92b2c3-a959-5171-b5bf-8ced8ee07fdb |  | note | Conformance Criteria - Delivery Dockets are collected and signed before precast pipe materials are removed from the truck.
label | a8a647bf-1d66-5d9f-b759-ba9a0540f835 |  | note | ○ Class 4 RCRRJ 525 pipe to comply with AS/NZS 4058
label | db8fe520-30c9-5fa0-8849-8d0077e43fb6 |  | note | Records - Manufacturer cert, Delivery dockets, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.7 - Precast materials
label | ab7cab42-c02c-5363-8a0d-ed2160b9c4ad |  | note | ACTION (Hold, Monitor, Witness) - H
label | ec76aceb-1c47-58d0-a05f-4ffd11352837 |  | note | Specification/Drawings Reference - F3202A-Culvert ID 614, F3202A-DS-GT-RP-0001
label | d0fcfd8a-8b7c-5f1d-a85b-2d8a54b75747 |  | note | Frequency - Prior to unloading
label | f7dad77a-2c38-5a22-851c-644c68e0c632 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 9a06d241-5c02-5fc6-9139-ab7f60520535 |  | note | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
label | 24c61288-adf1-583e-951c-eb8206951456 |  | note | Records - Manufacturer cert, Delivery dockets, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.8 - Hynds Mountable Wingwall for Culvert Inlet or similar approved by Engineer
label | fe948366-b8bd-5e30-93ac-864bf862e4b4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 35e2bcaf-3ec7-5f04-b64c-b55927a3a8e0 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair - Drwg ref: 12617302-01-Q001 rev.1
label | da73fdc9-c1f1-549b-b09f-be9bf26830e8 |  | note | Frequency - Prior to unloading
label | 2e89d27b-9eea-5bc3-9e40-86222bd31e6a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 72601a65-0808-5f96-b0df-2b1a5e5fc637 |  | note | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
label | 9aede700-1f17-54f8-8c91-dce586e957fa |  | note | Records - Manufacturer cert, Delivery dockets, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.9 - D1050mm Concrete Pre-cast Manhole with concrete lid
label | b16b1a1d-236f-557f-87dc-dbe8399aad61 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 93d04a23-80e1-5f5b-9b08-45ce15c88fb9 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair - Drwg ref: 12617302-01-Q001 rev.1
label | 65498fc5-d63a-54f1-bec4-4502521b3b74 |  | note | Frequency - Prior to unloading
label | c75ceb4b-f172-55a0-a7e1-e7aecfaecf8b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 7e54bf4b-0c7c-5b1f-b2db-9ed02070a0ab |  | note | Conformance Criteria - Any damage to precast materials is to be assessed, returned to the manufacturer if not compliant or remedial work to be done by the manufacturer onsite & an OFI to be completed
label | 31453115-2341-56d5-b3cc-855a6630bfaa |  | note | Records - Manufacturer cert, Delivery dockets, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.10 - AP40 (Basecourse) or approved basecourse modification
label | 08c3b89c-77c3-5802-8576-263abe4ec3e2 |  | note | ACTION (Hold, Monitor, Witness) - H
label | d155378b-c160-558f-b6ab-e5d89e012640 |  | note | Specification/Drawings Reference - TNZ M/4 Section 3.2 & 3.3
label | 024eb254-564f-53ed-ba9f-1e94793ec411 |  | note | Frequency - 1/source and at least 1/3 months
label | 6b24b15e-8ea4-53f8-b828-c52327ca9f3d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 8dd12409-e64c-5862-96ba-c3457a3aabbc |  | note | Conformance Criteria - Particle Size Distribution, Plasticity Index, Soak CBR, Crushing & weathering resistance, Clay Index, Sand equivalent
label | 2041fcaf-6f18-5365-9b22-7fe4c6843066 |  | note | Records - Material Source testing and approval, Delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.11 - AP65 (Sub-base)
label | 844df46d-f13b-5c72-b6ed-38f4c39ccf3b |  | note | ACTION (Hold, Monitor, Witness) - W
label | b5e94ee2-c691-5fd6-ad7d-2325c687ed27 |  | note | Specification/Drawings Reference - NZTA
label | 03c7659c-f35e-5889-bc90-39845a7db075 |  | note | Frequency - 1/source and at least 1/3 months
label | 6db84737-e842-5ba3-8eec-7608c544ad54 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 9b1c2c94-e134-51a4-8606-11a67844ac92 |  | note | Conformance Criteria - Particle Size Distribution, Maximum Dry Density, Plasticity Index, Soak CBR, Crushing & weathering resistance, Sand equivalent
label | 6a924ccc-d802-5cc1-802a-334f842e7b71 |  | note | Records - Material Source testing and approval, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.12 - Grade 3/5 Chip
label | c5149dce-0442-5137-b2c4-d52b4d928acb |  | note | ACTION (Hold, Monitor, Witness) - W
label | 49f6ddba-ecf8-5af5-a860-69b719104bc2 |  | note | Specification/Drawings Reference - NZTA M/6
label | e346fb44-f599-569e-8d64-1e9dfb682d20 |  | note | Frequency - Prior to commencement
label | 0e84e7ed-1071-5b7b-a407-a55e5562bad5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 912309b6-250e-510d-8448-e00410cf21c0 |  | note | Conformance Criteria - Source property testing
label | a7a578de-9204-580c-8efc-01af0caafecb |  | note | ○ Traceability of all materials delivered to site
label | a7fc42df-b8b1-5bae-a5b7-7a8e9d27ed92 |  | note | Records - Lab test reports, Delivery dockets
checkpoint-status |  |  | checkpoint | 1.13 - Cement
label | e837a6e8-6364-5428-bb8d-f3b25a1065c4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2b265a18-a2bc-5382-a434-6d16fab748e1 |  | note | Specification/Drawings Reference -
label | 435bc650-01b1-59e9-b0da-1889b5d99ebc |  | note | Frequency - Prior to commencement
label | 14383c16-6629-5d4e-a0a8-c43159aea2da |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 5256ec22-a6de-5e90-913f-eeaa4737e74d |  | note | Conformance Criteria - Material compliance Certificate - Portland
label | 269239a3-bf4c-580f-bfd7-a92612adff35 |  | note | Records - Material certificate(s)
checkpoint-status |  |  | checkpoint | 1.14 - Bitumen
label | f187616f-3423-57d4-9729-2c325bbc9c0e |  | note | ACTION (Hold, Monitor, Witness) - W
label | d5137789-3adb-522e-b84e-738532333312 |  | note | Specification/Drawings Reference - TNZ M/1
label | 2e0e36a6-7b7c-52bf-ad1f-06c6c6c6f66d |  | note | Frequency - Prior to commencement
label | 2c54861d-f688-51f9-b69a-acdc32002216 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 9228b84d-2bb9-5be2-9f47-6c4396c388f6 |  | note | Conformance Criteria - Binder to meet TNZ M/1 standard. E2 Certificate
label | 0ae0805b-796b-5dde-82c2-993022f1fb5a |  | note | Records - E2 Certificate
checkpoint-status |  |  | checkpoint | 1.15 - Review contractor's materials supplier QA documentation
label | 9352b6cb-194d-5129-915e-54eaa90ed4f7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ce0f23bb-5177-5efb-a120-ef15a264ca3e |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | 1d9a887f-c7b0-5320-9e5a-87a104a9ddd9 |  | note | Frequency - Prior to commencement
label | 4c7c9f05-ab2a-5985-ac57-dfb5f5db0d42 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 8d2d21b4-7e1f-5108-a413-88cb829aaeae |  | note | Conformance Criteria - Review contractor's materials supplier QA documentation
label | e5a669fe-1884-5195-84d1-e7824b9acb7a |  | note | Records - Lab test reports, Delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Section 2: Construction QA/QC - SLIP REPAIR & CULVERT INSTALL INSPECTIONS
checkpoint-status |  |  | checkpoint | 2.1 - Survey Setout
label | cc9c8254-5f5e-5c77-836f-97c35a20269a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 03762eac-e556-5181-b1a3-2a416f9f7706 |  | note | Specification/Drawings Reference - Consistency with Construction Drawing
label | bfdc8ec8-c0e9-577f-ab4f-3584c884b368 |  | note | Frequency - Prior to commencement
label | 3457bd0f-6e40-51c6-8a86-51e995b94923 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | b867cef9-ba0e-5c7b-ac05-537be68aa822 |  | note | Conformance Criteria - Set out extents of works and check against design drawings
label | 20e7aa7a-0cf9-5d9e-a3f8-646f2400a1a5 |  | note | Records - Email/COR
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Vegetation Clearance and removal of loose debris
label | 2d8ae9af-cac3-5a3d-bb71-e90d16b8a985 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c72dc1e4-bcf5-5276-b037-e0dcb6ac6682 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | 98a74745-3119-5321-be91-2bf98afa81f6 |  | note | Frequency - During Construction
label | 9e999855-2220-5944-839f-39d128e8da84 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | ea0d1126-4f9a-5009-86ab-052e4ca0241c |  | note | Conformance Criteria - Remove and clear the vegetation
label | 7785655b-5e92-5330-9686-ff00cd20ca20 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.3 - Slope & Toe Subgrade Inspection
label | d08e5bfe-5dea-5aca-8910-93fc242b1b33 |  | note | ACTION (Hold, Monitor, Witness) - H
label | df0d37aa-ee3a-50fe-9deb-098c4d0f9217 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
label | 03fe6d4d-bbb5-59b5-8bec-7306ca88c7eb |  | note | Frequency - Cut slope and toe of Revetment
label | 772133f0-2457-592f-93c4-97ba54b87058 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 44a17048-c113-53bd-9656-71b99ab053e4 |  | note | Conformance Criteria - Subgrade Approval Check sheet, Bench slope and excavate toe key of the revetment key to the design formation level. Toe key subgrade to be a minimum ultimate bearing capacity of 300kpa and requires GHD Engineer to visual check inspection & approve
label | 9f0bca76-fde6-59e8-830c-f20c44fcd2a3 |  | note | Records - Subgrade Approval Check sheet (CS-4100), GHD COR
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.4 - Ground Improvements
label | dcd128d3-27d5-52fa-bf10-0c086a5fa719 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b510ba47-ce38-55ef-ba0f-53c2d453e26d |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G002
label | 489eae8e-9d6a-5159-843c-1d811164837e |  | note | Frequency - During Construction
label | dcec5e25-7688-5fa6-ad46-4095e2165322 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 50c6375f-7751-512a-beaa-514bb23ce757 |  | note | Conformance Criteria - Any additional undercuts in U/S areas to be approved by GHD engineer
label | 493e0484-0027-5f25-9a69-517af90e05d4 |  | note | Records - Photo's, GHD COR
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Form and cut fill batter in benches
label | 1fd42dab-3b25-5984-911b-9b22fb96c049 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f8dedd4b-b6f3-55fc-a123-b0c81686943c |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
label | 35019eb7-6381-516e-b1bc-69464304fc41 |  | note | Frequency - During Construction
label | af7fd3e7-40f8-5d13-b811-d991bf0491da |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 061737da-4a8b-52c3-9a25-48b55abcd655 |  | note | Conformance Criteria - The final Bench configuration will be considered and agreed on site with the Engineer.
label | ae9e06f1-ea3e-5230-ad5f-025237e56e2d |  | note | Records - Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Bidim A64 Geotextile installation on the cut surface/faces
label | 6355133a-0331-54d8-9b4c-54d9f74a6425 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7561c5ad-1268-5d2a-88ef-8ac59c95945c |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-G003
label | 0bb3ff79-6bf9-51de-9b79-44843e607513 |  | note | Frequency - During Construction
label | ce53a0d2-adbb-5c2c-8efd-4d87d964ed1b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 2f6d1170-36e5-5bd2-9230-c753351aa623 |  | note | Conformance Criteria - Excavation undercut to be underlain and pinned with Bidim A64 or similar approved before placing rock and be laid/overlapped as per manufacturers recommendations
label | ab428bd4-ee94-50fa-867e-ce49b565c2a3 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.7 - Rock Armour (700 to 1500dia) placed on the toe of the slope
label | 02fa882c-e922-58c2-b8c2-8e4289ac6011 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 664b7ba0-96f2-54a9-a798-007624483cc1 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
label | a63c98a2-1cf2-524f-97ca-7444c4d3b7ca |  | note | Frequency - During Construction
label | 926578ac-fb23-5fba-be02-119cb7539fc6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b550c8ce-1c67-5713-adff-166a92763426 |  | note | Conformance Criteria - 2t rock class 700 to 1500mm to be placed in toe and on benches to form revetment. Rock to be placed individually not dumped. Slope of the top face of each rock back towards the rockery/ revetment at an inclination of 5%. Any voids larger than 300mm shall be clinched with smaller rock and or infilled with granular aggregate (smaller rock).
label | 123320b3-75e6-5a12-b8a9-1bd3fa3cc781 |  | note | Records - Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Rock placement
label | 769f1152-a665-5412-83ea-e460a594e730 |  | note | ACTION (Hold, Monitor, Witness) - H
label | faa5bae1-f2fd-597c-a352-4912f4dbd10d |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12617302-01-G002
label | b597dd44-b841-5108-877d-1e1383236347 |  | note | Frequency - During Construction
label | 7da0ef31-bd62-5e2d-835f-784bd1828251 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 9a8e367b-574d-5879-a3bf-ee5a6604961d |  | note | Conformance Criteria - Engineer confirmation during inspection and monitoring that the rock placement should be well placed block shaped rock,
label | 8564e32f-7ed8-581a-b0c8-543d4ae197a5 |  | note | Records - GHD COR report, Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.8 - Verge
label | 4a676475-cf11-5695-aece-4984689bce10 |  | note | ACTION (Hold, Monitor, Witness) - M
label | bcbf21bf-97e1-53cc-a642-c72d23c89de4 |  | note | Specification/Drawings Reference - Buttress typical details type A and F3001B-DS-GT-RP-0001
label | 13e65308-7403-5ba0-9c66-47682b3c74db |  | note | Frequency - During Construction
label | 8e5e64a1-c594-50f9-90ce-01bed6621750 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 5db463ef-9a24-59b8-9ebf-37778d58cd9b |  | note | Conformance Criteria - Verge reinstatement to match existing
label | 8f3d20e2-be5a-54f6-8f81-6e5e7ffbc63b |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.9 - Replace existing culvert with new 525 diameter concrete culvert
label | 3866932f-6448-5c19-80b6-5146189d3ceb |  | note | ACTION (Hold, Monitor, Witness) - H
label | 065a1bdd-e118-51c5-86fe-9d8174023c95 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C002
label | ef47ee3f-f3b5-51fe-90f7-7298fea8d385 |  | note | Frequency - As works progress in agreement with the GHD engineer
label | 3297b933-3e97-5167-bfe1-d62e536025e4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 6236109d-eb93-5132-acdb-8767a002b6cd |  | note | Conformance Criteria - Exact location and alignment of the culvert as agreed on site with the engineer. Inlet and outlet areas to be shaped to be agreed on site with the engineer
label | 4911f833-409f-5569-b4ab-00cf3615eb7e |  | note | Records - Drainage Line Record (CS-4025), Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.10 - Foundation compliance (Culvert)
label | 04878e4d-bb44-5540-b862-2498613c549b |  | note | ACTION (Hold, Monitor, Witness) - H
label | b0f8a0a6-9113-512f-a435-1999711d75e3 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C004
label | 2f576e37-fc81-54d5-9560-dd60a80e1b3c |  | note | Frequency - During Construction
label | ca40dc0b-6c16-54e5-9eba-d60436b0e339 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala testing
label | 7e314018-bfbd-57b5-afb2-a861f93d0214 |  | note | Conformance Criteria - Bearing pressure >50 kPa (>= 2 Blows / 100mm Scala to >= 1m depth), to check if undercut is required
label | 1516f1a4-2def-506a-b9e4-c45153f10521 |  | note | Records - 1M Scala check sheet (CS-4000), Scala test results
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.11 -
label | 565732b9-71c3-54c4-b395-8fcb5ef4152d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 26c896ac-6f37-54e4-b8e7-f26b55c094c2 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C005
label | 9423a2d3-64eb-5218-8ac1-a902b2fd82aa |  | note | Frequency - During Construction
label | c03e6ff1-1853-55b4-9d69-889f8939aa54 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 23635b0c-c51f-56be-b470-69cdf711de8f |  | note | Conformance Criteria - GHD to inspect and approve formation level at outlet of Culvert
label | f7390a16-0082-58b3-bf24-8c08db2b6f48 |  | note | Records - GHD COR
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.12 - Trenching and Excavation (Culvert)
label | 31c7da60-d954-55bb-8e4a-fa2afe552bf7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4ba0c09f-f95a-5f2c-aaaf-a61e12084b08 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C006
label | a2ab2ada-2ea1-5aa6-a2a3-ed45ecac0b60 |  | note | Frequency - During Construction
label | 59783e2e-252e-5e7e-8989-9854010a164c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 80af389b-7b02-546d-9085-c74107ad9539 |  | note | Conformance Criteria - Ensure trench width is sufficient to provide enough space on either side of the pipe
label | 40d6f88f-5a18-5bcb-918f-38a749b157b4 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 2.13 -
label | 6a81172f-afb7-5fbb-9339-b292788c33b7 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 4c5defe2-050e-514b-b837-a8797e8ed6e0 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C007
label | 6d082053-4ecc-5830-8558-47cf97f0c33b |  | note | Frequency - During Construction
label | 118bf4ff-08ce-5149-8fbb-5fb347467875 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 913bf01b-9bec-5fa3-8b89-72f92024da70 |  | note | Conformance Criteria - Inspect trench profile and ensure it is correct to lines and levels as per design
label | 69fd984e-170d-5333-8001-8bb2437167e4 |  | note | Records - Survey As-Builts
checkpoint-status |  |  | checkpoint | Inlet and outlet shaping
label | 75e862d8-f86b-5748-95b8-8b4c2fe115c2 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 3ccb17e8-f0f7-581b-9851-26767b10b621 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | bdff2912-c1e4-5aea-a97f-44b525ab37f8 |  | note | Frequency - During Construction
label | e16da3a0-f309-5eeb-b9db-b9a5717feea7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 4ac8f3b2-47e5-5dc9-8eab-8a2514d6cfef |  | note | Conformance Criteria - Inlet and outlet areas to be shaped in consultation and to be agreed on site with the Engineer.
label | 8332e25f-68e4-54e2-b86a-43d4ac0af2cf |  | note | Records - GHD COR
checkpoint-status |  |  | checkpoint | 2.14 - Bulk Fill on drainage trench and final bench
label | bebf1f2e-f48b-5c06-9091-0fcdb019f6d0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8a70afe9-0ec0-56a7-b34e-25a305690569 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | ee677248-6cc3-5ce6-98e9-46130cd7b089 |  | note | Frequency - During Construction
label | 25c816e8-4e7c-59e0-ab97-3a3da5a352b5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | 6f97e408-3297-53c3-9124-1f20b8388920 |  | note | Conformance Criteria - Bulk Fill Earthworks Record, Place AP65 in 150mm deep layers target dry density at optimum water content of at least 95% should be achieved in accordance with NZS 4402:1986, Test 4.1.3
label | 162fc259-07cb-5eec-ae83-de8effee4b5d |  | note | Records - Bulk Fill Earthworks Record (CS-4020), Test reports
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.15 - Wingwall for Culvert Inlet and Concrete Pre-cast Manhole
label | f18dbfd0-2fe8-59bc-84bd-1a18f49d9883 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5babf932-00d0-5a0e-9df0-0f88f8eafdc7 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C002
label | 6e3cbf8c-b8e3-5c69-98fe-67c9fea63c68 |  | note | Frequency - During Construction
label | 8cd4fdec-8cca-5392-9a72-d3d6157e4fcb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | b996cf09-5d7a-59b3-a473-8d977c3d0b29 |  | note | Conformance Criteria - Install Hynds mountable wingwall or similar approved pointed towards approaching traffic tie in ground profile smoothly to match wingwall profile and to connect into 1050mm concrete pre-cast manhole with concrete lid. New culvert inlet pipe to have minimum 100mm drop from wingwall inverts.
label | 6ef4b340-6b31-50bd-ad52-94822a65d53b |  | note | Records - GHD COR, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.16 - Culvert installation - new RCRRJ 525mm dia. Pipe
label | f1830254-6796-5ebe-a79f-80972762eca4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 35dab34b-45f5-52d1-a209-37e63dc3263f |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | 4a7343bf-262f-595b-b0cc-cc0a245eb554 |  | note | Frequency - During Construction
label | a57b4753-f6de-5b70-94c6-a689a2502493 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | d6344577-b3ef-5820-b67f-eea4c78ee39b |  | note | Conformance Criteria - Installed in accordance with typical detail and manufacturers recommendations. Culvert construction and bedding to be as per NZTA F3 Specification. Consider using excavated river run as fill compacted to achieve 95% MDD
label | b515d3bd-56e7-5cc0-be9a-a3a6c8d8ed89 |  | note | Records - GHD COR, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.17 - Apron for Scour Protection at Culvert Outlet
label | ef226170-0e3b-5b4a-bc68-5252b5eb495c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 806c8a57-6da7-53cc-b743-17104f8ba6a3 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-C003
label | 1d8be51c-6a1f-5c26-9a97-4dedf26689ac |  | note | Frequency - During Construction
label | a2ea8d18-1d6c-5fd4-8958-401af6bc6011 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 4cabc19d-6578-5427-aba2-27f04f6c8e36 |  | note | Conformance Criteria - Construct 2.1m long X 1.5m wide X 0.5m deep Rip-Rap (300mm-500mm dia.) apron for Scour protection at culvert outlet. Install Filter Fabric A64 or equivalent under rock Rip-Rap.
label | e8194478-ff3a-5641-9d0d-eb53a5591c76 |  | note | Records - GHD COR, Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.18 - Fence installation
label | 052db378-6a25-5895-9a24-830829aa65a9 |  | note | ACTION (Hold, Monitor, Witness) - M
label | ed102309-38e5-5c9c-8c8b-4edc9015ccb2 |  | note | Specification/Drawings Reference - Buttress typical details C (Modified) and D1603B-DS-RP-GT-0001
label | d3a41696-9b2e-586d-be7e-b234e0cc08c7 |  | note | Frequency - During Construction
label | f5c8a831-75f0-534f-aedc-087a5dd92a3a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | cd78cdbe-c4d0-5187-88d7-d341ca19fe5c |  | note | Conformance Criteria - Fence line to be reinstated shall be "like for like" and positioned along similar alignment to the existing fence line
label | 727a3678-b543-5865-bde6-cacd1e4fcc9d |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 2.19 - Grass Seeding
label | 835f8f2d-3445-5e05-890f-b6161d70c04f |  | note | ACTION (Hold, Monitor, Witness) - M
label | 170b1910-aec9-5be8-8931-de1f3c504881 |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
label | cd8f635e-1870-57ec-8c0c-e9b3977ec3ef |  | note | Frequency - During Construction
label | ebb22050-0c2e-59cd-837e-7d0e6b0e3362 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | f545c450-67af-503b-9fb0-d4b17394f3d3 |  | note | Conformance Criteria - All exposed earth to be grass seeded
label | f787e933-3ec9-5078-abea-2c04cb67cc96 |  | note | Records - Photos
checkpoint-group |  |  | section | Section 3: CULVERT PAVEMENT INSPECTIONS
checkpoint-status |  |  | checkpoint | 3.1 - Saw cut existing pavement
label | e3f05dc5-9946-5dad-8455-4038aeafb1c7 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3b8e7e63-141e-5189-83db-9bd59c51e233 |  | note | Specification/Drawings Reference -
label | 6f49d878-25d7-5783-87ab-0f5299fc30bb |  | note | Frequency - Prior to pavement construction
label | 42f703e6-cf0a-525b-98c8-f0b32dc668d3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | a6615936-83fd-508f-8dae-b90f85d742ef |  | note | Conformance Criteria - Smooth and straight saw cut
label | 073956dd-9356-5b6e-96f8-27729dee1b1b |  | note | Records - Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Subgrade construction
label | 820a7423-0164-5d16-8301-a6804fd2193d |  | note | ACTION (Hold, Monitor, Witness) - W
label | cd4b3709-945e-5709-ab2d-50f9f27bc55a |  | note | Specification/Drawings Reference - TNZ B2
label | dfc28fee-3ab5-5e84-a200-5af5dc099182 |  | note | Frequency - Every 200-300mm
label | 8ee1c7e7-e757-5bde-8c9b-cf1751090340 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing & Clegg Hammer testing
label | de51802b-0ab3-54ce-a220-aa5f30e13cf5 |  | note | Conformance Criteria - Subgrade shall be AP65 compacted to average 95% MDD with nothing less than 92%, CIV>=25
label | dc1cf74b-155c-5c8b-ba26-8df6d31cbd5e |  | note | Records - Subgrade Approval Check sheet, Clegg Record Test Sheet, Test (CS-4100) reports
checkpoint-status |  |  | checkpoint | 3.4 - Sub-base construction
label | 881b7681-1792-597c-b2ee-cc10bf58f22a |  | note | ACTION (Hold, Monitor, Witness) - W
label | fafcdd8c-78af-5748-a0aa-f1a0f701ddfd |  | note | Specification/Drawings Reference - TNZ B2
label | 488b074e-bca0-52c3-991a-e550d62e8cc8 |  | note | Frequency - Every lift
label | aba9bd0e-281c-5202-84e2-9931f0e91506 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing & Clegg Hammer testing
label | 50e5cee3-28d4-5b53-833c-ce6134b96855 |  | note | Conformance Criteria - 200mm thick AP65 sub-base compacted to Average 95% of MDD with nothing less than 92% CIV>=25
label | 44970d8f-5ce5-5c76-9ec2-2a65adc365b9 |  | note | Records - Clegg record test sheet, Photos, Test reports
checkpoint-status |  |  | checkpoint | 3.5 - Sub-base construction
label | 1c99e405-a6ea-5443-99f4-2312be9fe2ce |  | note | ACTION (Hold, Monitor, Witness) - H
label | d1c30ae4-78e7-56bf-a68a-00b329b9d5d7 |  | note | Specification/Drawings Reference - TNZ B2
label | d1274894-7207-5f7a-8c5c-3a548b740ca2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | e04b068b-9c7a-5df3-b01e-2341f69f7c01 |  | note | Conformance Criteria - Tolerance -25mm, +5mm, Engineer to confirm the FL is within tolerance prior to further construction
label | b09345e5-4822-584a-bcbe-bd443ecad482 |  | note | Records - Survey as builts
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Basecourse construction
label | 1fa943b2-dc58-5ad1-a1e3-8acd1e3416b3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7f5ba2de-27b8-5ff8-b26c-9a8ea18ffd22 |  | note | Specification/Drawings Reference - TNZ B2
label | 1ff1d399-7fb1-5e22-9842-a6a1e79e68bd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM testing
label | 3391a213-947d-579d-ad67-827b4c3c0a06 |  | note | Conformance Criteria - 150mm thick cement stabilised basecourse (AP40) with 2% cement compacted to a minimum dry density of 98%
label | ed08f4fd-5016-5d5e-811e-1034aa10edd4 |  | note | ○ Average 98% of MDD with nothing less than 95%
label | f14999f0-e855-5cc4-acf3-d03f1d9a1999 |  | note | Records - Test reports, Photo's
checkpoint-status |  |  | checkpoint | 3.7 - Basecourse Cement application rate
label | 2cece770-a6dc-5cfc-a509-1692de721552 |  | note | ACTION (Hold, Monitor, Witness) - M
label | a54ea526-1f1f-57f1-96dd-2bc087e74982 |  | note | Specification/Drawings Reference - TNZ B/5
label | 7eec204e-a31a-5fd5-9db8-7efe2e78c093 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 75d29dee-2a0f-5ad4-8884-da7924c6904c |  | note | Conformance Criteria - 2% cement stabilisation at 150mm deep basecourse
label | d48a90f3-bb6a-5d03-82f3-4233b34bf78d |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 3.8 - Basecourse construction
label | 75860352-26d5-555b-84e3-d754f26a43e3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ee24cac9-af32-5734-a685-38521b071ec6 |  | note | Specification/Drawings Reference - TNZ B2
label | 527e7ba9-b37a-5346-a03e-383c7dd95cc7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 1552abd5-0913-5bdb-8c7d-8dfd75663cdf |  | note | Conformance Criteria - Tolerance -5mm, +15mm, Engineer to confirm the FL is within tolerance prior to further construction
label | 809e53d3-2406-5416-9d8d-6953bc18bb86 |  | note | Records - Survey as builts
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.9 - Basecourse construction
label | 904c9fff-f20c-59e3-8a19-74fe8a8e34bd |  | note | ACTION (Hold, Monitor, Witness) - W
label | d3c7a6c2-29b0-59c1-a308-5926ad0f40ff |  | note | Specification/Drawings Reference - TNZ B2
label | bce3d906-ccc0-5aff-9ed4-28de8a2cc3c4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Clegg Hammer testing
label | b455ee13-2b61-5c75-ad71-2e27b58e439d |  | note | Conformance Criteria - CIV>=25
label | 66445809-7b48-57cc-a8d8-544d8caeb469 |  | note | Records - Test reports, Photo's
checkpoint-status |  |  | checkpoint | 3.1 - Basecourse construction
label | 593bc92f-2a37-5135-beac-6554c2e15a63 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 80765426-c388-5561-a7b0-3a138f17a4f0 |  | note | Specification/Drawings Reference - TNZ B2
label | 8767bef9-a043-53f5-aae6-f90bf4bc64bb |  | note | Frequency - Before sealing
label | a448771b-0eeb-511b-a1cc-34fe900b4307 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | 2d5b19ef-d7e9-5f34-9f50-f60ed0d24ba8 |  | note | Conformance Criteria - Mosaic surface
label | e4d65fd4-dcb1-55e5-887b-ae934b5f9c6d |  | note | Records - Photo's, Pre-seal checksheet (CS-4060)
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.11 - Applying Bitumen
label | 9cb0f1d4-2a11-5049-b031-5ec39c96a857 |  | note | ACTION (Hold, Monitor, Witness) - W
label | db9ba2a9-ef25-5368-acd2-bae6715eab06 |  | note | Specification/Drawings Reference - NZTA M/6
label | fa2b8412-280f-5c1c-823f-deefc169fe0a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | d2407a53-8761-5fb1-a9b2-2ab2448fef58 |  | note | Conformance Criteria - Minimum residue rate is 1.8 l/m2. Pre-sealing Check Sheets to check degree of saturation, good mosaic texture, basecourse free of soft spots, pre along kerb and channel compact and flush with lip of channel, straight edge checks, no rain forecast for 48 hours
label | a130ec71-0535-5221-aa54-3d6ce04ce2c5 |  | note | Records - Photo's, Pre-seal checksheet (CS-4060)
checkpoint-status |  |  | checkpoint | 3.12 - Degree of saturation
label | 29a24789-b019-53e2-8ab2-d3a28ab8968f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8e25cd6a-7625-5e6a-b344-396d7261cdc2 |  | note | Specification/Drawings Reference -
label | 3ceabb78-541d-514e-8fe9-3f95f2b6a114 |  | note | Frequency - Before sealing
label | 047733a5-a0dd-5636-9f07-cfa2835d8aab |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Pre-seal checksheet
label | 5c8c3caa-21eb-5bbf-ab5d-b098c395a178 |  | note | Conformance Criteria - Degree of saturation should not exceed 80%
label | 4799a418-526d-597d-a436-6d59e60ece7a |  | note | Records - Pre-seal checksheet (CS-4060)
checkpoint-status |  |  | checkpoint | 3.13 - Chip seal laying
label | 6a0ba525-2a2c-5c4d-a499-0c0cf754b151 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7e4d681b-7d6e-581b-ae71-4ab99b82f64a |  | note | Specification/Drawings Reference - NZTA M/6
label | 2615a5f3-6b6a-5290-9c74-bffe4efd8383 |  | note | Frequency - During Construction
label | a1e2ae64-2d1a-5806-ab6d-22e610527024 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | c3daa349-edd0-5b44-84f6-3d4c05d2c76c |  | note | Conformance Criteria - grade 3 and 5 chip seal. The seal will be placed and compacted in accordance with NZTA P/17. The seal will be rolled in accordance with NZTA P/3
label | 3759ec59-1751-5642-9ab1-0176646fccd9 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 3.14 - Sweep & Line marking to new chip seal road
label | 619cd07b-1ecf-5508-b27e-c602f073dc1a |  | note | ACTION (Hold, Monitor, Witness) - W
label | f4d601a2-d7d9-5a38-bcc5-d34b264d13d7 |  | note | Specification/Drawings Reference - TNZ P/12:2000
label | 523cc3f2-11f3-50ef-8d14-de030a28f0b0 |  | note | Frequency - During Construction
label | d8c5d4a5-7801-5d9d-8e8c-25a32d9b226e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | ec285ab7-a7bd-5169-968c-4a2608674fcc |  | note | Conformance Criteria - As per TNZ P/12:2000
label | de40ede8-f93b-5622-a119-8acdd1cddf19 |  | note | Records - Photo's
checkpoint-group |  |  | section | Section 4: Post Construction - FINAL INSPECTION & HANDOVER
checkpoint-status |  |  | checkpoint | 4.1 - As-built Survey
label | de3dd19c-1e4c-5d39-a5b3-fd14f52da74e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7913f9b3-7faf-5406-9a6a-2b291a0c3731 |  | note | Specification/Drawings Reference -
label | 0cee0d96-7cff-55f7-b906-0fc739ae20d5 |  | note | Frequency - At completion of Lot
label | 9fbba6e7-6f40-5ccf-b2e2-a0b36afebe9d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | 9a5d4416-3825-5873-8400-1e58cee22b23 |  | note | Conformance Criteria - As-built Survey & Drawing Mark-Ups to be reviewed and accepted by GHD Engineer
label | 1dd0bacf-f0c6-5a8f-a372-5f9e0e3de8b2 |  | note | Records - As-builts, GHD COR
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | Inspection of site following completion of physical works
label | 8a7b5465-536a-519b-afb8-6da74c978a98 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e4a643a6-98ea-53e8-9cc8-92f3cc5b93da |  | note | Specification/Drawings Reference - Hicks Bay SH35 Slip Repair-12533432-Q002
label | 0c8f83a7-2496-5ae8-ab31-cbd763ecdfda |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover/Visual Inspection
label | 6bb50ab6-45b8-5428-b932-06c695e33a3c |  | note | Conformance Criteria - Inspection of site following completion of physical works
label | 01be4d60-72ee-5289-8b70-e03142fdb9e9 |  | note | Records - GHD COR
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Quality Assurance deliverables
label | 24525758-4de0-5f88-bc1a-489b0a4c66ce |  | note | ACTION (Hold, Monitor, Witness) - W
label | 14fe81ed-fbfd-55a8-804c-6b9a8b6bb5dd |  | note | Specification/Drawings Reference - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | c2900dfa-3b65-5a8b-8109-8ea0f2aeebbd |  | note | Frequency - At completion of Lot
label | 55c23ded-4a83-526b-bf5d-5da8ae2bce44 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | a1247148-3da7-5eaf-a792-e9f50b0349c9 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | c1910acf-6226-5f2d-8035-8e4a4d54bf4b |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 4.3 - Completion Sign Off From Fields Below
label | 6a76a45a-b4c4-5845-9c11-3077f384f9dc |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2a333d35-6d53-53fd-8702-c8ba2dc42c48 |  | note | Records - Signatures
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - C1603A - Waikare Gorge Descent - Basecourse Construction | itp |  |  |  | Yes | ITP - C1603A - Waikare Gorge Descent - Basecourse Construction | f2874e3e-d6e4-4b93-9b52-60e0c58a929c
checkpoint-group |  |  | section | Details
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 8a1bf955-012d-56db-96ce-6e95f9578ef0 |  | textbox | CPS Eng.
text | dc9bc617-d02f-5aa2-b92a-595fbe4102af |  | textbox | Site Engineer
text | b7c9aa30-a42d-51c8-b820-41ef4e8a0883 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Sub Base Signed off
label | 2668510f-631d-5368-9c61-69fde62311e3 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f5994546-4acf-54e5-b893-3d79058b2fcd |  | note | Detail - All previous Activities completed & signed off before Placing base course
label | a4d55f60-43f5-5759-a068-80ef7cc7727d |  | note | Frequency - Prior to commencement
label | 99b3a2cf-6cc8-5666-a422-16725d4ed881 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 535c8374-0c83-5556-bd4b-5617e6dedaf5 |  | note | Conformance Criteria - Previous ITP completed
label | eed39c70-777e-5118-b587-ddecd81ab565 |  | note | Records - ITP - Subbase Construction
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | 4f9d36ac-0a5b-55df-9a30-6ddd9665bbcc |  | note | ACTION (Hold, Monitor, Witness) - H
label | 970e644d-a0d2-51a5-a327-ab8ccb79fe4f |  | note | Detail - Cross Fall and levels to tie in with pre-existing carriageway
label | 798a1fc5-ef98-5267-83fc-bd4db4f6a116 |  | note | Frequency - Prior to commencement
label | 59af329b-ba23-5899-add1-626fd6b00025 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | a58b6133-8a39-5327-b07c-60952ed3b3f4 |  | note | Conformance Criteria - Set out and levels agreed with CPS Engineer on site
label | 15df0b4d-c336-566c-90ff-cebea009cb5b |  | note | Records - Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Material Compliance
label | 43b39d8e-c592-530e-94c4-d79582f05b4c |  | note | ACTION (Hold, Monitor, Witness) - M
label | 98dcdad6-863b-5148-9133-f23cd6ad2e9d |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile.
label | ea658786-3ce5-5759-8e14-6d078b3b0a27 |  | note | Frequency - During construction, traceability of all materials delivered to site
label | 64233547-a811-5072-83a1-1579b8453865 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual check, document review
label | 180c1c08-79f4-5126-9562-9fe3bb3cd94e |  | note | Conformance Criteria - Conforms to TNZ M/4 specification
label | 5028fc67-ac0c-5696-b9d3-0f983732f0ff |  | note | Records - Delivery Dockets / Records
checkpoint-status |  |  | checkpoint | 4 - Basecourse Construction
label | b8d0ffed-9f79-5ade-b7db-8a9acae4f700 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 49400f2e-1e8c-5412-a6aa-69d9093cbd93 |  | note | Detail - Basecourse Aggregate
label | 36f7dd26-7718-511b-acbd-b12ec416884e |  | note | Frequency - 1 sample/10,000M3 or 1 per source stockpile.
label | e0267267-2c58-5ee0-9699-2cb8e3c3dd80 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - PSD, Atterberg Limits, MDD, OMC and CBR
label | 64033c3d-b289-55e0-9135-3be2de4dd93c |  | note | Conformance Criteria - Comply with TNZ M/4 specification
label | 20eb7018-d96a-5d88-8712-ec5288f2a6a3 |  | note | Records - Lab test result
checkpoint-status |  |  | checkpoint | 5 - Basecourse Construction
label | a0cf2fb8-f697-56a5-b58b-fc78a80dca7b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 020b629b-0f45-5075-8487-d76ddf3cd549 |  | note | Detail - Degree of Compaction
label | aba17465-446d-57d9-964f-7f4e6bdae2ec |  | note | Frequency - 1 per 1000m2 staggered
label | 64255000-1bcc-597b-8d3b-e835a9416646 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | c181b696-68fe-5270-a8a9-c38c912429e1 |  | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | 381336ca-d351-50dc-87e1-91ee82c840a0 |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Survey checks
label | 81b3e9d2-d4a3-51da-99b3-8c56876d50b4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9510d273-b871-5158-851e-bff06a361d95 |  | note | Detail - Cross fall check. Surface shape check.
label | a06a8942-34d1-55d5-92cb-06c83e963257 |  | note | Frequency - 1 per 20m staggered
label | 9d480a0c-fac6-57c4-8303-e46ce260178e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual check & Measurement
label | 42a7003b-b390-53ad-ac47-11a1e1135014 |  | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | ff9229f0-7da1-5178-8e79-0f09524c0fdb |  | note | Records - Photo's / QA records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Surface finish visual inspection
label | a3d3f94c-93c0-56b8-90dc-78caf0838085 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 11dcd8f1-ec59-55c4-aa7b-4f661bbedcef |  | note | Detail - Surface finish check
label | 9169b6cc-619a-5443-897b-2a62c5d870de |  | note | Frequency - Prior to sealing
label | d5c8edb3-a99b-5234-ad54-845bb2b8446d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | 877a337c-63ff-5c33-8bfe-a48c41105592 |  | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | 93619291-382e-5455-828e-6b3a275b2e78 |  | note | Records - Photo's
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-flat |  |  | checklist | ITP - E1401A - Captain's Culvert Inlet Remediation - Guardrail & Wire Rope Barriers | itp |  |  |  | Yes | ITP - E1401A - Captain's Culvert Inlet Remediation - Guardrail & Wire Rope Barriers | f2a2ecde-fa69-4c4d-ae22-46fb3e016e3f
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 7e67311a-f7a4-56dc-a430-4880f64d5e55 |  | textbox | CPS Eng.
text | fe0201d9-2854-5104-b9b0-0558b48943f3 |  | textbox | Site Engineer
text | 6aa0d848-06d5-5906-aa92-961f16379f1b |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 -
label | fd480884-d911-5456-bb80-b4c9a5d6bbae |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5fc2b66c-9504-592b-8202-2839548e9a9b |  | note | Detail - Design check locations of Poles and check for any clashes with underground services or similar
label | 305b9e25-517d-5726-83c6-b46b3fb5ffbb |  | note | Frequency - Prior to commencement
label | af903e71-99f6-5e0f-9d34-a9f75d57f10f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document review
label | 938d62ef-dcde-5dcd-81f9-37a43e43c87c |  | note | Conformance Criteria - National Standard for Traffic Signal
label | 118ad260-5bdd-58c3-9ad1-b1c6e76368fa |  | note | Records - OFI or NTD/NTC
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | 80dfe984-7aad-5251-ad78-09ed4d8e6e00 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0fb77631-0e73-5809-9666-6f4f0c0f3e6c |  | note | Detail - Surveyor to mark 20M Chainages on the Kerbs from which Start and End Point of Barriers will be referred.
label | b242d87a-5cbb-5563-8839-2c772098fa43 |  | note | Frequency - Prior to commencement
label | 5089a9a2-488a-559e-bf42-c415298bc264 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 201311ab-a705-5795-b5bf-1517bffbfb9f |  | note | Conformance Criteria - Consistency with latest revision of Approved Construction Drawing.
label | 0edf1ffc-cda0-59eb-8c1a-94964f4c949a |  | note | Records - Approved Construction Drawing.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Material Compliance
label | 881f70ad-47c3-506b-8dcd-8f637996a9ad |  | note | ACTION (Hold, Monitor, Witness) - H
label | fd3ad304-2ae5-5dce-81c2-03204bc5e63e |  | note | Detail - All roadside barriers shall comply with TNZ M/23:2009 for NCHRP Report 350 Test Level 4
label | f07137a9-744b-5fc7-9665-f1b53d8df1d4 |  | note | Frequency - Prior to commencement
label | 84d69baf-5f87-5121-b551-9b4feef9739a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection/ Document review
label | 54f56f49-6363-54eb-baea-0914a729c071 |  | note | Conformance Criteria - TNZ M/23:2009
label | 73f1450e-1f93-5421-8803-fd84fbdea634 |  | note | Records - Manufacturing certificates and delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4 -
label | 620ed9bc-bb12-5026-b516-c89dba658d4f |  | note | ACTION (Hold, Monitor, Witness) - H
label | b20ff2a8-e908-5fd0-a044-be42e575e070 |  | note | Detail - All materials to be sourced from registered suppliers
label | 3fd2cfd0-88de-551f-bfe5-2b3bbd099980 |  | note | Frequency - Prior to commencement
label | dc9849ec-806c-5af2-8770-7fa621658f80 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | bedc839f-0031-529c-981c-91d2551d28a0 |  | note | Conformance Criteria - Registered suppliers
label | 6894c0a7-dc89-501c-b85d-4149e5e4b8f1 |  | note | Records - Materials register
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 -
label | 7e780dfb-055a-50a9-97aa-e938da42a94b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 05e0ba92-2fea-52d6-baf4-03612a021803 |  | note | Detail - Proposed galvanising repair methodology to be approved by Engineer
label | 922f6925-941c-5181-a1a3-e0d0a5e614ce |  | note | Frequency - Prior to commencement
label | c57123d7-99a5-5a39-9aae-6030cd0c56fe |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 1f336ca6-0966-505d-ada0-cacae8251b79 |  | note | Conformance Criteria - Best practice
label | 7fbeb7b7-b52c-5aa3-84d8-c5eaf0409d3f |  | note | Records - Approved / Signature
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6 - Guardrail Installation
label | cb5f2e74-1213-5ef4-9f6a-e52f2754d4fc |  | note | ACTION (Hold, Monitor, Witness) - H
label | 49f8c806-ee18-5e95-aa88-52b34e0cf209 |  | note | Detail - Certified Competent Installer. All roadside barrier work shall be undertaken by certified installers
label | b08eddb3-c307-59e9-9edd-e18c04b8d045 |  | note | Frequency - On Procurement of installer
label | 16e346d7-f373-5646-bac0-8aa11e83add3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Written confirmation
label | de40ea62-f0a1-5dc1-86ae-f74888781545 |  | note | Conformance Criteria - ASHTAS operative and installer course
label | 273fb345-2de7-59cf-a67f-008abeae1e29 |  | note | Records - Attendance Certificate
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 -
label | 2186d151-9c42-5db6-ae17-6154f3912a38 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b7d0d6b8-25ce-505b-aeca-10ff3d36fba9 |  | note | Detail - Nu-Guard 31 shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | afce9aae-c89a-5766-baa6-8472cde71ad5 |  | note | Frequency - During installation and on completion
label | ea025653-a263-5613-a9c7-6674e06497c4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | 09d9d9ba-687f-54ab-af8e-20acca29c691 |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | 4b09ae37-e6ef-5084-9c42-e8f904dda42f |  | note | Records - CS-4117 Guardrail Installation Checksheet
checkpoint-status |  |  | checkpoint | 8 -
label | 65d15aa5-6688-51e3-bfc6-d8be45aadaf4 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0d419b3b-c2fe-5405-8699-a2cb0d107c9a |  | note | Detail - W-Beam Guardrail on ductile steel shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications.
label | 8c1b78f6-8e71-54bc-94b7-dd2706f49ae4 |  | note | Frequency - During installation and on completion
label | 3daaedbf-b5d4-5110-ae3f-81bd5bb7e6dc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | 2ff353b9-86aa-52ea-aa86-b0883e077a8b |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
label | 884a50fa-c003-5cd1-bf2d-5356c594ee27 |  | note | Records - Installation Checklist
checkpoint-status |  |  | checkpoint | 9 -
label | a411f0f0-26b4-58b3-8e36-e38953c96d89 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a83596ec-2d9b-593e-9354-71b09d9fc5a6 |  | note | Detail - Leading & Trailing End Terminal shall be installed at locations shown on Drawings to the specified Off-set and in accordance to Installation Manual and Specifications
label | 6469b66f-def1-531f-bd76-1118454f736d |  | note | Frequency - During installation and on completion
label | 2422f282-3fac-5e19-999d-4d8277ebef11 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection, measurement
label | 1dc493b1-c6c1-5577-8941-270c9f082865 |  | note | Conformance Criteria - Each section inspected to comply with specifications and CSP Pacific barrier field manual V6: April 2010
checkpoint-status |  |  | checkpoint | 10 - Fit for purpose Inspection
label | 692ed231-6daf-5432-b987-e403e18a6d23 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4adac4aa-3b9d-57a2-b321-df6d5ad9c295 |  | note | Detail - Barrier to undergo fit for purpose inspection by competent person
label | 301e402a-5b2f-5ba4-ac26-061692e988f0 |  | note | Frequency - Prior to trafficking,
label | 387cdafe-7344-5f76-a986-362b09e35ea4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 1d35634a-5140-5240-83bc-09f152424411 |  | note | Conformance Criteria - Pass inspection
label | b9c9f1c0-116f-5a6e-bbcc-7e8cf40298d6 |  | note | Records - Confirmation from inspector
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 11 - Lot Number QA File
label | 1303552c-89d8-50f1-83fb-ed8d78e92ce6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7e2bbe81-d910-52aa-a934-5e401e32379c |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | b5884c68-96f4-5ca6-bfc2-7e73dd4df044 |  | note | Frequency - At completion of Lot
label | 67d12a49-1915-5fdf-bb14-a80f6273059a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 6867b06c-bd18-5d4d-bcb7-1fcf763134d4 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 0170d500-fbda-5ab3-9b4e-5f71338ddc7d |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 12 - As-builts
label | 395d48e3-5558-56cb-b728-6aa53ffaac45 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | a25a7940-1ef0-5e8c-a86e-28569095421e |  | note | Frequency - At the completion of the Lot of work
label | 908b537d-134b-5486-9a9e-627681caa28f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | d9ae161c-1343-5637-9bc8-401b56aabe67 |  | note | Records - As-built Drawing
checklist-sectioned |  |  | checklist | ITP - E3001A - SH05 SIP Site 1 - Pavement Construction | itp |  |  |  | Yes | ITP - E3001A - SH05 SIP Site 1 - Pavement Construction | f3cbf27c-bd31-431e-a580-9c262f9e9028
checkpoint-group |  |  | section | Survey Setout
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 95e36960-0f44-59e7-b8b6-14e42d889e8d |  | textbox | CPS Eng.
text | 2824c54f-ef10-5f71-bd34-8cca164080cf |  | textbox | Site Engineer
text | ea45a22f-879f-515e-a84c-e2297a7c4fdc |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | ea0b8d2d-950a-5ce6-a9de-656123ba6805 |  | note | ACTION (Hold, Monitor, Witness) - M
label | db1b826a-a5b2-559d-af10-2d91da596d9b |  | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
label | d80add25-2fea-52f3-a6a7-854c24d281c6 |  | note | Frequency - Prior to commencement
label | 10872cfd-fbca-527a-947b-c84a86423b95 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 9beaa8d1-fd8b-5c4c-9c3d-20627d72fb01 |  | note | Records - Survey receipt
checkpoint-group |  |  | section | Sub Grade
checkpoint-status |  |  | checkpoint | 2 - Sub Grade Strength
label | df2f0c61-cf0d-5c10-9441-5b7eb838642f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2ae50419-40ac-582e-8690-c2e3ae233ce8 |  | note | Detail - Determine Bearing strength of Sub Grade
label | 82664e5e-0d40-594e-b65e-d26e78a9f386 |  | note | Frequency - After Dig out Every 5m
label | a7f704b6-588a-5686-86fb-72b8183e58ae |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | d8def8d6-5773-5dc9-ae8f-87a8acb30f91 |  | note | Conformance Criteria - Min. 4 blows /100mm
label | 74190072-5015-5b2e-af23-58526321a84b |  | note | Records - QA measurement Sheet (CS-4000) 1m Scala
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Proof Roll of subgrade
label | 030d113b-fab0-5776-978e-5589049a6628 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0f81fdb9-598f-5cd5-9bd6-5f9405be87c6 |  | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
label | 0f6657d7-4fef-5465-8e72-bd1c68283376 |  | note | Frequency - Prior to Sub Base Construction
label | a70220d8-7cf8-5fff-b790-120a4fc0386c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 4a673cc2-41af-580c-9424-eec918d1c17e |  | note | Conformance Criteria - Engineers Acceptance
label | e5ae4f58-2c05-50b7-8a7e-1e7f1f9aaceb |  | note | Records - Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Sub base
checkpoint-status |  |  | checkpoint | 4 - Material Compliance
label | 4241f76b-cc22-5af8-8075-9d4cc8bd7984 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0bcb0e91-e79f-5972-9aed-aa533e1708f5 |  | note | Detail - Aggregate material compliance for Subbase stockpiles
label | d205c2ca-9026-5e24-969b-9756df572af0 |  | note | Frequency - Prior to commencement
label | c83795fd-d266-51ce-9ca5-a3bb364ddae5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 92139b96-71eb-517a-a76c-36f71b3dc676 |  | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC.
label | 79405a2c-50a2-5925-bde1-0fe5dec906df |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
checkpoint-status |  |  | checkpoint | 5 - Material Compliance
label | d37f8c02-ad22-5fc5-9c72-4b232f293dd8 |  | note | ACTION (Hold, Monitor, Witness) - M
label | d7419b9a-1d45-5ef6-a79a-4c3188c4eb71 |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | 4f10568a-01cf-56a0-8a63-4e94acefda90 |  | note | Frequency - During construction
label | 3db631f4-8dbd-52ab-ac09-73cd7e9cfaf6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | 49f3534a-47dc-569d-82f9-a1171e356d20 |  | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification.
label | 5ac2b9b1-ef5e-564d-9c72-5babcc96c413 |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 6 - Saw cutting
label | 2883083b-fa90-5b46-b6bd-764206182518 |  | note | ACTION (Hold, Monitor, Witness) - H
label | cf9695a7-a20c-5f54-960c-3f6ff5be3264 |  | note | Detail - proposed Sawcut line to be inspected by the engineer
label | 3573352e-8d7e-58d3-b4dc-054d5464bae3 |  | note | Frequency - During construction
label | a7a21952-55c5-583f-a379-08533d422eb9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 205ccacb-90b8-55d2-bf39-5a7f58366ff9 |  | note | Conformance Criteria - project spec 6.6
label | 3ee2ff66-5770-5906-8720-ffa47beb112d |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 7 - Sub Base Construction
label | b3f9f7fe-4a4f-5c2d-a4ac-a50e128bd31b |  | note | ACTION (Hold, Monitor, Witness) - M
label | 6469eb0b-5db6-5301-9fe9-cf0143dc0474 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 6fc9a07b-42e1-5fd3-b706-384098d570ed |  | note | Frequency - During construction
label | 86b40359-2eb6-5836-93f1-85ee80aded7a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 368712ef-5c26-5dbd-aa4f-4538e7051ba9 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 8 - Sub Base Construction
label | 99b323e2-e6b7-5a57-ad2a-3a067fa3117a |  | note | ACTION (Hold, Monitor, Witness) - M
label | 903785f2-fd6e-5d24-becd-a6f24a2a1fe4 |  | note | Detail - Carry out a Level Check on the trimmed Sub base
label | 65480e54-d199-59a1-969c-0c15a0d16b23 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | 45ceb81f-ce6b-5f24-b941-e19ce7111a6f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | e48472b8-433b-5d76-a432-cceea9190a18 |  | note | Conformance Criteria - Tolerance = -5mm/+15mm
label | 64f1daed-2319-558c-9f93-a05f7fa26a72 |  | note | Records - QA measurement Sheet
checkpoint-status |  |  | checkpoint | 9 - Sub Base Construction
label | 1b167e96-26d5-58bf-bee2-4cbc35551ec4 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 0272f934-bc18-51f1-9cbb-d7b4869a2ec1 |  | note | Detail - Degree of Compaction
label | 6aef43a9-fdc3-5ed5-bf23-a27bb4dbe060 |  | note | Frequency - 5 per Lot
label | 762ac5d3-da1f-5bd6-b369-44ee1d5b090b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | 31dbc2c2-134c-5d9d-a147-516c08860087 |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | bf76b00a-1463-5512-bb85-7dece0b390da |  | note | Records - Pavement Lab Testing Spreadsheet
checkpoint-status |  |  | checkpoint | 10 - Sub Base Construction
label | faa702b1-48ba-512d-a4be-27c4a68f1b41 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 552567c8-eb97-5bec-8567-7fd43448bff8 |  | note | Detail - Surface shape check
label | f7e571f6-b097-5d4c-b297-08b7657f23b9 |  | note | Frequency - Prior to base course Construction
label | 249efe03-36d6-5056-852f-b101df813e6c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | e8e663c4-b23e-550e-a9eb-42cd4b77519e |  | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | 3645976b-26af-5925-acd3-9dc78ed0bde6 |  | note | Records - QA measurement Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Base Course Construction
checkpoint-status |  |  | checkpoint | 11 - Material Compliance
label | 51ed6460-b614-5fc4-ae72-fd1c91c45786 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ccc22f5f-eefe-56c7-a53e-b617fa659639 |  | note | Detail - Aggregate material compliance for base Course stockpiles
label | a0baa6be-ddbc-5d2e-a2d2-c25d0ac0112d |  | note | Frequency - Prior to commencement
label | 8d22f10a-89c1-5e48-b9f4-2783ade0be7e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | c905c117-690f-5e1e-b8a5-ec3a64908e6a |  | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
label | c49c28a4-e816-5137-9089-b9c441337212 |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 12 - Material Compliance
label | 2901494d-8bf7-5164-9833-315f8ddc0597 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 95d18a78-06fc-58e6-bc89-7b6887e6fa09 |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | e5385767-f309-55ca-a5b2-9035b7651529 |  | note | Frequency - During construction
label | d9230cb4-5fe6-541e-aaf9-bdc38ae7d619 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | b33c412f-006e-59ab-9228-aa9fda5329be |  | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
label | 3e017c69-e9d7-5dba-aecf-5d59918696f5 |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 13 - Base Course Construction
label | 0e41d4a9-61db-54be-b3ca-e5130b2d42e5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8e623039-036a-5446-b4f0-c38a550e0af1 |  | note | Detail - Mat sampling of Basecourse Material
label | 7a5cad43-1c37-5dfe-a0f3-50b973d29598 |  | note | Frequency - 1 mat sample for the job. Pavement CPS Engineer for further instruction
label | 4c9727b4-0a4d-5919-ba7d-8d726e4ceb20 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab testing
label | 795d6b3c-af21-5b88-8a94-c8be1df6a5e2 |  | note | Conformance Criteria - Grading to comply with specification
label | e75e93b0-025e-587a-9ade-5345270f67cd |  | note | Records - Mat sample lab test result
checkpoint-status |  |  | checkpoint | 14 - Base Course Construction
label | 419fa2f5-d4c1-5f03-8f23-6a4d38eb896d |  | note | ACTION (Hold, Monitor, Witness) - M
label | e862d8bc-7bf3-5ea6-9d71-da09fbc221d4 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | efb1530d-4749-5ed7-b518-ae6b308d8bd4 |  | note | Frequency - During construction
label | dcc40f09-31dc-54e4-a501-27a9c97fbf0b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 58d67b24-abca-5d39-8ee2-2db7dbc1a74d |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 15 - Base Course Construction
label | 4e2ba83f-881d-5015-ab5e-0826ebe7e2c9 |  | note | ACTION (Hold, Monitor, Witness) - M
label | a0339c51-d203-5aee-a3e8-235a86764e4a |  | note | Detail - Carry out a Level Check on the trimmed Basecourse
label | 033c1216-895c-5216-9fe6-dbbd42dbf275 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | 77c0ee77-2e7f-5079-933b-38502cf5af6f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | b36434d8-2d26-5cce-af28-9365c5f972b8 |  | note | Conformance Criteria - Tolerance = -5mm/+15mm
label | a8105d8d-d214-5a6f-bce2-a0e2c9bd53f9 |  | note | ○ if constrained (kerb) Tolerance = -5mm/+5mm
label | 72490a64-41b1-5fe2-a80d-b23e4ea7c0ab |  | note | Records - QA measurement Sheet
checkpoint-status |  |  | checkpoint | 16 - Base Course Construction
label | 133f1ced-0b73-56e0-acaa-95bd68a148b7 |  | note | ACTION (Hold, Monitor, Witness) - M
label | a0324919-c357-541f-8b4b-0dcde1d6b6c8 |  | note | Detail - Degree of Compaction
label | 47761358-9fda-5dfb-80c0-38247a58fd86 |  | note | Frequency - 5 per Lot
label | f7e47071-2b75-5024-b5a8-f0e9589297c1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | 7bd08962-e0c2-5c4f-b76c-2abb067ce9c4 |  | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | 204f4119-d10a-53e0-9466-88ad08ed08b0 |  | note | Records - Pavement Lab Testing Spreadsheet
checkpoint-status |  |  | checkpoint | 17 - Base Course Construction
label | 720a2457-3a05-5ed9-acbf-365b71db73fe |  | note | ACTION (Hold, Monitor, Witness) - H
label | ad78bc89-c0e5-5011-82f1-16cb5fb8a690 |  | note | Detail - Surface shape check
label | 771d3a75-7c08-5599-8861-57f22e747a19 |  | note | Frequency - Prior to sealing
label | 8031421c-6869-54e0-a745-c248669cc022 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 20332fec-6ec9-5e44-ba6f-2a2a617c1e99 |  | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | e3a8827b-c72f-5ce0-add0-423c5fce2aef |  | note | Records - QA measurement Sheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 18 - Base Course Construction
label | d7cd3ae6-bc88-5ec7-8bd6-c306dac228ef |  | note | ACTION (Hold, Monitor, Witness) - H
label | c3417ff0-dd5f-502a-b194-b7b4820de217 |  | note | Detail - Surface finish check
label | 60430a24-ced8-5414-b17d-e5da6b5fe783 |  | note | Frequency - Prior to sealing
label | 21a3a31f-f29b-5864-8b27-57aa5981f2a3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | 132e1ac2-0150-5a38-8774-3fe32c683476 |  | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | f42b6529-cd2d-5598-97df-e4e30b0aa722 |  | note | Records - Site photos, Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Sealing
checkpoint-status |  |  | checkpoint | 19 - Seal design
label | f8e2f490-3d34-583a-996f-2a009d08cedf |  | note | ACTION (Hold, Monitor, Witness) - H
label | 23fc39c0-8cc6-5288-8d1c-f0badbb53e83 |  | note | Detail - Seal design to be reviewed prior to sealing
label | cf611b15-186c-5f3d-a9b9-532595616ec3 |  | note | Frequency - Prior to Sealing
label | eb9910c1-c4e2-553c-955a-b005a8023f8b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | a92faff2-0915-5538-ba64-56dcca7971e1 |  | note | Records - Emails/NTE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 20 - Location/Size Confirmation
label | 2f8c3013-d04c-559c-8617-b9164e583aea |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7ed6814d-f28a-5408-a486-1efa62981f19 |  | note | Detail - Mark up extent of Chipseal
label | 6e9de0a7-884f-5dc1-ab9e-0cfabb6c856e |  | note | Frequency - Prior to Sealing
label | b91a9d06-73d4-5897-a799-d28a03ea3289 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
label | c7600a81-b918-5a55-9cf4-2b86ea7ee319 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 21 - Surface Cleanliness
label | 0d8b8d4e-c8c6-590d-890a-e2c7d8bc62f6 |  | note | ACTION (Hold, Monitor, Witness) - W
label | a298b0d0-cafa-531b-b10e-247bb7a62c6f |  | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
label | 2ba37e51-1d9f-5c9a-8610-8e98d593b1aa |  | note | Frequency - Prior to application of binder
label | ef11102a-4906-5963-9d58-73a9e85b5ded |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 5d53cbe8-75eb-5ca7-ab01-02b2ea304af6 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 22 - Binder Application
label | 5da651b3-4cbf-5aeb-9f5b-884423520abe |  | note | ACTION (Hold, Monitor, Witness) - W
label | fdccd612-1d83-53ee-a3c0-e6ddd61718b1 |  | note | Detail - Ensure the Binder application is according to the seal design
label | b565f0cb-9059-5ed8-a21a-35a9108ba5ba |  | note | Frequency - During sealing
label | 25c77802-79be-50cc-8d58-8defc8aa9c73 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 1d0d9cbb-ce30-5eac-ae62-28feaa7de358 |  | note | Conformance Criteria - According to seal design
label | 6623bccc-1ced-5bd0-9f3c-481627e1ea6c |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 23 - Chip Application
label | 9e031834-5be7-5f52-8172-d8126b8198b8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 00fcd43e-335b-5866-90a2-78a82d61169a |  | note | Detail - Ensure the Chip application is according to the seal design
label | cab4487d-ae8e-5123-a7d0-ba2361e9a6d2 |  | note | Frequency - During sealing
label | 457f2b2c-5e74-5c8d-a805-5adc657fecd4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 54f94261-669b-5948-b655-dc5ff332cba6 |  | note | Conformance Criteria - According to seal design
label | 398ab96a-471c-51b8-b2b9-27aaecc1e26a |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 24 - Compaction
label | 162eb295-3e9a-53d0-926c-40932b143efc |  | note | ACTION (Hold, Monitor, Witness) - W
label | aa044b9c-95b5-59fc-b1fe-90c65a7ee67d |  | note | Detail - At completion of rolling
label | 310e7cdf-75e3-5f66-a3c8-4da912498209 |  | note | Frequency - During sealing
label | 1c72d500-716e-5aa5-95e0-8a4fd45e3134 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | f898307a-01bb-50a3-a9fb-3006f9eefb6e |  | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | 446095f0-848e-5451-abeb-58ce5a408b11 |  | note | Records - Photos, QA measurement Sheet
checkpoint-status |  |  | checkpoint | 25 - Photos, QA measurement Sheet
label | b3a077b7-48e3-5115-82df-9703fec2bab8 |  | note | ACTION (Hold, Monitor, Witness) - M
label | e567a069-cef7-5ed3-a7b3-eda3f2a76f92 |  | note | Detail - Removal of excess chip
label | a3f5b202-b5d1-57ee-94f2-28bf3a7d2ade |  | note | Frequency - Within 48 Hours of Sealing
label | 7c6f22c3-cd4e-58c7-851c-f9daa255b3b1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 0c5c5010-3afe-5b68-86c8-091ca53f5e6a |  | note | Conformance Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | b6422c6c-30c3-5b7e-a1aa-540876378fbc |  | note | Records - Photos, Site logs
checkpoint-status |  |  | checkpoint | 26 - Compaction
label | 6bfd5eda-4a6b-52de-9626-3d3797c56b88 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8848c619-713d-560f-8d94-bf1a4b52b87e |  | note | Detail - Surface finish check
label | 109a8e7b-d582-561a-ba1d-f6bdbecf3368 |  | note | Frequency - After sealing
label | 060e7d25-a06e-54d2-a4f4-1e4b0f7f513e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | f5dbcf16-5396-5770-a4bb-f6efae58f91b |  | note | Conformance Criteria - Engineers Acceptance
label | e1cc6816-e88a-5d11-b201-ee32c273bda7 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Road Marking
checkpoint-status |  |  | checkpoint | 27 - Road Marking
label | d7c97dd9-f0e3-5af7-8a64-371269240feb |  | note | ACTION (Hold, Monitor, Witness) - H
label | 00e3103f-18ac-5122-b2c1-0e782f743505 |  | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
label | ed0a2251-2c5e-5cb7-b607-5147bbd3a259 |  | note | Frequency - Prior to the final line marking
label | 389d49a6-506b-597f-baa2-9fab0b3f2784 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | e188f3a3-aacb-5eb0-8834-218d6f5ea504 |  | note | Conformance Criteria - Engineers Acceptance
label | d48c5991-3d2f-509f-83b6-1ae74ac7c4e7 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Hydroseeding
checkpoint-status |  |  | checkpoint | 28 - Hydroseeding
label | 43bc1796-5fc7-56e8-bd47-ef8c32d39928 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b6d28b08-99be-5b11-bf58-d9b0947b2bd8 |  | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
label | 792b4fe0-913a-520a-9b1d-51f5e497fbac |  | note | Frequency - At the completion of the Lot of work
label | b463cf11-502f-57d2-b12c-6c1d2011f2be |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | ce5c40fd-afab-56e2-8efa-6723653fcff9 |  | note | Conformance Criteria - Engineers Acceptance
label | f418fb20-020d-5e61-bf95-90bff0e5858c |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | Final Inspection and Handover
checkpoint-status |  |  | checkpoint | 29 - Quality Assurance deliverables
label | e59ee23f-4bd8-5b2d-9c29-ea8ba812f172 |  | note | ACTION (Hold, Monitor, Witness) - W
label | de6b2fd8-50a6-530d-b101-40e09e917cd4 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 657121df-3073-5345-992f-1ce2512ad087 |  | note | Frequency - At completion of Lot
label | 4f893e6d-c756-56bd-bd9d-8c9ab3a2bef3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 58b36bca-d887-5e43-ae4f-90d038f0f7a2 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | c5415ccc-44c6-52ff-97d9-7ac558546783 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 30 - Completion Sign Off From Fields Below
label | 948e2af4-3520-5317-a58a-e152c71a2a29 |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | CS-4069 - Stringline Dipsheet |  |  |  |  | Yes | CS-4069 - Stringline Dipsheet | f53c28e5-27fa-4b09-9aef-10b0daec0e30
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | e54e0bba-6789-5757-bd7b-8a3c1db3518e |  | textbox | Project No.
text | 854c8023-289a-585e-879b-4d6a38b144bb |  | textbox | Stage:
text | 12e60cd1-31c8-50fa-b1c0-e5a9f8582582 |  | textbox | Material:
label | ac16abc2-531f-54ea-82a0-f3cd70b9cf59 |  | note | ○ Subgrade TNZ F/1 Tolerance: -30mm / 0mm
label | edee0e11-3878-576e-b4cc-391e56284abc |  | note | ○ SIL TNZ F/1 Tolerance: -30mm / 0mm
label | 22d294fe-ee97-5cdc-87f3-478853a8a7f1 |  | note | ○ Subbase TNZ B/2 Tolerance: -25mm / +5mm
label | b5250a0f-ef5a-5857-b645-a7a16728f502 |  | note | ○ Basecourse TNZ B/2 Tolerance: -5mm/+15mm without concrete channel
label | 4e44e9a6-79eb-52ff-8530-92698d59d039 |  | note | ○ Basecourse TNZ B/2 Tolerance: -5mm/+5mm with concrete channel in locations close to or at the lip of the channel
text | 6c226aa7-a265-5193-a8bc-8e8af721d522 |  | textbox | String Lift: |  |  | mm
checkpoint-group |  |  | section | Chainage
checkpoint-no-status |  |  | checkpoint | Chainage (1)
text | 6dfbc0ac-acab-5592-a787-1dc52326e9ac |  | textbox | (m)
text | 4ed42599-275a-59d1-874e-7a3fa08cd00a |  | textbox | Width - Left Shoulder:
text | 0064b6ed-f1b0-5a24-8d55-c36dd40c1740 |  | textbox | Depth Below String line - Left edge:
text | 07ed378a-ec12-559f-903e-163c35116cf6 |  | textbox | Depth Below String line - Left mid-lane:
text | ed519ffe-4207-51cf-87eb-9fd904f62401 |  | textbox | Depth Below String line - Centreline:
text | 31803c36-ac1c-5686-9d62-1cebf60e23c7 |  | textbox | Depth Below String line - Right mid-lane:
text | b4ce011f-dd60-53cb-8f9a-9da95bb74e80 |  | textbox | Depth Below String line - Right edge:
text | bbbcd990-36c8-52c6-93b0-b3bad4d67cc3 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (2)
text | 20e185f0-8108-5bc9-a9d1-b2f5918af893 |  | textbox | (m)
text | c1843abc-732c-592e-9c93-a167be7588b8 |  | textbox | Width - Left Shoulder:
text | 6644a7a3-20d6-5ac6-ad6e-4063c530732c |  | textbox | Depth Below String line - Left edge:
text | 3041446a-84c9-5ce4-849d-4d5a87b5724d |  | textbox | Depth Below String line - Left mid-lane:
text | 9ef0b314-51ba-57aa-9d4d-babdf44ad256 |  | textbox | Depth Below String line - Centreline:
text | 0519e268-0d2f-5533-9703-79e7fa9fabb2 |  | textbox | Depth Below String line - Right mid-lane:
text | c3c0cac8-6347-5148-9bd1-896dccb97a65 |  | textbox | Depth Below String line - Right edge:
text | 370cf376-6087-5b61-8fd9-808bcc66ec2e |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (3)
text | ae92531e-fe10-5758-9785-b188ddb5ca2e |  | textbox | (m)
text | b7ed0b8e-382d-550c-8404-b6bcf83bff93 |  | textbox | Width - Left Shoulder:
text | a930ec0d-b813-573a-87ef-95b0d1d068aa |  | textbox | Depth Below String line - Left edge:
text | 3b6bf40c-1607-5e96-ab06-d51328091228 |  | textbox | Depth Below String line - Left mid-lane:
text | 3ddb6169-f5a0-5694-9f2c-a24517c47cd9 |  | textbox | Depth Below String line - Centreline:
text | d942fd14-5457-5dc9-9735-ca7f0e592b7e |  | textbox | Depth Below String line - Right mid-lane:
text | 33ac2c1b-f169-5a3f-a5d1-efbf9ad3dde2 |  | textbox | Depth Below String line - Right edge:
text | 395e0eb2-6493-5cf5-a913-089614aaa4d9 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (4)
text | 4298a9fe-9760-5391-b199-e16d1bed1ab1 |  | textbox | (m)
text | 82ec638a-49fe-5a1f-8a6a-6e051dce9fde |  | textbox | Width - Left Shoulder:
text | 331a9351-1c67-5f1b-85bd-ff81cc0ed0b8 |  | textbox | Depth Below String line - Left edge:
text | e5c84147-c22d-5ba7-951f-5b24c70efc98 |  | textbox | Depth Below String line - Left mid-lane:
text | c81690b3-4b9d-5236-b527-acb5725c7f3b |  | textbox | Depth Below String line - Centreline:
text | 77208a0d-e5f2-5bac-ba92-e230f4429b86 |  | textbox | Depth Below String line - Right mid-lane:
text | 167bd9a5-186a-5f13-aba1-99cdc75496bf |  | textbox | Depth Below String line - Right edge:
text | b507ec65-6b95-5ec5-a2ba-99691c84571b |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (5)
text | e4f83531-b2c7-55f4-9616-d40602c3b4ad |  | textbox | (m)
text | 75bc90d6-9cf7-5306-89c4-0e69e5a1cbfb |  | textbox | Width - Left Shoulder:
text | 1c2bea52-017d-596b-81d7-12cd9b616998 |  | textbox | Depth Below String line - Left edge:
text | aa43e138-9e8b-5d08-bfe4-e8697ef68e45 |  | textbox | Depth Below String line - Left mid-lane:
text | 223a7ef0-7f67-5b5f-b296-fb3adb7e15c0 |  | textbox | Depth Below String line - Centreline:
text | fcd20a93-0e29-56bf-90e2-092edcb939e4 |  | textbox | Depth Below String line - Right mid-lane:
text | 8d2e2bda-b615-5b9a-9d4b-cab75974dd47 |  | textbox | Depth Below String line - Right edge:
text | 3c7c5f3c-1be6-5e93-86e9-563d713b280f |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (6)
text | aa29042a-5f6f-51ba-9c4f-545f60433e68 |  | textbox | (m)
text | 30b9a845-3248-5526-a8a7-a935dc154218 |  | textbox | Width - Left Shoulder:
text | 26fed5f9-f7a7-5e15-b842-81895fb28f27 |  | textbox | Depth Below String line - Left edge:
text | 4467fd96-f609-53ac-9b68-694df114b8fd |  | textbox | Depth Below String line - Left mid-lane:
text | e053135d-9b42-5c42-9a96-dafb958960e5 |  | textbox | Depth Below String line - Centreline:
text | 09471cd0-fa3c-5e31-8e07-119e5beb5d75 |  | textbox | Depth Below String line - Right mid-lane:
text | 344ab302-0f4e-53e2-9c7a-c04f0e650c6e |  | textbox | Depth Below String line - Right edge:
text | 3726afc2-2ce0-5447-bc8c-57040b561234 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (7)
text | b93614f7-c77b-5e6d-82c2-622819e28633 |  | textbox | (m)
text | 4bf715c9-3985-5b60-9025-b353bbb3a2c0 |  | textbox | Width - Left Shoulder:
text | 02a998bb-9827-52cd-b4ba-5f2e9ac31d09 |  | textbox | Depth Below String line - Left edge:
text | b5218789-e420-5817-acc3-3a4053269abf |  | textbox | Depth Below String line - Left mid-lane:
text | 184ff356-206b-5bb6-a192-5bad4f30d9c7 |  | textbox | Depth Below String line - Centreline:
text | ca137814-51a5-5e7b-98ea-a528c4e2f39f |  | textbox | Depth Below String line - Right mid-lane:
text | 2433bdd4-cd4f-5419-a1f3-3a56dadf0d67 |  | textbox | Depth Below String line - Right edge:
text | 93a650d7-391e-5b1c-a281-a5d524935b07 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (8)
text | a719b05a-5bf6-53f4-9d73-56fcb156f16c |  | textbox | (m)
text | 2f6231ee-2ab7-58e9-9894-5193ece61a03 |  | textbox | Width - Left Shoulder:
text | f2b00c23-5a1d-59c7-b3ec-d8bbfd67ea99 |  | textbox | Depth Below String line - Left edge:
text | 535866ca-b380-5b76-97c4-0c9543cfb5cd |  | textbox | Depth Below String line - Left mid-lane:
text | 5e6c9719-939a-5f88-b0e0-2bcf7549fc0f |  | textbox | Depth Below String line - Centreline:
text | e750ed71-f770-5069-8875-ec69ca097818 |  | textbox | Depth Below String line - Right mid-lane:
text | fba10cc8-e1de-5c6c-862f-8657e7988d0b |  | textbox | Depth Below String line - Right edge:
text | 6dd5ebb2-5a5e-5e6c-8e24-66c696026dda |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (9)
text | 2b6e83fd-8279-5edf-9c7f-4bdf1a994d11 |  | textbox | (m)
text | 84625485-c853-55fa-b274-cff970088f97 |  | textbox | Width - Left Shoulder:
text | 450bf888-ea95-5b11-ad82-20db54471e50 |  | textbox | Depth Below String line - Left edge:
text | b7c1636d-ccda-5f0c-b8d2-ae12e6980f18 |  | textbox | Depth Below String line - Left mid-lane:
text | 9f03f076-7dc4-54ad-82af-721794f32277 |  | textbox | Depth Below String line - Centreline:
text | b03b3188-85e0-5b7f-b0aa-5b3059986938 |  | textbox | Depth Below String line - Right mid-lane:
text | 120815ec-f7cf-5ba8-879b-2fa29aef984f |  | textbox | Depth Below String line - Right edge:
text | 48ee7822-e010-5d9a-a228-9d3fecc47e39 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (10)
text | c129c220-9bfe-5c95-b201-6784bc84f556 |  | textbox | (m)
text | 270c754c-4bb7-5098-9350-c368e6aec632 |  | textbox | Width - Left Shoulder:
text | 39b05d5d-6bcb-5740-b081-d1c37d8e7972 |  | textbox | Depth Below String line - Left edge:
text | 5e0dda29-b2e5-5ee0-9d1d-611cee256d2b |  | textbox | Depth Below String line - Left mid-lane:
text | 0c8f571c-9a8c-5a59-bbb5-c989ea18c912 |  | textbox | Depth Below String line - Centreline:
text | 4ed53b1a-8332-5030-9512-af54ec895ee3 |  | textbox | Depth Below String line - Right mid-lane:
text | 3dadd15b-2c6e-5bce-87bc-95c12be64671 |  | textbox | Depth Below String line - Right edge:
text | 810478dc-2ec4-5d0a-8de5-594ffe3ecd0c |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (11)
text | 99fbe9e5-b71b-5c0f-bacb-7745c198574d |  | textbox | (m)
text | 056882cf-9b3a-5212-a7c1-5192b4ef1338 |  | textbox | Width - Left Shoulder:
text | 96c6e6e8-25ad-542e-b9cc-d21fcc02c727 |  | textbox | Depth Below String line - Left edge:
text | d97e9b2d-25c2-584a-994f-7baa34317452 |  | textbox | Depth Below String line - Left mid-lane:
text | f96f21fe-2423-5f97-a976-2fa1c17dbc0d |  | textbox | Depth Below String line - Centreline:
text | 36556c79-00a0-5d52-95bf-b907bf2263dc |  | textbox | Depth Below String line - Right mid-lane:
text | 450fc8fa-47e1-52a6-a72e-10e20b1ecdd3 |  | textbox | Depth Below String line - Right edge:
text | d196d829-fc03-512c-bffa-c1888c83cdf4 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (12)
text | 8ae839b6-7077-51d6-95b2-41cf52f84477 |  | textbox | (m)
text | 0fbe0171-1130-5d4f-9608-4e3d630b59e5 |  | textbox | Width - Left Shoulder:
text | 6da0c6b5-abcd-5237-ad9c-55cb3fc2d5c8 |  | textbox | Depth Below String line - Left edge:
text | 222be27d-8a44-58e5-b5cb-fec2e6d6c0db |  | textbox | Depth Below String line - Left mid-lane:
text | ec41199d-f7c9-5574-a68f-1afeae6fee31 |  | textbox | Depth Below String line - Centreline:
text | 0317b100-2ddb-56be-862f-57153533ebd1 |  | textbox | Depth Below String line - Right mid-lane:
text | 63ff0250-263f-53b6-80f8-091b91428a6e |  | textbox | Depth Below String line - Right edge:
text | 75756872-962a-595d-9edd-5693225f96da |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (13)
text | f66017c8-363e-5e9a-aa07-40169440792d |  | textbox | (m)
text | 190b34a6-0d3d-5e45-bb06-4b52259b9eac |  | textbox | Width - Left Shoulder:
text | ff0cf95b-b111-5cd5-8a92-c714cc1fea68 |  | textbox | Depth Below String line - Left edge:
text | 0cf77e15-3593-517c-acab-285e6ad375d1 |  | textbox | Depth Below String line - Left mid-lane:
text | f013b1bf-c78b-5891-8752-bb42036a4e10 |  | textbox | Depth Below String line - Centreline:
text | b3f483e7-78be-5b10-a3e2-7de9a6c2243f |  | textbox | Depth Below String line - Right mid-lane:
text | 1671ff0f-b17a-50a6-b131-9294c400504d |  | textbox | Depth Below String line - Right edge:
text | 52a6b850-9894-5da7-bf2d-e523d39cfc13 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (14)
text | afb43c77-ef1e-5ef5-95d0-83a62c35e12f |  | textbox | (m)
text | e9b11da6-955a-5c64-bc6d-a2698a557150 |  | textbox | Width - Left Shoulder:
text | 875af6b3-3fda-5cbc-842a-501dae2ed2d1 |  | textbox | Depth Below String line - Left edge:
text | a91bfba3-c8f0-5ff7-ae1a-23e3d4fe2b77 |  | textbox | Depth Below String line - Left mid-lane:
text | fb059cca-d30b-562f-8ac8-5506ea3ecc20 |  | textbox | Depth Below String line - Centreline:
text | 840bb212-6650-5aa6-8d23-7469965a869e |  | textbox | Depth Below String line - Right mid-lane:
text | 5fc75898-4449-5249-9f56-149e7b412043 |  | textbox | Depth Below String line - Right edge:
text | 362b319d-f833-5d0f-ae51-e8ffde725f6d |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (15)
text | ea48af33-d15b-5fb3-b79a-f828328c62c7 |  | textbox | (m)
text | ec0e59d8-bb9e-544a-82d5-927c0413bbf2 |  | textbox | Width - Left Shoulder:
text | cd599c2d-fe40-548b-a81b-73be8d6ea75e |  | textbox | Depth Below String line - Left edge:
text | f135780c-5698-5cfa-aa4b-408c19aea5e3 |  | textbox | Depth Below String line - Left mid-lane:
text | 0dd1150c-262c-5fde-b3d1-da5b3f457a5b |  | textbox | Depth Below String line - Centreline:
text | d7af50aa-a12d-5ba2-bdb3-05f69a6e806e |  | textbox | Depth Below String line - Right mid-lane:
text | f7487437-cb8a-5779-95ba-1cac426dcdc6 |  | textbox | Depth Below String line - Right edge:
text | 9260f7d5-7e57-50a0-b97c-9d007d5503b9 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (16)
text | 07aebf13-52c6-53b3-9ba8-9fdca12aa5e8 |  | textbox | (m)
text | 5ce3e775-dedd-5bfa-b0c1-4fa53d06492e |  | textbox | Width - Left Shoulder:
text | 6ac8872a-49d8-59e0-9c3f-4bb9b74a42ec |  | textbox | Depth Below String line - Left edge:
text | 36f82440-a285-5dd1-87f2-e102794bf6c5 |  | textbox | Depth Below String line - Left mid-lane:
text | 5514987e-6fe4-5999-b27a-4a3aba54e799 |  | textbox | Depth Below String line - Centreline:
text | 51b65320-eaad-5686-a11c-959a7b24f0ad |  | textbox | Depth Below String line - Right mid-lane:
text | 2368ef4e-3f9c-56cb-93d3-80a474b966e6 |  | textbox | Depth Below String line - Right edge:
text | 432dd6fa-3425-59d4-8d87-957bfb76d421 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (17)
text | 8e661e78-47ee-5c51-90c1-94814b4053ab |  | textbox | (m)
text | 75e06089-c071-5989-bd1d-15d602c09b86 |  | textbox | Width - Left Shoulder:
text | 2b1da45b-bdf7-5dc1-8b1c-88f62eeae23f |  | textbox | Depth Below String line - Left edge:
text | 4b06590f-eb8c-5c73-8a8e-9d5042f84b55 |  | textbox | Depth Below String line - Left mid-lane:
text | 003ce279-4f21-5500-89bd-da28a86d8d50 |  | textbox | Depth Below String line - Centreline:
text | aad7c468-aad1-5256-a4e6-8f3c1a79e85f |  | textbox | Depth Below String line - Right mid-lane:
text | 6a4a78ec-3303-5b5f-a5d6-5860abef03d7 |  | textbox | Depth Below String line - Right edge:
text | 5f15ef6f-3fce-5ae1-b087-2afb35f46ff8 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (18)
text | 4c31b678-0a72-5c02-9812-b579a99fb020 |  | textbox | (m)
text | bed872aa-3968-5146-9f23-a59fecec8b2c |  | textbox | Width - Left Shoulder:
text | e86842b5-140d-5364-b170-7168e9be34b3 |  | textbox | Depth Below String line - Left edge:
text | 36072089-91b4-5946-8589-5b6023af3872 |  | textbox | Depth Below String line - Left mid-lane:
text | 43299b86-faad-520e-9b29-e1f03399cb5e |  | textbox | Depth Below String line - Centreline:
text | bad1972c-7344-564a-8e03-adc43da777f5 |  | textbox | Depth Below String line - Right mid-lane:
text | e08ab975-8e7f-56bf-a781-330d430d831c |  | textbox | Depth Below String line - Right edge:
text | 8a4e97af-d8e5-5f13-9d2b-cf538b44081a |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (19)
text | 5b8e6e02-31f0-5705-b64f-f08769c79700 |  | textbox | (m)
text | 0bc80d02-6f2b-5412-98b6-927c4aa89fbb |  | textbox | Width - Left Shoulder:
text | 5c2ecb01-cc18-52c1-9f6d-67bcd84c8ce1 |  | textbox | Depth Below String line - Left edge:
text | 4da7ddab-82dc-5663-b41f-4e86f994851c |  | textbox | Depth Below String line - Left mid-lane:
text | eb1e44f8-643e-5e99-89a1-fe3b78f8f769 |  | textbox | Depth Below String line - Centreline:
text | e484f3da-64a8-54e9-9917-9c0cb13185f5 |  | textbox | Depth Below String line - Right mid-lane:
text | 4cf8ee9c-8d11-5f67-bc58-e7919aecc769 |  | textbox | Depth Below String line - Right edge:
text | 16301353-6e5a-5334-9407-5ff093581d51 |  | textbox | Width - Right shoulder:
checkpoint-no-status |  |  | checkpoint | Chainage (20)
text | 19feb1dd-cb98-5a6e-b216-7d01b22224a5 |  | textbox | (m)
text | 734d3e78-d8e3-52a8-8831-c9fefd7123fd |  | textbox | Width - Left Shoulder:
text | 996e13bc-f232-5f62-a184-46c5168bd407 |  | textbox | Depth Below String line - Left edge:
text | d752ce51-dcd6-5583-a14d-0d550cf69bf9 |  | textbox | Depth Below String line - Left mid-lane:
text | 3676aa2b-80da-5c22-9ee8-620ac32e966f |  | textbox | Depth Below String line - Centreline:
text | 2a22f83b-4989-592f-8b9a-e8fba71d3227 |  | textbox | Depth Below String line - Right mid-lane:
text | d092df9d-7c96-504d-9333-d77f577cef8b |  | textbox | Depth Below String line - Right edge:
text | 920256f6-346d-5bce-aeb7-b6bc4f4035c4 |  | textbox | Width - Right shoulder:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
text | 73a9a5fa-8101-54ed-accf-1a90e2ac6eb5 |  | textbox | Site Engineer - Name:
text | d3c43505-82ec-57f8-9659-83179b6f9b3a |  | textbox | Site Engineer - Date:
text | a5d48f73-ca8e-5cd0-a0bc-c42d0f169dc8 |  | textbox | CPS Engineer - Name:
text | 74a88726-ef0d-587c-bbf5-e18f2de6ba02 |  | textbox | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-sectioned |  |  | checklist | CS-4114 - Anti-Graffiti Coating Daily Checksheet |  |  |  |  | Yes | CS-4114 - Anti-Graffiti Coating Daily Checksheet | f6ee217e-5c9b-4bba-bdf5-55f65a1df077
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | a330c9e0-ca3f-5468-b7c9-f23ea72b86a8 |  | textbox | Project No.
text | 78d5767c-cada-5531-9060-d0050651f0ed |  | textbox | Applicator:
text | f4957993-6f28-5bd9-9432-864be0b7eae9 |  | textbox | Supervisor:
checkpoint-group |  |  | section | Weather Conditions
checkpoint-status |  |  | checkpoint | Humidity
text | 6f64aac3-c19b-5bb2-a8f3-74e997815564 |  | textbox | Result:
checkpoint-status |  |  | checkpoint | Temperature
text | 404a5443-c31b-5799-b49f-e2db9445728e |  | textbox | Result:
checkpoint-status |  |  | checkpoint | General (overcast, windy etc.)
text | 0b432f12-51ce-5d30-8e49-a05946e41ed7 |  | textbox | Result:
checkpoint-group |  |  | section | Material Application
checkpoint-status |  |  | checkpoint | Substrate Material
text | 92a67dbb-1cd5-5d55-99aa-63fab146a2c3 |  | textbox | 1st Coat WFT |  |  | (µm)
text | f1f32d0a-9a4b-56e8-b9ba-0a7cc00c4aa1 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | d17d7136-9340-551e-9e71-3c5e5287f983 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Brand Name
text | d45b0e1f-5f6b-5673-af34-952d96ff7c31 |  | textbox | 1st Coat WFT |  |  | (µm)
text | cbc9473a-8ea5-59dc-9843-8d90893f0cfc |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 22db8b13-787d-5dfe-acec-72eb0943f530 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Batch Number Base
text | 2e57e745-08e1-56a2-a802-cd7a54bdee5a |  | textbox | 1st Coat WFT |  |  | (µm)
text | b0df202e-1fa7-5a1b-abba-b093aefbf7cf |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 76a9670e-b6f8-5aef-89f2-ccead2d2c2b7 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Batch Number Hardner
text | 9826556a-f6a7-5227-8aff-092e62c0a68e |  | textbox | 1st Coat WFT |  |  | (µm)
text | b884a55a-912a-5086-be91-86684de769b3 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 28ce75fc-5979-5049-aa1d-ea63a6611680 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Colour
text | 968b0f9a-e9cc-5605-9c07-953a4f247c2e |  | textbox | 1st Coat WFT |  |  | (µm)
text | ff801982-665e-5f26-9c85-90456953f242 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | b1efcdfd-2023-5754-b025-395a9981f96e |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Thinner Used (Ref Number)
text | 1ceac1f6-3501-55b5-abb0-b1067f4b340c |  | textbox | 1st Coat WFT |  |  | (µm)
text | eda99d30-9a6e-5e92-b407-8a51ba02d9aa |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 9efbd107-7939-58bf-9f1f-bcf934c204c3 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | % Thinner used
text | 849db240-f4cd-5a55-b9b1-3cecc17ec390 |  | textbox | 1st Coat WFT |  |  | (µm)
text | d8add2b4-36ca-552c-88a8-fe60095b9ca0 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 69d4c554-77d7-512c-a147-a1bc8769dcf3 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Brush
text | 64437f30-dfde-5cdc-9b84-d1daaedb03a8 |  | textbox | 1st Coat WFT |  |  | (µm)
text | 36e73faa-580e-55c1-8745-b0effc713bcd |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 034b179a-4e3c-556a-ab9f-2a9c017bb542 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Roller
text | 4a1d5292-3431-5202-a565-72bc498ab1c3 |  | textbox | 1st Coat WFT |  |  | (µm)
text | 0e9011fe-686b-5d38-92fa-2d962a3f3b85 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | b7e0a0d6-e76f-58d0-93f6-b94726864f14 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Spray
text | 3f0de69b-268f-5328-aeb1-4fce481ad72a |  | textbox | 1st Coat WFT |  |  | (µm)
text | ea35a198-0f95-5886-ab98-f0bdc170a13c |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 97247706-ef80-5776-806b-d541fc80ad76 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-group |  |  | section | To be filled out by Inspector
checkpoint-status |  |  | checkpoint | Dry Film Thickness (µm)
text | 4d6c2284-ca16-596e-9846-6153812b7329 |  | textbox | 1st Coat WFT |  |  | (µm)
text | 28382cfc-a9c5-5505-a244-9980abc1e312 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | da59e1a9-d9a7-5620-b2c2-c87e03bff2c8 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Specified (µm)
text | b828a61f-c11c-51c7-9e40-34f2b4dd8fcf |  | textbox | 1st Coat WFT |  |  | (µm)
text | d990a72a-ee12-5b66-a812-4f32bf9c02e1 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 9e0e32e7-94d3-55c7-bace-51510f99db20 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Average (µm)
text | 9c7748b9-6d60-5acb-857d-166eb2202983 |  | textbox | 1st Coat WFT |  |  | (µm)
text | 5de75487-2103-5b6c-ac49-412aba108ee9 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 6f92008a-a363-5049-aa1d-ac9e9c015ff6 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Maximum (µm)
text | 15fe5137-0423-5367-afc2-aea42d31e7f6 |  | textbox | 1st Coat WFT |  |  | (µm)
text | 7c8cc3ed-6bf5-5a32-ac7b-2d2b3b6aa7e6 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 62466be7-a561-5879-af08-2771a101e239 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Minimum (µm)
text | ec48d63a-6bf9-5c35-abfa-f689efa797db |  | textbox | 1st Coat WFT |  |  | (µm)
text | b3a79ce2-c37f-5b2b-a88b-a36d2315e112 |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 1390b3ba-55f4-5f1d-90b0-d9727b75b467 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-status |  |  | checkpoint | Number of Readings taken
text | eef004bb-71e3-5033-b033-b59bd9a92360 |  | textbox | 1st Coat WFT |  |  | (µm)
text | dcfffa1a-c81a-5f9c-a5e1-cb8717ce943f |  | textbox | 2nd Coat WFT |  |  | (µm)
text | 3276f9e5-8870-5473-8391-4abb5f28d2b6 |  | textbox | 3rd Coat WFT |  |  | (µm)
checkpoint-group |  |  | section | Outcome
checkpoint-status |  |  | checkpoint | Passed
checkpoint-status |  |  | checkpoint | Rejected
text | 07e2310a-264b-503d-a932-9e3df0842d20 |  | textbox | OFI #
checkpoint-status |  |  | checkpoint | Rework
text | da67e47d-79c5-545f-bae6-cd94b248911d |  | textbox | OFI #
checkpoint-status |  |  | checkpoint | Checked and Accepted – HOLD POINT – Applicator, Site Engineer & CPS Engineer to sign
text | ef2f6877-254b-5771-bbdb-ae98f8520fde |  | textbox | Name: Applicator
date | 633b8a39-622a-54fd-bf07-14ec2e24af5a |  | date | Applicator - Date:
text | 81d03088-ebd5-553a-9514-6300fb57cf1a |  | textbox | Name: Site Engineer
date | e743822b-cc2c-5600-95b3-b4c6ac62c13f |  | date | Site Engineer - Date:
text | 0e069799-27aa-5730-b4d6-235edbeef8bb |  | textbox | Name: CPS Engineer
date | ad997ee0-5393-594a-8d30-7bb720840106 |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign:
checklist-flat |  |  | checklist | ITP - G1202A - Waikaretaheke Riverbend Recovery - Rock Armouring / Bulk Fill | itp |  |  |  | Yes | ITP - G1202A - Waikaretaheke Riverbend Recovery - Rock Armouring / Bulk Fill | f787917b-d7d8-4d41-8a02-33791c141049
checkpoint-status |  |  | checkpoint | Project Site reps.
text | d2a0936c-1361-5cc7-ad04-61798a8a96c7 |  | textbox | CPS Eng.
text | 77830ba1-13b9-5061-8157-75144483b612 |  | textbox | Site Engineer
text | 80805fb3-9a2f-502c-8e6d-2eac03919090 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1 - Survey Setout
label | f13839b3-625e-5e9e-a18e-0d1e787ba921 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 6563edd2-254b-5ace-8d82-742a8ff93901 |  | note | Detail - Set out lateral extents of buttress. Geotech Engineer to confirm extent of works
label | e49df920-ed1b-5427-a974-4fbc3c0a6bdb |  | note | Frequency - Prior to commencement
label | 57258033-502c-515c-9262-4dda11e037e4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | cd37160f-f724-57cc-925c-c2982155707e |  | note | Conformance Criteria - Fault ID 530 - Underslip Recovery Remediation Design Report
label | 5bdada54-7f0d-5730-b3ed-76595fb6f8bd |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2 - Survey Setout
label | 9e0d1e36-f6e4-51a1-8996-c6f0b685adad |  | note | ACTION (Hold, Monitor, Witness) - H
label | ea62ae68-78f5-5469-8986-a6e9fba091ec |  | note | Detail - The buttress slope face angle should be 2H:1V. The buttress slope face angle may be steepened to no more than 1.5H:1V if required by site constraints, this will need to be approved by the Geotechnical Site Engineer
label | fbe62728-362a-57b4-944e-0195bd310d0d |  | note | Frequency - Prior to commencement
label | 418e96ad-a179-5654-9b12-1f3614d57634 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | 7d938b50-0411-5510-8acd-5868444014c4 |  | note | Conformance Criteria - Fault ID 530 - Underslip Recovery Remediation Design Report
label | 43687502-dd4b-5bcf-922d-24024877a374 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3 - Remove all loose materials
label | 0ac8bc5c-3bb3-530d-a828-8ab4702bd6b8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 349bb2dd-5216-5868-8905-0e00a6047cd9 |  | note | Detail - Once all ESC controls have been installed
label | bbccbaae-1f5e-55ba-9101-08a99d428e90 |  | note | Frequency - Prior to commencement
label | 041df88f-e44f-5cdc-81f7-b2d4b7dea796 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
checkpoint-status |  |  | checkpoint | 4 - Excavate to Sub-Grade
label | 4907b1b8-39f6-5d20-8f3d-4b55756fcfee |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0003bc22-27a1-5507-b0d9-083b68f96305 |  | note | Detail - Inspect fill foundation
label | acacd9da-9f2f-5854-887b-5631366653ef |  | note | Frequency - Per area as required
label | 3ef168ba-d3ee-5cdc-800d-ec4a9ac0fa57 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | f93077ec-dbc2-58ff-8241-bfec7a1cede5 |  | note | Conformance Criteria - Fill foundation must be approved, in writing, before filling commences
label | 002ab2d4-7521-58a0-a580-355ccfa762b5 |  | note | Records - CS-4100 Subgrade Approval Checksheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5 - Excavate to Sub-Grade
label | 9cfbe2aa-b06d-51f8-9131-40cceadbf525 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 8cac154c-ff61-52fe-918e-5f67ff2c2abc |  | note | Detail - Foundation compliance. May be performed by site engineer or CPS as is specifically only for ground strength data for future review.
label | ee9a5d69-5c13-5f82-8621-fd41d23c3164 |  | note | Frequency - Per area as required
label | 3a01d25b-f976-5d6e-b81d-f469c01076aa |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Per area as required
label | a9fe85fd-b964-5d22-9510-a9fe70901a9e |  | note | Conformance Criteria - >= 1 test per 10 linear metres, where access is practical and available
label | 4fe77421-d047-5029-82c1-aafbfb8c576b |  | note | Records - Engineer or Lab Test Report
checkpoint-status |  |  | checkpoint | 6 - Material Compliance Testing
label | c21fb40e-ecb6-53f0-b389-a7017aed39b8 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 62a72fd9-7657-5be7-8408-32aa3c4237c2 |  | note | Detail - Material to meet specifications dependant on material type selected
label | 678d0ddb-9196-551e-9794-f25cf0b4ddba |  | note | Frequency - Each material used
label | ce7fecc0-d49d-5fda-a0f8-b8097c7663d7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 15b2703c-ab64-5c01-a2b7-c9a09dbf572f |  | note | Conformance Criteria - a. GRADATION D85/D15 = 1.9
label | 20505638-2b1a-5cec-86fa-77427620cd09 |  | note | b. D85 690 (MAX) AND 590 (MIN)
label | ecfa3bda-9988-5a26-a118-dee885a7c083 |  | note | c. D15 390 (MAX) AND 275 (MIN)
label | 49a8a889-a430-56c1-a137-ee846c664388 |  | note | Records - Supplier Record or Lab Test Report
checkpoint-status |  |  | checkpoint | 7 - Material Compliance Testing
label | a9622b56-bff2-5a50-8b34-1743cc6fccdd |  | note | ACTION (Hold, Monitor, Witness) - W
label | 923f6d74-21f6-5046-91d2-9ae0de8d2c9c |  | note | Detail - Rock Construction Material
label | fda6b4c9-bd8e-5ef3-a8ec-71323d1db986 |  | note | Frequency - 1 test per 1 000m3
label | ae87f384-8f40-59f9-bc6a-895b698dea98 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 69be5886-54be-5f78-ba5c-e2c1f6bafa6d |  | note | Conformance Criteria - D50 OF 450 WITH A MINIMUM SPECIFIC GRAVITY (SG) OF 2,350kg/m3
label | 19d5ab7e-680b-59ae-8df7-529e4c7b2ab5 |  | note | Records - Lab Test Report
checkpoint-status |  |  | checkpoint | 8 - Material Compliance Testing
label | fc419a85-8478-53f9-93df-d8678a1bde34 |  | note | ACTION (Hold, Monitor, Witness) - H
label | edaf621f-31e5-511f-8087-7edfcaf7c686 |  | note | Detail - Bulk Construction Material
label | 2e725d94-1437-5cf7-8add-bc57a1c30ba5 |  | note | Frequency - 1 test SET per 1 000m3
label | f71d0027-5e36-5427-a51b-d156b405dcbf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing - OMC Standard Compaction; Grading Curve (wet or dry sieve)
label | 6de63a39-cf7b-599a-bed5-0f9c27defc49 |  | note | Conformance Criteria - All bulk fill comprising clean graded granular aggregate with broken faces AP65 (i.e. gravel).
label | ed5b2e22-bec3-56ad-b1fa-5f5b402f204d |  | note | Records - Lab Test Reports
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 9 - Material Compliance Testing
label | 0881e1c6-1d28-58b3-b442-0338f8ebe58a |  | note | ACTION (Hold, Monitor, Witness) - M
label | e922d9d0-4c0e-5e4f-9ca3-c622d66b6bea |  | note | Detail - Back Face Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A39 (Class D) or similar
label | 0cf4fd6a-58fb-5d8f-8c92-59121538445e |  | note | Frequency - Prior to commencement of placement
label | 6ecd2e71-c900-5435-a5f3-45879cf5659c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 94988dbe-701c-5458-b3b3-e7767cc21b9e |  | note | Conformance Criteria - Conformance with Specification
label | 470fd9f2-e8d5-504a-bfc1-de6649bbe861 |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 10 - Material Compliance Testing
label | de4d336e-40ce-53ad-b717-695932e27279 |  | note | ACTION (Hold, Monitor, Witness) - M
label | dab923b5-f745-5b26-bea3-925d44a00c68 |  | note | Detail - Between Rock Armour and bulk fill Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bidim A49 (Class E) or similar
label | 222ac956-8ee7-5c65-9ca5-18562efccb05 |  | note | Frequency - Prior to commencement of placement
label | bc58f48a-2422-5f8a-8204-b2cc88a49096 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 7f2f8376-12ef-5d0e-9d81-f7ae73524f9d |  | note | Conformance Criteria - Conformance with Specification
label | c0a6f8ac-7abe-5bd9-953c-4ff4c880269d |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 11 - Geotextile Placement - Backface
label | fa3f4201-49f0-5fb0-b8a8-2888f3097055 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c41198a8-428f-5c57-ac1f-aed8460e4d4a |  | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | eabdb306-8ac1-52be-9ba2-7bdf87164fd1 |  | note | Frequency - Daily visual check
label | 50120ae6-8d6f-546a-9514-b6674220ef1c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 8d6a348e-aec1-5f0c-ae42-e380da403203 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 12 - Perforated Drainage Coils
label | 7d9e4b26-790c-53ac-aaaa-3028f0ac2c7d |  | note | ACTION (Hold, Monitor, Witness) - W
label | 762fce90-6017-5238-affc-7adf053b3035 |  | note | Detail - TAP ANY SEEPAGE OR GROUNDWATER FLOW WITH MEGA FLOW/ PERFORATED DRAINAGE COIL. THE OUTLET SHOULD BE AT THE TOE OF THE BUTTRESS.
label | 82a3ea47-e4e0-5771-b470-5fd59161ed6d |  | note | Frequency - Daily visual check
label | 105bdfc0-2b4f-530b-ad86-6304dbb661ad |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | d03f971e-c121-528a-a694-e8a4af4ca93c |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 13 - Backfilling of Engineered Fill Embankment
label | 1d50bb1c-efc0-5361-aa4a-83654b5b4d81 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0009544e-40ce-5099-9b73-27969eff00c2 |  | note | Detail - Engineered bulk construction material 250mm lifts with material and regular compaction testing
label | 2de22a9d-a3e8-59c3-9810-77f8bca163ea |  | note | Frequency - 1 test per 10m linear length (forming a test set). At least 1 test set every 2m fill height (minimum total of 3 evenly spaced test set intervals over total height of bulk fill).
label | 79265aa0-9cf4-5abe-9e0c-de4a464c81d5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing - NDM (required), supplemented with Clegg Hammer tests at discretion of site engineer.
label | 908b5d17-82a2-57bb-a8df-dbe61e625c21 |  | note | Conformance Criteria - 95% of MDD or clegg equivalent
label | cdc53b12-22bd-5184-94d1-dfdba12e841e |  | note | Records - Lab Test Reports
checkpoint-status |  |  | checkpoint | 14 - Backfilling of Engineered Fill Embankment
label | 324dab97-bb41-50f4-bbf7-ee5adc382372 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 796aba56-3208-58a5-bc73-e02932a566d4 |  | note | Detail - Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap
label | a38d704b-953c-54b4-80f9-ffd9d941356a |  | note | Frequency - At completion of bulk filling
label | 00eada8f-e51f-5bc9-bb04-4ae3f087d064 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | a19dad3b-7d9b-5418-ac5d-8ddd101eff9f |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 15 - Geotextile Placement - front face
label | 42131609-b110-5761-b2d6-c05ae6f8a68f |  | note | ACTION (Hold, Monitor, Witness) - W
label | bc1587ea-02da-5a12-bcab-697aa10fa47f |  | note | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | ca8cafe2-f36b-5490-b44f-487179c4c1ae |  | note | Frequency - At completion of bulk filling
label | 9e58f22a-a5aa-5eb0-80f6-9a4942ce62ae |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | c6073179-d230-5351-b0d6-1140a1419c09 |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 16 - Riprap Placement
label | 1131da71-5aba-5b56-a2f5-d993598af579 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 512670ec-ff67-5dd4-830f-31c303974560 |  | note | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. CPS Engineer given notice to visually inspect initial placement of riprap material
label | 5b5714ba-dcd4-50ce-bcf1-b9c2d2e8eba0 |  | note | Frequency - Daily visual check
label | 564d08d0-ada6-5239-b080-3b9a716d9913 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 6f9caeb5-1603-596f-8a30-a6bafbc7b1df |  | note | Conformance Criteria - Specification
label | 725e91a1-d8e8-5fac-9cbc-9c75a9576a9b |  | note | Records - Photo's
checkpoint-status |  |  | checkpoint | 17 - Survey As Built
label | ed5b144e-399f-5cf5-8f58-6cc396f12501 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 110ae3a7-bdbe-53a9-8c8e-cf1f9f5a74bc |  | note | Detail - Ensure rock slopes comply with design prior to next process taking place
label | 0519734a-f154-5022-b918-154c4cba8d67 |  | note | Frequency - At completion of Lot
label | 2bf8ba30-9e1a-5558-9384-e4f2d50f8f7b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | f204cdec-6de2-5c93-8203-3e1e72f4df7c |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 18 - Lot Number QA File
label | 3d28326a-5afc-58cb-a3fd-c84df00daea3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | f8f61be5-81fe-5360-8ac2-eb4ef53d7e67 |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 304db41c-fc8f-5cbd-a25c-8615316eafac |  | note | Frequency - At completion of Lot
label | bd11cdb2-100e-5425-bb0c-fc54dc0214f0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 6b37e9f1-55e2-5481-bc51-4786f2537454 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 40827fed-a49b-5b98-9fba-7681f3577a20 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 19 - As-builts
label | 50950d3b-5cbe-539c-bb17-743587837b93 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 58c57be2-04c5-52a0-9926-2ccbe9ab2fc0 |  | note | Detail - Red pen mark up drawings to be included in QA file
label | d7312da9-8104-57d8-a980-526b16bebabc |  | note | Frequency - At the completion of the Lot of work
label | 057410e7-f682-5fe0-8ce2-74e8ce7041ce |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | f062531c-3621-5a3b-b567-24aed46757a8 |  | note | Records - As-built Drawing
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 20 - Quality Assurance deliverables
label | 5f709ebc-7653-59fa-91ee-74e465ec8793 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0b149e25-b2a7-5483-8412-a8d09a4557a3 |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file. Red line mark up drawings to be included in QA file.
label | 1a22fef4-3007-505a-aee1-c04d73c7e37d |  | note | Frequency - At completion of Lot
label | b908f2b7-6269-5a13-995d-5ccf1703351f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | bd2bede7-a71c-5627-b1f4-9946019f08b9 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 683eb719-18bc-5778-80cc-678c9c133835 |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 21 - Completion Sign Off From Fields Below
label | e6e3a030-a362-5765-9bbf-182a8a4d11ab |  | note | Records - Signatures
checklist-flat |  |  | checklist | CS-4055 - Pavement Layers Checksheet |  |  |  |  | Yes | CS-4055 - Pavement Layers Checksheet | f7ffa9f7-3c2b-4274-81ea-3d3dd77e2c67
checkpoint-no-status |  |  | checkpoint | Details
text | 8b08887b-7393-5824-acf8-9e1c859915a9 |  | textbox | Paved Date:
text | 2385e446-d8c9-5876-b89a-da61519bbb98 |  | textbox | Location/ Direction:
text | b001dcbd-fd11-5321-a55d-5141a56cf149 |  | textbox | Day:
text | 80670e94-28dd-5616-aefb-eccffde25944 |  | textbox | Shift:
text | a4448f78-137b-581e-b0e5-0a854ef34fcc |  | textbox | Chainage(s) From:
text | 386093e1-f759-5ac1-8f3f-503435610f04 |  | textbox | Chainage(s) To:
text | dbad8e15-acd9-52d5-8d07-16286449641b |  | textbox | Previous Lot(s):
button | 0d094bcd-4ab9-5bec-bfad-c5e0ab72165b |  | button | Previous Lot(s) Comply? | Yes, No
text | 38bd6ef8-b557-5a3f-a390-e7dff3695ed2 |  | textbox | Corrective action?
checkpoint-status |  |  | checkpoint | HOLD POINT: Previous Layers Quality Manager signed off
button | f0c673b2-db37-5d5a-889e-68b778114a44 |  | button | Pave this layer | Yes, No
checkpoint-status |  |  | checkpoint | Layer Type:
boolean | 915300dc-c021-5fa5-89e3-c729322fa98c |  | tickbox | AC___ Layer # 1
boolean | 80b22f19-356e-5453-9eb3-5ec84339d688 |  | tickbox | AC___ Layer # 2
boolean | 804ccbde-770a-5591-a0df-a620ef7663c3 |  | tickbox | OGPA / SMA
text | 263f658f-25a5-596e-b23c-77b97525d362 |  | textbox | Other:
text | 1521bbab-e123-5373-b955-721d3b3ed4b3 |  | textbox | Nominal Depth To Pave:
text | dd2b6e16-9685-5c7c-bbf8-54e49f0ad2c9 |  | textbox | m² Paved:
text | 15842e6c-6489-5e03-b196-15f0bf7e8f39 |  | textbox | Linear(m):
text | 0fbbae2b-e12f-55d4-aeb8-6b20c18ba646 |  | textbox | Tack coat/Membrane l/m²:
text | 7e51c0bc-1e60-5106-8a49-975b7093770f |  | textbox | Nº of Cores required:
text | 3a5ff6ee-7c73-5579-8bbf-f90fc4bb7124 |  | textbox | Mat:
text | 78d84e91-8e6e-5bb8-b2cc-06bce3fbd70c |  | textbox | Joint:
text | 6ca7c3cc-82e2-5726-8de6-7c6b64c6c239 |  | textbox | Nº of Cores taken:
text | c3a7ad9d-43ff-54be-a4ed-cf377a470cb4 |  | textbox | Mat:
text | 02e4b44e-ac1a-57bd-9aa0-c50c526bf1ac |  | textbox | Joint:
button | 70435d1e-7591-5bba-9f97-33c03d568ce6 |  | button | Cores Taken: | Yes, No
button | f7ddd2b9-cff8-53f4-b7f2-9e260b30cd44 |  | button | Cores Filled: | Yes, No
text | 1d9b3157-f945-5ec2-8170-ab1e115342f8 |  | textbox | Laid (Ton):
text | 9b675a2a-b178-5174-8617-53de4201f80b |  | textbox | Nº of Binder & Gradings required:
text | 9987679e-81cc-5be3-b388-4b30079edb11 |  | textbox | Nº of Binder & Gradings supplied:
text | 6c4e93e9-3d00-5b74-b2ad-9bd0d6ad7bb2 |  | textbox | Lab Air Voids (%)
button | 1db4fec0-dd0d-5789-a015-08f57318d48b |  | button | Binder & Gradings Comply? | Yes, No
button | 735c6fc2-8828-5855-9457-d482c1bcbfeb |  | button | As built Survey Completed? | Yes, No
checkpoint-status |  |  | checkpoint | Air Voids - Run 1
text | cf04065e-e73f-5bbd-9e2f-3ccb8c7a7b5b |  | textbox | Characteristic High:
text | 34bc8c4f-e0bb-539c-b51d-be73ae893b09 |  | textbox | Characteristic Low:
text | 00fd1c6b-781c-5faa-86ef-a546d10bdc53 |  | textbox | Average:
text | f07642c2-c35a-57d9-8657-ebf60d0f9c98 |  | textbox | Joint:
checkpoint-status |  |  | checkpoint | Air Voids - Run 2
text | 600e60d2-348b-5b86-9ff0-9c096af8bd48 |  | textbox | Characteristic High:
text | 0eea81f9-deec-5706-a757-8bf3fc20f487 |  | textbox | Characteristic Low:
text | d08e5994-0464-5073-956f-3df15d46228a |  | textbox | Average:
text | 2b834365-2451-5919-8e88-211f6e182841 |  | textbox | Joint:
checkpoint-status |  |  | checkpoint | Air Voids - Run 3
text | fb9c7af6-0fa6-570b-b34a-f734e575f7c5 |  | textbox | Characteristic High:
text | 46a57e2b-bace-5254-ab47-6c32a1bcf253 |  | textbox | Characteristic Low:
text | 3cd0c37b-97ab-50b6-ae8c-a4aed3514e1b |  | textbox | Average:
text | 9143c710-49a6-53d0-af58-1a818e5ae149 |  | textbox | Joint:
button | ae13335d-9c19-5cf8-84f2-b37ed2811458 |  | button | Air Voids Comply? | Yes, No
button | fb2d897c-ba2c-5d87-a116-fb4b343cc7dd |  | button | Core Thickness Comply? | Yes, No
button | 588b51ef-2dcc-5921-a36e-53d2ee7464af |  | button | OFI attached for non-conformance | Yes, No
checkpoint-status |  |  | checkpoint | The above works have been inspected and on the basis of this check sheet are considered compliant with the drawings, specifications and instructions.
button | 3690756a-cf0a-5fe1-9564-29f29405ab4d |  | button | HOLD POINT: Does everything above comply? | Yes, No
button | 30464cd6-a818-5b13-8448-c9ba4b5546f1 |  | button | Pave next layer | Yes, No
checkpoint-status |  |  | checkpoint | Site Engineer
text | 5c0e8e58-7a5e-50e6-8ad0-5d425aa5c18e |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checkpoint-status |  |  | checkpoint | Quality Engineer
text | d05380db-ec16-5fa1-86e9-5c1a4e139f1a |  | textbox | Name:
holdpoint |  |  | signoff | Add Signature
checklist-sectioned |  |  | checklist | ITP - B1004B - WPB Slip - Reinforced Slope - Soil Nails | itp |  |  |  | Yes | ITP - B1004B - WPB Slip - Reinforced Slope - Soil Nails | f8bb0e78-656e-47be-8c8c-336fb7830f4e
checkpoint-group |  |  | section | 1. Minor Earthworks
checkpoint-status |  |  | checkpoint | Project Site reps.
text | 00440c30-d547-5ec3-8352-9a1e381b689b |  | textbox | CPS Eng.
text | ebe45485-b0a7-5d68-928d-4a5e5a34ae7f |  | textbox | Site Engineer
text | bf12f35f-64c6-5c3e-929d-6ad6e7acf19c |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Clearing & Earthworks
label | d8e32a5b-d891-5032-acfc-f96796cc066c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 729490f3-b0e0-558a-bfe4-7c5afdf54f3f |  | note | Detail - Before setout of the reinforced slope method all vegetation and debris clearance within the limits of the site is to be completed
label | cfde101c-023b-5a4d-b86b-df6f78bc674c |  | note | Frequency - Prior to commencement
label | 4d2054fe-588f-5ecb-9eca-24cefbcbdaca |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | a0fe6f21-4387-594c-aa12-b506a9626b01 |  | note | Conformance Criteria - In accordance with TNZ F/1
label | 40c2be53-ca8b-5b18-af9a-93466b45d860 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 1.2 - Cut/Fill Required
label | 03822524-35fb-5722-a7b7-e43508f9bf84 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 3c64e834-39d3-5be5-8e1f-c39bb14f58c4 |  | note | Detail - Any excavation and filling required is to be carried out. Excavation should be kept to a minimum
label | 220bdb98-009c-5a65-a598-3aa0920facb9 |  | note | Frequency - Prior to commencement
label | 12413c99-7f97-5ef0-9052-9efc09b203a6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 1d8f41f3-e491-5e25-8c24-ccd8b4fea872 |  | note | Conformance Criteria - In accordance with TNZ F/1.
label | 04e9c7a5-0509-594a-aebf-c76687573c6c |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 2. Material Production
checkpoint-status |  |  | checkpoint | 2.1 - Material Compliance (Rock Works)
label | 28fe644c-2fc8-5e1c-be20-ac9237f4c651 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c94ed8b6-0612-5220-b9e1-fefdfa430ec5 |  | note | Detail - Material to meet specifications dependant on material type selected
label | 5deb11ce-db25-5af5-ad9c-7223a1279680 |  | note | Frequency - Source test of each material used (minimum 10 rocks per source)
label | b374d0b7-6243-5820-8d3f-b658d5eef44c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | fb794b5c-f38f-598a-86ac-a14141793e2d |  | note | Conformance Criteria - 1. Schmidt Hammer test (minimum of 10 rocks per source) and 90% result ≥ 50 in all direction or
label | 121ac9b8-002d-5500-b27b-0668d060ea90 |  | note | 2. Weathering resistance AA,AB, BB or CA (NZS4407)
label | de3f7317-71b6-571f-b66e-c04d13005c78 |  | note | 3. Specific of gravity ≥ 2.56 or up size rock to compensate
label | 84b18f81-e93d-565e-8cf0-9f38dfe5a260 |  | note | 4. maximum dimension of any rock ≤ 3 times narrowest dimension
label | 878885f1-cf5d-528f-b87d-8693743a5671 |  | note | Records - Lab Reports, delivery dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.2 - Material Compliance (Rock Works)
label | 164d5bc9-50f5-5672-ac8a-d89f94579f75 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b3011cc9-5f3c-5651-800e-853e010a0fd9 |  | note | Detail - Consistency though construction and clean of dirt
label | 271b0d4d-e3d4-525d-b620-38c5f92641b6 |  | note | Frequency - Each rock source
label | 333a404a-3550-58be-982a-01421b2c47a0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Monitor on site
label | 9607f717-3b12-5d24-8d71-a8e1d2b363e4 |  | note | Conformance Criteria - Visual inspection for consistency of rock from the source should be undertaken throughout works, if variation is noted additional testing should be undertaken
label | af699c13-6d68-5f49-a55d-87c267c0c0b4 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 2.3 - Material Compliance Subsoil
label | 6081ee81-3bbd-50ef-9afe-1fddc617881a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 26a7fd49-04f3-5cc7-9ba6-cbc5fc273121 |  | note | Detail - Material to meet specifications
label | 870206bf-a920-5b2c-acbe-0ce44929460f |  | note | Frequency - Each rock source
label | dd1979d1-ddcb-529a-8d88-73eb7dc28ccd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Supplier certification and delivery dockets
label | 10b1a9ff-19cf-55ea-9812-2e9af4758fcb |  | note | Conformance Criteria - Prior to megaflow installation
label | 1bd1d1e3-5051-5d0e-b86c-595031025c2d |  | note | Records - Collect all delivery dockets and photos
checkpoint-status |  |  | checkpoint | 2.4 - Material Compliance and Methodology Approval
label | 7caa20f3-d02b-5c8b-a3dc-602c94147c75 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a67d9443-6850-5b4c-b129-32b9ee76c030 |  | note | Detail - Rock Bolt & Soil Nail materials to be ordered in accordance with the specification & design drawings
label | 01915dea-3612-5b83-a266-6ec8c355c83b |  | note | Frequency - Prior to commencement
label | 39516644-e5cf-5cf4-b42a-44ef7970fe81 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | ead264c6-4174-553d-b815-6774599f4e9e |  | note | Conformance Criteria - Grade 500E soil nail
label | 4e3f27ca-d44f-529a-9454-b3ed3341923d |  | note | ○ Class II corrosion protection
label | bb84d162-c6e7-5a4a-9f40-9099964ac1d5 |  | note | ○ Lengths and diameters shown on drawings are the minimum required
label | 093a306a-feb3-515e-b620-df349582b000 |  | note | Records - Delivery Docket
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.5 - Concrete Quality Plan and Work Plan
label | bd7a686c-5a48-57cf-972f-5afe51b32dd9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 15800eac-dab2-5c9a-8855-b268ac0b679b |  | note | Detail - Concrete Quality Plan and Work Plan
label | 19fab772-f4e9-5d16-948c-6fdfafad9027 |  | note | Frequency - Prior to commencement
label | b4dae406-60c7-5cc3-a6cf-cdf579737686 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | a05283eb-5cd2-51b8-a786-0ca540f9d40b |  | note | Conformance Criteria - Refer to section 8.3.1 for the Contract Quality Plan and Section 8.3.2 for the Work Plan
label | 3ff66707-3488-5774-a261-1d29dd245325 |  | note | Including:
label | b3988177-898a-518c-a212-350c5b9c7958 |  | note | – Name, qualification and experience of concrete works inspector
label | 846169e8-564c-5eed-ac08-72f046806823 |  | note | – Form and content of concrete placement card
label | 6c32256d-78e9-5b7a-a811-9e8a1863eb22 |  | note | Records - Email / RFI
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.6 - Concrete Supply Plant Approval
label | 23ae677e-4174-505a-b28a-fd20786b21e3 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 068c7f45-dbae-530d-8a8b-8cb22ca5f460 |  | note | Detail - Details of concrete supply plant, copy of certificate of audit for plant
label | 26d43b1e-7fec-59ae-b113-4cdf385033f2 |  | note | Frequency - Three weeks prior to pouring concrete
label | 9fff83ed-50f5-5bd5-8011-a3f7c0cbaea0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 57af2f6c-94b5-557a-8cc6-40c5d753a922 |  | note | Conformance Criteria - Including:
label | b66295a8-a1d7-5792-a0e0-08e5f33fe3d4 |  | note | – Plant test Results
label | 2bb5d547-de6f-5441-97af-8efda291090f |  | note | – ASR Compliance Records
label | 67c021e9-c770-5715-b6b9-3d151f41b452 |  | note | Records - Email / RFI
checkpoint-status |  |  | checkpoint | 2.7 - Reinforcement Steel Certification
label | a497e2a0-3e8b-5883-842d-26babcebb503 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 7ce3e3aa-a52d-5a9d-9acc-9d4e6416b8df |  | note | Detail - Reinforcing steel manufacturers test reports and certificates
label | 097ea0ba-8fcb-594b-90c6-f083fbec7f7f |  | note | Frequency - Prior to undertaking works
label | 08ff3c71-7e97-54e6-a02c-b84321a509cf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 2ffeec80-91ce-5734-bfb3-e917e0fdedfc |  | note | Conformance Criteria - Including despatch records
label | e264e7d2-6100-52fc-9cc3-cb98bc9edef0 |  | note | Records - Email / RFI
checkpoint-status |  |  | checkpoint | 2.8 - Concrete Mix Designs
label | 5bf1e082-03b3-54f8-bb9c-c23648b9d8a4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | bccb9bd7-8986-5933-b62b-a7fa4086ef4c |  | note | Detail - Submit all concrete mix designs, trial mixes and compliance records
label | e15e21d1-8f01-5dc9-bb65-ed2481731184 |  | note | Frequency - Three weeks prior to pouring concrete
label | 870f2ab3-65e5-51ec-a025-3e5c57bb0929 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | ed6ee4aa-207d-5089-80aa-ae565d96f511 |  | note | Conformance Criteria - Mix Design to be approved by CPS Engineer before commencing construction
label | 27f39fc2-11e8-5b6c-a248-d15782f9e153 |  | note | Records - Email / RFI
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.9 - Grout Mix Design
label | dbfdf946-e741-5486-87b3-713d360c6725 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9e3cb908-0e0e-5d4f-9fec-54a3651bf0f6 |  | note | Detail - Test to be carried out on Grout mix before it is ordered for construction
label | ebd73716-7b0c-549f-b7a3-8de72dc245f8 |  | note | Frequency - Prior to commencement
label | 3ab055a9-cc7a-5f51-82ce-1e2f3374ac18 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 578a411d-a49e-51a2-96b3-d4c0cabc96d0 |  | note | Conformance Criteria - Mix design to be approved by CPS Engineer three weeks before commencing construction
label | 701112f2-c8b4-563a-bec5-bde53c2e377b |  | note | Records - Test results to CONQA Procore
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 2.10 - Grout Mix Check - On-site
label | 3d93ec34-0a3f-5c53-975a-7397bcb06b14 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 551706f9-ddc8-5d7f-949b-1855e6adc162 |  | note | Detail - Grout checked if its free from lumps & segregation
label | c9bf6c59-423d-585e-9ea5-2b5f9eed5001 |  | note | Frequency - Prior to commencement
label | 76f3813c-e270-51ed-8c28-f57b45f45060 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
checkpoint-status |  |  | checkpoint | 2.11 - Alternative Drilling Fluid
label | a1e41f75-5129-5694-ae03-a90582771c04 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 67edb5bd-e3e5-59ac-a868-95ec24a67878 |  | note | Detail - Request for use of alternative Drilling Fluid (Section 7.5.2)
label | 87b633af-c4ad-54f7-98a0-bdd0cfcb5e74 |  | note | Frequency - Prior to Commencement
label | a2b351d7-0089-5faa-a480-b0359d12ea51 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | b0317148-c760-5e8d-ad77-fae58189b073 |  | note | Conformance Criteria - If required
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3. Soil Nails Installation
checkpoint-status |  |  | checkpoint | 3.1 - Survey Setout
label | d753f58e-b1c2-5c9e-917e-54e653901403 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b0164de0-788b-502e-96ef-b614040858eb |  | note | Detail - Arrange for a set out survey to be carried out & check against design drawings including sacrificial nails
label | dea9a925-99ce-5e82-bfd0-7b25477fdc05 |  | note | Frequency - Prior to commencement
label | f74c13f0-52d7-5455-9152-1d335708d843 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 2a59749a-dee4-54ad-bd9d-c9d91422f603 |  | note | Conformance Criteria - Consistency with Construction Drawing
label | 7b12dc5a-ff08-5c88-a7de-c08d56d3a96a |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Soil Nail Construction Methodology
label | 2fa26c26-0a90-5b55-a579-14c8f5134f6e |  | note | ACTION (Hold, Monitor, Witness) - H
label | b5ad95aa-5ead-5052-9fab-9eb85e6b10f0 |  | note | Detail - Soil Nail construction methodology plan must be submitted two weeks prior to works starting
label | 0b6737f6-73a4-53d5-9b32-e2923ed5f520 |  | note | Frequency - Prior to commencement
label | a4adf54d-c367-5eb8-96d4-cdaa8689d716 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 3d15c801-295d-5830-9615-b8a2eafb0216 |  | note | Conformance Criteria - Include sprayed concrete, grouting and tremie concrete in methodology
label | ffe7357f-b16e-57b7-bd1a-5a2778ef8c55 |  | note | Records - Methodology
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Trial installation of Sacrificial Nails
label | 51578571-b723-512a-acd8-e85deaf9e49b |  | note | ACTION (Hold, Monitor, Witness) - H
label | d1e0a6c5-3fa0-50ec-8da9-a82ed67f6c18 |  | note | Detail - Drill hole, install Bolt/Nail, install Grout. Location for Sacrificial Soil Nails to be agreed on Site with CPS Engineer.
label | 23ca16e1-bac4-565b-a54e-0f0c884b14e8 |  | note | Frequency - Test
label | cdf42f4f-6b9a-51ae-a868-bb3d194cbbca |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection/ Document Review
label | f389107f-ba77-55f0-ba5d-5b5161574923 |  | note | Conformance Criteria - Bore logs of Drilling, installation record
label | 3464434a-2773-502e-8a2c-499a301070ea |  | note | Records - Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.4 - Sacrificial Nail Testing
label | eb5f4f0a-d16a-5c40-9f8a-91632f5b803b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2539aa9b-2eb8-52d6-9f51-4d3cc60f25a6 |  | note | Detail - Test after a 7 day period. Load up to the specified requirements with the CPS Engineer overseeing proceedings
label | 6eb35d3a-1bc3-5acb-9cc4-78b694f8d263 |  | note | Frequency - Test
label | 9badf5b9-c81c-5d32-b2e3-92f95b8834ee |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection/ Document Review
label | 0d81fd0e-6b8a-569f-a6ed-d2f04144ecb1 |  | note | Conformance Criteria - Design Team to approve grout test result prior to sacrificial testing being commenced.
label | 3cbc5e8c-8505-5e79-856d-40ae1017b9be |  | note | ○ Calibration of testing equipment
label | 7728fab2-6338-541e-8116-2c3dd4b3a730 |  | note | ○ CPS Engineer to observe testing and provide feedback.
label | 12517c57-d435-5711-8e50-29a5ebbbc1a1 |  | note | Records - Instruction to proceed
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.5 - Working Bench
label | 48c68db0-ee87-5b63-b26f-bf02a9184a8f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 618cdb2e-cf4a-576b-ac4d-ce1732451376 |  | note | Detail - The construction team shall stage the excavation of the retained face such that the excavation proceeds no more than 1m below the current level of soil nails being installed or vertical spacing of the soil nails plus the required reinforcing lap or the short term stand up height of the ground, whichever is less. The construction team shall protect the face of the excavation from damage at all times.
label | a59514a2-836b-5e45-b6ef-03733fb5bfaf |  | note | Frequency - Prior to commencement
label | 490d7de9-44b1-5419-81ec-58a34275f52f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 6897087f-992e-5cea-a0c3-715579ea5701 |  | note | Conformance Criteria -
label | 2ac2e294-5691-5f7b-910a-e83f35eabc3d |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.6 - Production Nails Location
label | 3072a15e-51f6-54fb-822a-c325d206847b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7178f942-46b8-55ec-a196-18d943a7ffac |  | note | Detail - Location of all Test Nails to be agree on site (Section 7.8.1)
label | 722c34b6-7036-552e-9893-ce863953a615 |  | note | Frequency - Prior to Trial
label | 54126a1f-048e-5995-8237-3fb47f33e7e8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection
label | f15aa840-45d8-5912-911e-d9b8782fae5e |  | note | Conformance Criteria -
label | 96d47d32-4886-54d0-b858-cc55b68eb9aa |  | note | Records - Photos, Site Diary
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.7 - Production Soil Nails Bore Hole Drilling
label | 8f5b30c4-f447-5c5c-a165-49bb99296bc5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | b3d7e6b4-9503-53c4-b8e7-de36c9155057 |  | note | Detail - Drill hole
label | 4e9e0a0a-c891-58bc-bcbd-bd9537659463 |  | note | Frequency - During construction
label | faadf23e-bc09-51ff-b67e-72b8d8e20321 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | a99b4db1-9cd1-5175-bdaa-563630cb3b27 |  | note | Conformance Criteria - +/- 2 Degrees
label | ba13561f-fb30-5f6e-a593-18d1353757f2 |  | note | ○ Drill log to be submitted to CPS Engineer including the depth at which water was encountered if there was any.
label | c6e76951-9739-5009-9974-1745e7512648 |  | note | ○ Submit all installation records for each soil nail and pile.
label | 3e213ad5-9efb-51ea-ae73-00688cbbea3d |  | note | Records - Drill Logs, submission records
checkpoint-status |  |  | checkpoint | 3.8 - Bore Hole Flushing
label | b3139f5a-809e-5048-9556-805a393be159 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 45a0a594-7a69-5c1a-89cd-7b889d8cfa85 |  | note | Detail - Flush all soil nail holes with water and air after drilling to remove smear and drilling debris
label | f6df731f-6df7-5c43-8fa0-ea5a365be57d |  | note | Frequency - During Construction
label | 3e322e2e-b63f-5edb-87fd-d2b027e4424b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | e06f1abf-e983-5dee-8a86-3d5c04617bdb |  | note | Conformance Criteria -
label | 5adb451c-9325-5b19-823b-40f4841f3faa |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.9 - Soil Nails Insertion
label | 846ac870-bf89-5fff-a0c2-45bc3084410a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1efa8030-f93d-56ce-b79c-319b12cebe6f |  | note | Detail - Insert soil nails as specified
label | 56066f57-f0a8-592f-836e-bb5cd6ba398b |  | note | Frequency - During Construction
label | 4d4f4883-a5ce-5eb1-b04b-1a030f590947 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 79e71df3-89e8-51b3-88a4-af34f0132d45 |  | note | Conformance Criteria - Soil nails must be inserted into the drill hole to the required length without difficulty to prevent damage
label | 5733789b-d7d5-5500-9398-a0381e5dcea0 |  | note | Records - Subcontractor QA Records
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.10 - Soil Nail Logging
label | b6eb0ab0-0f07-5567-b71c-de347af66974 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 62b8a2b5-9098-56ff-b12f-200aa3566181 |  | note | Detail - A record is to be maintained showing the type and installation date for each soil nail
label | e790fd68-807b-55e1-9eb9-7b58f57726d9 |  | note | Frequency - During Construction
label | 20eb6728-f7d8-571b-a258-b917480c9dab |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 23b18756-5d1b-5d12-b625-d73564f3d8c0 |  | note | Conformance Criteria - Installation records shall include:
label | e7f60210-e97f-528a-9cb0-22ecd96c2a42 |  | note | – Length of bar
label | 16f0f5c9-2159-58a6-bafd-aab114062d62 |  | note | – Depth of drill hole
label | b1083823-08dd-5a71-8fa8-8e27a00b1ea6 |  | note | – Inclination/Verticality achieved
label | 00452d58-1573-51fa-8ffc-704639454240 |  | note | – Level of grout placed
label | 28f28e56-f651-5b6e-b24e-777a7ca65bf3 |  | note | – Batch numbers associated with grout placed in each hole
label | 1f8c1a8c-0d9d-5863-899f-9565858e7d98 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 3.11 - Grouting
label | 971d1ff3-a15e-5960-a9b0-c11d22581638 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0e42a7b9-c971-5e62-a447-42e878868bfb |  | note | Detail - Install Grout. Install Grout on the same day of drilling unless otherwise approved by Designer
label | 9667c879-eab6-5d77-9947-b4103c10231d |  | note | Frequency - During Construction
label | b4a87a53-a35b-5de4-9af5-269eb4224ff8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 03b24b0d-940d-5939-82b3-25d1f65883c5 |  | note | Conformance Criteria - Including:
label | 21f1b4e5-b494-5ee8-9be3-f6c9c2bc8997 |  | note | – Concrete despatch records
label | 926d95c6-2382-54da-b058-1d57b4e4bb46 |  | note | – Compression test results
label | 8a09b718-8c63-53e1-b273-d5a52f3a61d7 |  | note | – Slump and spread test reports
label | 4cdf1e0b-39ca-5ce7-b288-dab6b4b57280 |  | note | ○ Must notify CPS for any failed result and cease works until resolved
label | 58a96c0f-2d90-58e8-92f4-41234445bc60 |  | note | Records - Subcontractor QA Records and Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.12 - Grout Sampling
label | c4b1baee-e035-58cb-a86f-9566fd292ad9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 88b28117-88d8-572b-8ccc-261488567357 |  | note | Detail - Grout samples shall be taken from each batch and tested by an approved laboratory. Flow cone tests shall be undertaken for each batch
label | 0d6abb6a-6cb2-535f-b67f-2be95b0c1441 |  | note | Frequency - During Construction
label | e25aa4c9-d31d-587b-a15f-152b9c0ce2b1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 1ed66778-40bb-5197-a943-ca5eb28906dd |  | note | Conformance Criteria - Must reach specified minimum 7-day and 28-day compressive strengths
label | 1c530408-57a1-53fb-a7b6-240357c9e5f0 |  | note | Records - CONQA
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.13 - Grout Loss Recording
label | a509821e-9907-598e-b998-a2d5abfb4edc |  | note | ACTION (Hold, Monitor, Witness) - W
label | 2a6003ac-5432-5f6c-82e9-4070ba26df08 |  | note | Detail - Loss of grout shall be monitored and recorded for each hole during and immediately after grouting
label | 1011006b-1dbd-59ec-ab46-9c407f85afb9 |  | note | Frequency - During Construction
label | 01b5507f-e719-5ea9-b8ff-56fcbe6ed4f5 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | 00a16777-1259-5f46-ab1c-6083308a9239 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 3.14 - Bolts/Washer/Nuts Installation
label | 49b62731-2f5a-5c7e-8d29-a7d5371e1582 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 88bab05a-1682-52d5-844f-50aab0c8a0ce |  | note | Detail - Install Bolts/Nails washers & nuts
label | 08fb1317-f0be-5a70-9fc6-06d0c7a5aadb |  | note | Frequency - During Construction
label | 15192c38-3b9f-5807-be5e-455c0a3d404a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | f8932789-1654-5bf8-a732-f1a2194c75e4 |  | note | Conformance Criteria - All materials delivery dockets to be collected to ensure that corrosion protection materials has been delivered & installed.
label | 537be528-dc3e-55c3-a99e-d10f9365eb2b |  | note | Records - Delivery Dockets
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.15 - Testing of Soil Nails - Each Row
label | 9313176a-f7f0-5b07-a506-50b5a552a01e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 85cbe815-1f5c-5cfe-a52f-a50b8e19205d |  | note | Detail - All testing equipment must have been calibrated by an IANZ registered laboratory (or approved equivalent) within the last three months and shall be certified
label | b09e91fb-3059-54b5-9ab1-8cd311865a2f |  | note | Frequency - After Construction
label | e9de091b-dbea-5a40-a2a3-9ebd8c5b2320 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Submission
label | dbc7cd60-94f3-5630-a945-0c8b6a3bdfb6 |  | note | Conformance Criteria - Certifications of all testing equipment within the last 3 months
label | bf534be5-f59a-5206-a93a-d60d5e0aecf2 |  | note | Records - Certifications
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.16 - Testing of Soil Nails - Minimum Resting Period Before Testing
label | ef5a51a8-f266-5c07-886c-37141626b172 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 64c56c14-c982-5940-aff1-90052f72bd9c |  | note | Detail - Leave nails in an undisturbed condition until the specified 7-day grout strengths have been achieved
label | e9ac28a1-b309-5e5e-8c11-fcae26e27be2 |  | note | Frequency - After Construction
label | fe866452-51f8-5456-b826-5a8928011f14 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 7157dc27-9baf-5e28-b6fd-834eef1d9fb3 |  | note | Conformance Criteria -
label | d38ba849-051c-5f0a-b380-c6518e9a481b |  | note | Records -
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.17 - Testing of Soil Nails - Testing Specs
label | 44d3e066-d710-55a9-b81e-803ad07ec1f1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 16a3adc7-e67a-5d0c-abb9-7d5672c56c28 |  | note | Detail - Test soil nails in accordance to design specs (Section 7.6.1 and 7.6.2)
label | 9b634919-238e-59dd-be06-5e6def946b64 |  | note | Frequency - After Construction
label | 326a2581-badd-5222-914f-e2aabaa2af9f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 3b49f46e-e212-52af-af68-90c83eeb1864 |  | note | Conformance Criteria - Load testing 10% of working soil nails - CPS Engineer to witness testing & give approval to carryon with next lift of Bolts/Nails
label | 872e8e78-5a78-5763-b052-f65d54a6f036 |  | note | Records - Test results to CONQA Procore
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.18 - Final Inspection Before Next Row Commencement
label | e691dc89-f4c8-5c26-9625-aba885df213c |  | note | ACTION (Hold, Monitor, Witness) - H
label | ad83d3d6-15de-596e-a404-8ab69e46ec5f |  | note | Detail - Final inspection of CPS Engineer to give approval to remove bench and start on next rows of Bolts/Nails
label | d652fe92-5ed6-5c24-b744-6ce24b75380e |  | note | Frequency - After Construction
label | 65458c40-d98d-5906-8059-115cc9be0ef1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | eb5c5f6b-e0a9-5218-a59d-d582b1a19b81 |  | note | Conformance Criteria - CPS Engineer to give approval via a NTC
label | 54dde10a-142f-5c02-b484-51cd901e1f05 |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.19 - Subsoil Drainage
label | be85bef3-4ea9-53a3-aa5d-63ee4fdee561 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ddabe305-4ac7-5a10-b754-4622c370976e |  | note | Detail - Install subsoil drainage as required in accordance with specification
label | 226fbacc-e384-5ae8-a978-8d261c51ac13 |  | note | Frequency - During Construction
label | b4772702-3c0f-561c-9041-4b01d2bd4dcb |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 7ac86e26-4c50-5445-80b8-4b909860c95b |  | note | Conformance Criteria - As per drawing 1.5m alternate with weep holes
label | 661c65ef-ada8-55ec-8357-2c628d520f20 |  | note | Records - Photographs
checkpoint-status |  |  | checkpoint | 3.20 - Shotcreting
label | 74a9857f-3a9b-59df-989d-788ba020f6b5 |  | note | ACTION (Hold, Monitor, Witness) - W
label | e16e1d48-88df-527a-9f24-ae5a0d6c058f |  | note | Detail - Prepare shotcrete surface - Soil surface is to remain stable and in profile required until the shotcrete is applied and hardened
label | 42b2eae3-6149-5063-b873-2dfed7da7dcc |  | note | Frequency - During Construction
label | a76d8b99-3485-5abf-b4d1-1ef8f55844f2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | f8534172-df62-5b5e-8b6c-65bae83949ec |  | note | Conformance Criteria -
label | 356d6c83-811d-5f5b-b0a5-211c6a4e2137 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 3.21 - Pre-Shotcreting Inspection
label | 7a48db10-7a67-57d2-8e4a-d169c20e4c81 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8eec79dc-bc60-5954-ad9e-27f3cc2d0b37 |  | note | Detail - No concrete shall be placed until the CPS Engineer has had the opportunity to ensure the drawings and specification have been complied with . 48 Hours notice required.
label | 76d42ebb-0722-5986-85b6-8a710802f429 |  | note | Frequency - During Construction
label | c40717c4-b9d8-59b6-99ee-539d04e940cf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | e8dbc5dd-874d-5039-b542-0f4cdd7f6cd0 |  | note | Conformance Criteria - Compliance with Drawings and Specification
label | 76a8096b-2d3d-55a6-9d7b-3adf1935d226 |  | note | Records - COR/Email/Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.22 - Shotcrete Minimum Application Requirements
label | 71b37f27-6b85-59d1-8205-c44d3e139e96 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 89a294a4-fe8c-561e-a880-78dfe55feb69 |  | note | Detail - Apply shotcrete - 200mm Nominal thick (Vertical). Apply shotcrete - minimum 150mm thick and nominal 175mm (Horizontal)
label | f4ed0fbd-e3ca-532c-b593-901fcf863eb6 |  | note | Frequency - During construction
label | 9299dcf8-0131-5b77-8b1c-2476620de876 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 760ee52b-d6f9-5b2a-9aac-0c6d5dca4c57 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 3.23 - Shotcrete Compression Testing - Core Test
label | 6e3b4379-4158-513f-91eb-cfb97449348a |  | note | ACTION (Hold, Monitor, Witness) - H
label | dd3a4815-d3bf-5250-82ef-9f1a85d77d39 |  | note | Detail - Compression Testing - Coring > 20 hours after placing - 75mm minimum dimension of the cores
label | 42a46b5d-47c2-581a-acbf-70acf9e1ebd0 |  | note | Frequency - After Construction
label | c64dda76-65d4-5586-af1c-8d005f1b6533 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | d5f868c7-8d5d-53de-b221-57bda0d3e757 |  | note | Records - Test results to CONQA Procore
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.24 - Final Inspection - Each Shotcrete Soil Nails Row
label | 5ecd819a-2cbd-5c76-a9f7-2fff4b3aa892 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 362d348c-8ed6-5137-ad45-806e64006e66 |  | note | Detail - Final surface inspection - Shotcrete shall be cured for a minimum period of seven days with no cracks greater than 0.3m
label | e7d237fa-c8b0-5572-bfce-0f119e641222 |  | note | Frequency - After Construction
label | a5e1e71b-d560-5dca-8dbc-7d1860c246a8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | dfcd013d-219a-53a4-8d7e-4f0100d44d3b |  | note | Conformance Criteria - Surface Inspected by CPS Engineer & Approval given to carry on with works
label | 15bab154-a597-505d-9868-402da93032a9 |  | note | Records - Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4. As-built Requirements
checkpoint-status |  |  | checkpoint | 4.1 - Post Construction Survey
label | e46d3bff-a6e3-5b04-8f9c-d1532b548e3b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5c390b52-dc36-5733-a527-00781c506b92 |  | note | Detail - Survey final position of bolts for as-built purposes
label | de14ec71-c9c6-5baa-84a8-38560762c8d0 |  | note | Frequency - At completion of Lot
label | 3edb73c1-f5c5-5137-a094-528866d836e0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | a25a0d74-3544-56a0-8179-6752caf38ee6 |  | note | Conformance Criteria - Survey report complete and conforms to specification
label | 42079f57-929a-5146-80f1-3af65c210666 |  | note | Records - Survey receipt
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.2 - Lot Number QA File
label | cf762284-90f1-55d3-85b2-68bc08a6b75c |  | note | ACTION (Hold, Monitor, Witness) - W
label | f76a7599-5e88-5bb5-8f48-5af400f6f80e |  | note | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | 2a4285b1-ed1b-5421-ba16-3f0088095889 |  | note | Frequency - At completion of Lot
label | 5d744d6d-d487-5998-8791-0f7f6e35e2dd |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 5f268dd3-94e6-56e7-8a17-03f97026911b |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 11b3d128-8f60-5e52-9ca2-c0d453d74bf4 |  | note | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint-status |  |  | checkpoint | 4.3 - Subcontractor Quality Assurance
label | 49b012da-ea7b-58e5-ab54-17f1a2b4cf38 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1f06d587-23b2-5323-9341-696a3adb2101 |  | note | Detail - All subcontractor documentation to be included in QA file
label | bf2bffe0-6a7b-55c2-a68b-cd35c2099e71 |  | note | Frequency - At completion of Lot
label | ddb30eb5-8fa3-5b3d-8180-143ece25718d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 214c49ad-e33f-5dc8-8f2f-8bcebeb3b3d8 |  | note | Records - Subcontractor QA Records
checkpoint-status |  |  | checkpoint | 4.4 - As-built
label | 5487d1ff-7e20-558d-9f73-ad299d3fa83e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 57a2fa0a-3ef3-5d9f-94be-0baf9ee799bb |  | note | Detail - Any works outside Construction tolerance and signed off on OFI or similar. As Built by Surveyor. Red pen mark up drawings to be included in QA file
label | 11e79958-10e2-5a56-9a5d-b1873b504a4b |  | note | Frequency - During and at completion of work.
label | 8ebe550c-3665-5d22-a0e9-10ef49b29696 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey / Drawings
label | 5a219cfe-2482-5937-a9f5-ba56b157760c |  | note | Records - Survey receipts, As-built plans
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Quality Assurance deliverables
label | 5ee410a9-4d38-5745-9a75-3b4b3e47c984 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 594b8c4f-2f9d-5223-805b-79043a08846c |  | note | Detail - Red line mark up drawings to be reviewed and accepted. All NCRs and RFIs are closed and included with Handover QA file.
label | 88d40f10-4382-57a2-8803-e7811cd8f58d |  | note | Frequency - At completion of Lot
label | f4c04611-b613-53c2-b181-29035cd77a2b |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 3a51c41b-1150-51c5-8bd3-1010de8353bc |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | 59c3532b-ac1b-5880-a07d-b322cdcd286a |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 4.6 - Completion Sign Off From Fields Below
label | 1cebdb56-9a10-522b-8fb2-3e5c3059b080 |  | note | Records - Signatures
checklist-sectioned |  |  | checklist | CS-4053 - Fencing Checksheet |  |  |  |  | Yes | CS-4053 - Fencing Checksheet | fdc8f2fe-4eca-423d-85f8-79a5c4cb6589
checkpoint-group |  |  | section | DETAILS
checkpoint-no-status |  |  | checkpoint | DETAILS
text | 292f2762-7820-52a5-aa4b-eced863a55bc |  | textbox | Project No.
checkpoint-group |  |  | section | Inspection
checkpoint-status |  |  | checkpoint | Fence Height - 1200mm
text | f8755ebd-e2ed-5901-b405-ed86c2d06e26 |  | textbox | Initials - Site Engineer:
date | 4ea82b95-2102-5fed-ad63-55a1d229dedb |  | date | Date:
checkpoint-status |  |  | checkpoint | Strainers 2.4m long, 1.2m embedded, (min 1.1m)
text | 3a8c78b7-8aa0-567a-b66a-18d97124d8eb |  | textbox | Initials - Site Engineer:
date | a2921caa-49f6-57ee-8dbf-a8fa78102fec |  | date | Date:
label | b7eb0219-7d99-5402-a185-755248c6218d |  | note | Comments: Max dist between strainers 300m
checkpoint-status |  |  | checkpoint | Posts 1.8m long, 0.6m embedded
text | abf6cd27-5fbd-5e30-b5b7-db03d7ac45d0 |  | textbox | Initials - Site Engineer:
date | 429e34a2-c1b3-5f16-a3dd-a170a953dfd1 |  | date | Date:
label | f2696df4-bbcd-53bb-834d-4dc115d561a2 |  | note | Comments: Max distance between posts 5m, slope spacing as required.
checkpoint-status |  |  | checkpoint | Battens 1.14 x 50 x40
text | 667986ae-dabf-53e6-88eb-00e64850fae0 |  | textbox | Initials - Site Engineer:
date | aaf5d665-01d4-5d4e-8a38-d44c5bb5b292 |  | date | Date:
label | a39baa52-a01d-5334-bb81-2e31af5a4125 |  | note | Comments: Battens placed at not more than 1.0m intervals and stapled at each wire.
checkpoint-status |  |  | checkpoint | 9 wires 2.5mm HT
text | 52e0932e-c554-5916-9f6b-156e8ae90a34 |  | textbox | Initials - Site Engineer:
date | 45611464-b66e-563e-b53a-23c2e8c240de |  | date | Date:
label | 816d01d4-7485-566a-992d-8a94c62d897f |  | note | Comments: Bottom wire to be max 100mm from ground level
label | 38152e34-9e94-5241-a647-14be12eddaff |  | note | ○ Wires spaced at 75, 100, 100, 120, 130, 130, 150, 160, 180mm and all stapled to post/battens.
label | 13f0d5e3-7197-503e-bfdf-3b50c9c4a023 |  | note | ○ Top wire min 100mm from ground.
checkpoint-status |  |  | checkpoint | Stays
text | cb4b77e9-5636-5cc3-bcdf-ed99087a28d9 |  | textbox | Initials - Site Engineer:
date | 8d4726e5-d141-503c-9a14-d4d007c683d8 |  | date | Date:
label | b81f46ed-bab9-5a10-afeb-9a99545ee220 |  | note | Comments: Footed stays must be used on all strainers.
label | 92161d24-4f33-584e-a8f5-1e2a442c95b0 |  | note | ○ ‘Feet” also to be used on posts in the bottom of gulley’s to prevent pulling out when wire tensioned.
checkpoint-status |  |  | checkpoint | Gate min height 1.2m
text | 2e4d7643-5bf2-5a3b-86cf-1da23d5e522a |  | textbox | Initials - Site Engineer:
date | db9814fa-eb8a-5045-bb46-ed3511bc0c19 |  | date | Date:
label | 3344b8a6-5ba7-566f-9415-a2b03a57ef82 |  | note | Comments: Alloy/wooden gate new or reused. Hung correctly/does it open?
checkpoint-status |  |  | checkpoint | Is fence vertical & true to line?
text | 19e86be9-af47-5ce9-8e8e-61e1239bf022 |  | textbox | Initials - Site Engineer:
date | 84bfa725-c475-5526-a12b-38a88fba1573 |  | date | Date:
checkpoint-status |  |  | checkpoint | Fence Height 1200mm
text | 0296c3d9-6d0e-5fe4-8992-9e69e8ae88a7 |  | textbox | Initials - Site Engineer:
date | eb1410c2-e9d6-5af0-966d-4fede242cec7 |  | date | Date:
checkpoint-status |  |  | checkpoint | Strainers 2.4m long, 1.2m embedded, (min 1.1m)
text | 9cf8d53e-aa21-5cbc-a44b-da146edbb516 |  | textbox | Initials - Site Engineer:
date | 09676bcd-27ad-561b-93dd-da9c57015655 |  | date | Date:
checkpoint-status |  |  | checkpoint | The above works have been inspected and are considered compliant with the drawings, specifications and instructions
label | 9abcbdc0-3af9-57fa-8bd3-c076e236fb14 |  | note | Position: Site Engineer
text | b9687caf-accb-59cb-91e4-01782ad2cc07 |  | textbox | Site Engineer - Name:
date | f1e2868b-93fa-5cb0-b4c4-642ff7bf06ed |  | date | Site Engineer - Date:
label | 4cf9b57a-5d42-58f4-a6ce-335eb7f033b6 |  | note | Position: CPS Engineer
text | 4c204edc-b108-5909-9db2-b3e0ad8cf8e8 |  | textbox | CPS Engineer - Name:
date | a03d2479-8d4f-52b0-9449-83519408b692 |  | date | CPS Engineer - Date:
holdpoint |  |  | signoff | Sign: