## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | ITP - E3002BCD - SH05 SIP Site 8, 9, 14 - Pavement incl Culvert Extn | itp |  |  |  | Yes | ITP - E3002BCD - SH05 SIP Site 8, 9, 14 - Pavement incl Culvert Extn | 357a2c98-2397-44f3-918f-f22648e6a289
checkpoint-group |  |  | section | 1 - Survey Setout
checkpoint-status |  |  | checkpoint | Project Site reps.
text | ee1a23ab-be67-5903-bc24-e8284093dd9a |  | textbox | CPS Eng.
text | 049ae183-2464-5eab-80be-41cdf86abe99 |  | textbox | Site Engineer
text | f72edf6f-e992-5014-9b52-700cba73382c |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Survey Setout
label | 6907e981-f3b3-5827-bab9-77ccd121a351 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 2b8334d1-11ac-58c5-8b20-57a0b8522f95 |  | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
label | bba36c2d-c8a3-5c16-b107-cc15921a1105 |  | note | Frequency - Prior to commencement
label | f8cb683a-7434-525a-a342-e4901ab232ba |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | b22179ca-c017-55b4-9dd7-24efc4f2b359 |  | note | Conformance Criteria -
label | f5c7b5a5-4b4d-5aa7-a2f7-556d84dd389b |  | note | Records - Survey receipt
checkpoint-group |  |  | section | 2 - Material Compliance
checkpoint-status |  |  | checkpoint | 2.1 - Sub Base Material Compliance
label | ebd8efb4-d353-5b10-a415-30d70a4e5295 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 21e90c78-562b-55c6-bf4a-3bb6c2d9058f |  | note | Detail - Aggregate material compliance for Sub Base stockpiles
label | 0a13351e-1764-5866-bc04-9d6fc69630ad |  | note | Frequency - Prior to commencement
label | 1183c6c7-b369-5e88-a1d6-da5899e5e598 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | efbbe4f3-ad32-5fc2-99bb-2e35da8d26b4 |  | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC.
label | 5c8e147e-e426-5905-ab0a-626874e5e00e |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
checkpoint-status |  |  | checkpoint | 2.2 - Base Course Material Compliance
label | 1bde9524-8530-50fc-90d8-af8b5994a252 |  | note | ACTION (Hold, Monitor, Witness) - W
label | dc99e203-3402-54ef-bb56-2d86229a81d4 |  | note | Detail - Aggregate material compliance for Base Course stockpiles
label | d7d7d756-9a72-59d9-8ba3-010ff6234ed9 |  | note | Frequency - Prior to commencement
label | 28840db7-c199-5f5d-b0b2-3521057331a8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 18b05787-e1be-58b7-a350-fbb139dde46b |  | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
label | 67038c9e-ecd2-5fec-afbe-d066ebca4144 |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
checkpoint-status |  |  | checkpoint | 2.3 - Concrete Pipes
label | 4d67241f-c5ed-53a2-a4e1-18acd20fd265 |  | note | ACTION (Hold, Monitor, Witness) - W
label | c5a98c76-5c96-5edc-ab31-194c58f1fc6b |  | note | Detail - Specification Compliance
label | 660a25cc-4e50-5440-bf34-65c05b86383b |  | note | Frequency - Each delivery to site
label | a331b3d8-f412-54dd-8e85-4c3b3e40f4a6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
label | 800ad4b9-710d-5940-9e8f-6ef7a006cee9 |  | note | Conformance Criteria - All concrete pipes shall comply with the requirements of NZS 3107 "Precast Concrete Drainage and Pressure Pipes".
label | 40ca76c5-79e7-557e-a1d1-f17a12c297d9 |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 2.4 - Pipe Bedding Material Compliance
label | bc5fc9e6-a232-5b84-8db7-9f4cad716bea |  | note | ACTION (Hold, Monitor, Witness) - W
label | 57f53d04-c4c6-59c9-95e3-365b6143d01b |  | note | Detail - Material to meet specifications dependant on material type selected
label | f155fe0c-2397-569c-9200-ed6b6e24f2cb |  | note | Frequency - Each material used
label | 1dc122d4-ac9c-5898-b852-ac30c010fca3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | dd842495-c091-5c58-a89a-66da9e993834 |  | note | Conformance Criteria - Compliance with requirements from Specifications
label | a8e0f772-204f-5047-bb45-ec27b9531a77 |  | note | Records - Lab Test Report
checkpoint-status |  |  | checkpoint | 2.5 - Pipe Backfill Compliance
label | 7ccc4329-b0cd-5c7e-bbba-a4518ed13fad |  | note | ACTION (Hold, Monitor, Witness) - W
label | adeea588-acdb-57de-bfbf-3aa7a64df790 |  | note | Detail - Material to meet specifications dependant on material type selected
label | f98896eb-8040-5103-a973-9b5ff25ad186 |  | note | Frequency - Each material used
label | 5dd2785d-35fd-5ac8-9e73-5a7b7b33678d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | a991cb82-56e3-5e12-999f-5a6df3e5f4e0 |  | note | Conformance Criteria - Comply with grading specification
label | a95dc6db-073a-5656-bb49-c984560dd960 |  | note | Records - Lab Test Report
checkpoint-status |  |  | checkpoint | 2.6 - Chip Seal design
label | da881361-2901-555c-a6af-cba67c88ac7a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 323bd58d-ea36-5815-bdf8-dbdccce6990c |  | note | Detail - Seal design to be reviewed prior to sealing.
label | 0f7e9cd3-8a0a-5a27-b001-59458c31a94b |  | note | ○ Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer.
label | 615392c4-eee9-50f6-86bb-6060f48670e4 |  | note | Frequency - Prior to Sealing
label | 83344722-5f89-5691-9a9d-277a094dfb53 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 5f9c19e6-4abf-5689-8fbc-2749eedc9555 |  | note | Conformance Criteria - The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995.
label | 70318b24-a9d3-56a4-ad66-34295c87ab1b |  | note | Records - Emails/NTE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Sub Grade Construction
checkpoint-status |  |  | checkpoint | 3.1 - Sub Grade Strength
label | 34b8c3bb-13b6-5bac-9515-c6b4ade94668 |  | note | ACTION (Hold, Monitor, Witness) - H
label | da69e99b-3bf4-5ca0-8d1a-26d69d6d59cd |  | note | Detail - Determine Bearing strength of Sub Grade
label | 9e357a8b-19b9-55fd-b81d-4ced4050c871 |  | note | Frequency - After Dig out, every 10m
label | 93f4970c-5c09-5e0c-aa53-fd080018c69c |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 30b0ce7c-e3bc-561f-b19c-681f86fdaf5f |  | note | Conformance Criteria - Min. 2 blows /100mm, 2 blows = 4 CBR
label | 9eeb9138-e8be-590e-9511-82a7b7002369 |  | note | Records - QA measurement Sheet. CS-4000 1m Scala.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Sub Grade Proof Roll
label | 55a7bb0a-1d70-547a-be2f-8703c72bb70d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 7ee34545-49a7-5c82-bef2-5f7996d61f4b |  | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
label | 86050918-3c3e-532f-b5f3-9a15d281f9b8 |  | note | Frequency - Prior to Sub Base Construction
label | 15c9e234-33a8-509f-a88c-5965b49e85f6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 54c7e2eb-7c09-5d2d-8e07-903f0c2aefa4 |  | note | Conformance Criteria - Engineers Acceptance
label | 4b8e9266-ba67-5b15-88c7-db106add3320 |  | note | Records - Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Sub Grade Survey
label | 00f81ab3-3f89-55ba-81de-694e90ec6558 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f7d482b2-0971-57fb-b8ca-ec06cdd61474 |  | note | Detail - Survey the full subgrade surface
label | 4417f2e8-a388-5095-9faf-78fa60bf1d24 |  | note | Frequency - Prior to Sub Base Construction
label | 8f736763-3959-58bd-b856-a170c9f03740 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 9733ce04-be94-57b4-a333-406b55f51d4c |  | note | Conformance Criteria - Whole surface
label | 01bd8dfc-b632-5382-aeaa-704d0aeccc45 |  | note | Records - Survey Data
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4 - Sub Base Construction
checkpoint-status |  |  | checkpoint | 4.1 - Sub Base Aggregate Delivery Checks
label | fcccd52b-c2d2-5fa9-a164-6d7beae2587b |  | note | ACTION (Hold, Monitor, Witness) - M
label | b91806ff-95bf-5343-b542-f3b76bb3e0a8 |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | 73ef0ada-6d62-52f3-b3e9-b370f576be8b |  | note | Frequency - During construction
label | f0a65ffb-76d4-5d98-92f6-bdcd0dd4ac6d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | ab712513-94fe-505d-87ea-466f4b3907d7 |  | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification.
label | 2d4db383-bf2b-591a-acd3-ccd67953dd54 |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 4.2 - Sub Base Material Contamination Checks
label | 9e94ac90-a5f8-525b-ae85-9e4ab086159a |  | note | ACTION (Hold, Monitor, Witness) - M
label | ff395a41-f860-5016-b093-8b70bc326447 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | f307f898-4082-5d9d-b516-037341295567 |  | note | Frequency - During construction
label | acf24461-f075-5d63-a7a9-e4f5c8b650c6 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 4bab1501-73b1-506e-aff4-8bab3953d533 |  | note | Conformance Criteria -
label | c215c7cd-3c93-5869-9a9a-5a50324d2a8f |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 4.3 - Sub Base Compaction Lower
label | 99cfdeac-3783-59c7-8af0-7d0a845ca8f1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9cf1b763-3821-5cbf-8426-733672094838 |  | note | Detail - Degree of Compaction.
label | 114fdc83-400d-52a9-a65d-35dd210551e9 |  | note | ○ The subbase shall be constructed in two layers.
label | 86da690b-e12e-5158-8bee-836020efd3a4 |  | note | ○ Lower subbase results must be approved before construction of upper layer.
label | 6acc21c5-db89-5e28-9be3-d3a9019b7e77 |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | 6cb8069b-0b80-5184-93d7-68621052b413 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | 08cb37d7-910e-5bb5-8916-e1f20fa559a0 |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | d7560041-56f4-5dd0-b4e8-aed07b59816e |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Sub Base Compaction Upper
label | 49123423-1eab-5417-b67e-498db23c7fc8 |  | note | ACTION (Hold, Monitor, Witness) - H
label | e388c80e-7375-5e83-a866-29494ec011b5 |  | note | Detail - Degree of Compaction.
label | 9fdd3dac-f5df-58c0-a9d4-8730bf5f2085 |  | note | ○ The subbase shall be constructed in two layers.
label | df31a700-1e3f-521a-936c-579a2a324cc2 |  | note | ○ Upper subbase results must be approved before construction of basecourse.
label | 3cd1df53-7376-5bd5-8088-72996597522d |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | f6725cf2-608a-5390-8799-645e9121466a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | 6cb6ba5b-e564-5a8a-a4c2-56416f37a8ca |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | 43c754d0-c6af-5a75-88cc-a67a27e989bf |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Sub Base Trimmed Level Checks
label | 816ede2f-c26e-5a45-a3be-e89f59529b2b |  | note | ACTION (Hold, Monitor, Witness) - H
label | f7ab4143-2643-54c0-b193-c40e3e10f7e9 |  | note | Detail - Carry out a Level Check on the trimmed Sub base
label | f745c0d3-8812-53b3-b879-6a8671a933da |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | b8609b23-a3bf-531a-9923-ad75ef8da29d |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 30f94b38-8239-54c7-8a11-17effd63f5f7 |  | note | Conformance Criteria - TNZ B/2 Tolerance = -25mm/+5mm
label | 3ec2d75d-dc59-5a1e-a0a9-44f6091ea21b |  | note | Records - QA measurement Sheet. CS-4100a Subbase Approval.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.6 - Sub Base Survey
label | 3693b2a9-f1e2-5464-82e8-c9534560ee46 |  | note | ACTION (Hold, Monitor, Witness) - H
label | ea4aa0d3-6b07-516d-88f7-2f030bcdb19d |  | note | Detail - Survey top of Sub Base Surface
label | b64732f8-860e-5bf6-8f90-f34068ded6c7 |  | note | Frequency - Random 10 spot checks per lot prior to basecourse construction
label | 61ad312e-5f72-5e6f-80b8-63137d5c5042 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 3bd8adeb-51fe-5143-9f90-73e4b0a7552a |  | note | Conformance Criteria - TNZ B/2 Tolerance = -25mm/+5mm
label | 733a0a2e-2c97-5184-bf7b-ce0afeddf960 |  | note | Records - Survey Data
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.7 - Saw cutting
label | 26c9e0d2-86db-5302-9a18-3d34c468c9a4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1a665449-3f58-5cda-a185-f2007301ab86 |  | note | Detail - Proposed Sawcut line to be inspected by the engineer
label | af40aed8-dd44-5cfb-9648-8b531f94c633 |  | note | Frequency - During construction
label | 081862c1-4d1f-523f-aee3-83200a4f1ef9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 90725048-da7d-54a2-b687-eded22eee762 |  | note | Conformance Criteria - Project Specification 6.6
label | 5ed69861-fe04-5c37-8e96-f596e463a04a |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5 - Base Course Construction
checkpoint-status |  |  | checkpoint | 5.1 - Base Course Aggregate Delivery Checks
label | 93239102-d997-52af-87c2-409e4f2d5615 |  | note | ACTION (Hold, Monitor, Witness) - M
label | c108a4d3-b740-5129-9379-2faf6f0e6044 |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | 5bebeb0d-6485-5379-a986-b42b82fa2823 |  | note | Frequency - During construction
label | 0c398cfb-109b-5e89-88a6-3fc241144ef7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | f17e7f54-d74c-5e8d-824e-06552f8ead13 |  | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
label | bce5d683-0271-5843-b11a-981368150dea |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 5.2 - Base Course Material Contamination Checks
label | d9226edb-acc6-5df5-b17c-e18bca50cc72 |  | note | ACTION (Hold, Monitor, Witness) - M
label | d7cd23c2-5272-568f-abd1-b1ad6bdf223d |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 95e414a9-37cc-5fc1-a497-7accd078d00d |  | note | Frequency - During construction
label | 8a0399f0-a2c5-5464-8e0c-39d3ee57a7d0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 32ec1452-3e23-5dcf-87c5-194306d18f09 |  | note | Conformance Criteria -
label | a23a589e-3b67-5d70-ad50-677daef25432 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 5.3 - Base Course Compaction
label | 45e35f09-d9a1-5345-9a2b-7737fec23b2b |  | note | ACTION (Hold, Monitor, Witness) - H
label | c59db112-277d-593f-95de-2b4add7aa71d |  | note | Detail - Degree of Compaction
label | 63fd6d96-21a7-57cf-b480-88c529fa64d5 |  | note | Frequency - 5 per Lot
label | a65f56de-c045-5384-905d-cb9bf9ff9755 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | a0cbe965-c2c4-57d1-92d2-2327f6c8ebd9 |  | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | d489d04b-2db6-524f-a5c3-7fa7744f45ca |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Base Course Trimmed Level Checks
label | bb975718-5d5b-5da3-9121-7d251f72557d |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9fb63695-0f6b-5cc4-9501-992f81c93643 |  | note | Detail - Carry out a Level Check on the trimmed Basecourse
label | 76eb1149-f51a-5a50-875f-38a97516393a |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | 3d792ee5-384c-5574-b4e9-af39cd0d4dc0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | f92480b2-cfab-58a9-8021-c855602fdeeb |  | note | Conformance Criteria - Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm
label | 83f40c06-b08a-5f54-91fd-d63121416be5 |  | note | Records - QA measurement Sheet. CS-4100b Basecourse Approval.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Basecourse Survey
label | 77e0b51b-79cd-5d45-83d6-2b89aa5edd51 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 9636f020-2f7f-51e4-aa67-89577e051792 |  | note | Detail - Survey top of Basecourse Surface
label | 6326fe80-16d1-5742-871c-fed9995fd6f5 |  | note | Frequency - Random 10 spot checks per lot prior to sealing
label | d63f2498-0f53-5e3c-875c-5864ae8fe350 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 936953b8-8d56-592a-b616-8c538db255d2 |  | note | Conformance Criteria - Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm
label | 40337637-81de-5853-a2c7-c2ce357a591a |  | note | Records - Survey Data
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Base Course Surface shape check
label | 504720de-e082-5b80-be9f-a9b84b832f3c |  | note | ACTION (Hold, Monitor, Witness) - H
label | f713eaf5-b684-5659-8f88-7f693cae893c |  | note | Detail - Surface shape check
label | af385aeb-a6c7-50e0-9fae-9693fc20518b |  | note | Frequency - Prior to sealing
label | 7d7c02a1-83d9-5e13-b6c9-ebd62d5d8b55 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 7db9f6d9-c9ad-5443-a4f2-eb641424d62f |  | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | a9921015-5b82-5486-9e95-2a14045136dc |  | note | Records - QA measurement Sheet. CS-4100b Basecourse Approval.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.7 - Base Course Surface finish check
label | 04c58ee6-3c67-5700-a5d2-753edd46e395 |  | note | ACTION (Hold, Monitor, Witness) - H
label | adf9503f-020f-5704-8017-d0a16186eff4 |  | note | Detail - Surface finish check
label | 9e2a5d25-6576-519d-9e18-bf313b648f6c |  | note | Frequency - Prior to sealing
label | 9568bb22-7517-5598-9a62-058d4ac90534 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | 2cb16601-bbb5-53c7-99fb-ce05ec09bc46 |  | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | 326a59da-13e3-5202-bd0d-d62cffe1c770 |  | note | Records - Site photos, Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6 - Extension of Culvert
checkpoint-status |  |  | checkpoint | 6.1 - Foundation Compliance
label | 6e3d8503-f3d7-5e92-b182-24570e9abdc0 |  | note | ACTION (Hold, Monitor, Witness) - H
label | f730a8cd-c5f7-5257-acaf-77da46221440 |  | note | Detail - Test formation level on completion of excavation to check if undercut required
label | b8edf7f1-8201-5468-8cc1-5be4cbe7c60c |  | note | Frequency - One test per 5 linear metres
label | 3e6ae74f-2c49-51c1-9da0-f2eacfc94179 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
label | 2107d4b6-bec4-5273-b60d-152a282847ee |  | note | Conformance Criteria - Min. 2 blows /100mm, 2 blows = 4 CBR
label | 45e2ed68-c56e-5651-88dc-dbb5f0dff581 |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 - Levels Compliance
label | 0af6b545-3fb1-51ef-936a-b112510cf956 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8bd6ea7d-5026-59f9-8c4e-3376ecd2dcd1 |  | note | Detail - Inspect formation level on completion of excavation to check if further excavation is required to achieve levels
label | 7a833145-ab37-52ec-8225-02b4a262a970 |  | note | Frequency - As stated
label | 07653e10-3355-5f7f-961f-83b1d199c98f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 6c1a2400-f15f-5743-b766-ccfeb298d091 |  | note | Conformance Criteria - Designer to inspect formation level at outfalls / inlets.
label | 3aeecaad-c9d3-5361-93c1-acd0d7126130 |  | note | Records - Photos, Visual
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7 - Sealing
checkpoint-status |  |  | checkpoint | 7.1 - Location/Size Confirmation
label | 1a53d99b-6abc-54b0-98be-278a98805bfb |  | note | ACTION (Hold, Monitor, Witness) - W
label | 3b3aa8af-c6d5-5b1b-a9d3-1253faf77784 |  | note | Detail - Mark up extent of Chipseal
label | a2bb04ca-c742-542a-8a38-4aa8a834dfed |  | note | Frequency - Prior to Sealing
label | 86aa64ca-bfe7-5cc1-a6d4-76fab9bb93e7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
label | a61c251e-c9e6-5b8a-8d76-cce119f7e375 |  | note | Conformance Criteria -
label | ace594a4-41f3-5d0d-8cc3-108fb228bd7a |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 7.2 - Surface Cleanliness
label | 94dc2f32-1287-5c52-9ad4-93fbf4d3ed79 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 74fb5c53-1c3d-5cc7-8014-266c1f42dfe3 |  | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
label | e8a74dd4-f1d9-55f2-97c3-5e4ea6cc3a92 |  | note | Frequency - Prior to application of binder
label | d8d88610-966d-54c9-86e8-e3224394b90f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | 1efc0f68-e461-5e3a-abdf-0266cfa91d34 |  | note | Conformance Criteria -
label | 2e214aa0-eabb-5629-9e25-d639ddd2f464 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 7.3 - Binder Application
label | 8b149d88-bfda-54ef-9350-56f3bfbf0bba |  | note | ACTION (Hold, Monitor, Witness) - W
label | e9ea2939-76be-5e22-a5c0-e3b546648e96 |  | note | Detail - Ensure the Binder application is according to the seal design
label | a54f4f33-522d-5668-8652-a6b8b6948541 |  | note | Frequency - During sealing
label | 9416a6d7-975a-5ced-a28b-1987d8e6ad67 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | bb70fffe-cdfc-51d3-8005-efcc79819a76 |  | note | Conformance Criteria - According to seal design
label | a7d45692-cc96-5395-9b96-062f50ebb570 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 7.4 - Chip Application
label | 9b11cc38-c96f-5b81-820a-6fd289d83106 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 34287822-3160-57e5-a13c-086c78b6c6ba |  | note | Detail - Ensure the Chip application is according to the seal design
label | 8c26174c-f9e7-5b73-a7de-9b31787873cb |  | note | Frequency - During sealing
label | 917b977d-af4b-5f8e-9532-51867a8a4816 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | b39cd932-cda0-547c-818d-e4402f8b7188 |  | note | Conformance Criteria - According to seal design
label | 9d997e6a-cf1b-533d-b067-0adfb8be6be3 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 7.5 - Compaction
label | 0ce37c26-7fd3-5510-bfef-a6695b19d120 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 5c21d8be-eb8b-5cec-bcdf-616af17bc4a4 |  | note | Detail - At completion of rolling
label | 5d33128b-ed1d-50ce-9cee-f1c324ce732e |  | note | Frequency - During sealing
label | eaf77675-fe38-537e-9651-28a92e13704a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | eb38c069-4352-5aed-bd8c-a5200e78c61d |  | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | 117cd5fe-f125-5eb9-be00-f4417689bfd7 |  | note | Records - Photos, QA measurement Sheet
checkpoint-status |  |  | checkpoint | 7.6 - Removal of excess chip
label | 3eb7fa2e-9ecc-5a7c-b8c1-fcafdad81a72 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 0f4594aa-c6ff-5c06-80b4-20685bba1382 |  | note | Detail - Removal of excess chip
label | ca19b25a-171a-5945-9af1-6f9d577e7583 |  | note | Frequency - Within 48 Hours of Sealing
label | e2c0b5fe-5132-58c9-be4e-76c780bc88d0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | e513ffab-aea7-52a7-ac4b-3c33ce962f65 |  | note | Conformance Criteria - Ensure all excess chip removed from site.
label | 7ddef8d5-6a99-5935-8d50-2468de38e793 |  | note | ○ No chip windrows left on site in Shoulders.
label | f8489c8f-c44a-51c2-8b18-a6c2a6b3369c |  | note | Records - Photos, Site logs
checkpoint-status |  |  | checkpoint | 7.7 - Surface finish check
label | b670f9c0-1817-559b-8a43-de9e6ce9187c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5eb0bf35-96d0-5c78-afc1-eedca6a6e3ee |  | note | Detail - Surface finish check
label | 27f99051-be39-5355-b4f8-47691953520f |  | note | Frequency - After sealing
label | 58a7d7de-b14c-5468-baf7-d1d9ef0fc440 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | c97cf200-68f1-5972-8375-589815bea978 |  | note | Conformance Criteria - Engineers Acceptance
label | 69be2015-d683-5898-b155-d80d39dff986 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 8 - Road Marking
checkpoint-status |  |  | checkpoint | 8.1 - Road Marking Setout
label | 8c90febb-fe67-569c-aaf7-0d18a935fe36 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c59e6f5a-4c20-5526-a8a8-63cc7fef22ed |  | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
label | fcbaf42b-ac2c-5f43-8f4f-15a9e2de3f6a |  | note | Frequency - Prior to the final line marking
label | b77e6afc-d19a-59c6-8749-53289b675c20 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
label | 85afebef-a1f1-5440-a67d-aae08789d5ad |  | note | Conformance Criteria - Engineers Acceptance
label | afae688c-b8a0-575d-aae8-1718bff383ad |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 9 - Hydroseeding
checkpoint-status |  |  | checkpoint | 9.1 - Hydroseeding
label | 23ea6780-27f1-5ebb-b951-36c41bee4158 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 28d0ff9a-ac29-58c7-8dd0-82810c03e137 |  | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
label | 20b802ff-471e-5a2d-a6e2-3a7b790ea037 |  | note | Frequency - At the completion of the Lot of work
label | 89217211-9d98-5cdf-98e9-4abb1e3b7d33 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 29a7e17e-34a3-5e6f-a96b-e6ab718585c1 |  | note | Conformance Criteria - Engineers Acceptance
label | 37294cf9-d883-5ad7-99c3-0c4fb6dd1d5d |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 10 - Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 10.1 - Final Walkover (Snags)
label | f7a5fba1-11c1-58dd-a329-252c4e5e130c |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1a334285-657b-532f-a9ed-c47451c140f9 |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | 26821f9b-b139-5d3f-900c-eaa7f3c4870a |  | note | Frequency - At the completion of the Lot of work
label | e98605ec-7db6-58a6-a46b-17d2990021d8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | 71d903ea-30ab-5c66-9b0b-5d4f62041f46 |  | note | Conformance Criteria - Completed report
label | 2c2f5e2d-a027-5027-bee9-e0d130c9e075 |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.2 - Survey As-builts
label | a351bc08-4bf6-5e2e-bf81-25bc7dd27bb4 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b0766f34-2f92-50d5-be43-bba48a01b5e4 |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | 0adaced8-2375-58cd-8b7a-349a9f15a046 |  | note | ○ A survey as-built of completed work must be provided.
label | 492405e9-33c1-535c-97ae-1ea289815e18 |  | note | Frequency - At the completion of the CWP of work
label | 3f8cb4d5-c539-5703-a6c4-9e845fc893ae |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | c4106abe-74cb-558a-8d17-4c2945591979 |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | 7d238d6d-ba63-5f0a-952e-fbaf6bc5a606 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.3 - Quality Assurance Deliverables
label | 5b9d8a97-8ef0-5986-a5f5-ff14aa1d672f |  | note | ACTION (Hold, Monitor, Witness) - W
label | 70d71417-04aa-58a3-aa54-bf3a26d20794 |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | 2b92b5e5-5329-5b65-940d-2d86805f200f |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | 533af868-5e5c-5782-bc04-ef875b8c2668 |  | note | Frequency - At the completion of the CWP
label | 8bb1e7f0-e2be-55ff-9b4c-ae300e453b06 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | db3c18bf-e476-535f-8d12-320f58357966 |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | e59d771c-b02c-583d-978e-1955faae53bc |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 10.4 - Final Approvals
label | b172694f-09b0-57c4-ab3b-54fca8255ada |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4611bc21-1431-54b8-bdef-2052bd85dd23 |  | note | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
label | 1b21e170-d6ab-569b-b9e9-d05f0634a862 |  | note | Frequency - At the completion of the CWP
label | f5ee7300-606e-5f3b-bf38-b486bde184d1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 77052014-943f-5b16-a302-038a22eb059a |  | note | Conformance Criteria - Ensure all parties have signed and approved ITP
label | f33ee95f-a61b-52b9-a7dc-428266e147ce |  | note | Records - Signatures
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checklist-sectioned |  |  | checklist | ITP - E3002A - SH05 SIP Site 5a - Pavement Construction | itp |  |  |  | Yes | ITP - E3002A - SH05 SIP Site 5a - Pavement Construction | d3134165-423e-447f-83a0-9464e8829c1f
checkpoint-group |  |  | section | 1 - Survey Setout
checkpoint-status |  |  | checkpoint | Project Site reps.
text | c0515ac9-cd01-5a92-9e05-d3905d4b1ac9 |  | textbox | CPS Eng.
text | f91e604b-b660-5d16-938a-d8040501375e |  | textbox | Site Engineer
text | 5f886a28-a60c-5bb5-b2b2-332bd5d3ac62 |  | textbox | Quality Eng.
checkpoint-status |  |  | checkpoint | 1.1 - Survey Setout
label | 31691b3e-5ab0-5e74-8aba-47140c79c5f5 |  | note | ACTION (Hold, Monitor, Witness) - M
label | e5e21bc0-fc0e-5e2d-bb39-0da026cc3f13 |  | note | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
label | e5c4ab05-9dee-5b3e-ac37-dfa02a95893d |  | note | Frequency - Prior to commencement
label | cd2824ec-1240-540d-af26-be95e3031da9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | dfb80265-c343-5f26-8761-d7e58d85f6fe |  | note | Records - Survey receipt
checkpoint-group |  |  | section | 2 - Material Compliance
checkpoint-status |  |  | checkpoint | 2.1 - Sub Base Material Compliance
label | ebc9d69e-0196-5be6-a7f5-2bd39e807869 |  | note | ACTION (Hold, Monitor, Witness) - W
label | d2551835-3fe0-5e49-a8ef-dd140c31a336 |  | note | Detail - Aggregate material compliance for Sub Base stockpiles
label | ac2961bd-51a8-5eb2-8f16-2ce6dfe3d5f9 |  | note | Frequency - Prior to commencement
label | 90fa0fa8-09ca-5ae3-943f-808bbcee341e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 49cfe294-df10-5d09-9d7a-3e3524d1891f |  | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC
label | 57a69a95-ec21-5eaf-87dd-9cc8407072a6 |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
checkpoint-status |  |  | checkpoint | 2.2 - Base Course Material Compliance
label | 40999254-4b48-59e2-ae5c-e67d26f2e78b |  | note | ACTION (Hold, Monitor, Witness) - W
label | 566b2b1e-6cef-501e-ab53-70cf80e475fa |  | note | Detail - Aggregate material compliance for Base Course stockpiles
label | c7324156-c90b-5ba8-a928-b31602c71427 |  | note | Frequency - Prior to commencement
label | 6e55217c-0140-51f7-b7a7-6593375473f4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | 2976fe6a-7299-5308-b68b-707f8125fea1 |  | note | Conformance Criteria - Aggregate shall comply with TNZ M/4
label | cc3f6a50-1499-5b81-8337-aadebc01710c |  | note | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
checkpoint-status |  |  | checkpoint | 2.3 - Concrete Pipes
label | 8a644a99-5055-5fc6-b8cc-68bad78c7ead |  | note | ACTION (Hold, Monitor, Witness) - W
label | ef3bf306-aa41-51ac-a3ee-d73802ddf096 |  | note | Detail - Specification Compliance
label | 880d4e06-e386-5091-8e56-db5807498047 |  | note | Frequency - Each delivery to site
label | 015b5296-f8f3-5ca3-b97d-98c81f2045c2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
label | 6a0603e8-2868-55cc-8273-742232ac470e |  | note | Conformance Criteria - All concrete pipes shall comply with the requirements of NZS 3107 "Precast Concrete Drainage and Pressure Pipes".
label | 6492c547-d5ea-5659-b673-dbf70fc934c0 |  | note | Records - Delivery Dockets
checkpoint-status |  |  | checkpoint | 2.4 - Pipe Bedding Material Compliance
label | b202d822-6037-5396-be74-ff6f65098a2e |  | note | ACTION (Hold, Monitor, Witness) - W
label | 949e44df-b200-5477-be82-6b3ceeffe6e1 |  | note | Detail - Material to meet specifications dependant on material type selected
label | ac75e243-b1af-5159-90a8-471ceeca4930 |  | note | Frequency - Each material used
label | 9b6d4ba0-737f-582b-83af-92b5d14ab7b8 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 3bfcd1a0-30ca-5e29-858d-09a0740ebece |  | note | Conformance Criteria - Compliance with requirements from Specifications
label | f92c15c7-6e62-566b-9d4f-bf5293177e9e |  | note | Records - Lab Test Report
checkpoint-status |  |  | checkpoint | 2.5 - Pipe Backfill Compliance
label | a4edb0d5-89a7-59a0-bf37-8bc133481135 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 1091db44-008a-5719-9d8c-a72759491c0d |  | note | Detail - Material to meet specifications dependant on material type selected
label | c6d712d5-a278-5cb0-955e-3d902c053b88 |  | note | Frequency - Each material used
label | e0058b42-e656-5e94-8086-cc7ef1aef753 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | aa38a29c-67d0-573b-a271-4093fb63885d |  | note | Conformance Criteria - Comply with grading specification
label | a8842ce7-c31a-544b-8aff-ff99f47a0772 |  | note | Records - Lab Test Report
checkpoint-status |  |  | checkpoint | 2.6 - Chip Seal design
label | 7467503b-d98e-57d0-a974-b3106989e6b9 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 87557249-494b-5cf0-9000-3e1f0370774b |  | note | Detail - Seal design to be reviewed prior to sealing.
label | 206398a5-5f44-5fe8-ab41-9943f4060d11 |  | note | ○ Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer.
label | af47fc05-934e-5b83-8e01-cdc3822784ae |  | note | Frequency - Prior to Sealing
label | 20bd58c0-03d3-5526-b5e1-ae30fd1d8d5a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | 31f833ec-b415-5e1c-a3af-8c0c5ff43ebc |  | note | Conformance Criteria - The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995.
label | dc755240-c491-5a6c-85d1-3d003e07c8a7 |  | note | Records - Emails/NTE
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 3 - Sub Grade Construction
checkpoint-status |  |  | checkpoint | 3.1 - Sub Grade Strength
label | 00e2b83a-1a82-5ed5-a517-fdb04986273b |  | note | ACTION (Hold, Monitor, Witness) - H
label | b6184de0-ff22-5381-9813-d2aa2bceec41 |  | note | Detail - Determine Bearing strength of Sub Grade
label | 0632bd81-0c35-5dd6-af05-8f59f7c7d296 |  | note | Frequency - After Dig out, every 10m
label | f2ffc15a-7ca4-55ca-b46e-d69809703aa4 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | 32fefad6-72ff-5c5a-b03f-f26eb7dc6fe7 |  | note | Conformance Criteria - Min. 2 blows /100mm, 2 blows = 4 CBR
label | b852df96-5eed-5798-8990-203e6d1abaad |  | note | Records - QA measurement Sheet, CS-4000 1m Scala
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.2 - Sub Grade Proof Roll
label | d9913091-3262-5aeb-b4e3-c4eae1cc0147 |  | note | ACTION (Hold, Monitor, Witness) - H
label | b079e331-1f24-5235-9ddd-2522c0a3dbb2 |  | note | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
label | 33e5eb4a-6bc2-56a6-b0d8-d29694b5a98e |  | note | Frequency - Prior to Sub Base Construction
label | 87eaeeb6-d93d-50e6-a847-b3a8fca3bfd7 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 4fe4276f-a3c9-5def-855d-0e109cba275a |  | note | Conformance Criteria - Engineers Acceptance
label | 773a9a7f-fc94-51fb-a05c-c7294947191e |  | note | Records - Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 3.3 - Sub Grade Survey
label | f145ba22-289d-55e1-92d2-fd6fbab20f50 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a5eb5e11-d509-59e3-a83e-dd977c84e1c6 |  | note | Detail - Survey the full subgrade surface
label | 0e1fd4cf-276c-5a2e-9549-7091f70d157b |  | note | Frequency - Prior to Sub Base Construction
label | e650b860-7da3-57f2-afb4-879f13d4101f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | ec24b1fb-94ff-5c8c-8243-24ade08561db |  | note | Conformance Criteria - Whole surface
label | 71c6c9db-7e1d-5ac9-a12e-38325e91a69a |  | note | Records - Survey Data
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 4 - Sub Base Construction
checkpoint-status |  |  | checkpoint | 4.1 - Sub Base Aggregate Delivery Checks
label | e556e9e0-588b-5521-9c58-c0e5c8574547 |  | note | ACTION (Hold, Monitor, Witness) - M
label | b9bc938c-352e-545d-994a-aa4a0ccf2727 |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | 33dce71a-7146-5b4f-bf2f-84bded2cb708 |  | note | Frequency - During construction
label | b6d076c7-ac71-5305-b0e2-e024ba737dc0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | 723d4cf1-486e-5f0a-8e1d-d959aa2a92e1 |  | note | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification.
label | 367304b3-18d0-5ee8-96aa-1bc8a2baa547 |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 4.2 - Sub Base Material Contamination Checks
label | 7401305d-1756-571b-9659-7541acddf194 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 1ebfcefa-5e3b-5b70-b09b-44972bbe9356 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 93e97a9b-be79-5844-945c-14899d9d2ccb |  | note | Frequency - During construction
label | 3d9fc794-4e5a-504c-9541-7dfb64494cae |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | ed4541e7-c592-5593-a88f-3b1eb919164f |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 4.3 - Sub Base Compaction Lower
label | 02cfbfe2-669e-5e6b-a7eb-46ddba96c01a |  | note | ACTION (Hold, Monitor, Witness) - H
label | 86b4247a-d6f0-5ae4-8195-593fddcbaee7 |  | note | Detail - Degree of Compaction.
label | 88793569-0fa5-5a93-bc84-dfc952238fc0 |  | note | ○ The subbase shall be constructed in two layers.
label | a6d0092c-e350-58b4-be9e-bb8771c90023 |  | note | ○ Lower subbase results must be approved before construction of upper layer.
label | b6d6d0bf-7410-591d-a039-e99a03f257f8 |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | a8da3463-d166-5ff3-b3bd-ad7b585668d9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | 308eb868-458f-55e0-846c-dd08490c499d |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | da56c722-07fd-53ab-9054-294852f7aec0 |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.4 - Sub Base Compaction Upper
label | aec03155-5b99-5cd7-bf06-5b17f6759395 |  | note | ACTION (Hold, Monitor, Witness) - H
label | a00c1bc3-9b77-5dea-a713-7f262249ebe4 |  | note | Detail - Degree of Compaction.
label | 50ce0fc1-9bc8-55ff-bf12-f0630367ca3f |  | note | ○ The subbase shall be constructed in two layers.
label | 49c00ea8-3be4-5cb7-83a3-62479f732f5a |  | note | ○ Upper subbase results must be approved before construction of basecourse.
label | c4e06f37-a7c9-54c5-9e7f-5ecbd7a1ccc3 |  | note | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | 9b573d6c-2507-5d21-8fa8-17be22161067 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | 079793f0-1c75-5062-a9ce-8ada73718646 |  | note | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | f75f9e1d-3f5c-541c-8b7c-38ba9e703a04 |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.5 - Sub Base Trimmed Level Checks
label | 21e2c2d1-73da-5f4d-91f6-96b2c250a61e |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5a678929-b811-5ea5-ab94-8659945bac9f |  | note | Detail - Carry out a Level Check on the trimmed Sub base
label | 4b59b0b2-d3c0-5d5e-9c9b-1981fc4de32e |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | 294cc88a-3724-5e3f-a77c-7f09b22943e0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | a803e526-ba0e-5d44-bce6-3860496e2085 |  | note | Conformance Criteria - TNZ B/2 Tolerance = -25mm/+5mm
label | e29ebbc1-53b1-53e7-a94d-36256558a259 |  | note | Records - QA measurement Sheet. CS-4100a Subbase Approval.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.6 - Sub Base Survey
label | 523cfb48-e08d-5246-ab02-05fff006c9d1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 0ee95852-e174-56b4-af6a-64853065b087 |  | note | Detail - Survey top of Sub Base Surface
label | 92a805cb-a26f-5f4f-b780-796984bab36f |  | note | Frequency - Random 10 spot checks per lot prior to basecourse construction
label | 6620bd47-0411-544e-9376-c6bea7547b28 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | 43368fcb-effa-58ec-b78f-880768b0eb93 |  | note | Conformance Criteria - TNZ B/2 Tolerance = -25mm/+5mm
label | eb2a82c3-6838-577a-ac37-f971016fa659 |  | note | Records - Survey Data
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 4.7 - Saw cutting
label | 7e3c2a8a-b508-539f-ab40-c84e567d787b |  | note | ACTION (Hold, Monitor, Witness) - H
label | 67961899-296f-5e40-b36c-c84ebfcde902 |  | note | Detail - Proposed Sawcut line to be inspected by the engineer
label | 5df8fddb-301d-5f48-a828-f918889a37bb |  | note | Frequency - During construction
label | d02128f4-2d42-5666-a53e-acfa33448cbc |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | 3a2861e2-c3e4-5eb6-a4ce-2138e16bfb17 |  | note | Conformance Criteria - Project Specification 6.6
label | cf9f6146-303a-5d98-88e0-0c791291d544 |  | note | Records - Photos
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 5 - Base Course Construction
checkpoint-status |  |  | checkpoint | 5.1 - Base Course Aggregate Delivery Checks
label | fca1f198-1dd1-5492-86c7-6bfd35a6f92b |  | note | ACTION (Hold, Monitor, Witness) - M
label | dd0fa73e-0666-5fae-8327-8a6b5ddc7f6f |  | note | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | 0eb76670-151b-5110-9ba9-494562735b4f |  | note | Frequency - During construction
label | 822db8d1-8c50-581e-bcb7-f84076efab7a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | c8f1926e-d4c1-5d91-b54e-3165eb32fe2b |  | note | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
label | 2702e6dd-1149-55c5-8227-28b690169b62 |  | note | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint-status |  |  | checkpoint | 5.2 - Base Course Material Contamination Checks
label | af29ef3c-7958-5e55-945a-4e4712007468 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 384c0076-e091-5e91-9937-513e29620c54 |  | note | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | 230f181c-77b7-502f-97a7-d33543d784d5 |  | note | Frequency - During construction
label | 221dea4c-d804-538b-9803-d207afd175c0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | fd8ce33d-70ef-5db9-b2da-210867fee991 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 5.3 - Base Course Compaction
label | 6d24e34b-1d6c-5e74-8256-5b2f16a167a1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 1f1bcfe6-4459-5a3f-9103-cab743c21bfd |  | note | Detail - Degree of Compaction
label | 21d66408-1b4a-5790-a4b8-b7ee2ff1e48a |  | note | Frequency - 5 per Lot
label | 204b6922-d41b-5ef7-b20a-994f053fe962 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | c21b90b0-379b-5de3-a9cd-525662dad646 |  | note | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | cfb60a08-85b9-597c-9cf8-df510efd8225 |  | note | Records - Pavement Lab Testing Spreadsheet
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.4 - Base Course Trimmed Level Checks
label | c0c4772a-30d2-5786-8fca-fd85f543e441 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 43cf6506-dd20-58a3-844f-07e22b3df447 |  | note | Detail - Carry out a Level Check on the trimmed Basecourse
label | 266ce1da-8ffc-5517-bfa0-a4736e3ad9f8 |  | note | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | f3c05036-d375-5a1d-a39b-4bee94d66e9a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 40f17334-b05c-5b33-b680-6d62771c2fe1 |  | note | Conformance Criteria - Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm
label | 61d75327-80d4-5c7d-9de2-feb2d74a839f |  | note | Records - QA measurement Sheet. CS-4100b Basecourse Approval.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.5 - Basecourse Survey
label | c8a6999a-9894-52a8-8a8a-8e3b006443ad |  | note | ACTION (Hold, Monitor, Witness) - H
label | 5ded7299-cd63-5603-83fa-65fa643a4900 |  | note | Detail - Survey top of Basecourse Surface
label | fb7c1323-df80-5a30-80c2-f3e4ded35f71 |  | note | Frequency - Random 10 spot checks per lot prior to sealing
label | 84015079-96d4-5661-8bd0-7eae461377ca |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | ae91cb3e-5c7a-5ead-9579-f4573cdc8810 |  | note | Conformance Criteria - Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm
label | 3bca6710-c54a-5a85-b524-ead310dcbe04 |  | note | Records - Survey Data
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.6 - Base Course Surface shape check
label | 7452ba28-7890-51f0-b793-e21ce7300d37 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 2c6c357f-eb70-54ec-86aa-9fe96e38b44c |  | note | Detail - Surface shape check
label | 8eb7c2a5-4e73-5d26-a482-75d91ea2d23f |  | note | Frequency - Prior to sealing
label | 37a8d220-8ca5-5c5f-89b4-78aaa88342c0 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | 447d9740-581b-5025-bc7d-972fc9123862 |  | note | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | 0cc2441d-8198-5e92-a484-76cbadaf449c |  | note | Records - QA measurement Sheet. CS-4100b Basecourse Approval.
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 5.7 - Base Course Surface finish check
label | 5c457520-044a-5aba-9f8d-6bf68f4afdb6 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 75c03d18-11f8-54d5-888f-1fcf6e8e5ec0 |  | note | Detail - Surface finish check
label | 5e963668-0371-5671-bbbc-2ec8401f9721 |  | note | Frequency - Prior to sealing
label | 53ef57bb-689c-5327-8542-5de122bdb0c9 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | 74e6452a-a530-5265-9718-023e4474e8e4 |  | note | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | ece140f8-4d95-5689-adc4-505dee74d03f |  | note | Records - Site photos, Emails
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 6 - Extension of Culvert
checkpoint-status |  |  | checkpoint | 6.1 - Foundation Compliance
label | bff08b5f-be51-5dfb-a714-0a705e15fd78 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 11e88e2c-aa7f-5d9c-967a-14a1c93894fe |  | note | Detail - Test formation level on completion of excavation to check if undercut required
label | 8e4c7925-e38d-5832-a482-971cb78cf700 |  | note | Frequency - One test per 5 linear metres
label | 3fc2af45-db57-58b4-8e37-ebb2f4e9f1ec |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
label | 5875be77-5b92-5b31-8e60-64fb30e5dcf9 |  | note | Conformance Criteria - Min. 2 blows /100mm, 2 blows = 4 CBR
label | a1707b6b-98ec-5f6b-8846-71ee759125b4 |  | note | Records - Lab Test Report
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 6.2 - Levels Compliance
label | 540f36c9-264d-5a1a-8f60-b470dcce2151 |  | note | ACTION (Hold, Monitor, Witness) - H
label | cc6786d2-fb58-5a31-8c0f-4599f89e4414 |  | note | Detail - Inspect formation level on completion of excavation to check if further excavation is required to achieve levels
label | 30b02e5c-53ee-51b0-bbb3-89b91a9f1197 |  | note | Frequency - As stated
label | 6997ed46-3d2b-5364-be4e-41efd9f3fcc1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | b04104a4-6509-5ffb-bc06-c4e4061d5213 |  | note | Conformance Criteria - Designer to inspect formation level at outfalls / inlets.
label | 2a8125d2-8f0f-5ac6-983d-35c29748bb3a |  | note | Records - Photos, Visual
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 7 - Sealing
checkpoint-status |  |  | checkpoint | 7.1 - Location/Size Confirmation
label | 299efc87-332a-5579-b051-a6d4e622829a |  | note | ACTION (Hold, Monitor, Witness) - W
label | 668e08d4-d4e6-5a90-8d46-aa49f8b329ec |  | note | Detail - Mark up extent of Chipseal
label | 4f49f31a-d819-5eba-a856-8f78d0b85c37 |  | note | Frequency - Prior to Sealing
label | 557cc8d6-68b6-5a13-9a43-f6f9d8f9a17f |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
label | dd812849-bd3e-5a06-992e-6ca9cc78a094 |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 7.2 - Surface Cleanliness
label | 9f1e286d-2042-5951-a6bb-13cfab438b02 |  | note | ACTION (Hold, Monitor, Witness) - W
label | ad952383-30a2-5d0c-a3e7-3d1e81c1323f |  | note | Detail - To confirm that all loose material is removed from the surface and surrounding area.
label | 486c0aa5-4ec4-523f-91ed-3e46171dacb5 |  | note | Frequency - Prior to application of binder
label | f3e13543-7372-56db-80b7-06c2c68a2966 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | dff662f1-d055-58be-85f2-948851ccd28e |  | note | Records - Photos
checkpoint-status |  |  | checkpoint | 7.3 - Binder Application
label | 99925b67-5405-5791-8d8f-48c06f6f0773 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 635af93a-957c-553b-ad53-606a2e0ba855 |  | note | Detail - Ensure the Binder application is according to the seal design
label | ba1e1de6-7cfe-5ddd-a088-387529e231ba |  | note | Frequency - During sealing
label | 5c6807d8-c6d5-5cc6-88a4-e7bdb0d9e7c3 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 283f3567-800f-5eaa-9e4c-4bf175eb709f |  | note | Conformance Criteria - According to seal design
label | a05099ba-a0f8-5e56-9087-9dddb177d3a9 |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 7.4 - Chip Application
label | a1181e4d-9280-57f2-8de8-1feecab8caac |  | note | ACTION (Hold, Monitor, Witness) - W
label | f3ba3a97-8243-50dd-a275-8b03e1801cfd |  | note | Detail - Ensure the Chip application is according to the seal design
label | e56cc3fd-179c-5744-90e4-02bbeb98c416 |  | note | Frequency - During sealing
label | 04d52846-3499-58a3-aa4a-a7ac6d73e805 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | 677e396d-64af-56be-8db8-33493f60905c |  | note | Conformance Criteria - According to seal design
label | dfac4eaa-219b-5a10-8c86-96876a14d97d |  | note | Records - Sealing sheet
checkpoint-status |  |  | checkpoint | 7.5 - Compaction
label | 3a1f5f21-7699-523d-9176-f91383c2ec60 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 0a683a63-ccde-5209-91c4-0832ff144513 |  | note | Detail - At completion of rolling
label | daedaa82-33c0-5056-9c82-89d881cb1231 |  | note | Frequency - During sealing
label | 752f8153-6549-5645-97fc-64114a77cdf2 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 75f689c6-f774-5049-9a8d-0a24ed3768d2 |  | note | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | 64d3021c-54c7-51e6-8af4-22b1a5ededc2 |  | note | Records - Photos, QA measurement Sheet
checkpoint-status |  |  | checkpoint | 7.6 - Removal of excess chip
label | 4939778b-d040-58a1-aef6-e4feb9424643 |  | note | ACTION (Hold, Monitor, Witness) - M
label | 5245c22e-877f-5e32-9a53-68aac3633075 |  | note | Detail - Removal of excess chip
label | 3571a5a0-05e2-500e-b153-924767928e1b |  | note | Frequency - Within 48 Hours of Sealing
label | 10453f31-8cb6-5f76-b40a-3c3891ac4598 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | f94b027a-2d99-50a2-897b-bb69cb034374 |  | note | Conformance Criteria - Ensure all excess chip removed from site.
label | db556e63-31dd-55a2-b26d-cb2fc322123d |  | note | ○ No chip windrows left on site in Shoulders.
label | 0ffd4905-0be0-53a4-9202-eb0ece7f4c0e |  | note | Records - Photos, Site logs
checkpoint-status |  |  | checkpoint | 7.7 - Surface finish check
label | fa01dc67-5469-57b7-93da-b123a41d93ee |  | note | ACTION (Hold, Monitor, Witness) - H
label | 4673f079-fd9c-515d-a5eb-f8c7136b0de7 |  | note | Detail - Surface finish check
label | e96c0cb2-3e1f-55c0-b424-d588f82f0250 |  | note | Frequency - After sealing
label | 90be8435-33df-569d-934a-b9ee6f2e5883 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | 9a12d256-3346-570e-853a-d398883b57ec |  | note | Conformance Criteria - Engineers Acceptance
label | b49f131e-cd42-5559-abbc-1e2854645486 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 8 - Road Marking
checkpoint-status |  |  | checkpoint | 8.1 - Road Marking Setout
label | a6e5f3e8-1e71-5699-a8a1-85764320d781 |  | note | ACTION (Hold, Monitor, Witness) - H
label | c3a149f6-0f60-521f-a286-74633e9e853a |  | note | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
label | c1bda6b7-2a67-5edf-a24b-36d313097d7c |  | note | Frequency - Prior to the final line marking
label | e636f903-6a2b-55d5-a31b-9de439f8e40a |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
label | b9106f7e-e093-5674-a589-c9405247e346 |  | note | Conformance Criteria - Engineers Acceptance
label | f8c7591c-4529-527d-bc88-34b0fd5fb162 |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 9 - Hydroseeding
checkpoint-status |  |  | checkpoint | 9.1 - Hydroseeding
label | 0afdfca5-6835-5361-8881-aa8271ad7805 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 31060b99-997f-552c-8f7c-03bb68f20f16 |  | note | Detail - Engineer to inspect and confirm satisfactory cover achieved
label | b6512bec-3bfb-5f7c-872e-3ea6714cda69 |  | note | Frequency - At the completion of the Lot of work
label | 5a13e2e4-096e-5535-b788-ad934ba47dbf |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | cdeff05b-5d19-5f3a-b779-920504b6a6cf |  | note | Conformance Criteria - Engineers Acceptance
label | 535b567e-5bb6-5e5a-a8df-25f962985b6c |  | note | Records - Photos Email
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-group |  |  | section | 10 - Post-Construction Closeout
checkpoint-status |  |  | checkpoint | 10.1 - Final Walkover (Snags)
label | 2e3f7f01-5c03-5408-bf66-8f82e20c5ea1 |  | note | ACTION (Hold, Monitor, Witness) - H
label | 8bc36f1d-4b9b-570e-995c-cf02828832f5 |  | note | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | 5bde4e6c-d9d5-5772-88b6-f62a76fb052b |  | note | Frequency - At the completion of the Lot of work
label | 47520585-f5d9-5a7f-a53c-5b84be71a15e |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | 8e246fc9-f2af-5851-97a6-53c95183eaca |  | note | Conformance Criteria - Completed report
label | 45325b4e-2cbb-5005-b7de-8150fbeeb743 |  | note | Records - Snag List signed by attendees
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.2 - Survey As-builts
label | d97d78a8-d187-5418-a885-c6ad93f93d0f |  | note | ACTION (Hold, Monitor, Witness) - H
label | 838e0cd9-52c3-52bd-b81b-10484900dd7f |  | note | Detail - Red pen mark-up drawings are to be included in the QA file.
label | 85147e2d-3685-5791-ba07-d6d63ff99b21 |  | note | ○ A survey as-built of completed work must be provided
label | 14ac0ad3-35f3-57ce-8beb-b681ffc55519 |  | note | Frequency - At the completion of the CWP of work
label | d5e15747-0744-5b90-9292-79c57b5a4223 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | 8880a717-c1de-54c4-891c-209f0127659d |  | note | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | 9828de73-baa2-50fd-9e14-0e312c061c81 |  | note | Records - As-built Drawings. Redline Markups
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT
checkpoint-status |  |  | checkpoint | 10.3 - Quality Assurance Deliverables
label | 168392f9-039b-5b8d-ae87-43eeff61e917 |  | note | ACTION (Hold, Monitor, Witness) - W
label | 87dddae0-06f4-5b12-b4b5-06b8ddbc4fd9 |  | note | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | 763f6ec9-5ba4-5076-b6b5-2ffa46fa8614 |  | note | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | 978a4276-febf-51ec-ad0b-a47fa479cc8c |  | note | Frequency - At the completion of the CWP
label | c7cf75e2-168e-5831-ae2e-d22832559bda |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | 7de4c597-67ec-5944-9311-21d1fda21aad |  | note | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | f4d8f68a-cc04-539b-abbb-6ca38cd8e5cc |  | note | Records - As-builts, NCR's and RFI's
checkpoint-status |  |  | checkpoint | 10.4 - Final Approvals
label | cf7432c4-8cd0-5ced-a533-2437d419665c |  | note | ACTION (Hold, Monitor, Witness) - H
label | e9ddb9d4-a71b-5cae-b4e4-a3a7d612679c |  | note | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
label | fcb92487-30a1-52dc-b826-e92cf90afabd |  | note | Frequency - At the completion of the CWP
label | bf65e1f8-a343-5cbf-9195-f944fc1c74b1 |  | note | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | dcba420f-f3db-5f49-b089-325a08e8ce57 |  | note | Conformance Criteria - Ensure all parties have signed and approved ITP
label | e8bd3cf7-6109-5ef4-a0fc-01e17cc7cc6a |  | note | Records - Signatures
holdpoint |  |  | signoff | AUTHORITY HOLDPOINT