## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - E3002BCD - SH05 SIP Site 8, 9, 14 - Pavement incl Culvert Extn | itp |  |  |  |  | ITP - E3002BCD - SH05 SIP Site 8, 9, 14 - Pavement incl Culvert Extn
section | 1 - Survey Setout
checkpoint | Project Site reps.
textbox | CPS Eng.
textbox | Site Engineer
textbox | Quality Eng.
checkpoint | 1.1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Set out pegs installed every 20m if no grader control or 100m if grader control is used during Subgrade Construction
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria -
label | Records - Survey receipt
section | 2 - Material Compliance
checkpoint | 2.1 - Sub Base Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Aggregate material compliance for Sub Base stockpiles
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification Lab test for MDD at OWC.
label | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
checkpoint | 2.2 - Base Course Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Aggregate material compliance for Base Course stockpiles
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - Aggregate shall comply with TNZ M/4
label | Records - Notice to Supplier and Lab Test results for the stockpiles used during construction
checkpoint | 2.3 - Concrete Pipes
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Specification Compliance
label | Frequency - Each delivery to site
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Certification
label | Conformance Criteria - All concrete pipes shall comply with the requirements of NZS 3107 "Precast Concrete Drainage and Pressure Pipes".
label | Records - Delivery Dockets
checkpoint | 2.4 - Pipe Bedding Material Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Compliance with requirements from Specifications
label | Records - Lab Test Report
checkpoint | 2.5 - Pipe Backfill Compliance
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Comply with grading specification
label | Records - Lab Test Report
checkpoint | 2.6 - Chip Seal design
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Seal design to be reviewed prior to sealing.
label | ○ Approval to commence will not be given until evidence of a valid certificate of compliance with BCA E/2 (1992 Provisional), together with approved operating instructions for each particular distributor to be used in the work, is supplied to the CPS Engineer.
label | Frequency - Prior to Sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Review
label | Conformance Criteria - The Contractor shall ensure that all materials comply with TNZ M/1: 2011, M/06S and M/06C: 2011 (and Napier addendum) and M/13: 1995.
label | Records - Emails/NTE
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Sub Grade Construction
checkpoint | 3.1 - Sub Grade Strength
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Determine Bearing strength of Sub Grade
label | Frequency - After Dig out, every 10m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Testing
label | Conformance Criteria - Min. 2 blows /100mm, 2 blows = 4 CBR
label | Records - QA measurement Sheet. CS-4000 1m Scala.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Sub Grade Proof Roll
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Site Engineer and CPS Engineer to undertake a Proof Roll test on the trimmed subgrade prior to Sub base placement
label | Frequency - Prior to Sub Base Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Engineers Acceptance
label | Records - Emails
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.3 - Sub Grade Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Survey the full subgrade surface
label | Frequency - Prior to Sub Base Construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Whole surface
label | Records - Survey Data
holdpoint | AUTHORITY HOLDPOINT
section | 4 - Sub Base Construction
checkpoint | 4.1 - Sub Base Aggregate Delivery Checks
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | Conformance Criteria - Comply with TNZ M/3 Specification. NZTA B/2 Specification.
label | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint | 4.2 - Sub Base Material Contamination Checks
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria -
label | Records - Photos
checkpoint | 4.3 - Sub Base Compaction Lower
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Degree of Compaction.
label | ○ The subbase shall be constructed in two layers.
label | ○ Lower subbase results must be approved before construction of upper layer.
label | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | Records - Pavement Lab Testing Spreadsheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.4 - Sub Base Compaction Upper
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Degree of Compaction.
label | ○ The subbase shall be constructed in two layers.
label | ○ Upper subbase results must be approved before construction of basecourse.
label | Frequency - Maximum of 20m intervals, with test locations at each interval are to be varied across the new pavement area.
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Testing
label | Conformance Criteria - Avg. >= 95% MDD and Min. >= 92% MDD
label | Records - Pavement Lab Testing Spreadsheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.5 - Sub Base Trimmed Level Checks
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Carry out a Level Check on the trimmed Sub base
label | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - TNZ B/2 Tolerance = -25mm/+5mm
label | Records - QA measurement Sheet. CS-4100a Subbase Approval.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.6 - Sub Base Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Survey top of Sub Base Surface
label | Frequency - Random 10 spot checks per lot prior to basecourse construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - TNZ B/2 Tolerance = -25mm/+5mm
label | Records - Survey Data
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.7 - Saw cutting
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Proposed Sawcut line to be inspected by the engineer
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Project Specification 6.6
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
section | 5 - Base Course Construction
checkpoint | 5.1 - Base Course Aggregate Delivery Checks
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - All aggregate loads coming to site to have delivery dockets checked to ensure material is coming from the correct stockpile. Site Engineer to keep a running tally of material delivered to site and docket number
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement and recording
label | Conformance Criteria - Comply with TNZ M/4 Specification. Traceability of all materials delivered to site
label | Records - Delivery Dockets, Aggregate Deliveries Register
checkpoint | 5.2 - Base Course Material Contamination Checks
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Material is spread from truck & trailers and any contamination is removed or loads are to be rejected if material is non compliant
label | Frequency - During construction
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria -
label | Records - Photos
checkpoint | 5.3 - Base Course Compaction
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Degree of Compaction
label | Frequency - 5 per Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - NDM Lab Testing
label | Conformance Criteria - Avg. >= 98% MDD and Min. >= 95% MDD
label | Records - Pavement Lab Testing Spreadsheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.4 - Base Course Trimmed Level Checks
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Carry out a Level Check on the trimmed Basecourse
label | Frequency - 1/100m if machine control is used or 1/20m if no machine control
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm
label | Records - QA measurement Sheet. CS-4100b Basecourse Approval.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.5 - Basecourse Survey
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Survey top of Basecourse Surface
label | Frequency - Random 10 spot checks per lot prior to sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Tolerance = -5mm/+15mm if constrained (kerb) Tolerance = -5mm/+5mm
label | Records - Survey Data
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.6 - Base Course Surface shape check
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface shape check
label | Frequency - Prior to sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Conformance Criteria - No point of the surface shall vary more than 10mm over a 3m long straight edge
label | Records - QA measurement Sheet. CS-4100b Basecourse Approval.
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5.7 - Base Course Surface finish check
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface finish check
label | Frequency - Prior to sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection by CPS Engineer after site sweeping
label | Conformance Criteria - The large and small aggregates are held in place and the matrix does not displace under normal trafficking or sweeping
label | Records - Site photos, Emails
holdpoint | AUTHORITY HOLDPOINT
section | 6 - Extension of Culvert
checkpoint | 6.1 - Foundation Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test formation level on completion of excavation to check if undercut required
label | Frequency - One test per 5 linear metres
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Scala Penetrometer
label | Conformance Criteria - Min. 2 blows /100mm, 2 blows = 4 CBR
label | Records - Lab Test Report
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6.2 - Levels Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspect formation level on completion of excavation to check if further excavation is required to achieve levels
label | Frequency - As stated
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Designer to inspect formation level at outfalls / inlets.
label | Records - Photos, Visual
holdpoint | AUTHORITY HOLDPOINT
section | 7 - Sealing
checkpoint | 7.1 - Location/Size Confirmation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Mark up extent of Chipseal
label | Frequency - Prior to Sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
label | Conformance Criteria -
label | Records - Photos
checkpoint | 7.2 - Surface Cleanliness
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - To confirm that all loose material is removed from the surface and surrounding area.
label | Frequency - Prior to application of binder
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria -
label | Records - Photos
checkpoint | 7.3 - Binder Application
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure the Binder application is according to the seal design
label | Frequency - During sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - According to seal design
label | Records - Sealing sheet
checkpoint | 7.4 - Chip Application
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure the Chip application is according to the seal design
label | Frequency - During sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measure
label | Conformance Criteria - According to seal design
label | Records - Sealing sheet
checkpoint | 7.5 - Compaction
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - At completion of rolling
label | Frequency - During sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | Records - Photos, QA measurement Sheet
checkpoint | 7.6 - Removal of excess chip
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Removal of excess chip
label | Frequency - Within 48 Hours of Sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Ensure all excess chip removed from site.
label | ○ No chip windrows left on site in Shoulders.
label | Records - Photos, Site logs
checkpoint | 7.7 - Surface finish check
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Surface finish check
label | Frequency - After sealing
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Engineers Acceptance
label | Records - Photos Email
holdpoint | AUTHORITY HOLDPOINT
section | 8 - Road Marking
checkpoint | 8.1 - Road Marking Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The engineer is to be given the opportunity to inspect the proposed location & type of markings
label | Frequency - Prior to the final line marking
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Mark out
label | Conformance Criteria - Engineers Acceptance
label | Records - Photos Email
holdpoint | AUTHORITY HOLDPOINT
section | 9 - Hydroseeding
checkpoint | 9.1 - Hydroseeding
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Engineer to inspect and confirm satisfactory cover achieved
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Conformance Criteria - Engineers Acceptance
label | Records - Photos Email
holdpoint | AUTHORITY HOLDPOINT
section | 10 - Post-Construction Closeout
checkpoint | 10.1 - Final Walkover (Snags)
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - The final walkover must be scheduled at least one week before the site's completion or demobilisation.
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Walkover must be attended by Handover, Quality, CPS & Construction (other parties might be invited e.g. Resource consent close out)
label | Conformance Criteria - Completed report
label | Records - Snag List signed by attendees
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.2 - Survey As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark-up drawings are to be included in the QA file.
label | ○ A survey as-built of completed work must be provided.
label | Frequency - At the completion of the CWP of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings, Survey as-built
label | Conformance Criteria - All RFI, NCRs and site changes must be recorded. Signed and dated.
label | Records - As-built Drawings. Redline Markups
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.3 - Quality Assurance Deliverables
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Redline mark-up drawings are to be reviewed and accepted by CPS.
label | ○ All NCRs and RFIs are closed and included with the Handover QA file.
label | Frequency - At the completion of the CWP
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into ConQA / Procore
label | Records - As-builts, NCR's and RFI's
checkpoint | 10.4 - Final Approvals
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Signoffs by Project Manager, Quality Manager and CPS Manager
label | Frequency - At the completion of the CWP
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all parties have signed and approved ITP
label | Records - Signatures
holdpoint | AUTHORITY HOLDPOINT