## Table 1
HAND OVER DOCUMENT ITR
STEP 1 | Project: Contract Number: Drawing : | NFH Building: Level: Zone: |  | A or B |  |  | Checklist Number: Date:
STEP 2 | DOCUMENT | ITEMS/ACTIVITIES TO BE VERIFIED |  |  | SIGNED | YES | NO | N/A | COMMENTS
| 1 | PRIOR TRADES
All Prior Trades completed (kickers, cutouts etc, Plaster quality check
AS1884 Level Areas Identified - Out of Tolerance Slab Rectification Works Report
|  | INSTRUCTION TO PROCEED |  |  | DATE:
| 2 | FLOOR PREPARATION AND SCREEDING
Check MAPEI Short form Specification details
Assessment of ventilation required; Assessment of barricades required; Assessment of door and fire seal requirements
Grading layout approved If bulk screeding to falls in wet areas
DRY AREAS
Light Diamond Grind, Vacuum , Apply ECO PRIMER T; Repeat clean and primer process
Complete out of Tolerance Slab Rectification.
Complete 3mm ULTRAPLAN Topping Screed
WET AREAS
Light Diamond Grind, Vacuum , Apply ECO PRIMER T; Repeat clean and primer process
| Pre-Tanking below | Ensure the surface is free of all dirt, loose particle and other surface contaminants; Ensure that screeds/toppings have cured as per manufacturers specifications; Materials Delivery / Batches; Apply PRIMER T to all surfaces to be treated with waterproof membraneApply MAPEGUM WPS or MAPEI AQUADEFENSE membrane to all surfaces by brush or roller to achieve a wet film thickness of no less than 1.0mm; Allow to cure hard (approx. 4hrs) and apply a second coat to achieve a wet film thickness of not less than 1.0mm
Apply ECO PRIMER T Apply UC Leveller and aggregate bulk fill (or TOPCHEM PRONTO to required thickness. NIVORAPID for additional grading
|  | INSTRUCTION TO PROCEED |  |  | DATE:
| 3 | TANKING AND WATERPROOFING
Check MAPEI Short form Specification details
Ensure the surface is free of all dirt, loose particle and other surface contaminants; Ensure that screeds/toppings have cured as per manufacturers specifications; Materials Delivery / Batches; Apply PRIMER T to all surfaces to be treated with waterproof membrane;L to joins in first coat; Apply MAPEGUM WPS or MAPEI AQUADEFENSE membrane to all surfaces by brush or roller to achieve a wet film thickness of no less than 1.0mm; Allow to cure hard (approx. 4hrs) and apply a second coat to achieve a wet film thickness of not less than 1.0mm
Apply ECO PRIMER T and LATEX PLAN Top Coat
Provide flood test report — 1 per Zone per Level
|  | INSTRUCTION TO PROCEED |  |  | DATE:
| 4 | VINYL INSTALLATION
Specification Materials and Final Layout Checks
Current Plan and Elevation in use
Trims, Angles and Expansion Joints, Door Seals; Material Selection; Colour Selection; 150mm High Coving and Extent; Seam Layout to approved methods; Feature Layout; Wallsheet Extent & Layout; Hose Reel Cupboards; Adhesive Selections
Install wall and floor vinyl to manufacturers installation methods and specifications
HAND OVER DOCUMENT ITR
STEP 1 | Project: Contract Number: Drawing : | NFH | Building: A or B Level: Zone: |  |  | Checklist Number: Date:
Ensure the surface is free of all dirt, loose particle and other surface contaminants - vacuum only; Clean and patch using Planiprep SC to 3mm ULTRAPLAN topping; Final visual check of floor preparation; Saw cut and PU 45 Caulk Slab Pour Joints for PVC Expansion Strips; Check Door Clearances and Fire Seals
Hot Weld and Trim
Clean area and defect free
Protection Installed works with recommend protection , Tape all joins
Monthly Manufacturer report (Supplier)
|  | INSTRUCTION TO PROCEED |  |  | DATE:
We hereby give notice 24/48 hours we shall be ready for the final joint inspection on:
| DATE: | TIME: |  |  |  | NAME:
STEP 3 | SIGN AND PROCEED TO THE NEXT STAGE OF WORKS Any inspections conducted / acknowledged by Builder for any works on this form does not relieve Floor91 or any of their Sub-contractors from compliance to the Contract Documents & Specifications
| SUBCONTRACTOR NAME | ENGINEER / SUPERVISOR NAME |  |  |  | OTHERS / CLIENT (Where Required) NAME
| SIGNED DATE | SIGNED DATE |  |  |  | SIGNED DATE
Photo
Photo
Photo for ECO PRIMER & Final Photo
Photo
Photo (Start & Finish)
Photo