## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | Handover Document ITR - Rev 1 | [5 empty] | Handover Document ITR - Rev 1
section | 001 - PRIOR TRADES
checkpoint | All Prior Trades completed (kickers, cutouts etc, Plaster quality check
checkpoint | AS1884 Level Areas Identified - Out of Tolerance Slab Rectification Works Report
checkpoint-no-status | INSTRUCTION TO PROCEED
date | DATE:
section | 002 - FLOOR PREPARATION AND SCREEDING
checkpoint | Check MAPEI Short form Specification details
checkpoint | Assessment of ventilation required; Assessment of barricades required; Assessment of door and fire seal requirements
checkpoint | Grading layout approved If bulk screeding to falls in wet areas
section | 002 - FLOOR PREPARATION AND SCREEDING (DRY AREAS)
checkpoint | Light Diamond Grind, Vacuum , Apply ECO PRIMER T; Repeat clean and primer process
checkpoint | Complete out of Tolerance Slab Rectification.
checkpoint | Complete 3mm ULTRAPLAN Topping Screed
section | 002 - FLOOR PREPARATION AND SCREEDING (WET AREAS)
checkpoint | Light Diamond Grind, Vacuum , Apply ECO PRIMER T; Repeat clean and primer process
section | Pre-Tanking below
checkpoint | Ensure the surface is free of all dirt, loose particle and other surface contaminants;
label | ○ Ensure that screeds/toppings have cured as per manufacturers specifications;
label | ○ Materials Delivery / Batches;
label | ○ Apply PRIMER T to all surfaces to be treated with waterproof membrane
label | ○ Apply MAPEGUM WPS or MAPEI
label | ○ AQUADEFENSE membrane to all surfaces by brush or roller to achieve a wet film thickness of no less than 1.0mm; Allow to cure hard (approx. 4hrs) and apply a second coat to achieve a wet film thickness of not less than 1.0mm
checkpoint | Apply ECO PRIMER T Apply UC Leveller and aggregate bulk fill (or TOPCHEM PRONTO to required thickness. NIVORAPID for additional grading.
checkpoint-no-status | INSTRUCTION TO PROCEED
date | DATE:
section | 003 - TANKING AND WATERPROOFING
checkpoint | Check MAPEI Short form Specification details
checkpoint | Ensure the surface is free of all dirt, loose particle and other surface contaminants; Ensure that screeds/toppings have cured as per manufacturers specifications;
label | ○ Materials Delivery / Batches;
label | ○ Apply PRIMER T to all surfaces to be treated with waterproof membrane;
label | ○ L to joins in first coat;
label | ○ Apply MAPEGUM WPS or MAPEI AQUADEFENSE membrane to all surfaces by brush or roller to achieve a wet film thickness of no less than 1.0mm;
label | ○ Allow to cure hard (approx. 4hrs) and apply a second coat to achieve a wet film thickness of not less than 1.0mm
checkpoint | Apply ECO PRIMER T and LATEX PLAN Top Coat
checkpoint | Provide flood test report - 1 per Zone per Level
checkpoint-no-status | INSTRUCTION TO PROCEED
date | DATE:
section | 004 - VINYL INSTALLATION
checkpoint | Specification Materials and Final Layout Checks
checkpoint | Current Plan and Elevation in use
checkpoint | Trims, Angles and Expansion Joints, Door Seals; Material Selection; Colour Selection; 150mm High Coving and Extent; Seam Layout to approved methods; Feature Layout; Wallsheet Extent & Layout; Hose Reel Cupboards; Adhesive Selections
checkpoint | Install wall and floor vinyl to manufacturers installation methods and specifications
checkpoint | Ensure the surface is free of all dirt, loose particle and other surface contaminants - vacuum only; Clean and patch using Planiprep SC to 3mm ULTRAPLAN topping; Final visual check of floor preparation; Saw cut and PU 45 Caulk Slab Pour Joints for PVC Expansion Strips; Check Door Clearances and Fire Seals
checkpoint | Hot Weld and Trim
checkpoint | Clean area and defect free
checkpoint | Protection Installed works with recommend protection , Tape all joins
checkpoint | Monthly Manufacturer report (Supplier)
checkpoint-no-status | INSTRUCTION TO PROCEED
date | DATE:
section | SIGN AND PROCEED TO THE NEXT STAGE OF WORKS
checkpoint | SIGN & PROCEED TO THE NEXT STAGE OF WORKS
label | We hereby give notice 24/48 hours we shall be ready for the final joint inspection on:
date | DATE:
textbox | TIME:
textbox | NAME:
label | Any inspections conducted / acknowledged by Builder for any works on this form does not relieve Floor91 or any of their Sub-contractors from compliance to the Contract Documents & Specifications
textbox | SUBCONTRACTOR - Name:
date | SUBCONTRACTOR - Date:
textbox | ENGINEER / SUPERVISOR - Name:
date | ENGINEER / SUPERVISOR - Date:
textbox | OTHERS / CLIENT (Where Required) - Name:
date | OTHERS / CLIENT (Where Required) - Date:
holdpoint | Sign ITR