## Table 1
160 Gordon St
Footscray, Victoria 3011
4 - Irrigation
Name |  | Plan Manager |  | Location
Irrigation |  | Brad Ockwell |  | PROJECT WIDE
Description
This Inspection and Test Plan (ITP) is crafted to guide the installation of irrigation plumbing throughout a building and extending to garden beds/planters. It ensures all stages, from design to commissioning, adhere to quality standards and regulatory requirements. The plan includes critical hold points for inspections and testing, assigns responsible parties, and outlines verification methods. Aimed at achieving a high-performance irrigation system, this ITP emphasizes compliance, efficiency, and safety throughout the installation process.
Note: Hold/Witness points are specific to each project and to be specified prior to works commencing. Works are not to proceed past Hold/Witness points until signed off
Attachments
Plan Approver Signatures
Completed Plan Receiver Signatures
PRELIMINARY APPROVALS
# | Activity Title |  | References |  | Assignees and Verification Method | Records
1 | Design Review and Approval Internal - Hold Point
Acceptance Criteria Irrigation design drawing has been approved - ensure design meets plumbing requirements and is suitable for intended irrigation needs. Review by licensed plumber and sign off by client.
2 | Material Review and Approval Internal - Hold Point
Acceptance Criteria Irrigation material samples and material types have been approved
# | Activity Title |  | References |  | Assignees and Verification Method | Records
3 | Coordination and Permit Acquisition for Internal - Hold Point Live Area Work
Acceptance Criteria All necessary permits for work within live areas obtained. Compliance with zoning and site work plans documented through coordination efforts.
MATERIAL INSPECTION
# | Activity Title |  | References |  | Assignees and Verification Method | Records
1 | Inspection of Delivered Materials Internal - Surveillance
Acceptance Criteria Upon delivery of piping, fittings, valves, and other materials. Check for damage, ensure specifications (size, material type) match the project requirements, and materials meet approvals.
PENETRATIONS
# | Activity Title |  | References |  | Assignees and Verification Method | Records
1 | Review of Scanning Reports for Area Penetration |  | Internal - Surveillance
Acceptance Criteria Scanning reports for areas to be penetrated are reviewed to ensure avoidance of existing services and structural elements.
2 | Engineering Approval |  | Internal - Hold Point
Acceptance Criteria Obtain approval from a licensed engineer for all proposed penetrations, ensuring they do not compromise structural integrity or interfere with other building services.
3 | Penetration Execution (Peno) |  | Internal - Surveillance
Acceptance Criteria Proceed with penetrations only after engineering approval and successful scanning.
4 | Waterproofing Coordination |  | Internal - Surveillance
Acceptance Criteria Verify waterproofing has been completed by the designated contractor and ensure its integration with our scope of work is documented.
IRRIGATION INSTALLATION
# | Activity Title |  | References |  | Assignees and Verification Method | Records
1 | Rough-In Plumbing Installation |  | Internal - Hold Point
Acceptance Criteria Poly pipework for water points is installed according to approved design, securely and correctly. Installation is visually inspected and approved by site plumber.
2 | Vertical Cabling for Irrigation Control |  | Internal - Surveillance
Acceptance Criteria Ensure vertical cabling to centralized controllers is installed using scissor lifts or similar equipment under strict safety controls, with all installations matching the design.
3 | Dripline Irrigation System Installation |  | Internal - Surveillance
Acceptance Criteria Dripline system is installed as per design, with secure placement and proper connection to water sources. System passes visual inspection, ensuring it's ready for testing.
4 | System Testing and Commissioning |  | Internal - Hold Point
Acceptance Criteria The irrigation system undergoes pressure testing for leaks and functional testing of automation. Testing results meet project standards, ensuring system is operational and effective.
HANDOVER
# | Activity Title |  | References |  | Assignees and Verification Method | Records
1 | ITP and Handover Approval Client - Surveillance Internal - Surveillance
Acceptance Criteria ITP reviewed with client, all sections signed off.