## Table 1
160 Gordon St
Footscray, Victoria 3011
1 - Soft Landscaping
Name |  | Plan Manager |  | Location
Soft Landscaping |  | Brad Ockwell |  | PROJECT WIDE
Description
This Inspection and Test Plan (ITP) guides soft landscaping activities, emphasizing quality and project compliance from initial plan approval to handover. It details critical hold and witness points for sign-offs, sets specific acceptance criteria, and assigns responsibilities. The plan aims for efficient, compliant, and safe landscaping execution, ensuring high-performance outcomes.
Note: Hold/Witness points are specific to each project and to be specified prior to works commencing. Works are not to proceed past Hold/Witness points until signed off
Attachments
Plan Approver Signatures
Completed Plan Receiver Signatures
PRELIMINARY APPROVALS
# | Activity Title |  | References |  | Assignees and Verification Method | Records
1 | Insulation, Drainage Cell, and Geo-fabric Internal - Hold Point Approval
Acceptance Criteria Insulation, drainage cells, and geofabric specs submitted and approved per project requirements.
2 | Soil Quality Testing Internal - Hold Point
Acceptance Criteria Test results documented and approved.
# | Activity Title |  | References |  | Assignees and Verification Method | Records
3 | Mulch Type Approval Internal - Hold Point
Acceptance Criteria Mulch type sample and data sheet approved.
4 | Plant Substitution Approval Internal - Hold Point
Acceptance Criteria Substitutes listed and approved.
5 | Nursery Visit with Architect for Plant Internal - Hold Point Selection
Acceptance Criteria Plants inspected and selection approved by the architect.
ON-STRUCTURE GARDEN BED & PLANTER INFILL
# | Activity Title |  | References |  | Assignees and Verification Method | Records
1 | Installation of Insulation Layer (for Green Roof Only) |  | Internal - Surveillance Internal - Surveillance
Acceptance Criteria 20mm insulation layer correctly installed, inspected, and approved by foreman. Photo evidence and docket.
2 | Installation of Coreflute |  | Internal - Surveillance
Acceptance Criteria Coreflute installed as per specifications, inspected, and approved by foreman. Photo evidence.
3 | Geo-fabric Laying |  | Internal - Surveillance
Acceptance Criteria Geo-fabric properly laid out, inspected, and approved by foreman. Photo evidence.
4 | Drainage Cell Installation |  | Internal - Surveillance
Acceptance Criteria Drainage cells installed correctly, inspected, and approved by foreman. Photo evidence.
5 | Soil and Mulch Type Verification |  | Internal - Surveillance
# | Activity Title |  | References |  | Assignees and Verification Method | Records
Acceptance Criteria Soil and mulch added to specified levels, correct type, inspected, and approved by foreman. Docket to be retained.
PLANTING
# | Activity Title |  | References |  | Assignees and Verification Method | Records
1 | Delivered Plant Health Inspection |  | Internal - Surveillance
Acceptance Criteria Health and accuracy verified, approved by foreman.
2 | Verification of Plant Layout According to Design |  | Internal - Hold Point Internal - Hold Point
Acceptance Criteria Plant placement matches the design plans, approved by foreman and client.
3 | Tree Securing and Stability Inspection |  | Internal - Surveillance
Acceptance Criteria Anchoring methods inspected, approved by foreman.
4 | Installation and Inspection of Tree Inspection Risers |  | Internal - Surveillance
Acceptance Criteria One inspection riser per tree within planters installed and inspected for compliance with specifications.
HANDOVER
# | Activity Title |  | References |  | Assignees and Verification Method | Records
1 | ITP and Handover Approval Internal - Surveillance Client - Surveillance
Acceptance Criteria ITP reviewed with client, all sections signed off.