## Table 1
160 Gordon St
Footscray, Victoria 3011
2 - Various Planters (Fascade Planters/Proprietary Planters)
Name Plan Manager Location
Various Planters (Fascade Planters/Proprietary Planters)
Brad Ockwell PROJECT WIDE
Description
This Inspection and Test Plan (ITP) directs the implementation and evaluation of various planters, including fascade and proprietary types, focusing on adherence to design specifications and quality benchmarks from approval to final acceptance. It delineates essential hold and witness points for necessary approvals, defines precise acceptance criteria, and allocates task responsibilities. The objective is to ensure an efficient, compliant, and secure installation process, aiming for optimal integration and performance of the planters within the project's scope.
Note: Hold/Witness points are determined based on specific project needs and must be established before initiating work. Progression beyond these points is contingent upon obtaining the requisite approvals.
Attachments
Plan Approver Signatures
Completed Plan Receiver Signatures
PRELIMINARY APPROVALS
# | Activity Title | References | Assignees and Verification Method | Records
1 | Shop Drawings Approval Internal - Hold Point
Acceptance Criteria All shop drawings submitted and approved.
2 | Physical Samples Approval / Selections Internal - Hold Point of Material including Color
# | Activity Title | References | Assignees and Verification Method | Records
Acceptance Criteria Physical samples, material types, and color selections submitted and approved.
3 | Approval of Pedestal for Planters Internal - Hold Point
Acceptance Criteria Specifications for pedestals, including design, load capacity, and materials, submitted and approved.
DELIVERED GOODS INSPECTION
# | Activity Title | References | Assignees and Verification Method | Records
1 | Verification of Delivered Items Against Internal - Surveillance Shop Drawings
Acceptance Criteria Delivered items match the approved shop drawings, verified by foreman with photographic evidence.
2 | Confirmation of Delivered Goods Internal - Surveillance Quantities
Acceptance Criteria Quantities of delivered goods align with documented requirements, confirmed by foreman's sign-off.
INSTALLATION INSPECTION
# | Activity Title | References | Assignees and Verification Method | Records
1 | Compliance of Fixings on Shop Drawings Internal - Surveillance
Acceptance Criteria Installation of fixings verified against shop drawings, approved by foreman.
2 | Completion and Testing of Waterproofing Internal - Hold Point
Acceptance Criteria Waterproofing finished as per design and successfully tested, with foreman's approval.
3 | Security of Planter Installations Internal - Surveillance
Acceptance Criteria Planters secured correctly as per installation guidelines, confirmed by foreman's sign-off.
HANDOVER
# | Activity Title | References | Assignees and Verification Method | Records
1 | ITP and Handover Approval Internal - Hold Point Client - Hold Point
Acceptance Criteria ITP reviewed with client, all sections signed off.