## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP 04 - Irrigation | itp |  |  |  |  | ITP 04 - Irrigation
section | PRELIMINARY APPROVALS
checkpoint | 1 - Design Review and Approval
label | Acceptance Criteria: Irrigation design drawing has been approved - ensure design meets plumbing requirements and is suitable for intended irrigation needs. Review by licensed plumber and sign off by client.
label | Assignees and Verification Method: Internal - Hold Point
holdpoint | HOLD POINT
checkpoint | 2 - Material Review and Approval
label | Acceptance Criteria: Irrigation material samples and material types have been approved
label | Assignees and Verification Method: Internal - Hold Point
holdpoint | HOLD POINT
checkpoint | 3 - Coordination and Permit Acquisition for Live Area Work
label | Acceptance Criteria: All necessary permits for work within live areas obtained. Compliance with zoning and site work plans documented through coordination efforts.
label | Assignees and Verification Method: Internal - Hold Point
holdpoint | HOLD POINT
section | MATERIAL INSPECTION
checkpoint | 1 - Inspection of Delivered Materials
label | Acceptance Criteria: Upon delivery of piping, fittings, valves, and other materials. Check for damage, ensure specifications (size, material type) match the project requirements, and materials meet approvals.
label | Assignees and Verification Method: Internal - Surveillance
section | PENETRATIONS
checkpoint | 1 - Review of Scanning Reports for Area Penetration
label | Acceptance Criteria: Scanning reports for areas to be penetrated are reviewed to ensure avoidance of existing services and structural elements.
label | Assignees and Verification Method: Internal - Surveillance
checkpoint | 2 - Engineering Approval
label | Acceptance Criteria: Obtain approval from a licensed engineer for all proposed penetrations, ensuring they do not compromise structural integrity or interfere with other building services.
label | Assignees and Verification Method: Internal - Hold Point
holdpoint | HOLD POINT
checkpoint | 3 - Penetration Execution (Peno)
label | Acceptance Criteria: Proceed with penetrations only after engineering approval and successful scanning.
label | Assignees and Verification Method: Internal - Surveillance
checkpoint | 4 - Waterproofing Coordination
label | Acceptance Criteria: Verify waterproofing has been completed by the designated contractor and ensure its integration with our scope of work is documented.
label | Assignees and Verification Method: Internal - Surveillance
section | IRRIGATION INSTALLATION
checkpoint | 1 - Rough-In Plumbing Installation
label | Acceptance Criteria: Poly pipework for water points is installed according to approved design, securely and correctly. Installation is visually inspected and approved by site plumber.
label | Assignees and Verification Method: Internal - Hold Point
holdpoint | HOLD POINT
checkpoint | 2 - Vertical Cabling for Irrigation Control
label | Acceptance Criteria: Ensure vertical cabling to centralized controllers is installed using scissor lifts or similar equipment under strict safety controls, with all installations matching the design.
label | Assignees and Verification Method: Internal - Surveillance
checkpoint | 3 - Dripline Irrigation System Installation
label | Acceptance Criteria: Dripline system is installed as per design, with secure placement and proper connection to water sources. System passes visual inspection, ensuring it's ready for testing.
label | Assignees and Verification Method: Internal - Surveillance
checkpoint | 4 - System Testing and Commissioning
label | Acceptance Criteria: The irrigation system undergoes pressure testing for leaks and functional testing of automation. Testing results meet project standards, ensuring system is operational and effective.
label | Assignees and Verification Method: Internal - Hold Point
holdpoint | HOLD POINT
section | HANDOVER
checkpoint | 1 - ITP and Handover Approval
label | Acceptance Criteria: ITP reviewed with client, all sections signed off.
label | Assignees and Verification Method: Client - Surveillance, Internal - Surveillance