## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP 01 - Soft Landscaping | itp |  |  |  |  | ITP 01 - Soft Landscaping
section | PRELIMINARY APPROVALS
checkpoint | 1 - Insulation, Drainage Cell, and Geo-fabric Approval
label | Acceptance Criteria: Insulation, drainage cells, and geofabric specs submitted and approved per project requirements.
label | Assignees and Verification Method: Internal - Hold Point
holdpoint | HOLD POINT
checkpoint | 2 - Soil Quality Testing
label | Acceptance Criteria: Test results documented and approved.
label | Assignees and Verification Method: Internal - Hold Point
holdpoint | HOLD POINT
checkpoint | 3 - Mulch Type Approval
label | Acceptance Criteria: Mulch type sample and data sheet approved.
label | Assignees and Verification Method: Internal - Hold Point
holdpoint | HOLD POINT
checkpoint | 4 - Plant Substitution Approval
label | Acceptance Criteria: Substitutes listed and approved.
label | Assignees and Verification Method: Internal - Hold Point
holdpoint | HOLD POINT
checkpoint | 5 - Nursery Visit with Architect for Plant Selection
label | Acceptance Criteria: Plants inspected and selection approved by the architect.
label | Assignees and Verification Method: Internal - Hold Point
holdpoint | HOLD POINT
section | ON-STRUCTURE GARDEN BED & PLANTER INFILL
checkpoint | 1 - Installation of Insulation Layer (for Green Roof Only)
label | Acceptance Criteria: 20mm insulation layer correctly installed, inspected, and approved by foreman. Photo evidence and docket.
label | Assignees and Verification Method: Internal - Surveillance
checkpoint | 2 - Installation of Coreflute
label | Acceptance Criteria: Coreflute installed as per specifications, inspected, and approved by foreman. Photo evidence.
label | Assignees and Verification Method: Internal - Surveillance
checkpoint | 3 - Geo-fabric Laying
label | Acceptance Criteria: Geo-fabric properly laid out, inspected, and approved by foreman. Photo evidence.
label | Assignees and Verification Method: Internal - Surveillance
checkpoint | 4 - Drainage Cell Installation
label | Acceptance Criteria: Drainage cells installed correctly, inspected, and approved by foreman. Photo evidence.
label | Assignees and Verification Method: Internal - Surveillance
checkpoint | 5 - Soil and Mulch Type Verification
label | Acceptance Criteria: Soil and mulch added to specified levels, correct type, inspected, and approved by foreman. Docket to be retained.
label | Assignees and Verification Method: Internal - Surveillance
section | PLANTING
checkpoint | 1 - Delivered Plant Health Inspection
label | Acceptance Criteria: Health and accuracy verified, approved by foreman.
label | Assignees and Verification Method: Internal - Surveillance
checkpoint | 2 - Verification of Plant Layout According to Design
label | Acceptance Criteria: Plant placement matches the design plans, approved by foreman and client.
label | Assignees and Verification Method: Internal - Hold Point
holdpoint | HOLD POINT
checkpoint | 3 - Tree Securing and Stability Inspection
label | Acceptance Criteria: Anchoring methods inspected, approved by foreman.
label | Assignees and Verification Method: Internal - Surveillance
checkpoint | 4 - Installation and Inspection of Tree Inspection Risers
label | Acceptance Criteria: One inspection riser per tree within planters installed and inspected for compliance with specifications.
label | Assignees and Verification Method: Internal - Surveillance
section | HANDOVER
checkpoint | 1 - ITP and Handover Approval
label | Acceptance Criteria: ITP reviewed with client, all sections signed off.
label | Assignees and Verification Method: Internal - Surveillance, Client - Surveillance