## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP 02 - Various Planters (Fascade Planters/Proprietary Planters) | itp |  |  |  |  | ITP 02 - Various Planters (Fascade Planters/Proprietary Planters)
section | PRELIMINARY APPROVALS
checkpoint | 1 - Shop Drawings Approval
label | Acceptance Criteria: All shop drawings submitted and approved.
label | Assignees and Verification Method: Internal - Hold Point
holdpoint | HOLD POINT
checkpoint | 2 - Physical Samples Approval / Selections of Material including Color
label | Acceptance Criteria: Physical samples, material types, and color selections submitted and approved.
label | Assignees and Verification Method: Internal - Hold Point
holdpoint | HOLD POINT
checkpoint | 3 - Approval of Pedestal for Planters
label | Acceptance Criteria: Specifications for pedestals, including design, load capacity, and materials, submitted and approved.
label | Assignees and Verification Method: Internal - Hold Point
holdpoint | HOLD POINT
section | DELIVERED GOODS INSPECTION
checkpoint | 1 - Verification of Delivered Items Against Shop Drawings
label | Acceptance Criteria: Delivered items match the approved shop drawings, verified by foreman with photographic evidence.
label | Assignees and Verification Method: Internal - Surveillance
checkpoint | 2 - Confirmation of Delivered Goods Quantities
label | Acceptance Criteria: Quantities of delivered goods align with documented requirements, confirmed by foreman's sign-off.
label | Assignees and Verification Method: Internal - Surveillance
section | INSTALLATION INSPECTION
checkpoint | 1 - Compliance of Fixings on Shop Drawings
label | Acceptance Criteria: Installation of fixings verified against shop drawings, approved by foreman.
label | Assignees and Verification Method: Internal - Surveillance
checkpoint | 2 - Completion and Testing of Waterproofing
label | Acceptance Criteria: Waterproofing finished as per design and successfully tested, with foreman's approval.
label | Assignees and Verification Method: Internal - Hold Point
holdpoint | HOLD POINT
checkpoint | 3 - Security of Planter Installations
label | Acceptance Criteria: Planters secured correctly as per installation guidelines, confirmed by foreman's sign-off.
label | Assignees and Verification Method: Internal - Surveillance
section | HANDOVER
checkpoint | 1 - ITP and Handover Approval
label | Acceptance Criteria: ITP reviewed with client, all sections signed off.
label | Assignees and Verification Method: Internal - Hold Point, Client - Hold Point
holdpoint | HOLD POINT