## res_ITP_1_Inspection_and_Test_P
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP - Separable Portion 3 (Intersection Upgrade) | itp |  |  |  |  | ITP - Separable Portion 3 (Intersection Upgrade)
section | Pavements
checkpoint | Subgrade
label | SPECIFICATION REFERENCE - Pavement and Surfacing Technical Specification, clause 2.1
label | TEST/TASK REQUIRED - Scala and/or Benkelman Beam Deflections
label | INSPECTION BY - After excavation and prior to any construction, installation or backfilling
label | TASK TIMING OR TASK FREQUENCY - Areas that fail to achieve the minimum subgrade CBR and deflection criteria will require the construction of Subgrade Improvement Layers (SIL). Acceptance by Engineer before proceeding.
checkpoint | Imported Granular Fill
label | TEST/TASK REQUIRED - Record of Fill
label | INSPECTION BY - On completion of granular fill layer.
label | TASK TIMING OR TASK FREQUENCY - Submitted to Engineer.
checkpoint | SIL Material Testing
label | SPECIFICATION REFERENCE - Pavement and Surfacing Technical Specification, clause 2.2.2
label | TEST/TASK REQUIRED - Material Test Certificates
label | INSPECTION BY - Prior to using the material on site
label | TASK TIMING OR TASK FREQUENCY - Material meets specification. Material approval by Engineer.
checkpoint | Subgrade Improvement Layer
label | SPECIFICATION REFERENCE - Pavement and Surfacing Technical Specification, clause 2.2
label | TEST/TASK REQUIRED - Benkelman Beam Deflections
label | INSPECTION BY - Benkelman Beam testing where possible on completion Subgrade Improvement Layers. On completiond of the Subgrade Improvement layer. Inspection by the Engineer.
label | TASK TIMING OR TASK FREQUENCY - Benkelman Beam Deflections meet specification. Acceptance by Engineer before proceeding.
checkpoint | Lean Mix Concrete Layer
label | TEST/TASK REQUIRED - Concrete Dockets, Benkelman Beam Deflections
label | INSPECTION BY - On completion of the Lean Mix Concrete layer.
label | TASK TIMING OR TASK FREQUENCY - Increase in Benkelman Beam Deflections meet Engineers criteria. Acceptance by Engineer before proceeding.
checkpoint | Lower Subbase Material Testing
label | SPECIFICATION REFERENCE - Pavement and Surfacing Technical Specification, clause 2.3.2
label | TEST/TASK REQUIRED - Material Test Certificates
label | INSPECTION BY - Prior to using the material on site
label | TASK TIMING OR TASK FREQUENCY - Material meets specification. Material approval by Engineer.
checkpoint | Lower Subbase
label | SPECIFICATION REFERENCE - Pavement and Surfacing Technical Specification, clause 2.3
label | TEST/TASK REQUIRED - NDM Testing and Benkelman Beam Deflections
label | INSPECTION BY - On completion of the Lowe Subbase layer, prior to construction Upper Subbase layer.
label | TASK TIMING OR TASK FREQUENCY - NDM results and Benkelman Beam Deflections meet specification. Acceptance by the Engineer.
checkpoint | Upper Subbase Material Testing
label | SPECIFICATION REFERENCE - Pavement and Surfacing Technical Specification, clause 2.4.2
label | TEST/TASK REQUIRED - Material Test Certificates
label | INSPECTION BY - Prior to using the material on site
label | TASK TIMING OR TASK FREQUENCY - Material meets specification. Material approval by Engineer.
checkpoint | Upper Subbase
label | SPECIFICATION REFERENCE - Pavement and Surfacing Technical Specification, clause 2.4
label | TEST/TASK REQUIRED - NDM Testing and Benkelman Beam Deflections
label | INSPECTION BY - On completion of the Upper Subbase layer, prior to construction of the Basecourse layer.
label | TASK TIMING OR TASK FREQUENCY - NDM results and Benkelman Beam Deflections meet specification. Acceptance by the Engineer.
checkpoint | Basecourse Material Testing
label | SPECIFICATION REFERENCE - CON21015 Project Specification, clause 23.8
label | TEST/TASK REQUIRED - Material Test Certificates
label | INSPECTION BY - Prior to using the material on site
label | TASK TIMING OR TASK FREQUENCY - Material meets specification. Material approval by Engineer.
checkpoint | Basecourse
label | SPECIFICATION REFERENCE - CON21015 Project Specification, clause 23.8
label | TEST/TASK REQUIRED - NDM Testing and Benkelman Beam Deflections
label | INSPECTION BY - On completion of the Basecourse layer, prior to construction of the deep lift or wearing course layers.
label | TASK TIMING OR TASK FREQUENCY - NDM results and Benkelman Beam Deflections meet specification. Acceptance by the Engineer.
checkpoint | AC20 Material Testing
label | SPECIFICATION REFERENCE - NZTA M10 Specification
label | TEST/TASK REQUIRED - Material Test Certificates
label | INSPECTION BY - Prior to using the material on site
label | TASK TIMING OR TASK FREQUENCY - Material meets specification. Material approval by Engineer.
checkpoint | AC20 Deep Lift Layers
label | SPECIFICATION REFERENCE - NZTA M10 Specification
label | TEST/TASK REQUIRED - Testing as per NZTA M10
label | INSPECTION BY - On completion of the AC20 Deep Lift Layers, prior to construction of the AC14 wearing course.
label | TASK TIMING OR TASK FREQUENCY - Testing results meet specification. Acceptance by the Engineer.
checkpoint | AC14 Material Testing
label | SPECIFICATION REFERENCE - NZTA M10 Specification
label | TEST/TASK REQUIRED - Testing as per NZTA M10
label | INSPECTION BY - Prior to using the material on site
label | TASK TIMING OR TASK FREQUENCY - Material meets specification. Material approval by Engineer.
checkpoint | AC14 Wearing Course
label | SPECIFICATION REFERENCE - NZTA M10 Specification
label | TEST/TASK REQUIRED - Testing as per NZTA M10
label | INSPECTION BY - On completion of the AC14 wearing course.
label | TASK TIMING OR TASK FREQUENCY - Testing results meet specification. Acceptance by the Engineer.
checkpoint | Two Coat Chip Seal Surfacing
label | SPECIFICATION REFERENCE - Pavement and Surfacing Technical Specification, clause 2.12
label | TEST/TASK REQUIRED - Testing as per clause 2.12
section | STORMWATER
checkpoint | Stormwater Construction Methodology
label | SPECIFICATION REFERENCE - CON21015 Project Specification, clause 18
label | TEST/TASK REQUIRED - Construction Methodology submitted for specific works
label | INSPECTION BY - Prior to the commencement of specific works
label | TASK TIMING OR TASK FREQUENCY - Construction Methodology accepted by the Engineer.
checkpoint | Stormwater Installation
label | TEST/TASK REQUIRED - Photos, as-built drawings and CCTV of installed stormwater
label | INSPECTION BY - On completion of the installation of the stormwater system.
label | TASK TIMING OR TASK FREQUENCY - Installation meets WDC Engineering Standards.
section | SEWER
checkpoint | Sewer Construction Methodology
label | SPECIFICATION REFERENCE - CON21015 Project Specification, clause 18
label | TEST/TASK REQUIRED - Construction Methodology submitted for specific works
label | INSPECTION BY - Prior to the commencement of specific works
label | TASK TIMING OR TASK FREQUENCY - Construction Methodology accepted by the Engineer.
checkpoint | Sewer Installation
label | TEST/TASK REQUIRED - Photos, PE weld records, pressure testing records, as-built drawings
label | INSPECTION BY - On completion of the installation of the sewer system.
label | TASK TIMING OR TASK FREQUENCY - Installation meets WDC Engineering Standards.
section | WATER
checkpoint | Water Construction Methodology
label | TEST/TASK REQUIRED - Construction Methodology submitted for specific works
label | INSPECTION BY - Prior to the commencement of specific works
label | TASK TIMING OR TASK FREQUENCY - Construction Methodology accepted by the Engineer.
checkpoint | Watermain Installation
label | TEST/TASK REQUIRED - Photos, PE weld records, pressure testing records, chlorination records, as-built drawings
label | INSPECTION BY - On completion of the installation of the watermain system
label | TASK TIMING OR TASK FREQUENCY - Installation meets WDC Engineering Standards and WDC Water Services General Specification.
section | CONCRETE WORKS
checkpoint | Kerb and Channel
label | SPECIFICATION REFERENCE - CON21015 Project Specification, clause 22.3
label | TEST/TASK REQUIRED - Photos, concrete dockets
label | INSPECTION BY - On completion of kerb and channel construction.
label | TASK TIMING OR TASK FREQUENCY - Construction meets specification.
checkpoint | Vehicle Crossings
label | SPECIFICATION REFERENCE - CON21015 Project Specification, clause 22.6
label | TEST/TASK REQUIRED - Photos, concrete dockets, CIV results
label | INSPECTION BY - On completion of vehicle crossing construction.
label | TASK TIMING OR TASK FREQUENCY - Construction meets specification.
checkpoint | Concrete Footpaths
label | SPECIFICATION REFERENCE - CON21015 Project Specification, clause 22.5
label | TEST/TASK REQUIRED - Photos, concrete dockets, CIV results
label | INSPECTION BY - On completion of shared user path construction.
label | TASK TIMING OR TASK FREQUENCY - Construction meets specification.
checkpoint | Coloured Concrete (Islands, KiwiRail)
label | TEST/TASK REQUIRED - Photos, concrete dockets
label | INSPECTION BY - On completion of coloured concrete construction.
label | TASK TIMING OR TASK FREQUENCY - Construction meets specification.
section | LIGHTING
checkpoint | Lighting Material Supply
label | SPECIFICATION REFERENCE - CON21015 Project Specification, clause 26.3
label | TEST/TASK REQUIRED - Material dockets/statements
label | INSPECTION BY - On completion of lighting installation.
label | TASK TIMING OR TASK FREQUENCY - Materials meet lighting specification.
checkpoint | Lighting Installation
label | SPECIFICATION REFERENCE - CON21015 Project Specification, clause 26.3
label | TEST/TASK REQUIRED - Checklists confirming installation and electrical testing
label | INSPECTION BY - On completion of lighting installation.
label | TASK TIMING OR TASK FREQUENCY - Installation meets lighting specification.
section | TRAFFIC SIGNALS
checkpoint | Traffic Signals Material Supply
label | SPECIFICATION REFERENCE - CON21015 Project Specification, clause 25.8
label | TEST/TASK REQUIRED - Material dockets/statements
label | INSPECTION BY - On completion of traffic signal installation.
label | TASK TIMING OR TASK FREQUENCY - Materials meet traffic signal specification.
checkpoint | Traffic Signals Installation
label | SPECIFICATION REFERENCE - CON21015 Project Specification, clause 25.8
label | TEST/TASK REQUIRED - Checklists confirming installation and electrical testing
label | INSPECTION BY - On completion of traffic signal installation.
label | TASK TIMING OR TASK FREQUENCY - Materials meet traffic signal specification.
section | TRAFFIC SERVICES
checkpoint | Pavement Marking
label | SPECIFICATION REFERENCE - CON21015 Project Specification, clause 25.2
label | TEST/TASK REQUIRED - Material dockets/statements, set-out
label | INSPECTION BY - On completion of pavement marking.
label | TASK TIMING OR TASK FREQUENCY - Pavement markings meet NZTA M07 specification and IFC drawings.
checkpoint | Tactile Ground Indicators
label | SPECIFICATION REFERENCE - CON21015 Project Specification, clause 25.2
label | TEST/TASK REQUIRED - Photos, material dockets
label | INSPECTION BY - On completion of tactile paving installation.
label | TASK TIMING OR TASK FREQUENCY - Tactile paving installed as per IFC drawings.
section | FINISHING WORKS
checkpoint | Landscaping
label | SPECIFICATION REFERENCE - Port Road Roundabout Landscape Drawings (IFC)
label | TEST/TASK REQUIRED - Photos, Supplier Dockets
label | INSPECTION BY - On completion of landscaping/installation.
label | TASK TIMING OR TASK FREQUENCY - Installation as per IFC Port Road Roundabout Landscape Drawings
checkpoint | Reserve Fencing
label | TEST/TASK REQUIRED - Photos
label | INSPECTION BY - On completion of reserve fencing.
label | TASK TIMING OR TASK FREQUENCY - Installation as per Engineers instruction.
section | KIWIRAIL LEVEL CROSSING
checkpoint | Pedestrian Access and Fencing
label | TEST/TASK REQUIRED - Photos
label | INSPECTION BY - On completion of pedestrian access installation.
label | TASK TIMING OR TASK FREQUENCY - Installation as per IFC Drawings.