## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned |  |  | checklist | Drainage - Manhole Install Checklist |  |  |  |  | Yes | QA - Drainage - Manhole Install Checklist | 05f050c1-6482-44a5-a04e-ad1d236fa091
checkpoint-group |  |  | section | Manhole Install
checkpoint-status |  |  | checkpoint | Latest consented drawings
text | ecec2db3-87e5-5fbd-a162-89608b7e2aec |  | textbox | Drawing Ref No.
checkpoint-status |  |  | checkpoint | Setout an manhole sizing checked
checkpoint-status |  |  | checkpoint | Services Located and before you dig plans checked
checkpoint-status |  |  | checkpoint | MHS measured onsite. Prep height determined from Lid Level.
text | 32778dcd-dc3b-594b-8142-67d8aeb28cc0 |  | textbox | Lid Level RL
boolean | ada79209-5511-5d56-b3cb-1d1c4399d296 |  | tickbox | Lid level confirmed as correct
text | 106d2cf9-b76b-53e0-bb7a-f0bc9ace4f4e |  | textbox | Manhole System allow 50mm play
text | acef8efc-1884-5b7f-9332-880b60ff7b6f |  | textbox | Prep height RL
text | bba5f888-1250-5606-bc00-36f368be8e75 |  | textbox | Outlet RL
boolean | be71643c-9535-5717-b8f0-6aa06f05fccd |  | tickbox | Outlet RL is 200mm greater than Prep height RL
boolean | 19042b81-c46d-5c0e-a841-95a07099a257 |  | tickbox | Throat height checked to be less than 450mm
boolean | 3ad72655-1bcb-5ef8-ac4d-f62b5280a332 |  | tickbox | Concrete lid will be underneath future works
checkpoint-status |  |  | checkpoint | Benching/shield required if >1.5m
checkpoint-status |  |  | checkpoint | Ground conditions checked & acceptable
checkpoint-status |  |  | checkpoint | Bedding depth and material correct & compacted (Photo Required)
checkpoint-status |  |  | checkpoint | Cut in Manhole Shearbands ( Photos required)
checkpoint-status |  |  | checkpoint | Manhole Risers epoxyed (if applicable Photo required)
checkpoint-status |  |  | checkpoint | Inside of starters epoxyed all the way around
checkpoint-status |  |  | checkpoint | Manhole benching completed and acceptable (Photo required)
checkpoint-status |  |  | checkpoint | Concrete Lid Installed, Correct orientation and sealed
checkpoint-status |  |  | checkpoint | Cast Iron Lid Raised and Installed at 90 degrees to steps
checkpoint-status |  |  | checkpoint | Epoxy completed inside lid and
checkpoint-status |  |  | checkpoint | Stormwater lids to be spray painted blue
checkpoint-status |  |  | checkpoint | Sewer manhole safety grille installed
checklist-flat |  |  | checklist | QA - Civil - Retaining walls |  |  |  |  | Yes | QA - Civil - Retaining walls | 49ae8c03-1de8-4eea-beb2-402ab3f8c09b
checkpoint-status |  |  | checkpoint | Retaining wall(s) setout/heights confirmed
checkpoint-status |  |  | checkpoint | Services Located
checkpoint-status |  |  | checkpoint | Profiles set out level and rigid. Ensure boundary is encompassed within profile.
checkpoint-status |  |  | checkpoint | Finished heights are set hole spacing and pole sizes depending on retained height
boolean | 78296352-123a-5300-ac4a-a0cdb069cb68 |  | tickbox | Excavation correct
boolean | d4b0fa3c-f67e-56f1-8796-177600cf8463 |  | tickbox | correct hole size
boolean | 15265bd2-a1cc-524f-a90f-c44ba0077597 |  | tickbox | correct pole size
boolean | 555a07ad-baa1-59f0-83a6-802bb01c3ca6 |  | tickbox | correct depth
boolean | 43aa7c4d-6d4a-538f-b963-d8d1e4a8bd6b |  | tickbox | All pile holes are inside boundary
checkpoint-status |  |  | checkpoint | General install photos and observations attached
checkpoint-status |  |  | checkpoint | Geotech Pre-pour Inspection
checkpoint-status |  |  | checkpoint | Structural Engineer Inspection
checkpoint-status |  |  | checkpoint | Lagging to be arissed on visible side.
checkpoint-status |  |  | checkpoint | Correct screws/nails used, galvanised/stainless steel etc
checkpoint-status |  |  | checkpoint | Backfill completed - correct materials and compaction methodology used
checklist-flat |  |  | checklist | Detailed Excavation - |  |  |  |  | Yes | QA - Detailed Excavation - | 50ba94d6-c376-4cae-9993-3f08401b16c0
checkpoint-status |  |  | checkpoint | Services Located
checkpoint-status |  |  | checkpoint | Location accurate
checkpoint-status |  |  | checkpoint | Topsoil stripped completely
checkpoint-status |  |  | checkpoint | Building pads set out correctly with RLs as required for cut/fill
checkpoint-status |  |  | checkpoint | Correct cut back for walls/foundations
checkpoint-status |  |  | checkpoint | Geotech Engineer Inspection
checkpoint-status |  |  | checkpoint | Detailed excavation completed, reviewed and approved
checklist-flat |  |  | checklist | Cap existing connection |  |  |  |  | Yes | QA - Cap existing connection | 651426ca-5b75-4257-b77a-dd85fda6e389
checkpoint-status |  |  | checkpoint | Photo and location of capped connection
checklist-sectioned |  |  | checklist | Sewer Junction |  |  |  |  | Yes | QA - Sewer Junction | 728e6a9b-96a3-4f92-a3b1-80cb460b5e3d
checkpoint-group |  |  | section | Sewer Junction
checkpoint-status |  |  | checkpoint | Correct Junction SN16 Y Junction or SN16 Z Junction
checkpoint-status |  |  | checkpoint | Target Checked on Junction
checkpoint-status |  |  | checkpoint | Fall Checked with level
checkpoint-status |  |  | checkpoint | Angle of Junction between 30 and 60 degrees (Photo Required)
checkpoint-status |  |  | checkpoint | Junction Pegged and Sprayed Red
checkpoint-status |  |  | checkpoint | Inspection straight if connecting to private drainage (Photo Required)
checklist-sectioned |  |  | checklist | Cesspit QA |  |  |  |  | Yes | QA - Cesspit | 85358af1-6f6d-4d66-b3c5-92e743a6dc47
checkpoint-group |  |  | section | Cesspit Install
checkpoint-status |  |  | checkpoint | Latest consented drawings
checkpoint-status |  |  | checkpoint | Services Located and before you dig plans checked
checkpoint-status |  |  | checkpoint | Cesspit correct distance off edge of driveway or kerb line
checkpoint-status |  |  | checkpoint | MHS measured onsite. Prep height determined from Lid Level.
text | 0e5ee299-5ef8-5737-b8b8-75a3df87a802 |  | textbox | Lid Level RL
boolean | c7075135-1ce4-5747-bb0e-dcbcebfc9499 |  | tickbox | Lid level confirmed as correct
text | c7e907ea-27b9-5ed0-ba9b-2de0c0401d3f |  | textbox | Manhole System allow 50mm play
boolean | cbed9f19-6ca2-5f77-a91e-d575df9e6575 |  | tickbox | Lid level below formed concrete channel
text | b8f79704-4530-5fac-89df-94bd93082c99 |  | textbox | Prep height RL
checkpoint-status |  |  | checkpoint | Ground conditions checked & acceptable
checkpoint-status |  |  | checkpoint | Bedding depth and material correct & compacted
checkpoint-status |  |  | checkpoint | Half Siphon where required. (Photo required with bedding)
checklist-sectioned |  |  | checklist | Pipeline Installation Checklist |  |  |  |  | Yes | QA - Pipeline Installation Checklist | 960a094d-1869-440d-a1d2-94cdbe387f3e
checkpoint-group |  |  | section | Pipe Laying
checkpoint-status |  |  | checkpoint | Latest consented drawings
text | a9cbb9b8-73f3-5b34-8f32-ec3a53be672b |  | textbox | Drawing Ref No.
checkpoint-status |  |  | checkpoint | Setout completed checked and accurate
checkpoint-status |  |  | checkpoint | Services Located and before you dig plans checked
checkpoint-status |  |  | checkpoint | All junctions marked out and run through with operator
checkpoint-status |  |  | checkpoint | Laser grade checked. Correct +/-. Benching required if >1.5m
text | 0a89d5bb-e70e-560b-99e5-a7338368af52 |  | textbox | Design Grade %
checkpoint-status |  |  | checkpoint | Laser checked for line with string line
checkpoint-status |  |  | checkpoint | Correct trench width for pipe size
checkpoint-status |  |  | checkpoint | Starter checked for fall. Starter epoxyed to seal from water.
checkpoint-status |  |  | checkpoint | Corbel installed with suitable bedding around pipe (Photo Required)
checkpoint-status |  |  | checkpoint | Ground Conditions Checked & Acceptable
checkpoint-status |  |  | checkpoint | General photos during pipe laying
checkpoint-status |  |  | checkpoint | Pipe Laying Completed
text | b1969e14-9f31-57cf-ad40-28be8e3bd8d3 |  | textbox | Laid by
boolean | d5f8d845-4cd8-5b87-aceb-51091273e5dc |  | tickbox | Trench Compacted
boolean | a7e6701b-ac34-5dd8-ba7f-658fc456a176 |  | tickbox | Vehicle Areas or Road Reserve Hard Filled
checkpoint-status |  |  | checkpoint | CCTV Completed
checklist-sectioned |  |  | checklist | Stormwater PVC Junction |  |  |  |  | Yes | QA - Stormwater PVC Junction | 9ec4fe23-fc36-41fd-8983-053bed76c998
checkpoint-group |  |  | section | Stormwater PVC Junction
checkpoint-status |  |  | checkpoint | Correct Junction SN16 London Junction or SN16 Y Junction
checkpoint-status |  |  | checkpoint | Target Checked on Junction
checkpoint-status |  |  | checkpoint | Fall Checked with level
checkpoint-status |  |  | checkpoint | Angle of Junction Between Spring level and 60 degrees (Photo Required)
checkpoint-status |  |  | checkpoint | Junction Pegged and Sprayed Blue
checkpoint-status |  |  | checkpoint | Inspection straight if connecting to private drainage (Photo Required)
checklist-sectioned |  |  | checklist | Stormwater Concrete Junction |  |  |  |  | Yes | QA - Stormwater Concrete Junction | a773b1db-93ae-40ae-97ce-0a44827adfb0
checkpoint-group |  |  | section | Stormwater Concrete Junction
checkpoint-status |  |  | checkpoint | Correct sized junction
checkpoint-status |  |  | checkpoint | Angle of Junction Between Spring level and 60 degrees (Photo Required)
checkpoint-status |  |  | checkpoint | Expoxy inside and out
checkpoint-status |  |  | checkpoint | Shear band connection (Photo required)
checkpoint-status |  |  | checkpoint | Junction Pegged and Sprayed Blue
checkpoint-status |  |  | checkpoint | Inspection straight if connecting to private drainage (Photo Required)
checklist-flat |  |  | checklist | QA - APD Tank Installation |  |  |  |  | Yes | QA - APD Tank Installation | cb2c684e-24a3-4f19-889d-38e197b1216d
checkpoint-status |  |  | checkpoint | Latest consented drawings
text | e70bff9c-1f26-4eef-9601-4626523220b7 |  | textbox | Drawing Ref No.
checkpoint-status |  |  | checkpoint | Tank sizing checked to match plans
checkpoint-status |  |  | checkpoint | Setout checked and run through with operator
checkpoint-status |  |  | checkpoint | Prep Height Determined
text | 305f27e6-d6e6-45f9-a93c-dfbb3deab16f |  | textbox | IL Outlet
boolean | c374809b-b88e-4ae8-bb99-0c885d921a6d |  | tickbox | IL Outlet = Prep height
boolean | d8bf4d31-e9f4-4add-a6c1-c8b9ed92e8f4 |  | tickbox | Ensure lid level is lower than future works
checkpoint-status |  |  | checkpoint | Ground conditions checked & acceptable
checkpoint-status |  |  | checkpoint | Benching/shield required if depth is >1.5m
checkpoint-status |  |  | checkpoint | Bedding depth and material correct and compacted (Photo Required)
boolean | af73e943-0e47-47c4-b3e3-6e36f374ab27 |  | tickbox | Ensure Sump is dug out
checkpoint-status |  |  | checkpoint | Backfill material correct and compacted in 300mm layers (Photos required)
boolean | 9747a689-8ab4-48bb-ad36-011f3b0e430b |  | tickbox | Anchors required for tanks not under future concrete works
checkpoint-status |  |  | checkpoint | Pipes connected according to plan with suitable bedding and haunching (Photo Required)
checklist-sectioned |  |  | checklist | Concrete Surface - Ashphalt or whatever? |  |  |  |  | Yes | QA - Concrete Surface - Ashphalt or whatever? | f560d933-4bfc-41c6-ba58-d7dbd7ff1434
checkpoint-group |  |  | section | Concrete Right of Way
checkpoint-status |  |  | checkpoint | Setout complete and checked
checkpoint-status |  |  | checkpoint | Services Located and before you dig plans checked
checkpoint-status |  |  | checkpoint | Stringline set out
boolean | 13340743-8c36-5efd-8b00-a19088e10bbe |  | tickbox | String checked for fall
boolean | 3fdfc254-ffc5-5602-9afc-4ceacca35b8e |  | tickbox | Driveway checked for correct width
checkpoint-status |  |  | checkpoint | Excavation correct depth
checkpoint-status |  |  | checkpoint | Metal correct depth (Photos required)
checkpoint-status |  |  | checkpoint | Metal compacted
checkpoint-status |  |  | checkpoint | Lids set
checkpoint-status |  |  | checkpoint | Steel placed
checkpoint-status |  |  | checkpoint | Engineer Inspection
checkpoint-status |  |  | checkpoint | Boxing stripped
checkpoint-status |  |  | checkpoint | Topsoil placed (if required)