## ITP-xxx
|  |  | Inspection and Test Plan - Pavement Marking Works | [6 empty] | Document # ITP-03
Revision : 1
Client: |  | DTP |  | Construction Process: | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Buninyong Community Safety Project |  | Linemarking | Name: | Jarvis Gleeson | Name: |  |  | Name:
Contract No: |  |  |  | Specifications:
|  |  |  | Structure / Component: | Signed : | J.GLEESON | Signed : |  |  | Signed :
|  |  |  | Location: | Date : | 2025-08-07 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Inspection / Test Method | Acceptance Criteria | Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | Date
1 | Construction Works
1.01 | Redundant Linemarking Removal |  | Visual Inspection | Markings removed via approved method (jet blast/Black grit). No visible ghosting. | Jet blast or black grit spray minimum 20% wider than existing lines. | This ITP, Photographic record | HP | Superintendent
1.02 | Surface Preperation |  | Visual and manual check | Surface clean, dry, and dust free before application | Manual brooming, air blowing, and drying where needed. | Supervisor sign off | IP | Site Engineer | N/A
1.03 | Linemarking and RRPM set out |  | Measurement review | Set out conforms to drawings.Symbols in correct orientation and location. | Measure up, mark with paint/chalk, verify spacings as per plan. | This ITP, Photographic record | HP | Superintendent
1.04 | Linemarking Installation |  | Visual inspectioon, dry film thickness check, reflectivity. | Thickness per spec (≤2.0mm for thermoplastic), reflectivity to AS 1742. | Apply materials as per spec, black grit as required. | Thickness guage, luminance/reflectivity test records. | IP | Site Engineer | N/A
1.05 | RRPM installation |  | Visual inspection | Correct colour, spacing, aligned with edges/centrelines. | install with approved adhesive per manufacturer; must not be dislodged with hand pressure. | RRPM placement log with spacings and colour coding noted. | IP | Site Engineer | N/A
1.06 | Completion insoection - Linemarking & RRPMs |  | Joint inspections with superintendent | Works complete, complient, free from defects, overspray or misaligned markings. | Walkhrough audit with reference to drawings and spec. punch list created and rectifies if needed. | Final sign off form, defect rectification log if neededn | HP | Superintendent
COMMENTS |  | _______________________________________________________________________________________________________________________________________________________________ ________________________________________________________________________________________________________________________________________________________________
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: | [5 empty] | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent