## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 7ABC0560 - 1.02 - Pavement marking works | itp |  |  |  |  | 7ABC0560 - 1.02 - Pavement marking works Rev1
section | 1 - Construction Works
checkpoint | 1.01 - Redundant Linemarking Removal
label | INSPECTION / TEST METHOD: Visual Inspection
label | ACCEPTANCE CRITERIA: Markings removed via approved method (jet blast/Black grit). No visible ghosting.
label | METHOD: Jet blast or black grit spray minimum 20% wider than existing lines.
label | RECORD OF CONFORMITY: This ITP, Photographic record
label | HP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.02 - Surface Preperation
label | INSPECTION / TEST METHOD: Visual and manual check
label | ACCEPTANCE CRITERIA: Surface clean, dry, and dust free before application
label | METHOD: Manual brooming, air blowing, and drying where needed.
label | RECORD OF CONFORMITY: Supervisor sign off
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.03 - Linemarking and RRPM set out
label | INSPECTION / TEST METHOD: Measurement review
label | ACCEPTANCE CRITERIA: Set out conforms to drawings.Symbols in correct orientation and location.
label | METHOD: Measure up, mark with paint/chalk, verify spacings as per plan.
label | RECORD OF CONFORMITY: This ITP, Photographic record
label | HP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.04 - Linemarking Installation
label | INSPECTION / TEST METHOD: Visual inspectioon, dry film thickness check, reflectivity.
label | ACCEPTANCE CRITERIA: Thickness per spec (≤2.0mm for thermoplastic), reflectivity to AS 1742.
label | METHOD: Apply materials as per spec, black grit as required.
label | RECORD OF CONFORMITY: Thickness guage, luminance/reflectivity test records.
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.05 - RRPM installation
label | INSPECTION / TEST METHOD: Visual inspection
label | ACCEPTANCE CRITERIA: Correct colour, spacing, aligned with edges/centrelines.
label | METHOD: install with approved adhesive per manufacturer; must not be dislodged with hand pressure.
label | RECORD OF CONFORMITY: RRPM placement log with spacings and colour coding noted.
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.06 - Completion insoection - Linemarking & RRPMs
label | INSPECTION / TEST METHOD: Joint inspections with superintendent
label | ACCEPTANCE CRITERIA: Works complete, complient, free from defects, overspray or misaligned markings.
label | METHOD: Walkhrough audit with reference to drawings and spec. punch list created and rectifies if needed.
label | RECORD OF CONFORMITY: Final sign off form, defect rectification log if neededn
label | HP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP