## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Communications Cabinet | [5 empty] | Quality - Communications Cabinet
section | Details
checkpoint | Receipt of Cabinet delivery to site
checkpoint | set out to be confirmed with latest cabinet Shop drawings
checkpoint | Correct alignment to set out drawings
checkpoint | Correct bracket and safe fixing
checkpoint | Photos of cabinet attached
holdpoint | Signoff Required from Heyday/MDE
checklist | Communications Cabling | [5 empty] | Quality - Communications Cabling
section | Details
checkpoint | Correct cable type.
checkpoint | Installed to correct cable routing arrangements & cable number.
checkpoint | Installed to final location.
checkpoint | Photo evidence captured for cable containment install.
holdpoint | Signoff Required from Heyday/MDE
checkpoint | Attach Photos
checklist | In Slab LV & Communication Conduits | [5 empty] | Quality - In Slab LV & Communication Conduits
section | Details
checkpoint | Receipt of conduit delivery to site & storage.
checkpoint | Correct location to Drawing
checkpoint | Correct size and type
checkpoint | Correct spacing in slab
checkpoint | Correct depth in slab
checkpoint | Clear to other services
checkpoint | Conduits glued together
checkpoint | No Damage
holdpoint | Signoff Required from Heyday
checkpoint | Record photo evidence.