## to_add
Step Id | Warnings | State | Checklist Template | Type | addStep | addPost | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6
29391546-bfda-4c14-bf6f-051ccd551aaf |  | pass | Quality - Light Fitting Installation | checklist | FALSE | FALSE | Sign Offs - Installation and Rough in | B2 | Basement 2 | Fire Pump room | Fire Pump Room B2 - Light Fitting Installation
deb5020f-9943-46d9-b445-ec35addeb438 |  | pass | Quality - Light Fitting Installation | checklist | FALSE | FALSE | Sign Offs - Installation and Rough in | B2 | Basement 2 | Atlassian store | Atlassian Store B2 - Light Fitting Installation
821fe6e5-555c-4974-894d-fff1fcfa908e |  | pass | Quality - Light Fitting Installation | checklist | FALSE | FALSE | Sign Offs - Installation and Rough in | B2 | Basement 2 | Hydraulic Pump room | Hydraulic Room B2 - Light Fitting Installation
b8a9d3e3-21a6-4904-9695-e4fc5d61084e |  | pass | Quality - Light Fitting Installation | checklist | FALSE | FALSE | Sign Offs - Installation and Rough in | B2 | Basement 2 | DAS Room | DAS Room B2 - Light Fitting Installation
b1d1cd33-5ab3-4f01-a8d3-71f2bc1893b9 |  | work-in-progress | Quality - Light Fitting Installation | checklist | FALSE | FALSE | Sign Offs - Installation and Rough in | B2 | Basement 2 | YHA Store | YHA Store B2 - Light Fitting Installation
50e2421a-4a13-4526-a8fb-158384ca59d8 |  | not-started | Quality - Light Fitting Installation | checklist | FALSE | FALSE | Sign Offs - Installation and Rough in | B2 | Basement 2 | Retail Store 006 | Retail Store B2 - Light Fitting Installation
a768985f-fff4-420c-a534-cc4eee56334d |  | pass | Quality - Light Fitting Installation | checklist | FALSE | FALSE | Sign Offs - Installation and Rough in | B2 | Basement 2 | Atlassian Store 026 | Atlassian Store 026 - Light Fitting Installation
6df7256b-5449-4504-990f-45d12f9e2707 |  | pass | Quality - Light Fitting Installation | checklist | FALSE | FALSE | Sign Offs - Installation and Rough in | B1 | Basement 1 | B1 ACC WC | B1 Acc WC - Light Fitting Installation
43fd9983-8738-491c-bde1-4cc94f909d89 |  | pass | Quality - Light Fitting Installation | checklist | FALSE | FALSE | Sign Offs - Installation and Rough in | B1M | Basement 1 Mezz | B1 Mezz - Cleaner Ammenities and Change | B1 Mezz Cleaners Amenities and Change - Light Fitting Installation
c508d855-de6e-4648-9eb0-8f96b7e8151f |  | pass | Quality - Light Fitting Installation | checklist | FALSE | FALSE | Sign Offs - Installation and Rough in | B1M | Basement 1 Mezz | B1 Mezz - Cleaners office/Briefing | Cleaners Office B1 Mezz - Light Fitting Installation
e236b170-0a1d-4440-9e61-ce99496c24dc |  | pass | Quality - Light Fitting Installation | checklist | FALSE | FALSE | Sign Offs - Installation and Rough in | B1M | Basement 1 Mezz | Comms Room | B1 Mezz Comms - Light Fitting Installation
93d23262-0bc2-4c19-be69-f1d32426282b |  | pass | Quality - Light Fitting Installation | checklist | FALSE | FALSE | Sign Offs - Installation and Rough in | B1M | Basement 1 Mezz | Building Spares Store | Building Spares Store B1 Mezz - Light Fitting Installation
8de53761-11ee-48eb-80cb-5b1a5630a051 |  | pass | Quality - Light Fitting Installation | checklist | FALSE | FALSE | Sign Offs - Installation and Rough in | B1M | Basement 1 Mezz | Main Cleaners Store | Main Cleaners store B1 Mezz - Light Fitting Installation
a2499787-0bc0-4915-8e4b-89d0628555ad |  | not-started | Quality - Light Fitting Installation | checklist | FALSE | FALSE | Site QA | Distribution Boards | Basements | House DBs | DB-H-B00-COMMS | Quality - Light Fitting Installation
cbfaf08d-df33-472f-bc70-1eb09ed43a4b |  | not-started | Quality - Light Fitting Installation | checklist | FALSE | FALSE | Tier 1: Site QA; Tier 2: Emergency Lighting; Tier 3: Quality - Light Fitting Installation
27248c0e-4098-45b3-9215-b53040dd3e48 |  | not-started | Quality - Light Fitting Installation | checklist | FALSE | FALSE | Tier 1: Quality Templates; Tier 2: Quality - Light Fitting Installation