## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
c28c2c2f-6b0a-4130-8abe-7f138a63caca | checklist | Cleaning |  | Cleaning
22654eb7-c445-4614-904b-a6538848fd90 | checkpoint | Has level been cleaned - please attach a photo
2d440e79-edf6-4b42-9b43-b0046542afa6 | checklist | Commissioning/Handover & Testing Checklist |  | Commissioning
7a003222-1cfe-4910-89c3-65116a7be45a | checkpoint | Final completed for fire hydrant
54dc8d96-21f4-4d7a-ba91-6da0654748ed | checkpoint | Final sign off - Pass when happy to proceed (Any issues please comment & Add photos below)
487421c3-f981-4f7c-ae5b-e6bfb2c0d30d | checklist | Copper Riser Penetration |  | Copper Riser Penetration
c155a2f3-ff38-459a-bb4e-1c573c664af2 | checkpoint | Copper Riser Penetration - Please add any photos / comments
c7060e30-41db-5b17-9070-fca752673703 | tickbox | MAXILTE 60 (FIRE BOARD 1525x1000x60mm)
a80d6f6c-8672-5024-b335-9ee963979820 | tickbox | TWRAP 300mm (TWRAP PENETRATION WRAP -25mm THICK 300 X 7620mm)
42a030c1-418a-5553-8d08-578bdf53123c | tickbox | TWRAP 600mm (TWRAP PENETRATION WRAP -25mm THICK 600 X 7620mm)
d95b9351-1a51-511a-acaa-3bf9aab32a5a | tickbox | FRYREFLEX 600W (FRYREFLEX 600mL SAUSAGE)
3fd9289d-546f-5b9d-826b-fcc8c5e88992 | tickbox | CABLE TIE SS 4.6 X 520 (STAINLESS STEEL CABLE TIES 4.6mm X 520mm)
53d3e83f-5f2a-49cd-a18b-33609273afcf | checklist | Fit Off Checklist |  | Fit Off
def94965-c9a7-43b2-b1f0-21d6b948cef4 | checkpoint | Fixtures installed at correct height/clearance
d16e6cfe-a1f8-4785-81c4-6a0c0ec98f6d | checkpoint | Appliances installed at correct location
0d1af62e-9ad2-4f6e-8985-43bfcc585a25 | checkpoint | Dishwasher installed & tested
3431deb0-7346-42ae-8bb9-429c371ace1a | checkpoint | Correct clearance between appliance & walls, fixtures/equipment
b90d8ad3-56c2-4596-bb31-cef805dea422 | checkpoint | Correct clearance for connections & maintenance
4cf30706-281e-49ea-8fe7-a54a99d84a28 | checkpoint | Ensure bath is installed as per specifications
5d429867-2989-4b2b-a7ea-2741a61a52de | checkpoint | Final test completed & hot water tempered
0b93799d-571b-49b1-9263-7f84ef632191 | checkpoint | Valves Installed/Completed (As Per Below) - Any issues comment below
1e09ee46-64fc-4112-9b01-61be546c61cd | checklist | Internal Drainage |  | Internal Drainage
271b29bf-596c-4547-90fa-edfbfb6322f5 | checkpoint | Ensure pipes are at correct fall as per AS3500
a9e98d0f-6f4d-4a94-8ac3-ba938586c7bb | checkpoint | Backfilling material has been backfilled & compacted as per AS3500
3d7514f1-b5b2-4a7f-a255-a00a6a215573 | checkpoint | Pipes are clear of debris
09e45cd9-0592-4980-9c54-8f53a1773d14 | checkpoint | Jump ups at floor waste gulleys
d56bc237-e988-4b4f-a3dd-e9efcd2314a5 | checkpoint | Direct rotting to WC's
841ccb50-1b5e-4e16-ac39-e06dd876e6cc | checkpoint | Vents installed on main lines
34f2c93b-b141-434c-807d-571199382f99 | checkpoint | Chamber vent installed
18fc495f-de79-4885-b0dc-34bfbd3eadec | checkpoint | General photos, comments & observations during internal drainage
c27126bd-224b-4418-b12e-3bab33cea4ad | checkpoint | Pipework fixture connections capped & secure
cd80c5fc-981b-4618-be91-32851a877f94 | checklist | Internal Stormwater |  | Internal Stormwater
d0748c0f-2df5-4e6c-9ed9-1175939f5010 | checkpoint | Ensure pipes are at correct fall as per AS3500
9bea4884-9a81-4729-8f2d-a519d4fabb04 | checkpoint | Backfilling material has been backfilled & compacted as per AS3500
a82460bb-dcb4-42f8-a3b6-e685159761b5 | checkpoint | Pipes are clear of debris
60e03e59-be51-4aee-a71a-60f65cda2b26 | checkpoint | Pit invert levels & RL's are per plan
2da3964b-7f59-48c4-a1bf-c92065e59a5b | checkpoint | General photos, comments & observations during internal drainage
0bef6dd1-617d-41a5-adf2-3bf90bdd10a6 | checkpoint | Pipework fixture connections capped & secure
94c5c927-63cc-49e6-af69-29af7eb748be | checklist | Meter Cupboard / Copper Riser |  | Meter Cupboard / Copper Riser
ee7e8bd5-2fea-416d-88d4-ef2a45d81728 | checkpoint | All copper piping installed & pressure tested to AS/NZS3500:2018
05c406da-3b38-4933-b04c-153a94b50ea8 | checkpoint | Valves Installed/Completed (As Per Below) - Any issues comment below
fbd19d90-7057-5ffe-ae97-d906871da3e9 | button | Tempering valves installed | Yes, No, N/A
4e47d9fb-ba7d-50d6-b56d-3afa5ad84751 | button | Air admittance valves installed & connected as specified & readily accessible | Yes, No, N/A
5a9d0574-e116-5541-96ef-1952704b4fcd | button | Pressure regulating valve assembles fitted, connected & pipework flushed prior to install | Yes, No, N/A
ae323a0b-881b-525f-b463-e945ae16e356 | button | Tempering valve tested ready for temperature setting | Yes, No, N/A
ccb884a0-9065-416c-8522-5a9103fc8cb2 | checkpoint | General photos, comments & observations during Sewer Rough-In (Add below)
bb950f52-3d86-4031-b2b6-7fe3d2eaea12 | checklist | Passive Fire Penetration |  | Passive Fire Penetration
4ba3b1f3-a9cb-4e25-b009-48334d461b9e | checkpoint | Confirm area of work is accessible & acceptable to commence (If not comment below)
73b4e2f5-0e7d-5df9-a207-1c76c685cc41 | dropdown | Material | Hilti CP 611A Firestop Intumescent Sealant, Hilti Firestop Acrylic Sealant 209633, Hilti Firestop Acrylic Sealant CP 606, Hilti Firestop Collar 100 No. 435410, Hilti Firestop collar 50 No. 455405, Hilti Firestop collar 50 No. 455406, Promaseal FC 100 No. 27253, Promaseal FC 100 No. 78269, Promaseal FC 150 No. 78254, Promaseal FC 150 No. 78270, Promaseal FC 50 No. 78272, Promaseal FCR 100 No. 78253, Promaseal FCR 100 No. 78282, Promaseal FCW 40 No. 78271, Promaseal FCW 50 No. 435906, Promaseal FCW 50 No. 78272, Promaseal FCW 50 No. 78273, Promaseal FCW 50 No. 922310, Promaseal FCW 65 No. 78273, Trafalgar Wrap, Uni Collar No. 78342, Promaseal FCW 100, Promaseal FCW 150
38e1c5f8-6d37-5c24-b267-9062c9485d7d | dropdown | Description | PVC Sewer, PVC Stormwater, 20mm PEX, Copper Water, Copper Gas
f7c566d5-a25a-5df5-bc51-c0e8afb6a5d9 | dropdown | Pipe size | 16mm, 20mm, 40mm, 50mm, 65mm, 80mm, 100mm, 150mm, 225mm
887abb31-bd95-4f07-9a90-9eab2d010e45 | checkpoint | Please take detail photos of penetration & labelling
a3a6483d-f931-557b-a543-08509bfdd88d | textbox | ID Number
21218a77-8552-4387-b340-66a58be98964 | checkpoint | Please attach copy of test report / certificate
19dfa4f9-0cbe-47ab-916a-0bfb0423dd9c | checklist | Plumbing Rough-In Water/Gas/Sewer Checklist |  | Plumbing Rough-In
894326da-b9a4-48f5-aec2-2324e1343ae0 | section | Sewer Stacks
711f9ee7-80dc-4d86-9ec4-4acd35da3cd4 | checkpoint | Pipework fastened, fixed, supported & secured (clipped) correct spacings
250213e1-1be3-4eb0-bcb6-648be6dbdc4d | checkpoint | Pipework connection points at fixtures & fittings installed at correct height & fall
b63bfb2e-04d7-5752-8571-c6f1b5523157 | note | Consider ceiling height
70de5bf4-caae-4159-985b-42ad5402b53f | checkpoint | Correct invert level (As per Standards)
7e093d08-b71e-4fa6-8890-a468e4af780f | checkpoint | Pipework fixture connections capped & secure
65b43ad3-c20f-48e9-8600-a328625d13c4 | checkpoint | General photos, comments & observations during Sewer Rough-In (Add below)
8e70a6ec-23cd-5d30-94ba-3575f4fb0328 | button | Passive Fire collars/Sealant(s) for all pipework completed (Any issues comment below) | Yes, No
f6c293a1-1ec4-4e70-bb39-abef067aff0d | checkpoint | Drainage flood tested
c535b4b1-f6a2-5c6a-96ec-3326de2494b0 | note | FINAL - Pass when happy to proceed with work(s) (Any issues please comment below)
62b71cf0-3061-4a5c-aceb-7cdc44fefbe0 | section | Water & Gas Rough-In
eb5abc24-648d-4917-ac22-9f7fd551abcf | checkpoint | Pipework run to the correct points & there are no cross connections
244803ec-78e7-4a66-9cd5-2c9dd759f7c9 | checkpoint | Pipework fastened, fixed, supported & secured (clipped) correct spacings
281bfb2f-ad9f-55c8-b364-ba2f46ab7ece | note | Make sure no water hammer on Water pipes
51401d57-be7e-4d86-98ae-265c3d650334 | checkpoint | Pipework connection points at fixtures & fittings installed at correct height
ed0ed3be-3049-5f14-b7a8-e277c3d7fc7f | note | Consider ceiling height
d442beeb-9b02-4588-8b9b-f99e138b119e | checkpoint | Pipework fittings capped, connection loops joined & secure
3b9d6ddc-4fce-4b2d-8fbf-0e9478862b08 | checkpoint | Leak test piping before proceeding to 1500KPA
52e69bb9-a94c-4201-a591-5720ae5d7e1e | checkpoint | Gas test pressure holding point 14KPA
8a1d4412-156f-529e-b54c-1c5339ae32ea | button | Isolation valves installed & located readily accessible for maintenance | Yes, No, N/A
e164b918-9655-5348-97dc-39766c088361 | button | TMV/Tempering valve installed | Yes, No, N/A
bc5995fe-637b-4e1a-a116-9234096a2959 | checkpoint | All rough in fire rated
f236189b-6fef-4208-a5c3-a531e09186b3 | checkpoint | Ensure all drainage is capped
96a7217d-564a-438e-b5e2-1f26c14d8c8a | checkpoint | General photos, comments & observations during Rough-In (Add below)
b4db1c8d-f9a9-4514-9255-0870b3b85191 | checkpoint | Rough-In completed to specification/drawings
116aa257-0fb2-41d1-9cc1-b777a7773d73 | checkpoint | Final test completed
4115ef39-5d3a-4c00-a0f6-065944fbfcca | checklist | Sewer Stacks / Storm water stacks |  | Sewer Stacks / Storm water stacks
17df91e2-fe95-4137-a26e-ab4b933626b5 | checkpoint | Pipework fastened, fixed, supported & secured (clipped) correct spacings
44e25d39-16f1-4e63-9c2a-1d5a0377b55e | checkpoint | Pipework connection points at fixtures & fittings installed at correct height
030fbf79-1e88-51ce-89a9-384a22a0b82e | note | Consider ceiling height
d2aefbff-f3c9-4072-b630-fef848f491cf | checkpoint | Correct invert level (As per Standards)
959728b5-fde6-408b-a541-5a5af61b6cd1 | checkpoint | Pipework fixture connections capped & secure
a2ef292e-9227-4e9b-87b3-3d257dbd4230 | checkpoint | General photos, comments & observations during Sewer Rough-In (Add below)
8d52ba18-d8eb-46d1-b4fa-156ea914c74c | checkpoint | Passive Fire collars/Sealant(s) for all pipework completed (Any issues comment below)