## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-299-CIV-PSDS-Lean Concrete
ITP Description: |  | PSDS-Lean Concrete
Discipline (e.g. CIV/STR/RAIL: |  | 299-CIV
Revision Number: |  | 0
Revision Date: |  | 2025-08-07
ITP created by: |  | Nathan Cooper
ITP approved for use by: |  | Romualdo Magpantay
Special Notes to ConQA Team : |  | ITP for ProgressStreet
Inspection & Test Plan - Lean Concrete
|  |  | Document No.: | [5 empty] | Revision: | 0
[9 empty] | Date: | 2025-08-07
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | Vic road 503 November 2018 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | Vic Road 173,408,610,687, 689 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | AS 1012 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.4 | Non Dependent | AS 1379 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Concrte mix | Vic Road 503.04 | Ensure all plant, materials, mix design and/or any additional approvals have been obtained prior to planning commencement. Requirements for Lean Mix Concrete Subbase Course The mean 28 day compressive strength of the concrete mix used for the construction of the lean mix concrete subbase course shall be 6 MPa to 15 MPa. The lean mix concrete shall be sampled and tested in accordance with the requirements of clause 503.05, except that each sample shall consist of four specimens tested in accordance with AS 1012. The mean compressive strength shall be the average of at least three individual results within a range of 2.0 MPa. The minimum cementitious material content in the lean subbase course mix shall be 150 kg/m3 of concrete. | Document Review | Each Lot | HP | Nominated Authority | ConQA Hold Point Release
2.2 | Plant and Equipment | Vic Road 503.07 | Equipment as proposed for the construction of the full scale works, to satisfy the specification requirements. | Document Review | Each period/change | IP | Nominated Authority | ConQA Hold Point Release
3 | Construction Activities
3.1 | Check subgrade or lower sub-base course | Vic Road 503.03 | Check the shape and level of base course and ensure specified thickness of concrete is achieved. Surface must be clean and free of excess water | Visual | Each Lot | IP | SE/PE | This ITP
3.2 | Inspection of the Area & Formwork | Vic Road 503.07a | The area in which concrete is proposed to be placed shall be inspected and checked immediately prior to commencement of placing. | Visual | Each Lot | HP | SE/PE | This ITP
3.3 | Commence hand placing of concrete | Vic road 503.07 | Concrete shall not be placed until the proposed method of placement, spacing of planned transverse construction joints and the provision of dowels, constructed formwork, reinforcement and embedments conforming to the requirements of this specification and the drawings, has been reviewed by the Superintendent For the subbase course loose material shall be removed from the surface of the subgrade and the subgrade shall be wetted to ensure a uniformly moist surface at the time of placing. Concrete shall not be placed when the temperature is below 5C or above 35C and the temperature of concrete, when placed, shall be not less than 10C nor more than 32C. Concrete shall not be placed when rain is falling or when rain is expected within one hour of placing. The Contractor shall have available on site sufficient waterproof covers to protect the freshly placed concrete against the effects of unexpected rain. Covers when required shall be installed in such a manner to not disturb the surface of the subbase or base slab. | Visual | Each Lot | HP | Nominated Authority | ConQA Hold Point Release
3.4 | Assesment of Concrete | Vic Road 503.05e(ii) | Assessment of concrete shall be based upon the following criterion: (i) 28 day compressive strength values of cylinder specimens cast on site with strengths adjusted for in situ density; (ii) thickness determined from subbase and base surface level measurements; (iii) rideability as indicated by the Profile Factor. The Contractor shall sample, prepare, cure and compression test the cylinders cast on site in accordance with AS 1012. | Visual | Each Lot | NATA | SE/PE | This ITP
4 | Post-construction Activities
4.1 | Complete Straight edge Finishing | Vic road 503.03 | (a) Alignment The edge of the base and subbase shall be within 15 mm and 25 mm of the plan location, respectively. The horizontal alignment of the edges shall not deviate by more than 5 mm and 10 mm from a 3 metre straight edge placed along the edge of the base and subbase, respectively Surface Level The level at the top of the base shall not be less than the specified level nor exceed the specified level by more than 10 mm except against kerb and channel where the surface shall be flush with or not more than 5 mm above the lip of the channel. The level of the top of the subbase shall not exceed the specified level or be more than 15 mm below the specified level. Shape No point on the finished surface of the base shall lie more than 5 mm below a 3 metre straight edge laid on the surface at any location, and in any direction, including across joints. The surface shape of the base shall be such that water cannot pond at any point. No point on the surface of the subbase shall lie more than 5 mm below a 3 metre straight edge laid on the surface in any direction. | Visual | Each Lot | IP | SE/PE | This ITP
4.2 | Curing | Vic 503.18 | Prior to the use of curing compounds, the Contractor shall submit to the Superintendent for review not less than four weeks prior to placement of concrete Concrete shall not be placed until the Superintendent has reviewed the proposed method of placement, compaction, and curing of concrete. | Visual | Each Lot | IP | Nominated Authority | ConQA Hold Point Release
4.3 | Ensure adequate surface protection | Vic 503.18 | Curing protection for base and subbase concrete shall be achieved by the application of a chlorinated rubber curing compound and a pigmented wax emulsion curing compound respectively , complying with the requirements of AS 3799. Two coats shall be applied at the full rate. The compound shall be sprayed onto the concrete surface at a rate of 0.2 l/m2 per coat. | Visual | Each Lot | IP | SE/PE | This ITP
4.4 | Conduct surface smoothness testing | Vic 503.07c | Shape No point on the finished surface of the base shall lie more than 5 mm below a 3 metre straight edge laid on the surface at any location, and in any direction, including across joints. The surface shape of the base shall be such that water cannot pond at any point. No point on the surface of the subbase shall lie more than 5 mm below a 3 metre straight edge laid on the surface in any direction. | Visual | Each Lot | IP | SE/PE | This ITP
4.5 | Complete Survey Conformance and submit report | Vic 503.03b | The level at the top of the base shall not be less than the specified level nor exceed the specified level by more than 10 mm except against kerb and channel where the surface shall be flush with or not more than 5 mm above the lip of the channel. The level of the top of the subbase shall not exceed the specified level or be more than 15 mm below the specified level. | Visual | Each Lot | HP* | Nominated Authority | ConQA Hold Point Release
4.6 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /