## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource ID
checklist | ITP-299-CIV-PSDS-Lean Concrete | itp |  |  |  |  | ITP-299-CIV-PSDS-Lean Concrete Rev 0
section | Referenced Documentation
checkpoint | Referenced Documentation
label | Document Title: ITP-299-CIV-PSDS-Lean Concrete
label | ITP Description: PSDS-Lean Concrete
label | Discipline (e.g. CIV/STR/RAIL): 299-CIV
label | Revision Number: 0
label | Revision Date: 7/08/2025
label | ITP created by: Nathan Cooper
label | ITP approved for use by: Romualdo Magpantay
label | 1.1 Non Dependent
label | Reference: Vic road 503 November 2018
label | 1.2 Non Dependent
label | Reference: Vic Road 173,408,610,687, 689
label | 1.3 Non Dependent
label | Reference: AS 1012
label | 1.4 Non Dependent
label | Reference: AS 1379
section | Preliminaries - Materials
checkpoint | 2.1 Concrete mix
label | REFERENCE: Vic Road 503.04
label | ACCEPTANCE CRITERIA: Ensure all plant, materials, mix design and/or any additional approvals have been obtained prior to planning commencement.
label | ○ Requirements for Lean Mix Concrete Subbase Course
label | ○ The mean 28 day compressive strength of the concrete mix used for the construction of the lean mix concrete subbase course shall be 6 MPa to 15 MPa. The lean mix concrete shall be sampled and tested in accordance with the requirements of clause 503.05, except that each sample shall consist of four specimens tested in accordance with AS 1012. The mean compressive strength shall be the average of at least three individual results within a range of 2.0 MPa.
label | ○ The minimum cementitious material content in the lean subbase course mix shall be 150 kg/m3 of concrete.
label | METHOD: Document Review
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 2.2 Plant and Equipment
label | REFERENCE: Vic Road 503.07
label | ACCEPTANCE CRITERIA: Equipment as proposed for the construction of the full scale works, to satisfy the specification requirements.
label | METHOD: Document Review
label | FREQUENCY: Each period/change
label | CATEGORY: IP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
section | Construction Activities
checkpoint | 3.1 Check subgrade or lower sub-base course
label | REFERENCE: Vic Road 503.03
label | ACCEPTANCE CRITERIA: Check the shape and level of base course and ensure specified thickness of concrete is achieved.
label | ○ Surface must be clean and free of excess water
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 3.2 Inspection of the Area & Formwork
label | REFERENCE: Vic Road 503.07a
label | ACCEPTANCE CRITERIA: The area in which concrete is proposed to be placed shall be inspected and checked immediately prior to commencement of placing.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.3 Commence hand placing of concrete
label | REFERENCE: Vic road 503.07
label | ACCEPTANCE CRITERIA: Concrete shall not be placed until the proposed method of placement, spacing of planned transverse construction joints and the provision of dowels, constructed formwork, reinforcement and embedments conforming to the requirements of this specification and the drawings, has been reviewed by the Superintendent
label | ○ For the subbase course loose material shall be removed from the surface of the subgrade and the subgrade shall be wetted to ensure a uniformly moist surface at the time of placing.
label | ○ Concrete shall not be placed when the temperature is below 5C or above 35C and the temperature of concrete, when placed, shall be not less than 10C nor more than 32C. Concrete shall not be placed when rain is falling or when rain is expected within one hour of placing. The Contractor shall have available on site sufficient waterproof covers to protect the freshly placed concrete against the effects of unexpected rain. Covers when required shall be installed in such a manner to not disturb the surface of the subbase or base slab.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: HP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
holdpoint | NOMINATED AUTHORITY HOLDPOINT
checkpoint | 3.4 Assesment of Concrete
label | REFERENCE: Vic Road 503.05e(ii)
label | ACCEPTANCE CRITERIA: Assessment of concrete shall be based upon the following criterion:
label | (i) 28 day compressive strength values of cylinder specimens cast on site with strengths adjusted for in situ density;
label | (ii) thickness determined from subbase and base surface level measurements;
label | (iii) rideability as indicated by the Profile Factor.
label | ○ The Contractor shall sample, prepare, cure and compression test the cylinders cast on site in accordance with AS 1012.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: NATA
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
section | Post-construction Activities
checkpoint | 4.1 Complete Straight edge Finishing
label | REFERENCE: Vic road 503.03
label | ACCEPTANCE CRITERIA: (a) Alignment
label | ○ The edge of the base and subbase shall be within 15 mm and 25 mm of the plan location, respectively. The horizontal alignment of the edges shall not deviate by more than 5 mm and 10 mm from a 3 metre straight edge placed along the edge of the base and subbase, respectively
label | Surface Level
label | — The level at the top of the base shall not be less than the specified level nor exceed the specified level by more than 10 mm except against kerb and channel where the surface shall be flush with or not more than 5 mm above the lip of the channel.
label | — The level of the top of the subbase shall not exceed the specified level or be more than 15 mm below the specified level.
label | Shape
label | — No point on the finished surface of the base shall lie more than 5 mm below a 3 metre straight edge laid on the surface at any location, and in any direction, including across joints. The surface shape of the base shall be such that water cannot pond at any point.
label | — No point on the surface of the subbase shall lie more than 5 mm below a 3 metre straight edge laid on the surface in any direction.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.2 Curing
label | REFERENCE: Vic 503.18
label | ACCEPTANCE CRITERIA: Prior to the use of curing compounds, the Contractor shall submit to the Superintendent for review not less than four weeks prior to placement of concrete
label | ○ Concrete shall not be placed until the Superintendent has reviewed the proposed method of placement, compaction, and curing of concrete.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
checkpoint | 4.3 Ensure adequate surface protection
label | REFERENCE: Vic 503.18
label | ACCEPTANCE CRITERIA: Curing protection for base and subbase concrete shall be achieved by the application of a chlorinated rubber curing compound and a pigmented wax emulsion curing compound respectively , complying with the requirements of AS 3799. Two coats shall be applied at the full rate. The compound shall be sprayed onto the concrete surface at a rate of 0.2 l/m2 per coat.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.4 Conduct surface smoothness testing
label | REFERENCE: Vic 503.07c
label | ACCEPTANCE CRITERIA: Shape
label | ○ No point on the finished surface of the base shall lie more than 5 mm below a 3 metre straight edge laid on the surface at any location, and in any direction, including across joints. The surface shape of the base shall be such that water cannot pond at any point.
label | ○ No point on the surface of the subbase shall lie more than 5 mm below a 3 metre straight edge laid on the surface in any direction.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: IP
label | RESPONSIBILITY: SE/PE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | 4.5 Complete Survey Conformance and submit report
label | REFERENCE: Vic 503.03b
label | ACCEPTANCE CRITERIA: The level at the top of the base shall not be less than the specified level nor exceed the specified level by more than 10 mm except against kerb and channel where the surface shall be flush with or not more than 5 mm above the lip of the channel.
label | ○ The level of the top of the subbase shall not exceed the specified level or be more than 15 mm below the specified level.
label | METHOD: Visual
label | FREQUENCY: Each Lot
label | CATEGORY: HP*
label | RESPONSIBILITY: Nominated Authority
label | VERIFYING DOCUMENTS: ConQA Hold Point Release
date | Date Completed:
checkpoint | 4.6 Non-conformance Report (NCR) Closure
label | REFERENCE: MRPA Quality Management Plan
label | ACCEPTANCE CRITERIA: Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
label | METHOD: Document Review
label | FREQUENCY: Once, prior to closure of this lot / element / Work area
label | CATEGORY: HP*
label | RESPONSIBILITY: SE/PE/SPE
label | VERIFYING DOCUMENTS: This ITP
date | Date Completed:
checkpoint | Final Inspection
label | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
text | Name:
text | Position:
date | Date Completed:
holdpoint | Sign ITP