## struct
resource | type | Add Step | Add Post | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Tier 5 | Tier 6 | Tier 7 | Tier 8 | Tier 9
| step |  |  | Tier 1: 9-11 Lindsay Kangaroo Flat
| step |  |  | Tier 2: IN GROUNDS
Ingrounds - Drainage | checklist |  |  | Tier 3: Ingrounds - Drainage
Ingrounds - Pumpwells/Tanks/Pits | checklist |  |  | Tier 3: Ingrounds - Pumpwells/Tanks/Pits
Ingrounds - Cast in | checklist |  |  | Tier 3: Ingrounds - Cast in
Ingrounds - Sewer BT Authority Connection | checklist |  |  | Tier 3: Ingrounds - Sewer BT Authority Connection
Ingrounds - Stormwater LPD | checklist |  |  | Tier 3: Ingrounds - Stormwater LPD
Ingrounds - Sewer BT Authority Connection | checklist |  |  | Tier 3: Ingrounds - Authority connection to meter room
| step |  |  | Tier 2: DRAINS
Drains: Underslung - Sewer, Stormwater & Vent | checklist |  |  | Tier 3: Drains: Underslung - Sewer, Stormwater & Vent
| step |  |  | Tier 2: ROUGH IN
Main Run Rough In (Cold Water) | checklist |  |  | Tier 3: Main Run Rough In (Cold Water)
Main Run Rough In (Hot Water) | checklist |  |  | Tier 3: Main Run Rough In (Hot Water)
Rough In: House Water Services (High & Low Level Rough In) | checklist |  |  | Tier 3: Rough In: Apartment Water Services (High & Low Level Rough In)
| step |  |  | Tier 2: FITOFF
Fit Off/ Fixture Install - Toilets & Cisterns | checklist |  |  | Tier 3: Fit Off/ Fixture Install - Toilets & Cisterns
Fit Off/ Fixture Install - All Items | checklist |  |  | Tier 3: Fit Off/ Fixture Install - All Items
Fit Off/ Fixture Install - Waste & Trap Clean Out | checklist |  |  | Tier 3: Fit Off/ Fixture Install - Waste & Trap Clean Out
Fit Off/ Fixture Install - Hose Taps | checklist |  |  | Tier 3: Fit Off/ Fixture Install - Hose Taps
| step |  |  | Tier 2: TESTING
Testing - Potable Water - 1500kpa water test (not an air test) | checklist |  |  | Tier 3: Testing - Potable Water - 1500kpa water test (not an air test)
Testing - Potable Water - 500kpa water test pressure sensitive valves (not an air test) | checklist |  |  | Tier 3: Testing - Potable Water - 500kpa water test pressure sensitive valves (not an air test)
Testing Potable Water - (1.5 times maximum working pressure) | checklist |  |  | Tier 3: Testing Potable Water - (1.5 times maximum working pressure)
Testing - Water Hold - Sewer & Stormwater Underslung | checklist |  |  | Tier 3: Testing - Water Hold - Sewer & Stormwater Underslung
Testing - Air Test - Stormwater & Downpipe | checklist |  |  | Tier 3: Testing - Air Test - Stormwater & Downpipe
Testing - Air Test - Sewer | checklist |  |  | Tier 3: Testing - Air Test - Sewer
Plant & Equipment Install - Sewer Pumpwell/s | checklist |  |  | Tier 3: Plant & Equipment Install - Sewer Pumpwell/s
Plant & Equipment Install - Stormwater Pumpwell/s | checklist |  |  | Tier 3: Plant & Equipment Install - Stormwater Pumpwell/s
Plant & Equipment Install - Stormwater Treatment System/Filter | checklist |  |  | Tier 3: Plant & Equipment Install - Stormwater Treatment System/Filter
Plant & Equipment Install - Rainwater Tank | checklist |  |  | Tier 3: Plant & Equipment Install - Rainwater Tank
Plant & Equipment Install - Rainwater Tank | checklist |  |  | Tier 3: Plant & Equipment Install - Water Storage Tank
| step |  |  | Tier 2: COMMISSIONING/ HANDOVER
Comm/HO - TMV | checklist |  |  | Tier 3: Comm/HO - TMV
Comm/HO - Tempering Valve | checklist |  |  | Tier 3: Comm/HO - Tempering Valve
Comm/HO - Apartment Final Commissioning - Fixture Group | checklist |  |  | Tier 3: Comm/HO - House Final Commissioning - Fixture Group
FINAL Commissioning - Hot Water Plant | checklist |  |  | Tier 3: FINAL Commissioning - Hot Water Plant
FINAL Commissioning - Cold Water Pumpset | checklist |  |  | Tier 3: FINAL Commissioning - Cold Water Pumpset
FINAL Commissioning - Sewer Pumpwell/s | checklist |  |  | Tier 3: FINAL Commissioning - Sewer Pumpwell/s
FINAL Commissioning - Stormwater Pumpwell/s | checklist |  |  | Tier 3: FINAL Commissioning - Stormwater Pumpwell/s
FINAL Commissioning - Stormwater Treatment System/Filter | checklist |  |  | Tier 3: FINAL Commissioning - Stormwater Treatment System/Filter
| step |  |  | Tier 1: 10 Anderson St Horsham
| step |  |  | Tier 2: IN GROUNDS
Ingrounds - Drainage | checklist |  |  | Tier 3: Ingrounds - Drainage
Ingrounds - Pumpwells/Tanks/Pits | checklist |  |  | Tier 3: Ingrounds - Pumpwells/Tanks/Pits
Ingrounds - Cast in | checklist |  |  | Tier 3: Ingrounds - Cast in
Ingrounds - Sewer BT Authority Connection | checklist |  |  | Tier 3: Ingrounds - Sewer BT Authority Connection
Ingrounds - Stormwater LPD | checklist |  |  | Tier 3: Ingrounds - Stormwater LPD
Ingrounds - Sewer BT Authority Connection | checklist |  |  | Tier 3: Ingrounds - Authority connection to meter room
| step |  |  | Tier 2: DRAINS
Drains: Underslung - Sewer, Stormwater & Vent | checklist |  |  | Tier 3: Drains: Underslung - Sewer, Stormwater & Vent
| step |  |  | Tier 2: ROUGH IN
Main Run Rough In (Cold Water) | checklist |  |  | Tier 3: Main Run Rough In (Cold Water)
Main Run Rough In (Hot Water) | checklist |  |  | Tier 3: Main Run Rough In (Hot Water)
Rough In: House Water Services (High & Low Level Rough In) | checklist |  |  | Tier 3: Rough In: Apartment Water Services (High & Low Level Rough In)
| step |  |  | Tier 2: FITOFF
Fit Off/ Fixture Install - Toilets & Cisterns | checklist |  |  | Tier 3: Fit Off/ Fixture Install - Toilets & Cisterns
Fit Off/ Fixture Install - All Items | checklist |  |  | Tier 3: Fit Off/ Fixture Install - All Items
Fit Off/ Fixture Install - Waste & Trap Clean Out | checklist |  |  | Tier 3: Fit Off/ Fixture Install - Waste & Trap Clean Out
Fit Off/ Fixture Install - Hose Taps | checklist |  |  | Tier 3: Fit Off/ Fixture Install - Hose Taps
| step |  |  | Tier 2: TESTING
Testing - Potable Water - 1500kpa water test (not an air test) | checklist |  |  | Tier 3: Testing - Potable Water - 1500kpa water test (not an air test)
Testing - Potable Water - 500kpa water test pressure sensitive valves (not an air test) | checklist |  |  | Tier 3: Testing - Potable Water - 500kpa water test pressure sensitive valves (not an air test)
Testing Potable Water - (1.5 times maximum working pressure) | checklist |  |  | Tier 3: Testing Potable Water - (1.5 times maximum working pressure)
Testing - Water Hold - Sewer & Stormwater Underslung | checklist |  |  | Tier 3: Testing - Water Hold - Sewer & Stormwater Underslung
Testing - Air Test - Stormwater & Downpipe | checklist |  |  | Tier 3: Testing - Air Test - Stormwater & Downpipe
Testing - Air Test - Sewer | checklist |  |  | Tier 3: Testing - Air Test - Sewer
Plant & Equipment Install - Sewer Pumpwell/s | checklist |  |  | Tier 3: Plant & Equipment Install - Sewer Pumpwell/s
Plant & Equipment Install - Stormwater Pumpwell/s | checklist |  |  | Tier 3: Plant & Equipment Install - Stormwater Pumpwell/s
Plant & Equipment Install - Stormwater Treatment System/Filter | checklist |  |  | Tier 3: Plant & Equipment Install - Stormwater Treatment System/Filter
Plant & Equipment Install - Rainwater Tank | checklist |  |  | Tier 3: Plant & Equipment Install - Rainwater Tank
Plant & Equipment Install - Rainwater Tank | checklist |  |  | Tier 3: Plant & Equipment Install - Water Storage Tank
| step |  |  | Tier 2: COMMISSIONING/ HANDOVER
Comm/HO - TMV | checklist |  |  | Tier 3: Comm/HO - TMV
Comm/HO - Tempering Valve | checklist |  |  | Tier 3: Comm/HO - Tempering Valve
Comm/HO - Apartment Final Commissioning - Fixture Group | checklist |  |  | Tier 3: Comm/HO - House Final Commissioning - Fixture Group
FINAL Commissioning - Hot Water Plant | checklist |  |  | Tier 3: FINAL Commissioning - Hot Water Plant
FINAL Commissioning - Cold Water Pumpset | checklist |  |  | Tier 3: FINAL Commissioning - Cold Water Pumpset
FINAL Commissioning - Sewer Pumpwell/s | checklist |  |  | Tier 3: FINAL Commissioning - Sewer Pumpwell/s
FINAL Commissioning - Stormwater Pumpwell/s | checklist |  |  | Tier 3: FINAL Commissioning - Stormwater Pumpwell/s
FINAL Commissioning - Stormwater Treatment System/Filter | checklist |  |  | Tier 3: FINAL Commissioning - Stormwater Treatment System/Filter
| step |  |  | Tier 1: 65 MacArthur Place Carlton
| step |  |  | Tier 2: IN GROUNDS
Ingrounds - Drainage | checklist |  |  | Tier 3: Ingrounds - Drainage
Ingrounds - Pumpwells/Tanks/Pits | checklist |  |  | Tier 3: Ingrounds - Pumpwells/Tanks/Pits
Ingrounds - Cast in | checklist |  |  | Tier 3: Ingrounds - Cast in
Ingrounds - Sewer BT Authority Connection | checklist |  |  | Tier 3: Ingrounds - Sewer BT Authority Connection
Ingrounds - Stormwater LPD | checklist |  |  | Tier 3: Ingrounds - Stormwater LPD
Ingrounds - Sewer BT Authority Connection | checklist |  |  | Tier 3: Ingrounds - Authority connection to meter room
| step |  |  | Tier 2: DRAINS
Drains: Underslung - Sewer, Stormwater & Vent | checklist |  |  | Tier 3: Drains: Underslung - Sewer, Stormwater & Vent
| step |  |  | Tier 2: ROUGH IN
Main Run Rough In (Cold Water) | checklist |  |  | Tier 3: Main Run Rough In (Cold Water)
Main Run Rough In (Hot Water) | checklist |  |  | Tier 3: Main Run Rough In (Hot Water)
Rough In: House Water Services (High & Low Level Rough In) | checklist |  |  | Tier 3: Rough In: Apartment Water Services (High & Low Level Rough In)
| step |  |  | Tier 2: FITOFF
Fit Off/ Fixture Install - Toilets & Cisterns | checklist |  |  | Tier 3: Fit Off/ Fixture Install - Toilets & Cisterns
Fit Off/ Fixture Install - All Items | checklist |  |  | Tier 3: Fit Off/ Fixture Install - All Items
Fit Off/ Fixture Install - Waste & Trap Clean Out | checklist |  |  | Tier 3: Fit Off/ Fixture Install - Waste & Trap Clean Out
Fit Off/ Fixture Install - Hose Taps | checklist |  |  | Tier 3: Fit Off/ Fixture Install - Hose Taps
| step |  |  | Tier 2: TESTING
Testing - Potable Water - 1500kpa water test (not an air test) | checklist |  |  | Tier 3: Testing - Potable Water - 1500kpa water test (not an air test)
Testing - Potable Water - 500kpa water test pressure sensitive valves (not an air test) | checklist |  |  | Tier 3: Testing - Potable Water - 500kpa water test pressure sensitive valves (not an air test)
Testing Potable Water - (1.5 times maximum working pressure) | checklist |  |  | Tier 3: Testing Potable Water - (1.5 times maximum working pressure)
Testing - Water Hold - Sewer & Stormwater Underslung | checklist |  |  | Tier 3: Testing - Water Hold - Sewer & Stormwater Underslung
Testing - Air Test - Stormwater & Downpipe | checklist |  |  | Tier 3: Testing - Air Test - Stormwater & Downpipe
Testing - Air Test - Sewer | checklist |  |  | Tier 3: Testing - Air Test - Sewer
Plant & Equipment Install - Sewer Pumpwell/s | checklist |  |  | Tier 3: Plant & Equipment Install - Sewer Pumpwell/s
Plant & Equipment Install - Stormwater Pumpwell/s | checklist |  |  | Tier 3: Plant & Equipment Install - Stormwater Pumpwell/s
Plant & Equipment Install - Stormwater Treatment System/Filter | checklist |  |  | Tier 3: Plant & Equipment Install - Stormwater Treatment System/Filter
Plant & Equipment Install - Rainwater Tank | checklist |  |  | Tier 3: Plant & Equipment Install - Rainwater Tank
Plant & Equipment Install - Rainwater Tank | checklist |  |  | Tier 3: Plant & Equipment Install - Water Storage Tank
| step |  |  | Tier 2: COMMISSIONING/ HANDOVER
Comm/HO - TMV | checklist |  |  | Tier 3: Comm/HO - TMV
Comm/HO - Tempering Valve | checklist |  |  | Tier 3: Comm/HO - Tempering Valve
Comm/HO - Apartment Final Commissioning - Fixture Group | checklist |  |  | Tier 3: Comm/HO - House Final Commissioning - Fixture Group
FINAL Commissioning - Hot Water Plant | checklist |  |  | Tier 3: FINAL Commissioning - Hot Water Plant
FINAL Commissioning - Cold Water Pumpset | checklist |  |  | Tier 3: FINAL Commissioning - Cold Water Pumpset
FINAL Commissioning - Sewer Pumpwell/s | checklist |  |  | Tier 3: FINAL Commissioning - Sewer Pumpwell/s
FINAL Commissioning - Stormwater Pumpwell/s | checklist |  |  | Tier 3: FINAL Commissioning - Stormwater Pumpwell/s
FINAL Commissioning - Stormwater Treatment System/Filter | checklist |  |  | Tier 3: FINAL Commissioning - Stormwater Treatment System/Filter
| step |  |  | Tier 1: 71 Bernard St Cheltenham
| step |  |  | Tier 2: IN GROUNDS
Ingrounds - Drainage | checklist |  |  | Tier 3: Ingrounds - Drainage
Ingrounds - Pumpwells/Tanks/Pits | checklist |  |  | Tier 3: Ingrounds - Pumpwells/Tanks/Pits
Ingrounds - Cast in | checklist |  |  | Tier 3: Ingrounds - Cast in
Ingrounds - Sewer BT Authority Connection | checklist |  |  | Tier 3: Ingrounds - Sewer BT Authority Connection
Ingrounds - Stormwater LPD | checklist |  |  | Tier 3: Ingrounds - Stormwater LPD
Ingrounds - Sewer BT Authority Connection | checklist |  |  | Tier 3: Ingrounds - Authority connection to meter room
| step |  |  | Tier 2: DRAINS
Drains: Underslung - Sewer, Stormwater & Vent | checklist |  |  | Tier 3: Drains: Underslung - Sewer, Stormwater & Vent
| step |  |  | Tier 2: ROUGH IN
Main Run Rough In (Cold Water) | checklist |  |  | Tier 3: Main Run Rough In (Cold Water)
Main Run Rough In (Hot Water) | checklist |  |  | Tier 3: Main Run Rough In (Hot Water)
Rough In: House Water Services (High & Low Level Rough In) | checklist |  |  | Tier 3: Rough In: Apartment Water Services (High & Low Level Rough In)
| step |  |  | Tier 2: FITOFF
Fit Off/ Fixture Install - Toilets & Cisterns | checklist |  |  | Tier 3: Fit Off/ Fixture Install - Toilets & Cisterns
Fit Off/ Fixture Install - All Items | checklist |  |  | Tier 3: Fit Off/ Fixture Install - All Items
Fit Off/ Fixture Install - Waste & Trap Clean Out | checklist |  |  | Tier 3: Fit Off/ Fixture Install - Waste & Trap Clean Out
Fit Off/ Fixture Install - Hose Taps | checklist |  |  | Tier 3: Fit Off/ Fixture Install - Hose Taps
| step |  |  | Tier 2: TESTING
Testing - Potable Water - 1500kpa water test (not an air test) | checklist |  |  | Tier 3: Testing - Potable Water - 1500kpa water test (not an air test)
Testing - Potable Water - 500kpa water test pressure sensitive valves (not an air test) | checklist |  |  | Tier 3: Testing - Potable Water - 500kpa water test pressure sensitive valves (not an air test)
Testing Potable Water - (1.5 times maximum working pressure) | checklist |  |  | Tier 3: Testing Potable Water - (1.5 times maximum working pressure)
Testing - Water Hold - Sewer & Stormwater Underslung | checklist |  |  | Tier 3: Testing - Water Hold - Sewer & Stormwater Underslung
Testing - Air Test - Stormwater & Downpipe | checklist |  |  | Tier 3: Testing - Air Test - Stormwater & Downpipe
Testing - Air Test - Sewer | checklist |  |  | Tier 3: Testing - Air Test - Sewer
Plant & Equipment Install - Sewer Pumpwell/s | checklist |  |  | Tier 3: Plant & Equipment Install - Sewer Pumpwell/s
Plant & Equipment Install - Stormwater Pumpwell/s | checklist |  |  | Tier 3: Plant & Equipment Install - Stormwater Pumpwell/s
Plant & Equipment Install - Stormwater Treatment System/Filter | checklist |  |  | Tier 3: Plant & Equipment Install - Stormwater Treatment System/Filter
Plant & Equipment Install - Rainwater Tank | checklist |  |  | Tier 3: Plant & Equipment Install - Rainwater Tank
Plant & Equipment Install - Rainwater Tank | checklist |  |  | Tier 3: Plant & Equipment Install - Water Storage Tank
| step |  |  | Tier 2: COMMISSIONING/ HANDOVER
Comm/HO - TMV | checklist |  |  | Tier 3: Comm/HO - TMV
Comm/HO - Tempering Valve | checklist |  |  | Tier 3: Comm/HO - Tempering Valve
Comm/HO - Apartment Final Commissioning - Fixture Group | checklist |  |  | Tier 3: Comm/HO - House Final Commissioning - Fixture Group
FINAL Commissioning - Hot Water Plant | checklist |  |  | Tier 3: FINAL Commissioning - Hot Water Plant
FINAL Commissioning - Cold Water Pumpset | checklist |  |  | Tier 3: FINAL Commissioning - Cold Water Pumpset
FINAL Commissioning - Sewer Pumpwell/s | checklist |  |  | Tier 3: FINAL Commissioning - Sewer Pumpwell/s
FINAL Commissioning - Stormwater Pumpwell/s | checklist |  |  | Tier 3: FINAL Commissioning - Stormwater Pumpwell/s
FINAL Commissioning - Stormwater Treatment System/Filter | checklist |  |  | Tier 3: FINAL Commissioning - Stormwater Treatment System/Filter