## Master List Templates
Id | Type | Name | Values | Prompting Name
afe7b93c-e018-4620-95e8-f586559d6c73 | checklist | Other Information |  | Other Information
b7f2991a-02f4-416a-9e95-d3cdf3e53c35 | section | Other Information
cbfdf91b-92cf-488e-9730-4a0d536770f2 | checkpoint | Variations and other works added into folder
61fc5e2a-e949-4f16-9903-8695497ed79e | checkpoint | Change of details or instructions
76417648-05a2-443a-95c5-81c8d7339ccf | checkpoint | Day works sheet extras
de885582-29e5-490f-8472-5a8bffd9b52d | checkpoint | Snag and defects list
96b38f51-ef5d-4422-a043-8de4c1b99929 | checkpoint | Materials storage ideas
9f97639d-7a4e-4f15-b157-f021c356f318 | checkpoint | Site specific details to be added
ac302691-0c9a-48ed-8965-bb3498b2944d | checkpoint | Materials Details - Notes of all materials used on site
3d30d3a0-e525-40c8-8b57-cb6268981cad | checkpoint | SSSP/TA forms attached
d5cab1a1-4706-4f77-9ee8-af49e807fc1f | checklist | Prestart Inspections |  | Prestart Inspection
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
53d67355-675c-4840-b155-e0fa2008411d | checkpoint | site has been cleaned in advance of our arrival on site
f7485b84-bbd5-4c58-9764-dca6cb0c94df | checkpoint | Walls are plumb and level
17237867-99fb-5d85-8274-d65f3d6132fe | note | IMPORTANT
1745bcd6-9335-419e-9df9-37723fc3955d | checkpoint | Tiling works running to programme - prior trades completed
bf9e1efa-a0ee-43a3-8cfd-8444bb06b94e | checkpoint | Has prior trades QA been signed off by main contractor
6e5aefd5-7f6a-4e3a-ac52-0f436eed6cb5 | checkpoint | Gib compound and sanding cleaned up from rooms
1cae73ac-41c3-4ebf-b6eb-8ee8616d3589 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor
55896372-e42c-4051-a23d-d44574f48486 | checkpoint | Inductions completed
505cbf24-8732-454b-aca7-b03ff989b11e | checkpoint | Site Inspection checklist has been completed
eb6918b8-1f41-4890-b024-d7e9a8350748 | checkpoint | All tools tagged and tested - (photo's required)
f063db2c-d159-47e2-b20a-43d687375d09 | checkpoint | Tiler has current site safe - Input number and expiry
2f702504-ffd2-40f8-9ea4-b6ae7b904925 | checkpoint | Tiler has correct PPE
87ce21dc-42bf-4693-9fa5-d550c96d31f3 | checkpoint | Correct drawings supplied as per onsite
babd3f93-cbf9-435e-92ef-5b3ea971e164 | checklist | QA - Floor Prep |  | QA - Floor Prep
3619af8f-edc7-4bd1-8a59-ed389d6199e9 | section | Floor Preparation
2ecdf421-b531-4687-b0ad-dadfbac1b1e1 | checkpoint | Is the area clean, and cleared, ready for necessary preparation
54bd46d0-a73a-4fc5-a959-cae704d0f6bc | checkpoint | Uplift carpet tiles
781d95fd-8d83-4faf-9848-89b5e41e1a3f | checkpoint | Floor preparation prior to tiling works completed
772c243e-b7eb-40ef-a6af-cfe7ff004fc0 | checkpoint | Grinding completed before works (photo required) after works (photo required)
04b99b35-b982-4bec-9269-2966cd4acdf0 | checkpoint | Floor levelling completed - hours and bags used to be recorded
8a648840-6dd1-4434-b080-4f301426f811 | checklist | QA - Floor Prep Bathroom |  | Floor prep
2f23ef41-5682-48a3-8101-56bf093019ed | section | Floor Preparation
3fc406c7-9359-4938-a227-f3a383ce68a5 | checkpoint | Is the area clean, and cleared, ready for necesssary preparation
932d72c5-dfdd-4921-ac24-e46fcae574ae | checkpoint | Is the floor prep completed and signed off
05a6a013-56bb-42fb-a15e-d5abf0ab2e29 | checkpoint | PHOTOS OF COMPLETED FLOOR PREP
41b7787c-22e6-4a86-b507-8d1f5c6111b4 | checklist | QA - Other Information |  | QA - Other Information
5d463afb-a401-4a59-a03a-84086639cdad | section | Other Information
e9d0c639-a1dc-4049-b766-aee560118102 | checkpoint | Variations and other works added into folder
80aadb27-d72a-4c98-ae55-6df420270b26 | checkpoint | Change of details or instructions
4214602c-bd33-47a9-8a77-d602910ecccd | checkpoint | Day works sheet extras
a8b9140e-8f40-4407-a47b-39dbe8a31146 | checkpoint | Snag and defects list
06aa8464-20ec-444d-b7cd-d5230c21d3ed | checkpoint | Materials storage ideas
741853ac-69df-40c6-a1c7-f5193f56f4e5 | checkpoint | Site specific details to be added
84a12dfe-747d-4610-a43c-c0cea6b60d87 | checkpoint | Materials Details - Notes of all materials used on site
9661d80c-8d35-4c53-acf9-adfbf4a149ef | checklist | QA - Splashback Installation |  | QA - Splashback Installation
c068f249-61ca-443d-a9d1-9a735cbc2079 | section | Splashback Installation
3dd2704a-3c65-4374-8837-308bc6ffc2b8 | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
6ffedcdc-f0a0-4c7f-b2d8-eef62bf55b1f | checkpoint | Splashback Tiles set out as per drawings
317019f8-f6fd-4fa0-b8aa-989ca396c718 | checkpoint | Tiles to walls
3fd4dd31-053f-408f-ac3e-9699c6762eb6 | checkpoint | Tiling is completed, checked and supervisor to sign on
8d52757c-f21b-49ed-bd78-9981694ca949 | checkpoint | silicone nominated is the correct colour and applied evenly and correctly
19b91765-6e64-4100-a777-d97b24071bb2 | checkpoint | correct tiles trim is supplied and installed as per drawings
ab632c6c-fcc8-4aee-a526-24661cb5f9fd | checkpoint | Area left clean & tidy
537aee98-a26b-4b77-90a7-f35f379c438f | checkpoint | Builders clean completed
56c9a12c-0fff-4a87-a12d-7284f25c7e03 | checklist | QA - Tiling Installation |  | Tiling Installation
72561780-db17-4f1d-bb45-d80a89d7fc91 | section | Tiling to floors
f5b2622e-4b74-4ed4-9e02-c7594a84861f | checkpoint | Tiles set out according to latest drawing - always check revisions on site
3858c395-5dc1-418a-838b-7fb16e011cd9 | checkpoint | Specified product used with notched trowel or required product
965c2ab3-8140-49b4-8b99-32ca1a4ab034 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
ded2644e-3c20-4037-9b19-b3ad558bdb91 | checkpoint | Floor substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
5eb0dbf7-5168-44f0-ade0-39a41d10f1e6 | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
2e040d2a-621c-44e0-8696-5628bfac6fde | checkpoint | Grout is consistent throughout and no missing grout.
945ee99f-8a11-4e70-ab68-c08a6d2bbc73 | checkpoint | Tiling completed, checked and Supervisor sign off
4c43df00-c994-4b19-95b7-4d2da7fb8001 | checkpoint | Silicone is completed to all tile junctions where required
4170243c-4c46-491a-ab6b-18bbcfbc45ca | checkpoint | Area left clean & tidy
a9673e36-ac50-4e6a-ac56-e9f313778675 | checkpoint | Builders clean completed
2b8fb16b-aaaf-44cb-a33d-97e1e6a921c4 | checklist | QA - Waterproofing |  | QA - Waterproofing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
ff9a2a3f-a7fe-4ab6-9ce2-d580fb4400fd | checkpoint | Waterproof materials applied to floor perimeter and gaskets to flanges
04f2ba32-5133-4b43-a0d9-951fbbbee90c | checkpoint | Waterproofing coat # 1 applied to floors and walls in laundry, powder & bathroom floors and walls (take photos)
5d6d1cde-a6e2-4f2e-a16e-c9a8ab3d2bc9 | checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos)
6b52b27f-6d7e-4154-9149-0400faf2b7ab | checkpoint | Flood tests, if required, undertaken and photos provided.
883b848f-f3e3-4ab3-b9f0-7296849dbc33 | checklist | Wall prep |  | Wall prep
79937e9f-d2eb-4ae0-9fbb-ec458728f7cd | section | Wall Preparation
4ec840b8-e5f1-43ec-9991-75e069bedfd4 | checkpoint | Is the area clean, and cleared, ready for necesssary preparation
9c118890-310a-4f3c-8424-90aafe8c8a93 | checkpoint | Is the floor prep completed and signed off
7854748d-e61b-4350-927e-4e67e334ce9f | checkpoint | PHOTOS OF COMPLETED FLOOR PREP
25c22a57-a83d-4b04-a241-de7aa5c014f4 | checklist | Ω (DEPRECATED) Other Information (v0) |  | Other Information
b7f2991a-02f4-416a-9e95-d3cdf3e53c35 | section | Other Information
cbfdf91b-92cf-488e-9730-4a0d536770f2 | checkpoint | Variations or extra works added into folder - all works and materials noted
61fc5e2a-e949-4f16-9903-8695497ed79e | checkpoint | change of details and or instructions
9f97639d-7a4e-4f15-b157-f021c356f318 | checkpoint | Site specific details to be added
ac302691-0c9a-48ed-8965-bb3498b2944d | checkpoint | Material Details - Notes to be added of materials used on site
3d30d3a0-e525-40c8-8b57-cb6268981cad | checkpoint | SSSP/TA forms attached
11bb8521-aeb8-46e0-8c74-144e1bdae140 | checklist | Ω (DEPRECATED) QA - Other Information (v0) |  | QA - Other Information
5d463afb-a401-4a59-a03a-84086639cdad | section | Other Information
e9d0c639-a1dc-4049-b766-aee560118102 | checkpoint | Variations or extra works added into folder - all works and materials noted
80aadb27-d72a-4c98-ae55-6df420270b26 | checkpoint | change of details and or instructions
741853ac-69df-40c6-a1c7-f5193f56f4e5 | checkpoint | Site specific details to be added
84a12dfe-747d-4610-a43c-c0cea6b60d87 | checkpoint | Material Details - Notes to be added of materials used on site

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
49bbb526-a68e-493d-a8f0-75c23360266d | checklist | Final Sign Off for Invoicing |  | Final Sign Off for Invoicing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8d135d52-ae65-4fd2-ab6b-a0b35681e76e | checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
da703ebd-2ca5-452e-98e6-2cd07ba45bcc | checklist | QA - Joinery Unit Installation |  | QA - Joinery Unit Installation
c5f891d4-bfc2-4d54-834a-e049f71add2d | section | Joinery Unit Installation
35fa888b-d081-464a-8936-6c7a3b93cc64 | checkpoint | Is the area clean, and cleared, ready for necessary preparation
09ceb846-a35a-4018-893f-2930e963889b | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
7c80a34d-92f4-47ca-980a-460e507fa156 | checkpoint | Install tiles to J01 unit
34f6dbb0-e40e-4708-b0b4-6da65933a6b3 | checkpoint | Install tiles to J04 Unit
d0e6a7a7-4fec-492a-b952-70b3563e5d90 | checkpoint | Install tiles to J05 Unit
9875a8b0-dea9-4300-aaca-6c1691edaf8c | checkpoint | Install tiles to J11 Unit
b60965c8-2870-43f8-84d5-8079e6d11661 | checkpoint | Install tiles to J18 Unit
7de7ea8e-417c-43d7-b2af-bde586bd2ec5 | checkpoint | Install tiles to J27 Unit
0346e9bc-b5a1-4202-9635-1dc9e4ffd9ca | checkpoint | Install tiles to J28 Unit
09690933-631c-4e04-adeb-d6fc93e25dca | checkpoint | Grouting is consistent, neat and cleaned from surface.
b5094a94-2e4e-41c4-913d-62dc98a6c4bb | checkpoint | Tiling is completed, checked and supervisor to sign on
c6650db0-4b0c-4c05-8343-520e269487f2 | checkpoint | Silicone nominated is the correct colour and applied evenly and consistently
8d6f8f42-d57f-4f2d-9d7f-b3a6ee44ef6d | checkpoint | Correct tiles trim is supplied and installed as per drawings
83c2e3f0-e04d-4875-a6dd-6a58f518219a | checkpoint | Area left clean & tidy
5c7c417b-e134-4367-a5d9-9c29b2a39da0 | checkpoint | Builders clean completed
3eba02dd-002e-42b1-bb20-b41a64f888f9 | checklist | QA - Tiling Installation - Pool area |  | QA - Tiling Installation - Pool area
e063abda-3708-4004-9120-4382069bc496 | section | Tiling to floors and walls
d6f4a0d2-3cc8-4c6a-8a31-b8df3cfddfc4 | checkpoint | Tiles set out according to latest drawing - always check revisions on site
44d4824b-d541-40d1-a7e8-83fb13d6ccd4 | checkpoint | Specified product used with notched trowel or required product
fe946612-b5f1-4c21-a16e-6be840ad02be | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
82ddea9f-f0cb-4421-98ac-a87090eeb743 | checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
68e790d9-0bf4-4c03-9a1b-8e8ef6de9f47 | checkpoint | Install FT1 600x600 tiles to floors throughout pool area
f249a25b-663f-45c8-8b9d-c16d96f05aa9 | checkpoint | Cut & install FT2 20mm pool coping tiles to perimeter of pool
9a9d77b8-6731-4714-9699-fbd9aae8c1d6 | checkpoint | Install approx 280mm high waterline tile to pool with suitable adhesive
f419f539-9210-45a6-92d6-d36c4b7af34a | checkpoint | Supply & install, with epoxy adhesive, channel L-angle to tiled waterline base
d18d96cd-4594-4718-bd4e-b2f6c0b22563 | checkpoint | Install FT2 600x600 tiles to steps, upstand and top of spa pool
fc0262c3-835d-4d14-bfdc-f79befb63bb0 | checkpoint | Install FT1 600x600 tiles to upstands and wall top edge as per details
5a938a52-9e21-468b-be8a-4656a5938469 | checkpoint | Supply & install Stainless Steel capping trim below tiles
e91c8ee6-d581-4650-ba46-a24fa8f8cf0f | checkpoint | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
dbb8c9a3-aa28-498b-8daf-3e5bff5bc248 | checkpoint | Install WT1 & WT2 tiles to walls surrounding pool & pool shower
b6ff37a6-0123-4ca3-9f53-183d0b4b7d02 | checkpoint | Install WT1 tiles to nib ledge on pool/changing room tiled wall
22021897-dd4d-471f-bd0e-f053be8d6bf6 | checkpoint | Install WT3 tiles to back wall of pool area shower
004c7a4e-442c-4c09-a5ac-91e0a265947c | checkpoint | Install trim to horizontal & vertical wall tile edges
b49722a1-2f16-47f8-a87c-1ccf059ee0ff | checkpoint | Install WT1 & WT2 tiles to changing room walls
d8ac94ad-e256-44ca-a9be-28321eb02d08 | checkpoint | Install WT3 tiles to shower walls in changing room
dd40208b-313d-44ce-9b3a-8f7eefd84eef | checkpoint | Install step nosing to FT2 tiles into spa pool
ca101c5a-e694-4c74-a39d-3fffd01b7c38 | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
93246657-566b-44ea-997c-f28ca9ea7010 | checkpoint | Grout is consistent throughout and no missing grout.
4cd3a201-c215-4511-b08c-b55594beff68 | checkpoint | Tiling completed, checked and Supervisor sign off
e9d8eb04-13cd-4fc1-97f1-f5f605d0acdd | checkpoint | Silicone is completed to all tile junctions where required
60db23be-b90b-47d4-967a-952ab1f0acdb | checkpoint | Area left clean & tidy
82cd79cd-0124-4a0e-a7cc-29a3a2b726d3 | checkpoint | Builders clean completed
c9823575-02d7-423c-83c9-85c611e5fa76 | checklist | QA - Tiling Installation - WC's |  | QA - Tiling Installation - WC's
2435b6a1-6266-4717-b1e8-24a758922004 | section | Tiling to floors and walls
dd169c1d-cb6b-4672-9c70-3fdcdea3c58e | checkpoint | Tiles set out according to latest drawing - always check revisions on site
400eed9f-51de-41e2-9234-d5f68106e132 | checkpoint | Specified product used with notched trowel or required product
6ffe21b9-dbbb-416d-a49d-473658498cfc | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
eb7aa05d-0e47-4243-b571-a993b15ba34c | checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
71bacb89-1ee5-48e7-8c8f-27e4f104fb8a | checkpoint | Install FT3 tiles to floors in Accessible & WC rooms.
d2118983-3cc3-4f2d-b135-ec143017a551 | checkpoint | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
288f3f62-fb07-49f6-bcf3-d8053a72416a | checkpoint | Install WT4 tiles 1200 high to walls in 2# accessible rooms
ec1298a3-08e0-4ef8-8b69-815984e8f99a | checkpoint | Install WT4 tiles full height to 1 wall in 2# WC rooms
2ace2dcf-2ded-4835-b76c-f9180c1ec4fc | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
6549bfdc-3c3c-459e-82b8-364dd0613fdc | checkpoint | Grout is consistent throughout and no missing grout.
c7a48229-7820-4f4d-b9c9-14c698aa68f4 | checkpoint | Tiling completed, checked and Supervisor sign off
03ebb4cd-f96d-4ce0-9644-6b6f3d6b2844 | checkpoint | Silicone is completed to all tile junctions where required
01fae7c6-e251-4edd-9a09-23c8fe6cbfa9 | checkpoint | Area left clean & tidy
c12f1a05-2b9b-4aa2-a952-4aa87a3c892b | checkpoint | Builders clean completed
ac586e59-ab58-4ae0-99af-49eb1d5bd2f6 | checklist | Wall/Floor Preparation Pool Area |  | Wall/Floor Preparation Pool Area
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
f45f08d4-2a3c-46d7-9fc3-68d4bd8b62eb | checkpoint | Is the area clean, and cleared, ready for necessary preparation
cf95ff00-cd63-4fa7-bb7c-f7bd421818cc | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
850cb183-3ef8-47be-beed-d11e8dda31ea | checkpoint | Screed changing room floor to falls 1:50 as per drawings
c11efbc7-779d-4eec-bc90-85101f97adbc | checkpoint | Screed 3# of changing room shower bases to falls (25mm setdown)
62a1549f-bfb8-4125-862d-33a5904aaa0c | checkpoint | Screed floors to pool channel drain
9b42108f-11d8-44f1-8042-b65ebb786649 | checkpoint | Screed floors to floors in pool area shower as per drawings
478a705b-030f-4b4a-bf95-fa50850e33d1 | checkpoint | Apply 3mm skim coat approx 280mm high to water line tiled perimeter
b8de346b-5134-404c-b628-412ebbc9dc72 | checkpoint | All falls to shower base, or outside shower are correct and signed off by TAL Tiling manager
8bfee671-fbb7-4dab-b78b-d95c521ee51e | checkpoint | Grinding, if required, completed before works (photo required) after works (photo required)
d6ac3bd7-8279-42a5-8450-8857f4a1c009 | checkpoint | Floor levelling completed and applied as per requirements. (m2 rate)
1bcc22b0-1930-4123-a4e2-a24b201627c9 | checkpoint | Floor levelling completed - hours and bags used to be recorded (if per bag/labour rate)
1d5f4e97-da65-415c-84e1-aef7b2fb21c3 | checklist | Wall/Floor Preparation WC's |  | Wall/Floor Preparation WC's
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b34abf8a-bbe6-4035-b1fe-c1a159ec3e1c | checkpoint | Is the area clean, and cleared, ready for necessary preparation
fd87b503-ded9-419c-9f17-09fb9de27e98 | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
82683e67-19c3-4120-a299-83468a4148eb | checkpoint | Has screeding been completed to shower at correct height and falls with correct product
899776f5-ff45-48ef-8788-2f2e96f97d06 | checkpoint | All falls to shower base, or outside shower are correct and signed off by TAL Tiling manager
3735f1d6-649e-4f93-afac-ed56ca5ed3d4 | checkpoint | Grinding, if required, completed before works (photo required) after works (photo required)
09c29808-a700-4337-8823-80e91cd7aa87 | checkpoint | Floor levelling completed and applied as per requirements. (m2 rate)
e4b3cc33-52f4-46c5-88b6-d4d28b1ded7e | checkpoint | Floor levelling completed - hours and bags used to be recorded (if per bag/labour rate)