## Master List Templates
Id | Type | Name | Values | Prompting Name
afe7b93c-e018-4620-95e8-f586559d6c73 | checklist | Other Information |  | Other Information
b7f2991a-02f4-416a-9e95-d3cdf3e53c35 | section | Other Information
cbfdf91b-92cf-488e-9730-4a0d536770f2 | checkpoint | Variations and other works added into folder
61fc5e2a-e949-4f16-9903-8695497ed79e | checkpoint | Change of details or instructions
76417648-05a2-443a-95c5-81c8d7339ccf | checkpoint | Day works sheet extras
de885582-29e5-490f-8472-5a8bffd9b52d | checkpoint | Snag and defects list
96b38f51-ef5d-4422-a043-8de4c1b99929 | checkpoint | Materials storage ideas
9f97639d-7a4e-4f15-b157-f021c356f318 | checkpoint | Site specific details to be added
ac302691-0c9a-48ed-8965-bb3498b2944d | checkpoint | Materials Details - Notes of all materials used on site
3d30d3a0-e525-40c8-8b57-cb6268981cad | checkpoint | SSSP/TA forms attached
25c22a57-a83d-4b04-a241-de7aa5c014f4 | checklist | Ω (DEPRECATED) Other Information (v0) |  | Other Information
b7f2991a-02f4-416a-9e95-d3cdf3e53c35 | section | Other Information
cbfdf91b-92cf-488e-9730-4a0d536770f2 | checkpoint | Variations or extra works added into folder - all works and materials noted
61fc5e2a-e949-4f16-9903-8695497ed79e | checkpoint | change of details and or instructions
9f97639d-7a4e-4f15-b157-f021c356f318 | checkpoint | Site specific details to be added
ac302691-0c9a-48ed-8965-bb3498b2944d | checkpoint | Material Details - Notes to be added of materials used on site
3d30d3a0-e525-40c8-8b57-cb6268981cad | checkpoint | SSSP/TA forms attached

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
bc72aa82-9da1-47f0-9e21-c97c72720ff3 | checklist | Final Sign Off for Invoicing |  | Final Sign Off for Invoicing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
df01b7b3-3d92-4a0b-a85a-604fb4d3c8a7 | checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
64da378d-d531-4454-8eaa-a8c84c19930b | checklist | Floor Preparation |  | Floor Preparation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
36e4d60b-95fd-414f-a81b-864f49c18156 | checkpoint | Is the area clean, and cleared, ready for necessary preparation
5ccae496-de7a-4833-908a-a0c226c88e64 | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
a40517d7-cece-4cd1-a2cb-aebc78adc1a2 | checkpoint | Has screeding been completed to shower at correct height and falls with correct product
f5eb6bda-e53c-4f67-9fc4-7bef371bb9c9 | checkpoint | All falls to shower base, or outside shower are correct and signed off by TAL Tiling manager
f9eb2d88-8b59-4338-868c-7920265396d4 | checkpoint | Grinding, if required, completed before works (photo required) after works (photo required)
950927d6-808b-4275-b9b5-f6c1e9d1a0b8 | checkpoint | Floor levelling completed and applied as per requirements. (m2 rate)
79d6cca2-6a4f-4b62-91a2-80f238ea3843 | checkpoint | Floor levelling completed - hours and bags used to be recorded (if per bag/labour rate)
30b99ae6-e62e-4d46-9ce5-4f74b896dab0 | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8059edfe-5fa2-4691-8ef4-1c5da41718e5 | checkpoint | site has been cleaned in advance of our arrival on site
2f4c7d3b-1c1d-480e-a697-46be8bb2a749 | checkpoint | Walls are plumb and level
6ae411d5-bd9b-539e-ba13-9b7e473ae0af | note | IMPORTANT
209f8959-3881-4376-aa2a-5d00fdb29633 | checkpoint | Tiling works running to programme - prior trades completed
edf9fd59-44f4-48e8-9536-aaca19bff2cb | checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
7e8f5536-db95-433a-8e16-553c78e31414 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
86e227a2-c4d9-44f3-936d-49ade2411ceb | checkpoint | Data sheets, of products, are supplied on site with TA's
1d91a6a8-ad7b-4903-b9e7-79905a7e378c | checkpoint | Inductions completed & Site Inspection checklist has been completed
0ccd7b1b-6471-4cfd-9a08-27cc651e4016 | checkpoint | All tools tagged and tested - (photo's required)
a1d43b08-9310-494e-a242-612bbab64dea | checkpoint | Tiler has current site safe - Input number and expiry
29e4b216-a6a7-4d63-90e7-3945d599bc18 | checkpoint | Tiler has correct PPE relevant to project.
ce57e964-9e33-45d5-a89d-259c81de1abe | checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
01a2a4b9-ac43-44bb-bccc-b3fd7c3e7e5e | checklist | QA - Waterproofing |  | QA - Waterproofing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a908b354-a1d0-4c13-85e4-7dc9ff7d4877 | checkpoint | Substrate to receive waterproofing has slimline installed to any corners and has been gib stopped
a0d81225-6e8b-4ad7-be8b-2670f120575d | checkpoint | Gaskets have been installed to floor flange and wall plumbing fittings
0cdeeb97-40da-40e2-8c29-29e9731690f6 | checkpoint | Correct waterproofing is supplied as per project specification.
1b58a413-2a08-46d2-a09f-4df2e9c54d48 | checkpoint | Waterproofing coat # 1 applied to floors, upstand and walls (take photos)
ab3609e9-63a9-47f1-8dd0-9eb47b5342ed | checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos)
df7730f9-a168-45d5-af68-640bbfe37cca | checkpoint | Flood tests, if required, undertaken and photos provided.
526653b2-bd88-4dc6-a224-f1cba19cd97e | checkpoint | Material Details - Notes to be added of materials used on site
ee447ce3-5de7-46a6-a29e-1b5e6c850fee | checklist | Tiling to floors and walls |  | Tiling to floors and walls
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
1484db7d-387c-4bb4-8d0d-bde298843f9e | checkpoint | Tiles set out according to latest drawing - always check revisions on site
c32691d8-e0cf-4e2f-8557-ab0eea0d9a6d | checkpoint | Specified product used with notched trowel or required product
d5e4b87c-042e-4b7d-b913-12997a4dccbd | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
731d0396-fc5a-4311-8bee-2b1facbddee6 | checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
81dff001-81ec-4c25-b8d7-aa8eab1afaa2 | checkpoint | Install tiles to floors as per drawings
1c663033-bf4d-4a55-a00b-bd85a4d94b75 | checkpoint | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
b3717831-d967-462c-814b-5f3ba4ce6383 | checkpoint | Install tiles to walls as per drawings
6c5c982b-aaf9-49d3-bd74-5999a3282052 | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
b4458230-65a0-41e2-aab4-6deaf8720ea8 | checkpoint | Grout is consistent throughout and no missing grout.
4d34e301-a00a-479a-b3e5-7f74949f9b3c | checkpoint | Tiling completed, checked and Supervisor sign off
f4ef73ec-23e3-46c3-af36-f6ea2b55c23a | checkpoint | Silicone is completed to all tile junctions where required
49d5d951-f03e-491f-99d8-8e312f3ae8c9 | checkpoint | Area left clean & tidy
e8b2b915-8560-4796-a843-741d67b6d49c | checkpoint | Builders clean completed
4925b3fe-cf39-4d5e-9d6a-ba7e8a043e36 | checklist | Tiling to floors/counter |  | Tiling to floors/counter
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
bb8dfe73-5ac5-45b2-8e13-4d0dc077ed0d | checkpoint | Tiles set out according to latest drawing - always check revisions on site
00974137-ebcf-4b27-824d-e04180e57b3b | checkpoint | Specified product used with notched trowel or required product
fbc65151-e81f-49ae-8905-01cc8b29c710 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
30886a21-79fb-4343-9447-6eb267cb8736 | checkpoint | Floor substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
0cbf5563-1168-4bcf-9b49-e738750307d4 | checkpoint | Install 10mm crazy paving to floors as per drawings
e92412bc-a52c-4769-8d93-0cc83e3113f9 | checkpoint | Install tiles to front of counter (100mm high)
c6848bd6-3523-4cd1-8a68-a9400b27c5cd | checkpoint | Install tiles to toilet lobby and perimeter of crazy paving floor
b32443f1-ae9c-4870-86d2-3ae2258167fb | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
424fc846-01f7-45c2-b6a3-dda94973c535 | checkpoint | Grout is consistent throughout and no missing grout.
401b2a21-981f-43c7-bcdb-5281d9ab44e0 | checkpoint | Tiling completed, checked and Supervisor sign off
608a5c17-197f-46b1-8cb8-beb7436ad4ca | checkpoint | Silicone is completed to all tile junctions where required
0cda880a-d85d-4ac1-b3eb-c22a68029bc4 | checkpoint | Area left clean & tidy
452b90ef-579d-4b2d-854f-439829e55aab | checkpoint | Builders clean completed
3b4d20c0-db16-40cd-aeec-bb169665fa14 | checkpoint | Material Details - Notes to be added of materials used on site
23721122-8635-43e5-a9a3-d1942016a746 | checklist | Wall/Floor Preparation |  | Wall/Floor Preparation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
cb74864e-960a-44c0-a2e0-84222dd51534 | checkpoint | Is the area clean, and cleared, ready for necessary preparation
1481bd0a-6985-4d22-a6ba-88ed6c646a6e | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
d5341aef-e2ea-4acf-8e3e-da82015ad4e2 | checkpoint | Has screeding been completed to shower at correct height and falls with correct product
ee712c7e-33cb-4e26-bd78-7e89dd08452d | checkpoint | All falls to shower base, or outside shower are correct and signed off by TAL Tiling manager
7e357f55-5380-4a65-ba41-eb0d9a962c90 | checkpoint | Grinding, if required, completed before works (photo required) after works (photo required)
961dd09f-8272-4fdb-8c86-3a9d1934cf72 | checkpoint | Floor levelling completed and applied as per requirements. (m2 rate)
f9fb09ae-180a-4a3b-8b81-538c5a6a8c73 | checkpoint | Floor levelling completed - hours and bags used to be recorded (if per bag/labour rate)