## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
38841d47-86f3-4375-9684-ecbc774f720c | checklist | Final Sign Off for Invoicing |  | Final Sign Off for Invoicing
574ccecc-ca34-4457-b0f6-735aaefb457d | section | Details
2c8e65c2-0e3a-43d1-8d1e-12c935ad14c4 | checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
15e36859-90a8-4573-8f3b-613ed1817a4a | checklist | Prestart Inspections |  | Prestart Inspections
93146518-bb0b-42a6-b2f8-3326f06103c7 | section | Details
b492c2c3-406c-4538-88dc-2e2ddfadaf89 | checkpoint | Site has been cleaned in advance of our arrival on site
73be4dc5-a550-41f7-a9ae-5a28f97f3c9a | checkpoint | Walls are plumb and level
d45626a1-5513-5c01-8e3a-bbd4df903b56 | note | IMPORTANT
a5263a21-7dc7-4601-94fa-71c12880ca43 | checkpoint | Tiling works running to programme - prior trades completed
ad1d79de-1280-4d4a-a7f2-671f8e8425e8 | checkpoint | Has prior trades QA been signed off by main contractor
2ebfcf02-196f-47a9-89ba-12b176a70b37 | checkpoint | Gib compound and sanding cleaned up from rooms
0274fea9-0ae5-4e77-bbc7-c719b435a2df | checkpoint | Task Analysis signed onto by tilers and provided to main contractor
66b9119d-1f1d-4893-b81f-801b5609d300 | checkpoint | Inductions completed
bca99972-c4ca-4942-8d67-9680f86c42ae | checkpoint | Site Inspection checklist has been completed
cef6835e-b53f-453f-8018-1dd11d6a5790 | checkpoint | All tools tagged and tested - (photo's required)
311fa5da-2763-4ff4-bacb-41ce98462629 | checkpoint | Tiler has current sitesafe - Input number and expiry
862f015b-b94d-4d79-a0c0-c74c097fa2af | checkpoint | Tiler has correct PPE
20eef1a5-16d7-42ff-904b-f5218e219816 | checkpoint | Correct drawings supplied as per onsite
88f6c12a-aec4-42c8-9a61-f1a6f6ab201b | checklist | QA - Crazy Pavers External |  | QA - Crazy Pavers External
dc51d9bb-49bf-4fcc-9a0d-ae95a0537095 | section | Crazy Pavers External
d7621cfd-3acc-406c-bf0a-405ba3a090a1 | checkpoint | surface grind of substrate prior to installation
3202ebb1-c2ce-41fb-9f1d-e8ffa8584482 | checkpoint | prime substrate prior to installation
92146fa2-8324-41ef-a989-21ceea37d2c0 | checkpoint | ensure set out correct as per sheet (1) 04
6df92261-7511-464b-a870-a0fe24c16bf1 | checkpoint | Install of crazy pavers to external area (Designstore P Trav Czy Trevertine Crazy pavers)
f005f9ee-53b5-4123-8205-7644b0b730dc | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
4dbdbde6-15db-486f-b5c5-8787df979999 | checkpoint | Grout is consistent throughout and no missing grout.
1d3fcc33-e2a4-4fb4-ad33-283702d5e552 | checkpoint | Apply 2 coats of Fila sealer to completed crazy paving
00403c3a-000e-4411-90c6-aafac8c096a6 | checkpoint | Pavers completed, checked and supervisor signed off
6810b5e5-8aab-4da2-bb15-d8cd4b5607d8 | checkpoint | Area left clean & tidy
4dc5424e-f176-46dc-86b8-e3b9ffb0a794 | checkpoint | Builders clean completed
4685b0be-4db3-45c4-be09-e541a223b875 | checklist | QA - Floor Prep Bathrooms |  | QA - Floor Prep Bathrooms
87cca430-2d65-4d08-833a-6310c8ac10c6 | section | Floor/wall Preparation
77dabc6a-1e2c-4d9a-ab31-4e4e1ba3b4e2 | checkpoint | Is the area clean, and cleared, ready for necessary preparation
d299f7e7-c234-4d46-8768-a31fb47679f4 | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
13d57b53-5a35-435f-9336-8752074cff44 | checkpoint | Has screeding been completed to shower at correct height and falls - A48 material
14ec8ca8-d88d-45b5-b7d4-2b16b7dd83db | checkpoint | All falls to shower base, or outside shower are correct and signed off by site manager
81eb4d1e-1f5f-43c8-ae83-e80bbb8b462d | checkpoint | Install shower upstand with Hebel
d5c048c1-9ada-4c1f-9f1a-7d61509d8d8d | checklist | QA - Other Information |  | QA - Other Information
891c3cc8-4fee-4294-aa3b-5efa658e5161 | section | Other Information
0a6e890c-69d8-4bde-b7e8-d18399db49a0 | checkpoint | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
a430807b-b077-40aa-93a2-c21cf7aa7bc6 | checkpoint | change of details and or instructions
508056ed-9ea2-4ee4-b9b6-44da3af96845 | checkpoint | Site specific details to be added
b51f6229-d707-478d-9e52-932714f247e9 | checkpoint | Material Details - Notes to be added of materials used on site
d026e095-1998-487d-839c-b96528aec46e | checklist | QA - Tiling Installation |  | QA - Tiling Installation
8b911ea8-e56f-4b6c-935f-1b861808ff18 | section | Tiling bathroom floor and walls
246b96a9-e8a0-4325-9cb1-4d1b27f17c39 | checkpoint | Tiles set out according to latest drawing - always check revisions on site
74c938d0-66af-4eb5-843c-df165739ddc0 | checkpoint | Specified product used with notched trowel or required product
994d7087-6be8-4c98-88de-e43f07bb2f96 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
e336d5dc-aa1a-47d6-a935-b3404d1049b3 | checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
df8853be-acde-429a-ac0a-10a9494c61d5 | checkpoint | Install 600x600 tile space Corten tiles to bathroom floors
f59a9bce-7903-43a0-a2be-63d7889ee0b4 | checkpoint | Wall tiles set out to match floor grout lines or as per drawings install tiles to walls
bcd94c83-38d7-4844-b557-293f59063231 | checkpoint | INTAL tiles to hebel upstand
891735ee-3c46-42db-b78e-f076e52e10f7 | checkpoint | Install 1200x600 tile space corten tiles to shower walls only
0bc20ee0-9416-4896-bc76-d869b5ff7f1c | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
400893d7-c368-4bc2-bff3-cad235e2d452 | checkpoint | Grout is consistent throughout and no missing grout.
9cfd8db3-b626-4ab4-ac26-b11f68342714 | checkpoint | Tiling completed, checked and Supervisor sign off
8b196df1-7610-4c3d-84ce-7316ecdb7f09 | checkpoint | Silicone is completed to all tile junctions where required
6b78e83b-7275-47d0-84f3-72fb5f4ef495 | checkpoint | Area left clean & tidy
cba9d616-b76f-4fae-83cf-2f44878d6c76 | checkpoint | Builders clean completed
3bff021d-5aeb-46a7-8d55-35a4c02bb9d3 | checklist | QA - Tiling Installation Spa Room |  | QA - Tiling Installation Spa Room
3b3794b4-2273-451b-b823-71050ca62453 | section | Tiling to spa area
c97f0f71-4a2e-4a46-86a0-d855fafbd75d | checkpoint | Tiles set out according to latest drawing - always check revisions on site
91355563-7cff-4634-b5c9-a7d09d086883 | checkpoint | Specified product used with notched trowel or required product
e9025b96-6279-45b8-ab90-2f978a300a58 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
103be5fa-314b-4eb6-8ee3-4c4c7907d881 | checkpoint | Floor substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
1c8956b5-3a6a-4c2e-a7f0-8dedf643ca38 | checkpoint | All Joints to be mitred
8af1a800-18be-4201-8050-c39f5197ad2a | checkpoint | Install of crazy pavers to Spa floor area. (Designstore P Trav Czy Trevertine Crazy Pavers)
afef1d4f-dd68-4dbc-b429-4f259fa16105 | checkpoint | Install of 1200x600 tiles space corten tiles to vertical Vanity faces
0d33e93a-4db3-46aa-8ec6-dd1034343402 | checkpoint | Install of 1200x600 tiles space corten tiles to Heated seat vertical faces and top
3ebc6b4d-ddab-4578-ab9c-ad3780e28d8e | checkpoint | Install of 1200x600 tiles to tap plinth vertical faces and top
4b6a8519-f845-456d-aa91-3cac05ff5ff0 | checkpoint | Install of 1200x600 tiles space corten tiles to Bath vertical faces (external & Internal)
bc8a045d-30f6-4b2d-b954-e00441872964 | checkpoint | Install of 1200x600 tiles space corten tiles bath floor
76703fa9-f90d-4369-a673-096a0017a2cf | checkpoint | Install 1200x600 tiles space corten tiles to bath tops
5ddd6ee6-9d27-4c00-bc91-2df7a2327681 | checkpoint | Tiling completed, checked and Supervisor sign off
c8e31868-60a6-481c-948e-907657ee3995 | checkpoint | Silicone is completed to all tile junctions where required
d73640a5-3a4a-45d3-953c-c3c29368ef2b | checkpoint | Area left clean & tidy
70a6e77d-f4cf-4d45-acf0-e8033eb4aebf | checkpoint | Builders clean completed
b4125415-f96c-4fc6-be76-23bf33ddb839 | checklist | QA - Waterproofing |  | QA - Waterproofing
8c6e9668-1f3b-4af1-a664-51d6a0028071 | section | Waterproofing
d4009b2d-6674-4c38-bc37-21006abf72f0 | checkpoint | Waterproof materials applied to floor perimeter and gaskets to flanges
bfad4d4e-b335-41d3-9eb5-83eb675fdf58 | checkpoint | Waterproofing coat # 1 applied to floors and walls Ardex WPM750 (take photos)
1f3ea08a-2558-4cd0-8d82-3a37d327e00f | checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat ArdexWPM750 (take photos)
b6fcde0b-eed4-4500-831d-ad6fbbacc3b3 | checkpoint | Flood tests, if required, undertaken and photos provided.
3b51f5bc-707e-49c7-985b-08a8d9640589 | checklist | QA - Waterproofing - Spa Room |  | QA - Waterproofing - Spa Room
293daf04-7c34-457c-a274-742ebb5c82c2 | section | Waterproofing Spa room
c6e4db3b-3e58-4fa2-99a6-3ad92f25dea4 | checkpoint | Waterproof materials applied to floor perimeter and gaskets to flanges
f13d84fb-282a-4513-80f4-5ed231ee6c14 | checkpoint | Apply liquid ARDEX waterproofing to ice bath, plinths & heated seat
d95e5933-6324-4c6f-926e-35b2c3fbd4f4 | checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat ArdexWPM750 (take photos)
c61ad398-22d1-4b74-b7b4-78c19e1a0f13 | checkpoint | Flood tests, if required, undertaken and photos provided.