## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
b6734d52-47f1-48c4-bff0-37b7f7a7ae32 | checklist | Final Sign Off for Invoicing |  | Final Sign Off for Invoicing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8f012a61-34fe-4c9d-a114-7ebdd6a7a5a6 | checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
88302ca2-ee4f-4ae7-8218-c5261a6e2852 | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
b4d07328-0683-422a-b282-4c71c38c9295 | checkpoint | site has been cleaned in advance of our arrival on site
85536c82-5b19-4763-a61b-78b739141eda | checkpoint | Walls are plumb and level
211ad0ed-73b8-58f0-9a25-b136fe3d3d94 | note | IMPORTANT
3e91b787-5e5a-482b-8889-17770106f185 | checkpoint | Tiling works running to programme - prior trades completed
afc381ff-ea68-464a-b33a-e2175f3f7cb1 | checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
a67ab566-4c3a-4e6d-9b67-21e4b818bb57 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
5d747ffd-e24f-42fe-b2f5-bfbe0ae86f21 | checkpoint | Data sheets, of products, are supplied on site with TA's
6fea8aa5-4bc3-4ee8-b23c-f1ccd448f50e | checkpoint | Inductions completed & Site Inspection checklist has been completed
feaef82a-2cc0-4b16-a408-3ee7980eacc8 | checkpoint | All tools tagged and tested - (photo's required)
e9841da1-826b-4792-9704-4f130f3dfc98 | checkpoint | Tiler has current site safe - Input number and expiry
199d865a-3f5b-49c2-b241-75feca1c3b15 | checkpoint | Tiler has correct PPE relevant to project.
1a25503e-ea69-4577-9aa7-15e7d4b6245a | checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
61af54d9-1df6-46e7-80e1-687231f19604 | checklist | QA - Wall tiling |  | QA - Wall tiling
21c7860e-7f62-4c17-ac47-558f586a412a | section | Wall tiling Installation
beb4a372-737f-4121-8e34-069bbd25d7cb | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
87111672-dccc-4d23-8a71-09db371af145 | checkpoint | Installation of tiles to splashback and as per drawings
e463e9c4-d552-4870-82d3-31b5b7504a68 | checkpoint | Grouting is consistent, neat and cleaned from surface.
2f3c60ae-086f-411e-bbab-5b6e693fa861 | checkpoint | Tiling is completed, checked and supervisor to sign on
9aa8950d-b95b-4a3c-aa52-62b1f4256615 | checkpoint | Silicone nominated is the correct colour and applied evenly and consistently
3ebe8cd2-50e9-4109-b2ce-e5f774189b48 | checkpoint | Correct tiles trim is supplied and installed as per drawings
362025a1-decf-47bf-a67f-24c519e2d7e0 | checkpoint | Area left clean & tidy
1e74eb28-6ec2-4c81-9dde-953fe838fd78 | checkpoint | Builders clean completed
a7b94e34-e791-4248-9d52-3a9b668f8c10 | checklist | QA-Other Information |  | QA-Other Information
897b1b8c-4c1d-4c4e-a51c-8e2d756556cc | section | Other Information
0d1af52b-2820-45f6-8f5f-75d7c84100f9 | checkpoint | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
deabae21-37d5-4ba3-972d-61ed74c50697 | checkpoint | change of details and or instructions
e499bb4d-ce69-4982-817e-fed5775527aa | checkpoint | Site specific details to be added
ebd258ad-f5b3-44f5-897d-03a669b38de0 | checkpoint | Material Details - Notes to be added of materials used on site
5fdead2d-6fd8-41f6-96ee-f76a99fb1b32 | checkpoint | SSSP/TA forms attached