## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
968c32ec-cd07-4502-ab00-a0feaf94280a | checklist | Final Sign Off for Invoicing |  | Final Sign Off for Invoicing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
1cbe4489-8dee-44d2-830b-a1fdf5d025a4 | checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
1dfef75e-d770-4b88-84c2-1dac171b06cb | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
17a87494-f0a0-4f58-8c43-874a1c9ea342 | checkpoint | site has been cleaned in advance of our arrival on site
ee9cff93-6efb-42e7-b7fe-eb3363e397a2 | checkpoint | Walls are plumb and level
2515961f-707c-5036-a092-aab2dc3d6622 | note | IMPORTANT
ba16a9db-c09d-46e6-a795-cf36eb7b6155 | checkpoint | Tiling works running to programme - prior trades completed
3ba15208-9831-4fe0-aa7a-4b85f6d7666b | checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
2d06e331-5489-4ccb-a980-dcdfcbef452b | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
213ce549-674b-47dd-94d8-b52095494cd8 | checkpoint | Data sheets, of products, are supplied on site with TA's
f34d1e38-c90c-426e-8396-8b0f9bcdd404 | checkpoint | Inductions completed & Site Inspection checklist has been completed
a6d74dea-4f76-4f1d-846c-15393c6fd9bd | checkpoint | All tools tagged and tested - (photo's required)
d4092e1c-3424-43dd-97f1-bcb124d99c46 | checkpoint | Tiler has current site safe - Input number and expiry
745ee724-0647-4134-b55f-94d391d2aaee | checkpoint | Tiler has correct PPE relevant to project.
cb76dbd9-aa67-4ff5-8362-dde021a7aef3 | checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
3a0c9377-90e5-43ec-90a3-6e1553e2c7e7 | checklist | QA - Splashback Installation |  | QA - Splashback Installation
f8984d52-a857-4dbb-9e41-1ba55d6ac339 | section | Splashback Installation
d7ba8680-4b7f-4849-9a10-295a4997b563 | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
6cffb83a-00ae-4f61-9a9f-482ff41f1c02 | checkpoint | Installation of tiles to splashback and as per drawings
8f8321e9-57a6-4eb2-b2d9-e0c7bddf566e | checkpoint | Grouting is consistent, neat and cleaned from surface.
04e87cdb-40e6-4869-b49c-dcb2496a9c9f | checkpoint | Tiling is completed, checked and supervisor to sign on
6e159872-f7d4-4e99-b2d6-3673222e1b67 | checkpoint | Silicone nominated is the correct colour and applied evenly and consistently
a5827cc1-8fb0-4239-82cb-05d47754ae0c | checkpoint | Correct tiles trim is supplied and installed as per drawings
9c8dbd3f-50b9-48e8-a02a-18fef539dd8c | checkpoint | Area left clean & tidy
3adb1d78-1edd-481a-9fcf-2b279abc6f97 | checkpoint | Builders clean completed