## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
156f16c8-10a0-4d4b-ad4d-ea1388a2758d | checklist | Final Sign Off for Invoicing |  | Final Sign Off for Invoicing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
924104cf-58a1-4bbe-9fed-97c48a267a36 | checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
f7e5efd2-1e38-4ad9-950e-849ae08d1ae3 | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
d9fba71a-6dea-4234-9233-3f8a599c5d1f | checkpoint | site has been cleaned in advance of our arrival on site
f78bba28-8a3e-4272-b9a8-15912a9ca474 | checkpoint | Walls are plumb and level
fa1c3e4d-dcad-538b-8dd0-cc4285223a9c | note | IMPORTANT
617a6cb9-01c6-422d-b54c-3720e17a45c3 | checkpoint | Tiling works running to programme - prior trades completed
e4949242-114f-4feb-8152-2853ffdb4f3e | checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
445463f4-a9cd-4e0b-ab20-e4ef08a1e0e9 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
6cac4418-1317-4441-af51-0b2a21a2f3c3 | checkpoint | Data sheets, of products, are supplied on site with TA's
bb694357-a2d7-413b-84fe-e1cbefb07f99 | checkpoint | Inductions completed & Site Inspection checklist has been completed
ecf58c79-14d9-4fb2-86b3-26dc9f4b5c66 | checkpoint | All tools tagged and tested - (photo's required)
52e22af6-cc61-43be-b224-36ef408b89a5 | checkpoint | Tiler has current site safe - Input number and expiry
f8302d79-a97a-4f19-bc94-62704831eb51 | checkpoint | Tiler has correct PPE relevant to project.
7a68ca8f-e816-4fd4-ba11-8ee5440ff3e9 | checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
2298f234-ec88-4c92-b12c-b4c01afc0f93 | checklist | QA - Splashback Installation |  | QA - Splashback Installation
5ce95227-33be-4920-8a6a-e7bed8b4a9a0 | section | Splashback Installation
84716c59-3c47-41d9-9a84-1a6990f89823 | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
4f78eda6-12f5-455d-88d8-7bf8cc7032f7 | checkpoint | Installation of tiles to splashback and as per drawings
9d41765e-f143-4f18-b669-a1e8afb485ea | checkpoint | Grouting is consistent, neat and cleaned from surface.
aae90c03-b97e-4051-96ee-51f249f6962d | checkpoint | Tiling is completed, checked and supervisor to sign on
f267892a-133a-472f-bc61-0375e1c3903a | checkpoint | Silicone nominated is the correct colour and applied evenly and consistently
4f91c127-df6f-4cd6-8a8f-f8e9b6503c17 | checkpoint | Correct tiles trim is supplied and installed as per drawings
ca3d3515-fd8b-42e7-9e4c-13269e8ec211 | checkpoint | Area left clean & tidy
2f1e85c4-2c00-4ec5-9f23-2cd7be99288a | checkpoint | Builders clean completed
c930c585-4025-4462-9e64-5907f1e3e57a | checklist | QA-Other Information |  | QA-Other Information
2545072e-b04f-4693-9b17-7e5edfab4227 | section | Other Information
4f0900b0-ad43-45cb-954c-459a781b575f | checkpoint | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
97ea49a9-8702-4c99-a876-2bd2e19937d2 | checkpoint | change of details and or instructions
999f1a11-3f46-4e97-b5c2-2622d918a5a9 | checkpoint | Site specific details to be added
f3551e32-d74b-4b46-96ae-c8c0873d14fc | checkpoint | Material Details - Notes to be added of materials used on site