## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
3bbdda42-9b56-4570-bae0-e879172a28eb | checklist | Prestart Inspections |  | Prestart Inspections
8ec43b7b-12bb-4a1d-a3e7-1b01ba9c5acd | section | Prestart
2f2248ff-1012-4046-9786-7fc5bfd7574b | checkpoint | Site has been cleaned in advance of our arrival on site
c1dbd71f-ca03-4347-b9e6-6f47a90cf5eb | checkpoint | Walls are plumb and level
b362921d-0ca5-54c8-985f-4b6d7a443eae | note | IMPORTANT
678f1fa5-0cec-4390-8bbc-c9aa494b7b00 | checkpoint | Tiling works running to programme - prior trades completed
d2d5d687-29cd-49cc-83b5-d8ecd9864193 | checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
bdd33775-596b-4d3a-a2b9-f447f43eb350 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
d8987f09-80b0-4407-af4a-dc5e37a57ad9 | checkpoint | Data sheets, of products, are supplied on site with TA's
87d12130-5e4a-4821-9e56-fd4db86d4858 | checkpoint | Inductions completed & Site Inspection checklist has been completed
b348fc17-732c-433b-84c3-e982404180b6 | checkpoint | All tools tagged and tested - (photo's required)
185016ba-91fa-4951-a3fb-899a879c7d40 | checkpoint | Tiler has current site safe - Input number and expiry
cb20c60a-3fc1-417c-881e-e28c230c3344 | checkpoint | Tiler has correct PPE relevant to project.
c13d9086-bc89-49dd-86cf-64a564f5a426 | checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
152dbf07-8b8a-4e84-9225-e7871751aad3 | checklist | QA - Final Sign Off for Invoicing |  | Final Sign Off for Invoicing
c7bbf17d-bc6e-4827-91fc-d3b75985bfd7 | section | Final Sign Off
4c1da5f8-ec2c-4462-8e61-4e5203d15689 | checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
f5833815-78a5-4c9d-8faa-91537eb0dd66 | checklist | QA - Herringbone Timber |  | Herringbone Timber
957f051f-6cee-4b25-80f5-4c9f1aa6a706 | section | Timber Floor installation
a47590f9-e05e-4e9b-a457-3b0fe4404ad1 | checkpoint | Floor substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
efba77cb-7740-417b-b6cd-28687059fa54 | checkpoint | Installation of Herringbone Flooring as per drawing
825e4d60-8e50-4a66-a464-f7080fd7d803 | checkpoint | Install trim to perimeter of herringbone floor
5f95d582-d697-408f-9e47-a77f219852e9 | checkpoint | Area left clean & tidy
3d3c60d7-00c3-4f9a-a144-1408504aef2c | checkpoint | Builders clean completed
b46eb4f3-88f3-4a6b-8ddb-09a0943e5e00 | checklist | QA - Miscellaneous Items |  | Miscellaneous Items
07ebddc1-bff7-452a-8167-89d9585e3c3b | section | Miscellaneous Items
652ef3a9-e011-4630-83e4-25f8d5a37155 | checkpoint | Supply & installation of all floor tactiles (TI01 x 4 areas) and trim thread insert to stone
8ffddf9d-dd6a-40b2-92b6-05ac7cabc503 | checkpoint | Install Fantima Stone to demo'd wall as per mark up
4dbfb2c5-edd3-46e7-81ba-e581eacfd56b | checklist | QA - Other Information |  | Other Information
d32c6fc9-5fad-4c80-88f9-dcd2fa412b54 | section | Other Information
a4acfdc4-3d77-40ba-9f28-e885728180b4 | checkpoint | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
adc02019-a6d0-4624-9c43-1ece52d0f672 | checkpoint | change of details and or instructions
0bca361e-f065-4e65-ba8c-10ef9fce541e | checkpoint | Site specific details to be added
26d5eeb1-702d-46a6-bf2d-8c2d3d3f5b3e | checkpoint | Material Details - Notes to be added of materials used on site
39136c85-9011-409b-a51e-9536a7139d9a | checklist | QA - Tiling Installation - Amenities |  | Tiling Installation - Amenities
f0d19bb0-ce80-4f90-be7d-59ab5f81e225 | section | Tiling to floors/walls
382f9960-6db3-4c54-9cb8-4feeeeb9aff0 | checkpoint | Tiles set out according to latest drawing - always check revisions on site
78d65220-4d1d-4136-a4c7-c730f48dcef5 | checkpoint | Specified product used with notched trowel or required product
9b893760-321c-4847-a811-563fdc5d36c5 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
57d5c869-3c6e-4d2e-9a80-27f75994a822 | checkpoint | Floor substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
eb8247b0-7380-4e7e-8f73-2de98d855b79 | checkpoint | Install 600x600 tiles to floors as per drawings
5453de7f-7e9c-4528-9470-cc17515f5b6a | checkpoint | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
5c86bb15-0d81-4e97-8ee5-a9c9205dd8be | checkpoint | Install 600x600 tiles to walls as per drawings
142d796d-a19c-4c54-b07d-78a0bcdd097f | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
df5bf2d2-1759-4ad9-8b2f-81e554e6a60d | checkpoint | Grout is consistent throughout and no missing grout.
d93dcb54-be06-4e4e-b9a3-dbe487cd6463 | checkpoint | Tiling completed, checked and Supervisor sign off
ea5546a7-c530-4e87-b374-6c3c7a3fcdad | checkpoint | Silicone is completed to all tile junctions where required
493000a5-d9ef-4e6f-997d-721b446a758c | checkpoint | Area left clean & tidy
9b113d0b-56c2-4de4-8f99-575da0e2a019 | checkpoint | Builders clean completed
5afc2c05-1736-46cb-a2ff-5ce08b9a0454 | checklist | QA - Tiling Installation - Floor & Lift Lobby |  | Tiling Installation - Floor & Lift Lobby
009c0c5d-4bc7-4628-9495-1899f280b7a3 | section | Tiling to floors/walls
a6db60ca-b2b0-45d3-a2f0-937366769b5c | checkpoint | Tiles set out according to latest drawing - always check revisions on site
ada48e5d-d893-4d10-ad68-f0dad2a5e3c8 | checkpoint | Specified product used with notched trowel or required product
3c5d3a34-e94c-43e8-9183-c0dfd2f2853d | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
6dd0ab98-acb0-433e-ab47-c3796dd87f97 | checkpoint | Floor substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
d3cc28f6-7f90-4c9e-8b24-a457e955d727 | checkpoint | Install 1200x600x20mm Panama Sonte Honed to floor
d06a9c0f-f85e-48c5-8313-6ad81a3492a5 | checkpoint | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
7d16b02a-2295-49d5-918c-bbc183fdfc6d | checkpoint | Install Chinchilla Hones 70x300x20 to lift lobby walls upto 3M high
1c4216ae-54ab-42c1-9473-20f9bd4ece7a | checkpoint | Install stone to stair threads, and risers as per details
64898271-2304-4fb7-b42e-aab1777afd8a | checkpoint | Trim - Install approved trim to tile/matwell and tile/vinyl junctions
5b06d2b6-4963-41b7-9c77-cb9438034c22 | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
ec78124f-2507-48e9-9a4b-c86acf485fca | checkpoint | Grout is consistent throughout and no missing grout.
b16c9c73-191e-46eb-a3d5-4b59b55cb2bd | checkpoint | Apply 6mm silicone movement joints for stone flooring 3.6-4.8 spacing
9a4eea7f-ac90-4d60-bbc0-c508eeb7ed6c | checkpoint | Tiling completed, checked and Supervisor sign off
95644865-c453-4416-8140-a70ce776f694 | checkpoint | Silicone is completed to all tile junctions where required
1e699a4f-a2d0-4af1-8b36-2099a187136a | checkpoint | Apply sealer to all floor stone and lift lobby walls stone
4c28ce77-236e-45b0-93ee-4df1dcbeb4de | checkpoint | Area left clean & tidy
59da2b6f-6397-4cfc-9031-38d4fbb813e5 | checkpoint | Builders clean completed
64e573dc-f98b-4917-9934-79462576d18d | checklist | QA - Wall/Floor Preparation |  | Wall/Floor Preparation
ac1aab7c-b0f9-4063-8f78-1d5c245ad1f6 | section | Details
1ba5fa2a-d523-48df-87a8-632ca572a8e5 | checkpoint | Is the area clean, and cleared, ready for necessary preparation
12d570c0-2d36-473f-9811-468987c2c970 | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
dd6f382d-06e2-469f-a718-d6a72d0a9d7f | checkpoint | Has screeding been completed to shower at correct height and falls with correct product
6941946e-6202-41f3-9db5-6292c7404a53 | checkpoint | All falls to shower base, or outside shower are correct and signed off by TAL Tiling manager
92f9b1b0-0db2-40ac-a110-0b605c9f657e | checkpoint | Grinding, if required, completed before works (photo required) after works (photo required)
4e66509c-7975-40a4-8a85-74f584370e32 | checkpoint | Floor levelling completed and applied as per requirements. (m2 rate)
60990b3c-51fd-4eae-bdf1-37ced4a48088 | checkpoint | Floor levelling completed - hours and bags used to be recorded (if per bag/labour rate)
d5883e40-bad5-47b5-a806-436eb89e65e2 | checklist | QA - Waterproofing |  | Waterproofing
216719d1-b815-4d0a-9091-93a85190cc1a | section | Details
2198bd20-1a84-42b5-8d03-a3edaa908cd6 | checkpoint | Substrate to receive waterproofing has slimline installed to any corners and has been gib stopped
77c5f9c4-1fe1-4361-9b58-30987db97b2b | checkpoint | Gaskets have been installed to floor flange and wall plumbing fittings
d689e525-9fe2-4437-bdfe-15ace81c214c | checkpoint | Correct waterproofing is supplied as per project specification.
c6729dfd-e0d2-4f1b-b5a0-0f4d5c99cc6b | checkpoint | Waterproofing coat # 1 applied to floors, upstand and walls (take photos)
7ad0349f-be74-407a-8bed-caadce4616e0 | checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos)
6ea56775-cc29-4739-8ed1-260c07b82406 | checkpoint | Flood tests, if required, undertaken and photos provided.