## Master List Templates
Id | Type | Name | Values | Prompting Name
883b848f-f3e3-4ab3-b9f0-7296849dbc33 | checklist | Wall prep |  | Wall prep
79937e9f-d2eb-4ae0-9fbb-ec458728f7cd | section | Wall Preparation
4ec840b8-e5f1-43ec-9991-75e069bedfd4 | checkpoint | Is the area clean, and cleared, ready for necesssary preparation
9c118890-310a-4f3c-8424-90aafe8c8a93 | checkpoint | Is the floor prep completed and signed off
7854748d-e61b-4350-927e-4e67e334ce9f | checkpoint | PHOTOS OF COMPLETED FLOOR PREP

## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
e186b21c-43d2-4e25-93fe-3f4f8b440877 | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
121d7b19-0bb8-4904-b180-59eb96f7b082 | checkpoint | site has been cleaned in advance of our arrival on site
1a8c2ffb-6127-4538-8a24-1d810aeaff47 | checkpoint | Walls are plumb and level
847f48d7-0cb2-5897-bd92-092e2fa459e8 | note | IMPORTANT
10c8782e-7702-40c1-ba28-8da796565db0 | checkpoint | Tiling works running to programme - prior trades completed
594c8bc0-1591-452b-a523-e7c49d6d5891 | checkpoint | Has prior trades QA been signed off by main contractor
3d4037cc-f0ea-45cf-80ed-054745b78d89 | checkpoint | Gib compound and sanding cleaned up from rooms
b1424373-099a-4854-be84-7a67bb85d86b | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
830448b2-047f-4fa4-b0da-e61cc68b7848 | checkpoint | Inductions completed
173db929-e0a0-454d-bee2-b4bf90ca9209 | checkpoint | Site Inspection checklist has been completed
72d65bcb-50de-478e-b931-9e30eeeabc9c | checkpoint | All tools tagged and tested - (photo's required)
3e825817-e968-49fa-b81a-dd60e53c4897 | checkpoint | Tiler has current site safe - Input number and expiry
76d4c8f4-8703-4a8d-9bb2-93586d24ff08 | checkpoint | Tiler has correct PPE
6a994308-27c1-41db-94a4-a2dc7a5919da | checkpoint | Correct drawings supplied as per onsite
c757cb19-e1af-48c0-87a7-3c18f78f22d0 | checklist | QA - Floor Prep |  | QA - Floor Prep
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a5212d98-ff64-413a-8180-27fd5f7f9b9c | checkpoint | Is the area clean, and cleared, ready for necessary preparation
3220cc97-086a-4a51-a929-894af3f9edc3 | checkpoint | Grinding completed before works (photo required) after works (photo required)
c34ea2b1-62e6-43e6-9e10-a5542cabef08 | checkpoint | Floor levelling completed - hours and bags used to be recorded
1d18b098-d1ef-4716-a0d6-e0359af9e76a | checkpoint | Extra floor prep/Site specific details to be added
0435a25a-5639-429c-8734-074ebf137b1c | checklist | QA - Other Information |  | QA - Other Information
99d90668-d475-4576-890a-9e7b3265bee3 | section | Other Information
3a7a7745-bbb4-4892-98e0-90238044da43 | checkpoint | Variations or extra works added into folder - all works and materials noted
7f5a1a35-7c99-4828-8229-dc0360c69191 | checkpoint | change of details and or instructions
66bcafc6-ae82-4f86-b2d0-6273442ccff2 | checkpoint | Site specific details to be added
3a055581-47d1-4e81-b78c-c697beb8fb6a | checkpoint | Material Details - Notes to be added of materials used on site
531df9a1-2874-483c-9e3d-de62244d5e04 | checkpoint | SSSP/TA forms attached
7a9504a1-d235-4ad9-96af-c0a722e1c5b5 | checklist | QA - Tiling Installation |  | QA - Tiling Installation
29a4bd62-42a8-4f46-8ba0-e821840eae83 | section | Tiling to floors
3bf9e308-5872-4708-80c2-ce4edb170040 | checkpoint | Tiles set out according to latest drawing - always check revisions on site
f0cc5472-d199-4728-a5dd-53f26c76265a | checkpoint | Specified product used with notched trowel or required product
4858f9c8-c53d-4e68-8535-c64bfdc21957 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
3ded7263-3094-4858-bea1-f1c4b7ec72cd | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
d2e0d332-e795-4caf-bc1e-c8e49c52d9c4 | checkpoint | Grout is consistent throughout and no missing grout.
0368d0d5-7d49-4387-a1f6-084ce0f81a38 | checkpoint | Tiling completed, checked and Supervisor sign off
cf76a92d-84c5-45de-bbf2-0db297ef39e4 | checkpoint | Silicone is completed to all tile junctions where required
23887d4c-3620-4395-9959-db465fe481f1 | checkpoint | Area left clean & tidy
142c7e6c-7b8f-41e9-86e8-940637c2f06c | checkpoint | Builders clean completed
b3b1bc8d-2565-4204-859f-00988ab0b301 | checklist | QA - Wall Tiling |  | QA - Wall Tiling
1275e1f4-f906-4420-bbbd-909a36801bda | section | Splashback Installation
af3cc144-b187-4674-9dab-b0cbb1d1a804 | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
341bea3f-0011-4b4e-9a62-6165f0952a61 | checkpoint | Tiles to walls
3345ce57-d393-453e-b889-7dd17bb5c597 | checkpoint | Tiling is completed, checked and supervisor to sign on
49376a5a-ea40-47b9-aa30-dcc19d7bee05 | checkpoint | silicone nominated is the correct colour and applied evenly and correctly
4ef82ed1-b4a3-4563-be74-ff6826dc1c96 | checkpoint | correct tiles trim is supplied and installed as per drawings
fa223a6d-e2a3-49e7-8a7a-16dcdcdd7eb3 | checkpoint | Area left clean & tidy
77ff6874-7aa7-4725-b922-0a54ff0321ae | checkpoint | Builders clean completed