## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
2a8cd179-8d12-400c-a845-878ed8856d40 | checklist | Final Sign Off for Invoicing |  | Final Sign Off for Invoicing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
13e22666-d954-4dd3-a202-7364389fdfab | checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
87598019-f9cd-4749-9f70-77da2dd6452f | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
e344cbb0-a4e5-4fd9-a63d-262e0817e0e3 | checkpoint | site has been cleaned in advance of our arrival on site
573160ac-ff8b-498b-8e91-8f6062084331 | checkpoint | Walls are plumb and level
270ef8c9-e6da-5246-98a4-9c6454e54f68 | note | IMPORTANT
fb7460f8-fbc6-480f-aedc-e8b255d51a08 | checkpoint | Tiling works running to programme - prior trades completed
cf89e9b2-7c60-400c-a151-2183c415459f | checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
423b4774-8fde-42ba-882b-1398ddaebf52 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
3cbec534-91dc-4493-ad3d-24f567b48de9 | checkpoint | Data sheets, of products, are supplied on site with TA's
40c62e71-cc45-4e00-9d3d-7dc61b5a58d6 | checkpoint | Inductions completed & Site Inspection checklist has been completed
6e4026a1-acea-4162-8c33-03452169308b | checkpoint | All tools tagged and tested - (photo's required)
e10f555d-270a-46f8-a48d-f336205e5d55 | checkpoint | Tiler has current site safe - Input number and expiry
350a3226-daa0-4c24-b159-40b48815cdd8 | checkpoint | Tiler has correct PPE relevant to project.
ef6568e7-a4e4-44fc-8762-c15a28da444d | checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
39d6594a-9875-48e4-b127-1f7bcecf902c | checklist | QA - Colum Tiling |  | QA - Colum Tiling
47215e86-b005-4da7-80fa-f96af236b2c2 | section | Coloum Tiling
098001e9-af8b-43c3-9ced-5ef1e5e05884 | checkpoint | Prime columns before tiling
6d3b259b-1fcb-4d15-94ee-87aa489f041c | checkpoint | Installation of tiles to splashback and as per drawings
a159835e-1bf0-4fd6-b738-e70ccf70fd5c | checkpoint | Grouting is consistent, neat and cleaned from surface.
c789523e-0e1d-46d0-b90c-a1ed524a9e8f | checkpoint | Tiling is completed, checked and supervisor to sign on
6eeac2a7-49a6-4bc3-9d20-34bd01500e99 | checkpoint | Silicone nominated is the correct colour and applied evenly and consistently
66a23970-fd6d-480d-b6d0-f5659bb08193 | checkpoint | Correct tiles trim is supplied and installed as per drawings
9e140c62-8e2f-48ac-9446-e4f4806b5b63 | checkpoint | Area left clean & tidy
e1203649-c90d-46e8-8ce1-ef25f4f34db1 | checkpoint | Builders clean completed