## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
96f411e3-537f-4bde-9902-dce2516f6e14 | checklist | Final Sign Off for Invoicing |  | Final Sign Off for Invoicing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
ef7ae86a-e330-49cc-8ea0-1305e398a61c | checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
1200fc52-4003-4687-8617-ae86bc63606f | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
ee0a96d2-1439-48e9-a9b2-46d8fd08feb2 | checkpoint | site has been cleaned in advance of our arrival on site
a096e4fe-0504-44e4-a4c1-24fa2df4e063 | checkpoint | Walls are plumb and level
d0b56344-7af9-50d7-aca6-efafe265f6d3 | note | IMPORTANT
3cf241d0-1248-4ca3-adf7-5b83741b3aff | checkpoint | Tiling works running to programme - prior trades completed
31b02c2a-cae7-48f9-8772-a225b73ace9b | checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
11981c8e-6350-4089-89ff-6e4ff7283bfa | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
51e48e2d-1135-4eae-ae31-afed28e1cb30 | checkpoint | Data sheets, of products, are supplied on site with TA's
fa894cba-3a95-463d-b6c8-b4b5fcca6790 | checkpoint | Inductions completed & Site Inspection checklist has been completed
06a005b0-5033-48ba-bee8-12cb1501028c | checkpoint | All tools tagged and tested - (photo's required)
3b514260-75be-406a-81b4-50f414576d2f | checkpoint | Tiler has current site safe - Input number and expiry
8cc9dc5a-f5c7-47f5-93f1-cb76e9f25a0f | checkpoint | Tiler has correct PPE relevant to project.
3c85cffc-1886-448e-9492-4dce3a7bc5f2 | checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
81038625-02ef-4605-ac9d-835af8121975 | checklist | QA - Splashback Installation |  | QA - Splashback Installation
20621c68-d23b-4709-b371-442a65279cfd | section | Splashback Installation
588a0019-8d44-4848-bfb4-ed2e378301cb | checkpoint | Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
12bfee9f-d016-4de0-baee-ae97625ee6ca | checkpoint | Apply waterproofing to wall behind splashback
0b77179b-efec-4a52-8999-6c5a6ecbe69a | checkpoint | Installation of tiles to splashback and as per drawings
9c74f6d3-0274-40b0-92ad-d969328a3708 | checkpoint | Grouting is consistent, neat and cleaned from surface.
86b574ed-e61f-41b1-84eb-6c557197d5c8 | checkpoint | Tiling is completed, checked and supervisor to sign on
de8fdcc6-a5d8-4ac5-8263-90969568671d | checkpoint | Silicone nominated is the correct colour and applied evenly and consistently
929a0850-af55-4fe4-99d5-f1b2aab85159 | checkpoint | Correct tiles trim is supplied and installed as per drawings
8adeeff0-e634-49f1-b401-00049ad780d9 | checkpoint | Area left clean & tidy
a29b03dd-daeb-4d30-90a0-ef8e8da06c95 | checkpoint | Builders clean completed
06825c69-2d99-467f-84b1-c10cab0efccc | checklist | QA Kitchen Island |  | QA Kitchen Island
c9adcf32-f306-4ee3-8390-c0084de5bceb | section | Kitchen Island Tiling
adc508d6-2f47-400b-a19d-64e150c6d8af | checkpoint | Substrate straight, signed off by MC, and ready for installation (insert notes for remediation if required)
53b78593-cd7a-432d-bb98-1260b3c9258a | checkpoint | Set out tiles and install as per drawings
e480e00e-9c47-42fa-b3ca-6b1dd68aaebc | checkpoint | Tiling is completed, checked and supervisor to sign on
ffddcb9e-cea7-4426-9631-370a32eb5e32 | checkpoint | Mitre 4 tile edges at 2 x corners of J06 kitchen island
89e549b3-1a04-45fc-a5e6-3757f998cb97 | checkpoint | Install 100mm high skirting to J06 unit
3cb778b4-a162-44f5-b7c2-ba6eec95373a | checkpoint | Manual cut & install 50mm wide tile strips to circular base of J06 kitchen island (including grout)
81b4dd10-3f1b-458e-8a1d-9ae3e5fb53c6 | checkpoint | correct tile trim is supplied and installed as per drawings
7e00669d-54fa-467f-8029-aa2bcb678595 | checkpoint | silicone nominated is the correct colour and applied evenly and correctly
3b5fe7c2-a4b5-41b5-8a3a-058ebd075234 | checkpoint | Area left clean & tidy
4f7b2b9a-9843-4c15-9c11-68aa562866a7 | checkpoint | Builders clean completed
5542758b-37fb-4d2c-8b71-532817588876 | checklist | QA-Other Information |  | QA-Other Information
c94dae84-61f8-4663-96cc-80a6d4bd13cb | section | Other Information
39d8a8a2-a511-4e18-854a-8fe408dea901 | checkpoint | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
754568e2-bb64-4d8c-9df6-dbf9806caeee | checkpoint | change of details and or instructions
f9210eb4-9194-4832-9d4a-fcf336c2900d | checkpoint | Site specific details to be added
3cf79635-6b0d-4adc-915f-b605403c4d3c | checkpoint | Material Details - Notes to be added of materials used on site