## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
52bb7226-ad7a-4c6c-9471-280489e05bd9 | checklist | Other Information |  | Other Information
0ea57be6-85b5-48ec-8232-82880979fd87 | section | Other Information
3ea9731f-073d-4b98-9a9d-51184444743b | checkpoint | Variations or extra works added into folder - all works and materials noted
b55c5add-d697-4dc6-8f84-f974944fda36 | checkpoint | change of details and or instructions
062f9eca-1428-4cd0-b441-ed812d5708f1 | checkpoint | Site specific details to be added
ffc9862d-60aa-4723-9981-27e2430f37a6 | checkpoint | Material Details - Notes to be added of materials used on site
123ab475-855f-47f7-aaf9-5cb1e3a45b19 | checkpoint | SSSP/TA forms attached
c317e276-5844-4c37-b575-41da769e67b9 | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
37b43f55-6f96-4d3a-99be-84645b198827 | checkpoint | site has been cleaned in advance of our arrival on site
7123a5f2-cc6d-4123-8f38-a8614d565060 | checkpoint | Walls are plumb and level
8e1179e6-292a-52bb-aaf6-8ed8202b2af6 | note | IMPORTANT
7b513a5d-e4ee-49ff-9ed8-ad65dcf37677 | checkpoint | Tiling works running to programme - prior trades completed
80709a22-2d89-4702-929c-fa10d0397908 | checkpoint | Has prior trades QA been signed off by main contractor
f1998aa2-e920-4078-bd0d-02b50797a319 | checkpoint | Gib compound and sanding cleaned up from rooms
8cbc34e8-3ded-40a9-aa47-aa64ebf24850 | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (photos requires)
d40de25d-5360-4bb0-a487-c709554809e4 | checkpoint | Inductions completed
77981beb-ae61-4414-a30a-9fbf3719e763 | checkpoint | Site Inspection checklist has been completed (photos required)
3aa4a206-69be-474e-a108-2e527f566d18 | checkpoint | All tools tagged and tested - (photo's required)
0befb29d-9192-4f85-a75b-1b5e52558618 | checkpoint | Tiler has current sitesafe - Input number and expiry
f38ced21-2beb-4577-877b-d805910cee29 | checkpoint | Tiler has correct PPE
17f15933-20d7-4f27-b25c-9f9a2c3d769e | checkpoint | Correct drawings supplied as per onsite
f6bbeaf9-be31-4e91-89ed-380fd90cd0e7 | checklist | QA - Floor Prep |  | QA - Floor Prep
6455eab4-5466-4bc5-9186-3b9fb47369a2 | section | Floor Preparation
5048026e-2f3d-477c-8c21-374c89ffb892 | checkpoint | Is the area clean, and cleared, ready for necessary preparation
07c7d41a-215f-4841-9b1f-ee76ebda83af | checkpoint | Floor levelling applied - upto 5mm (photos required)
6bc7bef8-9e49-48cf-8591-8a67ee7818a6 | checkpoint | Are flanges installed at correct depth in accordance with specified wastes
f57dc13d-d94a-44ba-b680-f4f61a2c87f9 | checkpoint | Has screeding been completed to shower at correct height and falls - R4 screed in Male and Female floors
911aa12a-06ca-464c-b829-97351a749ef5 | checkpoint | All falls to shower base, or outside shower are correct and signed off by site manager
e3938980-c19f-44cf-bc0e-bce5c1fabf4e | checklist | QA - Tiling Installation Fitout |  | QA - Tiling Installation Fitout
a05d888b-5447-4f44-8e37-522f79479114 | section | Tiling bathroom floor and walls
dadab9bc-6e93-458f-888a-67d08e71edea | checkpoint | Tiles set out according to latest drawing - always check revisions on site
4a4f186c-e703-4d60-9fae-ec261428f791 | checkpoint | Specified product used with notched trowel or required product
ff988690-0e15-4395-8458-b8cfdd94db76 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
ffbbb806-d2fc-4545-9c92-5e19ec881e6c | checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
4e12e0ab-a0a2-4411-83a9-ea9f879e6ee8 | checkpoint | Install tiles to floor
a2c06ddd-afe2-4f50-9725-fd9de81bb018 | checkpoint | Wall tiles set out to match floor grout lines or as per drawings install tiles to walls in ACC WC
4256770d-ba7e-477c-a63c-f6051096cda0 | checkpoint | Install FF5 tiles to corridor floors as per dawing 00-103
ecb5ab49-ebd8-4e52-9b40-2c79fabf3531 | checkpoint | Install FF7 tiles to updated corridor floors as per dawing 00-103 & 00-120
13ceb71f-befb-4664-8f7f-026c7684ea74 | checkpoint | Install WF14 mosaic tiles to JN-02 as per drawing 00-500 and 00-502
0bd85e1b-4632-480a-b03b-3ce47856938a | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
3ce568ce-0ca8-48f9-b38e-833efe9917a9 | checkpoint | Grout is consistent throughout and no missing grout.
b59bdf99-4e3f-4513-ae03-81e73c372130 | checkpoint | Tiling completed, checked and Supervisor sign off
ff4836ad-1bbe-421f-93e2-0fd158baf543 | checkpoint | Silicone is completed to all tile junctions where required
5d9945e8-22cd-450f-a0d1-b608edb3685c | checkpoint | Area left clean & tidy
2a975c2a-fdde-4567-9ecf-96ef395bfabf | checkpoint | Builders clean completed
a46c7f72-714d-4558-90dd-9fd5b8feabb8 | checklist | QA - Tiling Installation WC |  | QA - Tiling Installation WC
7bbadf5a-e997-4314-ad7c-f61a238cbe38 | section | Tiling bathroom floor and walls
6a57dda2-8173-4f50-a6ea-d39a62ac0472 | checkpoint | Tiles set out according to latest drawing - always check revisions on site
a941f925-63e2-4cd6-b956-59d90a8cf1de | checkpoint | Specified product used with notched trowel or required product
42598c76-909d-4228-90da-81f320cb456d | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
b8dc0cd2-c78f-4f8f-9491-187df4bf3a7f | checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
f8b4d2a5-8011-4eff-8d55-b479677ea037 | checkpoint | Install tiles to floor
a6e2fd25-1290-463b-a986-7f91d13e3372 | checkpoint | Wall tiles set out to match floor grout lines or as per drawings install tiles to walls in ACC WC
e3b5895a-6a30-45ff-ae15-f4fc26d38a44 | checkpoint | Install WF13 tiles to walls as per elevations - 00-121 & 00-122
590c45fc-cd27-4c9c-9dc7-0f4e12323ee8 | checkpoint | Install WF14 mosaic tiles to walls as per elevation B - 00-121 & C - 00-122 to doors
1153eeb2-c000-4c32-b98b-8ba7b6da6b95 | checkpoint | Install skirting tile 100mm high to all walls outside of the toilets in wc's. Includes matt L-Angle trim
c38305d4-e625-42cd-a330-87658c5cfe2f | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
ab70d3e3-3e4d-4092-93b6-6e8fe04823e0 | checkpoint | Grout is consistent throughout and no missing grout.
5d14379c-9b8a-45d1-bab3-26b8618e2d20 | checkpoint | Tiling completed, checked and Supervisor sign off
d72cb413-8218-4adb-a491-57950abdae70 | checkpoint | Silicone is completed to all tile junctions where required
62acd42b-470d-4066-9317-7d7dae5b573e | checkpoint | Area left clean & tidy
8a4189fe-5650-41db-825e-466b85ff4977 | checkpoint | Builders clean completed
5f0202c9-20b7-4516-ac2c-09330ee1a186 | checklist | QA - Waterproofing |  | QA - Waterproofing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c9fdd8ac-fd0a-4388-9050-0a5b0e364e5a | checkpoint | Waterproof materials applied to floor perimeter and gaskets to flanges
dd51bb71-2599-4510-919f-37b1f7510e75 | checkpoint | Waterproofing coat # 1 applied to floors and walls (take photos)
b61cdb2b-e6e7-4a4c-a519-c592917c10d2 | checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos)
1ae55ba9-edbf-4bcc-89f1-e0572a0303d8 | checkpoint | Flood tests, if required, undertaken and photos provided.