## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
1b0cb8a8-3c69-4a6c-a750-5902c9c89404 | checklist | Final Sign Off for Invoicing |  | Final Sign Off for Invoicing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
c92b4a3b-5a8b-49e7-ae7b-f072edfef879 | checkpoint | No items are left on fail. If so, provide reasons why before invoiced out.
fd58b220-9e4c-4fbd-b4a9-24d02d091bd5 | checklist | Floor Preparation |  | Floor Preparation
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
6cb9265a-f53f-458c-b30e-1b9db803f954 | checkpoint | Is the area clean, and cleared, ready for necessary preparation
cf9f79e2-5162-4722-8f5c-dcda51c2b3c6 | checkpoint | Light grind to kitchen area floor and patch infill
741413d7-c27d-43d7-82ef-aa1c990ae80d | checkpoint | Floor levelling completed and applied as per requirements. (m2 rate)
291070b4-b51c-40c3-af50-a0ca42385cee | checkpoint | Floor levelling completed - hours and bags used to be recorded (if per bag/labour rate)
6abfe641-9fde-4661-8e50-f166890b122b | checklist | Floor Preparation WC |  | Floor Preparation WC
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
98bd5f59-4f8b-426b-b991-514799af3a07 | checkpoint | Is the area clean, and cleared, ready for necessary preparation
e9395c5a-55bf-410c-a7f3-8f1fb30e1062 | checkpoint | Floor levelling completed and applied as per requirements. (m2 rate)
d8fed6da-2119-4da7-8698-68de9d217589 | checkpoint | Floor levelling completed - hours and bags used to be recorded (if per bag/labour rate)
4b1d4bc7-69ae-4736-a1a1-44fb2515d12b | checklist | Prestart Inspections |  | Prestart Inspections
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
0a58f5bb-6383-41ae-8a16-4a077573906f | checkpoint | site has been cleaned in advance of our arrival on site
6e8c2786-0eb2-4a5e-81c0-b12fe6500158 | checkpoint | Walls are plumb and level
a54aa6b5-96e2-5c85-a292-f100b0389ca2 | note | IMPORTANT
258929d2-be0b-4fbd-bb1b-bb6f4e83c75a | checkpoint | Tiling works running to programme - prior trades completed
9ead0231-6523-48b2-92d1-2e019b21973f | checkpoint | Gib compound and sanding cleaned up from rooms (prior to any works)
3843e081-d399-4fa5-a513-d5b02b2ca53d | checkpoint | Task Analysis signed onto by tilers and provided to main contractor (PHOTO REQUIRED)
f45c6a8a-99a3-4d2c-876b-c7c3ec8b4ab1 | checkpoint | Data sheets, of products, are supplied on site with TA's
5a188c23-d716-4ae5-9f03-f359212b9fc4 | checkpoint | Inductions completed & Site Inspection checklist has been completed
8d66363d-54a7-4760-883d-128182865142 | checkpoint | All tools tagged and tested - (photo's required)
c4f088ab-f0d8-4040-a6db-c9b1b0b030a0 | checkpoint | Tiler has current site safe - Input number and expiry
37846326-04af-486b-863a-108e38b8324c | checkpoint | Tiler has correct PPE relevant to project.
10b7c630-0078-4561-b311-f9cfd3381bb2 | checkpoint | Correct drawings being utilised by TAL Tiling. (Check on site for latest revision)
36ffb243-c468-411d-8ab0-7a0c398fd8dc | checklist | QA - Tiling Installation - WC |  | QA - Tiling Installation - WC
1a88762c-5183-4af4-8ff7-b02167c8ed93 | section | Tiling to floors and walls
31082cb1-ddf3-47f6-9b5b-4592b744fb89 | checkpoint | Tiles set out according to latest drawing - always check revisions on site
3c9205e0-a5ca-4b2c-a3da-1e8a32368c9b | checkpoint | Specified product used with notched trowel or required product
16c83fcb-812a-447a-8fbe-e698dc931b80 | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
ed4118d1-c869-4485-be73-826694718c21 | checkpoint | Floor/Wall substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
f9049cf4-4aec-48a9-8b6f-3ef9b6adcb3b | checkpoint | Install 600x600 tiles to floors as per drawings
021d9544-5d8e-4e6f-9d97-333910bbb797 | checkpoint | Wall tiles set out to match floor grout lines or as per drawings. (Provide explanation if changed)
6a193f6a-429f-4e0f-93af-6603627e0c0d | checkpoint | Install small format tiles to walls as per drawings
801b9587-7d91-4e97-a7d0-3f6225094b64 | checkpoint | Install 100mm high skirting to perimeter
b7762454-fa0f-42ad-be67-3fd4e3a0a085 | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
7530d1d0-e9a6-4851-8023-be11a5cb7759 | checkpoint | Grout is consistent throughout and no missing grout.
2a2ccf29-fce8-47d4-8687-87667621da0b | checkpoint | Tiling completed, checked and Supervisor sign off
798dd7f2-636b-49ce-84f3-af1798786902 | checkpoint | Silicone is completed to all tile junctions where required
a3111360-0aef-431f-9d24-d0debd4e4fcb | checkpoint | Area left clean & tidy
c1b297b9-2286-4f9a-82a4-a55e8defce46 | checkpoint | Builders clean completed
d8d4fd96-1377-4d02-8330-3b6ac3caab9e | checklist | QA - Waterproofing |  | QA - Waterproofing
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
9dc8f838-ca46-443a-b112-d521664c4719 | checkpoint | Substrate to receive waterproofing has slimline installed to any corners and has been gib stopped
d5644515-899d-4009-9ecd-93f421a80be6 | checkpoint | Correct waterproofing is supplied as per project specification.
553d26f3-f601-42b3-a521-738afb359c70 | checkpoint | Waterproofing coat # 1 applied to floors, upstand and walls (take photos)
962ecd8a-f16a-4c17-b963-5efffdf45500 | checkpoint | Waterproofing coat # 2 applied 90 degrees to 1st coat (take photos)
24135357-51c3-40ff-ab38-479dcac7af6b | checkpoint | Flood tests, if required, undertaken and photos provided.
e47d8a51-6e25-43e2-857a-af2b03855868 | checklist | QA-Other Information |  | QA-Other Information
13103e6b-0841-410e-b1a3-5bcf8e79c89a | section | Other Information
0697d6a2-ecc5-4ce7-8ce9-5906e2821732 | checkpoint | Variations or extra works added into folder - all works and materials noted. Use ISSUES tab.
9e01b578-7a0b-476d-bbdf-f28f269b8a1e | checkpoint | change of details and or instructions
7a588113-e289-44d3-bdfb-cd1b9b89a608 | checkpoint | Site specific details to be added
0a918454-05d5-47a5-993a-bc85843ea4e3 | checkpoint | Material Details - Notes to be added of materials used on site
decd81ce-6fa9-4853-9b61-eef87a09ec11 | checklist | Tiling Installation Floor |  | Tiling Installation Floor
a8e6966f-61e2-46ec-9b37-837800c67f32 | section | Tiling to floors
1b780a7e-35a3-4575-9b7f-004b02830f34 | checkpoint | Tiles set out according to latest drawing - always check revisions on site
0b8ec938-faed-4a53-864e-ab615736355b | checkpoint | Specified product used with notched trowel or required product
2e5b527d-d771-4275-84c0-b08bf3992e5c | checkpoint | Correct spacer size used for spacing as per specs and tile lipping within BRANZ tolerances
63822c22-83f2-4f75-8c2c-554ae85c2db2 | checkpoint | Floor substrate straight, signed off by MC, and ready for installation. (insert notes for remediation if required)
7483d729-9665-4d79-aed5-82513cceeb13 | checkpoint | Install 600x600 tiles to floors as per drawings
e4b30637-1fd6-4724-be32-1dbe58a3d0cb | checkpoint | Grout nominated is the correct colour and applied evenly and correctly
fbd55bdd-7ce8-4ac9-ad1c-f43a05520f42 | checkpoint | Grout is consistent throughout and no missing grout.
22540f65-67d1-4a30-9f02-cbe5dfb7c41a | checkpoint | Tiling completed, checked and Supervisor sign off
2c0dc959-194d-432f-b59e-b725228284af | checkpoint | Silicone is completed to all tile junctions where required
4f850782-a921-4a4d-80da-003c4b914755 | checkpoint | Area left clean & tidy
24cbef14-b460-4516-9831-8cba5823dba4 | checkpoint | Builders clean completed